## Abs. - L&T
APPLICATION FOR INTERIM PAYMENT
ABSTRACT SHEET
Interim Payment Application No. : |  | IPA - 34 |  |  | Bill date : | 2026-09-20
Type of Work : |  | Main Works & Price Adjustment
Period of bill : |  | 1st Jul'26 to 31st Jul'26
EPC Contractor : |  | Larsen and Toubro Limited
Address: |  | L&T Construction, Majirgaon Palashbari - Sualkuchi Bridge Project, Dag No. 268 & 269, Patta No. 43 & 168, Revenue Village - Santala, Revenue Circle - Palashbari, Kamrup District, Assam - 781125.
Employer : |  | The Chief Engineer (EAP), Public Works Roads Department (PWRD), Assam
Employer's Representative : |  | Rodic Consultants Private Limited in JV with Intercontinental Consultants and Technocrats Private Limited
LOA Ref. No. : |  | CE/EAP/ABP-II/EPC/OCB/2023/35 |  |  | Contract Value (INR) : | 26885400000
Work Order No : |  | Contract Agreement signed on 01-Mar-24 |  |  | Financial Progress: | 75.76%
Name of Work : |  | Construction of 4-lane Extradosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
S.No. | Description |  | Currency | Amount
|  |  |  | Cumulative Bill | Up to Previous Bill | This Bill
A | Work Done
a | Amount for the works executed under Sub-Clause 14.3 of the General Conditions |  | ₹ | 17226390633.8983 | 11013075548.3051 | 6213315085.5932
b | Amount for the Provisional Sum under Sub-Clause 13.4 of the General Conditions |  | ₹ | 1369786.4407 | 1369786.4407 | 0
c | Amount reflecting Changes in Cost under Sub-Clause 13.7 of the General Conditions |  | ₹ | 316689070.339 | 60193166.9492 | 256495903.3898
d | Amount of Variation Order executed under Sub-Clause 13.3 of the General Conditions |  | ₹ | 0 | 0 | 0
e | Amount reflecting Change in Law under Sub-Clause 13.6 of the General Conditions |  | ₹ | 0 | 0 | 0
f1 | CGST @ 9% on [Aa to Ae] |  | ₹ | 1579000454.161 | 996717465.1525 | 582282989
f2 | SGST @ 9% on [Aa to Ae] |  | ₹ | 1579000454.161 | 996717465.1525 | 582282989
| Total Work Done (A) = (Aa+Ab+Ac+Ad+Ae+Af1+Af2) |  | ₹ | 20702450399 | 13068073432 | 7634376966.9831
| Total Work Done (Excl. of taxes) (A1) = (A/1.18) |  | ₹ | 17544449490.678 | 11074638501.6949 | 6469810988.9687
B | Advances
a | Mobilization Advance under Sub-Clause 14.2 of General Condidtions - 1st Installment |  | ₹ | 1139211864.4068 | 1139211864.4068 | 0
b | Mobilization Advance under Sub-Clause 14.2 of General Condidtions - 2nd Installment |  | ₹ | 1139211864.4068 | 1139211864.4068 | 0
c1 | CGST @ 9% on [Ba to Bb] |  | ₹ | 205058135.5932 | 205058135.5932 | 0
c2 | SGST @ 9% on [Ba to Bb] |  | ₹ | 205058136 | 205058135.5932 | 0
| Total Advances (B) = (Ba+Bb+Bc1+Bc2) |  | ₹ | 2688540000.4068 | 2688540000 | 0
| Gross Amount (Incl. Advances) (B1) = (A+B) |  | ₹ | 23390990399.4068 | 15756613432 | 7634376966.9831
| Gross Amount (Excl. Taxes) (B2) = (B1/1.18) |  | ₹ | 19822873220 | 13353062231 | 6469810989
C | Recoveries
a | Mobilization Advance under Sub-Clause 14.2 of General Condidtions @ 15% on [A1] |  | ₹ | 2584164063.0508 | 1652166800.2119 | 931997262.839
b1 | CGST @ 9% on [Ca] |  | ₹ | 232574765.6746 | 148695012.0191 | 83879753.6555
b2 | SGST @ 9% on [Ca] |  | ₹ | 232574765.6746 | 148695012.0191 | 83879753.6555
| Total Recoveries (C) = (Ca+Cb1+Cb2) |  | ₹ | 3049313594.4 | 1949556824.25 | 1099756770.15
D | Withheld / Release
a | Retention Amount @ 6% upto 5% of Contract Value on [A] |  | ₹ | 1242147023.939 | 784084405.92 | 458062618.019
b | Release of Retention Amount |  | ₹ | -605998256 | -605998256 | 0
c | Withhled Amount |  | ₹ | 497964247 | 497964247 | 0
d | Release of Withheld Amount |  | ₹ | -497964247 | -497964247 | 0
e | Adjustment in Forest Royalty payments by the Contractor |  | ₹ | -137739041.32 | -127312122.4938 | -10426918.8262
| Total Withhled / Release (D) = (Da+Db+Dc+Dd+De) |  | ₹ | 498409726.619 | 50774027.4262 | 447635699.1928
| Taxable Amount (D1) = ((A+B-C)/1.18) |  | ₹ | 17238709156.7854 | 11700895430.2966 | 5537813726.1297
E | Deductions
a | Income Tax @ 2% on [D1/(1.01*1.02)] |  | ₹ | 334667232.7079 | 234017909 | 100649323.7079
b | Forest Royalty @ 2% on [(Aa+Ab)/1.02] |  | ₹ | 337799224 | 215969516 | 121829708
c | Income tax @ 2.5% on Forest Royalty [Eb] |  | ₹ | 8444981 | 5399238 | 3045743
d | Mines and Mineral Development, Restoration and Rehabilitation Fund @ 10% on [Eb] |  | ₹ | 33779922 | 21596952 | 12182970
e | District Foundation Fund Trust @ 10% on [Eb] |  | ₹ | 33779922 | 21596952 | 12182970
f | State Mineral Exploration Trust @ 2% on [Eb] |  | ₹ | 2606924.56 | 170330.4 | 2436594.16
g | CGST - TDS @ 1% on [D1] |  | ₹ | 172387092 | 117008954 | 55378138
h | SGST - TDS @ 1% on [D1] |  | ₹ | 172387092 | 117008954 | 55378138
i | Labour Cess @ 1% on [A1/1.01] |  | ₹ | 173707421 | 130680736 | 43026685
| Total Deductions (E) = (Ea+Eb+Ec+Ed+Ee+Ef+Eg+Eh+Ei) |  | ₹ | 1269559811.2679 | 863449541.4 | 406110269.8679
|  | Amount Payable (F) = (A+B-C-D-E) | ₹ | 18573707267 | 12892833039 | 5680874228
Amount Payable (In Words) - |  | Rupees Sixty Eight Crores Eight Lakhs Seventy Four Thousand Two Hundred and Twenty Eight Only
Sixty Eight Crores
Eight Lakhs
Seventy Four Thousand
Two Hundred and Twenty Eight
Rupees Sixty Eight Crores Eight Lakhs Seventy Four Thousand Two Hundred and Twenty Eight Only

## Abs. - PMC (hidden)
INTERIM PAYMENT CERTIFICATION
ABSTRACT SHEET
Interim Payment Certificate No. : |  | IPC - 15 |  |  | Bill date : | 2025-05-22
Type of Work : |  | Main Works and Price Adjustment
Period of bill : |  | 1st Jul'26 to 31st Jul'26
EPC Contractor : |  | Larsen and Toubro Limited
Address: |  | L&T Construction, Majirgaon Palashbari - Sualkuchi Bridge Project, Dag No. 268 & 269, Patta No. 43 & 168, Revenue Village - Santala, Revenue Circle - Palashbari, Kamrup District, Assam - 781125.
Employer : |  | The Chief Engineer (EAP), Public Works Roads Department (PWRD), Assam
Employer's Representative : |  | Rodic Consultants Private Limited in JV with Intercontinental Consultants and Technocrats Private Limited
LOA Ref. No. : |  | CE/EAP/ABP-II/EPC/OCB/2023/35 |  |  | Contract Value (INR) : | 26885400000
Work Order No : |  | Contract Agreement signed on 01-Mar-24 |  |  | Financial Progress: | 75.61%
Name of Work : |  | Construction of 4-lane Extradosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
S.No. | Description |  | Currency | Amount
|  |  |  | Cumulative Bill | Up to Previous Bill | This Bill
A | Work Done
a | Amount for the works executed under Sub-Clause 14.3 of the General Conditions |  | ₹ | 20327140948 | 12995429147 | 7331711801
b | Amount for the Provisional Sum under Sub-Clause 13.4 of the General Conditions |  | ₹ | 1616348 | 1616348 | 0
c | Amount reflecting Changes in Cost under Sub-Clause 13.7 of the General Conditions |  | ₹ | 373693103 | 71027937 | 302665166
d | Amount of Variation Order executed under Sub-Clause 13.3 of the General Conditions |  | ₹ | 0 | 0 | 0
e | Amount reflecting Change in Law under Sub-Clause 13.6 of the General Conditions |  | ₹ | 0 | 0 | 0
| Total Work Done (A) = (Aa+Ab+Ac+Ad+Ae) |  | ₹ | 20702450399 | 13068073432 | 7634376967
| Total Work Done (Excl. of Taxes) (A1) = (A/1.18) |  | ₹ | 17544449490.678 | 11074638501.6949 | 6469810988.9831
B | Advances
a | Mobilization Advance under Sub-Clause 14.2 of General Condidtions - 1st Installment |  | ₹ | 2688540000 | 2688540000 | 0
b | Mobilization Advance under Sub-Clause 14.2 of General Condidtions - 2nd Installment |  | ₹ | 0 | 0 | 0
| Total Advances (B) = (Ba+Bb) |  | ₹ | 2688540000 | 2688540000 | 0
| Gross Amount due including Advances (B1) = (A+B) |  | ₹ | 23390990399 | 15756613432 | 7634376967
| Gross Amount (Excl. of Taxes) (B2) = (B1/1.18) |  | ₹ | 19822873219.4915 | 13353062230.5085 | 6469810988.9831
C | Recoveries
a | Mobilization Advance under Sub-Clause 14.2 of General Condidtions @ 15% on [A] |  | ₹ | 3105367559.85 | 1960211014.8 | 1145156545.05
b | Retention Amount @ 6% upto 5% of Contract Value on [A] |  | ₹ | 1242147023.94 | 784084405.92 | 458062618.02
| Total Recoveries (C) = (Ca+Cb) |  | ₹ | 4347514583.79 | 2744295420.72 | 1603219163.07
| Amount due before Taxes (C1) = (B1-C) |  | ₹ | 19043475815.21 | 13012318011.28 | 6031157803.93
D | Withheld
a | Withheld Amount |  | ₹ | 0 | 0 | 0
b | Release of Withheld Amount |  | ₹ | 0 | 0 | 0
| Total Advances (D) = (Da+Db) |  | ₹ | 0 | 0 | 0
| Taxable Amount (D1) = ((A-Ca)/1.18) |  | ₹ | 14912782067.0763 | 9413442726.4407 | 5499339340.6356
E | Deductions
a | Income tax @ 2% on [(B+(A-Ca))/1.18] |  | ₹ | 343824115.9178 | 64838315 | 278985800.9178
b | Forest Royalty @ 2% on [A/1.18/1.02] |  | ₹ | 344008813.5427 | 22225883 | 321782930.5427
c | Income tax @ 2.5% on Forest Royalty [Eb] |  | ₹ | 8600220.3386 | 449089 | 8151131.3386
d | Mines and Mineral Development, Restoration and Rehabilitation Fund @ 10% on [Eb] |  | ₹ | 34400881.3543 | 1796354 | 32604527.3543
e | District Foundation Fund Trust @ 10% on [Eb] |  | ₹ | 34400881.3543 | 1796354 | 32604527.3543
f | CGST @ 1% on [(B+(A-Ca))/1.18] |  | ₹ | 171912057.9589 | 19179316 | 152732741.9589
g | SGST @ 1% on [(B+(A-Ca))/1.18] |  | ₹ | 171912057.9589 | 19179316 | 152732741.9589
h | Labour Cess @1% on [A1] |  | ₹ | 175444494.9068 | 10810459 | 164634035.9068
| Total Deductions (E) = (Ea+Eb+Ec+Ed+Ee+Ef+Eg+Eh) |  | ₹ | 1284503523.3322 | 140275086 | 1144228437.3322
|  | Amount Payable (F) = (C1-D-E) | ₹ | 17758972291.8778 | 12872042925.28 | 4886929366.5978
Amount Payable (In Words) - Rupees Sixteen Crores Forty Lakhs Eight Thousand Three Hundred and Fourteen Only

## Abs. - PMC (For Print)
INTERIM PAYMENT CERTIFICATION
ABSTRACT SHEET
Interim Payment Certificate No. : |  | IPC - 34 |  |  | Bill date : | 2026-09-20
Type of Work : |  | Main Works & Price Adjustment
Period of bill : |  | 1st Jul'26 to 31st Jul'26
EPC Contractor : |  | Larsen and Toubro Limited
Address: |  | L&T Construction, Majirgaon Palashbari - Sualkuchi Bridge Project, Dag No. 268 & 269, Patta No. 43 & 168, Revenue Village - Santala, Revenue Circle - Palashbari, Kamrup District, Assam - 781125.
Employer : |  | The Chief Engineer (EAP), Public Works Roads Department (PWRD), Assam
Employer's Representative : |  | Rodic Consultants Private Limited in JV with Intercontinental Consultants and Technocrats Private Limited
LOA Ref. No. : |  | CE/EAP/ABP-II/EPC/OCB/2023/35 |  |  | Contract Value (INR) : | 26885400000
Work Order No : |  | Contract Agreement signed on 01-Mar-24 |  |  | Financial Progress: | 75.76%
Name of Work : |  | Construction of 4-lane Extradosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
S.No. | Description |  | Currency | Amount
|  |  |  | Cumulative Bill | Up to Previous Bill | This Bill
A | Work Done
a | Amount for the works executed under Sub-Clause 14.3 of the General Conditions |  | ₹ | 20327140948 | 12995429147 | 7331711801
b | Amount for the Provisional Sum under Sub-Clause 13.4 of the General Conditions |  | ₹ | 1616348 | 1616348 | 0
c | Amount reflecting Changes in Cost under Sub-Clause 13.7 of the General Conditions |  | ₹ | 373693103 | 71027937 | 302665166
d | Amount of Variation Order executed under Sub-Clause 13.3 of the General Conditions |  | ₹ | 0 | 0 | 0
e | Amount reflecting Change in Law under Sub-Clause 13.6 of the General Conditions |  | ₹ | 0 | 0 | 0
| Total Work Done (A) = (Aa+Ab+Ac+Ad+Ae) |  | ₹ | 20702450399 | 13068073432 | 7634376967
B | Advances / Recovery
a | Mobilization Advance under Sub-Clause 14.2 of General Conditions - 1st Installment |  | ₹ | 1344270000 | 1344270000 | 0
b | Mobilization Advance under Sub-Clause 14.2 of General Conditions - 2nd Installment |  | ₹ | 1344270000 | 1344270000 | 0
c | Recovery of Mob. Advance under Sub-Clause 14.2 of GC @ 15% on [Aa+Ab] |  | ₹ | 3049313594 | 1949556824 | 1099756770
| Total Advances (B) = (Ba+Bb-Bc) |  | ₹ | -360773594 | 738983176 | -1099756770
| Gross Amount due including Advances (B1) = (A+B) |  | ₹ | 20341676805 | 13807056608 | 6534620197
| Taxable Amount (B2) = ((A+B)/1.18) |  | ₹ | 17238709157 | 11700895431 | 5537813726
C | Recovery / Release
a | Recovery of Retention Amount @ 6% upto 5% of Contract Value on [A] |  | ₹ | 1242147024 | 784084406 | 458062618
b | Release of Retention Amount against Bank Guarantee |  | ₹ | -605998256 | -605998256 | 0
| Total Recovery (C) = (Ca+Cb) |  | ₹ | 636148768 | 178086150 | 458062618
| Amount due before Taxes (C1) = (B1-C) |  | ₹ | 19705528037 | 13628970458 | 6076557579
D | Withheld / Release
a | Withheld Amount |  | ₹ | 497964247 | 497964247 | 0
b | Release of Withhled Amount |  | ₹ | -497964247 | -497964247 | 0
| Total Withheld (D) = (Da+Db) |  | ₹ | 0 | 0 | 0
| Amount due before Taxes after withheld (D1) = (C1-D) |  | ₹ | 19705528037 | 13628970458 | 6076557579
E | Deductions
a | TDS - Income tax @ 2% on [B2] |  | ₹ |  |  |  | 344774183 | 227561965 | 110756275 | 338318240 | 227561965 | 110756275
b | Forest Royalty @ 2% on [(Aa+Ab)/1.18/1.02] |  | ₹ |  |  |  | 232012489.8468 | 104591554 | 127420935.8468 | 224621346.3406 | 104591554 | 120029792.3406 | 7391143.5062 | 105786734.0814 | 337799223.9282
c | TCS - Income tax @ 2.5% on Forest Royalty [Eb] |  | ₹ |  |  |  | 8444980.5982 | 5247793 | 3197187.5982 | 8444980.5982 | 5247793 | 3197187.5982 |  | 281240.327 | 8726220.9252
d | Mines and Mineral Development, Restoration and Rehabilitation Fund @ 10% on [Eb] |  | ₹ |  |  |  | 23206613.3501 | 10459157 | 12747456.3501 | 22462136 | 10459157 | 12002979 |  | 10573309.0427 | 33779922.3928
e | District Foundation Fund Trust @ 10% on [Eb] |  | ₹ |  |  |  | 23206613.3501 | 10459157 | 12747456.3501 | 22462136 | 10459157 | 12002979 |  | 10573309.0427 | 33779922.3928
f | State Mineral Exploration Trust @ 2% on [Eb] |  | ₹ |  |  |  | 2625233.1323 | 97530 | 2527703.1323 | 2498126 | 97530 | 2400596 |  | 97530 | 2722763.1323
g | TDS - CGST @ 1% on [B2] |  | ₹ |  |  |  | 169159119 | 113780982 | 55378137 | 169159119 | 113780982 | 55378137
h | TDS - SGST @ 1% on [B2] |  | ₹ |  |  |  | 169159119 | 113780982 | 55378137 | 169159119 | 113780982 | 55378137 |  | 10578673.4081
i | Labour Cess @1% on [A] |  | ₹ |  |  |  | 202668665 | 126324895 | 76343770 | 202668665 | 126324895 | 76343770 |  | 10578673.4081
| Total Deductions (E) = (Ea+Eb+Ec+Ed+Ee+Ef+Eg+Eh+Ei) |  | ₹ |  |  |  | 1175257016.2776 | 712304015 | 456497058.2776 | 1159793867.9388 | 712304015 | 447489852.9388
|  | Amount Payable (F) = (C1-D-E) | ₹ |  |  |  | 18530271020.7224 | 12916666443 | 5620060520.7224 | 18545734169.0612 | 12916666443 | 5629067726.0612
Amount Payable (In Words) -
[10 empty] | 338318240 | 227561965 | 110756275
[10 empty] | 225721262 | 104591554 | 121129708
[10 empty] | 8293535.7 | 5247793 | 3045742.7
[10 empty] | 22572128 | 10459157 | 12112971
[10 empty] | 22572128 | 10459157 | 12112971
[10 empty] | 2520124 | 97530 | 2422594
[10 empty] | 169159119.26 | 113780982 | 55378137.26
[10 empty] | 169159119.26 | 113780982 | 55378137.26
[10 empty] | 202668664.67 | 126324895 | 76343769.67
[10 empty] | 1160984320.89 | 712304015 | 448680305.89
[10 empty] | 18544543716.11 | 12916666443 | 5627877273.11

## Breakup-Summary
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
General Conditions of Contract - Clause 14.4 - Summary - Schedule of Payments
Schedule No | Description | Schedule Cost (% of the Contract Price) |  | Cumulative Bill |  | Up to Previous Bill |  | This Bill (INR)
|  | Weightage % | Amount (INR) | Weightage % | Amount (Rs.) | Weightage % | Amount (Rs.) | Weightage % | Amount (Rs.)
Schedule 1 | Preliminaries & General Items | 2.5% | 670750000 | 1.911% | 512717121 | 1.911% | 512717121 | 0% | 0
Schedule 2 | Validation of Survey Data, Investigation, Design and As-Built Drawings | 3% | 804900000 | 2.728% | 731800089 | 2.724% | 730975066 | 0.003075% | 825023
Schedule 3 | Enabling Works for Main Works | 4.5% | 1207350000 | 4.149% | 1113176703 | 4.149% | 1113176703 | 0% | 0
Schedule 4 | Main Extradosed Bridge Works | 67% | 17976100000 | 53.04% | 14231152805 | 26.08% | 6996789931 | 26.96% | 7234362874
Schedule 5 | Wetland and Approach Viaduct Works | 14.5% | 3890350000 | 10.91% | 2928149367 | 10.57% | 2834648310 | 0.3485% | 93501057
Schedule 6 | Underpass Works | 2.5% | 670750000 | 2.21% | 593050320 | 2.21% | 593050320 | 0% | 0
Schedule 7 | Approach road Works | 6% | 1609800000 | 0.8091% | 217094543 | 0.7979% | 214071696 | 0.01127% | 3022847
Schedule 8 | Provisional Sum |  | 55400000 |  | 1616348 |  | 1616348 |  | 0
| Total | 100% | 26885400000 | 75.76% | 20328757296 | 48.44% | 12997045495 | 27.33% | 7331711801 | 339313902 | 6992397899
5.54
5352149614.73
7392224
11700000
5371241838.73
PL1 - Piercap - WV1
PL2 - Piercap - WV1
PR3 - Piercap - WV1
PR1 - Piercap - WV1
PL3 - Piercap - WV1
PR2 - Piercap - WV1
PL0 - Piercap - WV1
PR0 - Piercap - WV1

## Detailed breakup
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
General Conditions of Contract - Clause 14.4 - Schedule of Payments
[13 empty] | Period of bill : |  | 1st Jul'26 to 31st Jul'26
Schedule No | Description | Schedule Cost (% of the Contract Price) |  | Item No | Item Description | UOM | Percentage | Tentative Scope | Amount (INR) | Amount payable per Unit (INR) | Cumulative Bill |  | Upto Previous Bill |  | This Bill |  |  | Measurement Book
|  | Weightage % | Amount (INR) | [7 empty] | Quantity | Amount (INR) | Quantity | Amount (INR) | Quantity | Amount (INR) |  | Page | No
Schedule 1 | Preliminaries & General Items | 2.5% | 670750000 | 101 | Provision (construction) of office facilities for the Employer | LS | 30.5% |  | 204578750
|  |  |  | a | Completion of Foundation | Nos. | 20% | 2 | 40915750 | 20457875 | 2 | 40915750 | 2 | 40915750 | 0 | 0 | 0
|  |  |  | b | Completion of Plinth | Nos. | 18% | 2 | 36824175 | 18412087.5 | 2 | 36824175 | 2 | 36824175 | 0 | 0 | 0
|  |  |  | c | Completion of Walls | Nos. | 15% | 2 | 30686812.5 | 15343406.25 | 2 | 30686813 | 2 | 30686813 | 0 | 0 | 0
|  |  |  | d | Completion of Roofs | Nos. | 15% | 2 | 30686812.5 | 15343406.25 | 2 | 30686813 | 2 | 30686813 | 0 | 0 | 0
|  |  |  | e | Completion of Flooring | Nos. | 18% | 2 | 36824175 | 18412087.5 | 2 | 36824175 | 2 | 36824175 | 0 | 0 | 0
|  |  |  | f | Completion of Finishing Works | [11 empty] | 0
|  |  |  | i | Electrical and Sanitary Works | Nos. | 10% | 2 | 20457875 | 10228937.5 | 2 | 20457875 | 2 | 20457875 | 0 | 0 | 0
|  |  |  | ii | Office Furniture | [11 empty] | 0
|  |  |  | 1 | Executive Office Desk | Nos. | 0.25% | 8 | 511446.875 | 63930.8594 | 8 | 511447 | 8 | 511447 | 0 | 0 | 0
|  |  |  | 2 | Executive Chairs | Nos. | 0.25% | 8 | 511446.875 | 63930.8594 | 8 | 511447 | 8 | 511447 | 0 | 0 | 0
|  |  |  | 3 | Visitor Chairs | Nos. | 0.15% | 20 | 306868.125 | 15343.4062 | 20 | 306868 | 20 | 306868 | 0 | 0 | 0
|  |  |  | 4 | Conference Table | Nos. | 0.5% | 2 | 1022893.75 | 511446.875 | 2 | 1022894 | 2 | 1022894 | 0 | 0 | 0
|  |  |  | 5 | Conference Chairs | Nos. | 0.5% | 60 | 1022893.75 | 17048.2292 | 60 | 1022894 | 60 | 1022894 | 0 | 0 | 0
|  |  |  | 6 | Projector and Monitor in Conference room | Nos. | 0.3% | 1 | 613736.25 | 613736.25 | 1 | 613736 | 1 | 613736 | 0 | 0 | 0
|  |  |  | 7 | Display Arrangement | Nos. | 0.1% | 2 | 204578.75 | 102289.375 | 2 | 204579 | 2 | 204579 | 0 | 0 | 0
|  |  |  | 8 | Steel Almirah and Racks | Nos. | 0.2% | 10 | 409157.5 | 40915.75 | 10 | 409158 | 10 | 409158 | 0 | 0 | 0
|  |  |  | 9 | Domestic Water Purifier | Nos. | 0.25% | 2 | 511446.875 | 255723.4375 | 2 | 511447 | 2 | 511447 | 0 | 0 | 0
|  |  |  | iii | Office Equipment | [11 empty] | 0
|  |  |  | 1 | Laptops | Nos. | 1% | 6 | 2045787.5 | 340964.5833 | 6 | 2045788 | 6 | 2045788 | 0 | 0 | 0
|  |  |  | 2 | Colour Printer | Nos. | 0.5% | 2 | 1022893.75 | 511446.875 | 2 | 1022894 | 2 | 1022894 | 0 | 0 | 0
|  |  |  | 102 | Provision (construction) of contractor’s site office, site laboratories, labor camps etc | LS | 27.9% |  | 187139250 | [7 empty] | 0
|  |  |  | a | Completion of Foundation | [11 empty] | 0
|  |  |  | i | Office | Nos. | 10% | 1 | 18713925 | 18713925 | 1 | 18713925 | 1 | 18713925 | 0 | 0 | 0
|  |  |  | ii | Laboratory | Nos. | 4% | 2 | 7485570 | 3742785 | 2 | 7485570 | 2 | 7485570 | 0 | 0 | 0
|  |  |  | iii | Labour Camps | [11 empty] | 0
|  |  |  | 1 | Building | Nos. | 2% | 2 | 3742785 | 1871392.5 | 2 | 3742785 | 2 | 3742785 | 0 | 0 | 0
|  |  |  | 2 | Kitchen | Nos. | 1% | 2 | 1871392.5 | 935696.25 | 2 | 1871393 | 2 | 1871393 | 0 | 0 | 0
|  |  |  | b | Completion of Plinth | [11 empty] | 0
|  |  |  | i | Office | Nos. | 10% | 1 | 18713925 | 18713925 | 1 | 18713925 | 1 | 18713925 | 0 | 0 | 0
|  |  |  | ii | Laboratory | Nos. | 4% | 2 | 7485570 | 3742785 | 2 | 7485570 | 2 | 7485570 | 0 | 0 | 0
|  |  |  | iii | Labour Camps | [11 empty] | 0
|  |  |  | 1 | Building | Nos. | 2% | 2 | 3742785 | 1871392.5 | 2 | 3742785 | 2 | 3742785 | 0 | 0 | 0
|  |  |  | 2 | Kitchen | Nos. | 1% | 2 | 1871392.5 | 935696.25 | 2 | 1871393 | 2 | 1871393 | 0 | 0 | 0
|  |  |  | c | Completion of Walls | [11 empty] | 0
|  |  |  | i | Office | Nos. | 10% | 1 | 18713925 | 18713925 | 1 | 18713925 | 1 | 18713925 | 0 | 0 | 0
|  |  |  | ii | Laboratory | Nos. | 4% | 2 | 7485570 | 3742785 | 2 | 7485570 | 2 | 7485570 | 0 | 0 | 0
|  |  |  | iii | Labour Camps | [11 empty] | 0
|  |  |  | 1 | Building | Nos. | 2% | 2 | 3742785 | 1871392.5 | 2 | 3742785 | 2 | 3742785 | 0 | 0 | 0
|  |  |  | 2 | Kitchen | Nos. | 1% | 2 | 1871392.5 | 935696.25 | 2 | 1871393 | 2 | 1871393 | 0 | 0 | 0
|  |  |  | d | Completion of Roofs | [11 empty] | 0
|  |  |  | i | Office | Nos. | 9% | 1 | 16842532.5 | 16842532.5 | 1 | 16842533 | 1 | 16842533 | 0 | 0 | 0
|  |  |  | ii | Laboratory | Nos. | 4% | 2 | 7485570 | 3742785 | 2 | 7485570 | 2 | 7485570 | 0 | 0 | 0
|  |  |  | iii | Labour Camps | [11 empty] | 0
|  |  |  | 1 | Building | Nos. | 2% | 2 | 3742785 | 1871392.5 | 2 | 3742785 | 2 | 3742785 | 0 | 0 | 0
|  |  |  | 2 | Kitchen | Nos. | 1% | 2 | 1871392.5 | 935696.25 | 2 | 1871393 | 2 | 1871393 | 0 | 0 | 0
|  |  |  | e | Completion of Flooring | [11 empty] | 0
|  |  |  | i | Office | Nos. | 9% | 1 | 16842532.5 | 16842532.5 | 1 | 16842533 | 1 | 16842533 | 0 | 0 | 0
|  |  |  | ii | Laboratory | Nos. | 3% | 2 | 5614177.5 | 2807088.75 | 2 | 5614178 | 2 | 5614178 | 0 | 0 | 0
|  |  |  | iii | Labour Camps | [11 empty] | 0
|  |  |  | 1 | Building | Nos. | 2% | 2 | 3742785 | 1871392.5 | 2 | 3742785 | 2 | 3742785 | 0 | 0 | 0
|  |  |  | 2 | Kitchen | Nos. | 1% | 2 | 1871392.5 | 935696.25 | 2 | 1871393 | 2 | 1871393 | 0 | 0 | 0
|  |  |  | f | Completion of Finishing Works | [11 empty] | 0
|  |  |  | i | Office | Nos. | 8% | 1 | 14971140 | 14971140 | 1 | 14971140 | 1 | 14971140 | 0 | 0 | 0
|  |  |  | ii | Laboratory | [11 empty] | 0
|  |  |  | 1 | Civil Works | Nos. | 2% | 2 | 3742785 | 1871392.5 | 2 | 3742785 | 2 | 3742785 | 0 | 0 | 0
|  |  |  | 2 | Lab Equipment | Nos. | 4% | 2 | 7485570 | 3742785 | 2 | 7485570 | 2 | 7485570 | 0 | 0 | 0
|  |  |  | iii | Labour Camps | [11 empty] | 0
|  |  |  | 1 | Building | Nos. | 2% | 2 | 3742785 | 1871392.5 | 2 | 3742785 | 2 | 3742785 | 0 | 0 | 0
|  |  |  | 2 | Kitchen | Nos. | 2% | 2 | 3742785 | 1871392.5 | 2 | 3742785 | 2 | 3742785 | 0 | 0 | 0
|  |  |  | 103 | Operation and Maintenance of all temporary facilities including those mentioned in Item 101 & 102 | LS | 12.3% |  | 82502250 | [7 empty] | 0
|  |  |  | a | Employer's Office | Quarterly | 35% | 16 | 28875787.5 | 1804736.7188 | 8 | 14437894 | 8 | 14437894 | 0 | 0 | 8 | 1804736.7188
|  |  |  | b | Vehicles | [11 empty] | 0
|  |  |  | i | Bolero & Scorpio | Nos.-Quarterly | 20% | 96 | 16500450 | 171879.6875 | 48 | 8250225 | 48 | 8250225 | 0 | 0 | 48 | 1031278.125
|  |  |  | ii | Speed Boat | Nos.-Quarterly | 3% | 32 | 2475067.5 | 77345.8594 | 16 | 1237534 | 16 | 1237534 | 0 | 0 | 16 | 154691.7188
|  |  |  | iii | Rescue Boat | Nos.-Quarterly | 2% | 16 | 1650045 | 103127.8125 | 8 | 825023 | 8 | 825023 | 0 | 0 | 8 | 103127.8125
|  |  |  | c | Contractor's Office | Quarterly | 15% | 16 | 12375337.5 | 773458.5938 | 8 | 6187669 | 8 | 6187669 | 0 | 0 | 8 | 773458.5938
|  |  |  | d | Site Laboratory | Quarterly | 15% | 16 | 12375337.5 | 773458.5938 | 8 | 6187669 | 8 | 6187669 | 0 | 0 | 8 | 773458.5938
|  |  |  | e | Labour Camps | Quarterly | 10% | 16 | 8250225 | 515639.0625 | 8 | 4125113 | 8 | 4125113 | 0 | 0 | 8 | 515639.0625
|  |  |  | 104 | Compliance of Environmental Management Plan (EMP) | LS | 22.5% |  | 150918750 | [7 empty] | 0
|  |  |  | a | Environmental Management Plan Implementation - Preservation of Top Soil, Propeller Guards, Plant Establishments : CTE, CTO, NOC's, Dust Supression Measures, Compensatory afforestation, TBT for Wildlife conservation for consideration of 48 months construction period or till completion of the project, whichever is later | Half Yearly | 7.35% | 8 | 11092528.125 | 1386566.0156 | 4 | 5546264 | 4 | 5546264 | 0 | 0 | 4 | 1386566.0156
|  |  |  | b | Implementation of Environmental Monitoring Program for consideration of 48 months construction period or till completion of the project, whichever is later | [11 empty] | 0
|  |  |  | i | Ambient Air Quality | Bi-Monthly | 3% | 24 | 4527562.5 | 188648.4375 | 12 | 2263781 | 12 | 2263781 | 0 | 0 | 12 | 188648.4375
|  |  |  | ii | Noise Level | Bi-Monthly | 3% | 24 | 4527562.5 | 188648.4375 | 12 | 2263781 | 12 | 2263781 | 0 | 0 | 12 | 188648.4375
|  |  |  | iii | Water Quality | Bi-Monthly | 3% | 24 | 4527562.5 | 188648.4375 | 12 | 2263781 | 12 | 2263781 | 0 | 0 | 12 | 188648.4375
|  |  |  | iv | Soil Quality | Half Yearly | 3% | 8 | 4527562.5 | 565945.3125 | 4 | 2263781 | 4 | 2263781 | 0 | 0 | 4 | 565945.3125
|  |  |  | v | Ecology and Biodiversity - Regular Survey of Ecology and Biodiversity (Terrestrial & Aquatic), Survey Equipment | Half Yearly | 6% | 8 | 9055125 | 1131890.625 | 4 | 4527563 | 4 | 4527563 | 0 | 0 | 4 | 1131890.625
|  |  |  | c | Compliance of Environmental Clearance Conditions - EC identification no. EC22B039AS197455 - Handling of Hazardous Waste, Provision of First Aid Room, Sanitary Measures, Green Belt Plantation for consideration of 48 months construction period or till completion of the project, whichever is later | Half Yearly | 10% | 8 | 15091875 | 1886484.375 | 4 | 7545938 | 4 | 7545938 | 0 | 0 | 4 | 1886484.375
|  |  |  | d | Implementation of Environmental Management Plan - For Aquatic Ecology and Dolphin Conservation - Monitoring of Dolphins, Migratory Birds, Turtle & Fish through Dolphin Biologists, No-go Zone for Boats & Vessels for consideration of 48 months construction period or till completion of the project, whichever is later | Half Yearly | 10% | 8 | 15091875 | 1886484.375 | 4 | 7545938 | 4 | 7545938 | 0 | 0 | 4 | 1886484.375
|  |  |  | e | Dolphin Pinger for Dolphin Safety | [11 empty] | 0
|  |  |  | i | Installation & Monitoring | Nos. | 5% | 30 | 7545937.5 | 251531.25 | 30 | 7545938 | 30 | 7545938 | 0 | 0 | 0
|  |  |  | ii | Maintenance of Equipment | Quarterly | 5% | 16 | 7545937.5 | 471621.0938 | 8 | 3772969 | 8 | 3772969 | 0 | 0 | 8 | 84891796.875
|  |  |  | f | Wetland Restoration - Clearance of Eutrophication, Water area, etc as per EC Condition till completion of the project | LS | 6.65% | 1 | 10036096.875 | 10036096.875 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | g | EMP provisions - During Construction Phase for consideration of 48 months construction period or till completion of the project, whichever is later | [11 empty] | 0
|  |  |  | i | Solid Waste Management accessories | Quarterly | 3% | 16 | 4527562.5 | 282972.6562 | 8 | 2263781 | 8 | 2263781 | 0 | 0 | 8 | 282972.6562
|  |  |  | ii | Health and Occupational Safety Management Plan | Quarterly | 5% | 16 | 7545937.5 | 471621.0938 | 8 | 3772969 | 8 | 3772969 | 0 | 0 | 8 | 471621.0938
|  |  |  | iii | Environmental Training Plan | Quarterly | 3% | 16 | 4527562.5 | 282972.6562 | 8 | 2263781 | 8 | 2263781 | 0 | 0 | 8 | 282972.6562
|  |  |  | iv | Traffic Management Plan | Quarterly | 3% | 16 | 4527562.5 | 282972.6562 | 8 | 2263781 | 8 | 2263781 | 0 | 0 | 8 | 282972.6562
|  |  |  | v | Emergency Preparedness Plan | Quarterly | 3% | 16 | 4527562.5 | 282972.6562 | 8 | 2263781 | 8 | 2263781 | 0 | 0 | 8 | 282972.6562
|  |  |  | vi | Miscellaneous (repair and maintenance) | Quarterly | 1% | 16 | 1509187.5 | 94324.2188 | 8 | 754594 | 8 | 754594 | 0 | 0 | 8 | 94324.2188
|  |  |  | h | Provision for establishment of Sewage and Water Treatment Plant within construction period of 48 months or till completion of the project, whichever is later | [11 empty] | 0
|  |  |  | i | Sewage Treatment Plant | [11 empty] | 0
|  |  |  | 1 | Construction | Nos. | 3% | 3 | 4527562.5 | 1509187.5 | 3 | 4527563 | 3 | 4527563 | 0 | 0 | 0
|  |  |  | 2 | Maintenance | Quarterly | 1% | 15 | 1509187.5 | 100612.5 | 7 | 704288 | 7 | 704288 | 0 | 0 | 8 | 402450
|  |  |  | ii | Waste Water Treatment Plant | [11 empty] | 0
|  |  |  | 1 | Construction | Nos. | 3% | 4 | 4527562.5 | 1131890.625 | 4 | 4527563 | 4 | 4527563 | 0 | 0 | 0
|  |  |  | 2 | Maintenance | Quarterly | 1% | 10 | 1509187.5 | 150918.75 | 2 | 301838 | 2 | 301838 | 0 | 0 | 8
|  |  |  | iii | Silt Sedimentation Tank | [11 empty] | 0
|  |  |  | 1 | Construction | Nos. | 3% | 4 | 4527562.5 | 1131890.625 | 4 | 4527563 | 4 | 4527563 | 0 | 0 | 0
|  |  |  | 2 | Maintenance | Quarterly | 1% | 12 | 1509187.5 | 125765.625 | 6 | 754594 | 6 | 754594 | 0 | 0 | 6 | 754594
|  |  |  | iv | Effluent Treatment Plant | [11 empty] | 0
|  |  |  | 1 | Construction | Nos. | 3% | 2 | 4527562.5 | 2263781.25 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | 2 | Maintenance | Quarterly | 1% | 4 | 1509187.5 | 377296.875 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  |  |  | v | Toilets | [11 empty] | 0
|  |  |  | 1 | Construction | Nos. | 3% | 250 | 4527562.5 | 18110.25 | 250 | 4527563 | 250 | 4527563 | 0 | 0 | 0
|  |  |  | 2 | Maintenance | Quarterly | 1% | 16 | 1509187.5 | 94324.2188 | 8 | 754594 | 8 | 754594 | 0 | 0 | 8 | 94324.2188
|  |  |  | 105 | Demobilization of the Site on completion of the Works as per the General Specifications | LS | 6.8% |  | 45611000 | [7 empty] | 0
|  |  |  | a | Employer's Office | Nos. | 35% | 2 | 15963850 | 7981925 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | b | Contractor's Office | Nos. | 20% | 1 | 9122200 | 9122200 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | c | Site Laboratory | Nos. | 20% | 2 | 9122200 | 4561100 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | d | Labour Camps | Nos. | 25% | 2 | 11402750 | 5701375 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Preliminaries & General Items | [11 empty] | 512717121 |  | 512717121 |  | 0 | 0
0
Schedule 2 | Validation of Survey Data, Investigation, Design and As-Built Drawings | 3% | 804900000 | 201 | Site survey, establishment of bench marks, validation of ROW, identification of borrow areas. | LS | 4.8% |  | 38635200 | [7 empty] | 0
|  |  |  | a | Establishment of Bench Marks | Kms | 30% | 12.21 | 11590560 | 949267.8133 | 12.21 | 11590560 | 12.21 | 11590560 | 0 | 0 | 0
|  |  |  | b | Completion of Site Survey | Kms | 40% | 12.21 | 15454080 | 1265690.4177 | 12.21 | 15454080 | 12.21 | 15454080 | 0 | 0 | 0
|  |  |  | c | Validation of ROW | Kms | 20% | 12.21 | 7727040 | 632845.2088 | 12.21 | 7727040 | 12.21 | 7727040 | 0 | 0 | 0
|  |  |  | d | Identification of Borrow Areas | Nos. | 10% | 5 | 3863520 | 772704 | 5 | 3863520 | 5 | 3863520 | 0 | 0 | 0
|  |  |  | 202 | Site data collection, Detailed Geotechnical and Hydrological investigations and report submission & approval | LS | 9.8% |  | 78880200 | [7 empty] | 0
|  |  |  | a | Completion of Topographical Survey (Site data collection) | [11 empty] | 0
|  |  |  | i | Report Submission | Kms | 30% | 12.21 | 23664060 | 1938088.4521 | 12.21 | 23664060 | 12.21 | 23664060 | 0 | 0 | 0
|  |  |  | ii | Report Approval | Kms | 7.5% | 12.21 | 5916015 | 484522.113 | 12.21 | 5916015 | 12.21 | 5916015 | 0 | 0 | 0
|  |  |  | b | Detailed Geotechnical Investigation | [11 empty] | 0
|  |  |  | i | Report Submission | Nos. | 30% | 96 | 23664060 | 246500.625 | 96 | 23664060 | 96 | 23664060 | 0 | 0 | 0
|  |  |  | ii | Report Approval | Nos. | 7.5% | 96 | 5916015 | 61625.1562 | 96 | 5916015 | 96 | 5916015 | 0 | 0 | 0
|  |  |  | c | Detailed Hydrological Investigation | [11 empty] | 0
|  |  |  | i | Report Submission | LS | 25% | 1 | 19720050 | 19720050 | 1 | 19720050 | 1 | 19720050 | 0 | 0 | 0
|  |  |  | 203 | Preliminary Design of the approach formations, retaining structures, drainage system, bridges, major and /or minor structure and miscellaneous work. | LS | 29.4% |  | 236640600 | [7 empty] | 0
|  |  |  | a | Approach Formations (GAD / P&P) | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Kms | 4% | 7.314 | 9465624 | 1294178.8351 | 7.314 | 9465624 | 7.314 | 9465624 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Kms | 6% | 7.314 | 14198436 | 1941268.2527 | 7.314 | 14198436 | 7.314 | 14198436 | 0 | 0 | 0
|  |  |  | b | Retaining Structures (GAD / P&P) | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Kms | 2.5% | 5.2 | 5916015 | 1137695.1923 | 5.2 | 5916015 | 5.2 | 5916015 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Kms | 3.5% | 5.2 | 8282421 | 1592773.2692 | 5.2 | 8282421 | 5.2 | 8282421 | 0 | 0 | 0
|  |  |  | c | Drainage (GAD / P&P) | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Kms | 2.5% | 0.8 | 5916015 | 7395018.75 | 0.68 | 5028613 | 0.68 | 5028613 | 0 | 0 | 0.12
|  |  |  | ii | Documents & Reports - Approval | Kms | 3.5% | 0.8 | 8282421 | 10353026.25 | 0.68 | 7040058 | 0.68 | 7040058 | 0 | 0 | 0.12
|  |  |  | d | Wetland Viaducts (GAD / P&P) | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Nos. | 4% | 2 | 9465624 | 4732812 | 2 | 9465624 | 2 | 9465624 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Nos. | 6% | 2 | 14198436 | 7099218 | 2 | 14198436 | 2 | 14198436 | 0 | 0 | 0
|  |  |  | e | Approach Viaducts (GAD / P&P) | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Nos. | 4% | 2 | 9465624 | 4732812 | 2 | 9465624 | 2 | 9465624 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Nos. | 6% | 2 | 14198436 | 7099218 | 2 | 14198436 | 2 | 14198436 | 0 | 0 | 0
|  |  |  | f | Vehicular Underpass (GAD / P&P) | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Nos. | 2% | 3 | 4732812 | 1577604 | 3 | 4732812 | 3 | 4732812 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Nos. | 4% | 3 | 9465624 | 3155208 | 3 | 9465624 | 3 | 9465624 | 0 | 0 | 0
|  |  |  | g | Culverts (GAD) | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Nos. | 1% | 18 | 2366406 | 131467 | 18 | 2366406 | 18 | 2366406 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Nos. | 3% | 18 | 7099218 | 394401 | 18 | 7099218 | 18 | 7099218 | 0 | 0 | 0
|  |  |  | h | Main Bridge (GAD) | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Nos. | 15% | 1 | 35496090 | 35496090 | 1 | 35496090 | 1 | 35496090 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Nos. | 22% | 1 | 52060932 | 52060932 | 1 | 52060932 | 1 | 52060932 | 0 | 0 | 0
|  |  |  | i | Miscellaneous Works | [11 empty] | 0
|  |  |  | i | Temporary Access Bridge | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | ii | Casting Yard (Layout) | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | iii | River Training Works | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | Nos. | 0.5% | 2 | 1183203 | 591601.5 | 2 | 1183203 | 2 | 1183203 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | Nos. | 0.5% | 2 | 1183203 | 591601.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | iv | Labour Camps | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | v | Office | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | vi | Laboratory | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | vii | Precast Moulds | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | LS | 0.5% | 1 | 1183203 | 1183203 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | viii | Traffic Signages | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | ix | Road Marking | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | x | Bridge Illumination | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | LS | 0.5% | 1 | 1183203 | 1183203 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | 2 | Documents & Reports - Approval | LS | 0.5% | 1 | 1183203 | 1183203 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | xi | Bridge Health Monitoring | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | LS | 0.5% | 1 | 1183203 | 1183203 | 1 | 1183203 | 1 | 1183203 | 0 | 0 | 0
|  |  |  | 204 | Final Technical Design of the approach formation, retaining structures, drainage system, bridges, major and /or minor structures and miscellaneous work | LS | 41% |  | 330009000 | [7 empty] | 0
|  |  |  | a | Approach Formations | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Kms | 2% | 7.314 | 6600180 | 902403.6095 | 7.314 | 6600180 | 7.314 | 6600180 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Kms | 2% | 7.314 | 6600180 | 902403.6095 | 7.314 | 6600180 | 7.314 | 6600180 | 0 | 0 | 0
|  |  |  | iii | Issue of GFC Drawings | Kms | 1% | 7.314 | 3300090 | 451201.8048 | 7.314 | 3300090 | 7.314 | 3300090 | 0 | 0 | 0
|  |  |  | b | Retaining Structures | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Kms | 2% | 5.2 | 6600180 | 1269265.3846 | 5.2 | 6600180 | 5.2 | 6600180 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Kms | 2% | 5.2 | 6600180 | 1269265.3846 | 5.2 | 6600180 | 5.2 | 6600180 | 0 | 0 | 0
|  |  |  | iii | Issue of GFC Drawings | Kms | 1% | 5.2 | 3300090 | 634632.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2
|  |  |  | c | Drainage | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Kms | 1% | 0.8 | 3300090 | 4125112.5 | 0.65 | 2681323 | 0.65 | 2681323 | 0 | 0 | 0.15
|  |  |  | ii | Documents & Reports - Approval | Kms | 1% | 0.8 | 3300090 | 4125112.5 | 0.65 | 2681323 | 0.65 | 2681323 | 0 | 0 | 0.15
|  |  |  | iii | Issue of GFC Drawings | Kms | 0.5% | 0.8 | 1650045 | 2062556.25 | 0.23 | 474388 | 0.23 | 474388 | 0 | 0 | 0.57
|  |  |  | d | Wetland Viaducts | [11 empty] | 0
|  |  |  | i | Foundation | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | Nos. | 2% | 2 | 6600180 | 3300090 | 2 | 6600180 | 2 | 6600180 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | Nos. | 3% | 2 | 9900270 | 4950135 | 2 | 9900270 | 2 | 9900270 | 0 | 0 | 0
|  |  |  | 3 | Issue of GFC Drawings | Nos. | 2% | 2 | 6600180 | 3300090 | 2 | 6600180 | 2 | 6600180 | 0 | 0 | 0
|  |  |  | ii | Substructure | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | Nos. | 2% | 2 | 6600180 | 3300090 | 2 | 6600180 | 2 | 6600180 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | Nos. | 3% | 2 | 9900270 | 4950135 | 2 | 9900270 | 2 | 9900270 | 0 | 0 | 0
|  |  |  | 3 | Issue of GFC Drawings | Nos. | 2% | 2 | 6600180 | 3300090 | 2 | 6600180 | 2 | 6600180 | 0 | 0 | 0
|  |  |  | iii | Superstructure | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | Nos. | 2% | 2 | 6600180 | 3300090 | 2 | 6600180 | 2 | 6600180 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | Nos. | 3% | 2 | 9900270 | 4950135 | 2 | 9900270 | 2 | 9900270 | 0 | 0 | 0
|  |  |  | 3 | Issue of GFC Drawings | Nos. | 2% | 2 | 6600180 | 3300090 | 2 | 6600180 | 2 | 6600180 | 0 | 0 | 0
|  |  |  | e | Approach Viaducts | [11 empty] | 0
|  |  |  | i | Foundation | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | Nos. | 2% | 2 | 6600180 | 3300090 | 2 | 6600180 | 2 | 6600180 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | Nos. | 3% | 2 | 9900270 | 4950135 | 2 | 9900270 | 2 | 9900270 | 0 | 0 | 0
|  |  |  | 3 | Issue of GFC Drawings | Nos. | 2% | 2 | 6600180 | 3300090 | 1.875 | 6187669 | 1.875 | 6187669 | 0 | 0 | 0.125
|  |  |  | ii | Substructure | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | Nos. | 2% | 2 | 6600180 | 3300090 | 2 | 6600180 | 2 | 6600180 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | Nos. | 3% | 2 | 9900270 | 4950135 | 1.75 | 8662736 | 1.75 | 8662736 | 0 | 0 | 0.25
|  |  |  | 3 | Issue of GFC Drawings | Nos. | 2% | 2 | 6600180 | 3300090 | 1.688 | 5570552 | 1.438 | 4745529 | 0.25 | 825023 | 0.312
|  |  |  | iii | Superstructure | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | Nos. | 2% | 2 | 6600180 | 3300090 | 2 | 6600180 | 2 | 6600180 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | Nos. | 3% | 2 | 9900270 | 4950135 | 2 | 9900270 | 2 | 9900270 | 0 | 0 | 0
|  |  |  | 3 | Issue of GFC Drawings | Nos. | 2% | 2 | 6600180 | 3300090 | 0.857 | 2828177 | 0.857 | 2828177 | 0 | 0 | 1.143
|  |  |  | f | Vehicular Underpass | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Nos. | 2% | 3 | 6600180 | 2200060 | 3 | 6600180 | 3 | 6600180 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Nos. | 2% | 3 | 6600180 | 2200060 | 3 | 6600180 | 3 | 6600180 | 0 | 0 | 0
|  |  |  | iii | Issue of GFC Drawings | Nos. | 1% | 3 | 3300090 | 1100030 | 0 | 0 | 0 | 0 | 0 | 0 | 3
|  |  |  | g | Culverts | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Nos. | 2% | 18 | 6600180 | 366676.6667 | 18 | 6600180 | 18 | 6600180 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Nos. | 2% | 18 | 6600180 | 366676.6667 | 18 | 6600180 | 18 | 6600180 | 0 | 0 | 0
|  |  |  | iii | Issue of GFC Drawings | Nos. | 1% | 18 | 3300090 | 183338.3333 | 18 | 3300090 | 18 | 3300090 | 0 | 0 | 0
|  |  |  | h | Foundation of Main Bridge | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Nos. | 3% | 1 | 9900270 | 9900270 | 1 | 9900270 | 1 | 9900270 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Nos. | 4% | 1 | 13200360 | 13200360 | 1 | 13200360 | 1 | 13200360 | 0 | 0 | 0
|  |  |  | iii | Issue of GFC Drawings | Nos. | 1% | 1 | 3300090 | 3300090 | 1 | 3300090 | 1 | 3300090 | 0 | 0 | 0
|  |  |  | i | Substructure of Main Bridge | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Nos. | 3% | 1 | 9900270 | 9900270 | 1 | 9900270 | 1 | 9900270 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Nos. | 3% | 1 | 9900270 | 9900270 | 0.76 | 7524205 | 0.76 | 7524205 | 0 | 0 | 0.24
|  |  |  | iii | Issue of GFC Drawings | Nos. | 1% | 1 | 3300090 | 3300090 | 0.52 | 1716047 | 0.52 | 1716047 | 0 | 0 | 0.48
|  |  |  | j | Superstructure of Main Bridge | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Nos. | 3% | 1 | 9900270 | 9900270 | 1 | 9900270 | 1 | 9900270 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Nos. | 4% | 1 | 13200360 | 13200360 | 1 | 13200360 | 1 | 13200360 | 0 | 0 | 0
|  |  |  | iii | Issue of GFC Drawings | Nos. | 1% | 1 | 3300090 | 3300090 | 1 | 3300090 | 1 | 3300090 | 0 | 0 | 0
|  |  |  | k | Miscellaneous works | [11 empty] | 0
|  |  |  | i | Temporary Access Bridge | Rmt | 3% | 672 | 9900270 | 14732.5446 | 672 | 9900270 | 672 | 9900270 | 0 | 0 | 0
|  |  |  | ii | Launching System / Bridge Builder | [11 empty] | 0 | IDC Drawing
|  |  |  | 1 | Documents & Reports - Submission | Nos. | 2.01% | 1 | 6633180.9 | 6633180.9 | 1 | 6633181 | 1 | 6633181 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | Nos. | 0.99% | 1 | 3267089.1 | 3267089.1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | iii | Gantry | Nos. | 1% | 2 | 3300090 | 1650045 | 2 | 3300090 | 2 | 3300090 | 0 | 0 | 0
|  |  |  | iv | Bridge Health Monitoring | Span | 1% | 24 | 3300090 | 137503.75 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | v | Wind Tunnel Analysis | [11 empty] | 0
|  |  |  | 1 | Documents & Reports - Submission | Nos. | 1% | 1 | 3300090 | 3300090 | 1 | 3300090 | 1 | 3300090 | 0 | 0 | 0
|  |  |  | 2 | Documents & Reports - Approval | Nos. | 1% | 1 | 3300090 | 3300090 | 1 | 3300090 | 1 | 3300090 | 0 | 0 | 0
|  |  |  | l | Junctions | [11 empty] | 0
|  |  |  | i | Documents & Reports - Submission | Kms | 1% | 10 | 3300090 | 330009 | 10 | 3300090 | 10 | 3300090 | 0 | 0 | 0
|  |  |  | ii | Documents & Reports - Approval | Kms | 1% | 10 | 3300090 | 330009 | 10 | 3300090 | 10 | 3300090 | 0 | 0 | 0
|  |  |  | iii | Issue of GFC Drawings | Kms | 0.5% | 10 | 1650045 | 165004.5 | 10 | 1650045 | 10 | 1650045 | 0 | 0 | 0
|  |  |  | 205 | Setting out of the Final Alignment with location of all structures, approach formation work and Miscellaneous work | LS | 10% |  | 80490000 | [7 empty] | 0
|  |  |  | a | Documents & Reports - Submission | Kms | 40% | 12.21 | 32196000 | 2636855.0369 | 12.21 | 32196000 | 12.21 | 32196000 | 0 | 0 | 0
|  |  |  | b | Documents & Reports - Approval | Kms | 40% | 12.21 | 32196000 | 2636855.0369 | 12.21 | 32196000 | 12.21 | 32196000 | 0 | 0 | 0
|  |  |  | c | Issue of GFC Drawings | Kms | 20% | 12.21 | 16098000 | 1318427.5184 | 12.21 | 16098000 | 12.21 | 16098000 | 0 | 0 | 0
|  |  |  | 206 | Preparation of As-Built Drawings | LS | 5% |  | 40245000 | [7 empty] | 0
|  |  |  | a | Documents & Reports - Submission | Kms | 40% | 12.21 | 16098000 | 1318427.5184 | 0 | 0 | 0 | 0 | 0 | 0 | 12.21
|  |  |  | b | Documents & Reports - Approval | Kms | 40% | 12.21 | 16098000 | 1318427.5184 | 0 | 0 | 0 | 0 | 0 | 0 | 12.21
|  |  |  | c | Issue of Final Drawings | Kms | 20% | 12.21 | 8049000 | 659213.7592 | 0 | 0 | 0 | 0 | 0 | 0 | 12.21
Validation of Survey Data, Investigation, Design and As-Built Drawings | [11 empty] | 731800089 |  | 730975066 |  | 825023 | 0
0
Schedule 3 | Enabling Works for Main Works | 4.5% | 1207350000 | 301 | Construction of temporary jetties/ platforms (TAB) / load out jetties etc for marine working | LS | 17.9% |  | 216115650 | [7 empty] | 0
|  |  |  | a | Supply of TAB material at site | MT | 80% | 3899.3781 | 172892520 | 44338.4857 | 3899.3781 | 172892520 | 3899.3781 | 172892520 | 0 | 0 | 0
|  |  |  | b | Installation of TAB | Rmt | 20% | 672 | 43223130 | 64320.1339 | 672 | 43223130 | 672 | 43223130 | 0 | 0 | 0
|  |  |  | 302 | Establishment of batching plant, crusher (if any), rebar yards, formwork shops, fabrication shops etc for main works | LS | 12.1% |  | 146089350 | [7 empty] | 0
|  |  |  | a | Establishment of Batching Plants | [11 empty] | 0
|  |  |  | i | Receipt of Equipment | Nos. | 20% | 4 | 29217870 | 7304467.5 | 4 | 29217870 | 4 | 29217870 | 0 | 0 | 0
|  |  |  | ii | Foundation | Nos. | 10% | 4 | 14608935 | 3652233.75 | 4 | 14608935 | 4 | 14608935 | 0 | 0 | 0
|  |  |  | iii | Installation and Commissioning | Nos. | 20% | 4 | 29217870 | 7304467.5 | 4 | 29217870 | 4 | 29217870 | 0 | 0 | 0
|  |  |  | b | Establishment of Crusher Plant | [11 empty] | 0
|  |  |  | i | Receipt of Equipment | Nos | 8% | 1 | 11687148 | 11687148 | 1 | 11687148 | 1 | 11687148 | 0 | 0 | 0
|  |  |  | ii | Foundation | Nos | 4% | 1 | 5843574 | 5843574 | 1 | 5843574 | 1 | 5843574 | 0 | 0 | 0
|  |  |  | iii | Installation and Commissioning | Nos | 3% | 1 | 4382680.5 | 4382680.5 | 1 | 4382681 | 1 | 4382681 | 0 | 0 | 0
|  |  |  | c | Commissioning of Rebar Yard | Nos | 10% | 2 | 14608935 | 7304467.5 | 2 | 14608935 | 2 | 14608935 | 0 | 0 | 0
|  |  |  | d | Commissioning of Formwork Yard | Nos | 10% | 2 | 14608935 | 7304467.5 | 2 | 14608935 | 2 | 14608935 | 0 | 0 | 0
|  |  |  | e | Commissioning of Fabrication Yard | Nos | 15% | 1 | 21913402.5 | 21913402.5 | 1 | 21913403 | 1 | 21913403 | 0 | 0 | 0
|  |  |  | 303 | Establishment of Casting yards for casting of PSC Box girders, I-Girders etc as per requirement | LS | 27.9% |  | 336850650 | [7 empty] | 0
|  |  |  | a | Construction of Casting Yard | [11 empty] | 0
|  |  |  | i | Area Development | Nos | 20% | 2 | 67370130 | 33685065 | 2 | 67370130 | 2 | 67370130 | 0 | 0 | 0
|  |  |  | ii | Foundation of Gantry Track | Nos | 15% | 2 | 50527597.5 | 25263798.75 | 2 | 50527598 | 2 | 50527598 | 0 | 0 | 0
|  |  |  | iii | Casting Bed Foundation | Nos | 20% | 2 | 67370130 | 33685065 | 2 | 67370130 | 2 | 67370130 | 0 | 0 | 0
|  |  |  | iv | Stacking Bed Foundation | Nos | 20% | 2 | 67370130 | 33685065 | 2 | 67370130 | 2 | 67370130 | 0 | 0 | 0
|  |  |  | v | Finishing and Commisioning of Casting Yard | Nos | 25% | 2 | 84212662.5 | 42106331.25 | 2 | 84212663 | 2 | 84212663 | 0 | 0 | 0
|  |  |  | 304 | Supply and installation of moulds, gantries etc for precast works | LS | 17.9% |  | 216115650 | [7 empty] | 0
|  |  |  | a | Moulds - Material Procurement (Long Bed) | Nos | 25% | 4 | 54028912.5 | 13507228.125 | 4 | 54028913 | 4 | 54028913 | 0 | 0 | 0
|  |  |  | b | Moulds - Fabrication & Commissioning (Long Bed) | Nos | 20% | 4 | 43223130 | 10805782.5 | 4 | 43223130 | 4 | 43223130 | 0 | 0 | 0
|  |  |  | c | Gantry - Equipment Receipt | Nos | 35% | 2 | 75640477.5 | 37820238.75 | 2 | 75640478 | 2 | 75640478 | 0 | 0 | 0
|  |  |  | d | Gantry - Installation & Commissioning | Nos | 20% | 2 | 43223130 | 21611565 | 2 | 43223130 | 2 | 43223130 | 0 | 0 | 0 | TPT
|  |  |  | 305 | Supply and commissioning of Bridge Builders/Launchers for erection of bridge deck | LS | 8% |  | 96588000 | [7 empty] | 0
|  |  |  | a | Receipt of Equipment at site | Set | 75% | 10 | 72441000 | 7244100 | 4 | 28976400 | 4 | 28976400 | 0 | 0 | 6
|  |  |  | b | Installation & Commissioning | Set | 25% | 10 | 24147000 | 2414700 | 0 | 0 | 0 | 0 | 0 | 0 | 10
|  |  |  | 306 | Procurement/Mobilization of Marine Equipment’s (Barges/Tugs etc) for working in water | LS | 14% |  | 169029000 | [7 empty] | 0
|  |  |  | a | Procurement / Mobilization of Barges | Nos. | 75% | 6 | 126771750 | 21128625 | 6 | 126771750 | 6 | 126771750 | 0 | 0 | 0
|  |  |  | b | Procurement / Mobilization of Tugs | Nos. | 25% | 2 | 42257250 | 21128625 | 2 | 42257250 | 2 | 42257250 | 0 | 0 | 0
|  |  |  | 307 | Removal of temporary jetties, platforms, load out jetties and casting yards | LS | 2.2% |  | 26561700 | [7 empty] | 0
|  |  |  | a | Temporary Access Bridge | LS | 30% | 1 | 7968510 | 7968510 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | b | Casting Yard | Nos. | 70% | 2 | 18593190 | 9296595 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Enabling Works for Main Works | [11 empty] | 1113176703 |  | 1113176703 |  | 0 | 0
0
Schedule 4 | Main Extradosed Bridge Works | 67% | 17976100000 | 401 | On ground clearance, preparatory works for start of foundation works such as cutting edge, shutters, scaffoldings etc | LS | 0.4% |  | 71904400 | [7 empty] | 0
|  |  |  | a | Fabrication of Cutting Edge | Nos | 40% | 26 | 28761760 | 1106221.5385 | 1 | 1106222 | 1 | 28761760 | 0 | -27655538 | 25 |  |  | 1106221.5385 | 2212443.0769
|  |  |  | b | Ground preparation and placing of Cutting Edge | Nos | 10% | 26 | 7190440 | 276555.3846 | 1 | 276555 | 1 | 6913885 | 0 | -6637330 | 25 |  |  | 276555.3846 | 553110.7692
|  |  |  | c | Shuttering and scaffolding | Nos | 50% | 26 | 35952200 | 1382776.9231 | 1 | 1382777 | 1 | 34569423 | 0 | -33186646 | 25 |  |  | 1382776.9231 | 2765553.8462
|  |  |  | 402 | Construction of foundation | LS | 37.2% |  | 6687109200 | [7 empty] | 0
|  |  |  | a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | 80% | 1381.8 | 5349687360 | 3871535.2149 | 1.09 | 4219973 | 1 | 4992228514 | 0.09 | -4988008541 | 1380.71 |  |  | 3871535.2149 | 165004830.8606
|  |  |  | b | Well Bottom Plugging | Nos | 6.6% | 26 | 441349207.2 | 16974969.5077 | 2.5 | 42437424 | 3.15 | 169749695 | -0.65 | -127312271 | 23.5 |  |  | 16974969.5077 | 42437423.7692
|  |  |  | c | Well Cap | Nos | 13.4% | 26 | 896072632.8 | 34464332.0308 | 2.5 | 86160830 | 2.5 | 275714656 | 0 | -189553826 | 23.5 |  |  | 34464332.0308 | 86160830.0769
|  |  |  | 403 | Construction of sub- structure; abutment/ piers / lower pylon | LS | 2.1% |  | 377498100 | [7 empty] | 0
|  |  |  | a | Construction of abutment / piers / lower pylon | Rmt | 100% | 544.455 | 377498100 | 693350.4146 | 2.5 | 1733376 | 2.6 | 39500173 | -0.1 | -37766797 | 541.955
|  |  |  | 404 | Construction of pier-cap/ pier table | LS | 1.5% |  | 269641500 | [7 empty] | 0
|  |  |  | a | Construction of pier-cap/ pier table | Nos | 100% | 26 | 269641500 | 10370826.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 26
|  |  |  | 405 | Construction of upper pylon | LS | 1.1% |  | 197737100 | [7 empty] | 0
|  |  |  | a | Construction of upper pylon | Rmt | 100% | 490 | 197737100 | 403545.102 | 0 | 0 | 0 | 0 | 0 | 0 | 490
|  |  |  | 406 | Construction of PSC Box girders in casting yard | LS | 18.8% |  | 3379506800 | [7 empty] | 0
|  |  |  | a | Casting of PSC Box girder segments in casting yard | Nos | 75% | 1116 | 2534630100 | 2271173.9247 | 5777.302 | 13121257658 | 452 | 1026570614 | 5325.302 | 12094687044 | -4661.302
|  |  |  | b | Erection of PSC Box girder segments at site | Nos | 25% | 1116 | 844876700 | 757057.9749 | 0 | 0 | 0 | 0 | 0 | 0 | 1116
|  |  |  | 407 | Procurement, testing and supply of post tensioning material to site | LS | 3.9% |  | 701067900 | [7 empty] | 0
|  |  |  | a | Supply of Post tensioning material of PSC Box girder segments | MT | 40% | 4987 | 280427160 | 56231.6342 | 0 | 0 | 0 | 0 | 0 | 0 | 4987
|  |  |  | b | Testing of Material | MT | 5% | 4987 | 35053395 | 7028.9543 | 0 | 0 | 0 | 0 | 0 | 0 | 4987
|  |  |  | c | Post Tensioning Material consumed during casting of segments | Nos | 20% | 1116 | 140213580 | 125639.4086 | 5777.302 | 725856807 | 452 | 56789013 | 5325.302 | 669067794 | -4661.302
|  |  |  | d | Final stressing of PSC Box girder segments at site | Nos | 30% | 1116 | 210320370 | 188459.1129 | 0 | 0 | 0 | 0 | 0 | 0 | 1116
|  |  |  | e | Grouting of PSC Box girder segments at site | Nos | 5% | 1116 | 35053395 | 31409.8522 | 0 | 0 | 0 | 0 | 0 | 0 | 1116
|  |  |  | 408 | Procurement, testing and supply of Stay Cables to site | LS | 7.9% |  | 1420111900 | [7 empty] | 0
|  |  |  | a | Supply of stay cable material | MT | 35% | 1853 | 497039165 | 268234.8435 | 804.821 | 215881035 | 804.821 | 215881035 | 0 | 0 | 1048.179
|  |  |  | b | Testing of Material | MT | 5% | 1853 | 71005595 | 38319.2634 | 804.821 | 30840148 | 450.478 | 17261985 | 354.343 | 13578163 | 1048.179
|  |  |  | c | Stay Cable Material consumed during casting of each stay cable segment | Nos | 20% | 372 | 284022380 | 763501.0215 | 0 | 0 | 174 | 132849178 | -174 | -132849178 | 372
|  |  |  | d | Stressing of Stay Cable segments | Nos | 40% | 372 | 568044760 | 1527002.043 | 0 | 0 | 0 | 0 | 0 | 0 | 372
|  |  |  | 409 | Installation of PSC Box girders at site including installation of Stay Cable, Post Tensioning for completion of deck | LS | 22.8% |  | 4098550800 | [7 empty] | 0
|  |  |  | a | Installation of PSC Box Girder (Completion of Deck) after erection & stressing of segments | Nos | 40% | 1116 | 1639420320 | 1469014.6237 | 0 | 0 | 0 | 0 | 0 | 0 | 1116
|  |  |  | b | Installation and Stressing of each Stay Cable (Final) segments | Nos | 40% | 372 | 1639420320 | 4407043.871 | 0 | 0 | 0 | 0 | 0 | 0 | 372
|  |  |  | c | Post Tensioning of Continuity Cables | Nos | 10% | 1116 | 409855080 | 367253.6559 | 0 | 0 | 0 | 0 | 0 | 0 | 1116
|  |  |  | d | Final Tensioning and Fine Tuning of stay cables | Module | 10% | 6 | 409855080 | 68309180 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  |  |  | 410 | Installation of bearings and expansion joints, Bridge Health Monitoring Equipments | LS | 0.6% |  | 107856600 | [7 empty] | 0
|  |  |  | a | Bearings - Material Testing and Procurement | Nos | 15% | 28 | 16178490 | 577803.2143 | 0 | 0 | 0 | 0 | 0 | 0 | 28
|  |  |  | b | Bearings - Installation | Nos | 5% | 28 | 5392830 | 192601.0714 | 0 | 0 | 0 | 0 | 0 | 0 | 28
|  |  |  | c | Expansion Joints - Material Testing and Procurement | Nos | 30% | 7 | 32356980 | 4622425.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 7
|  |  |  | d | Expansion Joints - Installation | Nos | 10% | 7 | 10785660 | 1540808.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 7
|  |  |  | e | Bridge Health Monitoring Equipments - Material Procurement | Span | 30% | 24 | 32356980 | 1348207.5 |  | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | f | Bridge Health Monitoring Equipments - Installation | Span | 5% | 24 | 5392830 | 224701.25 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | g | Bridge Health Monitoring Equipments - Testing | Span | 5% | 24 | 5392830 | 224701.25 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | 411 | Construction of Crash Barriers & Hand Railling | LS | 0.7% |  | 125832700 | [7 empty] | 0
|  |  |  | a | Crash Barrier | Span | 70% | 24 | 88082890 | 3670120.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | b | Handrailing | Span | 20% | 24 | 25166540 | 1048605.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | c | Safety Fence | Span | 10% | 24 | 12583270 | 524302.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | 412 | Completion of bridge pavement | LS | 0.4% |  | 71904400 | [7 empty] | 0
|  |  |  | a | Water Proofing | Span | 20% | 24 | 14380880 | 599203.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | b | 1st layer wearing course | Span | 30% | 24 | 21571320 | 898805 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | c | Final layer wearing course | Span | 50% | 24 | 35952200 | 1498008.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | 413 | Completion of bridge lighting and electrical works | LS | 0.3% |  | 53928300 | [7 empty] | 0
|  |  |  | a | Material Procurement | Span | 80% | 24 | 43142640 | 1797610 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | b | Installation | Span | 10% | 24 | 5392830 | 224701.25 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | c | Commissioning | Span | 5% | 24 | 2696415 | 112350.625 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | d | Testing of Material | Span | 5% | 24 | 2696415 | 112350.625 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | 414 | Completion of balance ancillary and miscellaneous works for handing over | LS | 0.6% |  | 107856600 | [7 empty] | 0
|  |  |  | a | Traffic Signages | Span | 40% | 24 | 43142640 | 1797610 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | b | Road Marking | Span | 50% | 24 | 53928300 | 2247012.5 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | c | Crash Barrier Painting | Span | 10% | 24 | 10785660 | 449402.5 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | 415 | Drainage works for bridge downtake | LS | 1.7% |  | 305593700 | [7 empty] | 0
|  |  |  | a | Drainage Spouts | Span | 40% | 24 | 122237480 | 5093228.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | b | Drainage works for bridge downtake | Span | 60% | 24 | 183356220 | 7639842.5 | 0 | 0 | 0 | 0 | 0 | 0 | 24
Main Extradosed Bridge Works | [11 empty] | 14231152805 |  | 6996789931 |  | 7234362874 | 0
0
Schedule 5 | Wetland and Approach Viaduct Works | 14.5% | 3890350000 | 501 | Construction of foundation | LS | 49.5% |  | 1925723250 | [7 empty] | 0
|  |  |  | a | For Wetland Viaduct | [11 empty] | 0
|  |  |  | 1 | On completion of Piles | Nos | 45% | 236 | 866575462.5 | 3671929.9258 | 236 | 866575463 | 236 | 866575463 | 0 | 0 | 0
|  |  |  | 2 | On completion of Pile Cap | Nos | 5% | 52 | 96286162.5 | 1851656.9712 | 52 | 96286163 | 52 | 96286163 | 0 | 0 | 0
|  |  |  | b | For Approach Viaduct | [11 empty] | 0
|  |  |  | 1 | On completion of Piles | Nos | 35% | 194 | 674003137.5 | 3474242.9768 | 194 | 674003138 | 194 | 674003138 | 0 | 0 | 0
|  |  |  | 2 | On completion of Wells | Rmt | 11.5% | 101.1 | 221458173.75 | 2190486.3872 | 99.25 | 217405774 | 98.2 | 215105763 | 1.05 | 2300011 | 1.85
|  |  |  | 3 | On completion of Pile Cap | Nos | 2.5% | 28 | 48143081.25 | 1719395.7589 | 26 | 44704290 | 25 | 42984894 | 1 | 1719396 | 2
|  |  |  | 4 | On completion of Well Cap | Nos | 1% | 2 | 19257232.5 | 9628616.25 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | 502 & 503 | Construction of sub- structure; abutment/piers / lower pylon & Construction of pier- cap/ pier table | LS | 12.1% |  | 470732350 | [7 empty] | 0
|  |  |  | a | For Wetland Viaduct | [11 empty] | 0
|  |  |  | 1 | On completion of abutment / Pier / lower pylon | Nos | 40% | 52 | 238810558.0488 | 4592510.7317 | 52 | 238810558 | 52 | 238810558 | 0 | 0 | 0
|  |  |  | 2 | On completion of pier-cap / pier table | Nos | 10% | 52 | 59702639.5122 | 1148127.6829 | 52 | 59702640 | 49 | 56258256 | 3 | 3444384 | 0
|  |  |  | b | For Approach Viaduct | [11 empty] | 0
|  |  |  | 1 | On completion of abutment / Pier / lower pylon | Nos | 40% | 30 | 137775321.9512 | 4592510.7317 | 26 | 119405279 | 24 | 110220258 | 2 | 9185021 | 4
|  |  |  | 2 | On completion of pier-cap / pier table | Nos | 10% | 30 | 34443830.4878 | 1148127.6829 | 9 | 10333149 | 8 | 9185021 | 1 | 1148128 | 21
|  |  |  | 504 | Construction of PSC Box girders/I-Girders in casting yard | LS | 15.3% |  | 595223550 | [7 empty] | 0
|  |  |  | a | For Wetland Viaduct | [11 empty] | 0
|  |  |  | 1 | Casting of Girders in the precast yard | Nos | 40% | 192 | 304754457.6 | 1587262.8 | 140 | 222216792 | 125 | 198407850 | 15 | 23808942 | 52
|  |  |  | 2 | Erection of Girders at site | Nos | 10% | 192 | 76188614.4 | 396815.7 | 88 | 34919782 | 68 | 26983468 | 20 | 7936314 | 104
|  |  |  | b | For Approach Viaduct | [11 empty] | 0
|  |  |  | 1 | Casting of Girders in the precast yard | Nos | 40% | 108 | 171424382.4 | 1587262.8 | 49 | 77775877 | 45 | 71426826 | 4 | 6349051 | 59
|  |  |  | 2 | Erection of Girders at site | Nos | 10% | 108 | 42856095.6 | 396815.7 | 0 | 0 | 0 | 0 | 0 | 0 | 108
|  |  |  | 505 | Procurement, testing and supply of post tensioning material to site | LS | 3.4% |  | 132271900 | [7 empty] | 0
|  |  |  | a | For Wetland Viaduct | [11 empty] | 0
|  |  |  | 1 | Supply of material at site for Girders | MT | 25% | 330.24 | 42327008 | 128170.4457 | 330.24 | 42327008 | 330.24 | 42327008 | 0 | 0 | 0
|  |  |  | 2 | Testing of Material | MT | 15% | 330.24 | 25396204.8 | 76902.2674 | 330.24 | 25396205 | 330.24 | 25396205 | 0 | 0 | 0
|  |  |  | 3 | Final stressing of Girders at site | Nos | 10% | 192 | 16930803.2 | 88181.2667 | 113 | 9964483 | 109 | 9611758 | 4 | 352725 | 79
|  |  |  | b | For Approach Viaduct | [11 empty] | 0
|  |  |  | 1 | Supply of material at site for Girders | MT | 25% | 185.76 | 23808942 | 128170.4457 | 152.054 | 19488829 | 152.054 | 19488829 | 0 | 0 | 33.706
|  |  |  | 2 | Testing of Material | MT | 15% | 185.76 | 14285365.2 | 76902.2674 | 152.054 | 11693297 | 152.054 | 11693297 | 0 | 0 | 33.706
|  |  |  | 3 | Final stressing of Girders at site | Nos | 10% | 108 | 9523576.8 | 88181.2667 | 22 | 1939988 | 17 | 1499082 | 5 | 440906 | 86
|  |  |  | 506 | Installation of PSC Box girders/I-Girders at site including installation of Post Tensioning for completion of deck | LS | 16.2% |  | 630236700 | [7 empty] | 0
|  |  |  | a | For Wetland Viaduct | [11 empty] | 0
|  |  |  | 1 | Casting of Deck Panel | Span | 15% | 48 | 126047340 | 2625986.25 | 26 | 68275643 | 19 | 49893739 | 7 | 18381904 | 22
|  |  |  | 2 | Deck Panel Erection | Span | 7.5% | 48 | 63023670 | 1312993.125 | 12 | 15755918 | 9 | 11816938 | 3 | 3938980 | 36
|  |  |  | 3 | Deck Slab Casting | Span | 27.5% | 48 | 231086790 | 4814308.125 | 12 | 57771698 | 9 | 43328773 | 3 | 14442925 | 36
|  |  |  | b | For Approach Viaduct | [11 empty] | 0
|  |  |  | 1 | Casting of Deck Panel | Span | 15% | 24 | 63023670 | 2625986.25 | 4 | 10503945 | 4 | 10503945 | 0 | 0 | 20
|  |  |  | 2 | Deck Panel Erection | Span | 7.5% | 24 | 31511835 | 1312993.125 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | 3 | Deck Slab Casting | Span | 27.5% | 24 | 115543395 | 4814308.125 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | 507 | Installation of bearings and expansion joints | LS | 0.7% |  | 27232450 | [7 empty] | 0
|  |  |  | a | For Wetland Viaduct | [11 empty] | 0
|  |  |  | 1 | Bearings - Material Testing and Procurement | Nos | 7.5% | 128 | 2513764.6154 | 19638.7861 | 128 | 2513765 | 128 | 2513765 | 0 | 0 | 0
|  |  |  | 2 | Bearings - Installation | Nos | 2.5% | 128 | 837921.5385 | 6546.262 | 58 | 379683 | 50 | 327313 | 8 | 52370 | 70
|  |  |  | b | For Approach Viaduct | [11 empty] | 0
|  |  |  | 1 | Bearings - Material Testing and Procurement | Nos | 7.5% | 80 | 1571102.8846 | 19638.7861 | 0 | 0 | 0 | 0 | 0 | 0 | 80
|  |  |  | 2 | Bearings - Installation | Nos | 2.5% | 80 | 523700.9615 | 6546.262 | 0 | 0 | 0 | 0 | 0 | 0 | 80
|  |  |  | c | For Wetland Viaduct | [11 empty] | 0
|  |  |  | 1 | Expansion Joints - Material Testing and Procurement | Nos | 30% | 20 | 11671050 | 583552.5 | 0 | 0 | 0 | 0 | 0 | 0 | 20
|  |  |  | 2 | Expansion Joints - Installation | Nos | 10% | 20 | 3890350 | 194517.5 | 0 | 0 | 0 | 0 | 0 | 0 | 20
|  |  |  | d | For Approach Viaduct | [11 empty] | 0
|  |  |  | 1 | Expansion Joints - Material Testing and Procurement | Nos | 30% | 8 | 4668420 | 583552.5 | 0 | 0 | 0 | 0 | 0 | 0 | 8
|  |  |  | 2 | Expansion Joints - Installation | Nos | 10% | 8 | 1556140 | 194517.5 | 0 | 0 | 0 | 0 | 0 | 0 | 8
|  |  |  | 508 | Construction of Crash Barriers and Hand Railings | LS | 1.2% |  | 46684200 | [7 empty] | 0
|  |  |  | a | For Wetland Viaduct | [11 empty] | 0
|  |  |  | 1 | Crash Barrier | Rmt | 35% | 3456 | 21785960 | 6303.8079 | 0 | 0 | 0 | 0 | 0 | 0 | 3456
|  |  |  | 2 | Hand Railing | Rmt | 15% | 1728 | 9336840 | 5403.2639 | 0 | 0 | 0 | 0 | 0 | 0 | 1728
|  |  |  | b | For Approach Viaduct | [11 empty] | 0
|  |  |  | 1 | Crash Barrier | Rmt | 35% | 1728 | 10892980 | 6303.8079 | 0 | 0 | 0 | 0 | 0 | 0 | 1728
|  |  |  | 2 | Hand Railing | Rmt | 15% | 864 | 4668420 | 5403.2639 | 0 | 0 | 0 | 0 | 0 | 0 | 864
|  |  |  | 509 | Completion of bridge pavement | LS | 0.5% |  | 19451750 | [7 empty] | 0
|  |  |  | a | For Wetland Viaduct | [11 empty] | 0
|  |  |  | 1 | Water Proofing | Rmt | 20% | 1728 | 5187133.3333 | 3001.8133 | 0 | 0 | 0 | 0 | 0 | 0 | 1728
|  |  |  | 2 | 1st Layer of Wearing Course | Rmt | 10% | 1728 | 2593566.6667 | 1500.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 1728
|  |  |  | 3 | Final Layer of Wearing Course | Rmt | 20% | 1728 | 5187133.3333 | 3001.8133 | 0 | 0 | 0 | 0 | 0 | 0 | 1728
|  |  |  | b | For Approach Viaduct | [11 empty] | 0
|  |  |  | 1 | Water Proofing | Rmt | 20% | 864 | 2593566.6667 | 3001.8133 | 0 | 0 | 0 | 0 | 0 | 0 | 864
|  |  |  | 2 | 1st Layer of Wearing Course | Rmt | 10% | 864 | 1296783.3333 | 1500.9066 | 0 | 0 | 0 | 0 | 0 | 0 | 864
|  |  |  | 3 | Final Layer of Wearing Course | Rmt | 20% | 864 | 2593566.6667 | 3001.8133 | 0 | 0 | 0 | 0 | 0 | 0 | 864
|  |  |  | 510 | Completion of bridge lighting and electrical works | LS | 0.6% |  | 23342100 | [7 empty] | 0
|  |  |  | a | For Wetland Viaduct | [11 empty] | 0
|  |  |  | 1 | Material Procurement | Span | 40% | 48 | 12449120 | 259356.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 48
|  |  |  | 2 | Installation | Span | 7.5% | 48 | 2334210 | 48629.375 | 0 | 0 | 0 | 0 | 0 | 0 | 48
|  |  |  | 3 | Testing of Material | Span | 2.5% | 48 | 778070 | 16209.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 48
|  |  |  | b | For Approach Viaduct | [11 empty] | 0
|  |  |  | 1 | Material Procurement | Span | 40% | 24 | 6224560 | 259356.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | 2 | Installation | Span | 7.5% | 24 | 1167105 | 48629.375 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | 3 | Testing of Material | Span | 2.5% | 24 | 389035 | 16209.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | 511 | Completion of balance ancillary and river training work, Embankment/ abutment protection works and other miscellaneous works for handing over | LS | 0.5% |  | 19451750 | [7 empty] | 0
|  |  |  | a | River Training Works | Rmt | 100% | 1000 | 19451750 | 19451.75 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Wetland and Approach Viaduct Works | [11 empty] | 2928149367 |  | 2834648310 |  | 93501057 | 0
0
Schedule 6 | Underpass Works | 2.5% | 670750000 | 601 | Subbase Course & Base Course | LS | 1% |  | 6707500 | [7 empty] | 0
|  |  |  | a | Subbase Course | Rmt | 50% | 60 | 3353750 | 55895.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 60
|  |  |  | b | Base Course | Rmt | 50% | 60 | 3353750 | 55895.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 60
|  |  |  | 602 | Bituminous Base Course | LS | 0.1% |  | 670750 | [7 empty] | 0
|  |  |  | a | Bituminous Base Course | Rmt | 100% | 60 | 670750 | 11179.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 60
|  |  |  | 603 | Construction of foundation | LS | 49% |  | 328667500 | [7 empty] | 0
|  |  |  | a | Construction of Piles | Nos. | 54% | 16 | 177480450 | 11092528.125 | 16 | 177480450 | 16 | 177480450 | 0 | 0 | 0
|  |  |  | b | Construction of Raft | Nos. | 36% | 2 | 118320300 | 59160150 | 2 | 118320300 | 2 | 118320300 | 0 | 0 | 0
|  |  |  | c | Construction of Pile Cap | Nos. | 10% | 4 | 32866750 | 8216687.5 | 4 | 32866750 | 4 | 32866750 | 0 | 0 | 0
|  |  |  | 604 | Construction of sub-structure; abutment/ piers/ lower pylon | LS | 37.8% |  | 253543500 | [7 empty] | 0
|  |  |  | a | Construction of Abutment / Pier | Nos. | 48% | 2 | 121700880 | 60850440 | 2 | 121700880 | 2 | 121700880 | 0 | 0 | 0
|  |  |  | b | Construction of Wall | Nos. | 32% | 4 | 81133920 | 20283480 | 4 | 81133920 | 4 | 81133920 | 0 | 0 | 0
|  |  |  | c | Construction of Abutment / Pier cap | Nos. | 20% | 2 | 50708700 | 25354350 | 2 | 50708700 | 2 | 50708700 | 0 | 0 | 0
|  |  |  | 605 | Procurement, testing and supply of post tensioning material to site | LS | 0.9% |  | 6036750 | [7 empty] | 0
|  |  |  | a | Supply of material at site for each span | MT | 50% | 32 | 3018375 | 94324.2188 | 0 | 0 | 0 | 0 | 0 | 0 | 32
|  |  |  | b | Testing of Material | MT | 30% | 32 | 1811025 | 56594.5312 | 0 | 0 | 0 | 0 | 0 | 0 | 32
|  |  |  | c | Final stressing of each span at site | Span | 20% | 6 | 1207350 | 201225 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  |  |  | 606 | Construction of superstructure | LS | 10.1% |  | 67745750 | [7 empty] | 0
|  |  |  | a | Casting of Girders at Casting Yard | Nos | 40% | 8 | 27098300 | 3387287.5 | 0 | 0 | 0 | 0 | 0 | 0 | 8
|  |  |  | b | Erection of Girders | Nos | 20% | 8 | 13549150 | 1693643.75 | 0 | 0 | 0 | 0 | 0 | 0 | 8
|  |  |  | c | Completion of I girder Slab | Span | 24% | 2 | 16258980 | 8129490 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | d | Completion of Box Slab | Span | 16% | 4 | 10839320 | 2709830 | 4 | 10839320 | 4 | 10839320 | 0 | 0 | 0
|  |  |  | 607 | Installation of bearings and expansion joints | LS | 0.7% |  | 4695250 | [7 empty] | 0
|  |  |  | a | Bearings - Material Testing and Procurement | Nos. | 15% | 16 | 704287.5 | 44017.9688 | 0 | 0 | 0 | 0 | 0 | 0 | 16
|  |  |  | b | Bearings - Installation | Nos. | 5% | 16 | 234762.5 | 14672.6562 | 0 | 0 | 0 | 0 | 0 | 0 | 16
|  |  |  | c | Expansion Joints - Material Testing and Procurement | Nos. | 60% | 4 | 2817150 | 704287.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  |  |  | d | Expansion Joints - Installation | Nos. | 20% | 4 | 939050 | 234762.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  |  |  | 608 | Construction of Crash Barriers & Hand Railing | LS | 0.4% |  | 2683000 | [7 empty] | 0
|  |  |  | a | Crash Barrier | Span | 70% | 6 | 1878100 | 313016.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  |  |  | b | Hand Railing | Span | 30% | 6 | 804900 | 134150 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Underpass Works | [11 empty] | 593050320 |  | 593050320 |  | 0 | 0
0
Schedule 7 | Approach road Works | 6% | 1609800000 | 701 | Earthwork up to top of the sub-grade | Kms | 24.1% |  | 387961800 | [7 empty] | 0
|  |  |  | a | Embankment | Kms | 80% | 14.5032 | 310369440 | 21400066.1923 | 7.602 | 162683303 | 7.602 | 162683303 | 0 | 0 | 6.9012
|  |  |  | b | Subgrade | Kms | 20% | 14.5032 | 77592360 | 5350016.5481 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
|  |  |  | 702 | Sub Base Course | Kms | 7.7% |  | 123954600 | [7 empty] | 0
|  |  |  | a | Sub Base Course | Kms | 100% | 14.5032 | 123954600 | 8546706.9336 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
|  |  |  | 703 | Non-Bituminous Base Course | Kms | 8.2% |  | 132003600 | [7 empty] | 0
|  |  |  | a | 1st Layer | Kms | 50% | 14.5032 | 66001800 | 4550843.9517 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
|  |  |  | b | Final Layer | Kms | 50% | 14.5032 | 66001800 | 4550843.9517 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
|  |  |  | 704 | Bituminous Base Course | Kms | 12.3% |  | 198005400 | [7 empty] | 0
|  |  |  | a | 1st Layer | Kms | 60% | 14.5032 | 118803240 | 8191519.113 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
|  |  |  | b | Final Layer | Kms | 40% | 14.5032 | 79202160 | 5461012.742 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
|  |  |  | 705 | Wearing Coat | Kms | 5.5% |  | 88539000 | [7 empty] | 0
|  |  |  | a | Wearing Coat | Kms | 100% | 14.5032 | 88539000 | 6104790.6669 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
|  |  |  | 706 | Construction of earth retaining structures, culvert & minor structures | LS | 33.8% |  | 544112400 | [7 empty] | 0
|  |  |  | a | Completion of the main structural works excluding finishing works - Culverts | Nos | 20% | 18 | 108822480 | 6045693.3333 | 9 | 54411240 | 8.5 | 51388393 | 0.5 | 3022847 | 9
|  |  |  | b | Construction of Retaining wall | Rmt | 20% | 4200 | 108822480 | 25910.1143 | 0 | 0 | 0 | 0 | 0 | 0 | 4200
|  |  |  | c | Construction of Toe wall | Rmt | 20% | 1000 | 108822480 | 108822.48 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
|  |  |  | d | Construction of Road Side Drainage | Rmt | 20% | 800 | 108822480 | 136028.1 | 0 | 0 | 0 | 0 | 0 | 0 | 800
|  |  |  | e | Completion of all finishing works such as parapet wall, return walls, crash barrier etc. | Nos | 20% | 18 | 108822480 | 6045693.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 18
|  |  |  | 707 | Completion of other balance works e.g. marking, signage’s, lighting etc | LS | 8.4% |  | 135223200 | [7 empty] | 0
|  |  |  | a | Road Marking | Kms | 30% | 14.5032 | 40566960 | 2797104.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
|  |  |  | b | Traffic Signages | Kms | 30% | 14.5032 | 40566960 | 2797104.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
|  |  |  | c | Lighting - Installation | Kms | 30% | 14.5032 | 40566960 | 2797104.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
|  |  |  | d | Lighting - Testing | Kms | 10% | 14.5032 | 13522320 | 932368.0291 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5032
Approach road Works | [11 empty] | 217094543 |  | 214071696 |  | 3022847 | 0
0
Schedule 8 | Provisional Sum |  | 55400000 | 801 | Institutional Strengthening, Trainings and Capacity Building as per Employers Requirement, Seminar, Workshop, Exhibitions | LS | 100% |  | 50400000 | [7 empty] | 0
|  |  |  | a | Training & Capacity Building | Nos | 40% | 5 | 20160000 | 4032000 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  |  |  | b | International Seminar / Exposure Trip | Nos | 40% | 2 | 20160000 | 10080000 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | c | Institutional Strengthening and Capacity Building in Design & Planning | [11 empty] | 0
|  |  |  | 1 | Laptop | Nos | 5% | 10 | 2520000 | 252000 | 0 | 0 | 0 | 0 | 0 | 0 | 10
|  |  |  | 2 | Software | Nos | 7% | 14 | 3528000 | 252000 | 0 | 0 | 0 | 0 | 0 | 0 | 14
|  |  |  | 3 | Printer | Nos | 3% | 1 | 1512000 | 1512000 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | 4 | Plotter | Nos | 5% | 1 | 2520000 | 2520000 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | 802 | Dispute Board (DB) cost and expenses | LS | 100% |  | 5000000 | [7 empty] | 0
|  |  |  | a | Dispute Board | LS | 100% | 1 | 5000000 | 5000000 | 0.32327 | 1616348 | 0.32327 | 1616348 | 0 | 0 | 0.67673
Provisional Sum | [11 empty] | 1616348 |  | 1616348 |  | 0
Total Amount (Excl. Provisional Sum) | [8 empty] | 26885400000 |  |  | 20327140948 |  | 12995429147 |  | 7331711801
Total Amount of Provisional Sum | [11 empty] | 1616348 |  | 1616348 |  | 0
Total Amount | [11 empty] | 20328757296 |  | 12997045495 |  | 7331711801 | 51.22
[12 empty] | 17227760420.339 |  |  | Net Off GST | 6213315085.5932 | 37.3906

## MB Details
| Item No. | page No | Item Description | UoM | Location | Executed Quantity | RFI No. / Letter No. | Date | IPC No. | Signed date | Remarks
| 406.a / 407.c | 75 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/244 | 2025-10-10 | IPC - 34 | 2025-10-12 | P17-BP-S32a-O | 2
Installation of PSC Box girders/I-Girders at site including installation of Post Tensioning for completion of deck | 506.a.1 | 75 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4959 | 2026-06-20 | IPC - 34 | 2026-06-20 | PL10 to PL11 | 0
Construction of sub- structure; abutment/piers / lower pylon & Construction of pier- cap/ pier table | 502 & 503.a.2 | 76 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Str/4967 | 2026-06-20 | IPC - 34 | 2026-06-26 | Km 10+636 - PR1 - Piercap | 6
Procurement, testing and supply of post tensioning material to site | 505.a.3 | 76 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/5077 | 2026-07-03 | IPC - 34 | 2026-07-03 | WV2-P3-P4-G2 | 0
| 506.a.2 | 77 | For Wetland Viaduct - Deck Panel Erection | Span | Sualkuchi | 3 | MPSB/Str/5079 | 2026-07-03 | IPC - 34 | 2026-07-03 | PL9 to PL12 | 0
Installation of bearings and expansion joints | 507.a.2 | 77 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3725 | 2026-07-03 | IPC - 34 | 2026-07-03 | PR20 | 0
| 506.a.1 | 77 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5081 | 2026-07-03 | IPC - 34 | 2026-07-04 | PL1 to PL2 | 1
| 507.a.2 | 78 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3726 | 2026-07-03 | IPC - 34 | 2026-07-07 | PR21 | 4
| 505.a.3 | 78 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/5092 | 2026-07-07 | IPC - 34 | 2026-07-08 | WV2-P3-P4-G3 | 1
Construction of sub- structure; abutment/ piers / lower pylon | 403.a | 78 | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 2 | MPSB/Str/5108 | 2026-07-09 | IPC - 34 | 2026-07-11 | P7 - Lower Pylon - 2nd Lift | 2
| 403.a | 79 | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 2.115 | MPSB/Str/5101 | 2026-07-09 | IPC - 34 | 2026-07-11 | P25 - Lower Pylon - 2nd Lift | 2
| 406.a / 407.c | 79 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2089 | 2026-07-09 | IPC - 34 | 2026-07-11 | P16-KS-S09-M | 2
| 406.a / 407.c | 79 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2090 | 2026-07-09 | IPC - 34 | 2026-07-12 | P9-BP-S04a-O | 3
| 406.a / 407.c | 79 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2087 | 2026-07-08 | IPC - 34 | 2026-07-12 | P15-BP-S10-O | 4
Construction of PSC Box girders/I-Girders in casting yard | 504.a.1 | 80 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5105 | 2026-07-09 | IPC - 34 | 2026-07-12 | WV1-P1-P2-G3 | 3
| 406.a / 407.c | 80 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2101 | 2026-07-10 | IPC - 34 | 2026-07-13 | P9-KS-S32-O | 3
Construction of foundation | 501.b.3 | 81 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/5098 | 2026-07-08 | IPC - 34 | 2026-07-13 | Km 9+352 - PL34 - Pilecap | 5
| 406.a / 407.c / 408.c | 81 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2107 | 2026-07-10 | IPC - 34 | 2026-07-13 | P21-KS-S33-O© | 3
| 406.a / 407.c / 408.c | 81 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2113 | 2026-07-11 | IPC - 34 | 2026-07-14 | P21-BP-S25a-O© | 3
| 501.b.2 | 81 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 1.05 | MPSB/Str/5134 | 2026-07-13 | IPC - 34 | 2026-07-14 | P4 - 18th Lift | 1
| 507.a.2 | 82 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 4 | MPSB/Sur/3761 | 2026-07-14 | IPC - 34 | 2026-07-14 | PR18 | 0
| 406.a / 407.c / 408.c | 82 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2139 | 2026-07-15 | IPC - 34 | 2026-07-15 | P16-KS-S10-M© | 0
| 502 & 503.a.2 | 82 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Str/5112 | 2026-07-10 | IPC - 34 | 2026-07-15 | Km 10+230 - PL0 - Piercap | 5
| 505.b.3 | 83 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/5148 | 2026-07-15 | IPC - 34 | 2026-07-15 | SAV-P2-P3-G1 | 0
| 505.b.3 | 83 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/5149 | 2026-07-15 | IPC - 34 | 2026-07-15 | SAV-P2-P3-G2 | 0
| 506.a.1 | 83 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5135 | 2026-07-14 | IPC - 34 | 2026-07-15 | PL0 to PL1 | 1
| 406.a / 407.c | 84 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2109 | 2026-07-11 | IPC - 34 | 2026-07-15 | P16-BP-S17-M | 4
| 406.a / 407.c | 84 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2118 | 2026-07-13 | IPC - 34 | 2026-07-16 | P22-BP-S04-E | 3
| 406.a / 407.c / 408.c | 84 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2116 | 2026-07-13 | IPC - 34 | 2026-07-16 | P15-BP-S11-O© | 3
| 502 & 503.a.2 | 84 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Str/5118 | 2026-07-11 | IPC - 34 | 2026-07-16 | Km 10+230 - PR0 - Piercap | 5
| 504.b.1 | 85 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/5130 | 2026-07-13 | IPC - 34 | 2026-07-16 | SAV-P5-P6-G8 | 3
| 506.a.1 | 85 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5144 | 2026-07-15 | IPC - 34 | 2026-07-16 | PR19 to PR20 | 1
Construction of earth retaining structures, culvert & minor structures | 706.a | 86 | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 0.5 | MPSB/Str/5143 | 2026-07-14 | IPC - 34 | 2026-07-16 | Km 4+154 | 2
| 403.a | 86 | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 0.63 | MPSB/Str/5128 | 2026-07-13 | IPC - 34 | 2026-07-17 | P29 - Lower Pylon - Starter | 4
| 504.a.2 | 86 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5091 | 2026-07-07 | IPC - 34 | 2026-07-17 | WV2-P15-P16 (G5 to G8) | 10
| 406.a / 407.c | 87 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2133 | 2026-07-14 | IPC - 34 | 2026-07-17 | P9-BP-S05a-O | 3
| 406.a / 407.c | 87 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2138 | 2026-07-15 | IPC - 34 | 2026-07-17 | P21-KS-S34-O | 2
| 406.a / 407.c | 87 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2154 | 2026-07-17 | IPC - 34 | 2026-07-18 | P22-BP-S05-E | 1
| 406.a / 407.c / 408.c | 87 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2137 | 2026-07-15 | IPC - 34 | 2026-07-18 | P21-BP-S21a-O© | 3
| 504.a.1 | 88 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5138 | 2026-07-14 | IPC - 34 | 2026-07-18 | WV1-P1-P2-G2 | 4
| 403.a | 88 | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 4.329 | MPSB/Str/5151 | 2026-07-15 | IPC - 34 | 2026-07-19 | P8 - Lower Pylon - 7th Lift | 4
| 406.a / 407.c / 408.c | 88 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2140 | 2026-07-15 | IPC - 34 | 2026-07-19 | P9-KS-S33-O© | 4
| 406.a / 407.c | 89 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2149 | 2026-07-17 | IPC - 34 | 2026-07-19 | P16-BP-S18-M | 2
| 504.b.1 | 89 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/5160 | 2026-07-18 | IPC - 34 | 2026-07-19 | SAV-P5-P6-G7 | 1
| 406.a / 407.c | 89 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2159 | 2026-07-18 | IPC - 34 | 2026-07-20 | P21-BP-S26a-O | 2
| 406.a / 407.c | 90 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2144 | 2026-07-16 | IPC - 34 | 2026-07-20 | P24-KS-S01-M | 4
| 504.a.1 | 90 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5161 | 2026-07-18 | IPC - 34 | 2026-07-20 | WV1-P2-P3-G2 | 2
| 504.a.2 | 90 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5156 | 2026-07-17 | IPC - 34 | 2026-07-20 | WV2-P6-P7 (G1 to G4) | 3
| 502 & 503.b.1 | 91 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Str/5158 | 2026-07-17 | IPC - 34 | 2026-07-21 | Km 9+352 - PL34 - Pier | 4
| 406.a / 407.c | 91 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2156 | 2026-07-18 | IPC - 34 | 2026-07-21 | P15-BP-S12-O | 3
| 406.a / 407.c | 91 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2166 | 2026-07-20 | IPC - 34 | 2026-07-22 | P9-BP-S06a-O | 2
| 406.a / 407.c | 91 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2167 | 2026-07-20 | IPC - 34 | 2026-07-22 | P16-KS-S11-M | 2
| 504.a.1 | 92 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5177 | 2026-07-21 | IPC - 34 | 2026-07-22 | WV1-P2-P3-G8 | 1
| 504.b.1 | 92 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/5182 | 2026-07-22 | IPC - 34 | 2026-07-22 | SAV-P5-P6-G6 | 0
| 403.a | 92 | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 2.115 | MPSB/Str/5176 | 2026-07-21 | IPC - 34 | 2026-07-23 | P29 - Lower Pylon - 1st Lift | 2
| 406.a / 407.c | 93 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2171 | 2026-07-21 | IPC - 34 | 2026-07-23 | P9-KS-S34-O | 2
| 504.a.1 | 93 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5179 | 2026-07-21 | IPC - 34 | 2026-07-23 | WV1-P1-P2-G1 | 2
| 406.a / 407.c | 93 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2183 | 2026-07-23 | IPC - 34 | 2026-07-24 | P9-BP-S07a-O | 1
| 406.a / 407.c / 408.c | 94 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2179 | 2026-07-22 | IPC - 34 | 2026-07-24 | P21-BP-S27a-O© | 2
| 406.a / 407.c / 408.c | 94 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2192 | 2026-07-23 | IPC - 34 | 2026-07-25 | P15-BP-S13-O© | 2
| 406.a / 407.c | 94 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2178 | 2026-07-22 | IPC - 34 | 2026-07-25 | P22-BP-S06-E | 3
| 505.b.3 | 94 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/5191 | 2026-07-25 | IPC - 34 | 2026-07-25 | SAV-P1R-P2R-G2 | 0
| 505.b.3 | 95 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/5192 | 2026-07-25 | IPC - 34 | 2026-07-25 | SAV-P1R-P2R-G3 | 0
| 502 & 503.b.1 | 95 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Str/5184 | 2026-07-23 | IPC - 34 | 2026-07-26 | Km 9+316 - PR33 - Pier | 3
| 504.a.1 | 95 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5186 | 2026-07-23 | IPC - 34 | 2026-07-26 | WV1-P2-P3-G7 | 3
| 504.a.1 | 95 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5189 | 2026-07-24 | IPC - 34 | 2026-07-26 | WV1-P2-P3-G3 | 2
| 406.a / 407.c | 96 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2196 | 2026-07-25 | IPC - 34 | 2026-07-27 | P21-BP-S28a-O | 2
| 406.a / 407.c | 96 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2195 | 2026-07-24 | IPC - 34 | 2026-07-27 | P24-KS-S02-M | 3
| 504.a.2 | 96 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5188 | 2026-07-24 | IPC - 34 | 2026-07-27 | WV2-P5-P6 (G1 to G4) | 3
| 504.b.1 | 97 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/5194 | 2026-07-25 | IPC - 34 | 2026-07-27 | SAV-P5-P6-G5 | 2
| 406.a / 407.c / 408.c | 97 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2182 | 2026-07-23 | IPC - 34 | 2026-07-28 | P16-KS-S12-M© | 5
| 505.b.3 | 97 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/5211 | 2026-07-28 | IPC - 34 | 2026-07-28 | SAV-P1R-P2R-G1 | 0
Construction of foundation | 402.c | 98 | Well Cap | Nos. | Sualkuchi | 1 | MPSB/Str/5219 | 2026-07-29 | IPC - 34 | 2026-07-29 | P24 - Well Cap | 0
| 406.a / 407.c | 98 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2211 | 2026-07-27 | IPC - 34 | 2026-07-29 | P15-BP-S14-O | 2
| 406.a / 407.c / 408.c | 98 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2214 | 2026-07-28 | IPC - 34 | 2026-07-29 | P21-BP-S29a-O© | 1
| 504.a.1 | 99 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5222 | 2026-07-29 | IPC - 34 | 2026-07-29 | WV1-P0-P1-G7 | 0
| 506.a.1 | 99 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5213 | 2026-07-28 | IPC - 34 | 2026-07-29 | PR18 to PR19 | 1
| 506.a.1 | 99 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5212 | 2026-07-28 | IPC - 34 | 2026-07-29 | PR17 to PR18 | 1
| 506.a.3 | 99 | For Wetland Viaduct - Deck Slab casting | Span | Sualkuchi | 3 | MPSB/Str/5197 | 2026-07-25 | IPC - 34 | 2026-07-29 | PL9 to PL12 | 4
| 403.a | 100 | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 5.38 | MPSB/Str/5235 | 2026-07-30 | IPC - 34 | 2026-07-30 | P26 - Lower Pylon - 4th Lift | 0
| 403.a | 100 | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 4 | MPSB/Str/5231 | 2026-07-30 | IPC - 34 | 2026-07-30 | P29 - Lower Pylon - 2nd Lift | 0
| 406.a / 407.c | 100 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2218 | 2026-07-28 | IPC - 34 | 2026-07-30 | P9-BP-S08a-O | 2
| 406.a / 407.c | 100 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2210 | 2026-07-27 | IPC - 34 | 2026-07-30 | P16-KS-S13-M | 3
| 504.a.1 | 101 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5216 | 2026-07-28 | IPC - 34 | 2026-07-30 | WV1-P1-P2-G4 | 2
| 504.a.1 | 101 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5136 | 2026-07-14 | IPC - 34 | 2026-07-16 | WV1-P2-P3-G4 | 2
| 504.a.2 | 101 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5208 | 2026-07-28 | IPC - 34 | 2026-07-30 | WV2-P4-P5 (G1 to G4) | 2
| 505.a.3 | 102 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/5225 | 2026-07-29 | IPC - 34 | 2026-07-30 | WV2-P3-P4-G1 | 1
| 505.a.3 | 102 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/5226 | 2026-07-29 | IPC - 34 | 2026-07-30 | WV2-P1-P2-G1 | 1
Final Technical Design of the approach formation, retaining structures, drainage system, bridges, major and /or minor structures and miscellaneous work | 204.e.ii.3 | 102 | Approach Viaduct - Substructure - Issue of GFC Drawings | Nos. |  | 0.25 | HBT/1624/SO/DGV/2026/1771 | 2026-07-31 | IPC - 34 | 2026-07-31 | 2 / 16 Nos. - Approved - SAV - P1R & P2R, NAV - P32R & P33R - Balance 50% released | 0
| 406.a / 407.c / 408.c | 103 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2232 | 2026-07-30 | IPC - 34 | 2026-07-31 | P15-BP-S15-O© | 1
| 406.a / 407.c / 408.c | 103 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2231 | 2026-07-30 | IPC - 34 | 2026-07-31 | P15-KS-S09a-O© | 1
| 406.a / 407.c / 408.c | 103 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2244 | 2026-07-31 | IPC - 34 | 2026-07-31 | P16-KS-S14-M© | 0
| 406.a / 407.c / 408.c | 103 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2238 | 2026-07-31 | IPC - 34 | 2026-07-31 | P19-KS-S09a-O© | 0
| 406.a / 407.c / 408.c | 103 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2239 | 2026-07-31 | IPC - 34 | 2026-07-31 | P21-BP-S31a-O© | 0
| 406.a / 407.c | 104 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2246 | 2026-07-31 | IPC - 34 | 2026-07-31 | P15-KS-S10a-O | 0
| 406.a / 407.c | 104 | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2243 | 2026-07-31 | IPC - 34 | 2026-07-31 | P15-BP-S22-O | 0
| 406.a / 407.c | 104 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2235 | 2026-07-30 | IPC - 34 | 2026-07-31 | P21-BP-S30a-O | 1
| 406.a / 407.c | 104 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2225 | 2026-07-29 | IPC - 34 | 2026-07-31 | P24-KS-S03-M | 2
| 406.a / 407.c | 104 | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2241 | 2026-07-31 | IPC - 34 | 2026-07-31 | P24-KS-S04-M | 0
| 502 & 503.b.2 | 105 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Str/5228 | 2026-07-29 | IPC - 34 | 2026-07-31 | Km 9+424 - PL36 - Piercap | 2
| 504.a.1 | 105 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5224 | 2026-07-29 | IPC - 34 | 2026-07-31 | WV1-P0-P1-G3 | 2
| 504.a.1 | 105 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5243 | 2026-07-31 | IPC - 34 | 2026-07-31 | WV1-P2-P3-G6 | 0
| 504.a.1 | 105 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5247 | 2026-07-31 | IPC - 34 | 2026-07-31 | WV1-P2-P3-G1 | 0
| 504.a.1 | 105 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5249 | 2026-07-31 | IPC - 34 | 2026-07-31 | WV1-P2-P3-G5 | 0
| 504.a.1 | 106 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5251 | 2026-07-31 | IPC - 34 | 2026-07-31 | WV2-P10-P11-G8 | 0
| 504.a.2 | 106 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5229 | 2026-07-30 | IPC - 34 | 2026-07-31 | WV2-P3-P4 (G1 to G4) | 1
| 506.a.1 | 106 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5254 | 2026-07-31 | IPC - 34 | 2026-07-31 | PR16 to PR17 | 0
Procurement, testing and supply of Stay Cables to site | 408.b | 107 | Testing of Material | MT |  | 354.343 | As per Annexures |  | IPC - 34
187.82

## Schedule 1
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
Period of bill : 1st Jul'26 to 31st Jul'26
Schedule 1 - Preliminaries and General Items | [7 empty] | IPC - 34
Measurement Sheet
Item No. | Item Description | UoM | Location | Executed Quantity | RFI No. / Letter No. / Period | Date | Bill No. | Remarks
101 | Provision (construction) of office facilities for the Employer
101.a | Foundation | Nos. | Palashbari | 0.5 | MPSB/Temp/2 | 2024-06-07 | IPC - 02
101.a | Foundation | Nos. | Palashbari | 0.5 | MPSB/Temp/4 | 2024-06-08 | IPC - 02
101.a | Foundation | Nos. | Sualkuchi | 0.5 | MPSB/Temp/15 | 2024-06-13 | IPC - 02
101.a | Foundation | Nos. | Sualkuchi | 0.5 | MPSB/Temp/21 | 2024-06-15 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
101.b | Plinth | Nos. | Palashbari | 1 | MPSB/Temp/5 | 2024-06-10 | IPC - 02
101.b | Plinth | Nos. | Sualkuchi | 1 | MPSB/Temp/39 | 2024-07-12 | IPC - 03
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
101.c | Walls | Nos. | Palashbari | 1 | MPSB/Temp/11 | 2024-06-12 | IPC - 02
101.c | Walls | Nos. | Sualkuchi | 1 | MPSB/Temp/51 | 2024-07-31 | IPC - 03
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
101.d | Roof | Nos. | Palashbari | 1 | MPSB/Temp/18 | 2024-06-14 | IPC - 02
101.d | Roof | Nos. | Sualkuchi | 1 | MPSB/Temp/52 | 2024-07-31 | IPC - 03
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
101.e | Flooring | Nos. | Palashbari | 1 | MPSB/Temp/24 | 2024-06-16 | IPC - 02
101.e | Flooring | Nos. | Sualkuchi | 1 | MPSB/Temp/62 | 2024-07-31 | IPC - 03
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
101.f.i | Finishing Works - Electrical & Sanitary Works | Nos. | Palashbari | 1 | MPSB/Temp/43 | 2024-07-19 | IPC - 03
101.f.i | Finishing Works - Electrical & Sanitary Works | Nos. | Sualkuchi | 0.9 | MPSB/Temp/64 A | 2024-08-22 | IPC - 04
101.f.i | Finishing Works - Electrical & Sanitary Works | Nos. | Sualkuchi | 0.1 | MPSB/Temp/87 | 2024-09-28 | IPC - 05
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
101.f.ii.1 | Finishing Works - Office Furniture - Executive Office Desk | Nos. | Palashbari | 4 | MPSB/Temp/48 | 2024-07-29 | IPC - 03
101.f.ii.1 | Finishing Works - Office Furniture - Executive Office Desk | Nos. | Sualkuchi | 4 | MPSB/Temp/74 | 2024-08-29 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 8
| Paid upto previous Bill | Nos. |  | 8
| To be paid in this Bill | Nos. |  | 0
101.f.ii.2 | Finishing Works - Office Furniture - Executive Chairs | Nos. | Palashbari | 4 | MPSB/Temp/48 | 2024-07-29 | IPC - 03
101.f.ii.2 | Finishing Works - Office Furniture - Executive Chairs | Nos. | Sualkuchi | 4 | MPSB/Temp/74 | 2024-08-29 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 8
| Paid upto previous Bill | Nos. |  | 8
| To be paid in this Bill | Nos. |  | 0
101.f.ii.3 | Finishing Works - Office Furniture - Visitors Chairs | Nos. | Palashbari | 20 | MPSB/Temp/48 | 2024-07-29 | IPC - 03
| Cumulative paid upto this Bill | Nos. |  | 20
| Paid upto previous Bill | Nos. |  | 20
| To be paid in this Bill | Nos. |  | 0
101.f.ii.4 | Finishing Works - Office Furniture - Conference Table | Nos. | Palashbari | 2 | MPSB/Temp/48 | 2024-07-29 | IPC - 03
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
101.f.ii.5 | Finishing Works - Office Furniture - Conference Chairs | Nos. | Palashbari | 60 | MPSB/Temp/48 | 2024-07-29 | IPC - 03
| Cumulative paid upto this Bill | Nos. |  | 60
| Paid upto previous Bill | Nos. |  | 60
| To be paid in this Bill | Nos. |  | 0
101.f.ii.6 | Finishing Works - Office Furniture - Projector and Monitor in Conference Room | Nos. | Palashbari | 1 | MPSB/Temp/78 | 2024-08-30 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
101.f.ii.7 | Finishing Works - Office Furniture - Display Arrangement | Nos. | Palashbari | 2 | MPSB/Temp/78 | 2024-08-30 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
101.f.ii.8 | Finishing Works - Office Furniture - Steel Almirah & Racks | Nos. | Palashbari | 5 | MPSB/Temp/48 | 2024-07-29 | IPC - 03
101.f.ii.8 | Finishing Works - Office Furniture - Steel Almirah & Racks | Nos. | Sualkuchi | 5 | MPSB/Temp/74 | 2024-08-29 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 10
| Paid upto previous Bill | Nos. |  | 10
| To be paid in this Bill | Nos. |  | 0
101.f.ii.9 | Finishing Works - Office Furniture - Domestic Water Purifier | Nos. | Palashbari | 1 | MPSB/Temp/74 | 2024-08-29 | IPC - 04
101.f.ii.9 | Finishing Works - Office Furniture - Domestic Water Purifier | Nos. | Sualkuchi | 1 | MPSB/Temp/78 | 2024-08-30 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
101.f.iii.1 | Finishing Works - Office Equipment - Laptops | Nos. |  | 6 | MPSB/Temp/80 | 2024-08-31 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 6
| Paid upto previous Bill | Nos. |  | 6
| To be paid in this Bill | Nos. |  | 0
101.f.iii.2 | Finishing Works - Office Equipment - Colour Printer | Nos. |  | 2 | MPSB/Temp/80 | 2024-08-31 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102 | Provision (construction) of contractor’s site office, site laboratories, labor camps etc
102.a.i | Foundation - Office | Nos. | Palashbari | 0.5 | MPSB/Temp/1 | 2024-06-07 | IPC - 02
102.a.i | Foundation - Office | Nos. | Palashbari | 0.5 | MPSB/Temp/3 | 2024-06-08 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
102.a.ii | Foundation - Laboratory | Nos. | Palashbari | 1 | MPSB/Temp/54 | 2024-07-31 | IPC - 03
102.a.ii | Foundation - Laboratory | Nos. | Sualkuchi | 1 | MPSB/Temp/82 | 2024-09-27 | IPC - 05
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.a.iii.1 | Foundation - Labour Camp - Building | Nos. | Palashbari | 0.5 | MPSB/Temp/6 | 2024-06-10 | IPC - 02
102.a.iii.1 | Foundation - Labour Camp - Building | Nos. | Sualkuchi | 0.5 | MPSB/Temp/9 | 2024-06-11 | IPC - 02
102.a.iii.1 | Foundation - Labour Camp - Building | Nos. | Palashbari | 0.5 | MPSB/Temp/14 | 2024-06-12 | IPC - 02
102.a.iii.1 | Foundation - Labour Camp - Building | Nos. | Sualkuchi | 0.5 | MPSB/Temp/17 | 2024-06-13 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.a.iii.2 | Foundation - Labour Camp - Kitchen | Nos. | Palashbari | 1 | MPSB/Temp/12 | 2024-06-12 | IPC - 02
102.a.iii.2 | Foundation - Labour Camp - Kitchen | Nos. | Sualkuchi | 1 | MPSB/Temp/13 | 2024-06-12 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.b.i | Plinth - Office | Nos. | Palashbari | 1 | MPSB/Temp/8 | 2024-06-11 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
102.b.ii | Plinth - Laboratory | Nos. | Palashbari | 1 | MPSB/Temp/55 | 2024-07-31 | IPC - 03
102.b.ii | Plinth - Laboratory | Nos. | Sualkuchi | 1 | MPSB/Temp/86 | 2024-09-28 | IPC - 05
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.b.iii.1 | Plinth - Labour Camp - Building | Nos. | Palashbari | 1 | MPSB/Temp/23 | 2024-06-15 | IPC - 02
102.b.iii.1 | Plinth - Labour Camp - Building | Nos. | Sualkuchi | 0.5 | MPSB/Temp/28 | 2024-06-17 | IPC - 02
102.b.iii.1 | Plinth - Labour Camp - Building | Nos. | Sualkuchi | 0.5 | MPSB/Temp/31 | 2024-06-19 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.b.iii.2 | Plinth - Labour Camp - Kitchen | Nos. | Palashbari | 0.5 | MPSB/Temp/19 | 2024-06-14 | IPC - 02
102.b.iii.2 | Plinth - Labour Camp - Kitchen | Nos. | Sualkuchi | 1 | MPSB/Temp/20 | 2024-06-14 | IPC - 02
102.b.iii.2 | Plinth - Labour Camp - Kitchen | Nos. | Palashbari | 0.5 | MPSB/Temp/27 | 2024-06-17 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.c.i | Walls - Office | Nos. | Palashbari | 1 | MPSB/Temp/16 | 2024-06-13 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
102.c.ii | Walls - Laboratory | Nos. | Palashbari | 1 | MPSB/Temp/56 | 2024-07-31 | IPC - 03
102.c.ii | Walls - Laboratory | Nos. | Sualkuchi | 1 | MPSB/Temp/88 | 2024-09-29 | IPC - 05
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.c.iii.1 | Walls - Labour Camp - Building | Nos. | Palashbari | 1 | MPSB/Temp/65 | 2024-08-22 | IPC - 04
102.c.iii.1 | Walls - Labour Camp - Building | Nos. | Sualkuchi | 0.5 | MPSB/Temp/70 | 2024-08-27 | IPC - 04
102.c.iii.1 | Walls - Labour Camp - Building | Nos. | Sualkuchi | 0.5 | MPSB/Temp/99 | 2024-10-25 | IPC - 07
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.c.iii.2 | Walls - Labour Camp - Kitchen | Nos. | Palashbari | 1 | MPSB/Temp/25 | 2024-06-17 | IPC - 02
102.c.iii.2 | Walls - Labour Camp - Kitchen | Nos. | Sualkuchi | 1 | MPSB/Temp/26 | 2024-06-17 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.d.i | Roof - Office | Nos. | Palashbari | 1 | MPSB/Temp/22 | 2024-06-22 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
102.d.ii | Roof - Laboratory | Nos. | Palashbari | 1 | MPSB/Temp/57 | 2024-07-31 | IPC - 03
102.d.ii | Roof - Laboratory | Nos. | Sualkuchi | 1 | MPSB/Temp/89 | 2024-09-29 | IPC - 05
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.d.iii.1 | Roof - Labour Camp - Building | Nos. | Palashbari | 1 | MPSB/Temp/66 | 2024-08-22 | IPC - 04
102.d.iii.1 | Roof - Labour Camp - Building | Nos. | Sualkuchi | 1 | MPSB/Temp/85 | 2024-09-27 | IPC - 05
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.d.iii.2 | Roof - Labour Camp - Kitchen | Nos. | Palashbari | 1 | MPSB/Temp/73 | 2024-08-29 | IPC - 04
102.d.iii.2 | Roof - Labour Camp - Kitchen | Nos. | Sualkuchi | 1 | MPSB/Temp/90 | 2024-09-30 | IPC - 05
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.e.i | Flooring - Office | Nos. | Palashbari | 1 | MPSB/Temp/29 | 2024-06-18 | IPC - 02
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
102.e.ii | Flooring - Laboratory | Nos. | Palashbari | 1 | MPSB/Temp/58 | 2024-07-31 | IPC - 03
102.e.ii | Flooring - Laboratory | Nos. | Sualkuchi | 1 | MPSB/Temp/111 | 2024-11-28 | IPC - 08
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.e.iii.1 | Flooring - Labour Camp - Building | Nos. | Palashbari | 1 | MPSB/Temp/68 | 2024-08-26 | IPC - 04
102.e.iii.1 | Flooring - Labour Camp - Building | Nos. | Sualkuchi | 1 | MPSB/Temp/69 | 2024-08-26 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.e.iii.2 | Flooring - Labour Camp - Kitchen | Nos. | Palashbari | 1 | MPSB/Temp/46 | 2024-07-27 | IPC - 03
102.e.iii.2 | Flooring - Labour Camp - Kitchen | Nos. | Sualkuchi | 1 | MPSB/Temp/84 | 2024-09-27 | IPC - 05
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.f.i | Finishing Works - Office | Nos. | Palashbari | 1 | MPSB/Temp/67 | 2024-08-26 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
102.f.ii.1 | Finishing Works - Laboratory - Civil Works | Nos. | Palashbari | 1 | MPSB/Temp/59 | 2024-07-31 | IPC - 03
102.f.ii.1 | Finishing Works - Laboratory - Civil Works | Nos. | SualKuchi | 1 | MPSB/Temp/115 | 2024-11-30 | IPC - 08
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.f.ii.2 | Finishing Works - Laboratory - Lab Equipment | Nos. | Palashbari | 1 | MPSB/QAQC/32 | 2024-08-22 | IPC - 04
102.f.ii.2 | Finishing Works - Laboratory - Lab Equipment | Nos. | Sualkuchi | 1 | MPSB/QAQC/63 | 2024-11-29 | IPC - 08
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.f.iii.1 | Finishing Works - Labour Camps - Building | Nos. | Palashbari | 1 | MPSB/Temp/75 | 2024-08-30 | IPC - 04
102.f.iii.1 | Finishing Works - Labour Camps - Building | Nos. | Sualkuchi | 1 | MPSB/Temp/93 | 2024-09-30 | IPC - 05
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
102.f.iii.2 | Finishing Works - Labour Camps - Kitchen | Nos. | Palashbari | 1 | MPSB/Temp/76 | 2024-08-30 | IPC - 04
102.f.iii.2 | Finishing Works - Labour Camps - Kitchen | Nos. | Sualkuchi | 1 | MPSB/Temp/94 | 2024-09-30 | IPC - 05
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
103 | Operation and Maintenance of all temporary facilities including those mentioned in Item 101 & 102
103.a | Employer's Office | Quarterly | Palashbari | 0.5 | MPSB/Misc./2 Jun'24 - Aug'24 (Q1) | 2024-08-31 | IPC - 04
103.a | Employer's Office | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./3 Jun'24 - Aug'24 (Q1) | 2024-08-31 | IPC - 04
103.a | Employer's Office | Quarterly | Palashbari | 0.5 | MPSB/Misc./19 Sep'24 - Dec'24 (Q2) | 2024-12-29 | IPC - 09
103.a | Employer's Office | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./20 Sep'24 - Dec'24 (Q2) | 2024-12-29 | IPC - 09
103.a | Employer's Office | Quarterly | Palashbari | 0.5 | MPSB/Misc./30 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 13
103.a | Employer's Office | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./31 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 13
103.a | Employer's Office | Quarterly | Palashbari | 0.5 | MPSB/Misc./44 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 16
103.a | Employer's Office | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./45 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 16
103.a | Employer's Office | Quarterly | Palashbari | 0.5 | MPSB/Misc./60 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 20
103.a | Employer's Office | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./61 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 20
103.a | Employer's Office | Quarterly | Palashbari | 0.5 | MPSB/Misc./75 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
103.a | Employer's Office | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./76 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
103.a | Employer's Office | Quarterly | Palashbari | 0.5 | MPSB/Misc./87 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
103.a | Employer's Office | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./88 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
103.a | Employer's Office | Quarterly | Palashbari | 0.5 | MPSB/Misc./102 Apr'26 - Jun'26 (Q4) | 2026-06-30 | IPC - 33
103.a | Employer's Office | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./103 Apr'26 - Jun'26 (Q4) | 2026-06-30 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0
103.b.i | Vehicles - Bolero & Scorpio | Nos.-Quarterly |  | 6 | MPSB/L&T/TIIC/2024/294 Jun'24 - Aug'24 (Q1) | 2024-08-22 | IPC - 04
103.b.i | Vehicles - Bolero & Scorpio | Nos.-Quarterly |  | 6 | MPSB/Misc./26 Sep'24 - Dec'24 (Q2) | 2024-12-29 | IPC - 09
103.b.i | Vehicles - Bolero & Scorpio | Nos.-Quarterly |  | 6 | MPSB/Misc./37 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 13
103.b.i | Vehicles - Bolero & Scorpio | Nos.-Quarterly |  | 6 | MPSB/Misc./51 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 16
103.b.i | Vehicles - Bolero & Scorpio | Nos.-Quarterly |  | 6 | MPSB/Misc./67 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 20
103.b.i | Vehicles - Bolero & Scorpio | Nos.-Quarterly |  | 6 | MPSB/Misc./82 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
103.b.i | Vehicles - Bolero & Scorpio | Nos.-Quarterly |  | 6 | MPSB/Misc./94 Jan'25 - Mar'25 (Q3) | 2026-03-30 | IPC - 29
103.b.i | Vehicles - Bolero & Scorpio | Nos.-Quarterly |  | 6 | MPSB/Misc./104 Apr'26 - Jun'26 (Q4) | 2026-06-30 | IPC - 33
| Cumulative paid upto this Bill | Nos.-Quarterly |  | 48
| Paid upto previous Bill | Nos.-Quarterly |  | 48
| To be paid in this Bill | Nos.-Quarterly |  | 0
103.b.ii | Vehicles - Speed Boat | Nos.-Quarterly |  | 2 | MPSB/L&T/TIIC/2024/408 Jun'24 - Aug'24 (Q1) | 2024-10-31 | IPC - 07
103.b.ii | Vehicles - Speed Boat | Nos.-Quarterly |  | 2 | MPSB/Misc./27 Sep'24 - Dec'24 (Q2) | 2024-12-29 | IPC - 09
103.b.ii | Vehicles - Speed Boat | Nos.-Quarterly |  | 2 | MPSB/Misc./38 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 13
103.b.ii | Vehicles - Speed Boat | Nos.-Quarterly |  | 2 | MPSB/Misc./52 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 16
103.b.ii | Vehicles - Speed Boat | Nos.-Quarterly |  | 2 | MPSB/Misc./68 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 20
103.b.ii | Vehicles - Speed Boat | Nos.-Quarterly |  | 2 | MPSB/Misc./83 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
103.b.ii | Vehicles - Speed Boat | Nos.-Quarterly |  | 2 | MPSB/Misc./95 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
103.b.ii | Vehicles - Speed Boat | Nos.-Quarterly |  | 2 | MPSB/Misc./105 Apr'26 - Jun'26 (Q4) | 2026-06-30 | IPC - 33
| Cumulative paid upto this Bill | Nos.-Quarterly |  | 16
| Paid upto previous Bill | Nos.-Quarterly |  | 16
| To be paid in this Bill | Nos.-Quarterly |  | 0
103.b.iii | Vehicles - Rescue Boat | Nos.-Quarterly |  | 1 | MPSB/L&T/TIIC/2024/408 Jun'24 - Aug'24 (Q1) | 2024-10-31 | IPC - 07
103.b.iii | Vehicles - Rescue Boat | Nos.-Quarterly |  | 1 | MPSB/Misc./28 Sep'24 - Dec'24 (Q2) | 2024-12-29 | IPC - 09
103.b.iii | Vehicles - Rescue Boat | Nos.-Quarterly |  | 1 | MPSB/Misc./39 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 13
103.b.iii | Vehicles - Rescue Boat | Nos.-Quarterly |  | 1 | MPSB/Misc./53 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 16
103.b.iii | Vehicles - Rescue Boat | Nos.-Quarterly |  | 1 | MPSB/Misc./69 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 20
103.b.iii | Vehicles - Rescue Boat | Nos.-Quarterly |  | 1 | MPSB/Misc./84 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
103.b.iii | Vehicles - Rescue Boat | Nos.-Quarterly |  | 1 | MPSB/Misc./96 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
103.b.iii | Vehicles - Rescue Boat | Nos.-Quarterly |  | 1 | MPSB/Misc./106 Apr'26 - Jun'26 (Q4) | 2026-06-30 | IPC - 33
| Cumulative paid upto this Bill | Nos.-Quarterly |  | 8
| Paid upto previous Bill | Nos.-Quarterly |  | 8
| To be paid in this Bill | Nos.-Quarterly |  | 0
103.c | Contractor's Office | Quarterly | Palashbari | 1 | MPSB/Misc./4 Jun'24 - Aug'24 (Q1) | 2024-08-31 | IPC - 04
103.c | Contractor's Office | Quarterly | Palashbari | 1 | MPSB/Misc./21 Sep'24 - Dec'24 (Q2) | 2024-12-29 | IPC - 09
103.c | Contractor's Office | Quarterly | Palashbari | 1 | MPSB/Misc./32 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 13
103.c | Contractor's Office | Quarterly | Palashbari | 1 | MPSB/Misc./46 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 16
103.c | Contractor's Office | Quarterly | Palashbari | 1 | MPSB/Misc./62 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 20
103.c | Contractor's Office | Quarterly | Palashbari | 1 | MPSB/Misc./77 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
103.c | Contractor's Office | Quarterly | Palashbari | 1 | MPSB/Misc./89 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
103.c | Contractor's Office | Quarterly | Palashbari | 1 | MPSB/Misc./107 Apr'26 - Jun'26 (Q4) | 2026-06-30 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0
103.d | Site Laboratory | Quarterly | Palashbari | 0.5 | MPSB/Misc./5 Jun'24 - Aug'24 (Q1) | 2024-08-31 | IPC - 04
103.d | Site Laboratory | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./6 Jun'24 - Aug'24 (Q1) | 2024-08-31 | IPC - 04
103.d | Site Laboratory | Quarterly | Palashbari | 0.5 | MPSB/Misc./22 Sep'24 - Dec'24 (Q2) | 2024-12-29 | IPC - 09
103.d | Site Laboratory | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./23 Sep'24 - Dec'24 (Q2) | 2024-12-29 | IPC - 09
103.d | Site Laboratory | Quarterly | Palashbari | 0.5 | MPSB/Misc./33 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 13
103.d | Site Laboratory | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./34 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 13
103.d | Site Laboratory | Quarterly | Palashbari | 0.5 | MPSB/Misc./47 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 16
103.d | Site Laboratory | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./48 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 16
103.d | Site Laboratory | Quarterly | Palashbari | 0.5 | MPSB/Misc./63 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 20
103.d | Site Laboratory | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./64 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 20
103.d | Site Laboratory | Quarterly | Palashbari | 0.5 | MPSB/Misc./78 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
103.d | Site Laboratory | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./79 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
103.d | Site Laboratory | Quarterly | Palashbari | 0.5 | MPSB/Misc./90 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
103.d | Site Laboratory | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./91 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
103.d | Site Laboratory | Quarterly | Palashbari | 0.5 | MPSB/Misc./108 Apr'26 - Jun'26 (Q4) | 2026-06-30 | IPC - 33
103.d | Site Laboratory | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./109 Apr'26 - Jun'26 (Q4) | 2026-06-30 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0
103.e | Labour Camps | Quarterly | Palashbari | 0.5 | MPSB/Misc./7 Jun'24 - Aug'24 (Q1) | 2024-08-31 | IPC - 04
103.e | Labour Camps | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./8 Jun'24 - Aug'24 (Q1) | 2024-08-31 | IPC - 04
103.e | Labour Camps | Quarterly | Palashbari | 0.5 | MPSB/Misc./24 Sep'24 - Dec'24 (Q2) | 2024-12-29 | IPC - 09
103.e | Labour Camps | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./25 Sep'24 - Dec'24 (Q2) | 2024-12-29 | IPC - 09
103.e | Labour Camps | Quarterly | Palashbari | 0.5 | MPSB/Misc./35 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 13
103.e | Labour Camps | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./36 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 13
103.e | Labour Camps | Quarterly | Palashbari | 0.5 | MPSB/Misc./49 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 16
103.e | Labour Camps | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./50 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 16
103.e | Labour Camps | Quarterly | Palashbari | 0.5 | MPSB/Misc./65 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 20
103.e | Labour Camps | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./66 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 20
103.e | Labour Camps | Quarterly | Palashbari | 0.5 | MPSB/Misc./80 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
103.e | Labour Camps | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./81 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
103.e | Labour Camps | Quarterly | Palashbari | 0.5 | MPSB/Misc./92 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
103.e | Labour Camps | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./93 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
103.e | Labour Camps | Quarterly | Palashbari | 0.5 | MPSB/Misc./110 Apr'26 - Jun'26 (Q4) | 2026-06-30 | IPC - 33
103.e | Labour Camps | Quarterly | Sualkuchi | 0.5 | MPSB/Misc./111 Apr'26 - Jun'26 (Q4) | 2026-06-30 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0
104 | Compliance of Environmental Management Plan (EMP)
104.a | Environmental Management Plan Implementation | Half Yearly |  | 1 | MPSB/HSE/11 Jun'24 - Dec'24 (H1) | 2024-12-28 | IPC - 22
104.a | Environmental Management Plan Implementation | Half Yearly |  | 1 | MPSB/HSE/28 Jan'25 - Jun'25 (H2) | 2025-08-30 | IPC - 22
104.a | Environmental Management Plan Implementation | Half Yearly |  | 1 | MPSB/HSE/55 Jul'25 - Dec'25 (H1) | 2025-12-31 | IPC - 25
104.a | Environmental Management Plan Implementation | Half Yearly |  | 1 | MPSB/HSE/81 Jan'26 - Jun'26 (H2) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Half Yearly |  | 4
| Paid upto previous Bill | Half Yearly |  | 4
| To be paid in this Bill | Half Yearly |  | 0
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/1 Jun'24 - Aug'24 | 2024-08-31 | IPC - 04
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/2 Jun'24 - Aug'24 | 2024-08-31 | IPC - 04
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/5 Sep'24 - Oct'24 | 2024-10-18 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/6 Sep'24 - Oct'24 | 2024-10-18 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/8 Nov'24 - Dec'24 | 2024-12-21 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/9 Nov'24 - Dec'24 | 2024-12-21 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/15 Jan'25 - Feb'25 | 2025-02-24 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/16 Jan'25 - Feb'25 | 2025-02-24 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/18 Mar'25 - Apr'25 | 2025-04-24 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/19 Mar'25 - Apr'25 | 2025-04-24 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/21 May'25 - Jun'25 | 2025-06-24 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/20 May'25 - Jun'25 | 2025-06-24 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/25 Jul'25 - Aug'25 | 2025-08-30 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/26 Jul'25 - Aug'25 | 2025-08-30 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/32 Sep'25 - Oct'25 | 2025-10-22 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/33 Sep'25 - Oct'25 | 2025-10-22 | IPC - 22
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/39 Nov'25 - Dec'25 | 2025-12-31 | IPC - 25
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/40 Nov'25 - Dec'25 | 2025-12-31 | IPC - 25
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/61 Jan'26 - Feb'26 | 2026-03-27 | IPC - 29
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/62 Jan'26 - Feb'26 | 2026-03-27 | IPC - 29
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/65 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/66 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/67 May'26 - Jun'26 | 2026-06-23 | IPC - 33
104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/68 May'26 - Jun'26 | 2026-06-23 | IPC - 33
| Cumulative paid upto this Bill | Bi-Monthly |  | 12
| Paid upto previous Bill | Bi-Monthly |  | 12
| To be paid in this Bill | Bi-Monthly |  | 0
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/1 Jun'24 - Aug'24 | 2024-08-31 | IPC - 04
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/2 Jun'24 - Aug'24 | 2024-08-31 | IPC - 04
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/5 Sep'24 - Oct'24 | 2024-10-18 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/6 Sep'24 - Oct'24 | 2024-10-18 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/8 Nov'24 - Dec'24 | 2024-12-21 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/9 Nov'24 - Dec'24 | 2024-12-21 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/15 Jan'25 - Feb'25 | 2025-02-24 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/16 Jan'25 - Feb'25 | 2025-02-24 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/18 Mar'25 - Apr'25 | 2025-04-24 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/19 Mar'25 - Apr'25 | 2025-04-24 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/21 May'25 - Jun'25 | 2025-06-24 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/20 May'25 - Jun'25 | 2025-06-24 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/25 Jul'25 - Aug'25 | 2025-08-30 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/26 Jul'25 - Aug'25 | 2025-08-30 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/32 Sep'25 - Oct'25 | 2025-10-22 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/33 Sep'25 - Oct'25 | 2025-10-22 | IPC - 22
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/39 Nov'25 - Dec'25 | 2025-12-31 | IPC - 25
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/40 Nov'25 - Dec'25 | 2025-12-31 | IPC - 25
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/61 Jan'26 - Feb'26 | 2026-03-27 | IPC - 29
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/62 Jan'26 - Feb'26 | 2026-03-27 | IPC - 29
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/65 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/66 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/67 May'26 - Jun'26 | 2026-06-23 | IPC - 33
104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/68 May'26 - Jun'26 | 2026-06-23 | IPC - 33
| Cumulative paid upto this Bill | Bi-Monthly |  | 12
| Paid upto previous Bill | Bi-Monthly |  | 12
| To be paid in this Bill | Bi-Monthly |  | 0
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/1 Jun'24 - Aug'24 | 2024-08-31 | IPC - 04
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/2 Jun'24 - Aug'24 | 2024-08-31 | IPC - 04
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/5 Sep'24 - Oct'24 | 2024-10-18 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/6 Sep'24 - Oct'24 | 2024-10-18 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/8 Nov'24 - Dec'24 | 2024-12-21 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/9 Nov'24 - Dec'24 | 2024-12-21 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/15 Jan'25 - Feb'25 | 2025-02-24 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/16 Jan'25 - Feb'25 | 2025-02-24 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/18 Mar'25 - Apr'25 | 2025-04-24 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/19 Mar'25 - Apr'25 | 2025-04-24 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/21 May'25 - Jun'25 | 2025-06-24 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/20 May'25 - Jun'25 | 2025-06-24 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/25 Jul'25 - Aug'25 | 2025-08-30 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/26 Jul'25 - Aug'25 | 2025-08-30 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/32 Sep'25 - Oct'25 | 2025-10-22 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/33 Sep'25 - Oct'25 | 2025-10-22 | IPC - 22
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/39 Nov'25 - Dec'25 | 2025-12-31 | IPC - 25
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/40 Nov'25 - Dec'25 | 2025-12-31 | IPC - 25
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/61 Jan'26 - Feb'26 | 2026-03-27 | IPC - 29
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/62 Jan'26 - Feb'26 | 2026-03-27 | IPC - 29
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/65 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/66 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/67 May'26 - Jun'26 | 2026-06-23 | IPC - 33
104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/68 May'26 - Jun'26 | 2026-06-23 | IPC - 33
| Cumulative paid upto this Bill | Bi-Monthly |  | 12
| Paid upto previous Bill | Bi-Monthly |  | 12
| To be paid in this Bill | Bi-Monthly |  | 0
104.b.iv | Implementation of Environmental Monitoring Program - Soil Quality | Half Yearly | Palashbari | 0.5 | MPSB/HSE/8 Jun'24 - Dec'24 (H1) | 2024-12-21 | IPC - 22
104.b.iv | Implementation of Environmental Monitoring Program - Soil Quality | Half Yearly | Sualkuchi | 0.5 | MPSB/HSE/9 Jun'24 - Dec'24 (H1) | 2024-12-21 | IPC - 22
104.b.iv | Implementation of Environmental Monitoring Program - Soil Quality | Half Yearly | Palashbari | 0.5 | MPSB/HSE/21 Jan'25 - Jun'25 (H2) | 2025-06-24 | IPC - 22
104.b.iv | Implementation of Environmental Monitoring Program - Soil Quality | Half Yearly | Sualkuchi | 0.5 | MPSB/HSE/20 Jan'25 - Jun'25 (H2) | 2025-06-24 | IPC - 22
104.b.iv | Implementation of Environmental Monitoring Program - Soil Quality | Half Yearly | Palashbari | 0.5 | MPSB/HSE/39 Nov'25 - Dec'25 (H1) | 2025-12-31 | IPC - 25
104.b.iv | Implementation of Environmental Monitoring Program - Soil Quality | Half Yearly | Sualkuchi | 0.5 | MPSB/HSE/40 Nov'25 - Dec'25 (H1) | 2025-12-31 | IPC - 25
104.b.iv | Implementation of Environmental Monitoring Program - Soil Quality | Half Yearly | Palashbari | 0.5 | MPSB/HSE/67 Jan'26 - Jun'26 (H2) | 2026-06-23 | IPC - 33
104.b.iv | Implementation of Environmental Monitoring Program - Soil Quality | Half Yearly | Sualkuchi | 0.5 | MPSB/HSE/68 Jan'26 - Jun'26 (H2) | 2026-06-23 | IPC - 33
| Cumulative paid upto this Bill | Half Yearly |  | 4
| Paid upto previous Bill | Half Yearly |  | 4
| To be paid in this Bill | Half Yearly |  | 0
104.b.v | Implementation of Environmental Monitoring Program - Ecology and Biodiversity | Half Yearly |  | 1 | MPSB/HSE/10 Jun'24 - Dec'24 (H1) | 2024-12-28 | IPC - 22
104.b.v | Implementation of Environmental Monitoring Program - Ecology and Biodiversity | Half Yearly |  | 1 | MPSB/HSE/24 Jan'25 - Jun'25 (H2) | 2025-06-30 | IPC - 22
104.b.v | Implementation of Environmental Monitoring Program - Ecology and Biodiversity | Half Yearly |  | 1 | MPSB/HSE/57 Jul'25 - Dec'25 (H1) | 2025-12-31 | IPC - 25
104.b.v | Implementation of Environmental Monitoring Program - Ecology and Biodiversity | Half Yearly |  | 1 | MPSB/HSE/77 Jan'26 - Jun'26 (H2) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Half Yearly |  | 4
| Paid upto previous Bill | Half Yearly |  | 4
| To be paid in this Bill | Half Yearly |  | 0
104.c | Compliance of Environmental Clearance Conditions - EC identification no. EC22B039AS197455 | Half Yearly |  | 1 | MPSB/HSE/11 Jun'24 - Dec'24 (H1) | 2024-12-28 | IPC - 22
104.c | Compliance of Environmental Clearance Conditions - EC identification no. EC22B039AS197455 | Half Yearly |  | 1 | MPSB/HSE/28 Jan'25 - Jun'25 (H2) | 2025-08-30 | IPC - 22
104.c | Compliance of Environmental Clearance Conditions - EC identification no. EC22B039AS197455 | Half Yearly |  | 1 | MPSB/HSE/58 Jul'25 - Dec'25 (H1) | 2025-12-31 | IPC - 25
104.c | Compliance of Environmental Clearance Conditions - EC identification no. EC22B039AS197455 | Half Yearly |  | 1 | MPSB/HSE/80 Jan'26 - Jun'26 (H2) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Half Yearly |  | 4
| Paid upto previous Bill | Half Yearly |  | 4
| To be paid in this Bill | Half Yearly |  | 0
104.d | Implementation of Environmental Management Plan - For Aquatic Ecology and Dolphin Conservation | Half Yearly |  | 1 | MPSB/HSE/11 Jun'24 - Dec'24 (H1) | 2024-12-28 | IPC - 22
104.d | Implementation of Environmental Management Plan - For Aquatic Ecology and Dolphin Conservation | Half Yearly |  | 1 | MPSB/HSE/28 Jan'25 - Jun'25 (H2) | 2025-08-30 | IPC - 22
104.d | Implementation of Environmental Management Plan - For Aquatic Ecology and Dolphin Conservation | Half Yearly |  | 1 | MPSB/HSE/52 Jul'25 - Dec'25 (H1) | 2025-12-31 | IPC - 25
104.d | Implementation of Environmental Management Plan - For Aquatic Ecology and Dolphin Conservation | Half Yearly |  | 1 | MPSB/HSE/79 Jan'26 - Jun'26 (H2) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Half Yearly |  | 4
| Paid upto previous Bill | Half Yearly |  | 4
| To be paid in this Bill | Half Yearly |  | 0
104.e.i | Dolphin Pinger for Dolphin Safety - Equipment Provision | Nos. |  | 20 | MPSB/Misc./18 | 2024-11-30 | IPC - 22
104.e.i | Dolphin Pinger for Dolphin Safety - Equipment Provision | Nos. |  | 10 | MPSB/Misc./99 | 2026-04-30 | IPC - 30
| Cumulative paid upto this Bill | Nos. |  | 30
| Paid upto previous Bill | Nos. |  | 30
| To be paid in this Bill | Nos. |  | 0
104.e.ii | Dolphin Pinger for Dolphin Safety - Maintenance of Equipment | Quarterly |  | 2 | MPSB/Misc./29 Jun'24 - Dec'24 (Q1 & Q2) | 2024-12-30 | IPC - 22
104.e.ii | Dolphin Pinger for Dolphin Safety - Maintenance of Equipment | Quarterly |  | 1 | MPSB/Misc./42 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 22
104.e.ii | Dolphin Pinger for Dolphin Safety - Maintenance of Equipment | Quarterly |  | 1 | MPSB/Misc./54 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 22
104.e.ii | Dolphin Pinger for Dolphin Safety - Maintenance of Equipment | Quarterly |  | 1 | MPSB/Misc./70 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 22
104.e.ii | Dolphin Pinger for Dolphin Safety - Maintenance of Equipment | Quarterly |  | 1 | MPSB/HSE/51 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.e.ii | Dolphin Pinger for Dolphin Safety - Maintenance of Equipment | Quarterly |  | 1 | MPSB/Misc./86 Jan'26 - Mar'26 (Q3) | 2026-03-29 | IPC - 29
104.e.ii | Dolphin Pinger for Dolphin Safety - Maintenance of Equipment | Quarterly |  | 1 | MPSB/HSE/69 Apr'26 - Jun'26 (Q4) | 2026-06-23 | IPC - 33
| Cumulative paid upto this Bill | Nos.-Quarterly |  | 8
| Paid upto previous Bill | Nos.-Quarterly |  | 8
| To be paid in this Bill | Nos.-Quarterly |  | 0
104.g.i | EMP Provisions - Solid Waste Management accessories | Quarterly |  | 1 | PMB-II-99/Misc.(N)/24/142 Jun'24 - Aug'24 (Q1) | 2024-06-27 | IPC - 04
104.g.i | EMP Provisions - Solid Waste Management accessories | Quarterly |  | 1 | MPSB/HSE/34 Sep'24 - Dec'24 (Q2) | 2025-10-31 | IPC - 22
104.g.i | EMP Provisions - Solid Waste Management accessories | Quarterly |  | 1 | MPSB/HSE/34 Jan'25 - Mar'25 (Q3) | 2025-10-31 | IPC - 22
104.g.i | EMP Provisions - Solid Waste Management accessories | Quarterly |  | 1 | MPSB/HSE/34 Apr'25 - Jun'25 (Q4) | 2025-10-31 | IPC - 22
104.g.i | EMP Provisions - Solid Waste Management accessories | Quarterly |  | 1 | MPSB/HSE/34 Jul'25 - Sep'25 (Q1) | 2025-10-31 | IPC - 22
104.g.i | EMP Provisions - Solid Waste Management accessories | Quarterly |  | 1 | MPSB/HSE/53 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.g.i | EMP Provisions - Solid Waste Management accessories | Quarterly |  | 1 | MPSB/HSE/63 Jan'26 - Mar'26 (Q4) | 2026-03-31 | IPC - 29
104.g.i | EMP Provisions - Solid Waste Management accessories | Quarterly |  | 1 | MPSB/HSE/76 Apr'26 - Jun'26 (Q4) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0
104.g.ii | EMP Provisions - Health and Occupational Safety Management Plan | Quarterly |  | 1 | MPSB/L&T/TIIC/2024/201 Jun'24 - Aug'24 (Q1) | 2024-06-26 | IPC - 04
104.g.ii | EMP Provisions - Health and Occupational Safety Management Plan | Quarterly |  | 1 | MPSB/HSE/34 Sep'24 - Dec'24 (Q2) | 2025-10-31 | IPC - 22
104.g.ii | EMP Provisions - Health and Occupational Safety Management Plan | Quarterly |  | 1 | MPSB/HSE/34 Jan'25 - Mar'25 (Q3) | 2025-10-31 | IPC - 22
104.g.ii | EMP Provisions - Health and Occupational Safety Management Plan | Quarterly |  | 1 | MPSB/HSE/34 Apr'25 - Jun'25 (Q4) | 2025-10-31 | IPC - 22
104.g.ii | EMP Provisions - Health and Occupational Safety Management Plan | Quarterly |  | 1 | MPSB/HSE/34 Jul'25 - Sep'25 (Q1) | 2025-10-31 | IPC - 22
104.g.ii | EMP Provisions - Health and Occupational Safety Management Plan | Quarterly |  | 1 | MPSB/HSE/54 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.g.ii | EMP Provisions - Health and Occupational Safety Management Plan | Quarterly |  | 1 | MPSB/HSE/64 Jan'26 - Mar'26 (Q4) | 2026-03-31 | IPC - 29
104.g.ii | EMP Provisions - Health and Occupational Safety Management Plan | Quarterly |  | 1 | MPSB/HSE/78 Apr'26 - Jun'26 (Q4) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0
104.g.iii | EMP Provisions - Environmental Training Plan | Quarterly |  | 1 | Jun'24 - Aug'24 (Q1) | - | IPC - 04
104.g.iii | EMP Provisions - Environmental Training Plan | Quarterly |  | 1 | MPSB/HSE/34 Sep'24 - Dec'24 (Q2) | 2025-10-31 | IPC - 22
104.g.iii | EMP Provisions - Environmental Training Plan | Quarterly |  | 1 | MPSB/HSE/34 Jan'25 - Mar'25 (Q3) | 2025-10-31 | IPC - 22
104.g.iii | EMP Provisions - Environmental Training Plan | Quarterly |  | 1 | MPSB/HSE/34 Apr'25 - Jun'25 (Q4) | 2025-10-31 | IPC - 22
104.g.iii | EMP Provisions - Environmental Training Plan | Quarterly |  | 1 | MPSB/HSE/34 Jul'25 - Sep'25 (Q1) | 2025-10-31 | IPC - 22
104.g.iii | EMP Provisions - Environmental Training Plan | Quarterly |  | 1 | MPSB/HSE/53 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.g.iii | EMP Provisions - Environmental Training Plan | Quarterly |  | 1 | MPSB/HSE/63 Jan'26 - Mar'26 (Q4) | 2026-03-31 | IPC - 29
104.g.iii | EMP Provisions - Environmental Training Plan | Quarterly |  | 1 | MPSB/HSE/76 Apr'26 - Jun'26 (Q4) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0
104.g.iv | EMP Provisions - Traffic Management Plan | Quarterly |  | 1 | MPSB/L&T/TIIC/2024/201 Jun'24 - Aug'24 (Q1) | 2024-06-26 | IPC - 04
104.g.iv | EMP Provisions - Traffic Management Plan | Quarterly |  | 1 | MPSB/HSE/34 Sep'24 - Dec'24 (Q2) | 2025-10-31 | IPC - 22
104.g.iv | EMP Provisions - Traffic Management Plan | Quarterly |  | 1 | MPSB/HSE/34 Jan'25 - Mar'25 (Q3) | 2025-10-31 | IPC - 22
104.g.iv | EMP Provisions - Traffic Management Plan | Quarterly |  | 1 | MPSB/HSE/34 Apr'25 - Jun'25 (Q4) | 2025-10-31 | IPC - 22
104.g.iv | EMP Provisions - Traffic Management Plan | Quarterly |  | 1 | MPSB/HSE/34 Jul'25 - Sep'25 (Q1) | 2025-10-31 | IPC - 22
104.g.iv | EMP Provisions - Traffic Management Plan | Quarterly |  | 1 | MPSB/HSE/54 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.g.iv | EMP Provisions - Traffic Management Plan | Quarterly |  | 1 | MPSB/HSE/64 Jan'26 - Mar'26 (Q4) | 2026-03-31 | IPC - 29
104.g.iv | EMP Provisions - Traffic Management Plan | Quarterly |  | 1 | MPSB/HSE/78 Apr'26 - Jun'26 (Q4) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0
104.g.v | EMP Provisions - Emergency Preparedness Plan | Quarterly |  | 1 | MPSB/L&T/TIIC/2024/201 Jun'24 - Aug'24 (Q1) | 2024-06-26 | IPC - 04
104.g.v | EMP Provisions - Emergency Preparedness Plan | Quarterly |  | 1 | MPSB/HSE/34 Sep'24 - Dec'24 (Q2) | 2025-10-31 | IPC - 22
104.g.v | EMP Provisions - Emergency Preparedness Plan | Quarterly |  | 1 | MPSB/HSE/34 Jan'25 - Mar'25 (Q3) | 2025-10-31 | IPC - 22
104.g.v | EMP Provisions - Emergency Preparedness Plan | Quarterly |  | 1 | MPSB/HSE/34 Apr'25 - Jun'25 (Q4) | 2025-10-31 | IPC - 22
104.g.v | EMP Provisions - Emergency Preparedness Plan | Quarterly |  | 1 | MPSB/HSE/34 Jul'25 - Sep'25 (Q1) | 2025-10-31 | IPC - 22
104.g.v | EMP Provisions - Emergency Preparedness Plan | Quarterly |  | 1 | MPSB/HSE/54 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.g.v | EMP Provisions - Emergency Preparedness Plan | Quarterly |  | 1 | MPSB/HSE/64 Jan'26 - Mar'26 (Q4) | 2026-03-31 | IPC - 29
104.g.v | EMP Provisions - Emergency Preparedness Plan | Quarterly |  | 1 | MPSB/HSE/78 Apr'26 - Jun'26 (Q4) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0
104.g.vi | EMP Provisions - Miscellaneous (repair and maintenance) | Quarterly |  | 1 | Jun'24 - Aug'24 (Q1) | - | IPC - 04
104.g.vi | EMP Provisions - Miscellaneous (repair and maintenance) | Quarterly |  | 1 | MPSB/HSE/34 Sep'24 - Dec'24 (Q2) | 2025-10-31 | IPC - 22
104.g.vi | EMP Provisions - Miscellaneous (repair and maintenance) | Quarterly |  | 1 | MPSB/HSE/34 Jan'25 - Mar'25 (Q3) | 2025-10-31 | IPC - 22
104.g.vi | EMP Provisions - Miscellaneous (repair and maintenance) | Quarterly |  | 1 | MPSB/HSE/34 Apr'25 - Jun'25 (Q4) | 2025-10-31 | IPC - 22
104.g.vi | EMP Provisions - Miscellaneous (repair and maintenance) | Quarterly |  | 1 | MPSB/HSE/34 Jul'25 - Sep'25 (Q1) | 2025-10-31 | IPC - 22
104.g.vi | EMP Provisions - Miscellaneous (repair and maintenance) | Quarterly |  | 1 | MPSB/HSE/53 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.g.vi | EMP Provisions - Miscellaneous (repair and maintenance) | Quarterly |  | 1 | MPSB/HSE/63 Jan'26 - Mar'26 (Q4) | 2026-03-31 | IPC - 29
104.g.vi | EMP Provisions - Miscellaneous (repair and maintenance) | Quarterly |  | 1 | MPSB/HSE/76 Apr'26 - Jun'26 (Q4) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0
104.h.i.1 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Construction | Nos. | Palashbari | 1 | MPSB/Temp/117 | 2024-12-30 | IPC - 22
104.h.i.1 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Construction | Nos. | Sualkuchi | 1 | MPSB/Temp/118 | 2024-12-30 | IPC - 22
104.h.i.1 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Construction | Nos. | Palashbari | 1 | MPSB/Temp/143 | 2025-03-31 | IPC - 22
| Cumulative paid upto this Bill | Nos. |  | 3
| Paid upto previous Bill | Nos. |  | 3
| To be paid in this Bill | Nos. |  | 0
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/119 Sep'24 - Dec'24 (Q2) | 2024-12-30 | IPC - 22
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/120 Sep'24 - Dec'24 (Q2) | 2024-12-30 | IPC - 22
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/144 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 22
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/145 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 22
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/173 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 22
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/174 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 22
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/187 Jul'25 - Sep'25 | 2025-09-30 | IPC - 22
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/188 Jul'25 - Sep'25 | 2025-09-30 | IPC - 22
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/HSE/41 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/HSE/42 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/203 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/204 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/HSE/70 Apr'26 - Jun'26 (Q4) | 2026-06-23 | IPC - 33
104.h.i.2 | Provision of establishment of Sewage and Water Treatment Plant - Sewage Treatment Plant - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/HSE/71 Apr'26 - Jun'26 (Q4) | 2026-06-23 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 7
| Paid upto previous Bill | Quarterly |  | 7
| To be paid in this Bill | Quarterly |  | 0
104.h.ii.1 | Provision of establishment of Sewage and Water Treatment Plant - Waste Water Treatment Plant - Construction | Nos. | Palashbari | 2 | MPSB/Misc./97 | 2026-03-31 | IPC - 29
104.h.ii.1 | Provision of establishment of Sewage and Water Treatment Plant - Waste Water Treatment Plant - Construction | Nos. | Sualkuchi | 2 | MPSB/Misc./98 | 2026-03-31 | IPC - 29
| Cumulative paid upto this Bill | Nos. |  | 4
| Paid upto previous Bill | Nos. |  | 4
| To be paid in this Bill | Nos. |  | 0
104.h.ii.2 | Provision of establishment of Sewage and Water Treatment Plant - Waste Water Treatment Plant - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/207 Jan'26 - Mar'26 (Q3) | 2026-03-31 | IPC - 29
104.h.ii.2 | Provision of establishment of Sewage and Water Treatment Plant - Waste Water Treatment Plant - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/208 Jan'26 - Mar'26 (Q3) | 2026-03-31 | IPC - 29
104.h.ii.2 | Provision of establishment of Sewage and Water Treatment Plant - Waste Water Treatment Plant - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/HSE/74 Apr'26 - Jun'26 (Q4) | 2026-06-24 | IPC - 33
104.h.ii.2 | Provision of establishment of Sewage and Water Treatment Plant - Waste Water Treatment Plant - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/HSE/75 Apr'26 - Jun'26 (Q4) | 2026-06-24 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 2
| Paid upto previous Bill | Quarterly |  | 2
| To be paid in this Bill | Quarterly |  | 0
104.h.iii.1 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Construction | Nos. | Palashbari | 2 | MPSB/Temp/149 | 2025-03-31 | IPC - 22
104.h.iii.1 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Construction | Nos. | Sualkuchi | 2 | MPSB/Temp/150 | 2025-03-31 | IPC - 22
| Cumulative paid upto this Bill | Nos. |  | 4
| Paid upto previous Bill | Nos. |  | 4
| To be paid in this Bill | Nos. |  | 0
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/152 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 22
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/153 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 22
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/177 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 22
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/178 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 22
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/191 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 22
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/192 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 22
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/HSE/45 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/HSE/46 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/205 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/206 Jan'26 - Mar'26 (Q3) | 2026-03-30 | IPC - 29
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/HSE/72 Apr'26 - Jun'26 (Q4) | 2026-06-23 | IPC - 33
104.h.iii.2 | Provision of establishment of Sewage and Water Treatment Plant - Silt Sedimentation Tank - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/HSE/73 Apr'26 - Jun'26 (Q4) | 2026-06-23 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 6
| Paid upto previous Bill | Quarterly |  | 6
| To be paid in this Bill | Quarterly |  | 0
104.h.v.1 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Construction | Nos. | Palashbari | 48 | MPSB/Temp/71 | 2024-08-27 | IPC - 04
104.h.v.1 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Construction | Nos. | Sualkuchi | 48 | MPSB/Temp/101 | 2024-10-29 | IPC - 22
104.h.v.1 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Construction | Nos. | Sualkuchi | 32 | MPSB/Temp/121 | 2024-12-30 | IPC - 22
104.h.v.1 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Construction | Nos. | Palashbari | 32 | MPSB/Temp/151 | 2025-03-31 | IPC - 22
104.h.v.1 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Construction | Nos. | Palashbari | 48 | MPSB/Temp/179 | 2025-06-30 | IPC - 22
104.h.v.1 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Construction | Nos. | Palashbari | 22 | MPSB/HSE/82 | 2026-06-25 | IPC - 33
104.h.v.1 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Construction | Nos. | Palashbari | 20 | MPSB/HSE/83 | 2026-06-25 | IPC - 33
| Cumulative paid upto this Bill | Nos. |  | 250
| Paid upto previous Bill | Nos. |  | 250
| To be paid in this Bill | Nos. |  | 0
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly |  | 1 | Jun'24 - Aug'24 (Q1) | - | IPC - 04
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/122 Sep'24 - Dec'24 (Q2) | 2024-12-30 | IPC - 22
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/123 Sep'24 - Dec'24 (Q2) | 2024-12-30 | IPC - 22
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/146 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 22
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/147 Jan'25 - Mar'25 (Q3) | 2025-03-31 | IPC - 22
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/175 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 22
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/176 Apr'25 - Jun'25 (Q4) | 2025-06-30 | IPC - 22
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/189 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 22
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/190 Jul'25 - Sep'25 (Q1) | 2025-09-30 | IPC - 22
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/HSE/49 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/HSE/50 Oct'25 - Dec'25 (Q2) | 2025-12-31 | IPC - 25
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/209 Jan'26 - Mar'26 (Q3) | 2026-03-31 | IPC - 29
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/210 Jan'26 - Mar'26 (Q3) | 2026-03-31 | IPC - 29
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Palashbari | 0.5 | MPSB/Temp/207 Apr'26 - Jun'26 (Q4) | 2026-06-23 | IPC - 33
104.h.v.2 | Provision of establishment of Sewage and Water Treatment Plant - Toilets - Maintenance | Quarterly | Sualkuchi | 0.5 | MPSB/Temp/208 Apr'26 - Jun'26 (Q4) | 2026-06-23 | IPC - 33
| Cumulative paid upto this Bill | Quarterly |  | 8
| Paid upto previous Bill | Quarterly |  | 8
| To be paid in this Bill | Quarterly |  | 0

## Schedule 2
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
Period of bill : 1st Jul'26 to 31st Jul'26
Schedule 2 - Validation of Survey Data, Investigation, Design and As-Built Drawings | [7 empty] | IPC - 34
Measurement Sheet
Item No. | Item Description | UoM | Location | Executed Quantity | RFI No. / Letter No. / Period | Date | Bill No. | Remarks
201 | Site survey, establishment of bench marks, validation of ROW, identification of borrow areas
201.a | Establishment of Bench Marks | Kms |  | 12.21 | MPSB/SUR/1 | 2024-06-07 | IPC - 02
| Cumulative paid upto this Bill | Kms |  | 12.21
| Paid upto previous Bill | Kms |  | 12.21
| To be paid in this Bill | Kms |  | 0
201.b | Completion of Site Survey | Kms |  | 12.21 | MPSB/SUR/3 | 2024-06-15 | IPC - 02
| Cumulative paid upto this Bill | Kms |  | 12.21
| Paid upto previous Bill | Kms |  | 12.21
| To be paid in this Bill | Kms |  | 0
201.c | Validation of ROW | Kms |  | 5.6 | MPSB/SUR/4 | 2024-06-18 | IPC - 02
201.c | Validation of ROW | Kms |  | 6.61 | MPSB/SUR/5 | 2024-06-19 | IPC - 02
| Cumulative paid upto this Bill | Kms |  | 12.21
| Paid upto previous Bill | Kms |  | 12.21
| To be paid in this Bill | Kms |  | 0
201.d | Identification of Borrow Areas | Nos. |  | 2 | GM/MM/86-B(40)/Pt.VIII/214-17 GM/MM/86-B(40)/Pt. V/388-92 | 31-May-24 06-Jun-24 | IPC - 03
201.d | Identification of Borrow Areas | Nos. |  | 3 | GM/MM/86-B(40)/Pt. V/378-82 GM/MM/86-B(40)/Pt.VIII/383-87 GM/MM/86-B(40)/Pt.VIII/373-77 | 06-Jun-24 06-Jun-24 06-Jun-24 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 5
| Paid upto previous Bill | Nos. |  | 5
| To be paid in this Bill | Nos. |  | 0
202 | Site data collection, Detailed Geotechnical and Hydrological investigations and report submission & approval
202.a.i | Completion of Topographical Survey - Submission | Kms |  | 12.21 | MPSB/SUR/2 | 2024-06-12 | IPC - 02
| Cumulative paid upto this Bill | Kms |  | 12.21
| Paid upto previous Bill | Kms |  | 12.21
| To be paid in this Bill | Kms |  | 0
202.a.ii | Completion of Topographical Survey - Approval | Kms |  | 12.21 | RI-1624-SO-HWB-BR-S&I-0010-R0-254 | 2024-08-12 | IPC - 04
| Cumulative paid upto this Bill | Kms |  | 12.21
| Paid upto previous Bill | Kms |  | 12.21
| To be paid in this Bill | Kms |  | 0
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 2 | MPSB/QAQC/1 | 2024-06-07 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 3 | MPSB/QAQC/2 | 2024-06-08 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 4 | MPSB/QAQC/3 | 2024-06-10 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 1 | MPSB/QAQC/4 | 2024-06-11 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 5 | MPSB/QAQC/5 | 2024-06-12 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 5 | MPSB/QAQC/6 | 2024-06-13 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 5 | MPSB/QAQC/7 | 2024-06-14 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 5 | MPSB/QAQC/8 | 2024-06-15 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 2 | MPSB/QAQC/9 | 2024-06-17 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 2 | MPSB/QAQC/10 | 2024-06-18 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 2 | MPSB/QAQC/11 | 2024-06-19 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 2 | MPSB/QAQC/12 | 2024-06-20 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 2 | MPSB/QAQC/13 | 2024-06-21 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 4 | MPSB/QAQC/14 | 2024-06-22 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 2 | MPSB/QAQC/15 | 2024-06-24 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 1 | MPSB/QAQC/16 | 2024-06-25 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 5 | MPSB/QAQC/17 | 2024-06-26 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 2 | MPSB/QAQC/18 | 2024-06-27 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 6 | MPSB/QAQC/19 | 2024-06-28 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 6 | MPSB/QAQC/20 | 2024-06-29 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 5 | MPSB/QAQC/21 | 2024-06-29 | IPC - 02
202.b.i | Detailed Geotechnical Investigation - Submission | Nos. |  | 25 | MPSB/L&T/TIIC/2024/260 | 2024-07-31 | IPC - 03
| Cumulative paid upto this Bill | Nos. |  | 96
| Paid upto previous Bill | Nos. |  | 96
| To be paid in this Bill | Nos. |  | 0
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 9 | HBT/1624/SO/APR/2024/0220/415 | 2024-10-28 | IPC - 08 | P10 to P18
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 7 | HBT/1624/SO/APR/2024/0251/445 | 2024-11-12 | IPC - 08 | P19 to P26
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 10 | HBT/1624/SO/GIR/2024/0265/459 | 2024-11-15 | IPC - 08 | Northern & Southern Viaduct
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 1 | HBT/1624/SO/APR/2024/0251/445 | 2024-11-12 | IPC - 11 | P19 to P26
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 4 | HBT/1624/SO/APR/2024/0310/503 | 2024-12-03 | IPC - 11 | P6 to P9
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 4 | HBT/1624/SO/APR/2024/0319/512 | 2024-12-10 | IPC - 11 | P27 to P30
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 26 | HBT/1624/SO/GIR/2025/0378/569 | 2025-01-03 | IPC - 11 | Wetland Viaducts
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 2 | HBT/1624/SO/GIR/2025/703 | 2025-06-07 | IPC - 16 | P4 & P5
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 4 | HBT/1624/SO/GIR/2024/0265/459 | 2024-11-15 | IPC - 16 | Rescue Span
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 17 | HBT/1624/SO/GIR/2025/712 HBT/1624/SO/GIR/2025/714 | 2025-06-07 | IPC - 16 | Approach Formations
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 4 | HBT/1624/SO/GIR/2025/780 | 4-Jul-25 | IPC - 18 | VUP
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 2 | HBT/1624/SO/GIR/2025/815 | 15-Jul-25 | IPC - 18 | VUP
202.b.ii | Detailed Geotechnical Investigation - Approval | Nos. |  | 6 | HBT/1624/SO/GDV/2025/844 HBT/1624/SO/GDV/2025/865 | 26-Jul-25 31-Jul-25 | IPC - 18 | Approach Formations
| Cumulative paid upto this Bill | Nos. |  | 96
| Paid upto previous Bill | Nos. |  | 96
| To be paid in this Bill | Nos. |  | 0
202.c.i | Detailed Hydrological Investigation - Submission | LS |  | 1 | MPSB/L&T/TIIC/DGN/2024/033 | 2024-09-11 | IPC - 05
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203 | Preliminary Design of the approach formations, retaining structures, drainage system, bridges, major and /or minor structure and miscellaneous work.
203.a.i | Approach Formations (GAD / P&P) - Submission | Kms |  | 7.314 | MPSB/L&T/TIIC/DGN/2024/022 | 2024-08-30 | IPC - 04
| Cumulative paid upto this Bill | Kms |  | 7.314
| Paid upto previous Bill | Kms |  | 7.314
| To be paid in this Bill | Kms |  | 0
203.a.ii | Approach Formations (GAD / P&P) - Approval | Kms |  | 5.321 | HBT/1624/SO/APR/2024/0167/362 | 2024-09-30 | IPC - 05 |  | 0 | 5392 | 5.392 | 800 | 1300 | 0.5
203.a.ii | Approach Formations (GAD / P&P) - Approval | Kms |  | 1.993 | HBT/1624/SO/APR/2024/0256/450 HBT/1624/SO/APR/2024/0279/473 | 12-Nov-24 18-Nov-24 | IPC - 08 |  | 9424 | 10217 | 0.793 | 2600 | 3052 | 0.452
[9 empty] | 10325 | 10600 | 0.275 | 4220 | 4480 | 0.26
| Cumulative paid upto this Bill | Kms |  | 7.314 |  |  |  |  | 11356 | 12210 | 0.854 | 4515 | 4750 | 0.235
| Paid upto previous Bill | Kms |  | 7.314 | [6 empty] | 7.314 | 4750 | 4780 | 0.03
| To be paid in this Bill | Kms |  | 0 | [7 empty] | 9424 | 9880 | 0.456
203.b.i | Retaining Structures (GAD / P&P) - Submission | Kms |  | 5.2 | MPSB/L&T/TIIC/DGN/2025/473 | 2025-11-21 | IPC - 23 | [6 empty] | 1.933
| Cumulative paid upto this Bill | Kms |  | 5.2
| Paid upto previous Bill | Kms |  | 5.2
| To be paid in this Bill | Kms |  | 0
203.b.iI | Retaining Structures - Documents & Reports - Approval | Kms |  | 1 | HBT/1624/SO/DGV/2026/1511 | 2026-03-31 | IPC - 29 | Toe Wall | [5 empty] | 2.389
203.b.iI | Retaining Structures - Documents & Reports - Approval | Kms |  | 4.2 | HBT/1624/SO/DGV/2025/1164 HBT/1624/SO/DGV/2025/1142 HBT/1624/SO/DGV/2025/1139 | 13-Nov-25 8-Nov-25 8-Nov-25 | IPC - 29 | Box Culvert - R/W VUP - R/W
| Cumulative paid upto this Bill | Kms |  | 5.2
| Paid upto previous Bill | Kms |  | 5.2
| To be paid in this Bill | Kms |  | 0
203.c.i | Drainage (GAD / P&P) - Submission | Kms |  | 0.68 | MPSB/L&T/TIIC/DGN/2024/64 | 2024-11-07 | IPC - 09
[12 empty] | 300 | 800 | 500
| Cumulative paid upto this Bill | Kms |  | 0.68 | [7 empty] | 950 | 1130 | 180
| Paid upto previous Bill | Kms |  | 0.68 | [7 empty] | 800 | 950 | 150
| To be paid in this Bill | Kms |  | 0 | [9 empty] | 830
203.c.ii | Drainage (GAD / P&P) - Approval | Kms |  | 0.68 | HBT/1624/SO/APR/2024/0368/559 | 2024-12-28 | IPC - 09
| Cumulative paid upto this Bill | Kms |  | 0.68
| Paid upto previous Bill | Kms |  | 0.68
| To be paid in this Bill | Kms |  | 0
203.d.i | Wetland Viaduct (GAD / P&P) - Submission | Nos. |  | 2 | MPSB/L&T/TIIC/DGN/2024/026 | 2024-08-31 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
203.d.ii | Wetland Viaduct (GAD / P&P) - Approval | Nos. |  | 2 | HBT/1624/SO/DGV/2025/580 | 2025-04-16 | IPC - 14
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
203.e.i | Approach Viaduct (GAD / P&P) - Submission | Nos. |  | 2 | MPSB/L&T/TIIC/DGN/2024/026 | 2024-08-31 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
203.e.ii | Approach Viaduct (GAD / P&P) - Approval | Nos. |  | 2 | HBT/1624/SO/DGV/2025/580 | 2025-04-16 | IPC - 14
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
203.f.i | Vehicular Underpass (GAD / P&P) - Submission | Nos. |  | 1 | MPSB/L&T/TIIC/DGN/2024/026 | 2024-08-31 | IPC - 04
203.f.i | Vehicular Underpass (GAD / P&P) - Submission | Nos. |  | 1 | MPSB/L&T/TIIC/DGN/2025/210 | 2025-05-12 | IPC - 15
203.f.i | Vehicular Underpass (GAD / P&P) - Submission | Nos. |  | 1 | MPSB/L&T/TIIC/DGN/2025/423 | 2025-10-14 | IPC - 22
| Cumulative paid upto this Bill | Nos. |  | 3
| Paid upto previous Bill | Nos. |  | 3
| To be paid in this Bill | Nos. |  | 0
203.f.ii | Vehicular Underpass (GAD / P&P) - Approval | Nos. |  | 3 | HBT/1624/SO/DGV/2025/978 HBT/1624/SO/DGV/2025/979 HBT/1624/SO/DGV/2025/980 | 8-Sep-25 8-Sep-25 8-Sep-25 | IPC - 27
| Cumulative paid upto this Bill | Nos. |  | 3
| Paid upto previous Bill | Nos. |  | 3
| To be paid in this Bill | Nos. |  | 0
203.g.i | Culverts (GAD) - Submission | Nos. |  | 2 | MPSB/L&T/TIIC/DGN/2024/024 | 2024-08-31 | IPC - 04
203.g.i | Culverts (GAD) - Submission | Nos. |  | 2 | MPSB/L&T/TIIC/DGN/2024/026 | 2024-08-31 | IPC - 04
203.g.i | Culverts (GAD) - Submission | Nos. |  | 4 | MPSB/L&T/TIIC/DGN/2024/157 MPSB/L&T/TIIC/DGN/2024/162 | 8-Mar-25 15-Mar-25 | IPC - 08
203.g.i | Culverts (GAD) - Submission | Nos. |  | 1 | MPSB/L&T/TIIC/DGN/2024/162 | 2025-03-15 | IPC - 15
203.g.i | Culverts (GAD) - Submission | Nos. |  | 9 | MPSB/L&T/TIIC/DGN/2024/423 | 2025-10-14 | IPC - 22
| Cumulative paid upto this Bill | Nos. |  | 18
| Paid upto previous Bill | Nos. |  | 18
| To be paid in this Bill | Nos. |  | 0
203.g.ii | Culverts (GAD) - Approval | Nos. |  | 4 | HBT/1624/SO/APR/2025/373/564 | 2025-01-01 | IPC - 10
203.g.ii | Culverts (GAD) - Approval | Nos. |  | 5 | HBT/1624/SO/APR/2025/530 HBT/1624/SO/DGV/2025/584 HBT/1624/SO/DGV/2025/672 | 28-Mar-25 18-Apr-25 24-May-25 | IPC - 15
203.g.ii | Culverts (GAD) - Approval | Nos. |  | 9 | HBT/1624/SO/DGV/2025/1031 HBT/1624/SO/DGV/2025/1035 | 22-Sep-25 24-Sep-25 | IPC - 27
| Cumulative paid upto this Bill | Nos. |  | 18
| Paid upto previous Bill | Nos. |  | 18
| To be paid in this Bill | Nos. |  | 0
203.h.i | Main Bridge (GAD) - Submission | Nos. |  | 1 | MPSB/L&T/TIIC/DGN/2024/016 | 2024-07-31 | IPC - 03
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
203.h.ii | Main Bridge (GAD) - Approval | Nos. |  | 1 | HBT/1624/SO/APR/2024/0091/286 | 2024-08-27 | IPC - 04
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
203.i.i.1 | Miscellaneous Works - Temporary Access Bridge - Submission | LS |  | 1 | MPSB/L&T/TIIC/2024/166 | 2024-06-07 | IPC - 02
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.i.2 | Miscellaneous Works - Temporary Access Bridge - Approval | LS |  | 1 | HBT/1624/SO/PSR/2024/0100/292 | 2024-08-31 | IPC - 04
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.ii.1 | Miscellaneous Works - Casting Yard (Layout) - Submission | LS |  | 1 | MPSB/Temp/33 | 2024-06-24 | IPC - 02
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.iii.1 | Miscellaneous Works - River Training Works - Submission | LS |  | 1 | MPSB/L&T/TIIC/DGN/2025/172 | 2025-03-20 | IPC - 13 | Southern
203.i.iii.1 | Miscellaneous Works - River Training Works - Submission | LS |  | 1 | MPSB/L&T/TIIC/DGN/2025/273 | 2025-06-23 | IPC - 16 | Northern
| Cumulative paid upto this Bill | LS |  | 2
| Paid upto previous Bill | LS |  | 2
| To be paid in this Bill | LS |  | 0
203.i.ii.2 | Miscellaneous Works - Casting Yard (Layout) - Approval | LS |  | 1 | RI/1624/SO/HWB/BR/APR/0025/R0/179 | 2024-06-25 | IPC - 02
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.iv.1 | Miscellaneous Works - Labour Camps - Submission | LS |  | 1 | MPSB/Temp/34 | 2024-06-24 | IPC - 02
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.iv.2 | Miscellaneous Works - Labour Camps - Approval | LS |  | 1 | RI/1624/SO/HWB/BR/APR/0025/R0/179 | 2024-06-25 | IPC - 02
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.v.1 | Miscellaneous Works - Office - Submission | LS |  | 0.5 | MPSB/Temp/36 | 2024-06-25 | IPC - 02
203.i.v.1 | Miscellaneous Works - Office - Submission | LS |  | 0.5 | MPSB/Temp/37 | 2024-06-25 | IPC - 02
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.v.2 | Miscellaneous Works - Office - Approval | LS |  | 1 | RI/1624/SO/HWB/BR/APR/0025/R0/179 | 2024-06-25 | IPC - 02
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.vi.1 | Miscellaneous Works - Laboratory - Submission | LS |  | 1 | MPSB/Temp/35 | 2024-06-24 | IPC - 02
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.vi.2 | Miscellaneous Works - Laboratory - Approval | LS |  | 1 | RI/1624/SO/HWB/BR/APR/0025/R0/179 | 2024-06-25 | IPC - 02
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.vii.1 | Miscellaneous Works - Precast Moulds - Submission | LS |  | 1 | MPSB/L&T/TIIC/DGN/TMP/2025/145 | 2025-02-27 | IPC - 11
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.viii.1 | Miscellaneous Works - Traffic Signages - Submission | LS |  | 1 | MPSB/L&T/TIIC/DGN/2024/098 | 2024-12-09 | IPC - 09
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.viii.2 | Miscellaneous Works - Traffic Signages - Approval | LS |  | 1 | HBT/1624/SO/APR/2024/0347/538 | 2024-12-18 | IPC - 09
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.ix.1 | Miscellaneous Works - Road Marking - Submission | LS |  | 1 | MPSB/L&T/TIIC/DGN/2024/098 | 2024-12-09 | IPC - 09
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.ix.2 | Miscellaneous Works - Road Marking - Approval | LS |  | 1 | HBT/1624/SO/APR/2024/0347/538 | 2024-12-18 | IPC - 09
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.xi.1 | Miscellaneous Works - Bridge Health Monitoring - Submission | LS |  | 1 | MPSB/L&T/TIIC/DGN/2024/397 | 2025-09-30 | IPC - 20
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
203.i.xi.2 | Miscellaneous Works - Bridge Health Monitoring - Approval | LS |  | 1 | HBT/1624/SO/DGV/2025/1081 | 2025-10-18 | IPC - 22
| Cumulative paid upto this Bill | LS |  | 1
| Paid upto previous Bill | LS |  | 1
| To be paid in this Bill | LS |  | 0
204 | Final Technical Design of the approach formation, retaining structures, drainage system, bridges, major and /or minor structures and miscellaneous work
204.a.i | Approach Formations - Documents & Reports - Submission | Kms |  | 7.314 | MPSB/L&T/TIIC/DGN/2024/045 MPSB/L&T/TIIC/DGN/2024/060 MPSB/L&T/TIIC/DGN/2024/063 | 05-Oct-24 31-Oct-24 31-Oct-24 | IPC - 07 | Km 0+000 to Km 12+210
| Cumulative paid upto this Bill | Kms |  | 7.314
| Paid upto previous Bill | Kms |  | 7.314
| To be paid in this Bill | Kms |  | 0
204.a.ii | Approach Formations - Documents & Reports - Approval | Kms |  | 7.314 | HBT/1624/SO/APR/2024/0360/551 | 2024-12-24 | IPC - 09 | Km 0+000 to Km 12+210
| Cumulative paid upto this Bill | Kms |  | 7.314
| Paid upto previous Bill | Kms |  | 7.314
| To be paid in this Bill | Kms |  | 0
204.a.iii | Approach Formations - Documents & Reports - Issue of GFC Drawings | Kms |  | 7.314 | HBT/1624/SO/DGV/2025/1213 | 2025-11-25 | IPC - 23 | Km 0+000 to Km 12+210
| Cumulative paid upto this Bill | Kms |  | 7.314
| Paid upto previous Bill | Kms |  | 7.314
| To be paid in this Bill | Kms |  | 0
204.b.i | Retaining Structures - Documents & Reports - Submission | Kms |  | 5.2 | MPSB/L&T/TIIC/DGN/2025/242 MPSB/L&T/TIIC/DGN/2025/249 MPSB/L&T/TIIC/DGN/2025/281 | 30-May-25 02-Jun-25 26-Jun-25 | IPC - 22
| Cumulative paid upto this Bill | Kms |  | 5.2
| Paid upto previous Bill | Kms |  | 5.2
| To be paid in this Bill | Kms |  | 0
204.b.ii | Retaining Structures - Documents & Reports - Approval | Kms |  | 1 | HBT/1624/SO/DGV/2026/1511 | 2026-03-31 | IPC - 29 | Toe Wall
204.b.ii | Retaining Structures - Documents & Reports - Approval | Kms |  | 4.2 | HBT/1624/SO/DGV/2025/1164 HBT/1624/SO/DGV/2025/1142 HBT/1624/SO/DGV/2025/1139 | 13-Nov-25 8-Nov-25 8-Nov-25 | IPC - 29 | Box Culvert - R/W VUP - R/W
| Cumulative paid upto this Bill | Kms |  | 5.2
| Paid upto previous Bill | Kms |  | 5.2
| To be paid in this Bill | Kms |  | 0
204.c.i | Drainage - Documents & Reports - Submission | Kms |  | 0.27 | MPSB/L&T/TIIC/DGN/2025/246 | 2025-05-31 | IPC - 18 | Km 0+530 to Km 0+800
204.c.i | Drainage - Documents & Reports - Submission | Kms |  | 0.23 | MPSB/L&T/TIIC/DGN/2025/306 | 2025-07-07 | IPC - 18 | Km 0+300 to Km 0+530
204.c.i | Drainage - Documents & Reports - Submission | Kms |  | 0.15 | MPSB/L&T/TIIC/DGN/2025/506 | 2025-12-15 | IPC - 25 | Km 0+950 to Km 1+100
| Cumulative paid upto this Bill | Kms |  | 0.65
| Paid upto previous Bill | Kms |  | 0.65
| To be paid in this Bill | Kms |  | 0
204.c.ii | Drainage - Documents & Reports - Approval | Kms |  | 0.23 | HBT/1624/SO/DGV/2026/1334 | 2026-01-09 | IPC - 26 | Km 0+300 to Km 0+530
204.c.ii | Drainage - Documents & Reports - Approval | Kms |  | 0.27 | HBT/1624/SO/DGV/2026/1512 | 2026-03-31 | IPC - 29 | Km 0+530 to Km 0+800
204.c.ii | Drainage - Documents & Reports - Approval | Kms |  | 0.15 | HBT/1624/SO/DGV/2026/1577 | 2026-04-27 | IPC - 30 | Km 0+950 to Km 1+100
| Cumulative paid upto this Bill | Kms |  | 0.65
| Paid upto previous Bill | Kms |  | 0.65
| To be paid in this Bill | Kms |  | 0
204.c.iii | Drainage - Issue of GFC Drawings | Kms |  | 0.23 | HBT/1624/SO/DGV/2026/1667 | 2026-06-10 | IPC - 33 | Km 0+300 to Km 0+530
| Cumulative paid upto this Bill | Kms |  | 0.23
| Paid upto previous Bill | Kms |  | 0.23
| To be paid in this Bill | Kms |  | 0
204.d.i.1 | Wetland Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.30769 | MPSB/L&T/TIIC/DGN/2024/046 | 2024-10-05 | IPC - 07 | 4 / 26 Nos. - Submitted - WV2 - P3 to P6
204.d.i.1 | Wetland Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 1.3077 | MPSB/L&T/TIIC/DGN/2024/071 MPSB/L&T/TIIC/DGN/2024/075 MPSB/L&T/TIIC/DGN/2024/078 MPSB/L&T/TIIC/DGN/2024/089 | 18-Nov-24 18-Nov-24 18-Nov-24 25-Nov-24 | IPC - 08 | 17 / 26 Nos. - Submitted - WV2 - P0 to P2, P7 to P17, P19 to P21
204.d.i.1 | Wetland Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.38462 | MPSB/L&T/TIIC/DGN/2025/158 MPSB/L&T/TIIC/DGN/2025/165 | 08-Mar-25 17-Mar-25 | IPC - 13 | 5 / 26 Nos. - Submitted WV2 - P18 WV1 - P0 to P3
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.d.i.2 | Wetland Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.30769 | HBT/1624/SO/DGV/2025/579 HBT/1624/SO/DGV/2025/583 | 16-Apr-25 17-Apr-25 | IPC - 14 | 4 / 26 Nos. - Submitted - WV2 - P1, P2, P4 & P5
204.d.i.2 | Wetland Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 1.2308 | HBT/1624/SO/DGV/2025/627 HBT/1624/SO/DGV/2025/633 | 3-May-25 7-May-25 | IPC - 15 | 16 / 26 Nos. - Submitted - WV2 - P3, P6 to P20
204.d.i.2 | Wetland Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.15385 | HBT/1624/SO/DGV/2025/755 | 2025-06-26 | IPC - 18 | 2 / 26 Nos. - Submitted - WV2 - P0, P21
204.d.i.2 | Wetland Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.30769 | HBT/1624/SO/DGV/2025/781 | 2025-07-04 | IPC - 18 | 4 / 26 Nos. - Submitted - WV1 - P0 to P3
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.d.i.3 | Wetland Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 0.46154 | HBT/1624/SO/APR/2025/0857 | 2025-07-29 | IPC - 18 | 6 / 26 Nos. - Submitted - WV2 - P1 to P6
204.d.i.3 | Wetland Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 1.077 | HBT/1624/SO/APR/2025/1159 | 2025-11-12 | IPC - 23 | 14 / 26 Nos. - Submitted - WV2 - P7 to P20
204.d.i.3 | Wetland Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 0.15385 | HBT/1624/SO/APR/2026/1333 | 2026-01-09 | IPC - 26 | 2 / 26 Nos. - Submitted - WV2 - P0, P21
204.d.i.3 | Wetland Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 0.308 | HBT/1624/SO/APR/2026/1332 | 2026-01-09 | IPC - 26 | 4 / 26 Nos. - Submitted - WV1 - P0 to P3
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.d.ii.1 | Wetland Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 0.30769 | MPSB/L&T/TIIC/DGN/2024/046 | 2024-10-05 | IPC - 07 | 4 / 26 Nos. - Submitted - WV2 - P3 to P6
204.d.ii.1 | Wetland Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 1.3077 | MPSB/L&T/TIIC/DGN/2024/071 MPSB/L&T/TIIC/DGN/2024/075 MPSB/L&T/TIIC/DGN/2024/078 MPSB/L&T/TIIC/DGN/2024/089 | 18-Nov-24 18-Nov-24 18-Nov-24 25-Nov-24 | IPC - 08 | 17 / 26 Nos. - Submitted - WV2 - P0 to P2, P7 to P17, P19 to P21
204.d.ii.1 | Wetland Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 0.38462 | MPSB/L&T/TIIC/DGN/2025/158 MPSB/L&T/TIIC/DGN/2025/165 | 08-Mar-25 17-Mar-25 | IPC - 13 | 5 / 26 Nos. - Submitted - WV2 - 18, WV1 - P0 to P3
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.d.ii.2 | Wetland Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.076923 | HBT/1624/SO/DGV/2025/579 | 2025-04-16 | IPC - 20 | 2 / 26 Nos. - Approved - WV2 - P4 & P5 - 50% released
204.d.ii.2 | Wetland Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.076923 | HBT/1624/SO/DGV/2025/583 | 2025-04-17 | IPC - 20 | 2 / 26 Nos. - Approved - WV2 - P1 & P2 - 50% released
204.d.ii.2 | Wetland Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.076923 | HBT/1624/SO/DGV/2025/627 | 2025-05-03 | IPC - 20 | 2 / 26 Nos. - Approved - WV2 - P3 & P6 - 50% released
204.d.ii.2 | Wetland Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.53846 | HBT/1624/SO/DGV/2025/633 | 2025-05-07 | IPC - 20 | 14 / 26 Nos. - Approved - WV2 - P7 to P20 - 50% released
204.d.ii.2 | Wetland Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.076923 | HBT/1624/SO/DGV/2025/755 | 2025-06-26 | IPC - 20 | 2 / 26 Nos. - Approved - WV2 - P0, P21 - 50% released
204.d.ii.2 | Wetland Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.15385 | HBT/1624/SO/DGV/2025/781 | 2025-07-04 | IPC - 20 | 4 / 26 Nos. - Approved - WV1 - P0 to P3 - 50% released
204.d.ii.2 | Wetland Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 1 | HBT/1624/SO/DGV/2025/1250 | 2025-12-10 | IPC - 25 | 26 / 26 Nos. - Approved - WV1 - P0 to P3 & WV2 - P0 to P21 - Balance 50% released
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.d.ii.3 | Wetland Viaduct - Substructure - Documents & Reports - Issue of GFC Drawings | Nos. |  | 0.23077 | HBT/1624/SO/APR/2025/1170 | 2025-11-14 | IPC - 23 | 6 / 26 Nos. - Approved - WV2 - P1 to P6 - 50% released
204.d.ii.3 | Wetland Viaduct - Substructure - Documents & Reports - Issue of GFC Drawings | Nos. |  | 0.53846 | HBT/1624/SO/APR/2025/1159 | 2025-11-12 | IPC - 23 | 14 / 26 Nos. - Approved - WV2 - P7 to P20 - 50% released
204.d.ii.3 | Wetland Viaduct - Substructure - Documents & Reports - Issue of GFC Drawings | Nos. |  | 0.077 | HBT/1624/SO/APR/2026/1333 | 2026-01-09 | IPC - 26 | 2 / 26 Nos. - Submitted - WV2 - P0, P21 - 50% released
204.d.ii.3 | Wetland Viaduct - Substructure - Documents & Reports - Issue of GFC Drawings | Nos. |  | 0.154 | HBT/1624/SO/APR/2026/1332 | 2026-01-09 | IPC - 26 | 4 / 26 Nos. - Submitted - WV1 - P0 to P3 - 50% released
204.d.ii.3 | Wetland Viaduct - Substructure - Documents & Reports - Issue of GFC Drawings | Nos. |  | 0.84615 | HBT/1624/SO/DGV/2026/1386 | 2026-02-05 | IPC - 30 | 22/ 26 Nos. - Approved - WV2 - P0 to P21 - Balance 50% released
204.d.ii.3 | Wetland Viaduct - Substructure - Documents & Reports - Issue of GFC Drawings | Nos. |  | 0.15385 | HBT/1624/SO/LTR/2026/1452 | 2026-03-09 | IPC - 30 | 4 / 26 Nos. - Approved- WV1 - P0 to P3 - Balance 50% released
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.d.iii.1 | Wetland Viaduct - Superstructure - Documents & Reports - Submission | Nos. |  | 2 | MPSB/L&T/TIIC/DGN/2024/048 | 2024-10-09 | IPC - 07
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.d.iii.2 | Wetland Viaduct - Superstructure - Documents & Reports - Approval | Nos. |  | 2 | HBT/1624/SO/DGV/2025/664 | 2025-05-22 | IPC - 15
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.d.iii.3 | Wetland Viaduct - Superstructure - Issue of GFC Drawings | Nos. |  | 2 | HBT/1624/SO/APR/2025/0852 | 2025-07-28 | IPC - 18
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.e.i.1 | Approach Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.5 | MPSB/L&T/TIIC/DGN/2024/040 MPSB/L&T/TIIC/DGN/2024/056 | 27-Sep-24 26-Oct-24 | IPC - 07 | 4 / 16 Nos. - Submitted - SAV - P1 & P2, NAV - P31 & P34
204.e.i.1 | Approach Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.5 | MPSB/L&T/TIIC/DGN/2024/059 MPSB/L&T/TIIC/DGN/2024/070 MPSB/L&T/TIIC/DGN/2024/081 | 5-Nov-24 18-Nov-24 21-Nov-24 | IPC - 08 | 4 / 16 Nos. - Submitted - SAV - P0, NAV - P32, P33 & P35
204.e.i.1 | Approach Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.125 | MPSB/L&T/TIIC/DGN/2025/169 | 2025-03-19 | IPC - 13 | 1 / 16 Nos. - Submitted - SAV - P1R
204.e.i.1 | Approach Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.25 | MPSB/L&T/TIIC/DGN/2025/236 | 2025-05-28 | IPC - 16 | 2 / 16 Nos. - Submitted - SAV - P4 & P5
204.e.i.1 | Approach Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.125 | MPSB/L&T/TIIC/DGN/2025/226 | 2025-05-26 | IPC - 18 | 1 / 16 Nos. - Submitted - SAV - P2R
204.e.i.1 | Approach Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.125 | MPSB/L&T/TIIC/DGN/2025/245 | 2025-05-31 | IPC - 18 | 1 / 16 Nos. - Submitted | 1 / 16 Nos. - Submitted - SAV - P1R
204.e.i.1 | Approach Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.125 | MPSB/L&T/TIIC/DGN/2025/344 | 2025-07-29 | IPC - 19 | 1 / 16 Nos. - Submitted | 1 / 16 Nos. - Submitted - SAV - P0
204.e.i.1 | Approach Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.125 | MPSB/L&T/TIIC/DGN/2025/230 | 2025-05-27 | IPC - 19 | 1 / 16 Nos. - Submitted | 1 / 16 Nos. - Submitted - SAV - P1
204.e.i.1 | Approach Viaduct - Foundation - Documents & Reports - Submission | Nos. |  | 0.125 | MPSB/L&T/TIIC/DGN/2025/229 | 2025-05-27 | IPC - 19 | 1 / 16 Nos. - Submitted | 1 / 16 Nos. - Submitted - SAV - P2
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.e.i.2 | Approach Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.25 | HBT/1624/SO/DGV/2025/730 HBT/1624/SO/DGV/2025/731 | 2025-06-16 | IPC - 16 | 2 / 16 Nos. - Approved - SAV - P1 & P2 | P1,P2
204.e.i.2 | Approach Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.125 | HBT/1624/SO/DGV/2025/753 | 2025-06-25 | IPC - 19 | 1 / 16 Nos. - Approved - SAV - P3 | P3
204.e.i.2 | Approach Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.125 | HBT/1624/SO/DGV/2025/923 | 2025-08-22 | IPC - 19 | 1 / 16 Nos. - Approved - SAV - P0 | P0
204.e.i.2 | Approach Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.25 | HBT/1624/SO/DGV/2025/990 | 2025-09-10 | IPC - 20 | 2 / 16 Nos. - Approved - SAV - P4 & P5
204.e.i.2 | Approach Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.125 | HBT/1624/SO/DGV/2025/998 | 2025-09-12 | IPC - 20 | 1 / 16 Nos. - Approved - SAV - P2R
204.e.i.2 | Approach Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.125 | HBT/1624/SO/DGV/2025/1001 | 2025-09-12 | IPC - 20 | 1 / 16 Nos. - Approved - SAV - P1R
204.e.i.2 | Approach Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.25 | HBT/1624/SO/DGV/2025/1009 | 2025-09-16 | IPC - 20 | 1 / 16 Nos. - Approved - NAV - P32R & 33R
204.e.i.2 | Approach Viaduct - Foundation - Documents & Reports - Approval | Nos. |  | 0.75 | HBT/1624/SO/DGV/2025/1074 | 2025-10-14 | IPC - 22 | 1 / 16 Nos. - Approved - NAV - P31 to 36
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.e.i.3 | Approach Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 0.125 | HBT/1624/SO/APR/2025/0854 HBT/1624/SO/APR/2025/0859 | 28-Jul-25 29-Jul-25 | IPC - 18 | 2 / 16 Nos. - Submitted - SAV - P1 & P2 - 50% released
204.e.i.3 | Approach Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 0.125 | HBT/1624/SO/APR/2025/0854 HBT/1624/SO/APR/2025/0859 | 28-Jul-25 29-Jul-25 | IPC - 22 | 2 / 16 Nos. - Submitted - SAV - P1 & P2 - 50% released
204.e.i.3 | Approach Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 0.125 | HBT/1624/SO/APR/2025/0971 | 2025-09-05 | IPC - 22 | 1 / 16 Nos. - Submitted - SAV - P3
204.e.i.3 | Approach Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 0.25 | HBT/1624/SO/APR/2025/1176 | 2025-11-17 | IPC - 23 | 2 / 16 Nos. - Submitted - SAV - P1R & P2R
204.e.i.3 | Approach Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 0.25 | HBT/1624/SO/APR/2025/1167 | 2025-11-12 | IPC - 23 | 2 / 16 Nos. - Submitted - NAV - P32R & P33R
204.e.i.3 | Approach Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 0.25 | HBT/1624/SO/APR/2025/1269 | 2025-12-15 | IPC - 25 | 2 / 16 Nos. - Submitted - SAV - P4 & P5
204.e.i.3 | Approach Viaduct - Foundation - Issue of GFC Drawings | Nos. |  | 0.75 | HBT/1624/SO/APR/2025/1255 | 2025-12-11 | IPC - 25 | 6 / 16 Nos. - Submitted - NAV - P31 to P36 | P0 is pending
| Cumulative paid upto this Bill | Nos. |  | 1.875
| Paid upto previous Bill | Nos. |  | 1.875
| To be paid in this Bill | Nos. |  | 0
204.e.ii.1 | Approach Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 0.5 | MPSB/L&T/TIIC/DGN/2024/040 MPSB/L&T/TIIC/DGN/2024/056 | 27-Sep-24 26-Oct-24 | IPC - 07 | 4 / 16 Nos. - Submitted - SAV - P1 & P2, NAV - P31 & P34
204.e.ii.1 | Approach Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 0.25 | MPSB/L&T/TIIC/DGN/2024/059 MPSB/L&T/TIIC/DGN/2024/070 MPSB/L&T/TIIC/DGN/2024/081 | 5-Nov-24 18-Nov-24 21-Nov-24 | IPC - 08 | 2 / 16 Nos. - Submitted - SAV - P0, NAV - P33
204.e.ii.1 | Approach Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 0.125 | MPSB/L&T/TIIC/DGN/2025/169 | 2025-03-19 | IPC - 13 | 1 / 16 Nos. - Submitted - SAV - P3
204.e.ii.1 | Approach Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 0.25 | MPSB/L&T/TIIC/DGN/2025/226 MPSB/L&T/TIIC/DGN/2025/245 | 26-May-25 31-May-25 | IPC - 18 | 2 / 16 Nos. - Submitted - SAV - P1R & P2R | 2 / 16 Nos. - Submitted - SAV - P1R & P2R
204.e.ii.1 | Approach Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 0.25 | MPSB/L&T/TIIC/DGN/2025/378 | 2025-09-12 | IPC - 22 | 2 / 16 Nos. - Submitted - NAV - P31R & P32R
204.e.ii.1 | Approach Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 0.25 | MPSB/L&T/TIIC/DGN/2025/386 | 2025-09-23 | IPC - 22 | 2 / 16 Nos. - Submitted - NAV - P32 & P35
204.e.ii.1 | Approach Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 0.125 | MPSB/L&T/TIIC/DGN/2025/401 | 2025-10-03 | IPC - 22 | 1 / 16 Nos. - Submitted - NAV - P36
204.e.ii.1 | Approach Viaduct - Substructure - Documents & Reports - Submission | Nos. |  | 0.25 | MPSB/L&T/TIIC/DGN/2025/236 | 2025-05-28 | IPC - 23 | 2 / 16 Nos. - Submitted - SAV - P4 & P5
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.e.ii.2 | Approach Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.125 | HBT/1624/SO/DGV/2025/730 HBT/1624/SO/DGV/2025/731 | 2025-06-16 | IPC - 20 | 2 / 16 Nos. - Approved - SAV - P1 & P2 - 50% released | P1,P2
204.e.ii.2 | Approach Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.0625 | HBT/1624/SO/DGV/2025/753 | 2025-06-25 | IPC - 20 | 1 / 16 Nos. - Approved - SAV - P3 - 50% released | P3
204.e.ii.2 | Approach Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.0625 | HBT/1624/SO/DGV/2025/923 | 2025-08-22 | IPC - 20 | 1 / 16 Nos. - Approved - SAV - P0 - 50% released | P0
204.e.ii.2 | Approach Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.0625 | HBT/1624/SO/DGV/2025/998 | 2025-09-12 | IPC - 20 | 1 / 16 Nos. - Approved - SAV - P2R - 50% released | P2R
204.e.ii.2 | Approach Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.0625 | HBT/1624/SO/DGV/2025/1001 | 2025-09-12 | IPC - 20 | 1 / 16 Nos. - Approved - SAV - P1R - 50% released | P1R
204.e.ii.2 | Approach Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.125 | HBT/1624/SO/DGV/2025/1009 | 2025-09-16 | IPC - 20 | 2 / 16 Nos. - Approved - NAV - P32R & 33R - 50% released | P32R / P33R
204.e.ii.2 | Approach Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.375 | HBT/1624/SO/DGV/2025/1074 | 2025-10-14 | IPC - 22 | 6 / 16 Nos. - Approved - NAV - P31 to 36 - 50% released | P31 to P36
204.e.ii.2 | Approach Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.625 | HBT/1624/SO/DGV/2026/1392 HBT/1624/SO/DGV/2026/1393 | 2026-02-09 | IPC - 27 | 10 / 16 Nos. - Approved - NAV - P31 to 36, SAV - P0 to P3 - Balance 50% released | P31 to P36 & P0 to P3
204.e.ii.2 | Approach Viaduct - Substructure - Documents & Reports - Approval | Nos. |  | 0.25 | HBT/1624/SO/DGV/2026/1570 | 2026-04-24 | IPC - 31 | 4 / 16 Nos. - Approved - SAV - P1R & P2R; NAV - P32R & P33R - Balance 50% released | P1R, P2R, P32R, P33R
| Cumulative paid upto this Bill | Nos. |  | 1.75
| Paid upto previous Bill | Nos. |  | 1.75
| To be paid in this Bill | Nos. |  | 0
204.e.ii.3 | Approach Viaduct - Substructure - Issue of GFC Drawings | Nos. |  | 0.375 | HBT/1624/SO/DGV/2025/1255 | 2025-12-11 | IPC - 25 | 6 / 16 Nos. - Approved - NAV - P31 to P36 - 50% released | P31,P32, P33, P34, P35, P36
204.e.ii.3 | Approach Viaduct - Substructure - Issue of GFC Drawings | Nos. |  | 0.0625 | HBT/1624/SO/DGV/2025/854 | 2025-07-28 | IPC - 31 | 1 / 16 Nos. - SAV - P1 - 50% released | P1
204.e.ii.3 | Approach Viaduct - Substructure - Issue of GFC Drawings | Nos. |  | 0.0625 | HBT/1624/SO/DGV/2025/859 | 2025-07-29 | IPC - 31 | 1 / 16 Nos. - SAV - P2 - 50% released | P2
204.e.ii.3 | Approach Viaduct - Substructure - Issue of GFC Drawings | Nos. |  | 0.0625 | HBT/1624/SO/DGV/2025/971 | 2025-09-05 | IPC - 31 | 1 / 16 Nos. - SAV - P3 - 50% released | P3
204.e.ii.3 | Approach Viaduct - Substructure - Issue of GFC Drawings | Nos. |  | 0.125 | HBT/1624/SO/DGV/2025/1167 | 2025-11-12 | IPC - 31 | 2 / 16 Nos. - Approved - NAV - P32R & P33R - 50% released | P32R, P33R
204.e.ii.3 | Approach Viaduct - Substructure - Issue of GFC Drawings | Nos. |  | 0.125 | HBT/1624/SO/DGV/2025/1176 | 2025-11-17 | IPC - 31 | 2 / 16 Nos. - Approved - SAV - P1R & P2R - 50% released | P1R, P2R
204.e.ii.3 | Approach Viaduct - Substructure - Issue of GFC Drawings | Nos. |  | 0.25 | HBT/1624/SO/DGV/2026/1698 | 2026-06-25 | IPC - 33 | 4 / 16 Nos. - Approved - SAV - P0 to P3 - Balance 50% released | P0 to P3
204.e.ii.3 | Approach Viaduct - Substructure - Issue of GFC Drawings | Nos. |  | 0.375 | HBT/1624/SO/DGV/2026/1701 | 2026-06-26 | IPC - 33 | 6 / 16 Nos. - Approved - NAV - P31 to P36 - 50% released | P31,P32, P33, P34, P35, P36
204.e.ii.3 | Approach Viaduct - Substructure - Issue of GFC Drawings | Nos. |  | 0.25 | HBT/1624/SO/DGV/2026/1771 | 2026-07-31 | IPC - 34 | 2 / 16 Nos. - Approved - SAV - P1R & P2R, NAV - P32R & P33R - Balance 50% released | P1R, P2R, P32R, P33R
| Cumulative paid upto this Bill | Nos. |  | 1.688
| Paid upto previous Bill | Nos. |  | 1.438
| To be paid in this Bill | Nos. |  | 0.25
204.e.iii.1 | Approach Viaduct - Superstructure - Documents & Reports - Submission | Nos. |  | 0.85714 | MPSB/L&T/TIIC/DGN/2025/177 | 2025-03-21 | IPC - 13 | 6 / 14 Nos. - Submitted - SAV - P3 to P6, NAV - P33 to P36 | 12
204.e.iii.1 | Approach Viaduct - Superstructure - Documents & Reports - Submission | Nos. |  | 1.1429 | MPSB/L&T/TIIC/DGN/2025/243 MPSB/L&T/TIIC/DGN/2025/253 | 30-May-25 8-Jun-25 | IPC - 16 | 8 / 14 Nos. - Submitted - SAV - P0 to P3 NAV - P30 to P33 along with Rescue Spans
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.e.iii.2 | Approach Viaduct - Superstructure - Documents & Reports - Approval | Nos. |  | 0.85714 | HBT/1624/SO/DGV/2025/707 HBT/1624/SO/DGV/2025/708 | 2025-06-06 | IPC - 16 | 6 / 14 Nos. - Approved - SAV - P3 to P6, NAV - P33 to P36 | 12
204.e.iii.2 | Approach Viaduct - Superstructure - Documents & Reports - Approval | Nos. |  | 0.57143 | HBT/1624/SO/DGV/2025/1161 | 2025-11-12 | IPC - 23 | 4 / 14 Nos. - Approved - SAV - P0 to P3, P1R & P2R
204.e.iii.2 | Approach Viaduct - Superstructure - Documents & Reports - Approval | Nos. |  | 0.57143 | HBT/1624/SO/DGV/2025/1166 | 2025-11-12 | IPC - 23 | 4 / 14 Nos. - Approved - NAV - P30 to P33, P32R & P33R
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
204.e.iii.3 | Approach Viaduct - Superstructure - Issue of GFC | Nos. |  | 0.85714 | HBT/1624/SO/DGV/2025/858 | 2025-07-29 | IPC - 25 | 6 / 14 Nos. - Approved - SAV - P3 to P6, NAV - P33 to P36 | 12
| Cumulative paid upto this Bill | Nos. |  | 0.857
| Paid upto previous Bill | Nos. |  | 0.857
| To be paid in this Bill | Nos. |  | 0
204.f.i | Vehicular Underpass - Documents & Reports - Submission | Nos. |  | 1 | MPSB/L&T/TIIC/DGN/2024/034 | 2024-09-12 | IPC - 07 |  | Km 3+053
204.f.i | Vehicular Underpass - Documents & Reports - Submission | Nos. |  | 1 | MPSB/L&T/TIIC/DGN/2025/190 | 2025-04-09 | IPC - 15 |  | Km 3+053
204.f.i | Vehicular Underpass - Documents & Reports - Submission | Nos. |  | 1 | MPSB/L&T/TIIC/DGN/2025/210 | 2025-05-12 | IPC - 15 |  | Km 0+814
| Cumulative paid upto this Bill | Nos. |  | 3
| Paid upto previous Bill | Nos. |  | 3
| To be paid in this Bill | Nos. |  | 0
204.f.ii | Vehicular Underpass - Documents & Reports - Approval | Nos. |  | 1 | HBT/1624/SO/DGV/2025/980 | 2025-09-08 | IPC - 20 | Km 3+061
204.f.i | Vehicular Underpass - Documents & Reports - Approval | Nos. |  | 1 | HBT/1624/SO/DGV/2025/979 | 2025-09-08 | IPC - 20 | Km 0+814
204.f.i | Vehicular Underpass - Documents & Reports - Approval | Nos. |  | 0.667 | HBT/1624/SO/DGV/2025/1079 | 2025-10-07 | IPC - 23 | Km 4+480 (Fond.+Sub.S)
204.f.i | Vehicular Underpass - Documents & Reports - Approval | Nos. |  | 0.333 | HBT/1624/SO/DGV/2026/1371 | 2026-01-31 | IPC - 27 | Km 4+480 (+Sup.S)
| Cumulative paid upto this Bill | Nos. |  | 3
| Paid upto previous Bill | Nos. |  | 3
| To be paid in this Bill | Nos. |  | 0
204.g.i | Culverts - Documents & Reports - Submission | Nos. |  | 7 | MPSB/L&T/TIIC/DGN/2025/157 MPSB/L&T/TIIC/DGN/2025/162 | 08-Mar-25 15-Mar-25 | IPC - 13 | Km 11+580, Km 11+775, Km 12+040, Km 1+750, Km 3+760, Km 10+100, Km 0+298
204.g.i | Culverts - Documents & Reports - Submission | Nos. |  | 11 | MPSB/L&T/TIIC/DGN/2025/225 | 2025-05-25 | IPC - 15
| Cumulative paid upto this Bill | Nos. |  | 18
| Paid upto previous Bill | Nos. |  | 18
| To be paid in this Bill | Nos. |  | 0
204.g.ii | Culverts - Documents & Reports - Approval | Nos. |  | 5 | HBT/1624/SO/APR/2025/530 | 2025-03-28 | IPC - 13 | Km 11+580, Km 11+775, Km 12+040, Km 1+750, Km 3+760 |  | Initial
204.g.ii | Culverts - Documents & Reports - Approval | Nos. |  | 1 | HBT/1624/SO/DGV/2025/584 | 2025-04-18 | IPC - 14 | Km 10+100
204.g.ii | Culverts - Documents & Reports - Approval | Nos. |  | 1 | HBT/1624/SO/DGV/2025/672 | 2025-05-24 | IPC - 16 | Km 0+298
204.g.ii | Culverts - Documents & Reports - Approval | Nos. |  | 7 | HBT/1624/SO/DGV/2025/1031 | 2025-09-22 | IPC - 20 | Km 0+925, Km 0+939, Km 1+200, Km 1+436, Km 2+204, Km 2+465, Km 2+600
204.g.ii | Culverts - Documents & Reports - Approval | Nos. |  | 4 | HBT/1624/SO/DGV/2025/1035 | 2025-09-24 | IPC - 20 | Km 3+205, Km 4+154, Km 4+709, Km 4+914
| Cumulative paid upto this Bill | Nos. |  | 18
| Paid upto previous Bill | Nos. |  | 18
| To be paid in this Bill | Nos. |  | 0
204.g.iii | Culverts - Issue of GFC Drawings | Nos. |  | 11 | HBT/1624/SO/DGV/2025/1273 | 2025-12-15 | IPC - 25 | Km 0+925, Km 0+939, Km 1+200, Km 1+436, Km 2+204, Km 2+465, Km 2+600, Km 3+205, Km 4+154, Km 4+709, Km 4+914
204.g.iii | Culverts - Issue of GFC Drawings | Nos. |  | 7 | HBT/1624/SO/DGV/2026/1695 | 2026-06-24 | IPC - 33 | Km 11+580, Km 11+775, Km 12+040, Km 1+750, Km 3+760, Km 10+100, Km 0+298
| Cumulative paid upto this Bill | Nos. |  | 18
| Paid upto previous Bill | Nos. |  | 18
| To be paid in this Bill | Nos. |  | 0
204.h.i | Foundation of Main Bridge - Documents & Reports - Submission | Nos. |  | 0.68 | MPSB/L&T/TIIC/DGN/2024/042 MPSB/L&T/TIIC/DGN/2024/050 | 28-Sep-24 10-Oct-24 | IPC - 07 | 17 / 25 Nos. - Submitted - P10 to P26
204.h.i | Foundation of Main Bridge - Documents & Reports - Submission | Nos. |  | 0.32 | MPSB/L&T/TIIC/DGN/2024/072 MPSB/L&T/TIIC/DGN/2024/087 MPSB/L&T/TIIC/DGN/2024/088 | 18-Nov-24 25-Nov-24 25-Nov-24 | IPC - 08 | 8 / 25 Nos. - Submitted - P6 to P9, P27 to P30
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
204.h.ii | Foundation of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.92 | HBT/1624/SO/APR/2024/0305/498 HBT/1624/SO/APR/2024/0324/517 HBT/1624/SO/APR/2024/0328/520 HBT/1624/SO/APR/2024/0330/521 HBT/1624/SO/APR/2024/0331/522 HBT/1624/SO/APR/2024/0332/523 HBT/1624/SO/APR/2024/0333/524 HBT/1624/SO/APR/2024/0334/525 HBT/1624/SO/APR/2024/0355/546 HBT/1624/SO/APR/2024/0356/547 HBT/1624/SO/APR/2024/0357/548 HBT/1624/SO/APR/2024/0358/549 | 30-Nov-24 13-Dec-24 14-Dec-24 14-Dec-24 14-Dec-24 14-Dec-24 14-Dec-24 14-Dec-24 23-Dec-24 23-Dec-24 23-Dec-24 23-Dec-24 | IPC - 09 | 23 / 25 Nos. - Approved - P6 to P21, P23, P25 to P30
204.h.ii | Foundation of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.08 | HBT/1624/SO/APR/2025/0476/663 | 2025-02-24 | IPC - 11 | 2 / 25 Nos. - Approved - P22 & P24
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
204.h.iii | Foundation of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.92 | MPSB/L&T/TIIC/DGN/GFC/2025/109 MPSB/L&T/TIIC/DGN/GFC/2025/110 | 13-Jan-25 11-Jan-25 | IPC - 10 | 23 / 25 Nos. - P6 to P21, P23, P25 to P30
204.h.iii | Foundation of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.08 | MPSB/L&T/TIIC/DGN/2025/132 | 2025-02-14 | IPC - 13 | 2 / 25 Nos. - P22 & P24
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
204.i.i | Substructure of Main Bridge - Documents & Reports - Submission | Nos. |  | 0.36 | MPSB/L&T/TIIC/DGN/2024/052 | 2024-10-17 | IPC - 07 | 9 / 25 Nos. - Submitted - P10 to P18
204.i.i | Substructure of Main Bridge - Documents & Reports - Submission | Nos. |  | 0.32 | MPSB/L&T/TIIC/DGN/2024/074 | 2024-11-18 | IPC - 08 | 8 / 25 Nos. - Submitted - P19 to P26
204.i.i | Substructure of Main Bridge - Documents & Reports - Submission | Nos. |  | 0.32 | MPSB/L&T/TIIC/DGN/2025/121 | 2025-01-22 | IPC - 10 | 8 / 25 Nos. - Submitted - P6 to P9, P27 to P30
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
204.i.ii | Substructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.08 | MPSB/L&T/TIIC/DGN/2024/1121 | 2025-11-04 | IPC - 23 | 4 / 25 Nos. - Approved - P6 to P9 - 50% released
204.i.ii | Substructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.16 | HBT/1624/SO/DGV/2026/1405 | 2026-02-13 | IPC - 27 | 8 / 25 Nos. - Approved - P19 to P26 - 50% released
204.i.ii | Substructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.16 | HBT/1624/SO/DGV/2026/1396 | 2026-02-10 | IPC - 30 | 4 / 25 Nos. - Approved - P27 to P30
204.i.ii | Substructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.08 | HBT/1624/SO/DGV/2026/1547 | 2026-04-13 | IPC - 30 | 2/25 Nos. - Approved - P13 to P14
204.i.ii | Substructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.16 | HBT/1624/SO/DGV/2026/1548 | 2026-04-13 | IPC - 30 | 4/25 Nos. - Approved - P15 to P18
204.i.ii | Substructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.12 | HBT/1624/SO/DGV/2026/1549 | 2026-04-13 | IPC - 30 | 3/ 25 Nos. - Approved - P10 to P12A
| Cumulative paid upto this Bill | Nos. |  | 0.76
| Paid upto previous Bill | Nos. |  | 0.76
| To be paid in this Bill | Nos. |  | 0
204.i.iii | Substructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.08 | HBT/1624/SO/DGV/2026/1435 | 2026-02-28 | IPC - 29 | 4 / 25 Nos. - Approved - P6 to P9 - 50% released
204.i.iii | Substructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.16 | HBT/1624/SO/DGV/2026/1545 | 2026-04-13 | IPC - 31 | 8 / 25 Nos. - Approved - P19 to P26 - 50% released
204.i.iii | Substructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.08 | HBT/1624/SO/DGV/2026/1681 | 2026-06-17 | IPC - 33 | 4 / 25 Nos. - Approved - P27 to P30 - 50% released
204.i.iii | Substructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.08 | HBT/1624/SO/DGV/2026/1679 | 2026-06-17 | IPC - 33 | 4 / 25 Nos. - Approved - P10 to P12A - 50% released
204.i.iii | Substructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.04 | HBT/1624/SO/DGV/2026/1678 | 2026-06-17 | IPC - 33 | 2 / 25 Nos. - Approved - P13 & P14 - 50% released
204.i.iii | Substructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.08 | HBT/1624/SO/DGV/2026/1680 | 2026-06-17 | IPC - 33 | 4 / 25 Nos. - Approved - P15 to P18 - 50% released
| Cumulative paid upto this Bill | Nos. |  | 0.52
| Paid upto previous Bill | Nos. |  | 0.52
| To be paid in this Bill | Nos. |  | 0
204.j.i | Superstructure of Main Bridge - Documents & Reports - Submission | Nos. |  | 0.16667 | MPSB/L&T/TIIC/DGN/2024/106 | 2024-12-30 | IPC - 09 | 4 / 24 Nos. - Submitted - P10 to P13
204.j.i | Superstructure of Main Bridge - Documents & Reports - Submission | Nos. |  | 0.20833 | MPSB/L&T/TIIC/DGN/2024/106 | 2024-12-30 | IPC - 10 | 5 / 24 Nos. - Submitted - P14 to P18
204.j.i | Superstructure of Main Bridge - Documents & Reports - Submission | Nos. |  | 0.29167 | MPSB/L&T/TIIC/DGN/2025/197 | 2025-04-25 | IPC - 15 | 7 / 24 Nos. - Submitted - P19 to P26
204.j.i | Superstructure of Main Bridge - Documents & Reports - Submission | Nos. |  | 0.16667 | MPSB/L&T/TIIC/DGN/2025/343 | 2025-07-26 | IPC - 18 | 4 / 24 Nos. - Submitted - P6 to P10
204.j.i | Superstructure of Main Bridge - Documents & Reports - Submission | Nos. |  | 0.16667 | MPSB/L&T/TIIC/DGN/2025/350 | 2025-08-02 | IPC - 19 | 4 / 24 Nos. - Submitted - P27 to P30
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
204.j.ii | Superstructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.33333 | HBT/1624/SO/DGV/2025/698 | 2025-05-30 | IPC - 16 | 8 / 24 Nos. - Approved - P10 to P18
204.j.ii | Superstructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.33333 | HBT/1624/SO/DGV/2025/825 | 2025-07-19 | IPC - 18 | 8 / 24 Nos. - Approved - P18 to P26
204.j.ii | Superstructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.16667 | HBT/1624/SO/DGV/2025/1063 | 2025-10-08 | IPC - 22 | 4 / 24 Nos. - Approved - P6 to P10
204.j.ii | Superstructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.167 | HBT/1624/SO/DGV/2025/1107 | 2025-11-01 | IPC - 23 | 4 / 24 Nos. - Approved - P26 to P30
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
204.j.iii | Superstructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.33333 | MPSB/L&T/TIIC/DGN/GFC/2025/856 | 2025-07-29 | IPC - 18 | 8 / 24 Nos. - Submitted - P10 to P18
204.j.iii | Superstructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.33333 | HBT/1624/SO/APR/2025/969 | 2025-09-05 | IPC - 20 | 8 / 24 Nos. - Submitted - P18 to P26
204.j.iii | Superstructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.16667 | HBT/1624/SO/APR/2025/1365 | 2026-01-21 | IPC - 26 | 4 / 24 Nos. - Submitted - P6 to P10
204.j.iii | Superstructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.16667 | HBT/1624/SO/DGV/2026/1464 | 2026-03-14 | IPC - 30 | 4 / 24 Nos. - Submitted - P27 to P30
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
204.k.i | Miscellaneous Works - Temporary Access Bridge | Rmt |  | 672 | HBT/1624/SO/PSR/2024/0100/292 | 2024-08-31 | IPC - 04
| Cumulative paid upto this Bill | Rmt |  | 672
| Paid upto previous Bill | Rmt |  | 672
| To be paid in this Bill | Rmt |  | 0
204.k.ii | Miscellaneous Works - Launching System / Bridge Builder | Nos. |  | 1 | MPSB/L&T/TIIC/2025/676 | 2025-03-31 | IPC - 13
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1
| To be paid in this Bill | Nos. |  | 0
204.k.iii | Miscellaneous Works - Gantry | Nos. |  | 2 | MPSB/L&T/TIIC/2024/480 | 2024-11-29 | IPC - 08
[12 empty] | 800 | 1300 | 0.5
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2 | [7 empty] | 2600 | 3052 | 0.452
| To be paid in this Bill | Nos. |  | 0 | [7 empty] | 4220 | 4480 | 0.26
[12 empty] | 4515 | 4750 | 0.235
204.k.iv | Miscellaneous Works - Bridge Health Monitoring | Nos. |  |  | HBT/1624/SO/DGV/2025/1081 | 2025-10-18
[12 empty] | 800 | 1300 | 0.5
| Cumulative paid upto this Bill | Nos. |  | 0
| Paid upto previous Bill | Nos. |  | 0 | [7 empty] | 2600 | 3052 | 0.452
| To be paid in this Bill | Nos. |  | 0 | [7 empty] | 4220 | 4480 | 0.26
[12 empty] | 4515 | 4750 | 0.235
204.k.v.1 | Miscellaneous Works - Wind Tunnel Analysis - Submission | Nos. |  | 1 | MPSB/L&T/TIIC/DGN/2025/180 | 2025-03-25 | IPC - 13
[12 empty] | 800 | 1300 | 0.5
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1 | [7 empty] | 2600 | 3052 | 0.452
| To be paid in this Bill | Nos. |  | 0 | [7 empty] | 4220 | 4480 | 0.26
[12 empty] | 4515 | 4750 | 0.235
204.k.v.2 | Miscellaneous Works - Wind Tunnel Analysis - Approval | Nos. |  | 1 | HBT/1624/SO/LTR/2025/919 | 2025-08-21 | IPC - 19
[12 empty] | 800 | 1300 | 0.5
| Cumulative paid upto this Bill | Nos. |  | 1
| Paid upto previous Bill | Nos. |  | 1 | [7 empty] | 2600 | 3052 | 0.452
| To be paid in this Bill | Nos. |  | 0 | [7 empty] | 4220 | 4480 | 0.26
[12 empty] | 4515 | 4750 | 0.235
204.l.i | Miscellaneous Works - Junctions - Submission | Nos. |  | 10 | MPSB/L&T/TIIC/DGN/2025/317 | 2025-07-11 | IPC - 19
[12 empty] | 800 | 1300 | 0.5
| Cumulative paid upto this Bill | Nos. |  | 10
| Paid upto previous Bill | Nos. |  | 10 | [7 empty] | 2600 | 3052 | 0.452
| To be paid in this Bill | Nos. |  | 0 | [7 empty] | 4220 | 4480 | 0.26
[12 empty] | 4515 | 4750 | 0.235
204.l.ii | Miscellaneous Works - Junctions - Approval | Nos. |  | 10 | HBT/1624/SO/DGV/2025/809 | 2025-07-14 | IPC - 20
[12 empty] | 800 | 1300 | 0.5
| Cumulative paid upto this Bill | Nos. |  | 10
| Paid upto previous Bill | Nos. |  | 10 | [7 empty] | 2600 | 3052 | 0.452
| To be paid in this Bill | Nos. |  | 0 | [7 empty] | 4220 | 4480 | 0.26
[12 empty] | 4515 | 4750 | 0.235
204.l.iii | Miscellaneous Works - Junctions - Issue of GFC Drawings | Nos. |  | 10 | HBT/1624/SO/DGV/2025/1212 | 2025-11-25 | IPC - 27
[12 empty] | 800 | 1300 | 0.5
| Cumulative paid upto this Bill | Nos. |  | 10
| Paid upto previous Bill | Nos. |  | 10 | [7 empty] | 2600 | 3052 | 0.452
| To be paid in this Bill | Nos. |  | 0 | [7 empty] | 4220 | 4480 | 0.26
[12 empty] | 4515 | 4750 | 0.235
205 | Setting out of the Final Alignment with location of all structures, approach formation work and Miscellaneous work | [10 empty] | 4750 | 4780 | 0.03
205.a | Documents & Reports - Submission | Kms |  | 12.21 | MPSB/L&T/TIIC/DGN/2024/022 | 2024-08-30 | IPC - 04 |  |  |  |  | 9360 | 9880 | 0.52
10.679
| Cumulative paid upto this Bill | Kms |  | 12.21
| Paid upto previous Bill | Kms |  | 12.21
| To be paid in this Bill | Kms |  | 0
205.b | Documents & Reports - Approval | Kms |  | 0.175 | HBT/1624/SO/APR/2024/0167/362 | 2024-09-30 | IPC - 05
205.b | Documents & Reports - Approval | Kms |  | 12.035 | HBT/1624/SO/APR/2024/0256/450 HBT/1624/SO/APR/2024/0279/473 | 12-Nov-24 18-Nov-24 | IPC - 08
| Cumulative paid upto this Bill | Kms |  | 12.21
| Paid upto previous Bill | Kms |  | 12.21
| To be paid in this Bill | Kms |  | 0
205.c | Documents & Reports - Issue of GFC Drawings | Kms |  | 12.21 | HBT/1624/SO/DGV/2025/1213 | 2025-11-25 | IPC - 23 | Km 0+000 to Km 12+210 |  |  |  | 9360 | 9880 | 0.52
18.484
| Cumulative paid upto this Bill | Kms |  | 12.21
| Paid upto previous Bill | Kms |  | 12.21
| To be paid in this Bill | Kms |  | 0

## Schedule 3
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
Period of bill : 1st Jul'26 to 31st Jul'26
| Schedule 3 - Enabling Works for Main Works | [7 empty] | IPC - 34
Measurement Sheet
| Item No. | Item Description | UoM | Location | Executed Quantity | RFI No. / Letter No. / Period | Date | Bill No. | Remarks
| 301 | Construction of temporary jetties/ platforms (TAB) / load out jetties etc for marine working
| 301.a | Supply of TAB material at site | MT | Palashbari | 1929.425 | MPSB/Temp/7 | 2024-06-10 | IPC - 02
| 301.a | Supply of TAB material at site | MT | Sualkuchi | 1353.325 | MPSB/Temp/10 | 2024-06-11 | IPC - 02
| 301.a | Supply of TAB material at site | MT | Palashbari | 616.6281 | MPSB/Temp/49 | 2024-07-29 | IPC - 03
|  | Cumulative paid upto this Bill | MT |  | 3899.3781
|  | Paid upto previous Bill | MT |  | 3899.3781
|  | To be paid in this Bill | MT |  | 0
| 301.b | Installation of TAB | Rmt | Palashbari | 174.4 | MPSB/Temp/72 | 2024-08-29 | IPC - 04 | Km 5+558.6 - Km 5+733
| 301.b | Installation of TAB | Rmt | Sualkuchi | 36 | MPSB/Temp/79 | 2024-08-31 | IPC - 04 | Km 9+216 - Km 9+180
| 301.b | Installation of TAB | Rmt | Palashbari | 23 | MPSB/Temp/92 | 2024-09-28 | IPC - 05 | Km 5+733 - Km 5+756
| 301.b | Installation of TAB | Rmt | Palashbari | 25 | MPSB/Temp/95 | 2024-09-30 | IPC - 05 | Km 5+756 - Km 5+781
| 301.b | Installation of TAB | Rmt | Sualkuchi | 23 | MPSB/Temp/81 | 2024-09-11 | IPC - 05 | Km 9+182 - Km 9+159
| 301.b | Installation of TAB | Rmt | Sualkuchi | 54 | MPSB/Temp/91 | 2024-09-28 | IPC - 05 | Km 9+159 - Km 9+105
| 301.b | Installation of TAB | Rmt | Sualkuchi | 13 | MPSB/Temp/96 | 2024-09-30 | IPC - 05 | Km 9+105 - Km 9+092
| 301.b | Installation of TAB | Rmt | Sualkuchi | 62.5 | MPSB/Temp/100 | 2024-10-29 | IPC - 07 | Km 9+092 - Km 9+107.5
| 301.b | Installation of TAB | Rmt | Palashbari | 48 | MPSB/Temp/102 | 2024-10-29 | IPC - 07 | Km 5+781 - Km 5+829
| 301.b | Installation of TAB | Rmt | Sualkuchi | 25.5 | MPSB/Temp/103 | 2024-10-31 | IPC - 07 | Km 9+107.5 - Km 8+992
| 301.b | Installation of TAB | Rmt | Palashbari | 25 | MPSB/Temp/104 | 2024-10-31 | IPC - 07 | Km 5+829 - Km 5+854
| 301.b | Installation of TAB | Rmt | Sualkuchi | 36 | MPSB/Temp/109 | 2024-11-15 | IPC - 08 | Km 8+992 - Km 8+956
| 301.b | Installation of TAB | Rmt | Palashbari | 75 | MPSB/Temp/110 | 2024-11-28 | IPC - 08 | Km 5+854 - Km 5+929
| 301.b | Installation of TAB | Rmt | Sualkuchi | 22 | MPSB/Temp/113 | 2024-11-30 | IPC - 08 | Km 8+879.9 - Km 8+857.9
| 301.b | Installation of TAB | Rmt | Palashbari | 29.6 | MPSB/Temp/114 | 2024-11-30 | IPC - 08 | Km 5+929 - Km 5+959
|  | Cumulative paid upto this Bill | Rmt |  | 672
|  | Paid upto previous Bill | Rmt |  | 672
|  | To be paid in this Bill | Rmt |  | 0
| 302 | Establishment of batching plant, crusher (if any), rebar yards, formwork shops, fabrication shops etc for main works
| 302.a.i | Establishment of Batching Plants - Receipt of Equipment | Nos. | Palashbari | 2 | MPSB/Gen/1 | 2024-06-11 | IPC - 02
| 302.a.i | Establishment of Batching Plants - Receipt of Equipment | Nos. | Sualkuchi | 2 | MPSB/Gen/3 | 2024-06-19 | IPC - 02
|  | Cumulative paid upto this Bill | Nos. |  | 4
|  | Paid upto previous Bill | Nos. |  | 4
|  | To be paid in this Bill | Nos. |  | 0
c | 302.a.ii | Establishment of Batching Plants - Foundation | Nos. | Sualkuchi | 1 | MPSB/Gen/5 | 2024-06-30 | IPC - 02
| 302.a.ii | Establishment of Batching Plants - Foundation | Nos. | Palashbari | 1 | MPSB/Gen/6 | 2024-06-30 | IPC - 02
| 302.a.ii | Establishment of Batching Plants - Foundation | Nos. | Sualkuchi | 1 | MPSB/Gen/10 | 2025-01-31 | IPC - 10
| 302.a.ii | Establishment of Batching Plants - Foundation | Nos. | Palashbari | 1 | MPSB/Gen/12 | 2025-02-14 | IPC - 11
|  | Cumulative paid upto this Bill | Nos. |  | 4
|  | Paid upto previous Bill | Nos. |  | 4
|  | To be paid in this Bill | Nos. |  | 0
c | 302.a.iii | Establishment of Batching Plants - Installation and Commissioning | Nos. | Palashbari | 1 | MPSB/Gen/8 | 2024-11-30 | IPC - 08
| 302.a.iii | Establishment of Batching Plants - Installation and Commissioning | Nos. | Sualkuchi | 1 | MPSB/Gen/11 | 2025-01-31 | IPC - 10
| 302.a.iii | Establishment of Batching Plants - Installation and Commissioning | Nos. | Palashbari | 1 | MPSB/Gen/16 | 2025-02-28 | IPC - 11
| 302.a.iii | Establishment of Batching Plants - Installation and Commissioning | Nos. | Sualkuchi | 1 | MPSB/Gen/15 | 2025-02-28 | IPC - 11
|  | Cumulative paid upto this Bill | Nos. |  | 4
|  | Paid upto previous Bill | Nos. |  | 4
|  | To be paid in this Bill | Nos. |  | 0
| 302.b.i | Establishment of Crusher Plant - Receipt of Equipment | Nos. | Rangia | 1 | MPSB/Gen/7 | 2024-11-29 | IPC - 08
|  | Cumulative paid upto this Bill | Nos. |  | 1
|  | Paid upto previous Bill | Nos. |  | 1
|  | To be paid in this Bill | Nos. |  | 0
| 302.b.ii | Establishment of Crusher Plant - Foundation | Nos. | Rangia | 1 | MPSB/Temp/112 | 2024-11-29 | IPC - 08
|  | Cumulative paid upto this Bill | Nos. |  | 1
|  | Paid upto previous Bill | Nos. |  | 1
|  | To be paid in this Bill | Nos. |  | 0
| 302.b.iii | Establishment of Crusher Plant - Installation and Commissioning | Nos. | Rangia | 1 | MPSB/Temp/148 | 2025-03-31 | IPC - 13
|  | Cumulative paid upto this Bill | Nos. |  | 1
|  | Paid upto previous Bill | Nos. |  | 1
|  | To be paid in this Bill | Nos. |  | 0
| 302.c | Commissioning of Rebar Yard | Nos. | Palashbari | 1 | MPSB/Temp/105 | 2024-10-31 | IPC - 07
| 302.c | Commissioning of Rebar Yard | Nos. | Sualkuchi | 1 | MPSB/Temp/107 | 2024-10-31 | IPC - 07
|  | Cumulative paid upto this Bill | Nos. |  | 2
|  | Paid upto previous Bill | Nos. |  | 2
|  | To be paid in this Bill | Nos. |  | 0
| 302.d | Commissioning of Formwork Yard | Nos. | Palashbari | 1 | MPSB/Temp/106 | 2024-10-31 | IPC - 07
| 302.d | Commissioning of Formwork Yard | Nos. | Sualkuchi | 1 | MPSB/Temp/108 | 2024-10-31 | IPC - 07
|  | Cumulative paid upto this Bill | Nos. |  | 2
|  | Paid upto previous Bill | Nos. |  | 2
|  | To be paid in this Bill | Nos. |  | 0
| 302.e | Commissioning of Fabrication Yard | Nos. | Palashbari | 1 | MPSB/Temp/47 | 2024-07-27 | IPC - 03
|  | Cumulative paid upto this Bill | Nos. |  | 1
|  | Paid upto previous Bill | Nos. |  | 1
|  | To be paid in this Bill | Nos. |  | 0
| 303 | Establishment of Casting yards for casting of PSC Box girders, I-Girders etc as per requirement
| 303.a.i | Construction of Casting Yard - Area Development | Nos. | Palashbari | 0.75 | MPSB/Temp/126 | 2024-12-30 | IPC - 09
| 303.a.i | Construction of Casting Yard - Area Development | Nos. | Palashbari | 0.25 | MPSB/Temp/129 | 2025-01-31 | IPC - 10
| 303.a.i | Construction of Casting Yard - Area Development | Nos. | Sualkuchi | 0.75 | MPSB/Temp/128 | 2025-01-31 | IPC - 10 |  | RFI to be adjusted
| 303.a.i | Construction of Casting Yard - Area Development | Nos. | Sualkuchi | 0.25 | MPSB/Temp/133 | 2025-02-28 | IPC - 11
|  | Cumulative paid upto this Bill | Nos. |  | 2
|  | Paid upto previous Bill | Nos. |  | 2
|  | To be paid in this Bill | Nos. |  | 0
| 303.a.ii | Construction of Casting Yard - Foundation of Gantry | Nos. | Palashbari | 0.375 | MPSB/Temp/134 | 2025-02-28 | IPC - 11 | 600 / 1600 Rmt
| 303.a.ii | Construction of Casting Yard - Foundation of Gantry | Nos. | Sualkuchi | 0.15625 | MPSB/Temp/135 | 2025-02-28 | IPC - 11 | 250 / 1600 Rmt
| 303.a.ii | Construction of Casting Yard - Foundation of Gantry | Nos. | Palashbari | 0.375 | MPSB/Temp/140 | 2025-03-28 | IPC - 13 | 600 / 1600 Rmt
| 303.a.ii | Construction of Casting Yard - Foundation of Gantry | Nos. | Sualkuchi | 0.46875 | MPSB/Temp/141 MPSB/Temp/142 | 28-Mar-25 31-Mar-25 | IPC - 13 | 750 / 1600 Rmt
| 303.a.ii | Construction of Casting Yard - Foundation of Gantry | Nos. | Palashbari | 0.25 | MPSB/Temp/159 | 2025-04-30 | IPC - 14 | 400 / 1600 Rmt
| 303.a.ii | Construction of Casting Yard - Foundation of Gantry | Nos. | Sualkuchi | 0.21875 | MPSB/Str/1345 | 2025-04-30 | IPC - 14 | 350 / 1600 Rmt
| 303.a.ii | Construction of Casting Yard - Foundation of Gantry | Nos. | Sualkuchi | 0.15625 | MPSB/Temp/183 | 2025-06-30 | IPC - 16 | 250 / 1600 Rmt
|  | Cumulative paid upto this Bill | Nos. |  | 2
|  | Paid upto previous Bill | Nos. |  | 2
|  | To be paid in this Bill | Nos. |  | 0
| 303.a.iii | Construction of Casting Yard - Casting Bed Foundation | Nos. | Palashbari | 1 | MPSB/Str/946 | 2025-03-28 | IPC - 13
| 303.a.iii | Construction of Casting Yard - Casting Bed Foundation | Nos. | Sualkuchi | 1 | MPSB/Str/1346 | 2025-04-30 | IPC - 14
|  | Cumulative paid upto this Bill | Nos. |  | 2
|  | Paid upto previous Bill | Nos. |  | 2
|  | To be paid in this Bill | Nos. |  | 0
| 303.a.iv | Construction of Casting Yard - Stacking Bed Foundation | Nos. | Palashbari | 1 | MPSB/Temp/170 | 2025-05-31 | IPC - 15
| 303.a.iv | Construction of Casting Yard - Stacking Bed Foundation | Nos. | Sualkuchi | 1 | MPSB/Temp/171 | 2025-05-31 | IPC - 15
|  | Cumulative paid upto this Bill | Nos. |  | 2
|  | Paid upto previous Bill | Nos. |  | 2
|  | To be paid in this Bill | Nos. |  | 0
| 303.a.v | Construction of Casting Yard - Finishing and Commissioning of Casting yard | Nos. | Palashbari | 1 | MPSB/Temp/182 | 2025-06-30 | IPC - 16
| 303.a.v | Construction of Casting Yard - Finishing and Commissioning of Casting yard | Nos. | Sualkuchi | 1 | MPSB/Temp/181 | 2025-06-30 | IPC - 16
|  | Cumulative paid upto this Bill | Nos. |  | 2
|  | Paid upto previous Bill | Nos. |  | 2
|  | To be paid in this Bill | Nos. |  | 0
| 304 | Supply and installation of moulds, gantries etc for precast works
| 304.a | Moulds - Material Procurement (Long Bed) | Nos. |  | 4 | MPSB/Gen/9 | 2024-11-30 | IPC - 08
|  | Cumulative paid upto this Bill | Nos. |  | 4
|  | Paid upto previous Bill | Nos. |  | 4
|  | To be paid in this Bill | Nos. |  | 0
| 304.b | Moulds - Fabrication & Commissioning (Long Bed) | Nos. |  | 0.57798 | As per Annexure |  | IPC - 11 | 227 / 1571 MT
| 304.b | Moulds - Fabrication & Commissioning (Long Bed) | Nos. |  | 1.2043 | As per Annexure |  | IPC - 13 | 473 / 1571 MT
| 304.b | Moulds - Fabrication & Commissioning (Long Bed) | Nos. |  | 2.2177 | As per Annexure |  | IPC - 14 | 871 / 1571 MT
|  | Cumulative paid upto this Bill | Nos. |  | 4
|  | Paid upto previous Bill | Nos. |  | 4
|  | To be paid in this Bill | Nos. |  | 0
| 304.c | Gantry - Equipment Receipt | Nos. | Pal & Sual | 2 | MPSB/Temp/125 | 2024-12-30 | IPC - 09
|  | Cumulative paid upto this Bill | Nos. |  | 2
|  | Paid upto previous Bill | Nos. |  | 2
|  | To be paid in this Bill | Nos. |  | 0
| 304.d | Gantry - Installation & Commissioning | Nos. | Palashbari | 1 | MPSB/Gen/17 | 2025-03-31 | IPC - 13
| 304.d | Gantry - Installation & Commissioning | Nos. | Sualkuchi | 1 | MPSB/Gen/19 | 2025-04-30 | IPC - 14
|  | Cumulative paid upto this Bill | Nos. |  | 2
|  | Paid upto previous Bill | Nos. |  | 2
|  | To be paid in this Bill | Nos. |  | 0
| 305 | Supply and commissioning of Bridge Builders/Launchers for erection of bridge deck
| 305.a | Receipt of Equipment at site | Set |  | 4 | As per Annexure |  | IPC - 33
|  | Cumulative paid upto this Bill | Set |  | 4
|  | Paid upto previous Bill | Set |  | 4
|  | To be paid in this Bill | Set |  | 0
| 306 | Procurement/Mobilization of Marine Equipment’s (Barges/Tugs etc) for working in water
| 306.a | Procurement / Mobilization of Barges | Nos. | Palashbari | 3 | MPSB/L&T/TIIC/2024/367 | 2024-09-30 | IPC - 05
| 306.a | Procurement / Mobilization of Barges | Nos. | Palashbari | 3 | MPSB/L&T/TIIC/2024/407 | 2024-10-31 | IPC - 07
|  | Cumulative paid upto this Bill | Nos. |  | 6
|  | Paid upto previous Bill | Nos. |  | 6
|  | To be paid in this Bill | Nos. |  | 0
| 306.b | Procurement / Mobilization of Tugs | Nos. | Palashbari | 2 | MPSB/L&T/TIIC/2024/367 | 2024-09-30 | IPC - 05
|  | Cumulative paid upto this Bill | Nos. |  | 2
|  | Paid upto previous Bill | Nos. |  | 2
|  | To be paid in this Bill | Nos. |  | 0

## Segment Summary (hidden)
Main Bridge - Segments Scope Vs Casting
P6 |  | P7 |  | P8 |  | P9 |  | P10 |  | P11 |  | P12 |  | P13 |  | P14 |  | P15 |  | P16 |  | P17 |  | P18
Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in
P6-S01a-E | #N/A | P7-S01a-O | #N/A | P8-S01a-M | #N/A | P9-S01a-O | #N/A | P10-S01a-E | #N/A | P11-S01a-O | #N/A | P12-S01a-M | #N/A | P13-S01a-O | #N/A | P14-S01a-E | #N/A | P15-S01a-O | #N/A | P16-S01a-M | #N/A | P17-S01a-O | #N/A | P18-S01a-E | #N/A
P6-S01-E | #N/A | P7-S02a-O | #N/A | P8-S02a-M | #N/A | P9-S02a-O | #N/A | P10-S01-E | #N/A | P11-S02a-O | #N/A | P12-S02a-M | #N/A | P13-S02a-O | #N/A | P14-S01-E | #N/A | P15-S02a-O | #N/A | P16-S02a-M | #N/A | P17-S02a-O | #N/A | P18-S01-E | #N/A
P6-S02a-E | #N/A | P7-S03a-O | #N/A | P8-S03a-M | #N/A | P9-S03a-O | #N/A | P10-S02a-E | #N/A | P11-S03a-O | #N/A | P12-S03a-M | #N/A | P13-S03a-O | #N/A | P14-S02a-E | #N/A | P15-S03a-O | #N/A | P16-S03a-M | #N/A | P17-S03a-O | #N/A | P18-S02a-E | #N/A
P6-S03a-E | #N/A | P7-S04a-O | #N/A | P8-S04a-M | #N/A | P9-S04a-O | #N/A | P10-S03a-E | #N/A | P11-S04a-O | #N/A | P12-S04a-M | #N/A | P13-S04a-O | #N/A | P14-S03a-E | #N/A | P15-S04a-O | #N/A | P16-S04a-M | #N/A | P17-S04a-O | #N/A | P18-S03a-E | #N/A
P6-S04a-E | #N/A | P7-S05a-O | #N/A | P8-S05a-M | #N/A | P9-S05a-O | #N/A | P10-S04a-E | #N/A | P11-S05a-O | #N/A | P12-S05a-M | #N/A | P13-S05a-O | #N/A | P14-S04a-E | #N/A | P15-S05a-O | #N/A | P16-S05a-M | #N/A | P17-S05a-O | #N/A | P18-S04a-E | #N/A
P6-S05a-E | #N/A | P7-S06a-O | #N/A | P8-S06a-M | #N/A | P9-S06a-O | #N/A | P10-S05a-E | #N/A | P11-S06a-O | #N/A | P12-S06a-M | #N/A | P13-S06a-O | #N/A | P14-S05a-E | #N/A | P15-S06a-O | #N/A | P16-S06a-M | #N/A | P17-S06a-O | #N/A | P18-S05a-E | #N/A
P6-S06a-E | #N/A | P7-S07a-O | #N/A | P8-S07a-M | #N/A | P9-S07a-O | #N/A | P10-S06a-E | #N/A | P11-S07a-O | #N/A | P12-S07a-M | #N/A | P13-S07a-O | #N/A | P14-S06a-E | #N/A | P15-S07a-O | #N/A | P16-S07a-M | #N/A | P17-S07a-O | #N/A | P18-S06a-E | #N/A
P6-S34a-O | #N/A | P7-S08a-O | #N/A | P8-S08a-M© | #N/A | P9-S08a-O | #N/A | P10-S34a-O | #N/A | P11-S08a-O | #N/A | P12-S08a-M© | #N/A | P13-S08a-O | #N/A | P14-S34a-O | #N/A | P15-S08a-O | #N/A | P16-S08a-M© | #N/A | P17-S08a-O | #N/A | P18-S34a-O | #N/A
P6-S33a-O© | #N/A | P7-S09a-O© | #N/A | P8-S09a-M | #N/A | P9-S09a-O© | #N/A | P10-S33a-O© | #N/A | P11-S09a-O© | #N/A | P12-S09a-M | #N/A | P13-S09a-O© | #N/A | P14-S33a-O© | #N/A | P15-S09a-O© | #N/A | P16-S09a-M | #N/A | P17-S09a-O© | #N/A | P18-S33a-O© | #N/A
P6-S32a-O | #N/A | P7-S10a-O | #N/A | P8-S10a-M© | #N/A | P9-S10a-O | #N/A | P10-S32a-O | #N/A | P11-S10a-O | #N/A | P12-S10a-M© | #N/A | P13-S10a-O | #N/A | P14-S32a-O | #N/A | P15-S10a-O | #N/A | P16-S10a-M© | #N/A | P17-S10a-O | #N/A | P18-S32a-O | #N/A
P6-S31a-O© | #N/A | P7-S11a-O© | #N/A | P8-S11a-M | #N/A | P9-S11a-O© | #N/A | P10-S31a-O© | #N/A | P11-S11a-O© | #N/A | P12-S11a-M | #N/A | P13-S11a-O© | #N/A | P14-S31a-O© | #N/A | P15-S11a-O© | #N/A | P16-S11a-M | #N/A | P17-S11a-O© | #N/A | P18-S31a-O© | #N/A
P6-S30a-O | #N/A | P7-S12a-O | #N/A | P8-S12a-M© | #N/A | P9-S12a-O | #N/A | P10-S30a-O | #N/A | P11-S12a-O | #N/A | P12-S12a-M© | #N/A | P13-S12a-O | #N/A | P14-S30a-O | #N/A | P15-S12a-O | #N/A | P16-S12a-M© | #N/A | P17-S12a-O | #N/A | P18-S30a-O | #N/A
P6-S29a-O© | #N/A | P7-S13a-O© | #N/A | P8-S13a-M | #N/A | P9-S13a-O© | #N/A | P10-S29a-O© | #N/A | P11-S13a-O© | #N/A | P12-S13a-M | #N/A | P13-S13a-O© | #N/A | P14-S29a-O© | #N/A | P15-S13a-O© | #N/A | P16-S13a-M | #N/A | P17-S13a-O© | #N/A | P18-S29a-O© | #N/A
P6-S28a-O | #N/A | P7-S14a-O | #N/A | P8-S14a-M© | #N/A | P9-S14a-O | #N/A | P10-S28a-O | #N/A | P11-S14a-O | #N/A | P12-S14a-M© | #N/A | P13-S14a-O | #N/A | P14-S28a-O | #N/A | P15-S14a-O | #N/A | P16-S14a-M© | #N/A | P17-S14a-O | #N/A | P18-S28a-O | #N/A
P6-S27a-O© | #N/A | P7-S15a-O© | #N/A | P8-S15a-M | #N/A | P9-S15a-O© | #N/A | P10-S27a-O© | #N/A | P11-S15a-O© | #N/A | P12-S15a-M | #N/A | P13-S15a-O© | #N/A | P14-S27a-O© | #N/A | P15-S15a-O© | #N/A | P16-S15a-M | #N/A | P17-S15a-O© | #N/A | P18-S27a-O© | #N/A
P6-S26a-O | #N/A | P7-S16a-O | #N/A | P8-S16a-M© | #N/A | P9-S16a-O | #N/A | P10-S26a-O | #N/A | P11-S16a-O | #N/A | P12-S16a-M© | #N/A | P13-S16a-O | #N/A | P14-S26a-O | #N/A | P15-S16a-O | #N/A | P16-S16a-M© | #N/A | P17-S16a-O | #N/A | P18-S26a-O | #N/A
P6-S25a-O© | #N/A | P7-S17a-O© | #N/A | P8-S17a-M | #N/A | P9-S17a-O© | #N/A | P10-S25a-O© | #N/A | P11-S17a-O© | #N/A | P12-S17a-M | #N/A | P13-S17a-O© | #N/A | P14-S25a-O© | #N/A | P15-S17a-O© | #N/A | P16-S17a-M | #N/A | P17-S17a-O© | #N/A | P18-S25a-O© | #N/A
P6-S24a-O | #N/A | P7-S18a-O | #N/A | P8-S18a-M | #N/A | P9-S18a-O | #N/A | P10-S24a-O | #N/A | P11-S18a-O | #N/A | P12-S18a-M | #N/A | P13-S18a-O | #N/A | P14-S24a-O | #N/A | P15-S18a-O | #N/A | P16-S18a-M | #N/A | P17-S18a-O | #N/A | P18-S24a-O | #N/A
P6-S23a-O© | #N/A | P7-S19a-O© | #N/A | P8-S34a-O | #N/A | P9-S19a-O© | #N/A | P10-S23a-O© | #N/A | P11-S19a-O© | #N/A | P12-S34a-O | #N/A | P13-S19a-O© | #N/A | P14-S23a-O© | #N/A | P15-S19a-O© | #N/A | P16-S34a-O | #N/A | P17-S19a-O© | #N/A | P18-S23a-O© | #N/A
P6-S22a-O | #N/A | P7-S20a-O | #N/A | P8-S33a-O© | #N/A | P9-S20a-O | #N/A | P10-S22a-O | #N/A | P11-S20a-O | #N/A | P12-S33a-O© | #N/A | P13-S20a-O | #N/A | P14-S22a-O | #N/A | P15-S20a-O | #N/A | P16-S33a-O© | #N/A | P17-S20a-O | #N/A | P18-S22a-O | #N/A
P6-S21a-O© | #N/A | P7-S21a-O© | #N/A | P8-S32a-O | #N/A | P9-S21a-O© | #N/A | P10-S21a-O© | #N/A | P11-S21a-O© | #N/A | P12-S32a-O | #N/A | P13-S21a-O© | #N/A | P14-S21a-O© | #N/A | P15-S21a-O© | #N/A | P16-S32a-O | #N/A | P17-S21a-O© | #N/A | P18-S21a-O© | #N/A
P6-S20a-O | #N/A | P7-S22a-O | #N/A | P8-S31a-O© | #N/A | P9-S22a-O | #N/A | P10-S20a-O | #N/A | P11-S22a-O | #N/A | P12-S31a-O© | #N/A | P13-S22a-O | #N/A | P14-S20a-O | #N/A | P15-S22a-O | #N/A | P16-S31a-O© | #N/A | P17-S22a-O | #N/A | P18-S20a-O | #N/A
P6-S19a-O© | #N/A | P7-S23a-O© | #N/A | P8-S30a-O | #N/A | P9-S23a-O© | #N/A | P10-S19a-O© | #N/A | P11-S23a-O© | #N/A | P12-S30a-O | #N/A | P13-S23a-O© | #N/A | P14-S19a-O© | #N/A | P15-S23a-O© | #N/A | P16-S30a-O | #N/A | P17-S23a-O© | #N/A | P18-S19a-O© | #N/A
P6-S18a-O | #N/A | P7-S24a-O | #N/A | P8-S29a-O© | #N/A | P9-S24a-O | #N/A | P10-S18a-O | #N/A | P11-S24a-O | #N/A | P12-S29a-O© | #N/A | P13-S24a-O | #N/A | P14-S18a-O | #N/A | P15-S24a-O | #N/A | P16-S29a-O© | #N/A | P17-S24a-O | #N/A | P18-S18a-O | #N/A
P6-S17a-O© | #N/A | P7-S25a-O© | #N/A | P8-S28a-O | #N/A | P9-S25a-O© | #N/A | P10-S17a-O© | #N/A | P11-S25a-O© | #N/A | P12-S28a-O | #N/A | P13-S25a-O© | #N/A | P14-S17a-O© | #N/A | P15-S25a-O© | #N/A | P16-S28a-O | #N/A | P17-S25a-O© | #N/A | P18-S17a-O© | #N/A
P6-S16a-O | #N/A | P7-S26a-O | #N/A | P8-S27a-O© | #N/A | P9-S26a-O | #N/A | P10-S16a-O | #N/A | P11-S26a-O | #N/A | P12-S27a-O© | #N/A | P13-S26a-O | #N/A | P14-S16a-O | #N/A | P15-S26a-O | #N/A | P16-S27a-O© | #N/A | P17-S26a-O | #N/A | P18-S16a-O | #N/A
P6-S15a-O© | #N/A | P7-S27a-O© | #N/A | P8-S26a-O | #N/A | P9-S27a-O© | #N/A | P10-S15a-O© | #N/A | P11-S27a-O© | #N/A | P12-S26a-O | #N/A | P13-S27a-O© | #N/A | P14-S15a-O© | #N/A | P15-S27a-O© | #N/A | P16-S26a-O | #N/A | P17-S27a-O© | #N/A | P18-S15a-O© | #N/A
P6-S14a-O | #N/A | P7-S28a-O | #N/A | P8-S25a-O© | #N/A | P9-S28a-O | #N/A | P10-S14a-O | #N/A | P11-S28a-O | #N/A | P12-S25a-O© | #N/A | P13-S28a-O | #N/A | P14-S14a-O | #N/A | P15-S28a-O | #N/A | P16-S25a-O© | #N/A | P17-S28a-O | #N/A | P18-S14a-O | #N/A
P6-S13a-O© | #N/A | P7-S29a-O© | #N/A | P8-S24a-O | #N/A | P9-S29a-O© | #N/A | P10-S13a-O© | #N/A | P11-S29a-O© | #N/A | P12-S24a-O | #N/A | P13-S29a-O© | #N/A | P14-S13a-O© | #N/A | P15-S29a-O© | #N/A | P16-S24a-O | #N/A | P17-S29a-O© | #N/A | P18-S13a-O© | #N/A
P6-S12a-O | #N/A | P7-S30a-O | #N/A | P8-S23a-O© | #N/A | P9-S30a-O | #N/A | P10-S12a-O | #N/A | P11-S30a-O | #N/A | P12-S23a-O© | #N/A | P13-S30a-O | #N/A | P14-S12a-O | #N/A | P15-S30a-O | #N/A | P16-S23a-O© | #N/A | P17-S30a-O | #N/A | P18-S12a-O | #N/A
P6-S11a-O© | #N/A | P7-S31a-O© | #N/A | P8-S22a-O | #N/A | P9-S31a-O© | #N/A | P10-S11a-O© | #N/A | P11-S31a-O© | #N/A | P12-S22a-O | #N/A | P13-S31a-O© | #N/A | P14-S11a-O© | #N/A | P15-S31a-O© | #N/A | P16-S22a-O | #N/A | P17-S31a-O© | #N/A | P18-S11a-O© | #N/A
P6-S10a-O | #N/A | P7-S32a-O | #N/A | P8-S21a-O© | #N/A | P9-S32a-O | #N/A | P10-S10a-O | #N/A | P11-S32a-O | #N/A | P12-S21a-O© | #N/A | P13-S32a-O | #N/A | P14-S10a-O | #N/A | P15-S32a-O | #N/A | P16-S21a-O© | #N/A | P17-S32a-O | #N/A | P18-S10a-O | #N/A
P6-S09a-O© | #N/A | P7-S33a-O© | #N/A | P8-S20a-O | #N/A | P9-S33a-O© | #N/A | P10-S09a-O© | #N/A | P11-S33a-O© | #N/A | P12-S20a-O | #N/A | P13-S33a-O© | #N/A | P14-S09a-O© | #N/A | P15-S33a-O© | #N/A | P16-S20a-O | #N/A | P17-S33a-O© | #N/A | P18-S09a-O© | #N/A
P6-S08a-O | #N/A | P7-S34a-O | #N/A | P8-S19a-O© | #N/A | P9-S34a-O | #N/A | P10-S08a-O | #N/A | P11-S34a-O | #N/A | P12-S19a-O© | #N/A | P13-S34a-O | #N/A | P14-S08a-O | #N/A | P15-S34a-O | #N/A | P16-S19a-O© | #N/A | P17-S34a-O | #N/A | P18-S08a-O | #N/A
P6-S07a-O | #N/A | P7-S18a-M | #N/A | P8-S18a-O | #N/A | P9-S06a-E | #N/A | P10-S07a-O | #N/A | P11-S18a-M | #N/A | P12-S18a-O | #N/A | P13-S06a-E | #N/A | P14-S07a-O | #N/A | P15-S18a-M | #N/A | P16-S18a-O | #N/A | P17-S06a-E | #N/A | P18-S07a-O | #N/A
P6-S06a-O | #N/A | P7-S17a-M | #N/A | P8-S17a-O© | #N/A | P9-S05a-E | #N/A | P10-S06a-O | #N/A | P11-S17a-M | #N/A | P12-S17a-O© | #N/A | P13-S05a-E | #N/A | P14-S06a-O | #N/A | P15-S17a-M | #N/A | P16-S17a-O© | #N/A | P17-S05a-E | #N/A | P18-S06a-O | #N/A
P6-S05a-O | #N/A | P7-S16a-M© | #N/A | P8-S16a-O | #N/A | P9-S04a-E | #N/A | P10-S05a-O | #N/A | P11-S16a-M© | #N/A | P12-S16a-O | #N/A | P13-S04a-E | #N/A | P14-S05a-O | #N/A | P15-S16a-M© | #N/A | P16-S16a-O | #N/A | P17-S04a-E | #N/A | P18-S05a-O | #N/A
P6-S04a-O | #N/A | P7-S15a-M | #N/A | P8-S15a-O© | #N/A | P9-S03a-E | #N/A | P10-S04a-O | #N/A | P11-S15a-M | #N/A | P12-S15a-O© | #N/A | P13-S03a-E | #N/A | P14-S04a-O | #N/A | P15-S15a-M | #N/A | P16-S15a-O© | #N/A | P17-S03a-E | #N/A | P18-S04a-O | #N/A
P6-S03a-O | #N/A | P7-S14a-M© | #N/A | P8-S14a-O | #N/A | P9-S02a-E | #N/A | P10-S03a-O | #N/A | P11-S14a-M© | #N/A | P12-S14a-O | #N/A | P13-S02a-E | #N/A | P14-S03a-O | #N/A | P15-S14a-M© | #N/A | P16-S14a-O | #N/A | P17-S02a-E | #N/A | P18-S03a-O | #N/A
P6-S02a-O | #N/A | P7-S13a-M | #N/A | P8-S13a-O© | #N/A | P9-S01-E | #N/A | P10-S02a-O | #N/A | P11-S13a-M | #N/A | P12-S13a-O© | #N/A | P13-S01-E | #N/A | P14-S02a-O | #N/A | P15-S13a-M | #N/A | P16-S13a-O© | #N/A | P17-S01-E | #N/A | P18-S02a-O | #N/A
P6-S01a-O | #N/A | P7-S12a-M© | #N/A | P8-S12a-O | #N/A | P9-S01a-E | #N/A | P10-S01a-O | #N/A | P11-S12a-M© | #N/A | P12-S12a-O | #N/A | P13-S01a-E | #N/A | P14-S01a-O | #N/A | P15-S12a-M© | #N/A | P16-S12a-O | #N/A | P17-S01a-E | #N/A | P18-S01a-O | #N/A
|  | P7-S11a-M | #N/A | P8-S11a-O© | #N/A |  |  |  |  | P11-S11a-M | #N/A | P12-S11a-O© | #N/A |  |  |  |  | P15-S11a-M | #N/A | P16-S11a-O© | #N/A
|  | P7-S10a-M© | #N/A | P8-S10a-O | #N/A |  |  |  |  | P11-S10a-M© | #N/A | P12-S10a-O | #N/A |  |  |  |  | P15-S10a-M© | #N/A | P16-S10a-O | #N/A
|  | P7-S09a-M | #N/A | P8-S09a-O© | #N/A |  |  |  |  | P11-S09a-M | #N/A | P12-S09a-O© | #N/A |  |  |  |  | P15-S09a-M | #N/A | P16-S09a-O© | #N/A
|  | P7-S08a-M© | #N/A | P8-S08a-O | #N/A |  |  |  |  | P11-S08a-M© | #N/A | P12-S08a-O | #N/A |  |  |  |  | P15-S08a-M© | #N/A | P16-S08a-O | #N/A
|  | P7-S07a-M | #N/A | P8-S07a-O | #N/A |  |  |  |  | P11-S07a-M | #N/A | P12-S07a-O | #N/A |  |  |  |  | P15-S07a-M | #N/A | P16-S07a-O | #N/A
|  | P7-S06a-M | #N/A | P8-S06a-O | #N/A |  |  |  |  | P11-S06a-M | #N/A | P12-S06a-O | #N/A |  |  |  |  | P15-S06a-M | #N/A | P16-S06a-O | #N/A
|  | P7-S05a-M | #N/A | P8-S05a-O | #N/A |  |  |  |  | P11-S05a-M | #N/A | P12-S05a-O | #N/A |  |  |  |  | P15-S05a-M | #N/A | P16-S05a-O | #N/A
|  | P7-S04a-M | #N/A | P8-S04a-O | #N/A |  |  |  |  | P11-S04a-M | #N/A | P12-S04a-O | #N/A |  |  |  |  | P15-S04a-M | #N/A | P16-S04a-O | #N/A
|  | P7-S03a-M | #N/A | P8-S03a-O | #N/A |  |  |  |  | P11-S03a-M | #N/A | P12-S03a-O | #N/A |  |  |  |  | P15-S03a-M | #N/A | P16-S03a-O | #N/A
|  | P7-S02a-M | #N/A | P8-S02a-O | #N/A |  |  |  |  | P11-S02a-M | #N/A | P12-S02a-O | #N/A |  |  |  |  | P15-S02a-M | #N/A | P16-S02a-O | #N/A
|  | P7-S01a-M | #N/A | P8-S01a-O | #N/A |  |  |  |  | P11-S01a-M | #N/A | P12-S01a-O | #N/A |  |  |  |  | P15-S01a-M | #N/A | P16-S01a-O | #N/A
41 | 0 | 52 | 0 | 52 | 0 | 41 | 0 | 41 | 0 | 52 | 0 | 52 | 0 | 41 | 0 | 41 | 0 | 52 | 0 | 52 | 0 | 41 | 0 | 41 | 0
13 | 0 | 18 | 0 | 18 | 0 | 13 | 0 | 13 | 0 | 18 | 0 | 18 | 0 | 13 | 0 | 13 | 0 | 18 | 0 | 18 | 0 | 13 | 0 | 13 | 0
Main Bridge - Segments Scope Vs Casting
P19 |  | P20 |  | P21 |  | P22 |  | P23 |  | P24 |  | P25 |  | P26 |  | P27 |  | P28 |  | P29 |  | Total
Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Seg. ID | Casted in | Segments | Casted
P19-S01a-O | #N/A | P20-S01a-M | #N/A | P21-S01a-O | #N/A | P22-S01a-E | #N/A | P23-S01a-O | #N/A | P24-S01a-M | #N/A | P25-S01a-O | #N/A | P26-S01a-E | #N/A | P27-S01a-O | #N/A | P28-S01a-M | #N/A | P29-S01a-O | #N/A | 24 | 0
P19-S02a-O | #N/A | P20-S02a-M | #N/A | P21-S02a-O | #N/A | P22-S01-E | #N/A | P23-S02a-O | #N/A | P24-S02a-M | #N/A | P25-S02a-O | #N/A | P26-S01-E | #N/A | P27-S02a-O | #N/A | P28-S02a-M | #N/A | P29-S02a-O | #N/A | 24 | 0
P19-S03a-O | #N/A | P20-S03a-M | #N/A | P21-S03a-O | #N/A | P22-S02a-E | #N/A | P23-S03a-O | #N/A | P24-S03a-M | #N/A | P25-S03a-O | #N/A | P26-S02a-E | #N/A | P27-S03a-O | #N/A | P28-S03a-M | #N/A | P29-S03a-O | #N/A | 24 | 0
P19-S04a-O | #N/A | P20-S04a-M | #N/A | P21-S04a-O | #N/A | P22-S03a-E | #N/A | P23-S04a-O | #N/A | P24-S04a-M | #N/A | P25-S04a-O | #N/A | P26-S03a-E | #N/A | P27-S04a-O | #N/A | P28-S04a-M | #N/A | P29-S04a-O | #N/A | 24 | 0
P19-S05a-O | #N/A | P20-S05a-M | #N/A | P21-S05a-O | #N/A | P22-S04a-E | #N/A | P23-S05a-O | #N/A | P24-S05a-M | #N/A | P25-S05a-O | #N/A | P26-S04a-E | #N/A | P27-S05a-O | #N/A | P28-S05a-M | #N/A | P29-S05a-O | #N/A | 24 | 0
P19-S06a-O | #N/A | P20-S06a-M | #N/A | P21-S06a-O | #N/A | P22-S05a-E | #N/A | P23-S06a-O | #N/A | P24-S06a-M | #N/A | P25-S06a-O | #N/A | P26-S05a-E | #N/A | P27-S06a-O | #N/A | P28-S06a-M | #N/A | P29-S06a-O | #N/A | 24 | 0
P19-S07a-O | #N/A | P20-S07a-M | #N/A | P21-S07a-O | #N/A | P22-S06a-E | #N/A | P23-S07a-O | #N/A | P24-S07a-M | #N/A | P25-S07a-O | #N/A | P26-S06a-E | #N/A | P27-S07a-O | #N/A | P28-S07a-M | #N/A | P29-S07a-O | #N/A | 24 | 0
P19-S08a-O | #N/A | P20-S08a-M© | #N/A | P21-S08a-O | #N/A | P22-S34a-O | #N/A | P23-S08a-O | #N/A | P24-S08a-M© | #N/A | P25-S08a-O | #N/A | P26-S34a-O | #N/A | P27-S08a-O | #N/A | P28-S08a-M© | #N/A | P29-S08a-O | #N/A | 24 | 0
P19-S09a-O© | #N/A | P20-S09a-M | #N/A | P21-S09a-O© | #N/A | P22-S33a-O© | #N/A | P23-S09a-O© | #N/A | P24-S09a-M | #N/A | P25-S09a-O© | #N/A | P26-S33a-O© | #N/A | P27-S09a-O© | #N/A | P28-S09a-M | #N/A | P29-S09a-O© | #N/A | 24 | 0
P19-S10a-O | #N/A | P20-S10a-M© | #N/A | P21-S10a-O | #N/A | P22-S32a-O | #N/A | P23-S10a-O | #N/A | P24-S10a-M© | #N/A | P25-S10a-O | #N/A | P26-S32a-O | #N/A | P27-S10a-O | #N/A | P28-S10a-M© | #N/A | P29-S10a-O | #N/A | 24 | 0
P19-S11a-O© | #N/A | P20-S11a-M | #N/A | P21-S11a-O© | #N/A | P22-S31a-O© | #N/A | P23-S11a-O© | #N/A | P24-S11a-M | #N/A | P25-S11a-O© | #N/A | P26-S31a-O© | #N/A | P27-S11a-O© | #N/A | P28-S11a-M | #N/A | P29-S11a-O© | #N/A | 24 | 0
P19-S12a-O | #N/A | P20-S12a-M© | #N/A | P21-S12a-O | #N/A | P22-S30a-O | #N/A | P23-S12a-O | #N/A | P24-S12a-M© | #N/A | P25-S12a-O | #N/A | P26-S30a-O | #N/A | P27-S12a-O | #N/A | P28-S12a-M© | #N/A | P29-S12a-O | #N/A | 24 | 0
P19-S13a-O© | #N/A | P20-S13a-M | #N/A | P21-S13a-O© | #N/A | P22-S29a-O© | #N/A | P23-S13a-O© | #N/A | P24-S13a-M | #N/A | P25-S13a-O© | #N/A | P26-S29a-O© | #N/A | P27-S13a-O© | #N/A | P28-S13a-M | #N/A | P29-S13a-O© | #N/A | 24 | 0
P19-S14a-O | #N/A | P20-S14a-M© | #N/A | P21-S14a-O | #N/A | P22-S28a-O | #N/A | P23-S14a-O | #N/A | P24-S14a-M© | #N/A | P25-S14a-O | #N/A | P26-S28a-O | #N/A | P27-S14a-O | #N/A | P28-S14a-M© | #N/A | P29-S14a-O | #N/A | 24 | 0
P19-S15a-O© | #N/A | P20-S15a-M | #N/A | P21-S15a-O© | #N/A | P22-S27a-O© | #N/A | P23-S15a-O© | #N/A | P24-S15a-M | #N/A | P25-S15a-O© | #N/A | P26-S27a-O© | #N/A | P27-S15a-O© | #N/A | P28-S15a-M | #N/A | P29-S15a-O© | #N/A | 24 | 0
P19-S16a-O | #N/A | P20-S16a-M© | #N/A | P21-S16a-O | #N/A | P22-S26a-O | #N/A | P23-S16a-O | #N/A | P24-S16a-M© | #N/A | P25-S16a-O | #N/A | P26-S26a-O | #N/A | P27-S16a-O | #N/A | P28-S16a-M© | #N/A | P29-S16a-O | #N/A | 24 | 0
P19-S17a-O© | #N/A | P20-S17a-M | #N/A | P21-S17a-O© | #N/A | P22-S25a-O© | #N/A | P23-S17a-O© | #N/A | P24-S17a-M | #N/A | P25-S17a-O© | #N/A | P26-S25a-O© | #N/A | P27-S17a-O© | #N/A | P28-S17a-M | #N/A | P29-S17a-O© | #N/A | 24 | 0
P19-S18a-O | #N/A | P20-S18a-M | #N/A | P21-S18a-O | #N/A | P22-S24a-O | #N/A | P23-S18a-O | #N/A | P24-S18a-M | #N/A | P25-S18a-O | #N/A | P26-S24a-O | #N/A | P27-S18a-O | #N/A | P28-S18a-M | #N/A | P29-S18a-O | #N/A | 24 | 0
P19-S19a-O© | #N/A | P20-S34a-O | #N/A | P21-S19a-O© | #N/A | P22-S23a-O© | #N/A | P23-S19a-O© | #N/A | P24-S34a-O | #N/A | P25-S19a-O© | #N/A | P26-S23a-O© | #N/A | P27-S19a-O© | #N/A | P28-S34a-O | #N/A | P29-S19a-O© | #N/A | 24 | 0
P19-S20a-O | #N/A | P20-S33a-O© | #N/A | P21-S20a-O | #N/A | P22-S22a-O | #N/A | P23-S20a-O | #N/A | P24-S33a-O© | #N/A | P25-S20a-O | #N/A | P26-S22a-O | #N/A | P27-S20a-O | #N/A | P28-S33a-O© | #N/A | P29-S20a-O | #N/A | 24 | 0
P19-S21a-O© | #N/A | P20-S32a-O | #N/A | P21-S21a-O© | #N/A | P22-S21a-O© | #N/A | P23-S21a-O© | #N/A | P24-S32a-O | #N/A | P25-S21a-O© | #N/A | P26-S21a-O© | #N/A | P27-S21a-O© | #N/A | P28-S32a-O | #N/A | P29-S21a-O© | #N/A | 24 | 0
P19-S22a-O | #N/A | P20-S31a-O© | #N/A | P21-S22a-O | #N/A | P22-S20a-O | #N/A | P23-S22a-O | #N/A | P24-S31a-O© | #N/A | P25-S22a-O | #N/A | P26-S20a-O | #N/A | P27-S22a-O | #N/A | P28-S31a-O© | #N/A | P29-S22a-O | #N/A | 24 | 0
P19-S23a-O© | #N/A | P20-S30a-O | #N/A | P21-S23a-O© | #N/A | P22-S19a-O© | #N/A | P23-S23a-O© | #N/A | P24-S30a-O | #N/A | P25-S23a-O© | #N/A | P26-S19a-O© | #N/A | P27-S23a-O© | #N/A | P28-S30a-O | #N/A | P29-S23a-O© | #N/A | 24 | 0
P19-S24a-O | #N/A | P20-S29a-O© | #N/A | P21-S24a-O | #N/A | P22-S18a-O | #N/A | P23-S24a-O | #N/A | P24-S29a-O© | #N/A | P25-S24a-O | #N/A | P26-S18a-O | #N/A | P27-S24a-O | #N/A | P28-S29a-O© | #N/A | P29-S24a-O | #N/A | 24 | 0
P19-S25a-O© | #N/A | P20-S28a-O | #N/A | P21-S25a-O© | #N/A | P22-S17a-O© | #N/A | P23-S25a-O© | #N/A | P24-S28a-O | #N/A | P25-S25a-O© | #N/A | P26-S17a-O© | #N/A | P27-S25a-O© | #N/A | P28-S28a-O | #N/A | P29-S25a-O© | #N/A | 24 | 0
P19-S26a-O | #N/A | P20-S27a-O© | #N/A | P21-S26a-O | #N/A | P22-S16a-O | #N/A | P23-S26a-O | #N/A | P24-S27a-O© | #N/A | P25-S26a-O | #N/A | P26-S16a-O | #N/A | P27-S26a-O | #N/A | P28-S27a-O© | #N/A | P29-S26a-O | #N/A | 24 | 0
P19-S27a-O© | #N/A | P20-S26a-O | #N/A | P21-S27a-O© | #N/A | P22-S15a-O© | #N/A | P23-S27a-O© | #N/A | P24-S26a-O | #N/A | P25-S27a-O© | #N/A | P26-S15a-O© | #N/A | P27-S27a-O© | #N/A | P28-S26a-O | #N/A | P29-S27a-O© | #N/A | 24 | 0
P19-S28a-O | #N/A | P20-S25a-O© | #N/A | P21-S28a-O | #N/A | P22-S14a-O | #N/A | P23-S28a-O | #N/A | P24-S25a-O© | #N/A | P25-S28a-O | #N/A | P26-S14a-O | #N/A | P27-S28a-O | #N/A | P28-S25a-O© | #N/A | P29-S28a-O | #N/A | 24 | 0
P19-S29a-O© | #N/A | P20-S24a-O | #N/A | P21-S29a-O© | #N/A | P22-S13a-O© | #N/A | P23-S29a-O© | #N/A | P24-S24a-O | #N/A | P25-S29a-O© | #N/A | P26-S13a-O© | #N/A | P27-S29a-O© | #N/A | P28-S24a-O | #N/A | P29-S29a-O© | #N/A | 24 | 0
P19-S30a-O | #N/A | P20-S23a-O© | #N/A | P21-S30a-O | #N/A | P22-S12a-O | #N/A | P23-S30a-O | #N/A | P24-S23a-O© | #N/A | P25-S30a-O | #N/A | P26-S12a-O | #N/A | P27-S30a-O | #N/A | P28-S23a-O© | #N/A | P29-S30a-O | #N/A | 24 | 0
P19-S31a-O© | #N/A | P20-S22a-O | #N/A | P21-S31a-O© | #N/A | P22-S11a-O© | #N/A | P23-S31a-O© | #N/A | P24-S22a-O | #N/A | P25-S31a-O© | #N/A | P26-S11a-O© | #N/A | P27-S31a-O© | #N/A | P28-S22a-O | #N/A | P29-S31a-O© | #N/A | 24 | 0
P19-S32a-O | #N/A | P20-S21a-O© | #N/A | P21-S32a-O | #N/A | P22-S10a-O | #N/A | P23-S32a-O | #N/A | P24-S21a-O© | #N/A | P25-S32a-O | #N/A | P26-S10a-O | #N/A | P27-S32a-O | #N/A | P28-S21a-O© | #N/A | P29-S32a-O | #N/A | 24 | 0
P19-S33a-O© | #N/A | P20-S20a-O | #N/A | P21-S33a-O© | #N/A | P22-S09a-O© | #N/A | P23-S33a-O© | #N/A | P24-S20a-O | #N/A | P25-S33a-O© | #N/A | P26-S09a-O© | #N/A | P27-S33a-O© | #N/A | P28-S20a-O | #N/A | P29-S33a-O© | #N/A | 24 | 0
P19-S34a-O | #N/A | P20-S19a-O© | #N/A | P21-S34a-O | #N/A | P22-S08a-O | #N/A | P23-S34a-O | #N/A | P24-S19a-O© | #N/A | P25-S34a-O | #N/A | P26-S08a-O | #N/A | P27-S34a-O | #N/A | P28-S19a-O© | #N/A | P29-S34a-O | #N/A | 24 | 0
P19-S18a-M | #N/A | P20-S18a-O | #N/A | P21-S06a-E | #N/A | P22-S07a-O | #N/A | P23-S18a-M | #N/A | P24-S18a-O | #N/A | P25-S06a-E | #N/A | P26-S07a-O | #N/A | P27-S18a-M | #N/A | P28-S18a-O | #N/A | P29-S06a-E | #N/A | 24 | 0
P19-S17a-M | #N/A | P20-S17a-O© | #N/A | P21-S05a-E | #N/A | P22-S06a-O | #N/A | P23-S17a-M | #N/A | P24-S17a-O© | #N/A | P25-S05a-E | #N/A | P26-S06a-O | #N/A | P27-S17a-M | #N/A | P28-S17a-O© | #N/A | P29-S05a-E | #N/A | 24 | 0
P19-S16a-M© | #N/A | P20-S16a-O | #N/A | P21-S04a-E | #N/A | P22-S05a-O | #N/A | P23-S16a-M© | #N/A | P24-S16a-O | #N/A | P25-S04a-E | #N/A | P26-S05a-O | #N/A | P27-S16a-M© | #N/A | P28-S16a-O | #N/A | P29-S04a-E | #N/A | 24 | 0
P19-S15a-M | #N/A | P20-S15a-O© | #N/A | P21-S03a-E | #N/A | P22-S04a-O | #N/A | P23-S15a-M | #N/A | P24-S15a-O© | #N/A | P25-S03a-E | #N/A | P26-S04a-O | #N/A | P27-S15a-M | #N/A | P28-S15a-O© | #N/A | P29-S03a-E | #N/A | 24 | 0
P19-S14a-M© | #N/A | P20-S14a-O | #N/A | P21-S02a-E | #N/A | P22-S03a-O | #N/A | P23-S14a-M© | #N/A | P24-S14a-O | #N/A | P25-S02a-E | #N/A | P26-S03a-O | #N/A | P27-S14a-M© | #N/A | P28-S14a-O | #N/A | P29-S02a-E | #N/A | 24 | 0
P19-S13a-M | #N/A | P20-S13a-O© | #N/A | P21-S01-E | #N/A | P22-S02a-O | #N/A | P23-S13a-M | #N/A | P24-S13a-O© | #N/A | P25-S01-E | #N/A | P26-S02a-O | #N/A | P27-S13a-M | #N/A | P28-S13a-O© | #N/A | P29-S01-E | #N/A | 24 | 0
P19-S12a-M© | #N/A | P20-S12a-O | #N/A | P21-S01a-E | #N/A | P22-S01a-O | #N/A | P23-S12a-M© | #N/A | P24-S12a-O | #N/A | P25-S01a-E | #N/A | P26-S01a-O | #N/A | P27-S12a-M© | #N/A | P28-S12a-O | #N/A | P29-S01a-E | #N/A | 24 | 0
P19-S11a-M | #N/A | P20-S11a-O© | #N/A |  |  |  |  | P23-S11a-M | #N/A | P24-S11a-O© | #N/A |  |  |  |  | P27-S11a-M | #N/A | P28-S11a-O© | #N/A |  |  | 12 | 0
P19-S10a-M© | #N/A | P20-S10a-O | #N/A |  |  |  |  | P23-S10a-M© | #N/A | P24-S10a-O | #N/A |  |  |  |  | P27-S10a-M© | #N/A | P28-S10a-O | #N/A |  |  | 12 | 0
P19-S09a-M | #N/A | P20-S09a-O© | #N/A |  |  |  |  | P23-S09a-M | #N/A | P24-S09a-O© | #N/A |  |  |  |  | P27-S09a-M | #N/A | P28-S09a-O© | #N/A |  |  | 12 | 0
P19-S08a-M© | #N/A | P20-S08a-O | #N/A |  |  |  |  | P23-S08a-M© | #N/A | P24-S08a-O | #N/A |  |  |  |  | P27-S08a-M© | #N/A | P28-S08a-O | #N/A |  |  | 12 | 0
P19-S07a-M | #N/A | P20-S07a-O | #N/A |  |  |  |  | P23-S07a-M | #N/A | P24-S07a-O | #N/A |  |  |  |  | P27-S07a-M | #N/A | P28-S07a-O | #N/A |  |  | 12 | 0
P19-S06a-M | #N/A | P20-S06a-O | #N/A |  |  |  |  | P23-S06a-M | #N/A | P24-S06a-O | #N/A |  |  |  |  | P27-S06a-M | #N/A | P28-S06a-O | #N/A |  |  | 12 | 0
P19-S05a-M | #N/A | P20-S05a-O | #N/A |  |  |  |  | P23-S05a-M | #N/A | P24-S05a-O | #N/A |  |  |  |  | P27-S05a-M | #N/A | P28-S05a-O | #N/A |  |  | 12 | 0
P19-S04a-M | #N/A | P20-S04a-O | #N/A |  |  |  |  | P23-S04a-M | #N/A | P24-S04a-O | #N/A |  |  |  |  | P27-S04a-M | #N/A | P28-S04a-O | #N/A |  |  | 12 | 0
P19-S03a-M | #N/A | P20-S03a-O | #N/A |  |  |  |  | P23-S03a-M | #N/A | P24-S03a-O | #N/A |  |  |  |  | P27-S03a-M | #N/A | P28-S03a-O | #N/A |  |  | 12 | 0
P19-S02a-M | #N/A | P20-S02a-O | #N/A |  |  |  |  | P23-S02a-M | #N/A | P24-S02a-O | #N/A |  |  |  |  | P27-S02a-M | #N/A | P28-S02a-O | #N/A |  |  | 12 | 0
P19-S01a-M | #N/A | P20-S01a-O | #N/A |  |  |  |  | P23-S01a-M | #N/A | P24-S01a-O | #N/A |  |  |  |  | P27-S01a-M | #N/A | P28-S01a-O | #N/A |  |  | 12 | 0
52 | 0 | 52 | 0 | 41 | 0 | 41 | 0 | 52 | 0 | 52 | 0 | 41 | 0 | 41 | 0 | 52 | 0 | 52 | 0 | 41 | 0 | 1116 | 0
18 | 0 | 18 | 0 | 13 | 0 | 13 | 0 | 18 | 0 | 18 | 0 | 13 | 0 | 13 | 0 | 18 | 0 | 18 | 0 | 13 | 0 | 372 | 0
Description |  |  | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Total Segments Casted |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cable Segments Casted |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Schedule 4
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/19 MPSB/Sur/1429 MPSB/MB/20 | 2025-06-16 | IPC - 18 | P17-BP-S09a-O© | 2025-07-01 | Profile Check Survey Check Formwork & Concreting
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/22 MPSB/MB/25 | 21-Jun-25 25-Jun-25 | IPC - 18 | P17-BP-S10a-O | 2025-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/Sur/1482 MPSB/MB/0031 | 2-Jul-25 2-Jul-25 | IPC - 18 | P17-BP-S11a-O© | 2025-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/034 MPSB/Sur/1506 MPSB/MB/038 | 7-Jul-25 9-Jul-25 9-Jul-25 | IPC - 18 | P17-BP-S12a-O | 2025-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/040 MPSB/Sur/1527 MPSB/MB/042 | 11-Jul-25 15-Jul-25 15-Jul-25 | IPC - 18 | P17-BP-S13a-O© | 2025-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/046 MPSB/Sur/1558 MPSB/MB/049 | 17-Jul-25 21-Jul-25 21-Jul-25 | IPC - 18 | P17-BP-S14a-O | 2025-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/054 MPSB/Sur/1589 MPSB/MB/057 | 25-Jul-25 26-Jul-25 28-Jul-25 | IPC - 18 | P17-BP-S15a-O© | 2025-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/033 MPSB/Sur/1508 MPSB/MB/039 | 3-Jul-25 10-Jul-25 10-Jul-25 | IPC - 18 | P25-KS-S09-O© | 2025-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/044 MPSB/Sur/1546 MPSB/MB/047 | 16-Jul-25 19-Jul-25 19-Jul-25 | IPC - 18 | P25-KS-S10-O | 2025-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/037 MPSB/Sur/1603 MPSB/MB/059 | 8-Jul-25 29-Jul-25 29-Jul-25 | IPC - 18 | P25-KS-S11-O© | 2025-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/60 MPSB/Sur/1636 MPSB/MB/65 | 30-Jul-25 1-Aug-25 1-Aug-25 | IPC - 19 | P17-BP-S16a-O | 2025-08-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/69 MPSB/Sur/1657 MPSB/MB/74 | 4-Aug-25 7-Aug-25 7-Aug-25 | IPC - 19 | P17-BP-S17a-O© | 2025-08-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/75 MPSB/Sur/1685 MPSB/MB/83 | 7-Aug-25 12-Aug-25 12-Aug-25 | IPC - 19 | P17-BP-S18a-O | 2025-08-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/84 MPSB/Sur/1698 MPSB/MB/93 | 12-Aug-25 18-Aug-25 18-Aug-25 | IPC - 19 | P17-BP-S19a-O© | 2025-08-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/Sur/1727 MPSB/MB/107 | 24-Aug-25 24-Aug-25 | IPC - 19 | P17-BP-S20a-O | 2025-08-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/119 MPSB/Sur/1752 MPSB/MB/122 | 29-Aug-25 30-Aug-25 30-Aug-25 | IPC - 19 | P17-BP-S21a-O© | 2025-08-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/92 MPSB/Sur/1714 MPSB/MB/104 | 18-Aug-25 21-Aug-25 21-Aug-25 | IPC - 19 | P17-BP-S22a-O | 2025-08-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/110 MPSB/Sur/1741 MPSB/MB/116 | 26-Aug-25 28-Aug-25 28-Aug-25 | IPC - 19 | P17-BP-S23a-O© | 2025-08-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/58 MPSB/Sur/1645 MPSB/MB/68 | 29-Jul-25 4-Aug-25 4-Aug-25 | IPC - 19 | P17-KS-S09-O© | 2025-08-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/76 MPSB/Sur/1681 MPSB/MB/80 | 7-Aug-25 11-Aug-25 11-Aug-25 | IPC - 19 | P17-KS-S10-O | 2025-08-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/86 MPSB/Sur/1696 MPSB/MB/90 | 12-Aug-25 16-Aug-25 16-Aug-25 | IPC - 19 | P17-KS-S11-O© | 2025-08-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/95 MPSB/Sur/1713 MPSB/MB/103 | 18-Aug-25 21-Aug-25 21-Aug-25 | IPC - 19 | P17-KS-S12-O | 2025-08-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/108 MPSB/Sur/1736 MPSB/MB/112 | 24-Aug-25 27-Aug-25 27-Aug-25 | IPC - 19 | P17-KS-S13-O© | 2025-08-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/114 MPSB/Sur/1753 MPSB/MB/123 | 27-Aug-25 30-Aug-25 30-Aug-25 | IPC - 19 | P17-KS-S14-O | 2025-08-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/63 MPSB/Sur/1644 MPSB/MB/67 | 1-Aug-25 4-Aug-25 4-Aug-25 | IPC - 19 | P25-KS-S12-O | 2025-08-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/72 MPSB/Sur/1667 MPSB/MB/78 | 7-Aug-25 9-Aug-25 9-Aug-25 | IPC - 19 | P25-KS-S13-O© | 2025-08-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/85 MPSB/Sur/1695 MPSB/MB/89 | 12-Aug-25 16-Aug-25 16-Aug-25 | IPC - 19 | P25-KS-S14-O | 2025-08-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/96 MPSB/Sur/1712 MPSB/MB/101 | 18-Aug-25 21-Aug-25 21-Aug-25 | IPC - 19 | P25-KS-S15-O© | 2025-08-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/100 MPSB/Sur/1730 MPSB/MB/109 | 21-Aug-25 25-Aug-25 25-Aug-25 | IPC - 19 | P25-KS-S16-O | 2025-08-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/121 MPSB/Sur/1759 MPSB/MB/127 | 30-Aug-25 1-Sep-25 1-Sep-25 | IPC - 20 | P17-BP-S24a-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/134 MPSB/Sur/1778 MPSB/MB/138 | 4-Sep-25 6-Sep-25 6-Sep-25 | IPC - 20 | P17-BP-S25a-O© | 2025-09-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/141 MPSB/Sur/1800 MPSB/MB/144 | 8-Sep-25 9-Sep-25 9-Sep-25 | IPC - 20 | P17-BP-S26a-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/151 MPSB/Sur/1818 MPSB/MB/157 | 11-Sep-25 13-Sep-25 13-Sep-25 | IPC - 20 | P17-BP-S27a-O© | 2025-09-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/166 MPSB/Sur/1833 MPSB/MB/177 | 15-Sep-25 18-Sep-25 18-Sep-25 | IPC - 20 | P17-BP-S28a-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/182 MPSB/Sur/1861 MPSB/MB/192 | 19-Sep-25 23-Sep-25 23-Sep-25 | IPC - 20 | P17-BP-S29a-O© | 2025-09-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/200 MPSB/Sur/1882 MPSB/MB/207 | 25-Sep-25 27-Sep-25 27-Sep-25 | IPC - 20 | P17-BP-S30a-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/Str/2345 MPSB/Sur/1897 MPSB/MB/213 | 29-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | P17-BP-S31a-O© | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/128 MPSB/Sur/1769 MPSB/MB/135 | 1-Sep-25 4-Sep-25 4-Sep-25 | IPC - 20 | P17-KS-S15-O© | 2025-09-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/137 MPSB/Sur/1794 MPSB/MB/142 | 6-Sep-25 8-Sep-25 8-Sep-25 | IPC - 20 | P17-KS-S16-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/152 MPSB/Sur/1816 MPSB/MB/154 | 11-Sep-25 12-Sep-25 12-Sep-25 | IPC - 20 | P17-KS-S17-O© | 2025-09-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/162 MPSB/Sur/1834 MPSB/MB/178 | 13-Sep-25 18-Sep-25 18-Sep-25 | IPC - 20 | P17-KS-S18-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/185 MPSB/Sur/1859 MPSB/MB/188 | 20-Sep-25 22-Sep-25 22-Sep-25 | IPC - 20 | P17-KS-S19-O© | 2025-09-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/196 MPSB/Sur/1878 MPSB/MB/206 | 24-Sep-25 27-Sep-25 27-Sep-25 | IPC - 20 | P17-KS-S20-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/Str/2346 MPSB/Sur/1896 MPSB/MB/212 | 29-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | P17-KS-S21-O© | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/111 MPSB/Sur/1758 MPSB/MB/126 | 27-Aug-25 1-Sep-25 1-Sep-25 | IPC - 20 | P25-KS-S17-O© | 2025-09-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/133 MPSB/Sur/1793 MPSB/MB/140 | 4-Sep-25 8-Sep-25 8-Sep-25 | IPC - 20 | P25-KS-S18-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/148 MPSB/Sur/1820 MPSB/MB/159 | 10-Sep-25 13-Sep-25 13-Sep-25 | IPC - 20 | P25-KS-S19-O© | 2025-09-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/169 MPSB/Sur/1838 MPSB/MB/180 | 16-Sep-25 19-Sep-25 19-Sep-25 | IPC - 20 | P25-KS-S20-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/202 MPSB/Sur/1876 MPSB/MB/204 | 25-Sep-25 26-Sep-25 26-Sep-25 | IPC - 20 | P25-KS-S21-O© | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/125 MPSB/Sur/1819 MPSB/MB/158 | 1-Sep-25 13-Sep-25 13-Sep-25 | IPC - 20 | P25-BP-S09a-O© | 2025-09-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/170 MPSB/Sur/1860 MPSB/MB/191 | 16-Sep-25 22-Sep-25 22-Sep-25 | IPC - 20 | P25-BP-S10a-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/201 MPSB/Sur/1883 MPSB/MB/209 | 25-Sep-25 27-Sep-25 27-Sep-25 | IPC - 20 | P25-BP-S11a-O© | 2025-09-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/210 MPSB/Sur/1895 MPSB/MB/211 | 30-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | P25-BP-S12a-O | 2025-09-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/264 MPSB/Sur/2011 MPSB/MB/271 | 16-Oct-25 18-Oct-25 18-Oct-25 | IPC - 22 | P17-BP-S33a-O© | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/285 MPSB/Sur/2043 MPSB/MB/294 | 23-Oct-25 25-Oct-25 25-Oct-25 | IPC - 22 | P17-BP-S34a-O | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/197 MPSB/Sur/1898 MPSB/MB/214 | 24-Sep-25 30-Sep-25 30-Sep-25 | IPC - 22 | P18-KS-S01a-E | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/220 MPSB/Sur/1934 MPSB/MB/233 | 03-Oct-25 07-Oct-25 07-Oct-25 | IPC - 22 | P18-KS-S01-E | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/245 MPSB/Sur/1976 MPSB/MB/256 | 10-Oct-25 13-Oct-25 13-Oct-25 | IPC - 22 | P18-KS-S02-E | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/276 MPSB/Sur/2024 MPSB/MB/281 | 20-Oct-25 22-Oct-25 22-Oct-25 | IPC - 22 | P18-KS-S03-E | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/297 MPSB/Sur/2064 MPSB/MB/302 | 27-Oct-25 28-Oct-25 28-Oct-25 | IPC - 22 | P18-KS-S04-E | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/305 MPSB/Sur/2087 MPSB/MB/319 | 30-Oct-25 31-Oct-25 31-Oct-25 | IPC - 22 | P18-KS-S05-E | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/195 MPSB/Sur/1927 MPSB/MB/230 | 24-Sep-25 06-Oct-25 06-Oct-25 | IPC - 22 | P17-KS-S22-O | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/227 MPSB/Sur/1957 MPSB/MB/241 | 06-Oct-25 09-Oct-25 09-Oct-25 | IPC - 22 | P17-KS-S23-O© | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/249 MPSB/Sur/1978 MPSB/MB/257 | 11-Oct-25 14-Oct-25 14-Oct-25 | IPC - 22 | P17-KS-S24-O | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/259 MPSB/Sur/1998 MPSB/MB/266 | 14-Oct-25 17-Oct-25 17-Oct-25 | IPC - 22 | P17-KS-S25-O© | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/273 MPSB/Sur/2023 MPSB/MB/278 | 19-Oct-25 22-Oct-25 22-Oct-25 | IPC - 22 | P17-KS-S26-O | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/286 MPSB/Sur/2057 MPSB/MB/296 | 23-Oct-25 27-Oct-25 27-Oct-25 | IPC - 22 | P17-KS-S27-O© | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/301 MPSB/Sur/2073 MPSB/MB/307 | 28-Oct-25 30-Oct-25 30-Oct-25 | IPC - 22 | P17-KS-S28-O | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/232 MPSB/Sur/1949 MPSB/MB/239 | 06-Oct-25 09-Oct-25 09-Oct-25 | IPC - 22 | P25-BP-S13a-O© | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/248 MPSB/Sur/1972 MPSB/MB/253 | 11-Oct-25 13-Oct-25 13-Oct-25 | IPC - 22 | P25-BP-S14a-O | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/262 MPSB/Sur/2002 MPSB/MB/270 | 15-Oct-25 17-Oct-25 17-Oct-25 | IPC - 22 | P25-BP-S15a-O© | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/280 MPSB/Sur/2036 MPSB/MB/288 | 22-Oct-25 24-Oct-25 24-Oct-25 | IPC - 22 | P25-BP-S16a-O | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/304 MPSB/Sur/2074 MPSB/MB/310 | 28-Oct-25 30-Oct-25 30-Oct-25 | IPC - 22 | P25-BP-S17a-O© | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/198 MPSB/Sur/1915 MPSB/MB/217 | 24-Sep-25 03-Oct-25 03-Oct-25 | IPC - 22 | P23-KS-S09a-O© | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/231 MPSB/Sur/1948 MPSB/MB/235 | 06-Oct-25 08-Oct-25 08-Oct-25 | IPC - 22 | P23-KS-S10a-O | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/243 MPSB/Sur/1970 MPSB/MB/250 | 10-Oct-25 11-Oct-25 11-Oct-25 | IPC - 22 | P23-KS-S11a-O© | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/252 MPSB/Sur/1987 MPSB/MB/260 | 13-Oct-25 15-Oct-25 15-Oct-25 | IPC - 22 | P23-KS-S12a-O | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/269 MPSB/Sur/2015 MPSB/MB/272 | 17-Oct-25 18-Oct-25 18-Oct-25 | IPC - 22 | P23-KS-S13a-O© | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/274 MPSB/Sur/2018 MPSB/MB/279 | 19-Oct-25 22-Oct-25 22-Oct-25 | IPC - 22 | P23-KS-S14a-O | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/289 MPSB/Sur/2055 MPSB/MB/295 | 24-Oct-25 27-Oct-25 27-Oct-25 | IPC - 22 | P23-KS-S15a-O© | 2025-10-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/303 MPSB/Sur/2075 MPSB/MB/311 | 28-Oct-25 30-Oct-25 30-Oct-25 | IPC - 22 | P23-KS-S16a-O | 2025-10-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/320 MPSB/Sur/2119 MPSB/MB/327 | 01-Nov-25 03-Nov-25 03-Nov-25 | IPC - 23 | P17-KS-S29-O© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/329 MPSB/Sur/2169 MPSB/MB/344 | 04-Nov-25 10-Nov-25 10-Nov-25 | IPC - 23 | P17-KS-S30-O | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/369 MPSB/Sur/2237 MPSB/MB/381 | 17-Nov-25 20-Nov-25 20-Nov-25 | IPC - 23 | P17-KS-S31-O© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/390 MPSB/Sur/2272 MPSB/MB/402 | 22-Nov-25 25-Nov-25 25-Nov-25 | IPC - 23 | P17-KS-S32-O | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/323 MPSB/Sur/2129 MPSB/MB/332 | 03-Nov-25 06-Nov-25 06-Nov-25 | IPC - 23 | P18-KS-S06-E | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/312 MPSB/Sur/2122 MPSB/MB/331 | 31-Oct-25 04-Nov-25 04-Nov-25 | IPC - 23 | P23-KS-S17a-O© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/336 MPSB/Sur/2141 MPSB/MB/337 | 07-Nov-25 07-Nov-25 07-Nov-25 | IPC - 23 | P23-KS-S18a-O | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/346 MPSB/Sur/2194 MPSB/MB/359 | 11-Nov-25 15-Nov-25 15-Nov-25 | IPC - 23 | P23-KS-S19a-O© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/374 MPSB/Sur/2229 MPSB/MB/377 | 19-Nov-25 20-Nov-25 20-Nov-25 | IPC - 23 | P23-KS-S20a-O | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/414 MPSB/Sur/2299 MPSB/MB/417 | 27-Nov-25 28-Nov-25 28-Nov-25 | IPC - 23 | P23-KS-S21a-O© | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/343 MPSB/Sur/2182 MPSB/MB/353 | 09-Nov-25 13-Nov-25 13-Nov-25 | IPC - 23 | P24-KS-S08-M© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/366 MPSB/Sur/2220 MPSB/MB/373 | 17-Nov-25 18-Nov-25 18-Nov-25 | IPC - 23 | P24-KS-S09-M | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/386 MPSB/Sur/2248 MPSB/MB/389 | 21-Nov-25 22-Nov-25 22-Nov-25 | IPC - 23 | P24-KS-S10-M© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/400 MPSB/Sur/2281 MPSB/MB/406 | 25-Nov-25 26-Nov-25 26-Nov-25 | IPC - 23 | P24-KS-S11-M | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/425 MPSB/Sur/2305 MPSB/MB/426 | 29-Nov-25 29-Nov-25 29-Nov-25 | IPC - 23 | P24-KS-S12-M© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/347 MPSB/Sur/2195 MPSB/MB/360 | 11-Nov-25 15-Nov-25 15-Nov-25 | IPC - 23 | P25-BP-S18a-O | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/375 MPSB/Sur/2244 MPSB/MB/388 | 19-Nov-25 21-Nov-25 21-Nov-25 | IPC - 23 | P25-BP-S19a-O© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/418 MPSB/MB/427 | 28-Nov-25 30-Nov-25 | IPC - 23 | P25-BP-S20a-O | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/351 MPSB/Sur/2207 MPSB/MB/363 | 11-Nov-25 17-Nov-25 17-Nov-25 | IPC - 23 | P7-BP-S01-O | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/383 MPSB/Sur/2258 MPSB/MB/397 | 21-Nov-25 24-Nov-25 24-Nov-25 | IPC - 23 | P7-BP-S02-O | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/412 MPSB/Sur/2303 MPSB/MB/422 | 27-Nov-25 29-Nov-25 29-Nov-25 | IPC - 23 | P7-BP-S03-O | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/338 MPSB/Sur/2177 MPSB/MB/352 | 08-Nov-25 12-Nov-25 12-Nov-25 | IPC - 23 | P7-BP-S09-O© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/358 MPSB/Sur/2206 MPSB/MB/362 | 14-Nov-25 17-Nov-25 17-Nov-25 | IPC - 23 | P7-BP-S10-O | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/367 MPSB/Sur/2238 MPSB/MB/382 | 18-Nov-25 20-Nov-25 20-Nov-25 | IPC - 23 | P7-BP-S11-O© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/368 MPSB/Sur/2257 MPSB/MB/396 | 18-Nov-25 24-Nov-25 24-Nov-25 | IPC - 23 | P7-BP-S12-O | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/403 MPSB/Sur/2291 MPSB/MB/415 | 26-Nov-25 27-Nov-25 27-Nov-25 | IPC - 23 | P7-BP-S13-O© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/398 MPSB/MB/419 | 24-Nov-25 28-Nov-25 | IPC - 23 | P7-BP-S14-O | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/354 MPSB/Sur/2205 MPSB/MB/361 | 13-Nov-25 17-Nov-25 17-Nov-25 | IPC - 23 | P7-KS-S09a-O© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/384 MPSB/Sur/2249 MPSB/MB/391 | 21-Nov-25 22-Nov-25 22-Nov-25 | IPC - 23 | P7-KS-S10a-O | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/404 MPSB/Sur/2285 MPSB/MB/411 | 26-Nov-25 27-Nov-25 27-Nov-25 | IPC - 23 | P7-KS-S11a-O© | 2025-11-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/420 MPSB/Sur/2304 MPSB/MB/423 | 28-Nov-25 29-Nov-25 29-Nov-25 | IPC - 23 | P7-KS-S12a-O | 2025-11-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/434 MPSB/Sur/2336 MPSB/MB/435 | 2-Dec-25 4-Dec-25 2-Dec-25 | IPC - 25 | P17-KS-S33-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/453 MPSB/Sur/2366 MPSB/MB/464 | 6-Dec-25 8-Dec-25 8-Dec-25 | IPC - 25 | P17-KS-S34-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/461 MPSB/Sur/2377 MPSB/MB/472 | 7-Dec-25 9-Dec-25 9-Dec-25 | IPC - 25 | P23-BP-S09-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/490 MPSB/Sur/2402 MPSB/MB/491 | 13-Dec-25 13-Dec-25 13-Dec-25 | IPC - 25 | P23-BP-S10-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/508 MPSB/Sur/2445 MPSB/MB/522 | 16-Dec-25 18-Dec-25 18-Dec-25 | IPC - 25 | P23-BP-S11-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/528 MPSB/Sur/2458 MPSB/MB/534 | 20-Dec-25 21-Dec-25 21-Dec-25 | IPC - 25 | P23-BP-S12-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/540 MPSB/Sur/2496 MPSB/MB/566 | 23-Dec-25 25-Dec-25 25-Dec-25 | IPC - 25 | P23-BP-S13-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/569 MPSB/Sur/2512 MPSB/MB/575 | 26-Dec-25 27-Dec-25 27-Dec-25 | IPC - 25 | P23-BP-S14-O | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/387 MPSB/Sur/2347 MPSB/MB/452 | 21-Nov-25 5-Dec-25 5-Dec-25 | IPC - 25 | P24-KS-S13-M | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/462 MPSB/Sur/2376 MPSB/MB/471 | 8-Dec-25 9-Dec-25 9-Dec-25 | IPC - 25 | P24-KS-S14-M© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/485 MPSB/Sur/2398 MPSB/MB/487 | 12-Dec-25 12-Dec-25 12-Dec-25 | IPC - 25 | P24-KS-S15-M | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/505 MPSB/Sur/2420 MPSB/MB/507 | 15-Dec-25 16-Dec-25 16-Dec-25 | IPC - 25 | P24-KS-S16-M© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/527 MPSB/Sur/2451 MPSB/MB/529 | 20-Dec-25 20-Dec-25 20-Dec-25 | IPC - 25 | P24-KS-S17-M | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/564 MPSB/Sur/2497 MPSB/MB/567 | 25-Dec-25 25-Dec-25 25-Dec-25 | IPC - 25 | P24-KS-S18-M | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/595 MPSB/Sur/2578 MPSB/MB/611 | 30-Dec-25 31-Dec-25 31-Dec-25 | IPC - 25 | P25-BP-S21a-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/506 MPSB/Sur/2433 MPSB/MB/520 | 15-Dec-25 17-Dec-25 17-Dec-25 | IPC - 25 | P25-KS-S22-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/539 MPSB/Sur/2472 MPSB/MB/541 | 23-Dec-25 23-Dec-25 23-Dec-25 | IPC - 25 | P25-KS-S23-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/568 MPSB/Sur/2511 MPSB/MB/574 | 26-Dec-25 27-Dec-25 27-Dec-25 | IPC - 25 | P25-KS-S24-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/593 MPSB/Sur/2551 MPSB/MB/596 | 29-Dec-25 30-Dec-25 30-Dec-25 | IPC - 25 | P25-KS-S25-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/445 MPSB/Sur/2352 MPSB/MB/454 | 4-Dec-25 6-Dec-25 6-Dec-25 | IPC - 25 | P7-BP-S04-O | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/467 MPSB/Sur/2380 MPSB/MB/474 | 8-Dec-25 10-Dec-25 10-Dec-25 | IPC - 25 | P7-BP-S05-O | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/496 MPSB/Sur/2427 MPSB/MB/513 | 14-Dec-25 17-Dec-25 17-Dec-25 | IPC - 25 | P7-BP-S06-O | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/512 MPSB/Sur/2463 MPSB/MB/537 | 17-Dec-25 22-Dec-25 22-Dec-25 | IPC - 25 | P7-BP-S07-O | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/545 MPSB/Sur/2515 MPSB/MB/576 | 23-Dec-25 27-Dec-25 27-Dec-25 | IPC - 25 | P7-BP-S08-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/440 MPSB/Sur/2337 MPSB/MB/448 | 3-Dec-25 4-Dec-25 4-Dec-25 | IPC - 25 | P7-BP-S15-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/458 MPSB/Sur/2381 MPSB/MB/468 | 6-Dec-25 10-Dec-25 9-Dec-25 | IPC - 25 | P7-BP-S16-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/476 MPSB/Sur/2415 MPSB/MB/504 | 10-Dec-25 15-Dec-25 15-Dec-25 | IPC - 25 | P7-BP-S17-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/511 MPSB/Sur/2429 MPSB/MB/515 | 17-Dec-25 17-Dec-25 17-Dec-25 | IPC - 25 | P7-BP-S18-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/531 MPSB/Sur/2464 MPSB/MB/538 | 20-Dec-25 22-Dec-25 22-Dec-25 | IPC - 25 | P7-BP-S19-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/552 MPSB/Sur/2495 MPSB/MB/559 | 24-Dec-25 25-Dec-25 25-Dec-25 | IPC - 25 | P7-BP-S20-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/Sur/2531 MPSB/MB/584 | 29-Dec-25 30-Dec-25 | IPC - 25 | P7-BP-S21-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/459 MPSB/Sur/2367 MPSB/MB/465 | 6-Dec-25 8-Dec-25 8-Dec-25 | IPC - 25 | P7-BP-S22-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/477 MPSB/Sur/2399 MPSB/MB/489 | 10-Dec-25 12-Dec-25 12-Dec-25 | IPC - 25 | P7-BP-S23-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/502 MPSB/Sur/2421 MPSB/MB/510 | 15-Dec-25 16-Dec-25 16-Dec-25 | IPC - 25 | P7-BP-S24-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/521 MPSB/Sur/2449 MPSB/MB/525 | 18-Dec-25 19-Dec-25 19-Dec-25 | IPC - 25 | P7-BP-S25-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/543 MPSB/Sur/2490 MPSB/MB/553 | 23-Dec-25 24-Dec-25 24-Dec-25 | IPC - 25 | P7-BP-S26-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/578 MPSB/Sur/2530 MPSB/MB/583 | 27-Dec-25 29-Dec-25 29-Dec-25 | IPC - 25 | P7-BP-S27-O© | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/444 MPSB/Sur/2344 MPSB/MB/451 | 4-Dec-25 5-Dec-25 5-Dec-25 | IPC - 25 | P7-KS-S13a-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/466 MPSB/Sur/2379 MPSB/MB/473 | 8-Dec-25 10-Dec-25 10-Dec-25 | IPC - 25 | P7-KS-S14a-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/484 MPSB/Sur/2405 MPSB/MB/493 | 11-Dec-25 13-Dec-25 13-Dec-25 | IPC - 25 | P7-KS-S15a-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/501 MPSB/Sur/2428 MPSB/MB/514 | 15-Dec-25 17-Dec-25 17-Dec-25 | IPC - 25 | P7-KS-S16a-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/535 MPSB/Sur/2491 MPSB/MB/554 | 22-Dec-25 24-Dec-25 24-Dec-25 | IPC - 25 | P7-KS-S17a-O© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/601 MPSB/Sur/2552 MPSB/MB/604 | 30-Dec-25 30-Dec-25 30-Dec-25 | IPC - 25 | P7-KS-S18a-O | 2025-12-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/530 MPSB/Sur/2477 MPSB/MB/542 | 20-Dec-25 23-Dec-25 23-Dec-25 | IPC - 25 | P8-KS-S08-M© | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/Sur/2516 MPSB/MB/577 | 27-Dec-25 27-Dec-25 | IPC - 25 | P8-KS-S09-M | 2025-12-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/819 MPSB/Sur/2786 MPSB/MB/826 | 27-Jan-26 28-Jan-26 28-Jan-26 | IPC - 26 | P23-KS-S22a-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/881 MPSB/Sur/2838 MPSB/MB/883 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | P23-KS-S23a-O© | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/644 MPSB/Sur/2626 MPSB/MB/676 | 6-Jan-26 8-Jan-26 8-Jan-26 | IPC - 26 | P23-BP-S15-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/688 MPSB/Sur/2661 MPSB/MB/697 | 10-Jan-26 12-Jan-26 12-Jan-26 | IPC - 26 | P23-BP-S16-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/728 MPSB/Sur/2693 MPSB/MB/742 | 14-Jan-26 16-Jan-26 16-Jan-26 | IPC - 26 | P23-BP-S17-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/748 MPSB/Sur/2716 MPSB/MB/753 | 17-Jan-26 19-Jan-26 19-Jan-26 | IPC - 26 | P23-BP-S18-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/791 MPSB/Sur/2764 MPSB/MB/797 | 23-Jan-26 24-Jan-26 24-Jan-26 | IPC - 26 | P23-BP-S19-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/843 MPSB/Sur/2820 MPSB/MB/847 | 30-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | P23-BP-S20-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/610 MPSB/Sur/2594 MPSB/MB/618 | 31-Dec-25 3-Jan-26 3-Jan-26 | IPC - 26 | P25-KS-S26-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/642 MPSB/Sur/2614 MPSB/MB/645 | 5-Jan-26 6-Jan-26 6-Jan-26 | IPC - 26 | P25-KS-S27-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/Sur/2644 MPSB/MB/685 | 9-Jan-26 9-Jan-26 | IPC - 26 | P25-KS-S28-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/696 MPSB/Sur/2680 MPSB/MB/729 | 12-Jan-26 14-Jan-26 14-Jan-26 | IPC - 26 | P25-KS-S29-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/747 MPSB/Sur/2706 MPSB/MB/751 | 17-Jan-26 18-Jan-26 18-Jan-26 | IPC - 26 | P25-KS-S30-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/781 MPSB/Sur/2749 MPSB/MB/792 | 22-Jan-26 23-Jan-26 23-Jan-26 | IPC - 26 | P25-KS-S31-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/842 MPSB/Sur/2821 MPSB/MB/848 | 30-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | P25-KS-S32-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/790 MPSB/Sur/2781 MPSB/MB/818 | 23-Jan-26 27-Jan-26 27-Jan-26 | IPC - 26 | P25-KS-S01-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/767 MPSB/Sur/2741 MPSB/MB/777 | 20-Jan-26 22-Jan-26 22-Jan-26 | IPC - 26 | P25-BP-S22a-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/820 MPSB/Sur/2787 MPSB/MB/827 | 27-Jan-26 28-Jan-26 28-Jan-26 | IPC - 26 | P25-BP-S23a-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/882 MPSB/Sur/2839 MPSB/MB/884 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | P25-BP-S24a-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/Sur/2672 MPSB/MB/712 | 13-Jan-26 13-Jan-26 | IPC - 26 | P6-BP-S01a-E | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/735 MPSB/Sur/2690 MPSB/MB/737 | 15-Jan-26 16-Jan-26 16-Jan-26 | IPC - 26 | P6-BP-S01-E | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/756 MPSB/Sur/2721 MPSB/MB/763 | 19-Jan-26 20-Jan-26 20-Jan-26 | IPC - 26 | P6-BP-S02-E | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/789 MPSB/Sur/2776 MPSB/MB/810 | 23-Jan-26 27-Jan-26 27-Jan-26 | IPC - 26 | P6-BP-S03-E | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/Sur/2815 MPSB/MB/841 | 30-Jan-26 30-Jan-26 | IPC - 26 | P6-BP-S04-E | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/833 MPSB/Sur/2813 MPSB/MB/838 | 29-Jan-26 30-Jan-26 30-Jan-26 | IPC - 26 | P7-KS-S23a-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/806 MPSB/Sur/2777 MPSB/MB/811 | 25-Jan-26 27-Jan-26 27-Jan-26 | IPC - 26 | P7-KS-S22a-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/726 MPSB/Sur/2692 MPSB/MB/739 | 14-Jan-26 16-Jan-26 16-Jan-26 | IPC - 26 | P7-KS-S21a-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/686 MPSB/Sur/2662 MPSB/MB/700 | 10-Jan-26 12-Jan-26 12-Jan-26 | IPC - 26 | P7-KS-S20a-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/630 MPSB/Sur/2615 MPSB/MB/654 | 5-Jan-26 6-Jan-26 6-Jan-26 | IPC - 26 | P7-KS-S19a-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/831 MPSB/Sur/2814 MPSB/MB/839 | 29-Jan-26 30-Jan-26 30-Jan-26 | IPC - 26 | P7-KS-S08a-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/787 MPSB/Sur/2762 MPSB/MB/793 | 23-Jan-26 24-Jan-26 24-Jan-26 | IPC - 26 | P7-KS-S07a-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/755 MPSB/Sur/2722 MPSB/MB/764 | 19-Jan-26 20-Jan-26 20-Jan-26 | IPC - 26 | P7-KS-S06a-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/734 MPSB/Sur/2691 MPSB/MB/738 | 15-Jan-26 16-Jan-26 16-Jan-26 | IPC - 26 | P7-KS-S05a-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/710 MPSB/Sur/2671 MPSB/MB/711 | 13-Jan-26 13-Jan-26 13-Jan-26 | IPC - 26 | P7-KS-S04a-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/665 MPSB/Sur/2665 MPSB/MB/695 | 8-Jan-26 11-Jan-26 11-Jan-26 | IPC - 26 | P7-KS-S03a-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/628 MPSB/Sur/2611 MPSB/MB/636 | 4-Jan-26 5-Jan-26 5-Jan-26 | IPC - 26 | P7-KS-S02a-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/603 MPSB/Sur/2587 MPSB/MB/615 | 30-Dec-26 2-Jan-26 2-Jan-26 | IPC - 26 | P7-KS-S01a-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/602 MPSB/Sur/2586 MPSB/MB/614 | 30-Dec-26 2-Jan-26 2-Jan-26 | IPC - 26 | P7-BP-S28-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/629 MPSB/Sur/2616 MPSB/MB/655 | 5-Jan-26 6-Jan-26 6-Jan-26 | IPC - 26 | P7-BP-S29-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/657 MPSB/Sur/2639 MPSB/MB/678 | 7-Jan-26 9-Jan-26 9-Jan-26 | IPC - 26 | P7-BP-S30-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/689 MPSB/Sur/2679 MPSB/MB/727 | 11-Jan-26 14-Jan-26 14-Jan-26 | IPC - 26 | P7-BP-S31-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/741 MPSB/Sur/2719 MPSB/MB/757 | 16-Jan-26 19-Jan-26 19-Jan-26 | IPC - 26 | P7-BP-S32-O | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/770 MPSB/Sur/2739 MPSB/MB/774 | 21-Jan-26 22-Jan-26 22-Jan-26 | IPC - 26 | P7-BP-S33-O© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/808 MPSB/Sur/2797 MPSB/MB/829 | 25-Jan-26 29-Jan-26 29-Jan-26 | IPC - 26 | P7-BP-S34-O | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/854 MPSB/Sur/2831 MPSB/MB/874 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | P8-KS-S16-M© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/807 MPSB/Sur/2798 MPSB/MB/830 | 25-Jan-26 29-Jan-26 29-Jan-26 | IPC - 26 | P8-KS-S15-M | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/769 MPSB/Sur/2740 MPSB/MB/775 | 21-Jan-26 22-Jan-26 22-Jan-26 | IPC - 26 | P8-KS-S14-M© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/745 MPSB/Sur/2720 MPSB/MB/758 | 17-Jan-26 19-Jan-26 19-Jan-26 | IPC - 26 | P8-KS-S13-M | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/705 MPSB/Sur/2678 MPSB/MB/721 | 12-Jan-26 14-Jan-26 14-Jan-26 | IPC - 26 | P8-KS-S12-M© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/656 MPSB/Sur/2625 MPSB/MB/666 | 7-Jan-26 8-Jan-26 8-Jan-26 | IPC - 26 | P8-KS-S11-M | 2026-01-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/619 MPSB/Sur/2610 MPSB/MB/631 | 3-Jan-26 5-Jan-26 5-Jan-26 | IPC - 26 | P8-KS-S10-M© | 2026-01-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/853 MPSB/Sur/2850 MPSB/MB/892 | 31-Jan-26 3-Feb-26 3-Feb-26 | IPC - 27 | P6-BP-S05-E | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/910 MPSB/Sur/2888 MPSB/MB/937 | 5-Feb-26 8-Feb-26 8-Feb-26 | IPC - 27 | P6-BP-S06-E | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/867 MPSB/Sur/2832 MPSB/MB/875 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 27 | P7-KS-S24a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/931 MPSB/Sur/2896 MPSB/MB/942 | 7-Feb-26 9-Feb-26 9-Feb-26 | IPC - 27 | P7-KS-S25a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/980 MPSB/Sur/2941 MPSB/MB/999 | 13-Feb-26 16-Feb-26 16-Feb-26 | IPC - 27 | P7-KS-S26a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1000 MPSB/Sur/2959 MPSB/MB/1030 | 16-Feb-26 19-Feb-26 19-Feb-26 | IPC - 27 | P7-KS-S27a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/923 MPSB/Sur/2987 MPSB/MB/1073 | 6-Feb-26 24-Feb-26 24-Feb-26 | IPC - 27 | P7-KS-S28a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1082 MPSB/Sur/3011 MPSB/MB/1089 | 25-Feb-26 26-Feb-26 26-Feb-26 | IPC - 27 | P7-KS-S29a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/912 MPSB/Sur/2882 MPSB/MB/932 | 5-Feb-26 7-Feb-26 7-Feb-26 | IPC - 27 | P8-KS-S17-M | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/943 MPSB/Sur/2930 MPSB/MB/989 | 9-Feb-26 14-Feb-26 14-Feb-26 | IPC - 27 | P8-KS-S18-M | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1048 MPSB/Sur/3005 MPSB/MB/1081 | 23-Feb-26 25-Feb-26 25-Feb-26 | IPC - 27 | P8-BP-S08-M© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1095 MPSB/Sur/3023 MPSB/MB/1101 | 26-Feb-26 27-Feb-26 27-Feb-26 | IPC - 27 | P8-BP-S09-M | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/943 MPSB/Sur/2859 MPSB/MB/911 | 9-Feb-26 5-Feb-26 5-Feb-26 | IPC - 27 | P9-KS-S01-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/944 MPSB/Sur/2917 MPSB/MB/964 | 9-Feb-26 11-Feb-26 11-Feb-26 | IPC - 27 | P9-KS-S02-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1003 MPSB/Sur/2946 MPSB/MB/1009 | 17-Feb-26 17-Feb-26 17-Feb-26 | IPC - 27 | P9-KS-S03-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1028 MPSB/Sur/2975 MPSB/MB/1042 | 19-Feb-26 21-Feb-26 21-Feb-26 | IPC - 27 | P9-KS-S04-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1050 MPSB/Sur/3004 MPSB/MB/1080 | 23-Feb-26 25-Feb-26 25-Feb-26 | IPC - 27 | P9-KS-S05-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1091 MPSB/Sur/3013 MPSB/MB/1096 | 26-Feb-26 26-Feb-26 26-Feb-26 | IPC - 27 | P9-KS-S06-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1102 MPSB/Sur/3049 MPSB/MB/1126 | 27-Feb-26 28-Feb-26 28-Feb-26 | IPC - 27 | P9-KS-S07-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/930 MPSB/Sur/2895 MPSB/MB/941 | 7-Feb-26 9-Feb-26 9-Feb-26 | IPC - 27 | P9-BP-S09a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/895 MPSB/Sur/2929 MPSB/MB/988 | 3-Feb-26 14-Feb-26 14-Feb-26 | IPC - 27 | P9-BP-S10a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1002 MPSB/Sur/2945 MPSB/MB/1008 | 17-Feb-26 17-Feb-26 17-Feb-26 | IPC - 27 | P9-BP-S11a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1019 MPSB/Sur/2958 MPSB/MB/1029 | 18-Feb-26 19-Feb-26 19-Feb-26 | IPC - 27 | P9-BP-S12a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1049 MPSB/Sur/2986 MPSB/MB/1072 | 23-Feb-26 24-Feb-26 24-Feb-26 | IPC - 27 | P9-BP-S13a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1083 MPSB/Sur/3012 MPSB/MB/1092 | 25-Feb-26 26-Feb-26 26-Feb-26 | IPC - 27 | P9-BP-S14a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1093 MPSB/Sur/3047 MPSB/MB/1124 | 26-Feb-26 28-Feb-26 28-Feb-26 | IPC - 27 | P9-BP-S15a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1094 MPSB/Sur/3024 MPSB/MB/1125 | 26-Feb-26 27-Feb-26 28-Feb-26 | IPC - 27 | P10-KS-S01a-E | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/928 MPSB/Sur/2885 MPSB/MB/936 | 6-Feb-26 7-Feb-26 7-Feb-26 | IPC - 27 | P23-KS-S24a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/956 MPSB/Sur/2916 MPSB/MB/962 | 10-Feb-26 11-Feb-26 11-Feb-26 | IPC - 27 | P23-KS-S25a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/984 MPSB/Sur/2933 MPSB/MB/995 | 13-Feb-26 14-Feb-26 14-Feb-26 | IPC - 27 | P23-KS-S26a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1013 MPSB/Sur/2950 MPSB/MB/1012 | 17-Feb-26 17-Feb-26 17-Feb-26 | IPC - 27 | P23-KS-S27a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1023 MPSB/Sur/2968 MPSB/MB/1037 | 18-Feb-26 20-Feb-26 20-Feb-26 | IPC - 27 | P23-KS-S28a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1023 MPSB/Sur/2985 MPSB/MB/1064 | 18-Feb-26 24-Feb-26 24-Feb-26 | IPC - 27 | P23-KS-S29a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1066 MPSB/Sur/3026 MPSB/MB/1108 | 24-Feb-26 27-Feb-26 27-Feb-26 | IPC - 27 | P23-KS-S30a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1099 MPSB/Sur/3030 MPSB/MB/1114 | 26-Feb-26 28-Feb-26 28-Feb-26 | IPC - 27 | P23-KS-S31a-O© | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/927 MPSB/Sur/2897 MPSB/MB/948 | 6-Feb-26 9-Feb-26 9-Feb-26 | IPC - 27 | P23-BP-S21-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1061 MPSB/Sur/3002 MPSB/MB/1075 | 23-Feb-26 25-Feb-26 25-Feb-26 | IPC - 27 | P23-BP-S22-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1040 MPSB/Sur/3025 MPSB/MB/1107 | 20-Feb-26 27-Feb-26 27-Feb-26 | IPC - 27 | P23-BP-S23-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1113 MPSB/Sur/3029 MPSB/MB/1112 | 28-Feb-26 28-Feb-26 28-Feb-26 | IPC - 27 | P23-BP-S24-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/940 MPSB/Sur/2898 MPSB/MB/949 | 8-Feb-26 9-Feb-26 9-Feb-26 | IPC - 27 | P25-KS-S33-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/970 MPSB/Sur/2925 MPSB/MB/987 | 12-Feb-26 13-Feb-26 13-Feb-26 | IPC - 27 | P25-KS-S34-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/888 MPSB/Sur/2849 MPSB/MB/891 | 2-Feb-26 3-Feb-26 3-Feb-26 | IPC - 27 | P25-KS-S02-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/939 MPSB/Sur/2903 MPSB/MB/958 | 8-Feb-26 10-Feb-26 10-Feb-26 | IPC - 27 | P25-KS-S03-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/983 MPSB/Sur/2932 MPSB/MB/994 | 13-Feb-26 14-Feb-26 14-Feb-26 | IPC - 27 | P25-KS-S04-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1014 MPSB/Sur/2953 MPSB/MB/1021 | 17-Feb-26 18-Feb-26 18-Feb-26 | IPC - 27 | P25-KS-S05-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1045 MPSB/Sur/2979 MPSB/MB/1058 | 21-Feb-26 23-Feb-26 23-Feb-26 | IPC - 27 | P25-KS-S06-O | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1100 MPSB/Sur/3031 MPSB/MB/1115 | 26-Feb-26 28-Feb-26 28-Feb-26 | IPC - 27 | P25-KS-S07-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/957 MPSB/Sur/2915 MPSB/MB/961 | 10-Feb-26 11-Feb-26 11-Feb-26 | IPC - 27 | P25-BP-S25a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/982 MPSB/Sur/2937 MPSB/MB/998 | 13-Feb-26 15-Feb-26 15-Feb-26 | IPC - 27 | P25-BP-S26a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1015 MPSB/Sur/2954 MPSB/MB/1022 | 17-Feb-26 18-Feb-26 18-Feb-26 | IPC - 27 | P25-BP-S27a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1024 MPSB/Sur/2969 MPSB/MB/1038 | 18-Feb-26 20-Feb-26 20-Feb-26 | IPC - 27 | P25-BP-S28a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1039 MPSB/Sur/2980 MPSB/MB/1059 | 20-Feb-26 23-Feb-26 23-Feb-26 | IPC - 27 | P25-BP-S29a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1065 MPSB/Sur/3014 MPSB/MB/1097 | 24-Feb-26 26-Feb-26 26-Feb-26 | IPC - 27 | P25-BP-S30a-O | 2026-02-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1119 MPSB/Sur/3033 MPSB/MB/1120 | 28-Feb-26 28-Feb-26 28-Feb-26 | IPC - 27 | P25-BP-S31a-O© | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1060 MPSB/Sur/3003 MPSB/MB/1076 | 23-Feb-26 25-Feb-26 25-Feb-26 | IPC - 27 | P26-KS-S01a-E | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1109 MPSB/Sur/3032 MPSB/MB/1116 | 27-Feb-26 28-Feb-26 28-Feb-26 | IPC - 27 | P26-KS-S01-E | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1121 MPSB/Sur/3034 MPSB/MB/1122 | 28-Feb-26 28-Feb-26 28-Feb-26 | IPC - 27 | P26-KS-S02-E | 2026-02-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1090 MPSB/Sur/3065 MPSB/MB/1161 | 26-Feb-26 6-Mar-26 6-Mar-26 | IPC - 29 | P7-KS-S30a-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1200 MPSB/Sur/3085 MPSB/MB/1206 | 9-Mar-26 10-Mar-26 10-Mar-26 | IPC - 29 | P7-KS-S31a-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1244 MPSB/Sur/3122 MPSB/Str/4118 | 12-Mar-26 14-Mar-26 14-Mar-26 | IPC - 29 | P7-KS-S32a-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1298 MPSB/Sur/3144 MPSB/MB/1303 | 18-Mar-26 19-Mar-26 19-Mar-26 | IPC - 29 | P7-KS-S33a-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1344 MPSB/Sur/3177 MPSB/MB/1362 | 24-Mar-26 26-Mar-26 26-Mar-26 | IPC - 29 | P7-KS-S34a-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1160 MPSB/Sur/3072 MPSB/MB/1176 | 6-Mar-26 7-Mar-26 7-Mar-26 | IPC - 29 | P8-BP-S10-M© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1231 MPSB/Sur/3107 MPSB/MB/1247 | 11-Mar-26 12-Mar-26 12-Mar-26 | IPC - 29 | P8-BP-S11-M | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1278 MPSB/Sur/3139 MPSB/MB/1288 | 16-Mar-26 17-Mar-26 17-Mar-26 | IPC - 29 | P8-BP-S12-M© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1335 MPSB/Sur/3165 MPSB/MB/1341 | 23-Mar-26 24-Mar-26 24-Mar-26 | IPC - 29 | P8-BP-S13-M | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1370 MPSB/Sur/3192 MPSB/MB/1389 | 27-Mar-26 29-Mar-26 29-Mar-26 | IPC - 29 | P8-BP-S14-M© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1399 MPSB/Sur/3229 MPSB/MB/1419 | 31-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P8-BP-S15-M | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1265 MPSB/Sur/3134 MPSB/MB/1275 | 14-Mar-26 17-Mar-26 16-Mar-26 | IPC - 29 | P8-KS-S01-M | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1345 MPSB/Sur/3175 MPSB/MB/1358 | 24-Mar-26 26-Mar-26 26-Mar-26 | IPC - 29 | P8-KS-S02-M | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1388 MPSB/Sur/3211 MPSB/MB/1401 | 29-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P8-KS-S03-M | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1158 MPSB/Sur/3066 MPSB/MB/1162 | 6-Mar-26 6-Mar-26 7-Mar-26 | IPC - 29 | P9-KS-S08-O | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1177 MPSB/Sur/3077 MPSB/MB/1191 | 7-Mar-26 8-Mar-26 8-Mar-26 | IPC - 29 | P9-BP-S16a-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1190 MPSB/Sur/3100 MPSB/MB/1232 | 9-Mar-26 11-Mar-26 11-Mar-26 | IPC - 29 | P9-BP-S17a-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1257 MPSB/Sur/3062 MPSB/str/4107 | 13-Mar-26 14-Mar-26 14-Mar-26 | IPC - 29 | P9-BP-S18a-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1302 MPSB/Sur/3153 MPSB/MB/1311 | 19-Mar-26 20-Mar-26 20-Mar-26 | IPC - 29 | P9-BP-S19a-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1343 MPSB/Sur/3176 MPSB/MB/1360 | 24-Mar-26 26-Mar-26 26-Mar-26 | IPC - 29 | P9-BP-S20a-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1387 MPSB/Sur/3210 MPSB/MB/1398 | 29-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P9-BP-S21a-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1159 MPSB/Sur/3067 MPSB/MB/1163 | 6-Mar-26 6-Mar-26 6-Mar-26 | IPC - 29 | P10-KS-S01-E | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1230 MPSB/Sur/3106 MPSB/MB/1246 | 11-Mar-26 12-Mar-26 12-Mar-26 | IPC - 29 | P10-KS-S02-E | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1277 MPSB/Sur/3140 MPSB/MB/1289 | 16-Mar-26 17-Mar-26 17-Mar-26 | IPC - 29 | P10-KS-S03-E | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1336 MPSB/Sur/3166 MPSB/MB/1342 | 23-Mar-26 24-Mar-26 24-Mar-26 | IPC - 29 | P10-KS-S04-E | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1361 MPSB/Sur/3183 MPSB/MB/1377 | 26-Mar-26 28-Mar-26 28-Mar-26 | IPC - 29 | P10-KS-S05-E | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1400 MPSB/Sur/3227 MPSB/MB/1417 | 31-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P10-KS-S06-E | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1352 MPSB/Sur/3179 MPSB/MB/1363 | 24-Mar-26 26-Mar-26 26-Mar-26 | IPC - 29 | P21-KS-S09-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1382 MPSB/Sur/3217 MPSB/MB/1407 | 28-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P21-KS-S10-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1413 MPSB/Sur/3225 MPSB/MB/1414 | 31-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P21-KS-S11-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1145 MPSB/Sur/3061 MPSB/MB/1147 | 5-Mar-26 5-Mar-26 5-Mar-26 | IPC - 29 | P23-KS-S32a-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1210 MPSB/Sur/3104 MPSB/MB/1241 | 10-Mar-26 12-Mar-26 12-Mar-26 | IPC - 29 | P23-KS-S33a-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1322 MPSB/Sur/3127 MPSB/MB/1269 | 16-Mar-26 16-Mar-26 16-Mar-26 | IPC - 29 | P23-KS-S34a-O | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1233 MPSB/Sur/3101 MPSB/MB/1235 | 11-Mar-26 11-Mar-26 11-Mar-26 | IPC - 29 | P23-KS-S01a-O | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1262 MPSB/Sur/3128 MPSB/MB/1270 | 13-Mar-26 16-Mar-26 16-Mar-26 | IPC - 29 | P23-KS-S02a-O | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1299 MPSB/Sur/3157 MPSB/MB/1330 | 18-Mar-26 21-Mar-26 21-Mar-26 | IPC - 29 | P23-KS-S03a-O | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1338 MPSB/Sur/3167 MPSB/MB/1350 | 23-Mar-26 24-Mar-26 24-Mar-26 | IPC - 29 | P23-KS-S04a-O | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1372 MPSB/Sur/3186 MPSB/MB/1379 | 27-Mar-26 28-Mar-26 28-Mar-26 | IPC - 29 | P23-KS-S05a-O | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1402 MPSB/Sur/3222 MPSB/MB/1410 | 31-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P23-KS-S06a-O | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1409 MPSB/Sur/3224 MPSB/MB/1412 | 31-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P23-KS-S07a-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1171 MPSB/Sur/3073 MPSB/MB/1183 | 6-Mar-26 7-Mar-26 7-Mar-26 | IPC - 29 | P23-BP-S25-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1209 MPSB/Sur/3088 MPSB/MB/1211 | 10-Mar-26 10-Mar-26 10-Mar-26 | IPC - 29 | P23-BP-S26-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1240 MPSB/Sur/3121 MPSB/MB/1267 | 12-Mar-26 14-Mar-26 14-Mar-26 | IPC - 29 | P23-BP-S27-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1268 MPSB/Sur/3137 MPSB/MB/1283 | 16-Mar-26 17-Mar-26 17-Mar-26 | IPC - 29 | P23-BP-S28-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1329 MPSB/Sur/3161 MPSB/MB/1340 | 21-Mar-26 23-Mar-26 23-Mar-26 | IPC - 29 | P23-BP-S29-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1334 MPSB/Sur/3174 MPSB/MB/1357 | 21-Mar-26 25-Mar-26 25-Mar-26 | IPC - 29 | P23-BP-S30-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1374 MPSB/Sur/3205 MPSB/MB/1394 | 27-Mar-26 30-Mar-26 30-Mar-26 | IPC - 29 | P23-BP-S31-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1404 MPSB/Sur/3223 MPSB/MB/1411 | 31-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P23-BP-S32-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1381 MPSB/Sur/3218 MPSB/MB/1408 | 28-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P24-BP-S08-M© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1146 MPSB/Sur/3062 MPSB/MB/1148 | 5-Mar-26 5-Mar-26 5-Mar-26 | IPC - 29 | P25-BP-S32a-O | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1182 MPSB/Sur/3078 MPSB/MB/1195 | 7-Mar-26 8-Mar-26 8-Mar-26 | IPC - 29 | P25-BP-S33a-O© | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1234 MPSB/Sur/3103 MPSB/MB/1239 | 11-Mar-26 12-Mar-26 12-Mar-26 | IPC - 29 | P25-BP-S34a-O | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1181 MPSB/Sur/3079 MPSB/MB/1196 | 7-Mar-26 8-Mar-26 8-Mar-26 | IPC - 29 | P26-KS-S03-E | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1258 MPSB/Sur/3113 MPSB/MB/1259 | 13-Mar-26 13-Mar-26 13-Mar-26 | IPC - 29 | P26-KS-S04-E | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/Sur/3138 MPSB/MB/1284 | 17-Mar-26 17-Mar-26 | IPC - 29 | P26-KS-S05-E | 2026-03-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1300 MPSB/Sur/3158 MPSB/MB/1331 | 18-Mar-26 21-Mar-26 21-Mar-26 | IPC - 29 | P26-KS-S06-E | 2026-03-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1422 MPSB/Sur/3253 MPSB/MB/1449 | 31-Mar-26 6-Apr-26 6-Apr-26 | IPC - 30 | P8-BP-S16-M© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1452 MPSB/Sur/3290 MPSB/MB/1517 | 7-Apr-26 13-Apr-26 13-Apr-26 | IPC - 30 | P8-BP-S17-M | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1532 MPSB/Sur/3312 MPSB/MB/1556 | 14-Apr-26 17-Apr-26 17-Apr-26 | IPC - 30 | P8-BP-S18-M | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1622 MPSB/Sur/3349 MPSB/MB/1639 | 24-Apr-26 25-Apr-26 25-Apr-26 | IPC - 30 | P8-BP-S01-M | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1651 MPSB/Sur/3385 MPSB/MB/1665 | 27-Apr-26 29-Apr-26 29-Apr-26 | IPC - 30 | P8-BP-S02-M | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1421 MPSB/Sur/3254 MPSB/MB/1450 | 31-Mar-26 6-Apr-26 6-Apr-26 | IPC - 30 | P8-KS-S04-M | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1473 MPSB/Sur/3280 MPSB/MB/1510 | 10-Apr-26 12-Apr-26 12-Apr-26 | IPC - 30 | P8-KS-S05-M | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1525 MPSB/Sur/3298 MPSB/MB/1544 | 14-Apr-26 14-Apr-26 16-Apr-26 | IPC - 30 | P8-KS-S06-M | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1569 MPSB/Sur/3325 MPSB/MB/1570 | 18-Apr-26 18-Apr-26 18-Apr-26 | IPC - 30 | P8-KS-S07-M | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1474 MPSB/Sur/3272 MPSB/MB/1490 | 10-Apr-26 10-Apr-26 10-Apr-26 | IPC - 30 | P9-KS-S09-O© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1531 MPSB/Sur/3306 MPSB/MB/1534 | 14-Apr-26 15-Apr-26 15-Apr-26 | IPC - 30 | P9-KS-S10-O | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1558 MPSB/Sur/3326 MPSB/MB/1573 | 17-Apr-26 18-Apr-26 18-Apr-26 | IPC - 30 | P9-KS-S11-O© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1605 MPSB/Sur/3335 MPSB/MB/1606 | 21-Apr-26 21-Apr-26 21-Apr-26 | IPC - 30 | P9-KS-S12-O | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1619 MPSB/Sur/3345 MPSB/MB/1621 | 23-Apr-26 24-Apr-26 24-Apr-26 | IPC - 30 | P9-KS-S13-O© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1636 MPSB/Sur/3365 MPSB/MB/1652 | 25-Apr-26 27-Apr-26 27-Apr-26 | IPC - 30 | P9-KS-S14-O | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1668 MPSB/Sur/3401 MPSB/MB/1680 | 29-Apr-26 30-Apr-26 30-Apr-26 | IPC - 30 | P9-KS-S15-O© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1637 MPSB/Sur/3386 MPSB/MB/1667 | 25-Apr-26 29-Apr-26 29-Apr-26 | IPC - 30 | P9-KS-S22-O | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1451 MPSB/Sur/3256 MPSB/MB/1453 | 7-Apr-26 7-Apr-26 7-Apr-26 | IPC - 30 | P9-BP-S22a-O | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1471 MPSB/Sur/3275 MPSB/MB/1493 | 8-Apr-26 11-Apr-26 11-Apr-26 | IPC - 30 | P9-BP-S23a-O© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1516 MPSB/Sur/3297 MPSB/MB/1524 | 13-Apr-26 14-Apr-26 14-Apr-26 | IPC - 30 | P9-BP-S24a-O | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1545 MPSB/Sur/3313 MPSB/MB/1557 | 16-Apr-26 17-Apr-26 17-Apr-26 | IPC - 30 | P9-BP-S25a-O© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1578 MPSB/Sur/3330 MPSB/MB/1585 | 19-Apr-26 20-Apr-26 20-Apr-26 | IPC - 30 | P9-BP-S26a-O | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1607 MPSB/Sur/3343 MPSB/MB/1618 | 21-Apr-26 23-Apr-26 23-Apr-26 | IPC - 30 | P9-BP-S27a-O© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1638 MPSB/Sur/3366 MPSB/MB/1653 | 25-Apr-26 27-Apr-26 27-Apr-26 | IPC - 30 | P9-BP-S28a-O | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1641 MPSB/Sur/3377 MPSB/MB/1646 | 25-Apr-26 28-Apr-26 27-Apr-26 | IPC - 30 | P21-BP-S09a-O© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1673 MPSB/Sur/3392 MPSB/MB/1676 | 30-Apr-26 30-Apr-26 30-Apr-26 | IPC - 30 | P21-BP-S10a-O | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1444 MPSB/Sur/3248 MPSB/MB/1445 | 6-Apr-26 6-Apr-26 6-Apr-26 | IPC - 30 | P21-KS-S12-O | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1465 MPSB/Sur/3268 MPSB/MB/1487 | 7-Apr-26 10-Apr-26 10-Apr-26 | IPC - 30 | P21-KS-S13-O© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1491 MPSB/Sur/3288 MPSB/MB/1511 | 10-Apr-26 13-Apr-26 13-Apr-26 | IPC - 30 | P21-KS-S14-O | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1443 MPSB/Sur/3257 MPSB/MB/1467 | 6-Apr-26 7-Apr-26 7-Apr-26 | IPC - 30 | P23-KS-S08a-O | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1488 MPSB/Sur/3277 MPSB/MB/1500 | 10-Apr-26 11-Apr-26 11-Apr-26 | IPC - 30 | P23-BP-S34-O | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/Sur/3258 MPSB/MB/1472 | 8-Apr-26 8-Apr-26 | IPC - 30 | P23-BP-S33-O© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1672 MPSB/Sur/3391 MPSB/MB/1675 | 30-Apr-26 30-Apr-26 30-Apr-26 | IPC - 30 | P24-BP-S17-M | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1664 MPSB/Sur/3390 MPSB/MB/1674 | 29-Apr-26 30-Apr-26 30-Apr-26 | IPC - 30 | P24-BP-S16-M© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1631 MPSB/Sur/3364 MPSB/MB/1645 | 24-Apr-26 27-Apr-26 27-Apr-26 | IPC - 30 | P24-BP-S15-M | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1593 MPSB/Sur/3346 MPSB/MB/1630 | 20-Apr-26 24-Apr-26 24-Apr-26 | IPC - 30 | P24-BP-S14-M© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1560 MPSB/Sur/3332 MPSB/MB/1594 | 17-Apr-26 20-Apr-26 20-Apr-26 | IPC - 30 | P24-BP-S13-M | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1536 MPSB/Sur/3314 MPSB/MB/1561 | 15-Apr-26 17-Apr-26 17-Apr-26 | IPC - 30 | P24-BP-S12-M© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1498 MPSB/Sur/3289 MPSB/MB/1513 | 11-Apr-26 13-Apr-26 13-Apr-26 | IPC - 30 | P24-BP-S11-M | 2026-04-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1485 MPSB/Sur/3267 MPSB/MB/1486 | 10-Apr-26 10-Apr-26 10-Apr-26 | IPC - 30 | P24-BP-S10-M© | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1416 MPSB/Sur/3249 MPSB/MB/1446 | 31-Mar-26 6-Apr-26 6-Apr-26 | IPC - 30 | P24-BP-S09-M | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1497 MPSB/Sur/3315 MPSB/MB/1566 | 11-Apr-26 17-Apr-26 17-Apr-26 | IPC - 30 | P25-BP-S01a-O | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1596 MPSB/Sur/3384 MPSB/MB/1663 | 20-Apr-26 29-Apr-26 29-Apr-26 | IPC - 30 | P25-BP-S02a-O | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1666 MPSB/Sur/3389 MPSB/MB/1671 | 29-Apr-26 30-Apr-26 30-Apr-26 | IPC - 30 | P25-BP-S03a-O | 2026-04-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1686 MPSB/Sur/3417 MPSB/MB/1701 | 2-May-26 5-May-26 5-May-26 | IPC - 31 | P9-KS-S16-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1721 MPSB/Sur/3459 MPSB/MB/1743 | 8-May-26 11-May-26 11-May-26 | IPC - 31 | P9-KS-S17-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1758 MPSB/Sur/3487 MPSB/MB/1776 | 14-May-26 16-May-26 16-May-26 | IPC - 31 | P9-KS-S18-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1807 MPSB/Sur/3525 MPSB/MB/1817 | 20-May-26 21-May-26 21-May-26 | IPC - 31 | P9-KS-S19-O© | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1698 MPSB/Sur/3425 MPSB/MB/1712 | 5-May-26 7-May-26 7-May-26 | IPC - 31 | P9-KS-S23-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1741 MPSB/Sur/3467 MPSB/MB/1748 | 11-May-26 12-May-26 12-May-26 | IPC - 31 | P9-KS-S24-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1784 MPSB/Sur/3505 MPSB/MB/1795 | 17-May-26 18-May-26 18-May-26 | IPC - 31 | P9-KS-S25-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1836 MPSB/Sur/3553 MPSB/MB/1852 | 23-May-26 26-May-26 26-May-26 | IPC - 31 | P9-KS-S26-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1681 MPSB/Sur/3412 MPSB/MB/1691 | 30-Apr-26 4-May-26 4-May-26 | IPC - 31 | P9-BP-S29a-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1720 MPSB/Sur/3442 MPSB/MB/1729 | 8-May-26 9-May-26 9-May-26 | IPC - 31 | P9-BP-S30a-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1753 MPSB/Sur/3493 MPSB/MB/1783 | 13-May-26 16-May-26 16-May-26 | IPC - 31 | P9-BP-S31a-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1808 MPSB/Sur/3531 MPSB/MB/1824 | 20-May-26 22-May-26 22-May-26 | IPC - 31 | P9-BP-S32a-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1843 MPSB/Sur/3592 MPSB/MB/1888 | 25-May-26 31-May-26 31-May-26 | IPC - 31 | P9-BP-S33a-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1687 MPSB/Sur/3414 MPSB/MB/1696 | 2-May-26 4-May-26 4-May-26 | IPC - 31 | P8-BP-S03-M | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1700 MPSB/Sur/3426 MPSB/MB/1713 | 5-May-26 7-May-26 7-May-26 | IPC - 31 | P8-BP-S04-M | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1742 MPSB/Sur/3473 MPSB/MB/1752 | 11-May-26 13-May-26 13-May-26 | IPC - 31 | P8-BP-S05-M | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1785 MPSB/Sur/3518 MPSB/MB/1806 | 17-May-26 20-May-26 20-May-26 | IPC - 31 | P8-BP-S06-M | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1825 MPSB/Sur/3539 MPSB/MB/1837 | 22-May-26 23-May-26 23-May-26 | IPC - 31 | P8-BP-S07-M | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1685 MPSB/MB/1690 | 2-May-26 4-May-26 | IPC - 31 | P16-BP-S08-M© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1709 MPSB/Sur/3424 MPSB/MB/1711 | 6-May-26 7-May-26 7-May-26 | IPC - 31 | P16-BP-S09-M | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1744 MPSB/Sur/3472 MPSB/MB/1751 | 11-May-26 13-May-26 13-May-26 | IPC - 31 | P16-BP-S10-M© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1768 MPSB/Sur/3517 MPSB/MB/1805 | 15-May-26 20-May-26 20-May-26 | IPC - 31 | P16-BP-S11-M | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1835 MPSB/Sur/3548 MPSB/MB/1844 | 23-May-26 25-May-26 25-May-26 | IPC - 31 | P16-BP-S12-M© | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1706 MPSB/Sur/3427 MPSB/MB/1716 | 5-May-26 7-May-26 7-May-26 | IPC - 31 | P21-KS-S15-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1735 MPSB/Sur/3427 MPSB/MB/1747 | 9-May-26 12-May-26 12-May-26 | IPC - 31 | P21-KS-S16-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1761 MPSB/Sur/3488 MPSB/MB/1777 | 14-May-26 16-May-26 16-May-26 | IPC - 31 | P21-KS-S17-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1787 MPSB/Sur/3509 MPSB/MB/1802 | 18-May-26 19-May-26 19-May-26 | IPC - 31 | P21-KS-S18-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1827 MPSB/Sur/3562 MPSB/MB/1863 | 22-May-26 27-May-26 27-May-26 | IPC - 31 | P21-KS-S19-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1874 MPSB/Sur/3579 MPSB/MB/1880 | 29-May-26 30-May-26 30-May-26 | IPC - 31 | P21-KS-S20-O | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1880 MPSB/Sur/3534 MPSB/MB/1832 | 19-May-26 22-May-26 22-May-26 | IPC - 31 | P21-KS-S22-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1856 MPSB/Sur/3554 MPSB/MB/1857 | 26-May-26 26-May-26 26-May-26 | IPC - 31 | P21-KS-S23-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1862 MPSB/Sur/3569 MPSB/MB/1868 | 27-May-26 29-May-26 29-May-26 | IPC - 31 | P21-KS-S24-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1881 MPSB/Sur/3581 MPSB/MB/1883 | 30-May-26 30-May-26 30-May-26 | IPC - 31 | P21-KS-S25-O© | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1718 MPSB/Sur/3457 MPSB/MB/1737 | 7-May-26 11-May-26 11-May-26 | IPC - 31 | P21-BP-S11a-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1738 MPSB/MB/1762 | 11-May-26 14-May-26 | IPC - 31 | P21-BP-S12a-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1763 MPSB/Sur/3489 MPSB/MB/1778 | 14-May-26 16-May-26 16-May-26 | IPC - 31 | P21-BP-S13a-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1813 MPSB/Sur/3522 MPSB/MB/1814 | 20-May-26 20-May-26 20-May-26 | IPC - 31 | P21-BP-S14a-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1821 MPSB/Sur/3535 MPSB/MB/1833 | 21-May-26 22-May-26 22-May-26 | IPC - 31 | P21-BP-S15a-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1845 MPSB/Sur/3555 MPSB/MB/1860 | 25-May-26 26-May-26 26-May-26 | IPC - 31 | P21-BP-S16a-O | 2026-05-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1872 MPSB/Sur/3571 MPSB/MB/1873 | 29-May-26 29-May-26 29-May-26 | IPC - 31 | P21-BP-S17a-O© | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1865 MPSB/Sur/3570 MPSB/MB/1871 | 28-May-26 29-May-26 29-May-26 | IPC - 31 | P23-BP-S01-O | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1875 MPSB/Sur/3577 MPSB/MB/1877 | 29-May-26 30-May-26 30-May-26 | IPC - 31 | P23-BP-S02-O | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1727 MPSB/Sur/3446 MPSB/MB/1734 | 8-May-26 9-May-26 9-May-26 | IPC - 31 | P24-BP-S18-M | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1728 MPSB/Sur/3458 MPSB/MB/1740 | 8-May-26 11-May-26 11-May-26 | IPC - 31 | P25-BP-S05a-O | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1756 MPSB/Sur/3482 MPSB/MB/1773 | 13-May-26 15-May-26 15-May-26 | IPC - 31 | P25-BP-S06a-O | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1782 MPSB/Sur/3508 MPSB/MB/1801 | 16-May-26 19-May-26 19-May-26 | IPC - 31 | P25-BP-S07a-O | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1822 MPSB/Sur/3533 MPSB/MB/1831 | 21-May-26 22-May-26 22-May-26 | IPC - 31 | P25-BP-S08a-O | 2026-05-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2002 MPSB/Sur/3686 MPSB/MB/2022 | 22-Jun-26 24-Jun-26 24-Jun-26 | IPC - 33 | P9-BP-S01a-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2035 MPSB/Sur/3698 MPSB/MB/2046 | 26-Jun-26 28-Jun-26 28-Jun-26 | IPC - 33 | P9-BP-S02a-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2044 MPSB/Sur/3707 MPSB/MB/2056 | 27-Jun-26 30-Jun-26 30-Jun-26 | IPC - 33 | P9-BP-S03a-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1920 MPSB/Sur/3626 MPSB/MB/1942 | 6-Jun-26 10-Jun-26 10-Jun-26 | IPC - 33 | P9-BP-S34a-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/Sur/1842 MPSB/Sur/3619 MPSB/MB/1935 | 25-May-26 8-Jun-26 8-Jun-26 | IPC - 33 | P9-KS-S20-O | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1854 MPSB/Sur/3638 MPSB/MB/1957 | 26-May-26 11-Jun-26 11-Jun-26 | IPC - 33 | P9-KS-S21-O© | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1908 MPSB/Sur/3610 MPSB/MB/1910 | 4-Jun-26 5-Jun-26 5-Jun-26 | IPC - 33 | P9-KS-S27-O© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1943 MPSB/Sur/3645 MPSB/MB/1961 | 10-Jun-26 12-Jun-26 12-Jun-26 | IPC - 33 | P9-KS-S28-O | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1969 MPSB/Sur/3661 MPSB/MB/1984 | 15-Jun-26 17-Jun-26 17-Jun-26 | IPC - 33 | P9-KS-S29-O© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1989 MPSB/Sur/3678 MPSB/MB/2004 | 18-Jun-26 22-Jun-26 22-Jun-26 | IPC - 33 | P9-KS-S30-O | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2019 MPSB/Sur/3702 MPSB/MB/2053 | 24-Jun-26 29-Jun-26 29-Jun-26 | IPC - 33 | P9-KS-S31-O© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1967 MPSB/Sur/3657 MPSB/MB/1978 | 14-Jun-26 16-Jun-26 16-Jun-26 | IPC - 33 | P16-BP-S13-M | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1998 MPSB/Sur/3677 MPSB/MB/2003 | 19-Jun-26 22-Jun-26 22-Jun-26 | IPC - 33 | P16-BP-S14-M© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2024 MPSB/Sur/3695 MPSB/MB/2033 | 24-Jun-26 26-Jun-26 26-Jun-26 | IPC - 33 | P16-BP-S15-M | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2047 MPSB/Sur/3705 MPSB/MB/2054 | 28-Jun-26 30-Jun-26 30-Jun-26 | IPC - 33 | P16-BP-S16-M© | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2034 MPSB/Sur/3701 MPSB/MB/2052 | 26-Jun-26 29-Jun-26 29-Jun-26 | IPC - 33 | P16-KS-S08-M© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1878 MPSB/Sur/3578 MPSB/MB/1941 | 30-May-26 30-May-26 9-Jun-26 | IPC - 33 | P21-BP-S18a-O | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1982 MPSB/Sur/3665 MPSB/MB/1986 | 17-Jun-26 18-Jun-26 18-Jun-26 | IPC - 33 | P21-BP-S19a-O© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2051 MPSB/Sur/3715 MPSB/MB/2060 | 29-Jun-26 30-Jun-26 30-Jun-26 | IPC - 33 | P21-BP-S20a-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1876 MPSB/Sur/3615 MPSB/MB/1925 | 29-May-26 6-Jun-26 6-Jun-26 | IPC - 33 | P21-BP-S22a-O | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1952 MPSB/Sur/3650 MPSB/MB/1964 | 11-Jun-26 13-Jun-26 13-Jun-26 | IPC - 33 | P21-BP-S23a-O© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2001 MPSB/Sur/3679 MPSB/MB/2007 | 21-Jun-26 22-Jun-26 22-Jun-26 | IPC - 33 | P21-BP-S24a-O | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1916 MPSB/Sur/3611 MPSB/MB/1917 | 5-Jun-26 5-Jun-26 5-Jun-26 | IPC - 33 | P21-KS-S21-O© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1919 MPSB/Sur/3616 MPSB/MB/1926 | 5-Jun-26 6-Jun-26 6-Jun-26 | IPC - 33 | P21-KS-S26-O | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1933 MPSB/Sur/3627 MPSB/MB/1947 | 8-Jun-26 10-Jun-26 10-Jun-26 | IPC - 33 | P21-KS-S27-O© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1948 MPSB/Sur/3656 MPSB/MB/1972 | 10-Jun-26 15-Jun-26 15-Jun-26 | IPC - 33 | P21-KS-S28-O | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1966 MPSB/Sur/3659 MPSB/MB/1983 | 13-Jun-26 17-Jun-26 17-Jun-26 | IPC - 33 | P21-KS-S29-O© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1988 MPSB/Sur/3688 MPSB/MB/2025 | 18-Jun-26 24-Jun-26 24-Jun-26 | IPC - 33 | P21-KS-S30-O | 2026-06-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2010 MPSB/MB/2048 MPSB/MB/2049 | 22-Jun-26 29-Jun-26 29-Jun-26 | IPC - 33 | P21-KS-S31-O© | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2063 MPSB/Sur/3718 MPSB/MB/2065 | 30-Jun-26 30-Jun-26 30-Jun-26 | IPC - 33 | P21-KS-S32-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1993 MPSB/Sur/3669 MPSB/MB/1994 | 19-Jun-26 19-Jun-26 19-Jun-26 | IPC - 33 | P22-BP-S01a-E | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2012 MPSB/Sur/3683 MPSB/MB/2013 | 23-Jun-26 23-Jun-26 23-Jun-26 | IPC - 33 | P22-BP-S01-E | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2026 MPSB/Sur/3696 MPSB/MB/2036 | 24-Jun-26 26-Jun-26 26-Jun-26 | IPC - 33 | P22-BP-S02-E | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2041 MPSB/Sur/3716 MPSB/MB/2061 | 27-Jun-26 30-Jun-26 30-Jun-26 | IPC - 33 | P22-BP-S03-E | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/Sur/3617 MPSB/MB/1930 | 8-Jun-26 8-Jun-26 | IPC - 33 | P23-BP-S03-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1940 MPSB/Sur/3636 MPSB/MB/1951 | 9-Jun-26 11-Jun-26 11-Jun-26 | IPC - 33 | P23-BP-S04-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1963 MPSB/Sur/3655 MPSB/MB/1971 | 13-Jun-26 15-Jun-26 15-Jun-26 | IPC - 33 | P23-BP-S05-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1981 MPSB/Sur/3670 MPSB/MB/1996 | 17-Jun-26 19-Jun-26 19-Jun-26 | IPC - 33 | P23-BP-S06-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2005 MPSB/Sur/3684 MPSB/MB/2015 | 20-Jun-26 23-Jun-26 23-Jun-26 | IPC - 33 | P23-BP-S07-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2016 MPSB/MB/2037 | 23-Jun-26 26-Jun-26 | IPC - 33 | P23-BP-S08-O | 2026-06-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/237 MPSB/Sur/1963 MPSB/MB/244 | 08-Oct-25 10-Oct-25 10-Oct-25 | IPC - 34 | P17-BP-S32a-O | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2084 MPSB/Sur/3736 MPSB/MB/2090 | 7-Jul-26 9-Jul-26 9-Jul-26 | IPC - 34 | P9-BP-S04a-O | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2099 MPSB/Sur/3762 MPSB/MB/2133 | 10-Jul-26 14-Jul-26 14-Jul-26 | IPC - 34 | P9-BP-S05a-O | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2150 MPSB/Sur/3779 MPSB/MB/2166 | 17-Jul-26 20-Jul-26 20-Jul-26 | IPC - 34 | P9-BP-S06a-O | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2169 MPSB/Sur/3787 MPSB/MB/2183 | 21-Jul-26 23-Jul-26 23-Jul-26 | IPC - 34 | P9-BP-S07a-O | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2201 MPSB/Sur/3800 MPSB/MB/2218 | 25-Jul-26 28-Jul-26 28-Jul-26 | IPC - 34 | P9-BP-S08a-O | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2097 MPSB/Sur/3741 MPSB/MB/2101 | 10-Jul-26 10-Jul-26 10-Jul-26 | IPC - 34 | P9-KS-S32-O | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2131 MPSB/Sur/3766 MPSB/MB/2140 | 14-Jul-26 15-Jul-26 15-Jul-26 | IPC - 34 | P9-KS-S33-O© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2161 MPSB/Sur/3783 MPSB/MB/2171 | 19-Jul-26 21-Jul-26 21-Jul-26 | IPC - 34 | P9-KS-S34-O | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2086 MPSB/Sur/3731 MPSB/MB/2087 | 7-Jul-26 8-Jul-26 8-Jul-26 | IPC - 34 | P15-BP-S10-O | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2098 MPSB/Sur/3758 MPSB/MB/2116 | 10-Jul-26 13-Jul-26 13-Jul-26 | IPC - 34 | P15-BP-S11-O© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2148 MPSB/MB/2156 | 17-Jul-26 18-Jul-26 | IPC - 34 | P15-BP-S12-O | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2170 MPSB/Sur/3789 MPSB/MB/2192 | 21-Jul-26 23-Jul-26 23-Jul-26 | IPC - 34 | P15-BP-S13-O© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2181 MPSB/Sur/3797 MPSB/MB/2211 | 23-Jul-26 27-Jul-26 27-Jul-26 | IPC - 34 | P15-BP-S14-O | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2224 MPSB/Sur/3808 MPSB/MB/2232 | 29-Jul-26 30-Jul-26 30-Jul-26 | IPC - 34 | P15-BP-S15-O© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2227 MPSB/Sur/3816 MPSB/MB/2243 | 30-Jul-26 31-Jul-26 31-Jul-26 | IPC - 34 | P15-BP-S22-O | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2223 MPSB/Sur/3807 MPSB/MB/2231 | 29-Jul-26 30-Jul-26 30-Jul-26 | IPC - 34 | P15-KS-S09a-O© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2230 MPSB/Sur/3819 MPSB/MB/2246 | 30-Jul-26 31-Jul-26 31-Jul-26 | IPC - 34 | P15-KS-S10a-O | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2100 MPSB/Sur/3748 MPSB/MB/2109 | 10-Jul-26 11-Jul-26 11-Jul-26 | IPC - 34 | P16-BP-S17-M | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2147 MPSB/Sur/3773 MPSB/MB/2149 | 17-Jul-26 17-Jul-26 17-Jul-26 | IPC - 34 | P16-BP-S18-M | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2085 MPSB/Sur/3735 MPSB/MB/2089 | 7-Jul-26 9-Jul-26 9-Jul-26 | IPC - 34 | P16-KS-S09-M | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2132 MPSB/Sur/3765 MPSB/MB/2139 | 14-Jul-26 15-Jul-26 15-Jul-26 | IPC - 34 | P16-KS-S10-M© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2163 MPSB/Sur/3780 MPSB/MB/2167 | 19-Jul-26 20-Jul-26 20-Jul-26 | IPC - 34 | P16-KS-S11-M | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2168 MPSB/Sur/3786 MPSB/MB/2182 | 21-Jul-26 23-Jul-26 23-Jul-26 | IPC - 34 | P16-KS-S12-M© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2180 MPSB/Sur/3796 MPSB/MB/2210 | 23-Jul-26 27-Jul-26 27-Jul-26 | IPC - 34 | P16-KS-S13-M | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/2228 MPSB/Sur/3817 MPSB/MB/2244 | 30-Jul-26 31-Jul-26 31-Jul-26 | IPC - 34 | P16-KS-S14-M© | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2234 MPSB/Sur/3812 MPSB/MB/2238 | 30-Jul-26 31-Jul-26 31-Jul-26 | IPC - 34 | P19-KS-S09a-O© | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2114 MPSB/Sur/3763 MPSB/MB/2137 | 11-Jul-26 15-Jul-26 15-Jul-26 | IPC - 34 | P21-BP-S21a-O© | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/Sur/3749 MPSB/MB/2113 | 11-Jul-26 11-Jul-26 | IPC - 34 | P21-BP-S25a-O© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2135 MPSB/Sur/3777 MPSB/MB/2159 | 15-Jul-26 18-Jul-26 18-Jul-26 | IPC - 34 | P21-BP-S26a-O | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2165 MPSB/Sur/3785 MPSB/MB/2179 | 19-Jul-26 22-Jul-26 22-Jul-26 | IPC - 34 | P21-BP-S27a-O© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2189 MPSB/Sur/3791 MPSB/MB/2196 | 23-Jul-26 25-Jul-26 25-Jul-26 | IPC - 34 | P21-BP-S28a-O | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2199 MPSB/Sur/3799 MPSB/MB/2214 | 25-Jul-26 28-Jul-26 28-Jul-26 | IPC - 34 | P21-BP-S29a-O© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2217 MPSB/Sur/3809 MPSB/MB/2235 | 28-Jul-26 30-Jul-26 30-Jul-26 | IPC - 34 | P21-BP-S30a-O | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2236 MPSB/Sur/3813 MPSB/MB/2239 | 30-Jul-26 31-Jul-26 31-Jul-26 | IPC - 34 | P21-BP-S31a-O© | 2026-07-01
406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2095 MPSB/Sur/3745 MPSB/MB/2107 | 9-Jul-26 10-Jul-26 10-Jul-26 | IPC - 34 | P21-KS-S33-O© | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2120 MPSB/Sur/3764 MPSB/MB/2138 | 13-Jul-26 15-Jul-26 15-Jul-26 | IPC - 34 | P21-KS-S34-O | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2081 MPSB/Sur/3759 MPSB/MB/2118 | 7-Jul-26 13-Jul-26 13-Jul-26 | IPC - 34 | P22-BP-S04-E | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2136 MPSB/Sur/3775 MPSB/MB/2154 | 15-Jul-26 17-Jul-26 17-Jul-26 | IPC - 34 | P22-BP-S05-E | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2153 MPSB/Sur/3784 MPSB/MB/2178 | 17-Jul-26 22-Jul-26 22-Jul-26 | IPC - 34 | P22-BP-S06-E | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2127 MPSB/Sur/3771 MPSB/MB/2144 | 14-Jul-26 16-Jul-26 16-Jul-26 | IPC - 34 | P24-KS-S01-M | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2164 MPSB/Sur/3790 MPSB/MB/2195 | 19-Jul-26 24-Jul-26 24-Jul-26 | IPC - 34 | P24-KS-S02-M | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2216 MPSB/Sur/3802 MPSB/MB/2225 | 28-Jul-26 29-Jul-26 29-Jul-26 | IPC - 34 | P24-KS-S03-M | 2026-07-01
406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/2237 MPSB/Sur/3815 MPSB/MB/2241 | 30-Jul-26 31-Jul-26 31-Jul-26 | IPC - 34 | P24-KS-S04-M | 2026-07-01
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/357 | 2025-01-24 | IPC - 10 | P10 | P10
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/368 | 2025-01-27 | IPC - 10 | P10 | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 4.32 | MPSB/Str/489 MPSB/Sur/426 MPSB/Str/494 MPSB/Sur/453 MPSB/Sur/454 | 5-Feb-25 6-Feb-25 6-Feb-25 11-Feb-25 11-Feb-25 | IPC - 11 | P10 - Well Curb | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/577 MPSB/Sur/508 MPSB/Str/578 MPSB/Sur/545 | 19-Feb-25 19-Feb-25 19-Feb-25 24-Feb-25 | IPC - 11 | P10 - 1st Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/659 MPSB/Sur/580 MPSB/Str/660 | 27-Feb-25 27-Feb-25 27-Feb-25 | IPC - 11 | P10 - 2nd Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/666 MPSB/Sur/590 MPSB/Str/667 | 28-Feb-25 28-Feb-25 28-Feb-25 | IPC - 11 | P10 - 3rd Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.615 | MPSB/Str/837 MPSB/Str/838 MPSB/Sur/745 | 20-Mar-25 20-Mar-25 20-Mar-25 | IPC - 13 | P10 - 4th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.32 | MPSB/Str/914 MPSB/Str/915 MPSB/Sur/798 | 26-Mar-25 26-Mar-25 26-Mar-25 | IPC - 13 | P10 - 5th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/991 MPSB/Str/992 MPSB/Sur/859 | 31-Mar-25 31-Mar-25 31-Mar-25 | IPC - 13 | P10 - 6th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1102 MPSB/Sur/964 MPSB/Str/1103 MPSB/Sur/1000 | 11-Apr-25 11-Apr-25 11-Apr-25 15-Apr-25 | IPC - 14 | P10 - 7th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 0.545 | MPSB/Str/1216 MPSB/Sur/1057 MPSB/Str/1217 | 21-Apr-25 21-Apr-25 21-Apr-25 | IPC - 14 | P10 - 8th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.81 | MPSB/Str/1248 MPSB/Sur/1077 MPSB/Str/1249 | 24-Apr-25 24-Apr-25 24-Apr-25 | IPC - 14 | P10 - 9th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1472 MPSB/Sur/1253 MPSB/Str/1473 MPSB/Sur/1291 | 11-May-25 11-May-25 11-May-25 16-May-25 | IPC - 15 | P10 - 10th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1561 MPSB/Sur/1342 MPSB/Str/1562 | 24-May-25 24-May-25 24-May-25 | IPC - 15 | P10 - 11th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.2 | MPSB/Str/1600 MPSB/Sur/1385 MPSB/Str/1601 | 29-May-25 29-May-25 29-May-25 | IPC - 15 | P10 - 12th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/1674 MPSB/Str/1675 MPSB/Sur/1462 | 17-Jun-25 17-Jun-25 27-Jun-25 | IPC - 16 | P10 - 13th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.7 | MPSB/Str/1694 MPSB/Sur/1451 MPSB/Str/1695 MPSB/Sur/1462 | 23-Jun-25 23-Jun-25 23-Jun-25 27-Jun-25 | IPC - 16 | P10 - 14th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1720 MPSB/Sur/1466 MPSB/Str/1721 | 28-Jun-25 28-Jun-25 28-Jun-25 | IPC - 16 | P10 - 15th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1807 MPSB/Sur/1519 MPSB/Str/1808 MPSB/Sur/1550 | 14-Jul-25 14-Jul-25 14-Jul-25 19-Jul-25 | IPC - 18 | P10 - 16th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1930 MPSB/Sur/1615 MPSB/Str/1931 | 31-Jul-25 31-Jul-25 31-Jul-25 | IPC - 18 | P10 - 17th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.66 | MPSB/Str/2775 MPSB/Sur/2175 MPSB/Str/2776 | 12-Nov-25 12-Nov-25 12-Nov-25 | IPC - 23 | P10 - 18th Lift | P10
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.58 | MPSB/Str/2979 MPSB/Sur/2301 MPSB/Str/2980 | 29-Nov-25 29-Nov-25 29-Nov-25 | IPC - 23 | P10 - 19th Lift | P10
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/2561 | 2025-12-30 | IPC - 26 | P11 | P11
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/2637 | 2026-01-09 | IPC - 26 | P11 | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 6.2 | MPSB/Str/3534 MPSB/Sur/2710 MPSB/Str/3567 MPSB/Sur/2782 MPSB/Sur/2793 | 16-Jan-26 19-Jan-26 19-Jan-26 28-Jan-26 29-Jan-26 | IPC - 26 | P11 - Well Curb | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3715 MPSB/Sur/2818 MPSB/Str/3716 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | P11 - 1st Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3809 MPSB/Sur/2894 MPSB/Str/3810 MPSB/Sur/2924 | 9-Feb-26 9-Feb-26 9-Feb-26 13-Feb-26 | IPC - 27 | P11 - 2nd Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3859 MPSB/Sur/2934 MPSB/Str/3860 MPSB/Sur/2957 | 15-Feb-26 15-Feb-26 15-Feb-26 19-Feb-26 | IPC - 27 | P11 - 3rd Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3919 MPSB/Sur/2973 MPSB/Str/3920 MPSB/Sur/3041 | 21-Feb-26 21-Feb-26 21-Feb-26 28-Feb-26 | IPC - 27 | P11 - 4th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3960 MPSB/Sur/3009 MPSB/Str/3961 MPSB/Sur/3041 | 26-Feb-26 26-Feb-26 26-Feb-26 28-Feb-26 | IPC - 27 | P11 - 5th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4077 MPSB/Sur/3084 MPSB/Str/4078 | 10-Mar-26 10-Mar-26 10-Mar-26 | IPC - 29 | P11 - 6th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4120 MPSB/Sur/3123 MPSB/Str/4119 | 15-Mar-26 15-Mar-26 15-Mar-26 | IPC - 29 | P11 - 7th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4215 MPSB/Sur/3180 MPSB/Str/4216 | 27-Mar-26 27-Mar-26 27-Mar-26 | IPC - 29 | P11 - 8th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.7 | MPSB/Str/4345 MPSB/Sur/3255 MPSB/Str/4346 | 7-Apr-26 7-Apr-26 7-Apr-26 | IPC - 30 | P11 - 9th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4367 MPSB/Sur/3255 MPSB/Str/4368 | 11-Apr-26 7-Apr-26 11-Apr-26 | IPC - 30 | P11 - 10th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4473 MPSB/Sur/3344 MPSB/Str/4474 | 24-Apr-26 24-Apr-26 24-Apr-26 | IPC - 30 | P11 - 11th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4602 MPSB/Sur/3433 MPSB/Str/4603 | 8-May-26 8-May-26 8-May-26 | IPC - 31 | P11 - 12th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4684 MPSB/Sur/3480 MPSB/Str/4685 | 15-May-26 15-May-26 15-May-26 | IPC - 31 | P11 - 13th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4896 MPSB/Sur/3640 MPSB/Str/4897 | 12-Jun-26 12-Jun-26 12-Jun-26 | IPC - 33 | P11 - 14th Lift | P11
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/5002 MPSB/Sur/3690 MPSB/Str/5003 | 25-Jun-26 25-Jun-26 25-Jun-26 | IPC - 33 | P11 - 15th Lift | P11
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/477 | 2025-02-16 | IPC - 11 | P12 | P12
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/501 | 2025-02-19 | IPC - 11 | P12 | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 4.48 | MPSB/Str/628 MPSB/Sur/581 MPSB/Str/661 | 25-Feb-25 27-Feb-25 27-Feb-25 | IPC - 11 | P12 - Well Curb | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -2.7 |  |  | IPC - 26 | P12 - Well Curb | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.475 | MPSB/Sur/682 MPSB/Str/771 MPSB/Str/772 MPSB/Sur/718 | 10-Mar-25 10-Mar-25 10-Mar-25 15-Mar-25 | IPC - 13 | P12 - 1st Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -2.5 |  |  | IPC - 26 | P12 - 1st Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/839 MPSB/Str/840 MPSB/Sur/746 MPSB/Sur/845 | 20-Mar-25 20-Mar-25 20-Mar-25 28-Mar-25 | IPC - 13 | P12 - 2nd Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -1 |  |  | IPC - 26 | P12 - 2nd Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.32 | MPSB/Str/893 MPSB/Str/894 MPSB/Sur/784 MPSB/Sur/845 | 25-Mar-25 25-Mar-25 25-Mar-25 29-Mar-25 | IPC - 13 | P12 - 3rd Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -1 |  |  | IPC - 26 | P12 - 3rd Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/999 MPSB/Str/1000 MPSB/Sur/863 | 31-Mar-25 31-Mar-25 31-Mar-25 | IPC - 13 | P12 - 4th Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -1 |  |  | IPC - 26 | P12 - 4th Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.4 | MPSB/Str/1109 MPSB/Sur/985 MPSB/Str/1110 MPSB/Sur/1022 | 12-Apr-25 12-Apr-25 12-Apr-25 17-Apr-25 | IPC - 14 | P12 - 5th Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1 |  |  | IPC - 26 | P12 - 5th Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.6 | MPSB/Str/1199 MPSB/Sur/1043 MPSB/Str/1200 MPSB/Sur/1079 | 20-Apr-25 20-Apr-25 20-Apr-25 24-Apr-25 | IPC - 14 | P12 - 6th Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -2.5 |  |  | IPC - 26 | P12 - 6th Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1272 MPSB/Sur/1102 MPSB/Str/1273 | 25-Apr-25 25-Apr-25 25-Apr-25 | IPC - 14 | P12 - 7th Lift | P12
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -2.5 |  |  | IPC - 26 | P12 - 7th Lift | P12
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/2755 | 2026-01-24 | IPC - 33 | P12(A) | P12(A)
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/2783 | 2026-01-28 | IPC - 33 | P12(A) | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 4.48 | MPSB/Str/3668 MPSB/Sur/2802 MPSB/Str/3685 MPSB/Sur/2848 MPSB/Sur/2853 | 29-Jan-26 30-Jan-26 30-Jan-26 3-Feb-26 4-Feb-26 | IPC - 33 | P12(A) - Well Curb | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/3784 MPSB/Sur/2881 MPSB/Str/3785 MPSB/Sur/2905 | 7-Feb-26 7-Feb-26 7-Feb-26 11-Feb-26 | IPC - 33 | P12(A) - 1st Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/3827 MPSB/Sur/2906 MPSB/Str/3828 MPSB/Sur/2928 | 11-Feb-26 11-Feb-26 11-Feb-26 14-Feb-26 | IPC - 33 | P12(A) - 2nd Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/3864 MPSB/Sur/2939 MPSB/Str/3865 MPSB/Sur/2962 | 16-Feb-26 16-Feb-26 16-Feb-26 20-Feb-26 | IPC - 33 | P12(A) - 3rd Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/3929 MPSB/Sur/2976 MPSB/Str/3930 MPSB/Sur/3083 | 23-Feb-26 23-Feb-26 23-Feb-26 10-Mar-26 | IPC - 33 | P12(A) - 4th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/3962 MPSB/Sur/3010 MPSB/Str/3963 MPSB/Sur/3083 | 26-Feb-26 26-Feb-26 26-Feb-26 10-Mar-26 | IPC - 33 | P12(A) - 5th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4086 MPSB/Sur/3091 MPSB/Str/4087 MPSB/Sur/3118 | 11-Mar-26 11-Mar-26 11-Mar-26 14-Mar-26 | IPC - 33 | P12(A) - 6th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4153 MPSB/Sur/3145 MPSB/Str/4154 MPSB/Sur/3237 | 19-Mar-26 19-Mar-26 19-Mar-26 3-Apr-26 | IPC - 33 | P12(A) - 7th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 3.45 | MPSB/Str/4257 MPSB/Sur/3202 MPSB/Str/4258 MPSB/Sur/3237 | 30-Mar-26 30-Mar-26 30-Mar-26 3-Apr-26 | IPC - 33 | P12(A) - 8th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4362 MPSB/Sur/3269 MPSB/Str/4363 MPSB/Sur/3321 | 10-Apr-26 10-Apr-26 10-Apr-26 17-Apr-26 | IPC - 33 | P12(A) - 9th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4396 MPSB/Sur/3296 MPSB/Str/4397 MPSB/Sur/3321 | 14-Apr-26 14-Apr-26 14-Apr-26 17-Apr-26 | IPC - 33 | P12(A) - 10th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4525 MPSB/Sur/3381 MPSB/Str/4526 MPSB/Sur/3435 | 29-Apr-26 29-Apr-26 29-Apr-26 8-May-26 | IPC - 33 | P12(A) - 11th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4543 MPSB/Sur/3394 MPSB/Str/4544 MPSB/Sur/3435 | 30-Apr-26 30-Apr-26 30-Apr-26 8-May-26 | IPC - 33 | P12(A) - 12th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4716 MPSB/Sur/3501 MPSB/Str/4717 | 18-May-26 18-May-26 18-May-26 | IPC - 33 | P12(A) - 13th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4874 MPSB/Sur/3614 MPSB/Str/4875 | 6-Jun-26 6-Jun-26 6-Jun-26 | IPC - 33 | P12(A) - 14th Lift | P12(A)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4978 MPSB/Sur/3676 MPSB/Str/4979 | 22-Jun-26 22-Jun-26 22-Jun-26 | IPC - 33 | P12(A) - 15th Lift | P12(A)
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/2645 | 2026-01-10 | IPC - 26 | P13 | P13
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/2686 | 2026-01-16 | IPC - 26 | P13 | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 6.2 | MPSB/Str/3607 MPSB/Sur/2756 MPSB/Str/3637 MPSB/Sur/2819 | 22-Jan-26 24-Jan-26 24-Jan-26 31-Jan-26 | IPC - 26 | P13 - Well Curb | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3771 MPSB/Sur/2866 MPSB/Str/3772 MPSB/Sur/2908 | 6-Feb-26 6-Feb-26 6-Feb-26 11-Feb-26 | IPC - 27 | P13 - 1st Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3848 MPSB/Sur/2922 MPSB/Str/3849 MPSB/Sur/2948 | 13-Feb-26 13-Feb-26 13-Feb-26 17-Feb-26 | IPC - 27 | P13 - 2nd Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3894 MPSB/Sur/2955 MPSB/Str/3895 MPSB/Sur/2978 | 19-Feb-26 19-Feb-26 19-Feb-26 23-Feb-26 | IPC - 27 | P13 - 3rd Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3979 MPSB/Sur/3019 MPSB/Str/3980 | 27-Feb-26 27-Feb-26 27-Feb-26 | IPC - 27 | P13 - 4th Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4056 MPSB/Sur/3069 MPSB/Str/4057 | 7-Mar-26 7-Mar-26 7-Mar-26 | IPC - 29 | P13 - 5th Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4143 MPSB/Sur/3142 MPSB/Str/4144 | 18-Mar-26 18-Mar-26 18-Mar-26 | IPC - 29 | P13 - 6th Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4191 MPSB/Sur/3164 MPSB/Str/4192 | 24-Mar-26 24-Mar-26 24-Mar-26 | IPC - 29 | P13 - 7th Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4272 MPSB/Sur/3209 MPSB/Str/4273 | 31-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | P13 - 8th Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4359 MPSB/Sur/3264 MPSB/Str/4360 | 10-Apr-26 10-Apr-26 10-Apr-26 | IPC - 30 | P13 - 9th Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4416 MPSB/Sur/3307 MPSB/Str/4417 | 16-Apr-26 16-Apr-26 16-Apr-26 | IPC - 30 | P13 - 10th Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.7 | MPSB/Str/4527 MPSB/Sur/3382 MPSB/Str/4528 | 29-Apr-26 29-Apr-26 29-Apr-26 | IPC - 30 | P13 - 11th Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4543 MPSB/Sur/3394 MPSB/Str/4544 | 30-Apr-26 30-Apr-26 30-Apr-26 | IPC - 30 | P13 - 12th Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4764 MPSB/Sur/3536 MPSB/Str/4765 | 23-May-26 23-May-26 23-May-26 | IPC - 31 | P13 - 13th Lift | P13
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4943 MPSB/Sur/3664 MPSB/Str/4944 | 18-Jun-26 18-Jun-26 18-Jun-26 | IPC - 33 | P13 - 14th Lift | P13
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/441 | 2025-02-08 | IPC - 11 | P14 | P14
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/460 | 2025-02-12 | IPC - 11 | P14 | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 4.32 | MPSB/Str/566 MPSB/Sur/500 MPSB/Str/592 MPSB/Sur/551 MPSB/Sur/552 | 18-Feb-25 19-Feb-25 21-Feb-25 25-Feb-25 25-Feb-25 | IPC - 11 | P14 - Well Curb | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -2.5 |  |  | IPC - 26 | P14 - Well Curb | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.65 | MPSB/Str/668 MPSB/Sur/591 MPSB/Str/669 | 28-Feb-25 28-Feb-25 28-Feb-25 | IPC - 11 | P14 - 1st Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -2.5 |  |  | IPC - 26 | P14 - 1st Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.485 | MPSB/Str/799 MPSB/Str/800 MPSB/Sur/707 | 13-Mar-25 13-Mar-25 13-Mar-25 | IPC - 13 | P14 - 2nd Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -1 |  |  | IPC - 26 | P14 - 2nd Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/858 MPSB/Str/859 MPSB/Sur/765 | 22-Mar-25 22-Mar-25 22-Mar-25 | IPC - 13 | P14 - 3rd Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -1 |  |  | IPC - 26 | P14 - 3rd Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/926 MPSB/Str/927 MPSB/Sur/841 | 27-Mar-25 27-Mar-25 29-Mar-25 | IPC - 13 | P14 - 4th Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -1 |  |  | IPC - 26 | P14 - 4th Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Sur/861 MPSB/Str/995 MPSB/Str/996 | 31-Mar-25 31-Mar-25 31-Mar-25 | IPC - 13 | P14 - 5th Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -1 |  |  | IPC - 26 | P14 - 5th Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1142 MPSB/Sur/1001 MPSB/Str/1143 MPSB/Sur/1120 | 15-Apr-25 15-Apr-25 15-Apr-25 26-Apr-25 | IPC - 14 | P14 - 6th Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -2.485 |  |  | IPC - 26 | P14 - 6th Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1214 MPSB/Sur/1056 MPSB/Str/1215 MPSB/Sur/1120 | 21-Apr-25 21-Apr-25 21-Apr-25 26-Apr-25 | IPC - 14 | P14 - 7th Lift | P14
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -2.485 |  |  | IPC - 26 | P14 - 7th Lift | P14
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/2435 | 2025-12-17 | IPC - 26 | P14(N) | P14(N)
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/2466 | 2025-12-22 | IPC - 26 | P14(N) | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 4.48 | MPSB/Str/3229 MPSB/Sur/2510 MPSB/Str/3292 MPSB/Sur/2582 MPSB/Sur/2592 | 22-Dec-25 27-Dec-25 27-Dec-25 1-Jan-26 3-Jan-26 | IPC - 26 | P14(N) - Well Curb | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3422 MPSB/Sur/2603 MPSB/Str/3423 MPSB/Sur/2636 | 5-Jan-26 5-Jan-26 5-Jan-26 9-Jan-26 | IPC - 26 | P14(N) - 1st Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3477 MPSB/Sur/2646 MPSB/Str/3478 MPSB/Sur/2704 | 10-Jan-26 10-Jan-26 10-Jan-26 17-Jan-26 | IPC - 26 | P14(N) - 2nd Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3519 MPSB/Sur/2676 MPSB/Str/3520 MPSB/Sur/2704 | 14-Jan-26 14-Jan-26 14-Jan-26 17-Jan-26 | IPC - 26 | P14(N) - 3rd Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3597 MPSB/Sur/2732 MPSB/Str/3598 | 21-Jan-26 21-Jan-26 21-Jan-26 | IPC - 26 | P14(N) - 4th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3657 MPSB/Sur/2780 MPSB/Str/3658 | 27-Jan-26 27-Jan-26 27-Jan-26 | IPC - 26 | P14(N) - 5th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3713 MPSB/Sur/2817 MPSB/Str/3714 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | P14(N) - 6th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3758 MPSB/Sur/2852 MPSB/Str/3759 MPSB/Sur/2910 | 4-Feb-26 4-Feb-26 4-Feb-26 11-Feb-26 | IPC - 27 | P14(N) - 7th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 3.32 | MPSB/Str/3977 MPSB/Sur/3018 MPSB/Str/3978 | 27-Feb-26 27-Feb-26 27-Feb-26 | IPC - 27 | P14(N) - 8th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4097 MPSB/Sur/3109 MPSB/Str/4096 | 13-Mar-26 13-Mar-26 13-Mar-26 | IPC - 29 | P14(N) - 9th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4162 MPSB/Sur/3151 MPSB/Str/4163 | 20-Mar-26 20-Mar-26 20-Mar-26 | IPC - 29 | P14(N) - 10th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4259 MPSB/Sur/3203 MPSB/Str/4260 | 30-Mar-26 30-Mar-26 30-Mar-26 | IPC - 29 | P14(N) - 11th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4322 MPSB/Sur/3240 MPSB/Str/4323 | 4-Apr-26 4-Apr-26 4-Apr-26 | IPC - 30 | P14(N) - 12th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.2 | MPSB/Str/4395 MPSB/Sur/3295 MPSB/Str/4394 | 13-Apr-26 13-Apr-26 13-Apr-26 | IPC - 30 | P14(N) - 13th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4455 MPSB/Sur/3333 MPSB/Str/4456 | 21-Apr-26 21-Apr-26 21-Apr-26 | IPC - 30 | P14(N) - 14th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4666 MPSB/Sur/3474 MPSB/Str/4667 | 13-May-26 13-May-26 13-May-26 | IPC - 31 | P14(N) - 15th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4779 MPSB/Sur/3545 MPSB/Str/4780 | 25-May-26 25-May-26 25-May-26 | IPC - 31 | P14(N) - 16th Lift | P14(N)
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4894 MPSB/Sur/3639 MPSB/Str/4895 | 12-Jun-26 12-Jun-26 12-Jun-26 | IPC - 33 | P14(N) - 17th Lift | P14(N)
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/333 | 2025-01-20 | IPC - 10 | P15 | P15
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/367 | 2025-01-27 | IPC - 10 | P15 | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 6.2 | MPSB/Str/508 MPSB/Sur/457 MPSB/Str/526 MPSB/Sur/515 MPSB/Sur/536 | 9-Feb-25 12-Feb-25 12-Feb-25 20-Feb-25 23-Feb-25 | IPC - 11 | P15 - Well Curb | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.66 | MPSB/Str/670 MPSB/Sur/592 MPSB/Str/671 | 28-Feb-25 28-Feb-25 28-Feb-25 | IPC - 11 | P15 - 1st Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.49 | MPSB/Str/797 MPSB/Str/798 MPSB/Sur/706 MPSB/Sur/734 | 13-Mar-25 13-Mar-25 13-Mar-25 18-Mar-25 | IPC - 13 | P15 - 2nd Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/886 MPSB/Str/887 MPSB/Sur/777 | 24-Mar-25 24-Mar-25 24-Mar-25 | IPC - 13 | P15 - 3rd Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/997 MPSB/Str/998 MPSB/Sur/862 | 31-Mar-25 31-Mar-25 31-Mar-25 | IPC - 13 | P15 - 4th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1107 MPSB/Sur/971 MPSB/Str/1108 | 12-Apr-25 12-Apr-25 12-Apr-25 | IPC - 14 | P15 - 5th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1176 MPSB/Sur/1023 MPSB/Str/1177 | 17-Apr-25 17-Apr-25 17-Apr-25 | IPC - 14 | P15 - 6th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1234 MPSB/Sur/1067 MPSB/Str/1235 | 23-Apr-25 23-Apr-25 23-Apr-25 | IPC - 14 | P15 - 7th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1474 MPSB/Sur/1254 MPSB/Str/1475 MPSB/Sur/1289 | 12-May-25 12-May-25 12-May-25 16-May-25 | IPC - 15 | P15 - 8th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1538 MPSB/Sur/1325 MPSB/Str/1539 MPSB/Sur/1347 | 21-May-25 21-May-25 21-May-25 26-May-25 | IPC - 15 | P15 - 9th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1604 MPSB/Sur/1388 MPSB/Str/1605 | 30-May-25 30-May-25 30-May-25 | IPC - 15 | P15 - 10th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.34 | MPSB/Str/2591 MPSB/Sur/2054 MPSB/Str/2592 | 27-Oct-25 27-Oct-25 27-Oct-25 | IPC - 22 | P15 - 11th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 3.17 | MPSB/Str/2654 MPSB/Sur/2088 MPSB/Str/2655 | 31-Oct-25 31-Oct-25 31-Oct-25 | IPC - 23 | P15 - 12th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3094 MPSB/Sur/2378 MPSB/Str/3095 | 10-Dec-25 10-Dec-25 10-Dec-25 | IPC - 25 | P15 - 13th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3194 MPSB/Sur/2446 MPSB/Str/3195 | 19-Dec-25 19-Dec-25 19-Dec-25 | IPC - 25 | P15 - 14th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3317 MPSB/Sur/2529 MPSB/Str/3318 | 29-Dec-25 29-Dec-25 29-Dec-25 | IPC - 25 | P15 - 15th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3444 MPSB/Sur/2620 MPSB/Str/3445 | 7-Jan-26 7-Jan-26 7-Jan-26 | IPC - 26 | P15 - 16th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3886 MPSB/Sur/2951 MPSB/Str/3887 MPSB/Sur/2990 | 17-Feb-26 17-Feb-26 17-Feb-26 25-Feb-26 | IPC - 27 | P15 - 17th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2 | MPSB/Str/4091 MPSB/Sur/3105 MPSB/Str/4092 | 12-Mar-26 12-Mar-26 12-Mar-26 | IPC - 29 | P15 - 18th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.6 | MPSB/Str/4442 MPSB/Sur/3329 MPSB/Str/4443 | 20-Apr-26 20-Apr-26 20-Apr-26 | IPC - 30 | P15 - 19th Lift | P15
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.09 | MPSB/Str/4637 MPSB/Sur/3455 MPSB/Str/4638 | 11-May-26 11-May-26 11-May-26 | IPC - 31 | P15 - 20th Lift | P15
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/185 | 2024-12-09 | IPC - 09 | P16 | P16
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/205 | 2024-12-14 | IPC - 09 | P16 | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 4.32 | MPSB/Str/235 MPSB/Str/236 MPSB/Str/276 MPSB/Str/277 | 22-Dec-24 23-Dec-24 29-Dec-24 29-Dec-24 | IPC - 09 | P16 - Well Curb | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.65 | MPSB/Str/331 MPSB/Sur/270 MPSB/Str/349 MPSB/Sur/309 | 8-Jan-25 8-Jan-25 11-Jan-25 17-Jan-25 | IPC - 10 | P16 - 1st Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/394 MPSB/Sur/334 MPSB/Str/395 | 21-Jan-25 21-Jan-25 21-Jan-25 | IPC - 10 | P16 - 2nd Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/431 MPSB/Sur/366 MPSB/Str/441 MPSB/Sur/389 | 27-Jan-25 27-Jan-25 28-Jan-25 30-Jan-25 | IPC - 10 | P16 - 3rd Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/492 MPSB/Sur/437 MPSB/Str/503 MPSB/Sur/489 | 6-Feb-25 7-Feb-25 7-Feb-25 18-Feb-25 | IPC - 11 | P16 - 4th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/540 MPSB/Sur/466 MPSB/Str/539 MPSB/Sur/489 | 15-Feb-25 15-Feb-25 15-Feb-25 18-Feb-25 | IPC - 11 | P16 - 5th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/616 MPSB/Sur/549 MPSB/Str/624 | 24-Feb-25 25-Feb-25 25-Feb-25 | IPC - 11 | P16 - 6th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.51 | MPSB/Sur/679 MPSB/Str/767 MPSB/Str/768 MPSB/Sur/699 | 09-Mar-25 09-Mar-25 09-Mar-25 11-Mar-25 | IPC - 13 | P16 - 7th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/912 MPSB/Str/913 MPSB/Sur/797 | 26-Mar-25 26-Mar-25 26-Mar-25 | IPC - 13 | P16 - 8th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/989 MPSB/Str/990 MPSB/Sur/858 | 31-Mar-25 31-Mar-25 31-Mar-25 | IPC - 13 | P16 - 9th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1436 MPSB/Sur/1230 MPSB/Str/1437 | 7-May-25 7-May-25 7-May-25 | IPC - 15 | P16 - 10th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1491 MPSB/Sur/1278 MPSB/Str/1492 MPSB/Sur/1319 | 15-May-25 15-May-25 15-May-25 20-May-25 | IPC - 15 | P16 - 11th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1753 MPSB/Sur/1484 MPSB/Str/1754 | 3-Jul-25 3-Jul-25 3-Jul-25 | IPC - 18 | P16 - 12th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 3.15 | MPSB/Str/1883 MPSB/Sur/1577 MPSB/Str/1884 | 25-Jul-25 25-Jul-25 25-Jul-25 | IPC - 18 | P16 - 13th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1970 MPSB/Sur/1643 MPSB/Str/1971 MPSB/Sur/1732 | 4-Aug-25 4-Aug-25 4-Aug-25 26-Aug-25 | IPC - 19 | P16 - 14th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2094 MPSB/Sur/1735 MPSB/Str/2095 | 27-Aug-25 27-Aug-25 27-Aug-25 | IPC - 19 | P16 - 15th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2147 MPSB/Sur/1766 MPSB/Str/2148 MPSB/Sur/1788 | 4-Sep-25 4-Sep-25 4-Sep-25 8-Sep-25 | IPC - 20 | P16 - 16th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2290 MPSB/Sur/1855 MPSB/Str/2291 | 22-Sep-25 22-Sep-25 22-Sep-25 | IPC - 20 | P16 - 17th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2337 MPSB/Sur/1884 MPSB/Str/2338 | 29-Sep-25 29-Sep-25 29-Sep-25 | IPC - 20 | P16 - 18th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2458 MPSB/Sur/1971 MPSB/Str/2459 | 13-Oct-25 13-Oct-25 13-Oct-25 | IPC - 22 | P16 - 19th Lift | P16
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 0.82 | MPSB/Str/2530 MPSB/Sur/2016 MPSB/Str/2531 | 20-Oct-25 20-Oct-25 20-Oct-25 | IPC - 22 | P16 - 20th Lift | P16
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/202 | 2024-12-17 | IPC - 09 | P17 | P17
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/294 | 2025-01-13 | IPC - 10 | P17 | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 6.04 | MPSB/Str/439 MPSB/Str/455 | 27-Jan-25 30-Jan-25 | IPC - 10 | P17 - Well Curb | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.16 | MPSB/Str/602 MPSB/Sur/529 MPSB/Str/603 MPSB/Sur/583 | 22-Feb-25 22-Feb-25 22-Feb-25 27-Feb-25 | IPC - 11 | P17 - 1st Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.15 | MPSB/Str/604 MPSB/Sur/530 MPSB/Str/605 MPSB/Sur/585 | 22-Feb-25 22-Feb-25 22-Feb-25 27-Feb-25 | IPC - 11 | P17 - 2nd Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/674 MPSB/Sur/594 MPSB/Str/675 | 28-Feb-25 28-Feb-25 28-Feb-25 | IPC - 11 | P17 - 3rd Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/769 MPSB/Str/770 MPSB/Sur/680 MPSB/Sur/720 | 10-Mar-25 10-Mar-25 10-Mar-25 15-Mar-25 | IPC - 13 | P17 - 4th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/810 MPSB/Str/811 MPSB/Sur/722 MPSB/Sur/756 | 17-Mar-25 17-Mar-25 17-Mar-25 21-Mar-25 | IPC - 13 | P17 - 5th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/993 MPSB/Str/994 MPSB/Sur/860 | 31-Mar-25 31-Mar-25 31-Mar-25 | IPC - 13 | P17 - 6th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1088 MPSB/Sur/952 MPSB/Str/1089 MPSB/Sur/1069 | 9-Apr-25 9-Apr-25 9-Apr-25 23-Apr-25 | IPC - 14 | P17 - 7th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1189 MPSB/Sur/1032 MPSB/Str/1190 | 19-Apr-25 19-Apr-25 19-Apr-25 | IPC - 14 | P17 - 8th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.05 | MPSB/Str/1462 MPSB/Sur/1249 MPSB/Str/1463 | 10-May-25 10-May-25 10-May-25 | IPC - 15 | P17 - 9th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.88 | MPSB/Str/1588 MPSB/Sur/1371 MPSB/Str/1589 | 28-May-25 28-May-25 28-May-25 | IPC - 15 | P17 - 10th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 3.63 | MPSB/Str/1676 MPSB/Sur/1435 MPSB/Str/1677 | 18-Jun-25 18-Jun-25 18-Jun-25 | IPC - 16 | P17 - 11th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.65 | MPSB/Str/2101 MPSB/Sur/1737 MPSB/Str/2102 | 28-Aug-25 28-Aug-25 28-Aug-25 | IPC - 19 | P17 - 12th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2220 MPSB/Sur/1813 MPSB/Str/2221 MPSB/Sur/1837 | 12-Sep-25 12-Sep-25 12-Sep-25 19-Sep-25 | IPC - 20 | P17 - 13th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2365 MPSB/Sur/1894 MPSB/Str/2366 | 30-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | P17 - 14th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2512 MPSB/Sur/2005 MPSB/Str/2513 | 18-Oct-25 18-Oct-25 18-Oct-25 | IPC - 22 | P17 - 15th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2611 MPSB/Sur/2062 MPSB/Str/2612 | 28-Oct-25 28-Oct-25 28-Oct-25 | IPC - 22 | P17 - 16th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3569 MPSB/Sur/2711 MPSB/Str/3570 MPSB/Sur/2767 | 19-Jan-26 19-Jan-26 19-Jan-26 24-Jan-26 | IPC - 26 | P17 - 17th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3797 MPSB/Sur/2887 MPSB/Str/3798 MPSB/Sur/3053 | 7-Feb-26 7-Feb-26 7-Feb-26 28-Feb-26 | IPC - 27 | P17 - 18th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3922 MPSB/Sur/2974 MPSB/Str/3923 MPSB/Sur/3053 | 21-Feb-26 21-Feb-26 21-Feb-26 28-Feb-26 | IPC - 27 | P17 - 19th Lift | P17
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.85 | MPSB/Str/4475 MPSB/Sur/3347 MPSB/Str/4476 | 24-Apr-26 24-Apr-26 24-Apr-26 | IPC - 30 | P17 - 20th Lift | P17
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/167 | 2024-12-03 | IPC - 09 | P18 | P18
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/191 | 2024-12-14 | IPC - 09 | P18 | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 4.32 | MPSB/Str/250 MPSB/Str/264 MPSB/Str/301 MPSB/Str/302 | 25-Dec-24 28-Dec-24 31-Dec-24 31-Dec-24 | IPC - 09 | P18 - Well Curb | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.65 | MPSB/Str/346 MPSB/Sur/284 MPSB/Str/353 MPSB/Sur/306 | 10-Jan-25 10-Jan-25 12-Jan-25 16-Jan-25 | IPC - 10 | P18 - 1st Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/385 MPSB/Sur/325 MPSB/Str/386 MPSB/Sur/361 | 20-Jan-25 20-Jan-25 20-Jan-25 25-Jan-25 | IPC - 10 | P18 - 2nd Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/435 MPSB/Sur/372 MPSB/Str/436 | 27-Jan-25 27-Jan-25 27-Jan-25 | IPC - 10 | P18 - 3rd Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/474 MPSB/Sur/404 MPSB/Str/475 | 2025-01-31 | IPC - 10 | P18 - 4th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/530 MPSB/Str/537 MPSB/Sur/482 | 12-Feb-25 14-Feb-25 17-Feb-25 | IPC - 11 | P18 - 5th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/598 MPSB/Sur/527 MPSB/Str/599 MPSB/Sur/556 | 22-Feb-25 22-Feb-25 22-Feb-25 25-Feb-25 | IPC - 11 | P18 - 6th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.51 | MPSB/Str/746 MPSB/Sur/664 MPSB/Str/747 MPSB/Sur/686 | 07-Mar-25 07-Mar-25 07-Mar-25 11-Mar-25 | IPC - 13 | P18 - 7th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 0.5 | MPSB/Str/928 MPSB/Sur/807 MPSB/Str/929 | 27-Mar-25 27-Mar-25 27-Mar-25 | IPC - 13 | P18 - 8th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/939 MPSB/Str/940 MPSB/Sur/818 | 28-Mar-25 28-Mar-25 28-Mar-25 | IPC - 13 | P18 - 9th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1191 MPSB/Sur/1037 MPSB/Str/1220 | 19-Apr-25 19-Apr-25 21-Apr-25 | IPC - 14 | P18 - 10th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1240 MPSB/Sur/1074 MPSB/Str/1241 | 24-Apr-25 24-Apr-25 24-Apr-25 | IPC - 14 | P18 - 11th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1751 MPSB/Sur/1483 MPSB/Str/1752 MPSB/Sur/1574 | 2-Jul-25 2-Jul-25 2-Jul-25 24-Jul-25 | IPC - 18 | P18 - 12th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1784 MPSB/Sur/1505 MPSB/Str/1785 MPSB/Sur/1574 | 9-Jul-25 9-Jul-25 9-Jul-25 24-Jul-25 | IPC - 18 | P18 - 13th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1815 MPSB/Sur/1529 MPSB/Str/1816 | 15-Jul-25 15-Jul-25 15-Jul-25 | IPC - 18 | P18 - 14th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.3 | MPSB/Str/1928 MPSB/Sur/1614 MPSB/Str/1929 MPSB/Sur/1677 | 31-Jul-25 31-Jul-25 31-Jul-25 11-Aug-25 | IPC - 19 | P18 - 15th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.6 | MPSB/Str/1996 MPSB/Sur/1658 MPSB/Str/1997 MPSB/Sur/1677 | 7-Aug-25 7-Aug-25 7-Aug-25 11-Aug-25 | IPC - 19 | P18 - 16th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2107 MPSB/Sur/1745 MPSB/Str/2108 | 29-Aug-25 29-Aug-25 29-Aug-25 | IPC - 19 | P18 - 17th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.6 | MPSB/Str/2159 MPSB/Sur/1777 MPSB/Str/2160 | 6-Sep-25 6-Sep-25 6-Sep-25 | IPC - 20 | P18 - 18th Lift | P18
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.77 | MPSB/Str/2339 MPSB/Sur/1885 MPSB/Str/2340 | 29-Sep-25 29-Sep-25 29-Sep-25 | IPC - 20 | P18 - 19th Lift | P18
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/176 | 2024-12-05 | IPC - 08 | P19 | P19
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/228 | 2025-12-28 | IPC - 10 | P19 | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 6.04 | MPSB/Str/359 MPSB/Str/381 MPSB/Sur/380 | 13-Jan-25 18-Jan-25 28-Jan-25 | IPC - 10 | P19 - Well Curb | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.65 | MPSB/Str/546 MPSB/Sur/480 MPSB/Str/562 MPSB/Sur/511 | 15-Feb-25 17-Feb-25 17-Feb-25 20-Feb-25 | IPC - 11 | P19 - 1st Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/629 MPSB/Sur/557 MPSB/Str/630 MPSB/Sur/572 | 25-Feb-25 25-Feb-25 25-Feb-25 27-Feb-25 | IPC - 11 | P19 - 2nd Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.51 | MPSB/Str/758 MPSB/Sur/673 MPSB/Str/759 MPSB/Sur/701 | 09-Mar-25 09-Mar-25 09-Mar-25 12-Mar-25 | IPC - 13 | P19 - 3rd Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/853 MPSB/Sur/673 MPSB/Str/854 MPSB/Sur/788 | 22-Mar-25 22-Mar-25 22-Mar-25 26-Mar-25 | IPC - 13 | P19 - 4th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/954 MPSB/Sur/832 MPSB/Str/955 MPSB/Sur/876 | 29-Mar-25 29-Mar-25 29-Mar-25 31-Mar-25 | IPC - 13 | P19 - 5th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1069 MPSB/Sur/940 MPSB/Str/1070 MPSB/Sur/977 | 8-Apr-25 8-Apr-25 8-Apr-25 12-Apr-25 | IPC - 14 | P19 - 6th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1134 MPSB/Sur/996 MPSB/Str/1135 MPSB/Sur/1050 | 15-Apr-25 15-Apr-25 15-Apr-25 21-Apr-25 | IPC - 14 | P19 - 7th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2 | MPSB/Str/1351 MPSB/Sur/1157 MPSB/Str/1352 | 30-Apr-25 30-Apr-25 30-Apr-25 | IPC - 14 | P19 - 8th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.7 | MPSB/Str/1506 MPSB/Sur/1295 MPSB/Str/1507 MPSB/Sur/1355 | 17-May-25 17-May-25 17-May-25 26-May-25 | IPC - 15 | P19 - 9th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/1548 MPSB/Sur/1331 MPSB/Str/1549 | 22-May-25 22-May-25 22-May-25 | IPC - 15 | P19 - 10th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2839 MPSB/Sur/2213 MPSB/Str/2840 MPSB/Sur/2255 | 18-Nov-25 18-Nov-25 18-Nov-25 23-Nov-25 | IPC - 23 | P19 - 11th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2986 MPSB/Sur/2302 MPSB/Str/2987 | 29-Nov-25 29-Nov-25 29-Nov-25 | IPC - 23 | P19 - 12th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3148 MPSB/Sur/2417 MPSB/Str/3149 MPSB/Sur/2454 | 15-Dec-25 15-Dec-25 15-Dec-25 20-Dec-25 | IPC - 25 | P19 - 13th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3261 MPSB/Sur/2488 MPSB/Str/3262 MPSB/Sur/2504 | 24-Dec-25 24-Dec-25 24-Dec-25 26-Dec-25 | IPC - 25 | P19 - 14th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3352 MPSB/Sur/2554 MPSB/Str/3353 | 30-Dec-25 30-Dec-25 30-Dec-25 | IPC - 25 | P19 - 15th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3475 MPSB/Sur/2641 MPSB/Str/3476 MPSB/Sur/2668 | 9-Jan-26 9-Jan-26 9-Jan-26 13-Jan-26 | IPC - 26 | P19 - 16th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3545 MPSB/Sur/2697 MPSB/Str/3546 MPSB/Sur/2725 | 16-Jan-26 16-Jan-26 16-Jan-26 20-Jan-26 | IPC - 26 | P19 - 17th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3642 MPSB/Sur/2758 MPSB/Str/3643 MPSB/Sur/2789 | 24-Jan-26 24-Jan-26 24-Jan-26 28-Jan-26 | IPC - 26 | P19 - 18th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.85 | MPSB/Str/3795 MPSB/Sur/2886 MPSB/Str/3796 MPSB/Sur/2994 | 7-Feb-26 7-Feb-26 7-Feb-26 25-Feb-26 | IPC - 27 | P19 - 19th Lift | P19
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1 | MPSB/Str/3880 MPSB/Sur/2949 MPSB/Str/3881 MPSB/Sur/2994 | 17-Feb-26 17-Feb-26 17-Feb-26 25-Feb-26 | IPC - 27 | P19 - 20th Lift | P19
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 4 | MPSB/Str/4725 MPSB/Sur/3510 MPSB/Str/4726 | 19-May-26 19-May-26 19-May-26 | IPC - 31 | P19 - Lower Pylon - 1st Lift | P19
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 0.63 | MPSB/Str/4588 MPSB/Sur/3421 MPSB/Str/4589 | 6-May-26 6-May-26 6-May-26 | IPC - 31 | P19 - Lower Pylon - Starter | P19
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/103 | 2024-11-16 | IPC - 08 | P20 | P20
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/127 | 2024-11-25 | IPC - 08 | P20 | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 4.32 | MPSB/Str/209 MPSB/Str/210 MPSB/Sur/210 MPSB/Str/231 | 15-Dec-24 16-Dec-24 22-Dec-24 22-Dec-24 | IPC - 09 | P20 - Well Curb | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.65 | MPSB/Sur/219 MPSB/Str/251 MPSB/Str/252 MPSB/Str/280 | 25-Dec-24 25-Dec-24 25-Dec-24 29-Dec-24 | IPC - 09 | P20 - 1st Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Sur/237 MPSB/Str/287 MPSB/Str/288 | 30-Dec-24 30-Dec-24 30-Dec-24 | IPC - 09 | P20 - 2nd Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/338 MPSB/Sur/272 MPSB/Str/339 MPSB/Sur/312 | 8-Jan-25 8-Jan-25 8-Jan-25 17-Jan-25 | IPC - 10 | P20 - 3rd Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/420 MPSB/Sur/352 MPSB/Str/421 MPSB/Sur/392 | 24-Jan-25 24-Jan-25 24-Jan-25 29-Jan-25 | IPC - 10 | P20 - 4th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/456 MPSB/Sur/385 MPSB/Str/457 | 30-Jan-25 30-Jan-25 30-Jan-25 | IPC - 10 | P20 - 5th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/506 MPSB/Sur/440 MPSB/Str/550 MPSB/Sur/484 | 8-Feb-25 8-Feb-25 15-Feb-25 17-Feb-25 | IPC - 11 | P20 - 6th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/587 MPSB/Sur/521 MPSB/Str/588 MPSB/Sur/544 | 21-Feb-25 21-Feb-25 21-Feb-25 24-Feb-25 | IPC - 11 | P20 - 7th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/631 MPSB/Sur/558 MPSB/Str/632 MPSB/Sur/574 | 25-Feb-25 25-Feb-25 25-Feb-25 27-Feb-25 | IPC - 11 | P20 - 8th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.51 | MPSB/Str/812 MPSB/Sur/725 MPSB/Str/813 MPSB/Sur/750 | 17-Mar-25 17-Mar-25 17-Mar-25 20-Mar-25 | IPC - 13 | P20 - 9th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/865 MPSB/Sur/769 MPSB/Str/866 MPSB/Sur/817 | 24-Mar-25 24-Mar-25 24-Mar-25 28-Mar-25 | IPC - 13 | P20 - 10th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1008 MPSB/Sur/870 MPSB/Str/1009 | 31-Mar-25 31-Mar-25 31-Mar-25 | IPC - 13 | P20 - 11th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1476 MPSB/Sur/1259 MPSB/Str/1477 MPSB/Sur/1297 | 12-May-25 12-May-25 12-May-25 17-May-25 | IPC - 15 | P20 - 12th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 3.3 | MPSB/Str/1690 MPSB/Sur/1448 MPSB/Str/1691 | 21-Jun-25 21-Jun-25 21-Jun-25 | IPC - 16 | P20 - 13th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2402 MPSB/Sur/1923 MPSB/Str/2403 MPSB/Sur/1962 | 06-Oct-25 06-Oct-25 06-Oct-25 10-Oct-25 | IPC - 22 | P20 - 14th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2518 MPSB/Sur/2008 MPSB/Str/2519 MPSB/Sur/2031 | 18-Oct-25 18-Oct-25 18-Oct-25 23-Oct-25 | IPC - 22 | P20 - 15th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2628 MPSB/Sur/2069 MPSB/Str/2629 | 30-Oct-25 30-Oct-25 30-Oct-25 | IPC - 22 | P20 - 16th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2811 MPSB/Sur/2193 MPSB/Str/2812 MPSB/Sur/2215 | 14-Nov-25 14-Nov-25 14-Nov-25 18-Nov-25 | IPC - 23 | P20 - 17th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.7 | MPSB/Str/2962 MPSB/Sur/2289 MPSB/Str/2963 | 27-Nov-25 27-Nov-25 27-Nov-25 | IPC - 23 | P20 - 18th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3175 MPSB/Sur/2430 MPSB/Str/3176 MPSB/Sur/2485 | 17-Dec-25 17-Dec-25 17-Dec-25 24-Dec-25 | IPC - 25 | P20 - 19th Lift | P20
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.07 | MPSB/Str/3613 MPSB/Sur/2742 MPSB/Str/3614 | 22-Jan-26 22-Jan-26 22-Jan-26 | IPC - 26 | P20 - 20th Lift | P20
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 4 | MPSB/Str/4754 MPSB/Sur/3530 MPSB/Str/4755 | 22-May-26 22-May-26 22-May-26 | IPC - 31 | P20 - Lower Pylon - 1st Lift | P20
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 2 | MPSB/Str/4993 MPSB/Sur/3685 MPSB/Str/4994 | 23-Jun-26 23-Jun-26 23-Jun-26 | IPC - 33 | P20 - Lower Pylon - 2nd Lift | P20
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 0.515 | MPSB/Str/4660 MPSB/Sur/3470 MPSB/Str/4661 | 12-May-26 12-May-26 12-May-26 | IPC - 31 | P20 - Lower Pylon - Starter | P20
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/153 | 2024-11-30 | IPC - 08 | P21 | P21
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/314 | 2025-01-17 | IPC - 10 | P21 | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 6.2 | MPSB/Str/513 MPSB/Str/615 MPSB/Sur/600 MPSB/Sur/601 | 10-Feb-25 24-Feb-25 28-Feb-25 28-Feb-25 | IPC - 11 | P21 - Well Curb | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2 | MPSB/Str/802 MPSB/Sur/712 MPSB/Str/816 MPSB/Sur/760 | 15-Mar-25 15-Mar-25 17-Mar-25 22-Mar-25 | IPC - 13 | P21 - 1st Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.15 | MPSB/Str/804 MPSB/Sur/713 MPSB/Str/820 MPSB/Sur/762 | 15-Mar-25 15-Mar-25 18-Mar-25 22-Mar-25 | IPC - 13 | P21 - 2nd Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/888 MPSB/Sur/780 MPSB/Str/889 MPSB/Sur/880 | 25-Mar-25 25-Mar-25 25-Mar-25 31-Mar-25 | IPC - 13 | P21 - 3rd Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1111 MPSB/Sur/973 MPSB/Str/1112 MPSB/Sur/995 | 12-Apr-25 12-Apr-25 12-Apr-25 15-Apr-25 | IPC - 14 | P21 - 4th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1205 MPSB/Sur/1048 MPSB/Str/1206 MPSB/Sur/1100 | 21-Apr-25 21-Apr-25 21-Apr-25 25-Apr-25 | IPC - 14 | P21 - 5th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1312 MPSB/Sur/1135 MPSB/Str/1313 | 28-Apr-25 28-Apr-25 28-Apr-25 | IPC - 14 | P21 - 6th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1470 MPSB/Sur/1252 MPSB/Str/1471 MPSB/Sur/1285 | 11-May-25 11-May-25 11-May-25 16-May-25 | IPC - 15 | P21 - 7th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2065 MPSB/Sur/1715 MPSB/Str/2066 MPSB/Sur/1750 | 21-Aug-25 21-Aug-25 21-Aug-25 30-Aug-25 | IPC - 19 | P21 - 8th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.3 | MPSB/Str/2374 MPSB/Sur/1903 MPSB/Str/2375 | 30-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | P21 - 9th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.7 | MPSB/Str/2934 MPSB/Sur/2276 MPSB/Str/2935 | 26-Nov-25 26-Nov-25 26-Nov-25 | IPC - 23 | P21 - 10th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/2995 MPSB/Sur/2312 MPSB/Str/2996 | 30-Nov-25 30-Nov-25 30-Nov-25 | IPC - 23 | P21 - 11th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3227 MPSB/Sur/2467 MPSB/Str/3228 MPSB/Sur/2487 | 22-Dec-25 22-Dec-25 22-Dec-25 24-Dec-25 | IPC - 25 | P21 - 12th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3323 MPSB/Sur/2533 MPSB/Str/3324 | 29-Dec-25 29-Dec-25 29-Dec-25 | IPC - 25 | P21 - 13th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3438 MPSB/Sur/2618 MPSB/Str/3439 MPSB/Sur/2650 | 6-Jan-26 6-Jan-26 6-Jan-26 11-Jan-26 | IPC - 26 | P21 - 14th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3521 MPSB/Sur/2677 MPSB/Str/3522 MPSB/Sur/2713 | 14-Jan-26 14-Jan-26 14-Jan-26 19-Jan-26 | IPC - 26 | P21 - 15th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3617 MPSB/Sur/2746 MPSB/Str/3618 MPSB/Sur/2772 | 23-Jan-26 23-Jan-26 23-Jan-26 25-Jan-26 | IPC - 26 | P21 - 16th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3693 MPSB/Sur/2805 MPSB/Str/3694 | 30-Jan-26 30-Jan-26 30-Jan-26 | IPC - 26 | P21 - 17th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3855 MPSB/Sur/2931 MPSB/Str/3856 MPSB/Sur/2999 | 14-Feb-26 14-Feb-26 14-Feb-26 25-Feb-26 | IPC - 27 | P21 - 18th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3975 MPSB/Sur/3017 MPSB/Str/3976 | 27-Feb-26 27-Feb-26 27-Feb-26 | IPC - 27 | P21 - 19th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.85 | MPSB/Str/4128 MPSB/Sur/3131 MPSB/Str/4129 | 16-Mar-26 16-Mar-26 16-Mar-26 | IPC - 29 | P21 - 20th Lift | P21
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.05 | MPSB/Str/4376 MPSB/Sur/3279 MPSB/Str/4377 | 11-Apr-26 11-Apr-26 11-Apr-26 | IPC - 30 | P21 - 21st Lift | P21
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/60 | 2024-10-28 | IPC - 07 | P22 | P22
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/92 | 2024-11-13 | IPC - 08 | P22 | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 4.32 | MPSB/Str/135 MPSB/Sur/137 MPSB/Str/153 MPSB/Sur/175 MPSB/Str/182 | 26-Nov-24 28-Nov-24 29-Nov-24 4-Dec-24 4-Dec-24 | IPC - 08 | P22 - Well Curb | P22 | Reinforcement Checking Outer Shutter Checking Concreting Grounding Sinking
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.65 | MPSB/Sur/180 MPSB/Str/192 MPSB/Str/193 MPSB/Str/199 | 6-Dec-24 9-Dec-24 9-Dec-24 12-Dec-24 | IPC - 09 | P22 - 1st Lift | P22 | Survey Checking Reinforcement Checking Shutter & Concreting Sinking
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Sur/195 MPSB/Str/203 MPSB/Str/204 MPSB/Str/214 | 13-Dec-24 13-Dec-24 13-Dec-24 16-Dec-24 | IPC - 09 | P22 - 2nd Lift | P22 | Survey Checking Reinforcement Checking Shutter & Concreting Sinking
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Sur/209 MPSB/Str/229 MPSB/Str/230 MPSB/Str/270 | 21-Dec-24 21-Dec-24 22-Dec-24 28-Dec-24 | IPC - 09 | P22 - 3rd Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Sur/223 MPSB/Str/259 MPSB/Str/260 MPSB/Str/281 | 26-Dec-24 26-Dec-24 26-Dec-24 29-Dec-24 | IPC - 09 | P22 - 4th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Sur/239 MPSB/Str/290 MPSB/Str/291 | 30-Dec-24 30-Dec-24 30-Dec-24 | IPC - 09 | P22 - 5th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/340 MPSB/Sur/277 MPSB/Str/341 MPSB/Sur/299 | 9-Jan-25 9-Jan-25 9-Jan-25 14-Jan-25 | IPC - 10 | P22 - 6th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/437 MPSB/Sur/374 MPSB/Str/438 MPSB/Sur/400 | 27-Jan-25 27-Jan-25 27-Jan-25 31-Jan-25 | IPC - 10 | P22 - 7th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.31 | MPSB/Str/760 MPSB/Sur/674 MPSB/Str/761 MPSB/Sur/711 | 10-Mar-25 10-Mar-25 10-Mar-25 13-Mar-25 | IPC - 13 | P22 - 8th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 0.5 | MPSB/Str/1203 MPSB/Sur/1047 MPSB/Str/1204 | 21-Apr-25 21-Apr-25 21-Apr-25 | IPC - 14 | P22 - 9th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/1267 MPSB/Sur/1127 MPSB/Str/1300 | 25-Apr-25 27-Apr-25 27-Apr-25 | IPC - 14 | P22 - 10th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1464 MPSB/Sur/1250 MPSB/Str/1465 MPSB/Sur/1256 | 10-May-25 10-May-25 10-May-25 12-May-25 | IPC - 15 | P22 - 11th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1528 MPSB/Sur/1312 MPSB/Str/1529 MPSB/Sur/1328 | 19-May-25 19-May-25 19-May-25 21-May-25 | IPC - 15 | P22 - 12th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Sur/1360 MPSB/Str/1662 MPSB/Str/1663 | 27-May-25 14-Jun-25 14-Jun-25 | IPC - 16 | P22 - 13th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1889 MPSB/Sur/1583 MPSB/Str/1915 | 25-Jul-25 25-Jul-25 28-Jul-25 | IPC - 18 | P22 - 14th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2103 MPSB/Sur/1738 MPSB/Str/2104 | 28-Aug-25 28-Aug-25 28-Aug-25 | IPC - 19 | P22 - 15th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.57 | MPSB/Str/2356 MPSB/Sur/1890 MPSB/Str/2357 | 29-Sep-25 29-Sep-25 29-Sep-25 | IPC - 20 | P22 - 16th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2475 MPSB/Sur/1984 MPSB/Str/2476 MPSB/Sur/2010 | 14-Oct-25 14-Oct-25 14-Oct-25 18-Oct-25 | IPC - 22 | P22 - 17th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2 | MPSB/Str/2593 MPSB/Sur/2056 MPSB/Str/2594 MPSB/Sur/2072 | 27-Oct-25 27-Oct-25 27-Oct-25 30-Oct-25 | IPC - 22 | P22 - 18th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2873 MPSB/Sur/2240 MPSB/Str/2874 MPSB/Sur/2267 | 20-Nov-25 20-Nov-25 20-Nov-25 25-Nov-25 | IPC - 23 | P22 - 19th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2 | MPSB/Str/3136 MPSB/Sur/2409 MPSB/Str/3137 MPSB/Sur/2437 | 14-Dec-25 14-Dec-25 14-Dec-25 18-Dec-25 | IPC - 25 | P22 - 20th Lift | P22
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 0.9 | MPSB/Str/3263 MPSB/Sur/2489 MPSB/Str/3283 | 24-Dec-25 24-Dec-25 26-Dec-25 | IPC - 25 | P22 - 21st Lift | P22
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 4 | MPSB/Str/4428 MPSB/Sur/3318 MPSB/Str/4429 | 17-Apr-26 17-Apr-26 17-Apr-26 | IPC - 30 | P22 - Lower Pylon - 1st Lift | P22
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 4 | MPSB/Str/4678 MPSB/Sur/3479 MPSB/Str/4679 | 14-May-26 14-May-26 14-May-26 | IPC - 31 | P22 - Lower Pylon - 2nd Lift | P22
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 2 | MPSB/Str/5007 MPSB/Sur/3692 MPSB/Str/5008 | 25-Jun-26 25-Jun-26 25-Jun-26 | IPC - 33 | P22 - Lower Pylon - 3rd Lift | P22
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 0.63 | MPSB/Str/4332 MPSB/Sur/3247 MPSB/Str/4333 | 6-Apr-26 6-Apr-26 6-Apr-26 | IPC - 30 | P22 - Lower Pylon - Starter | P22
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/77 | 2024-10-31 | IPC - 07 | P23 | P23
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/461 | 2025-02-12 | IPC - 11 | P23 | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 6.2 | MPSB/Str/633 MPSB/Str/686 | 25-Feb-25 28-Feb-25 | IPC - 11 | P23 - Well Curb | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2 | MPSB/Str/956 MPSB/Sur/833 MPSB/Str/957 MPSB/Sur/884 | 29-Mar-25 29-Mar-25 29-Mar-25 31-Mar-25 | IPC - 13 | P23 - 1st Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.15 | MPSB/Str/958 MPSB/Sur/834 MPSB/Str/959 MPSB/Sur/886 | 29-Mar-25 29-Mar-25 29-Mar-25 31-Mar-25 | IPC - 13 | P23 - 2nd Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1136 MPSB/Sur/997 MPSB/Str/1137 MPSB/Sur/1042 | 15-Apr-25 15-Apr-25 15-Apr-25 20-Apr-25 | IPC - 14 | P23 - 3rd Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1269 MPSB/Sur/1128 MPSB/Str/1301 | 25-Apr-25 27-Apr-25 27-Apr-25 | IPC - 14 | P23 - 4th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1440 MPSB/Sur/1232 MPSB/Str/1441 MPSB/Sur/1258 | 7-May-25 7-May-25 7-May-25 12-May-25 | IPC - 15 | P23 - 5th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1552 MPSB/Sur/1333 MPSB/Str/1553 MPSB/Sur/1357 | 22-May-25 22-May-25 22-May-25 26-May-25 | IPC - 15 | P23 - 6th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1877 MPSB/Sur/1571 MPSB/Str/1878 MPSB/Sur/1609 | 24-Jul-25 24-Jul-25 24-Jul-25 30-Jul-25 | IPC - 18 | P23 - 7th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2058 MPSB/Sur/1726 MPSB/Str/2075 MPSB/Sur/1761 | 21-Aug-25 23-Aug-25 23-Aug-25 3-Sep-25 | IPC - 20 | P23 - 8th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.3 | MPSB/Str/2243 MPSB/Sur/1828 MPSB/Str/2244 MPSB/Sur/1905 | 16-Sep-25 16-Sep-25 16-Sep-25 30-Sep-25 | IPC - 20 | P23 - 9th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/2552 MPSB/Sur/2025 MPSB/Str/2553 | 23-Oct-25 23-Oct-25 23-Oct-25 | IPC - 22 | P23 - 10th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.7 | MPSB/Str/2602 MPSB/Sur/2061 MPSB/Str/2603 | 27-Oct-25 27-Oct-25 27-Oct-25 | IPC - 22 | P23 - 11th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2793 MPSB/Sur/2183 MPSB/Str/2794 MPSB/Sur/2223 | 13-Nov-25 13-Nov-25 13-Nov-25 19-Nov-25 | IPC - 23 | P23 - 12th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2921 MPSB/Sur/2264 MPSB/Str/2922 | 25-Nov-25 25-Nov-25 25-Nov-25 | IPC - 23 | P23 - 13th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3087 MPSB/Sur/2369 MPSB/Str/3088 MPSB/Sur/2401 | 8-Dec-25 8-Dec-25 8-Dec-25 12-Dec-25 | IPC - 25 | P23 - 14th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3177 MPSB/Sur/2431 MPSB/Str/3203 MPSB/Sur/2474 | 17-Dec-25 17-Dec-25 19-Dec-25 23-Dec-25 | IPC - 25 | P23 - 15th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3284 MPSB/Sur/2506 MPSB/Str/3285 | 26-Dec-25 26-Dec-25 26-Dec-25 | IPC - 25 | P23 - 16th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3387 MPSB/Sur/2575 MPSB/Str/3388 | 31-Dec-25 31-Dec-25 31-Dec-25 | IPC - 25 | P23 - 17th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3508 MPSB/Sur/2666 MPSB/Str/3509 MPSB/Sur/2695 | 13-Jan-26 13-Jan-26 13-Jan-26 16-Jan-26 | IPC - 26 | P23 - 18th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3591 MPSB/Sur/2727 MPSB/Str/3592 MPSB/Sur/2770 | 20-Jan-26 20-Jan-26 20-Jan-26 25-Jan-26 | IPC - 26 | P23 - 19th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 0.35 | MPSB/Str/3672 MPSB/Sur/2795 MPSB/Str/3673 | 29-Jan-26 29-Jan-26 29-Jan-26 | IPC - 26 | P23 - 20th Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.55 | MPSB/Str/3767 MPSB/Sur/2863 MPSB/Str/3768 MPSB/Sur/3001 | 5-Feb-26 5-Feb-26 5-Feb-26 25-Feb-26 | IPC - 27 | P23 - 21st Lift | P23
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1 | MPSB/Str/3904 MPSB/Sur/2963 MPSB/Str/3905 MPSB/Sur/3001 | 20-Feb-26 20-Feb-26 20-Feb-26 25-Feb-26 | IPC - 27 | P23 - 22nd Lift | P23
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/57 | 2024-10-26 | IPC - 07 | P24 | P24
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/102 | 2024-11-16 | IPC - 08 | P24 | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 4.32 | MPSB/Str/215 MPSB/Str/223 MPSB/Str/253 MPSB/Str/254 | 17-Dec-24 19-Dec-24 25-Dec-24 25-Dec-24 | IPC - 09 | P24 - Well Curb | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.65 | MPSB/Sur/227 MPSB/Str/265 MPSB/Str/266 MPSB/Str/294 | 28-Dec-24 28-Dec-24 28-Dec-24 30-Dec-24 | IPC - 09 | P24 - 1st Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/305 MPSB/Sur/250 MPSB/Str/306 MPSB/Sur/283 | 31-Dec-24 31-Dec-24 31-Dec-24 10-Jan-25 | IPC - 10 | P24 - 2nd Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/357 MPSB/Sur/295 MPSB/Str/367 MPSB/Sur/370 | 13-Jan-25 13-Jan-25 15-Jan-25 27-Jan-25 | IPC - 10 | P24 - 3rd Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/396 MPSB/Sur/335 MPSB/Str/397 MPSB/Sur/371 | 21-Jan-25 21-Jan-25 21-Jan-25 27-Jan-25 | IPC - 10 | P24 - 4th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/458 MPSB/Sur/386 MPSB/Str/459 | 30-Jan-25 30-Jan-25 30-Jan-25 | IPC - 10 | P24 - 5th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/514 MPSB/Sur/465 MPSB/Str/535 MPSB/Sur/476 | 10-Feb-25 13-Feb-25 13-Feb-25 16-Feb-25 | IPC - 11 | P24 - 6th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/573 MPSB/Sur/504 MPSB/Str/574 MPSB/Sur/542 | 19-Feb-25 19-Feb-25 19-Feb-25 24-Feb-25 | IPC - 11 | P24 - 7th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/635 MPSB/Sur/559 MPSB/Str/636 MPSB/Sur/576 | 25-Feb-25 25-Feb-25 25-Feb-25 27-Feb-25 | IPC - 11 | P24 - 8th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.51 | MPSB/Str/773 MPSB/Sur/687 MPSB/Str/774 MPSB/Sur/716 | 11-Mar-25 11-Mar-25 11-Mar-25 15-Mar-25 | IPC - 13 | P24 - 9th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/904 MPSB/Sur/790 MPSB/Str/905 | 26-Mar-25 26-Mar-25 26-Mar-25 | IPC - 13 | P24 - 10th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1458 MPSB/Sur/1247 MPSB/Str/1459 MPSB/Sur/1282 | 9-May-25 9-May-25 9-May-25 15-May-25 | IPC - 15 | P24 - 11th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2024 MPSB/Sur/1687 MPSB/Str/2025 | 12-Aug-25 12-Aug-25 12-Aug-25 | IPC - 19 | P24 - 12th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 0.5 | MPSB/Str/2483 MPSB/Sur/1989 MPSB/Str/2484 MPSB/Sur/2051 | 15-Oct-25 15-Oct-25 15-Oct-25 26-Oct-25 | IPC - 22 | P24 - 13th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/2537 MPSB/Sur/2017 MPSB/Str/2538 MPSB/Sur/2051 | 20-Oct-25 20-Oct-25 20-Oct-25 26-Oct-25 | IPC - 22 | P24 - 14th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2709 MPSB/Sur/2134 MPSB/Str/2710 | 06-Nov-25 06-Nov-25 06-Nov-25 | IPC - 23 | P24 - 15th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2923 MPSB/Sur/2265 MPSB/Str/2924 | 25-Nov-25 25-Nov-25 25-Nov-25 | IPC - 23 | P24 - 16th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3085 MPSB/Sur/2368 MPSB/Str/3086 MPSB/Sur/2388 | 8-Dec-25 8-Dec-25 8-Dec-25 11-Dec-25 | IPC - 25 | P24 - 17th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3300 MPSB/Sur/2518 MPSB/Str/3301 MPSB/Sur/2577 | 27-Dec-25 27-Dec-25 27-Dec-25 31-Dec-25 | IPC - 25 | P24 - 18th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3459 MPSB/Sur/2627 MPSB/Str/3460 MPSB/Sur/2660 | 8-Jan-26 8-Jan-26 8-Jan-26 12-Jan-26 | IPC - 26 | P24 - 19th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3572 MPSB/Sur/2715 MPSB/Str/3573 MPSB/Sur/2761 | 19-Jan-26 19-Jan-26 19-Jan-26 24-Jan-26 | IPC - 26 | P24 - 20th Lift | P24
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.27 | MPSB/Str/3709 MPSB/Sur/2816 MPSB/Str/3710 | 30-Jan-26 30-Jan-26 30-Jan-26 | IPC - 26 | P24 - 21st Lift | P24
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/76 | 2024-10-31 | IPC - 07 | P25 | P25
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/196 | 2024-12-11 | IPC - 09 | P25 | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 6.04 | MPSB/Str/267 MPSB/Str/289 | 28-Dec-24 30-Dec-24 | IPC - 09 | P25 - Well Curb | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 3.31 | MPSB/Str/388 MPSB/Sur/328 MPSB/Str/389 MPSB/Sur/354 | 20-Jan-25 20-Jan-25 20-Jan-25 24-Jan-25 | IPC - 10 | P25 - 1st Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/447 MPSB/Sur/378 MPSB/Str/469 | 28-Jan-25 28-Jan-25 30-Jan-25 | IPC - 10 | P25 - 2nd Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/544 MPSB/Sur/469 MPSB/Str/545 MPSB/Sur/503 | 15-Feb-25 15-Feb-25 15-Feb-25 19-Feb-25 | IPC - 11 | P25 - 3rd Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/600 MPSB/Sur/528 MPSB/Str/601 MPSB/Sur/561 | 22-Feb-25 22-Feb-25 22-Feb-25 25-Feb-25 | IPC - 11 | P25 - 4th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/652 MPSB/Str/653 MPSB/Sur/569 | 26-Feb-25 26-Feb-25 26-Feb-25 | IPC - 11 | P25 - 5th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/806 MPSB/Sur/714 MPSB/Str/807 MPSB/Sur/732 | 15-Mar-25 15-Mar-25 15-Mar-25 18-Mar-25 | IPC - 13 | P25 - 6th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/863 MPSB/Sur/771 MPSB/Str/864 MPSB/Sur/806 | 23-Mar-25 24-Mar-25 23-Mar-25 27-Mar-25 | IPC - 13 | P25 - 7th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.3 | MPSB/Str/1132 MPSB/Sur/993 MPSB/Str/1133 MPSB/Sur/1036 | 14-Apr-25 14-Apr-25 14-Apr-25 19-Apr-25 | IPC - 14 | P25 - 8th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.7 | MPSB/Str/1244 MPSB/Sur/1076 MPSB/Str/1245 | 24-Apr-25 24-Apr-25 24-Apr-25 | IPC - 14 | P25 - 9th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/1357 MPSB/Sur/1160 MPSB/Str/1358 | 30-Apr-25 30-Apr-25 30-Apr-25 | IPC - 14 | P25 - 10th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1513 MPSB/Sur/1302 MPSB/Str/1514 MPSB/Sur/1323 | 18-May-25 18-May-25 18-May-25 20-May-25 | IPC - 15 | P25 - 11th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1575 MPSB/Sur/1351 MPSB/Str/1576 | 26-May-25 26-May-25 26-May-25 | IPC - 15 | P25 - 12th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2193 MPSB/Sur/1797 MPSB/Str/2194 MPSB/Sur/1824 | 9-Sep-25 9-Sep-25 9-Sep-25 15-Sep-25 | IPC - 20 | P25 - 13th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2350 MPSB/Sur/1887 MPSB/Str/2351 | 29-Sep-25 29-Sep-25 29-Sep-25 | IPC - 20 | P25 - 14th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2488 MPSB/Sur/1991 MPSB/Str/2489 MPSB/Sur/2029 | 16-Oct-25 16-Oct-25 16-Oct-25 23-Oct-25 | IPC - 22 | P25 - 15th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2619 MPSB/Sur/2066 MPSB/Str/2620 | 29-Oct-25 29-Oct-25 29-Oct-25 | IPC - 22 | P25 - 16th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2749 MPSB/Sur/2161 MPSB/Str/2750 MPSB/Sur/2199 | 09-Nov-25 09-Nov-25 09-Nov-25 15-Nov-25 | IPC - 23 | P25 - 17th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2895 MPSB/Sur/2250 MPSB/Str/2896 MPSB/Sur/2297 | 22-Nov-25 22-Nov-25 22-Nov-25 28-Nov-25 | IPC - 23 | P25 - 18th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.9 | MPSB/Str/3001 MPSB/Sur/2315 MPSB/Str/3002 | 30-Nov-25 30-Nov-25 30-Nov-25 | IPC - 23 | P25 - 19th Lift | P25
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1 | MPSB/Str/3356 MPSB/Sur/2556 MPSB/Str/3357 | 30-Dec-25 30-Dec-25 30-Dec-25 | IPC - 25 | P25 - 20th Lift | P25
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 2.115 | MPSB/Str/5017 MPSB/Sur/3693 MPSB/Str/5018 | 26-Jun-26 26-Jun-26 26-Jun-26 | IPC - 33 | P25 - Lower Pylon - 1st Lift | P25
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | -0.14 | MPSB/Str/5100 MPSB/Sur/3733 MPSB/Str/5101 | 9-Jul-26 9-Jul-26 9-Jul-26 | IPC - 34 | P25 - Lower Pylon - 2nd Lift | P25 | P25
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 0.63 | MPSB/Str/4902 MPSB/Sur/3651 MPSB/Str/4903 | 14-Jun-26 14-Jun-26 14-Jun-26 | IPC - 33 | P25 - Lower Pylon - Starter | P25
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/56 | 2024-10-24 | IPC - 07 | P26 | P26
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/87 | 2024-11-09 | IPC - 08 | P26 | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 4.32 | MPSB/Str/99 MPSB/Sur/184 MPSB/Str/190 MPSB/Sur/194 MPSB/Str/202 | 16-Nov-24 8-Dec-24 8-Dec-24 13-Dec-24 13-Dec-24 | IPC - 09 | P26 - Well Curb | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.65 | MPSB/Sur/206 MPSB/Str/224 MPSB/Str/225 MPSB/Str/232 | 19-Dec-24 19-Dec-24 19-Dec-24 22-Dec-24 | IPC - 09 | P26 - 1st Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Sur/220 MPSB/Str/255 MPSB/Str/256 MPSB/Str/282 | 25-Dec-24 25-Dec-24 25-Dec-24 29-Dec-24 | IPC - 09 | P26 - 2nd Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/292 MPSB/Sur/240 MPSB/Str/293 MPSB/Sur/276 | 30-Dec-24 30-Dec-24 30-Dec-24 9-Jan-25 | IPC - 10 | P26 - 3rd Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/355 MPSB/Sur/292 MPSB/Str/366 MPSB/Sur/322 | 13-Jan-25 13-Jan-25 15-Jan-25 18-Jan-25 | IPC - 10 | P26 - 4th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/406 MPSB/Sur/344 MPSB/Str/407 MPSB/Sur/373 | 22-Jan-25 22-Jan-25 22-Jan-25 27-Jan-25 | IPC - 10 | P26 - 5th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/470 MPSB/Sur/402 MPSB/Str/471 | 31-Jan-25 31-Jan-25 31-Jan-25 | IPC - 10 | P26 - 6th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/516 MPSB/Sur/467 MPSB/Str/541 MPSB/Sur/492 | 10-Feb-25 15-Feb-25 15-Feb-25 18-Feb-25 | IPC - 11 | P26 - 7th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 0.51 | MPSB/Str/855 MPSB/Sur/763 MPSB/Str/862 MPSB/Sur/888 | 22-Mar-25 22-Mar-25 23-Mar-25 31-Mar-25 | IPC - 13 | P26 - 8th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/930 MPSB/Sur/808 MPSB/Str/931 MPSB/Sur/890 | 27-Mar-25 27-Mar-25 27-Mar-25 31-Mar-25 | IPC - 13 | P26 - 9th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1153 MPSB/Sur/1003 MPSB/Str/1154 MPSB/Sur/1066 | 16-Apr-25 16-Apr-25 16-Apr-25 22-Apr-25 | IPC - 14 | P26 - 10th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1242 MPSB/Sur/1075 MPSB/Str/1243 MPSB/Sur/1126 | 24-Apr-25 24-Apr-25 24-Apr-25 27-Apr-25 | IPC - 14 | P26 - 11th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1314 MPSB/Sur/1136 MPSB/Str/1315 | 28-Apr-25 28-Apr-25 28-Apr-25 | IPC - 14 | P26 - 12th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1359 MPSB/Sur/1161 MPSB/Str/1360 | 30-Apr-25 30-Apr-25 30-Apr-25 | IPC - 14 | P26 - 13th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1495 MPSB/Sur/1280 MPSB/Str/1496 MPSB/Sur/1316 | 15-May-25 15-May-25 15-May-25 19-May-25 | IPC - 15 | P26 - 14th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1550 MPSB/Sur/1332 MPSB/Str/1551 MPSB/Sur/1359 | 22-May-25 22-May-25 22-May-25 26-May-25 | IPC - 15 | P26 - 15th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1728 MPSB/Sur/1472 MPSB/Str/1729 | 29-Jun-25 29-Jun-25 29-Jun-25 | IPC - 16 | P26 - 16th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1857 MPSB/Sur/1557 MPSB/Str/1858 MPSB/Sur/1628 | 21-Jul-25 21-Jul-25 21-Jul-25 31-Jul-25 | IPC - 18 | P26 - 17th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.85 | MPSB/Str/1985 MPSB/Sur/1654 MPSB/Str/1986 | 5-Aug-25 5-Aug-25 5-Aug-25 | IPC - 19 | P26 - 18th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2154 MPSB/Sur/1773 MPSB/Str/2155 MPSB/Sur/1815 | 5-Sep-25 5-Sep-25 5-Sep-25 12-Sep-25 | IPC - 20 | P26 - 19th Lift | P26
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 0.92 | MPSB/Str/2435 MPSB/Sur/1956 MPSB/Str/2436 | 09-Oct-25 09-Oct-25 09-Oct-25 | IPC - 22 | P26 - 20th Lift | P26
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 4 | MPSB/Str/4523 MPSB/Sur/3378 MPSB/Str/4524 | 28-Apr-26 28-Apr-26 28-Apr-26 | IPC - 30 | P26 - Lower Pylon - 1st Lift | P26
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 4 | MPSB/Str/4741 MPSB/Sur/3526 MPSB/Str/4742 | 21-May-26 21-May-26 21-May-26 | IPC - 31 | P26 - Lower Pylon - 2nd Lift | P26
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 2.115 | MPSB/Str/4904 MPSB/Sur/3652 MPSB/Str/4905 | 15-Jun-26 15-Jun-26 15-Jun-26 | IPC - 33 | P26 - Lower Pylon - 3rd Lift | P26
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 5.38 | MPSB/Str/5234 MPSB/Sur/3806 MPSB/Str/5235 | 30-Jul-26 30-Jul-26 30-Jul-26 | IPC - 34 | P26 - Lower Pylon - 4th Lift | P26 | P29
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 0.515 | MPSB/Str/4318 MPSB/Sur/3238 MPSB/Str/4319 | 4-Apr-26 4-Apr-26 4-Apr-26 | IPC - 30 | P26 - Lower Pylon - Starter | P26
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/495 | 2025-02-18 | IPC - 11 | P27 | P27
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/512 | 2025-02-20 | IPC - 11 | P27 | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 6.2 | MPSB/Str/748 MPSB/Str/832 MPSB/Sur/819 MPSB/Sur/821 | 07-Mar-25 19-Mar-25 28-Mar-25 28-Mar-25 | IPC - 13 | P27 - Well Curb | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/962 MPSB/Sur/836 MPSB/Str/963 | 29-Mar-25 29-Mar-25 29-Mar-25 | IPC - 13 | P27 - 1st Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1172 MPSB/Sur/1015 MPSB/Str/1198 MPSB/Sur/1072 | 17-Apr-25 17-Apr-25 20-Apr-25 23-Apr-25 | IPC - 14 | P27 - 2nd Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1289 MPSB/Sur/1114 MPSB/Str/1290 MPSB/Sur/1143 | 26-Apr-25 26-Apr-25 26-Apr-25 29-Apr-25 | IPC - 14 | P27 - 3rd Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1361 MPSB/Sur/1162 MPSB/Str/1362 | 30-Apr-25 30-Apr-25 30-Apr-25 | IPC - 14 | P27 - 4th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1444 MPSB/Sur/1235 MPSB/Str/1445 MPSB/Sur/1273 | 8-May-25 8-May-25 8-May-25 13-May-25 | IPC - 15 | P27 - 5th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1532 MPSB/Sur/1314 MPSB/Str/1533 MPSB/Sur/1336 | 19-May-25 19-May-25 19-May-25 23-May-25 | IPC - 15 | P27 - 6th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1590 MPSB/Sur/1372 MPSB/Str/1591 | 28-May-25 28-May-25 28-May-25 | IPC - 15 | P27 - 7th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2 | MPSB/Str/1699 MPSB/Sur/1457 MPSB/Str/1700 MPSB/Sur/1470 | 24-Jun-25 24-Jun-25 24-Jun-25 28-Jun-25 | IPC - 16 | P27 - 8th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.7 | MPSB/Str/1924 MPSB/Sur/1610 MPSB/Str/1925 | 30-Jul-25 30-Jul-25 30-Jul-25 | IPC - 18 | P27 - 9th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/1994 MPSB/Sur/1656 MPSB/Str/1995 MPSB/Sur/1689 | 7-Aug-25 7-Aug-25 7-Aug-25 14-Aug-25 | IPC - 19 | P27 - 10th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2200 MPSB/Sur/1803 MPSB/Str/2201 MPSB/Sur/1848 | 10-Sep-25 10-Sep-25 10-Sep-25 20-Sep-25 | IPC - 20 | P27 - 11th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2348 MPSB/Sur/1886 MPSB/Str/2349 | 28-Sep-25 28-Sep-25 28-Sep-25 | IPC - 20 | P27 - 12th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2481 MPSB/Sur/1988 MPSB/Str/2482 MPSB/Sur/2042 | 15-Oct-25 15-Oct-25 15-Oct-25 25-Oct-25 | IPC - 22 | P27 - 13th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2706 MPSB/Sur/2128 MPSB/Str/2707 MPSB/Sur/2185 | 05-Nov-25 05-Nov-25 05-Nov-25 13-Nov-25 | IPC - 23 | P27 - 14th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2871 MPSB/Sur/2239 MPSB/Str/2872 MPSB/Sur/2260 | 20-Nov-25 20-Nov-25 20-Nov-25 24-Nov-25 | IPC - 23 | P27 - 15th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3003 MPSB/Sur/2316 MPSB/Str/3004 | 30-Nov-25 30-Nov-25 30-Nov-25 | IPC - 23 | P27 - 16th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3281 MPSB/Sur/2505 MPSB/Str/3325 | 26-Dec-25 26-Dec-25 29-Dec-25 | IPC - 25 | P27 - 17th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3695 MPSB/Sur/2806 MPSB/Str/3696 | 30-Jan-26 30-Jan-26 30-Jan-26 | IPC - 26 | P27 - 18th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.55 | MPSB/Str/3934 MPSB/Sur/2981 MPSB/Str/3935 | 24-Feb-26 24-Feb-26 24-Feb-26 | IPC - 27 | P27 - 19th Lift | P27
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.3 | MPSB/Str/4073 MPSB/Sur/3081 MPSB/Str/4074 | 9-Mar-26 9-Mar-26 9-Mar-26 | IPC - 29 | P27 - 20th Lift | P27
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/168 | 2024-12-03 | IPC - 08 | P28 | P28
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/190 | 2024-12-11 | IPC - 08 | P28 | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 4.32 | MPSB/Str/238 MPSB/Str/242 MPSB/Str/268 MPSB/Str/269 | 23-Dec-24 23-Dec-24 28-Dec-24 28-Dec-24 | IPC - 09 | P28 - Well Curb | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.65 | MPSB/Str/336 MPSB/Sur/271 MPSB/Str/337 MPSB/Sur/291 | 8-Jan-25 8-Jan-25 8-Jan-25 12-Jan-25 | IPC - 10 | P28 - 1st Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/374 MPSB/Sur/313 MPSB/Str/375 MPSB/Sur/326 | 17-Jan-25 17-Jan-25 17-Jan-25 20-Jan-25 | IPC - 10 | P28 - 2nd Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/433 MPSB/Sur/369 MPSB/Str/434 MPSB/Sur/401 | 27-Jan-25 27-Jan-25 27-Jan-25 31-Jan-25 | IPC - 10 | P28 - 3rd Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/472 MPSB/Sur/403 MPSB/Str/473 | 31-Jan-25 31-Jan-25 31-Jan-25 | IPC - 10 | P28 - 4th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/542 MPSB/Sur/468 MPSB/Str/561 MPSB/Sur/533 | 15-Feb-25 15-Feb-25 17-Feb-25 23-Feb-25 | IPC - 11 | P28 - 5th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/641 MPSB/Sur/563 MPSB/Str/642 MPSB/Sur/578 | 25-Feb-25 25-Feb-25 25-Feb-25 27-Feb-25 | IPC - 11 | P28 - 6th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.51 | MPSB/Str/762 MPSB/Sur/675 MPSB/Str/763 MPSB/Sur/709 | 10-Mar-25 10-Mar-25 10-Mar-25 13-Mar-25 | IPC - 13 | P28 - 7th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/830 MPSB/Sur/743 MPSB/Str/831 MPSB/Sur/767 | 19-Mar-25 19-Mar-25 19-Mar-25 23-Mar-25 | IPC - 13 | P28 - 8th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/902 MPSB/Sur/789 MPSB/Str/903 MPSB/Sur/854 | 26-Mar-25 26-Mar-25 26-Mar-25 30-Mar-25 | IPC - 13 | P28 - 9th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1123 MPSB/Sur/982 MPSB/Str/1124 MPSB/Sur/1034 | 13-Apr-25 13-Apr-25 13-Apr-25 19-Apr-25 | IPC - 14 | P28 - 10th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1327 MPSB/Sur/1144 MPSB/Str/1328 | 29-Apr-25 29-Apr-25 29-Apr-25 | IPC - 14 | P28 - 11th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1535 MPSB/Sur/1321 MPSB/Str/1536 MPSB/Sur/1341 | 20-May-25 20-May-25 20-May-25 24-May-25 | IPC - 15 | P28 - 12th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 0.5 | MPSB/Str/2008 MPSB/Sur/1666 MPSB/Str/2009 MPSB/Sur/1723 | 9-Aug-25 9-Aug-25 9-Aug-25 23-Aug-25 | IPC - 19 | P28 - 13th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/2038 MPSB/Sur/1697 MPSB/Str/2039 MPSB/Sur/1723 | 18-Aug-25 18-Aug-25 18-Aug-25 23-Aug-25 | IPC - 19 | P28 - 14th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2175 MPSB/Sur/1785 MPSB/Str/2176 MPSB/Sur/1810 | 7-Sep-25 7-Sep-25 7-Sep-25 11-Sep-25 | IPC - 20 | P28 - 15th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2292 MPSB/Sur/1856 MPSB/Str/2315 | 22-Sep-25 22-Sep-25 25-Sep-25 | IPC - 20 | P28 - 16th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2442 MPSB/Sur/1960 MPSB/Str/2460 MPSB/Sur/2001 | 10-Oct-25 10-Oct-25 13-Oct-25 17-Oct-25 | IPC - 22 | P28 - 17th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2632 MPSB/Sur/2070 MPSB/Str/2633 | 30-Oct-25 30-Oct-25 30-Oct-25 | IPC - 22 | P28 - 18th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2936 MPSB/Sur/2277 MPSB/Str/2937 | 26-Nov-25 26-Nov-25 26-Nov-25 | IPC - 23 | P28 - 19th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3179 MPSB/Sur/2432 MPSB/Str/3180 MPSB/Sur/2476 | 17-Dec-25 17-Dec-25 17-Dec-25 23-Dec-25 | IPC - 25 | P28 - 20th Lift | P28
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.27 | MPSB/Str/3486 MPSB/Sur/2648 MPSB/Str/3487 | 11-Jan-26 11-Jan-26 11-Jan-26 | IPC - 26 | P28 - 21st Lift | P28
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/241 | 2024-12-30 | IPC - 09 | P29 | P29
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/343 | 2025-01-22 | IPC - 10 | P29 | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 6.2 | MPSB/Str/500 MPSB/Str/523 MPSB/Sur/487 MPSB/Sur/493 | 7-Feb-25 10-Feb-25 17-Feb-25 18-Feb-25 | IPC - 11 | P29 - Well Curb | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2 | MPSB/Str/657 MPSB/Sur/579 MPSB/Str/658 | 27-Feb-25 27-Feb-25 27-Feb-25 | IPC - 11 | P29 - 1st Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1.15 | MPSB/Str/695 MPSB/Sur/606 MPSB/Str/696 | 28-Feb-25 28-Feb-25 28-Feb-25 | IPC - 11 | P29 - 2nd Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/784 MPSB/Sur/702 MPSB/Str/785 MPSB/Sur/724 | 12-Mar-25 12-Mar-25 12-Mar-25 16-Mar-25 | IPC - 13 | P29 - 3rd Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/848 MPSB/Sur/754 MPSB/Str/849 MPSB/Sur/779 | 21-Mar-25 21-Mar-25 21-Mar-25 25-Mar-25 | IPC - 13 | P29 - 4th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/964 MPSB/Sur/837 MPSB/Str/965 MPSB/Sur/894 | 29-Mar-25 29-Mar-25 29-Mar-25 31-Mar-25 | IPC - 13 | P29 - 5th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1121 MPSB/Sur/981 MPSB/Str/1122 MPSB/Sur/1018 | 13-Apr-25 13-Apr-25 13-Apr-25 17-Apr-25 | IPC - 14 | P29 - 6th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1207 MPSB/Sur/1051 MPSB/Str/1208 | 21-Apr-25 21-Apr-25 21-Apr-25 | IPC - 14 | P29 - 7th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/1418 MPSB/Sur/1218 MPSB/Str/1419 MPSB/Sur/1303 | 5-May-25 5-May-25 5-May-25 18-May-25 | IPC - 15 | P29 - 8th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.2 | MPSB/Str/1489 MPSB/Sur/1275 MPSB/Str/1490 MPSB/Sur/1324 | 14-May-25 14-May-25 14-May-25 20-May-25 | IPC - 15 | P29 - 9th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/1563 MPSB/Sur/1343 MPSB/Str/1564 MPSB/Sur/1362 | 24-May-25 24-May-25 24-May-25 27-May-25 | IPC - 15 | P29 - 10th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.7 | MPSB/Str/1708 MPSB/Sur/1460 MPSB/Str/1709 | 27-Jun-25 27-Jun-25 27-Jun-25 | IPC - 16 | P29 - 11th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/1760 MPSB/Sur/1490 MPSB/Str/1761 MPSB/Sur/1582 | 4-Jul-25 4-Jul-25 4-Jul-25 25-Jul-25 | IPC - 18 | P29 - 12th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2114 MPSB/Sur/1748 MPSB/Str/2115 | 30-Aug-25 30-Aug-25 30-Aug-25 | IPC - 19 | P29 - 13th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2280 MPSB/Sur/1846 MPSB/Str/2281 | 20-Sep-25 20-Sep-25 20-Sep-25 | IPC - 20 | P29 - 14th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2413 MPSB/Sur/1935 MPSB/Str/2414 MPSB/Sur/1974 | 07-Oct-25 07-Oct-25 07-Oct-25 13-Oct-25 | IPC - 22 | P29 - 15th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2586 MPSB/Sur/2049 MPSB/Str/2587 | 25-Oct-25 25-Oct-25 25-Oct-25 | IPC - 22 | P29 - 16th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2652 MPSB/Sur/2082 MPSB/Str/2653 | 31-Oct-25 31-Oct-25 31-Oct-25 | IPC - 22 | P29 - 17th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.55 | MPSB/Str/2972 MPSB/Sur/2296 MPSB/Str/2973 | 28-Nov-25 28-Nov-25 28-Nov-25 | IPC - 23 | P29 - 18th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 3.15 | MPSB/Str/3092 MPSB/Sur/2371 MPSB/Str/3123 | 9-Dec-25 9-Dec-25 12-Dec-25 | IPC - 25 | P29 - 19th Lift | P29
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 1 | MPSB/Str/3746 MPSB/Sur/2844 MPSB/Str/3747 | 2-Feb-26 2-Feb-26 2-Feb-26 | IPC - 27 | P29 - 20th Lift | P29
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 2.115 | MPSB/Str/5175 MPSB/Sur/3781 MPSB/Str/5176 | 21-Jul-26 21-Jul-26 21-Jul-26 | IPC - 34 | P29 - Lower Pylon - 1st Lift | P29
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 4 | MPSB/Str/5230 MPSB/Sur/3804 MPSB/Str/5231 | 30-Jul-26 30-Jul-26 30-Jul-26 | IPC - 34 | P29 - Lower Pylon - 2nd Lift | P29
403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 0.63 | MPSB/Str/5127 MPSB/Sur/3752 MPSB/Str/5128 | 13-Jul-26 12-Jul-26 13-Jul-26 | IPC - 34 | P29 - Lower Pylon - Starter | P29
401.b | Ground preparation and placing of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/Sur/2068 | 2025-10-29 | IPC - 22 | P30 | P30
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/2110 | 2025-11-01 | IPC - 23 | P30 | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 4.48 | MPSB/Str/2757 MPSB/Sur/2164 MPSB/Str/2758 MPSB/Sur/2225 | 10-Nov-25 10-Nov-25 10-Nov-25 19-Nov-25 | IPC - 23 | P30 - Well Curb | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2901 MPSB/Sur/2251 MPSB/Str/2902 MPSB/Sur/2275 | 23-Nov-25 23-Nov-25 23-Nov-25 26-Nov-25 | IPC - 23 | P30 - 1st Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2970 MPSB/Sur/2295 MPSB/Str/2971 | 28-Nov-25 28-Nov-25 28-Nov-25 | IPC - 23 | P30 - 2nd Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/2997 MPSB/Sur/2313 MPSB/Str/2998 | 30-Nov-25 30-Nov-25 30-Nov-25 | IPC - 23 | P30 - 3rd Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3069 MPSB/Sur/2353 MPSB/Str/3070 MPSB/Sur/2373 | 6-Dec-25 6-Dec-25 6-Dec-25 9-Dec-25 | IPC - 25 | P30 - 4th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3099 MPSB/Sur/2382 MPSB/Str/3100 | 10-Dec-25 10-Dec-25 10-Dec-25 | IPC - 25 | P30 - 5th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3152 MPSB/Sur/2418 MPSB/Str/3153 MPSB/Sur/2439 | 15-Dec-25 15-Dec-25 15-Dec-25 18-Dec-25 | IPC - 25 | P30 - 6th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3201 MPSB/Sur/2448 MPSB/Str/3202 MPSB/Sur/2469 | 19-Dec-25 19-Dec-25 19-Dec-25 22-Dec-25 | IPC - 25 | P30 - 7th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 0.5 | MPSB/Str/3307 MPSB/Sur/2526 MPSB/Str/3308 | 28-Dec-25 28-Dec-25 28-Dec-25 | IPC - 25 | P30 - 8th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.8 | MPSB/Str/3354 MPSB/Sur/2555 MPSB/Str/3355 | 30-Dec-25 30-Dec-25 30-Dec-25 | IPC - 25 | P30 - 9th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3510 MPSB/Sur/2669 MPSB/Str/3511 MPSB/Sur/2700 | 13-Jan-26 13-Jan-26 13-Jan-26 17-Jan-26 | IPC - 26 | P30 - 10th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3589 MPSB/Sur/2726 MPSB/Str/3590 MPSB/Sur/2744 | 20-Jan-26 20-Jan-26 20-Jan-26 22-Jan-26 | IPC - 26 | P30 - 11th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3640 MPSB/Sur/2757 MPSB/Str/3641 MPSB/Sur/2774 | 24-Jan-26 24-Jan-26 24-Jan-26 25-Jan-26 | IPC - 26 | P30 - 12th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3653 MPSB/Sur/2778 MPSB/Str/3654 MPSB/Sur/2801 | 27-Jan-26 27-Jan-26 27-Jan-26 30-Jan-26 | IPC - 26 | P30 - 13th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.5 | MPSB/Str/3732 MPSB/Sur/2826 MPSB/Str/3733 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | P30 - 14th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3834 MPSB/Sur/2914 MPSB/Str/3835 MPSB/Sur/2936 | 11-Feb-26 11-Feb-26 11-Feb-26 15-Feb-26 | IPC - 27 | P30 - 15th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3955 MPSB/Sur/3008 MPSB/Str/3956 | 26-Feb-26 26-Feb-26 26-Feb-26 | IPC - 27 | P30 - 16th Lift | P30
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4567 MPSB/Sur/3406 MPSB/Str/4568 | 30-Apr-26 30-Apr-26 30-Apr-26 | IPC - 30 | P30 - 17th Lift | P30
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/80 | 2024-11-04 | IPC - 08 | P6 | P6
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/115 | 2024-11-21 | IPC - 08 | P6 | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 4.32 | MPSB/Str/148 MPSB/Sur/157 MPSB/Str/164 MPSB/Sur/179 MPSB/Str/184 | 28-Nov-24 30-Nov-24 30-Nov-24 6-Dec-24 6-Dec-24 | IPC - 08 | P6 - Well Curb | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.65 | MPSB/Str/207 MPSB/Str/208 MPSB/Str/221 | 14-Dec-24 14-Dec-24 18-Dec-24 | IPC - 09 | P6 - 1st Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Sur/211 MPSB/Str/233 MPSB/Str/234 MPSB/Str/247 | 22-Dec-24 22-Dec-24 22-Dec-24 25-Dec-24 | IPC - 09 | P6 - 2nd Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Sur/295 MPSB/Str/295 MPSB/Sur/243 | 30-Dec-24 30-Dec-24 31-Dec-24 | IPC - 09 | P6 - 3rd Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/297 MPSB/Str/333 MPSB/Sur/274 MPSB/Sur/290 | 31-Dec-24 7-Jan-25 7-Jan-25 11-Jan-25 | IPC - 10 | P6 - 4th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/376 MPSB/Str/377 MPSB/Sur/362 | 17-Jan-25 17-Jan-25 26-Jan-25 | IPC - 10 | P6 - 5th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/410 MPSB/Sur/350 MPSB/Str/416 MPSB/Sur/393 | 22-Jan-25 23-Jan-25 23-Jan-25 31-Jan-25 | IPC - 10 | P6 - 6th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/547 MPSB/Sur/459 MPSB/Str/548 MPSB/Sur/507 | 15-Feb-25 12-Feb-25 15-Feb-25 19-Feb-25 | IPC - 11 | P6 - 7th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 0.5 | MPSB/Str/654 MPSB/Sur/570 MPSB/Str/655 | 27-Feb-25 27-Feb-25 27-Feb-25 | IPC - 11 | P6 - 8th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/712 MPSB/Sur/627 MPSB/Str/713 | 28-Feb-25 28-Feb-25 28-Feb-25 | IPC - 11 | P6 - 9th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.66 | MPSB/Str/1016 MPSB/Sur/843 MPSB/Str/1017 | 31-Mar-25 31-Mar-25 31-Mar-25 | IPC - 13 | P6 - 10th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1115 MPSB/Sur/978 MPSB/Str/1116 | 12-Apr-25 12-Apr-25 12-Apr-25 | IPC - 14 | P6 - 11th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1196 MPSB/Sur/1040 MPSB/Str/1197 MPSB/Sur/1091 | 19-Apr-25 19-Apr-25 19-Apr-25 24-Apr-25 | IPC - 14 | P6 - 12th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1521 MPSB/Sur/1307 MPSB/Str/1522 | 19-May-25 19-May-25 19-May-25 | IPC - 15 | P6 - 13th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.57 | MPSB/Str/1582 MPSB/Sur/1364 MPSB/Str/1583 | 27-May-25 27-May-25 27-May-25 | IPC - 15 | P6 - 14th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1705 MPSB/Sur/1458 MPSB/Str/1706 | 26-Jun-25 26-Jun-25 26-Jun-25 | IPC - 16 | P6 - 15th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1732 MPSB/Sur/1473 MPSB/Str/1733 | 29-Jun-25 29-Jun-25 29-Jun-25 | IPC - 16 | P6 - 16th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1902 MPSB/Sur/1594 MPSB/Str/1903 | 27-Jul-25 27-Jul-25 27-Jul-25 | IPC - 18 | P6 - 17th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.4 | MPSB/Str/2010 MPSB/Sur/1668 MPSB/Str/2011 MPSB/Sur/1704 | 9-Aug-25 9-Aug-25 9-Aug-25 20-Aug-25 | IPC - 19 | P6 - 18th Lift | P6
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.95 | MPSB/Str/2321 MPSB/Sur/1871 MPSB/Str/2322 | 25-Sep-25 25-Sep-25 25-Sep-25 | IPC - 20 | P6 - 19th Lift | P6
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/120 | 2024-11-22 | IPC - 08 | P7 | P7
401.c | Shuttering and Scaffolding | Nos. | Sualkuchi | 1 | MPSB/Sur/204 | 2024-12-19 | IPC - 09 | P7 | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 6.04 | MPSB/Str/299 MPSB/Str/334 MPSB/Sur/316 MPSB/Sur/317 | 31-Dec-24 8-Jan-25 17-Jan-25 17-Jan-25 | IPC - 10 | P7 - Well Curb | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 3.31 | MPSB/Str/450 MPSB/Str/467 MPSB/Sur/390 | 28-Jan-25 30-Jan-25 30-Jan-25 | IPC - 10 | P7 - 1st Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/585 MPSB/Sur/518 MPSB/Str/586 | 21-Feb-25 21-Feb-25 21-Feb-25 | IPC - 11 | P7 - 2nd Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.4 | MPSB/Str/791 MPSB/Str/792 MPSB/Sur/703 MPSB/Sur/727 | 12-Mar-25 12-Mar-25 12-Mar-25 17-Mar-25 | IPC - 13 | P7 - 3rd Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/932 MPSB/Str/933 MPSB/Sur/809 | 27-Mar-25 27-Mar-25 27-Mar-25 | IPC - 13 | P7 - 4th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.6 | MPSB/Str/1117 MPSB/Sur/979 MPSB/Str/1118 | 12-Apr-25 12-Apr-25 12-Apr-25 | IPC - 14 | P7 - 5th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1201 MPSB/Sur/1044 MPSB/Str/1202 | 21-Apr-25 21-Apr-25 21-Apr-25 | IPC - 14 | P7 - 6th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1504 MPSB/Sur/1294 MPSB/Str/1505 MPSB/Sur/1384 | 16-May-25 16-May-25 16-May-25 29-May-25 | IPC - 15 | P7 - 7th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1644 MPSB/Sur/1409 MPSB/Str/1645 MPSB/Sur/1434 | 9-Jun-25 9-Jun-25 9-Jun-25 17-Jun-25 | IPC - 16 | P7 - 8th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.7 | MPSB/Str/1803 MPSB/Sur/1517 MPSB/Str/1804 | 12-Jul-25 12-Jul-25 12-Jul-25 | IPC - 18 | P7 - 9th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Sualkuchi | 2.95 | MPSB/Str/1853 MPSB/Sur/1556 MPSB/Str/1854 | 21-Jul-25 21-Jul-25 21-Jul-25 | IPC - 18 | P7 - 10th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2073 MPSB/Sur/1721 MPSB/Str/2074 | 23-Aug-25 23-Aug-25 23-Aug-25 | IPC - 19 | P7 - 11th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2126 MPSB/Sur/1757 MPSB/Str/2127 | 31-Aug-25 31-Aug-25 31-Aug-25 | IPC - 20 | P7 - 12th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2229 MPSB/Sur/1822 MPSB/Str/2230 MPSB/Sur/1869 | 13-Sep-25 13-Sep-25 13-Sep-25 24-Sep-25 | IPC - 20 | P7 - 13th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2461 MPSB/Sur/1975 MPSB/Str/2462 | 13-Oct-25 13-Oct-25 13-Oct-25 | IPC - 22 | P7 - 14th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2569 MPSB/Sur/2037 MPSB/Str/2570 | 24-Oct-25 24-Oct-25 24-Oct-25 | IPC - 22 | P7 - 15th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2867 MPSB/Sur/2232 MPSB/Str/2868 | 20-Nov-25 20-Nov-25 20-Nov-25 | IPC - 23 | P7 - 16th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2938 MPSB/Sur/2278 MPSB/Str/2939 | 26-Nov-25 26-Nov-25 26-Nov-25 | IPC - 23 | P7 - 17th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3054 MPSB/Sur/2346 MPSB/Str/3055 MPSB/Sur/2522 | 5-Dec-25 5-Dec-25 5-Dec-25 28-Dec-25 | IPC - 25 | P7 - 18th Lift | P7
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.55 | MPSB/Str/3820 MPSB/Sur/2902 MPSB/Str/3821 | 10-Feb-26 10-Feb-26 10-Feb-26 | IPC - 27 | P7 - 19th Lift | P7
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 4 | MPSB/Str/4927 MPSB/Sur/3675 MPSB/Str/4976 | 17-Jun-26 21-Jun-26 21-Jun-26 | IPC - 33 | P7 - Lower Pylon - 1st Lift | P7
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 2 | MPSB/Str/5107 MPSB/Sur/3738 MPSB/Str/5108 | 9-Jul-26 9-Jul-26 9-Jul-26 | IPC - 34 | P7 - Lower Pylon - 2nd Lift | P7
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 0.525 | MPSB/Str/4886 MPSB/Sur/3625 MPSB/Str/4887 | 10-Jun-26 10-Jun-26 10-Jun-26 | IPC - 33 | P7 - Lower Pylon - Starter | P7
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/189 | 2024-12-11 | IPC - 09 | P8 | P8
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/207 | 2024-12-20 | IPC - 09 | P8 | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 4.32 | MPSB/Str/261 MPSB/Str/271 MPSB/Sur/245 MPSB/Sur/246 | 27-Dec-24 29-Dec-24 31-Dec-24 31-Dec-24 | IPC - 09 | P8 - Well Curb | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.65 | MPSB/Str/335 MPSB/Str/352 MPSB/Sur/288 MPSB/Sur/300 | 8-Jan-25 11-Jan-25 11-Jan-25 14-Jan-25 | IPC - 10 | P8 - 1st Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/392 MPSB/Sur/345 MPSB/Str/409 MPSB/Sur/394 | 20-Jan-25 22-Jan-25 22-Jan-25 31-Jan-25 | IPC - 10 | P8 - 2nd Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/432 MPSB/Sur/379 MPSB/Str/449 MPSB/Sur/395 | 27-Jan-25 28-Jan-25 28-Jan-25 31-Jan-25 | IPC - 10 | P8 - 3rd Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/509 MPSB/Sur/455 MPSB/Str/525 MPSB/Sur/537 | 9-Feb-25 11-Feb-25 11-Feb-25 23-Feb-25 | IPC - 11 | P8 - 4th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/575 MPSB/Sur/506 MPSB/Str/576 MPSB/Sur/554 | 19-Feb-25 19-Feb-25 19-Feb-25 25-Feb-25 | IPC - 11 | P8 - 5th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/702 MPSB/Sur/610 MPSB/Str/703 | 28-Feb-25 28-Feb-25 28-Feb-25 | IPC - 11 | P8 - 6th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.51 | MPSB/Str/825 MPSB/Str/826 MPSB/Sur/737 | 18-Mar-25 18-Mar-25 18-Mar-25 | IPC - 13 | P8 - 7th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/987 MPSB/Str/988 MPSB/Sur/856 | 30-Mar-25 30-Mar-25 30-Mar-25 | IPC - 13 | P8 - 8th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1276 MPSB/Sur/1104 MPSB/Str/1277 | 26-Apr-25 26-Apr-25 26-Apr-25 | IPC - 14 | P8 - 9th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.25 | MPSB/Str/1380 MPSB/Sur/1176 MPSB/Str/1381 | 30-Apr-25 30-Apr-25 30-Apr-25 | IPC - 14 | P8 - 10th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.75 | MPSB/Str/1554 MPSB/Sur/1334 MPSB/Str/1555 MPSB/Sur/1383 | 23-May-25 23-May-25 23-May-25 29-May-25 | IPC - 15 | P8 - 11th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1669 MPSB/Sur/1427 MPSB/Str/1670 | 16-Jun-25 16-Jun-25 16-Jun-25 | IPC - 16 | P8 - 12th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 3.15 | MPSB/Str/1765 MPSB/Sur/1494 MPSB/Str/1766 MPSB/Sur/1562 | 5-Jul-25 5-Jul-25 5-Jul-25 22-Jul-25 | IPC - 18 | P8 - 13th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1805 MPSB/Sur/1518 MPSB/Str/1806 MPSB/Sur/1562 | 12-Jul-25 12-Jul-25 12-Jul-25 22-Jul-25 | IPC - 18 | P8 - 14th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1968 MPSB/Sur/1642 MPSB/Str/1969 MPSB/Sur/1710 | 3-Aug-25 3-Aug-25 3-Aug-25 21-Aug-25 | IPC - 19 | P8 - 15th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2047 MPSB/Sur/1700 MPSB/Str/2048 MPSB/Sur/1710 | 18-Aug-25 18-Aug-25 18-Aug-25 21-Aug-25 | IPC - 19 | P8 - 16th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2190 MPSB/Sur/1796 MPSB/Str/2191 | 9-Sep-25 9-Sep-25 9-Sep-25 | IPC - 20 | P8 - 17th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2286 MPSB/Sur/1853 MPSB/Str/2287 | 22-Sep-25 22-Sep-25 22-Sep-25 | IPC - 20 | P8 - 18th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2360 MPSB/Sur/1891 MPSB/Str/2361 | 30-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | P8 - 19th Lift | P8
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.42 | MPSB/Str/2578 MPSB/Sur/2046 MPSB/Str/2579 | 25-Oct-25 25-Oct-25 25-Oct-25 | IPC - 22 | P8 - 20th Lift | P8
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 4 | MPSB/Str/4337 MPSB/Sur/3243 MPSB/Str/4328 | 5-Apr-26 5-Apr-26 5-Apr-26 | IPC - 30 | P8 - Lower Pylon - 1st Lift | P8
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 2 | MPSB/Str/4407 MPSB/Sur/3303 MPSB/Str/4408 | 15-Apr-26 15-Apr-26 15-Apr-26 | IPC - 30 | P8 - Lower Pylon - 2nd Lift | P8
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 2 | MPSB/Str/4514 MPSB/Sur/3370 MPSB/Str/4515 | 28-Apr-26 28-Apr-26 28-Apr-26 | IPC - 30 | P8 - Lower Pylon - 3rd Lift | P8
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 3.65 | MPSB/Str/4690 MPSB/Sur/3484 MPSB/Str/4691 | 15-May-26 15-May-26 15-May-26 | IPC - 31 | P8 - Lower Pylon - 4th Lift | P8
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 0.67 | MPSB/Str/4793 MPSB/Sur/3556 MPSB/Str/4794 | 27-May-26 27-May-26 27-May-26 | IPC - 31 | P8 - Lower Pylon - 5th Lift | P8
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 4.45 | MPSB/Str/4997 MPSB/Sur/3689 MPSB/Str/4998 | 24-Jun-26 24-Jun-26 24-Jun-26 | IPC - 33 | P8 - Lower Pylon - 6th Lift | P8
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 4.329 | MPSB/Str/5150 MPSB/Sur/3767 MPSB/Str/5151 | 15-Jul-26 15-Jul-26 15-Jul-26 | IPC - 34 | P8 - Lower Pylon - 7th Lift | P8
403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 0.525 | MPSB/Str/4310 MPSB/Sur/3233 MPSB/Str/4311 | 1-Apr-26 1-Apr-26 1-Apr-26 | IPC - 30 | P8 - Lower Pylon - Starter | P8
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | 1 | MPSB/Sur/216 | 2024-12-25 | IPC - 09 | P9 | P9
401.c | Shuttering and Scaffolding | Nos. | Palashbari | 1 | MPSB/Sur/289 | 2025-01-11 | IPC - 11 | P9 | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 6.04 | MPSB/Str/408 MPSB/Str/424 MPSB/Sur/396 MPSB/Sur/397 | 22-Jan-25 24-Jan-25 31-Jan-25 31-Jan-25 | IPC - 10 | P9 - Well Curb | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2 | MPSB/Str/538 MPSB/Sur/471 MPSB/Str/549 MPSB/Sur/534 | 14-Feb-25 15-Feb-25 15-Feb-25 23-Feb-25 | IPC - 11 | P9 - 1st Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.05 | MPSB/Str/563 MPSB/Sur/488 MPSB/Str/564 MPSB/Sur/535 | 17-Feb-25 17-Feb-25 17-Feb-25 23-Feb-25 | IPC - 11 | P9 - 2nd Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/704 MPSB/Sur/613 MPSB/Str/705 | 28-Feb-25 28-Feb-25 28-Feb-25 | IPC - 11 | P9 - 3rd Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.61 | MPSB/Str/827 MPSB/Str/828 MPSB/Sur/738 MPSB/Sur/855 | 18-Mar-25 18-Mar-25 18-Mar-25 30-Mar-25 | IPC - 13 | P9 - 4th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1048 MPSB/Sur/919 MPSB/Str/1049 MPSB/Sur/969 | 5-Apr-25 5-Apr-25 5-Apr-25 11-Apr-25 | IPC - 14 | P9 - 5th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1155 MPSB/Sur/1004 MPSB/Str/1156 | 16-Apr-25 16-Apr-25 16-Apr-25 | IPC - 14 | P9 - 6th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.6 | MPSB/Str/1274 MPSB/Sur/1103 MPSB/Str/1275 | 26-Apr-25 26-Apr-25 26-Apr-25 | IPC - 14 | P9 - 7th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1386 MPSB/Sur/1179 MPSB/Str/1387 | 30-Apr-25 30-Apr-25 30-Apr-25 | IPC - 14 | P9 - 8th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/1667 MPSB/Sur/1426 MPSB/Str/1668 | 16-Jun-25 16-Jun-25 16-Jun-25 | IPC - 16 | P9 - 9th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.7 | MPSB/Str/1976 MPSB/Sur/1648 MPSB/Str/1977 MPSB/Sur/1706 | 5-Aug-25 5-Aug-25 5-Aug-25 20-Aug-25 | IPC - 19 | P9 - 10th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/2012 MPSB/Sur/1669 MPSB/Str/2013 MPSB/Sur/1717 | 9-Aug-25 9-Aug-25 9-Aug-25 22-Aug-25 | IPC - 19 | P9 - 11th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2166 MPSB/Sur/1782 MPSB/Str/2167 | 6-Sep-25 6-Sep-25 6-Sep-25 | IPC - 20 | P9 - 12th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2288 MPSB/Sur/1854 MPSB/Str/2289 | 22-Sep-25 22-Sep-25 22-Sep-25 | IPC - 20 | P9 - 13th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2378 MPSB/Sur/1907 MPSB/Str/2379 | 30-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | P9 - 14th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2664 MPSB/Sur/2096 MPSB/Str/2665 | 31-Oct-25 31-Oct-25 31-Oct-25 | IPC - 22 | P9 - 15th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/2777 MPSB/Sur/2176 MPSB/Str/2778 | 12-Nov-25 12-Nov-25 12-Nov-25 | IPC - 23 | P9 - 16th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.3 | MPSB/Str/3165 MPSB/Sur/2424 MPSB/Str/3166 | 16-Dec-25 16-Dec-25 16-Dec-25 | IPC - 25 | P9 - 17th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.7 | MPSB/Str/3246 MPSB/Sur/2481 MPSB/Str/3247 | 24-Dec-25 24-Dec-25 24-Dec-25 | IPC - 25 | P9 - 18th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/3379 MPSB/Sur/2571 MPSB/Str/3380 | 31-Dec-25 31-Dec-25 31-Dec-25 | IPC - 25 | P9 - 19th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.8 | MPSB/Str/3624 MPSB/Sur/2750 MPSB/Str/3625 | 23-Jan-26 23-Jan-26 23-Jan-26 | IPC - 26 | P9 - 20th Lift | P9
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | -0.05 |  |  | IPC - 27 | P9 - 20th Lift | P9
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
Period of bill : 1st Jul'26 to 31st Jul'26
Schedule 4 - Main Extradosed Bridge Works | [7 empty] | IPC - 34
Measurement Sheet
Item No. | Item Description | UoM | Location | Executed Quantity | RFI No. / Letter No. / Period | Date | Bill No. | Remarks
401 | On ground clearance, preparatory works for start of foundation works such as cutting edge, shutters, scaffoldings etc
401.a | Fabrication of Cutting Edge | Nos. | Palashbari | 14 | MPSB/MB/1 | 2024-09-30 | IPC - 05 | Circular - 8 Nos. Double D - 6 Nos.
401.a | Fabrication of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/MB/2 | 2024-09-30 | IPC - 05 | Double D - 1 No.
401.a | Fabrication of Cutting Edge | Nos. | Sualkuchi | 1 | MPSB/MB/3 | 2024-10-28 | IPC - 07 | Double D - 1 No.
401.a | Fabrication of Cutting Edge | Nos. | Palashbari | 9 | MPSB/MB/4 | 2024-10-31 | IPC - 07 | Circular - 5 Nos. Double D - 4 Nos.
401.a | Fabrication of Cutting Edge | Nos. | Palashbari | -2 |  |  | IPC - 26 | Toppling of P12 & P14
401.a | Fabrication of Cutting Edge | Nos. | Palashbari | 1 | MPSB/MB/457 | 2025-12-06 | IPC - 26 | P14(N)
401.a | Fabrication of Cutting Edge | Nos. | Palashbari | 1 | MPSB/MB/0660 | 2026-01-07 | IPC - 33 | P12(A)
401.a | Fabrication of Cutting Edge | Nos. | Palashbari | 1 | MPSB/MB/1794 | 2026-05-18 | IPC - 33 | P12
| Cumulative paid upto this Bill | Nos. |  | 26
| Paid upto previous Bill | Nos. |  | 26
| To be paid in this Bill | Nos. |  | 0
401.b | Ground preparation and placing of Cutting Edge | Nos. | Palashbari | -2 |  |  | IPC - 26 | Toppling of P12 & P14
| Cumulative paid upto this Bill | Nos. |  | 87.75
| Paid upto previous Bill | Nos. |  | 25
| To be paid in this Bill | Nos. |  | 62.75
401.c | Shuttering and Scaffolding | Nos. | Palashbari | -2 |  |  | IPC - 26 | Toppling of P12 & P14
| Cumulative paid upto this Bill | Nos. |  | 249.5
| Paid upto previous Bill | Nos. |  | 25
| To be paid in this Bill | Nos. |  | 224.5
402 | Construction of foundation
| Cumulative paid upto this Bill | Rmt |  | 1952.994
| Paid upto previous Bill | Rmt |  | 1289.47
| To be paid in this Bill | Rmt |  | 663.524
402.b | Well Bottom Plugging | Nos. | Sualkuchi | 1 | MPSB/Str/3754 | 2026-02-03 | IPC - 27 | P26 - Bottom Plugging |  | Well Plugging
402.b | Well Bottom Plugging | Nos. | Palashbari | 1 | MPSB/Str/3781 | 2026-02-06 | IPC - 27 | P8 - Bottom Plugging
402.b | Well Bottom Plugging | Nos. | Sualkuchi | 1 | MPSB/Str/3952 | 2026-02-25 | IPC - 27 | P22 - Bottom Plugging
402.b | Well Bottom Plugging | Nos. | Sualkuchi | 1 | MPSB/Str/4164 | 2026-03-20 | IPC - 29 | P20 - Bottom Plugging
402.b | Well Bottom Plugging | Nos. | Sualkuchi | 1 | MPSB/Str/4231 | 2026-03-28 | IPC - 29 | P19 - Bottom Plugging
402.b | Well Bottom Plugging | Nos. | Sualkuchi | 1 | MPSB/Str/4435 | 2026-04-18 | IPC - 30 | P25 - Bottom Plugging
402.b | Well Bottom Plugging | Nos. | Palashbari | 1 | MPSB/Str/4565 | 2026-04-30 | IPC - 30 | P7 - Bottom Plugging
402.b | Well Bottom Plugging | Nos. | Sualkuchi | 1 | MPSB/Str/4803 | 2026-05-28 | IPC - 31 | P29 - Bottom Plugging
402.b | Well Bottom Plugging | Nos. | Sualkuchi | 1 | MPSB/Str/4975 | 2026-06-21 | IPC - 33 | P24 - Bottom Plugging
402.b | Well Bottom Plugging | Nos. | Sualkuchi | 1 | MPSB/Str/5073 | 2026-06-30 | IPC - 33 | P23 - Bottom Plugging
| Cumulative paid upto this Bill | Nos. |  | 10
| Paid upto previous Bill | Nos. |  | 10
| To be paid in this Bill | Nos. |  | 0
402.c | Well Cap | Nos. | Sualkuchi | 1 | MPSB/Str/3951 | 2026-02-25 | IPC - 27 | P26 - Well Cap |  | Well Cap Reinforcement Well Cap Concreting
402.c | Well Cap | Nos. | Palashbari | 1 | MPSB/Str/4033 MPSB/Str/4034 | 28-Feb-26 28-Feb-26 | IPC - 27 | P8 - Well Cap
402.c | Well Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/3119 MPSB/Str/4108 | 14-Mar-26 14-Mar-26 | IPC - 29 | P22 - Well Cap
402.c | Well Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/3195 MPSB/Str/4237 | 29-Mar-26 29-Mar-26 | IPC - 29 | P20 - Well Cap
402.c | Well Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/3342 MPSB/Str/4470 | 23-Apr-26 23-Apr-26 | IPC - 30 | P19 - Well Cap
402.c | Well Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/3497 MPSB/Str/4709 | 18-May-26 18-May-26 | IPC - 31 | P25 - Well Cap
402.c | Well Cap | Nos. | Palashbari | 1 | MPSB/Sur/3584 MPSB/Str/4837 | 31-May-26 31-May-26 | IPC - 31 | P7 - Well Cap
402.c | Well Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/3700 MPSB/Str/5029 | 29-Jun-26 29-Jun-26 | IPC - 33 | P29 - Well Cap
402.c | Well Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/3801 MPSB/Str/5219 | 29-Jul-26 29-Jul-26 | IPC - 34 | P24 - Well Cap
| Cumulative paid upto this Bill | Nos. |  | 9
| Paid upto previous Bill | Nos. |  | 8
| To be paid in this Bill | Nos. |  | 1
403 | Construction of sub- structure; abutment/ piers / lower pylon
| Cumulative paid upto this Bill | Rmt |  | 57
| Paid upto previous Bill | Rmt |  | 56.97
| To be paid in this Bill | Rmt |  | 0.03
Precast - Box girder segments
406 | Construction of PSC Box girders in casting yard
406.a | Casting of PSC Box girder segments in casting yard
| Cumulative paid upto this Bill | Nos. |  | 5777.302
| Paid upto previous Bill | Nos. |  | 452
| To be paid in this Bill | Nos. |  | 5325.302
407 | Procurement, testing and supply of post tensioning material to site
407.c | Post Tensioning Material consumed during casting of segments
| Cumulative paid upto this Bill | Nos. |  | 5777.302
| Paid upto previous Bill | Nos. |  | 452
| To be paid in this Bill | Nos. |  | 5325.302
408 | Procurement, testing and supply of Stay Cables to site
408.a | Supply of stay cable material | MT |  | 450.478 | As per Annexures |  | IPC - 29
408.a | Supply of stay cable material | MT |  | 354.343 | As per Annexures |  | IPC - 31
| Cumulative paid upto this Bill | MT |  | 804.821
| Paid upto previous Bill | MT |  | 804.821
| To be paid in this Bill | MT |  | 0
408.b | Testing of Material | MT |  | 450.478 | MPSB/L&T/TIIC/2026/1543 | 2026-03-31 | IPC - 30
408.b | Testing of Material | MT |  | 354.343 | As per Annexures |  | IPC - 34
| Cumulative paid upto this Bill | MT |  | 804.821
| Paid upto previous Bill | MT |  | 450.478
| To be paid in this Bill | MT |  | 354.343
408.c | Stay Cable Material consumed during casting of each stay cable segment
| Cumulative paid upto this Bill | Nos. |  | 0
| Paid upto previous Bill | Nos. |  | 174
| To be paid in this Bill | Nos. |  | -174
62.8983

## Well Cal.
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
Well Reconciliation Statement
Well ID | Well Depth | Length Executed | Lift | IPC - 08 | IPC - 09 | IPC - 10 | IPC - 11 | IPC - 13 | IPC - 14 | IPC - 15 | IPC - 16 | IPC - 18 | IPC - 19 | IPC - 20 | IPC - 22 | IPC - 23 | IPC - 25 | IPC - 26 | IPC - 27 | IPC - 29 | IPC - 30 | IPC - 31 | IPC - 33 | IPC - 34 | Total | Check | Component | Height |  |  |  |  | No. of Locations | Total Length | Locations
[28 empty] | Well Curb | Below Transition | Transition | Above Transition | Total
P4 | 50.55 | 48.7 | P4 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.7 | 0
|  |  | P4 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Middle Pylon | 4.32 | 30.53 | 2.7 | 16.5 | 54.05 | 6 | 324.3 | P8 / P12 / P16 / P20 / P24 / P28
|  |  | P4 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | EJ Pier | 4.32 | 17.98 | 2.7 | 25.55 | 50.55 | 7 | 353.85 | P6 / P10 / P14 / P18 / P22 / P26 / P30
|  |  | P4 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Outer Pylon | 6.04 | 19.76 | 4.8 | 23.45 | 54.05 | 12 | 648.6 | P7 / P9 / P11 / P13 / P15 / P17 / P19 / P21 / P23 / P25 / P27 / P29
|  |  | P4 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P4 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P4 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Package 1 | P10 to P18
|  |  | P4 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Package 2 | P19 to P26
|  |  | P4 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Package 3 | P6 to P9
|  |  | P4 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Package 4 | P27 to P30
|  |  | P4 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P4 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P4 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P4 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P4 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P4 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P4 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
|  |  | P4 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
|  |  | P4 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.05
P5 | 50.55 | 50.55 | P5 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.55 | 0
|  |  | P5 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P5 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P5 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0
|  |  | P5 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
|  |  | P5 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.77 | 0
Total | 101.1 | 99.25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.96 | 20 | 18.3 | 13.17 | 10 | 7.5 | 5 | 0 | 2.5 | 2.5 | 7.5 | 2.77 | 1.05 | 99.25 | 0
[27 empty] | Well ID | Scope | Executed | Balance
P6 | 50.55 | 0 | P6 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P4 | 50.55 | 48.7 | 1.85
|  |  | P6 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P5 | 50.55 | 50.55 | 0
|  |  | P6 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P6 | 50.55 | 0 | 50.55
|  |  | P6 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P7 | 54.05 | 0 | 54.05
|  |  | P6 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P8 | 54.05 | 0 | 54.05
|  |  | P6 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P9 | 54.05 | 0 | 54.05
|  |  | P6 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P10 | 50.55 | 50.55 | 0
|  |  | P6 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P11 | 54.05 | 44.2 | 9.85
|  |  | P6 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P12(N) | 54.05 | 0 | 54.05
|  |  | P6 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P12(A) | 54.05 | 47.13 | 6.92
|  |  | P6 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P13 | 54.05 | 41.4 | 12.65
|  |  | P6 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P14(N) | 50.55 | 48.1 | 2.45
|  |  | P6 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P15 | 54.05 | 52.96 | 1.09
|  |  | P6 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P16 | 54.05 | 0 | 54.05
|  |  | P6 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P17 | 54.05 | 0 | 54.05
|  |  | P6 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P18 | 50.55 | 0 | 50.55
|  |  | P6 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P19 | 54.05 | 0 | 54.05
|  |  | P6 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P20 | 54.05 | 0 | 54.05 |  | 54.05
|  |  | P6 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P21 | 54.05 | 0 | 54.05
|  |  | P6 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P22 | 51.55 | 0 | 51.55
[27 empty] | P23 | 54.05 | 0 | 54.05
P7 | 54.05 | 0 | P7 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P24 | 54.05 | 0 | 54.05
|  |  | P7 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P25 | 54.05 | 0 | 54.05
|  |  | P7 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P26 | 50.55 | 0 | 50.55
|  |  | P7 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P27 | 54.05 | 0 | 54.05
|  |  | P7 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P28 | 54.05 | 0 | 54.05
|  |  | P7 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P29 | 54.05 | 0 | 54.05
|  |  | P7 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P30 | 50.55 | 0 | 50.55
|  |  | P7 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P7 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P7 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P7 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P7 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P7 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P7 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P7 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P11 - 6th Lift
|  |  | P7 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P11 - 7th Lift
|  |  | P7 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P11 - 8th Lift
|  |  | P7 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P13- 5th Lift
|  |  | P7 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P13- 6th Lift
|  |  | P7 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P13- 7th Lift
P13- 8th Lift
P8 | 54.05 | 0 | P8 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | P14(N) - 10th Lift
|  |  | P8 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P14(N) - 11th Lift
|  |  | P8 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P14(N) - 9th Lift
|  |  | P8 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P15- 18th Lift
|  |  | P8 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P21 - 20th Lift
|  |  | P8 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P27 - 20th Lift
|  |  | P8 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P9 | 54.05 | 0 | P9 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P10 | 50.55 | 52.55 | P10 - Well Curb | 0 | 0 | 0 | 4.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.55 | 2
|  |  | P10 - 1st Lift | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 2nd Lift | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 3rd Lift | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 4th Lift | 0 | 0 | 0 | 0 | 2.615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 5th Lift | 0 | 0 | 0 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 6th Lift | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0.545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 2.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P11 | 54.05 | 46.2 | P11 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 44.2 | 2
|  |  | P11 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P11 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
|  |  | P11 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
|  |  | P11 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
|  |  | P11 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
|  |  | P11 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P11 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P11 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P11 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7 | 0 | 0 | 0
|  |  | P11 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 0 | 0
|  |  | P11 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0
|  |  | P11 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
|  |  | P11 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
|  |  | P11 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0
|  |  | P11 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0
P12 |  | 11.575 | P12 - Well Curb | 0 | 0 | 0 | 4.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 9.575 | 2
|  |  | P12 - 1st Lift | 0 | 0 | 0 | 0 | 2.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12 - 2nd Lift | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12 - 3rd Lift | 0 | 0 | 0 | 0 | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12 - 4th Lift | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.5 | 0 | 0 | 0 | 0 | 0 | 0
P12(N) | 54.05 | 0 | P12(N) - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12(N) - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12(N) - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12(N) - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12(N) - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12(N) - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12(N) - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12(N) - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12(A) | 54.05 | 49.13 | P12(A) - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.48 | 0 | 47.13 | 2
|  |  | P12(A) - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.45 | 0
|  |  | P12(A) - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
|  |  | P12(A) - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0
P13 | 54.05 | 43.4 | P13 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 41.4 | 2
|  |  | P13 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
|  |  | P13 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
|  |  | P13 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
|  |  | P13 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
|  |  | P13 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P13 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P13 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P13 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P13 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0
|  |  | P13 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0
|  |  | P13 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7 | 0 | 0 | 0
|  |  | P13 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0
|  |  | P13 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
|  |  | P13 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0
P14 |  | 9.985 | P14 - Well Curb | 0 | 0 | 0 | 4.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 7.985 | 2
|  |  | P14 - 1st Lift | 0 | 0 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14 - 2nd Lift | 0 | 0 | 0 | 0 | 2.485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14 - 3rd Lift | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14 - 4th Lift | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14 - 5th Lift | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.485 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.485 | 0 | 0 | 0 | 0 | 0 | 0
P14(N) | 50.55 | 50.1 | P14(N) - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.48 | 0 | 0 | 0 | 0 | 0 | 0 | 48.1 | 2
|  |  | P14(N) - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14(N) - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14(N) - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14(N) - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14(N) - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14(N) - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14(N) - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
|  |  | P14(N) - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.32 | 0 | 0 | 0 | 0 | 0
|  |  | P14(N) - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P14(N) - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P14(N) - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
|  |  | P14(N) - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 0 | 0
|  |  | P14(N) - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 0 | 0 | 0
|  |  | P14(N) - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 0 | 0
|  |  | P14(N) - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
|  |  | P14(N) - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
|  |  | P14(N) - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0
|  |  | P14(N) - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P15 | 54.05 | 54.96 | P15 - Well Curb | 0 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.96 | 2
|  |  | P15 - 1st Lift | 0 | 0 | 0 | 2.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 2nd Lift | 0 | 0 | 0 | 0 | 2.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 3rd Lift | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 4th Lift | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
|  |  | P15 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0
|  |  | P15 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P16 | 54.05 | 0 | P16 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P17 | 54.05 | 0 | P17 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P17 - 21st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P18 | 50.55 | 0 | P18 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P18 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P19 | 54.05 | 0 | P19 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P20 | 54.05 | 0 | P20 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P21 | 54.05 | 0 | P21 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - 21st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P22 | 51.55 | 0 | P22 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - 21st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P23 | 54.05 | 0 | P23 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 21st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - 22nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P24 | 54.05 | 0 | P24 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - 21st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P25 | 54.05 | 0 | P25 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P26 | 50.55 | 0 | P26 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P27 | 54.05 | 0 | P27 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P28 | 54.05 | 0 | P28 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - 21st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P29 | 54.05 | 0 | P29 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - 20th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P30 | 50.55 | 0 | P30 - Well Curb | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 1st Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 2nd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 3rd Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 4th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 5th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 6th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 7th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 8th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 9th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 10th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 11th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 12th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 13th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 14th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 15th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 16th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 17th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 18th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - 19th Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 1381.8 | 317.9 |  | 0 | 0 | 0 | 32.13 | 34.705 | 25.855 | 14.7 | 8 | 5 | 0 | 0 | 2.34 | 8.41 | 7.5 | 10.71 | 28.32 | 27 | 27.6 | 12.5 | 57.13 | 0 | 301.9 | 16

## Pylon Cal.
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
Lower Pylon Reconciliation Statement
Pylon ID | Well Depth | Length Executed | Lift | IPC - 30 | IPC - 31 | IPC - 33 | IPC - 34 | Total | Check
P4 | 50.55 | 48.7 | P4 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 48.7
|  |  | P4 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P5 | 50.55 | 50.55 | P5 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 50.55
|  |  | P5 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
Total | 101.1 | 99.25 |  | 0 | 0 | 0 | 0 | 0 | 99.25
P6 | 21.624 | 0 | P6 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P6 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P7 | 21.324 | 0 | P7 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P7 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
|  |  | P7 - Lower Pylon - 2nd Lift | 0 | 0 | 0 | 0
P8 | 21.624 | 0 | P8 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P8 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
|  |  | P8 - Lower Pylon - 2nd Lift | 0 | 0 | 0 | 0
|  |  | P8 - Lower Pylon - 3rd Lift | 0 | 0 | 0 | 0
|  |  | P8 - Lower Pylon - 4th Lift | 0 | 0 | 0 | 0
|  |  | P8 - Lower Pylon - 5th Lift | 0 | 0 | 0 | 0
|  |  | P8 - Lower Pylon - 6th Lift | 0 | 0 | 0 | 0
|  |  | P8 - Lower Pylon - 7th Lift | 0 | 0 | 0 | 0
P9 | 21.324 | 0 | P9 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P9 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P10 | 21.624 | 0 | P10 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P10 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P11 | 21.324 | 0 | P11 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P11 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P12(N) | 21.624 | 0 | P12(N) - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12(N) - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P12(A) | 21.624 | 0 | P12(A) - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P12(A) - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P13 | 21.324 | 0 | P13 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P13 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P14(N) | 21.624 | 0 | P14(N) - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P14(N) - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P15 | 21.324 | 0 | P15 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P15 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P16 | 21.624 | 0 | P16 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P16 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P17 | 21.324 | 31.06 | P17 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 31.06
|  |  | P17 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P18 | 21.624 | 44.68 | P18 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 44.68
|  |  | P18 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P19 | 21.324 | 0 | P19 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P19 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P20 | 21.624 | 0 | P20 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P20 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
|  |  | P20 - Lower Pylon - 2nd Lift | 0 | 0 | 0 | 0
P21 | 21.324 | 0 | P21 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P21 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P22 | 21.624 | 0 | P22 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P22 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
|  |  | P22 - Lower Pylon - 2nd Lift | 0 | 0 | 0 | 0
|  |  | P22 - Lower Pylon - 3rd Lift | 0 | 0 | 0 | 0
P23 | 21.324 | 0 | P23 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P23 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P24 | 21.624 | 0 | P24 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P24 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P25 | 21.324 | 0 | P25 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P25 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
|  |  | P25 - Lower Pylon - 2nd Lift | 0 | 0 | 0 | 0
P26 | 21.624 | 0 | P26 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P26 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
|  |  | P26 - Lower Pylon - 2nd Lift | 0 | 0 | 0 | 0
|  |  | P26 - Lower Pylon - 3rd Lift | 0 | 0 | 0 | 0
|  |  | P26 - Lower Pylon - 4th Lift | 0 | 0 | 0 | 0
P27 | 21.324 | 0 | P27 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P27 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P28 | 21.624 | 0 | P28 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P28 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
P29 | 21.324 | 0 | P29 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P29 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
|  |  | P29 - Lower Pylon - 2nd Lift | 0 | 0 | 0 | 0
P30 | 21.624 | 0 | P30 - Lower Pylon - Starter | 0 | 0 | 0 | 0 | 0 | 0
|  |  | P30 - Lower Pylon - 1st Lift | 0 | 0 | 0 | 0
Total | 558.624 | 75.74 |  | 0 | 0 | 0 | 0 | 0 | 75.74

## Segment Abs.
Main Bridge - Segments - Scope Vs Casting
| Module 1 |  | Module 2 |  | Module 3 |  | Module 4 |  | Module 5 |  | Module 6
| P6-BP-S01a-E | - | P10-BP-S01a-E | - | P14-BP-S01a-E | - | P18-BP-S01a-E | - | P22-BP-S01a-E | - | P26-BP-S01a-E | -
| P6-BP-S01-E | - | P10-BP-S01-E | - | P14-BP-S01-E | - | P18-BP-S01-E | - | P22-BP-S01-E | - | P26-BP-S01-E | -
| P6-BP-S02-E | - | P10-BP-S02-E | - | P14-BP-S02-E | - | P18-BP-S02-E | - | P22-BP-S02-E | - | P26-BP-S02-E | -
| P6-BP-S03-E | - | P10-BP-S03-E | - | P14-BP-S03-E | - | P18-BP-S03-E | - | P22-BP-S03-E | - | P26-BP-S03-E | -
| P6-BP-S04-E | - | P10-BP-S04-E | - | P14-BP-S04-E | - | P18-BP-S04-E | - | P22-BP-S04-E | - | P26-BP-S04-E | -
| P6-BP-S05-E | - | P10-BP-S05-E | - | P14-BP-S05-E | - | P18-BP-S05-E | - | P22-BP-S05-E | - | P26-BP-S05-E | -
| P6-BP-S06-E | - | P10-BP-S06-E | - | P14-BP-S06-E | - | P18-BP-S06-E | - | P22-BP-S06-E | - | P26-BP-S06-E | -
| P7-KS-S34a-O | - | P11-KS-S34a-O | - | P15-KS-S34a-O | - | P19-KS-S34a-O | - | P23-KS-S34a-O | - | P27-KS-S34a-O | -
| P7-KS-S33a-O© | - | P11-KS-S33a-O© | - | P15-KS-S33a-O© | - | P19-KS-S33a-O© | - | P23-KS-S33a-O© | - | P27-KS-S33a-O© | -
| P7-KS-S32a-O | - | P11-KS-S32a-O | - | P15-KS-S32a-O | - | P19-KS-S32a-O | - | P23-KS-S32a-O | - | P27-KS-S32a-O | -
| P7-KS-S31a-O© | - | P11-KS-S31a-O© | - | P15-KS-S31a-O© | - | P19-KS-S31a-O© | - | P23-KS-S31a-O© | - | P27-KS-S31a-O© | -
| P7-KS-S30a-O | - | P11-KS-S30a-O | - | P15-KS-S30a-O | - | P19-KS-S30a-O | - | P23-KS-S30a-O | - | P27-KS-S30a-O | -
| P7-KS-S29a-O© | - | P11-KS-S29a-O© | - | P15-KS-S29a-O© | - | P19-KS-S29a-O© | - | P23-KS-S29a-O© | - | P27-KS-S29a-O© | -
| P7-KS-S28a-O | - | P11-KS-S28a-O | - | P15-KS-S28a-O | - | P19-KS-S28a-O | - | P23-KS-S28a-O | - | P27-KS-S28a-O | -
| P7-KS-S27a-O© | - | P11-KS-S27a-O© | - | P15-KS-S27a-O© | - | P19-KS-S27a-O© | - | P23-KS-S27a-O© | - | P27-KS-S27a-O© | -
| P7-KS-S26a-O | - | P11-KS-S26a-O | - | P15-KS-S26a-O | - | P19-KS-S26a-O | - | P23-KS-S26a-O | - | P27-KS-S26a-O | -
| P7-KS-S25a-O© | - | P11-KS-S25a-O© | - | P15-KS-S25a-O© | - | P19-KS-S25a-O© | - | P23-KS-S25a-O© | - | P27-KS-S25a-O© | -
| P7-KS-S24a-O | - | P11-KS-S24a-O | - | P15-KS-S24a-O | - | P19-KS-S24a-O | - | P23-KS-S24a-O | - | P27-KS-S24a-O | -
| P7-KS-S23a-O© | - | P11-KS-S23a-O© | - | P15-KS-S23a-O© | - | P19-KS-S23a-O© | - | P23-KS-S23a-O© | - | P27-KS-S23a-O© | -
| P7-KS-S22a-O | - | P11-KS-S22a-O | - | P15-KS-S22a-O | - | P19-KS-S22a-O | - | P23-KS-S22a-O | - | P27-KS-S22a-O | -
| P7-KS-S21a-O© | - | P11-KS-S21a-O© | - | P15-KS-S21a-O© | - | P19-KS-S21a-O© | - | P23-KS-S21a-O© | - | P27-KS-S21a-O© | -
| P7-KS-S20a-O | - | P11-KS-S20a-O | - | P15-KS-S20a-O | - | P19-KS-S20a-O | - | P23-KS-S20a-O | - | P27-KS-S20a-O | -
| P7-KS-S19a-O© | - | P11-KS-S19a-O© | - | P15-KS-S19a-O© | - | P19-KS-S19a-O© | - | P23-KS-S19a-O© | - | P27-KS-S19a-O© | -
| P7-KS-S18a-O | - | P11-KS-S18a-O | - | P15-KS-S18a-O | - | P19-KS-S18a-O | - | P23-KS-S18a-O | - | P27-KS-S18a-O | -
| P7-KS-S17a-O© | - | P11-KS-S17a-O© | - | P15-KS-S17a-O© | - | P19-KS-S17a-O© | - | P23-KS-S17a-O© | - | P27-KS-S17a-O© | -
| P7-KS-S16a-O | - | P11-KS-S16a-O | - | P15-KS-S16a-O | - | P19-KS-S16a-O | - | P23-KS-S16a-O | - | P27-KS-S16a-O | -
| P7-KS-S15a-O© | - | P11-KS-S15a-O© | - | P15-KS-S15a-O© | - | P19-KS-S15a-O© | - | P23-KS-S15a-O© | - | P27-KS-S15a-O© | -
| P7-KS-S14a-O | - | P11-KS-S14a-O | - | P15-KS-S14a-O | - | P19-KS-S14a-O | - | P23-KS-S14a-O | - | P27-KS-S14a-O | -
| P7-KS-S13a-O© | - | P11-KS-S13a-O© | - | P15-KS-S13a-O© | - | P19-KS-S13a-O© | - | P23-KS-S13a-O© | - | P27-KS-S13a-O© | -
| P7-KS-S12a-O | - | P11-KS-S12a-O | - | P15-KS-S12a-O | - | P19-KS-S12a-O | - | P23-KS-S12a-O | - | P27-KS-S12a-O | -
| P7-KS-S11a-O© | - | P11-KS-S11a-O© | - | P15-KS-S11a-O© | - | P19-KS-S11a-O© | - | P23-KS-S11a-O© | - | P27-KS-S11a-O© | -
| P7-KS-S10a-O | - | P11-KS-S10a-O | - | P15-KS-S10a-O | - | P19-KS-S10a-O | - | P23-KS-S10a-O | - | P27-KS-S10a-O | -
| P7-KS-S09a-O© | - | P11-KS-S09a-O© | - | P15-KS-S09a-O© | - | P19-KS-S09a-O© | - | P23-KS-S09a-O© | - | P27-KS-S09a-O© | -
| P7-KS-S08a-O | - | P11-KS-S08a-O | - | P15-KS-S08a-O | - | P19-KS-S08a-O | - | P23-KS-S08a-O | - | P27-KS-S08a-O | -
| P7-KS-S07a-O | - | P11-KS-S07a-O | - | P15-KS-S07a-O | - | P19-KS-S07a-O | - | P23-KS-S07a-O | - | P27-KS-S07a-O | -
| P7-KS-S06a-O | - | P11-KS-S06a-O | - | P15-KS-S06a-O | - | P19-KS-S06a-O | - | P23-KS-S06a-O | - | P27-KS-S06a-O | -
| P7-KS-S05a-O | - | P11-KS-S05a-O | - | P15-KS-S05a-O | - | P19-KS-S05a-O | - | P23-KS-S05a-O | - | P27-KS-S05a-O | -
| P7-KS-S04a-O | - | P11-KS-S04a-O | - | P15-KS-S04a-O | - | P19-KS-S04a-O | - | P23-KS-S04a-O | - | P27-KS-S04a-O | -
| P7-KS-S03a-O | - | P11-KS-S03a-O | - | P15-KS-S03a-O | - | P19-KS-S03a-O | - | P23-KS-S03a-O | - | P27-KS-S03a-O | -
| P7-KS-S02a-O | - | P11-KS-S02a-O | - | P15-KS-S02a-O | - | P19-KS-S02a-O | - | P23-KS-S02a-O | - | P27-KS-S02a-O | -
| P7-KS-S01a-O | - | P11-KS-S01a-O | - | P15-KS-S01a-O | - | P19-KS-S01a-O | - | P23-KS-S01a-O | - | P27-KS-S01a-O | -
| P7-BP-S01-O | - | P11-BP-S01-O | - | P15-BP-S01-O | - | P19-BP-S01-O | - | P23-BP-S01-O | - | P27-BP-S01-O | -
| P7-BP-S02-O | - | P11-BP-S02-O | - | P15-BP-S02-O | - | P19-BP-S02-O | - | P23-BP-S02-O | - | P27-BP-S02-O | -
| P7-BP-S03-O | - | P11-BP-S03-O | - | P15-BP-S03-O | - | P19-BP-S03-O | - | P23-BP-S03-O | - | P27-BP-S03-O | -
| P7-BP-S04-O | - | P11-BP-S04-O | - | P15-BP-S04-O | - | P19-BP-S04-O | - | P23-BP-S04-O | - | P27-BP-S04-O | -
| P7-BP-S05-O | - | P11-BP-S05-O | - | P15-BP-S05-O | - | P19-BP-S05-O | - | P23-BP-S05-O | - | P27-BP-S05-O | -
| P7-BP-S06-O | - | P11-BP-S06-O | - | P15-BP-S06-O | - | P19-BP-S06-O | - | P23-BP-S06-O | - | P27-BP-S06-O | -
| P7-BP-S07-O | - | P11-BP-S07-O | - | P15-BP-S07-O | - | P19-BP-S07-O | - | P23-BP-S07-O | - | P27-BP-S07-O | -
| P7-BP-S08-O | - | P11-BP-S08-O | - | P15-BP-S08-O | - | P19-BP-S08-O | - | P23-BP-S08-O | - | P27-BP-S08-O | -
| P7-BP-S09-O© | - | P11-BP-S09-O© | - | P15-BP-S09-O© | - | P19-BP-S09-O© | - | P23-BP-S09-O© | - | P27-BP-S09-O© | -
| P7-BP-S10-O | - | P11-BP-S10-O | - | P15-BP-S10-O | - | P19-BP-S10-O | - | P23-BP-S10-O | - | P27-BP-S10-O | -
| P7-BP-S11-O© | - | P11-BP-S11-O© | - | P15-BP-S11-O© | - | P19-BP-S11-O© | - | P23-BP-S11-O© | - | P27-BP-S11-O© | -
| P7-BP-S12-O | - | P11-BP-S12-O | - | P15-BP-S12-O | - | P19-BP-S12-O | - | P23-BP-S12-O | - | P27-BP-S12-O | -
| P7-BP-S13-O© | - | P11-BP-S13-O© | - | P15-BP-S13-O© | - | P19-BP-S13-O© | - | P23-BP-S13-O© | - | P27-BP-S13-O© | -
| P7-BP-S14-O | - | P11-BP-S14-O | - | P15-BP-S14-O | - | P19-BP-S14-O | - | P23-BP-S14-O | - | P27-BP-S14-O | -
| P7-BP-S15-O© | - | P11-BP-S15-O© | - | P15-BP-S15-O© | - | P19-BP-S15-O© | - | P23-BP-S15-O© | - | P27-BP-S15-O© | -
| P7-BP-S16-O | - | P11-BP-S16-O | - | P15-BP-S16-O | - | P19-BP-S16-O | - | P23-BP-S16-O | - | P27-BP-S16-O | -
| P7-BP-S17-O© | - | P11-BP-S17-O© | - | P15-BP-S17-O© | - | P19-BP-S17-O© | - | P23-BP-S17-O© | - | P27-BP-S17-O© | -
| P7-BP-S18-O | - | P11-BP-S18-O | - | P15-BP-S18-O | - | P19-BP-S18-O | - | P23-BP-S18-O | - | P27-BP-S18-O | -
| P7-BP-S19-O© | - | P11-BP-S19-O© | - | P15-BP-S19-O© | - | P19-BP-S19-O© | - | P23-BP-S19-O© | - | P27-BP-S19-O© | -
| P7-BP-S20-O | - | P11-BP-S20-O | - | P15-BP-S20-O | - | P19-BP-S20-O | - | P23-BP-S20-O | - | P27-BP-S20-O | -
| P7-BP-S21-O© | - | P11-BP-S21-O© | - | P15-BP-S21-O© | - | P19-BP-S21-O© | - | P23-BP-S21-O© | - | P27-BP-S21-O© | -
| P7-BP-S22-O | - | P11-BP-S22-O | - | P15-BP-S22-O | - | P19-BP-S22-O | - | P23-BP-S22-O | - | P27-BP-S22-O | -
| P7-BP-S23-O© | - | P11-BP-S23-O© | - | P15-BP-S23-O© | - | P19-BP-S23-O© | - | P23-BP-S23-O© | - | P27-BP-S23-O© | -
| P7-BP-S24-O | - | P11-BP-S24-O | - | P15-BP-S24-O | - | P19-BP-S24-O | - | P23-BP-S24-O | - | P27-BP-S24-O | -
| P7-BP-S25-O© | - | P11-BP-S25-O© | - | P15-BP-S25-O© | - | P19-BP-S25-O© | - | P23-BP-S25-O© | - | P27-BP-S25-O© | -
| P7-BP-S26-O | - | P11-BP-S26-O | - | P15-BP-S26-O | - | P19-BP-S26-O | - | P23-BP-S26-O | - | P27-BP-S26-O | -
| P7-BP-S27-O© | - | P11-BP-S27-O© | - | P15-BP-S27-O© | - | P19-BP-S27-O© | - | P23-BP-S27-O© | - | P27-BP-S27-O© | -
| P7-BP-S28-O | - | P11-BP-S28-O | - | P15-BP-S28-O | - | P19-BP-S28-O | - | P23-BP-S28-O | - | P27-BP-S28-O | -
| P7-BP-S29-O© | - | P11-BP-S29-O© | - | P15-BP-S29-O© | - | P19-BP-S29-O© | - | P23-BP-S29-O© | - | P27-BP-S29-O© | -
| P7-BP-S30-O | - | P11-BP-S30-O | - | P15-BP-S30-O | - | P19-BP-S30-O | - | P23-BP-S30-O | - | P27-BP-S30-O | -
| P7-BP-S31-O© | - | P11-BP-S31-O© | - | P15-BP-S31-O© | - | P19-BP-S31-O© | - | P23-BP-S31-O© | - | P27-BP-S31-O© | -
| P7-BP-S32-O | - | P11-BP-S32-O | - | P15-BP-S32-O | - | P19-BP-S32-O | - | P23-BP-S32-O | - | P27-BP-S32-O | -
| P7-BP-S33-O© | - | P11-BP-S33-O© | - | P15-BP-S33-O© | - | P19-BP-S33-O© | - | P23-BP-S33-O© | - | P27-BP-S33-O© | -
| P7-BP-S34-O | - | P11-BP-S34-O | - | P15-BP-S34-O | - | P19-BP-S34-O | - | P23-BP-S34-O | - | P27-BP-S34-O | -
| P8-KS-S18-M | - | P12-KS-S18-M | - | P16-KS-S18-M | - | P20-KS-S18-M | - | P24-KS-S18-M | - | P28-KS-S18-M | -
| P8-KS-S17-M | - | P12-KS-S17-M | - | P16-KS-S17-M | - | P20-KS-S17-M | - | P24-KS-S17-M | - | P28-KS-S17-M | -
| P8-KS-S16-M© | - | P12-KS-S16-M© | - | P16-KS-S16-M© | - | P20-KS-S16-M© | - | P24-KS-S16-M© | - | P28-KS-S16-M© | -
| P8-KS-S15-M | - | P12-KS-S15-M | - | P16-KS-S15-M | - | P20-KS-S15-M | - | P24-KS-S15-M | - | P28-KS-S15-M | -
| P8-KS-S14-M© | - | P12-KS-S14-M© | - | P16-KS-S14-M© | - | P20-KS-S14-M© | - | P24-KS-S14-M© | - | P28-KS-S14-M© | -
| P8-KS-S13-M | - | P12-KS-S13-M | - | P16-KS-S13-M | - | P20-KS-S13-M | - | P24-KS-S13-M | - | P28-KS-S13-M | -
| P8-KS-S12-M© | - | P12-KS-S12-M© | - | P16-KS-S12-M© | - | P20-KS-S12-M© | - | P24-KS-S12-M© | - | P28-KS-S12-M© | -
| P8-KS-S11-M | - | P12-KS-S11-M | - | P16-KS-S11-M | - | P20-KS-S11-M | - | P24-KS-S11-M | - | P28-KS-S11-M | -
| P8-KS-S10-M© | - | P12-KS-S10-M© | - | P16-KS-S10-M© | - | P20-KS-S10-M© | - | P24-KS-S10-M© | - | P28-KS-S10-M© | -
| P8-KS-S09-M | - | P12-KS-S09-M | - | P16-KS-S09-M | - | P20-KS-S09-M | - | P24-KS-S09-M | - | P28-KS-S09-M | -
| P8-KS-S08-M© | - | P12-KS-S08-M© | - | P16-KS-S08-M© | - | P20-KS-S08-M© | - | P24-KS-S08-M© | - | P28-KS-S08-M© | -
| P8-KS-S07-M | - | P12-KS-S07-M | - | P16-KS-S07-M | - | P20-KS-S07-M | - | P24-KS-S07-M | - | P28-KS-S07-M | -
| P8-KS-S06-M | - | P12-KS-S06-M | - | P16-KS-S06-M | - | P20-KS-S06-M | - | P24-KS-S06-M | - | P28-KS-S06-M | -
| P8-KS-S05-M | - | P12-KS-S05-M | - | P16-KS-S05-M | - | P20-KS-S05-M | - | P24-KS-S05-M | - | P28-KS-S05-M | -
| P8-KS-S04-M | - | P12-KS-S04-M | - | P16-KS-S04-M | - | P20-KS-S04-M | - | P24-KS-S04-M | - | P28-KS-S04-M | -
| P8-KS-S03-M | - | P12-KS-S03-M | - | P16-KS-S03-M | - | P20-KS-S03-M | - | P24-KS-S03-M | - | P28-KS-S03-M | -
| P8-KS-S02-M | - | P12-KS-S02-M | - | P16-KS-S02-M | - | P20-KS-S02-M | - | P24-KS-S02-M | - | P28-KS-S02-M | -
| P8-KS-S01-M | - | P12-KS-S01-M | - | P16-KS-S01-M | - | P20-KS-S01-M | - | P24-KS-S01-M | - | P28-KS-S01-M | -
| P8-BP-S01-M | - | P12-BP-S01-M | - | P16-BP-S01-M | - | P20-BP-S01-M | - | P24-BP-S01-M | - | P28-BP-S01-M | -
| P8-BP-S02-M | - | P12-BP-S02-M | - | P16-BP-S02-M | - | P20-BP-S02-M | - | P24-BP-S02-M | - | P28-BP-S02-M | -
| P8-BP-S03-M | - | P12-BP-S03-M | - | P16-BP-S03-M | - | P20-BP-S03-M | - | P24-BP-S03-M | - | P28-BP-S03-M | -
| P8-BP-S04-M | - | P12-BP-S04-M | - | P16-BP-S04-M | - | P20-BP-S04-M | - | P24-BP-S04-M | - | P28-BP-S04-M | -
| P8-BP-S05-M | - | P12-BP-S05-M | - | P16-BP-S05-M | - | P20-BP-S05-M | - | P24-BP-S05-M | - | P28-BP-S05-M | -
| P8-BP-S06-M | - | P12-BP-S06-M | - | P16-BP-S06-M | - | P20-BP-S06-M | - | P24-BP-S06-M | - | P28-BP-S06-M | -
| P8-BP-S07-M | - | P12-BP-S07-M | - | P16-BP-S07-M | - | P20-BP-S07-M | - | P24-BP-S07-M | - | P28-BP-S07-M | -
| P8-BP-S08-M© | - | P12-BP-S08-M© | - | P16-BP-S08-M© | - | P20-BP-S08-M© | - | P24-BP-S08-M© | - | P28-BP-S08-M© | -
| P8-BP-S09-M | - | P12-BP-S09-M | - | P16-BP-S09-M | - | P20-BP-S09-M | - | P24-BP-S09-M | - | P28-BP-S09-M | -
| P8-BP-S10-M© | - | P12-BP-S10-M© | - | P16-BP-S10-M© | - | P20-BP-S10-M© | - | P24-BP-S10-M© | - | P28-BP-S10-M© | -
| P8-BP-S11-M | - | P12-BP-S11-M | - | P16-BP-S11-M | - | P20-BP-S11-M | - | P24-BP-S11-M | - | P28-BP-S11-M | -
| P8-BP-S12-M© | - | P12-BP-S12-M© | - | P16-BP-S12-M© | - | P20-BP-S12-M© | - | P24-BP-S12-M© | - | P28-BP-S12-M© | -
| P8-BP-S13-M | - | P12-BP-S13-M | - | P16-BP-S13-M | - | P20-BP-S13-M | - | P24-BP-S13-M | - | P28-BP-S13-M | -
| P8-BP-S14-M© | - | P12-BP-S14-M© | - | P16-BP-S14-M© | - | P20-BP-S14-M© | - | P24-BP-S14-M© | - | P28-BP-S14-M© | -
| P8-BP-S15-M | - | P12-BP-S15-M | - | P16-BP-S15-M | - | P20-BP-S15-M | - | P24-BP-S15-M | - | P28-BP-S15-M | -
| P8-BP-S16-M© | - | P12-BP-S16-M© | - | P16-BP-S16-M© | - | P20-BP-S16-M© | - | P24-BP-S16-M© | - | P28-BP-S16-M© | -
| P8-BP-S17-M | - | P12-BP-S17-M | - | P16-BP-S17-M | - | P20-BP-S17-M | - | P24-BP-S17-M | - | P28-BP-S17-M | -
| P8-BP-S18-M | - | P12-BP-S18-M | - | P16-BP-S18-M | - | P20-BP-S18-M | - | P24-BP-S18-M | - | P28-BP-S18-M | -
| P9-KS-S34-O | - | P13-KS-S34-O | - | P17-KS-S34-O | - | P21-KS-S34-O | - | P25-KS-S34-O | - | P29-KS-S34-O | -
| P9-KS-S33-O© | - | P13-KS-S33-O© | - | P17-KS-S33-O© | - | P21-KS-S33-O© | - | P25-KS-S33-O© | - | P29-KS-S33-O© | -
| P9-KS-S32-O | - | P13-KS-S32-O | - | P17-KS-S32-O | - | P21-KS-S32-O | - | P25-KS-S32-O | - | P29-KS-S32-O | -
| P9-KS-S31-O© | - | P13-KS-S31-O© | - | P17-KS-S31-O© | - | P21-KS-S31-O© | - | P25-KS-S31-O© | - | P29-KS-S31-O© | -
| P9-KS-S30-O | - | P13-KS-S30-O | - | P17-KS-S30-O | - | P21-KS-S30-O | - | P25-KS-S30-O | - | P29-KS-S30-O | -
| P9-KS-S29-O© | - | P13-KS-S29-O© | - | P17-KS-S29-O© | - | P21-KS-S29-O© | - | P25-KS-S29-O© | - | P29-KS-S29-O© | -
| P9-KS-S28-O | - | P13-KS-S28-O | - | P17-KS-S28-O | - | P21-KS-S28-O | - | P25-KS-S28-O | - | P29-KS-S28-O | -
| P9-KS-S27-O© | - | P13-KS-S27-O© | - | P17-KS-S27-O© | - | P21-KS-S27-O© | - | P25-KS-S27-O© | - | P29-KS-S27-O© | -
| P9-KS-S26-O | - | P13-KS-S26-O | - | P17-KS-S26-O | - | P21-KS-S26-O | - | P25-KS-S26-O | - | P29-KS-S26-O | -
| P9-KS-S25-O© | - | P13-KS-S25-O© | - | P17-KS-S25-O© | - | P21-KS-S25-O© | - | P25-KS-S25-O© | - | P29-KS-S25-O© | -
| P9-KS-S24-O | - | P13-KS-S24-O | - | P17-KS-S24-O | - | P21-KS-S24-O | - | P25-KS-S24-O | - | P29-KS-S24-O | -
| P9-KS-S23-O© | - | P13-KS-S23-O© | - | P17-KS-S23-O© | - | P21-KS-S23-O© | - | P25-KS-S23-O© | - | P29-KS-S23-O© | -
| P9-KS-S22-O | - | P13-KS-S22-O | - | P17-KS-S22-O | - | P21-KS-S22-O | - | P25-KS-S22-O | - | P29-KS-S22-O | -
| P9-KS-S21-O© | - | P13-KS-S21-O© | - | P17-KS-S21-O© | - | P21-KS-S21-O© | - | P25-KS-S21-O© | - | P29-KS-S21-O© | -
| P9-KS-S20-O | - | P13-KS-S20-O | - | P17-KS-S20-O | - | P21-KS-S20-O | - | P25-KS-S20-O | - | P29-KS-S20-O | -
| P9-KS-S19-O© | - | P13-KS-S19-O© | - | P17-KS-S19-O© | - | P21-KS-S19-O© | - | P25-KS-S19-O© | - | P29-KS-S19-O© | -
| P9-KS-S18-O | - | P13-KS-S18-O | - | P17-KS-S18-O | - | P21-KS-S18-O | - | P25-KS-S18-O | - | P29-KS-S18-O | -
| P9-KS-S17-O© | - | P13-KS-S17-O© | - | P17-KS-S17-O© | - | P21-KS-S17-O© | - | P25-KS-S17-O© | - | P29-KS-S17-O© | -
| P9-KS-S16-O | - | P13-KS-S16-O | - | P17-KS-S16-O | - | P21-KS-S16-O | - | P25-KS-S16-O | - | P29-KS-S16-O | -
| P9-KS-S15-O© | - | P13-KS-S15-O© | - | P17-KS-S15-O© | - | P21-KS-S15-O© | - | P25-KS-S15-O© | - | P29-KS-S15-O© | -
| P9-KS-S14-O | - | P13-KS-S14-O | - | P17-KS-S14-O | - | P21-KS-S14-O | - | P25-KS-S14-O | - | P29-KS-S14-O | -
| P9-KS-S13-O© | - | P13-KS-S13-O© | - | P17-KS-S13-O© | - | P21-KS-S13-O© | - | P25-KS-S13-O© | - | P29-KS-S13-O© | -
| P9-KS-S12-O | - | P13-KS-S12-O | - | P17-KS-S12-O | - | P21-KS-S12-O | - | P25-KS-S12-O | - | P29-KS-S12-O | -
| P9-KS-S11-O© | - | P13-KS-S11-O© | - | P17-KS-S11-O© | - | P21-KS-S11-O© | - | P25-KS-S11-O© | - | P29-KS-S11-O© | -
| P9-KS-S10-O | - | P13-KS-S10-O | - | P17-KS-S10-O | - | P21-KS-S10-O | - | P25-KS-S10-O | - | P29-KS-S10-O | -
| P9-KS-S09-O© | - | P13-KS-S09-O© | - | P17-KS-S09-O© | - | P21-KS-S09-O© | - | P25-KS-S09-O© | - | P29-KS-S09-O© | -
| P9-KS-S08-O | - | P13-KS-S08-O | - | P17-KS-S08-O | - | P21-KS-S08-O | - | P25-KS-S08-O | - | P29-KS-S08-O | -
| P9-KS-S07-O | - | P13-KS-S07-O | - | P17-KS-S07-O | - | P21-KS-S07-O | - | P25-KS-S07-O | - | P29-KS-S07-O | -
| P9-KS-S06-O | - | P13-KS-S06-O | - | P17-KS-S06-O | - | P21-KS-S06-O | - | P25-KS-S06-O | - | P29-KS-S06-O | -
| P9-KS-S05-O | - | P13-KS-S05-O | - | P17-KS-S05-O | - | P21-KS-S05-O | - | P25-KS-S05-O | - | P29-KS-S05-O | -
| P9-KS-S04-O | - | P13-KS-S04-O | - | P17-KS-S04-O | - | P21-KS-S04-O | - | P25-KS-S04-O | - | P29-KS-S04-O | -
| P9-KS-S03-O | - | P13-KS-S03-O | - | P17-KS-S03-O | - | P21-KS-S03-O | - | P25-KS-S03-O | - | P29-KS-S03-O | -
| P9-KS-S02-O | - | P13-KS-S02-O | - | P17-KS-S02-O | - | P21-KS-S02-O | - | P25-KS-S02-O | - | P29-KS-S02-O | -
| P9-KS-S01-O | - | P13-KS-S01-O | - | P17-KS-S01-O | - | P21-KS-S01-O | - | P25-KS-S01-O | - | P29-KS-S01-O | -
| P9-BP-S01a-O | - | P13-BP-S01a-O | - | P17-BP-S01a-O | - | P21-BP-S01a-O | - | P25-BP-S01a-O | - | P29-BP-S01a-O | -
| P9-BP-S02a-O | - | P13-BP-S02a-O | - | P17-BP-S02a-O | - | P21-BP-S02a-O | - | P25-BP-S02a-O | - | P29-BP-S02a-O | -
| P9-BP-S03a-O | - | P13-BP-S03a-O | - | P17-BP-S03a-O | - | P21-BP-S03a-O | - | P25-BP-S03a-O | - | P29-BP-S03a-O | -
| P9-BP-S04a-O | - | P13-BP-S04a-O | - | P17-BP-S04a-O | - | P21-BP-S04a-O | - | P25-BP-S04a-O | - | P29-BP-S04a-O | -
| P9-BP-S05a-O | - | P13-BP-S05a-O | - | P17-BP-S05a-O | - | P21-BP-S05a-O | - | P25-BP-S05a-O | - | P29-BP-S05a-O | -
| P9-BP-S06a-O | - | P13-BP-S06a-O | - | P17-BP-S06a-O | - | P21-BP-S06a-O | - | P25-BP-S06a-O | - | P29-BP-S06a-O | -
| P9-BP-S07a-O | - | P13-BP-S07a-O | - | P17-BP-S07a-O | - | P21-BP-S07a-O | - | P25-BP-S07a-O | - | P29-BP-S07a-O | -
| P9-BP-S08a-O | - | P13-BP-S08a-O | - | P17-BP-S08a-O | - | P21-BP-S08a-O | - | P25-BP-S08a-O | - | P29-BP-S08a-O | -
| P9-BP-S09a-O© | - | P13-BP-S09a-O© | - | P17-BP-S09a-O© | - | P21-BP-S09a-O© | - | P25-BP-S09a-O© | - | P29-BP-S09a-O© | -
| P9-BP-S10a-O | - | P13-BP-S10a-O | - | P17-BP-S10a-O | - | P21-BP-S10a-O | - | P25-BP-S10a-O | - | P29-BP-S10a-O | -
| P9-BP-S11a-O© | - | P13-BP-S11a-O© | - | P17-BP-S11a-O© | - | P21-BP-S11a-O© | - | P25-BP-S11a-O© | - | P29-BP-S11a-O© | -
| P9-BP-S12a-O | - | P13-BP-S12a-O | - | P17-BP-S12a-O | - | P21-BP-S12a-O | - | P25-BP-S12a-O | - | P29-BP-S12a-O | -
| P9-BP-S13a-O© | - | P13-BP-S13a-O© | - | P17-BP-S13a-O© | - | P21-BP-S13a-O© | - | P25-BP-S13a-O© | - | P29-BP-S13a-O© | -
| P9-BP-S14a-O | - | P13-BP-S14a-O | - | P17-BP-S14a-O | - | P21-BP-S14a-O | - | P25-BP-S14a-O | - | P29-BP-S14a-O | -
| P9-BP-S15a-O© | - | P13-BP-S15a-O© | - | P17-BP-S15a-O© | - | P21-BP-S15a-O© | - | P25-BP-S15a-O© | - | P29-BP-S15a-O© | -
| P9-BP-S16a-O | - | P13-BP-S16a-O | - | P17-BP-S16a-O | - | P21-BP-S16a-O | - | P25-BP-S16a-O | - | P29-BP-S16a-O | -
| P9-BP-S17a-O© | - | P13-BP-S17a-O© | - | P17-BP-S17a-O© | - | P21-BP-S17a-O© | - | P25-BP-S17a-O© | - | P29-BP-S17a-O© | -
| P9-BP-S18a-O | - | P13-BP-S18a-O | - | P17-BP-S18a-O | - | P21-BP-S18a-O | - | P25-BP-S18a-O | - | P29-BP-S18a-O | -
| P9-BP-S19a-O© | - | P13-BP-S19a-O© | - | P17-BP-S19a-O© | - | P21-BP-S19a-O© | - | P25-BP-S19a-O© | - | P29-BP-S19a-O© | -
| P9-BP-S20a-O | - | P13-BP-S20a-O | - | P17-BP-S20a-O | - | P21-BP-S20a-O | - | P25-BP-S20a-O | - | P29-BP-S20a-O | -
| P9-BP-S21a-O© | - | P13-BP-S21a-O© | - | P17-BP-S21a-O© | - | P21-BP-S21a-O© | - | P25-BP-S21a-O© | - | P29-BP-S21a-O© | -
| P9-BP-S22a-O | - | P13-BP-S22a-O | - | P17-BP-S22a-O | - | P21-BP-S22a-O | - | P25-BP-S22a-O | - | P29-BP-S22a-O | -
| P9-BP-S23a-O© | - | P13-BP-S23a-O© | - | P17-BP-S23a-O© | - | P21-BP-S23a-O© | - | P25-BP-S23a-O© | - | P29-BP-S23a-O© | -
| P9-BP-S24a-O | - | P13-BP-S24a-O | - | P17-BP-S24a-O | - | P21-BP-S24a-O | - | P25-BP-S24a-O | - | P29-BP-S24a-O | -
| P9-BP-S25a-O© | - | P13-BP-S25a-O© | - | P17-BP-S25a-O© | - | P21-BP-S25a-O© | - | P25-BP-S25a-O© | - | P29-BP-S25a-O© | -
| P9-BP-S26a-O | - | P13-BP-S26a-O | - | P17-BP-S26a-O | - | P21-BP-S26a-O | - | P25-BP-S26a-O | - | P29-BP-S26a-O | -
| P9-BP-S27a-O© | - | P13-BP-S27a-O© | - | P17-BP-S27a-O© | - | P21-BP-S27a-O© | - | P25-BP-S27a-O© | - | P29-BP-S27a-O© | -
| P9-BP-S28a-O | - | P13-BP-S28a-O | - | P17-BP-S28a-O | - | P21-BP-S28a-O | - | P25-BP-S28a-O | - | P29-BP-S28a-O | -
| P9-BP-S29a-O© | - | P13-BP-S29a-O© | - | P17-BP-S29a-O© | - | P21-BP-S29a-O© | - | P25-BP-S29a-O© | - | P29-BP-S29a-O© | -
| P9-BP-S30a-O | - | P13-BP-S30a-O | - | P17-BP-S30a-O | - | P21-BP-S30a-O | - | P25-BP-S30a-O | - | P29-BP-S30a-O | -
| P9-BP-S31a-O© | - | P13-BP-S31a-O© | - | P17-BP-S31a-O© | - | P21-BP-S31a-O© | - | P25-BP-S31a-O© | - | P29-BP-S31a-O© | -
| P9-BP-S32a-O | - | P13-BP-S32a-O | - | P17-BP-S32a-O | - | P21-BP-S32a-O | - | P25-BP-S32a-O | - | P29-BP-S32a-O | -
| P9-BP-S33a-O© | - | P13-BP-S33a-O© | - | P17-BP-S33a-O© | - | P21-BP-S33a-O© | - | P25-BP-S33a-O© | - | P29-BP-S33a-O© | -
| P9-BP-S34a-O | - | P13-BP-S34a-O | - | P17-BP-S34a-O | - | P21-BP-S34a-O | - | P25-BP-S34a-O | - | P29-BP-S34a-O | -
| P10-KS-S06-E | - | P14-KS-S06-E | - | P18-KS-S06-E | - | P22-KS-S06-E | - | P26-KS-S06-E | - | P30-KS-S06-E | -
| P10-KS-S05-E | - | P14-KS-S05-E | - | P18-KS-S05-E | - | P22-KS-S05-E | - | P26-KS-S05-E | - | P30-KS-S05-E | -
| P10-KS-S04-E | - | P14-KS-S04-E | - | P18-KS-S04-E | - | P22-KS-S04-E | - | P26-KS-S04-E | - | P30-KS-S04-E | -
| P10-KS-S03-E | - | P14-KS-S03-E | - | P18-KS-S03-E | - | P22-KS-S03-E | - | P26-KS-S03-E | - | P30-KS-S03-E | -
| P10-KS-S02-E | - | P14-KS-S02-E | - | P18-KS-S02-E | - | P22-KS-S02-E | - | P26-KS-S02-E | - | P30-KS-S02-E | -
| P10-KS-S01-E | - | P14-KS-S01-E | - | P18-KS-S01-E | - | P22-KS-S01-E | - | P26-KS-S01-E | - | P30-KS-S01-E | -
| P10-KS-S01a-E | - | P14-KS-S01a-E | - | P18-KS-S01a-E | - | P22-KS-S01a-E | - | P26-KS-S01a-E | - | P30-KS-S01a-E | -
| 186 | 0 | 186 | 0 | 186 | 0 | 186 | 0 | 186 | 0 | 186 | 0
| Month | No. of Segments Casted | No. of Cable Stay Segments Casted |  | Month | No. of Segments Casted | No. of Cable Stay Segments Casted |  | Month | No. of Segments Casted | No. of Cable Stay Segments Casted
| 2025-06-01 | 0 | 0 |  | 2026-06-01 | 0 | 0 |  | 2027-06-01 | 0 | 0
| 2025-07-01 | 0 | 0 |  | 2026-07-01 | 0 | 0 |  | 2027-07-01 | 0 | 0
| 2025-08-01 | 0 | 0 |  | 2026-08-01 | 0 | 0 |  | 2027-08-01 | 0 | 0
| 2025-09-01 | 0 | 0 |  | 2026-09-01 | 0 | 0 |  | 2027-09-01 | 0 | 0
| 2025-10-01 | 0 | 0 |  | 2026-10-01 | 0 | 0 |  | 2027-10-01 | 0 | 0
| 2025-11-01 | 0 | 0 |  | 2026-11-01 | 0 | 0 |  | 2027-11-01 | 0 | 0
| 2025-12-01 | 0 | 0 |  | 2026-12-01 | 0 | 0 |  | 2027-12-01 | 0 | 0
| 2026-01-01 | 0 | 0 |  | 2027-01-01 | 0 | 0 |  | 2028-01-01 | 0 | 0
| 2026-02-01 | 0 | 0 |  | 2027-02-01 | 0 | 0 |  | 2028-02-01 | 0 | 0
| 2026-03-01 | 0 | 0 |  | 2027-03-01 | 0 | 0 |  | 2028-03-01 | 0 | 0
| 2026-04-01 | 0 | 0 |  | 2027-04-01 | 0 | 0 |  | 2028-04-01 | 0 | 0
| 2026-05-01 | 0 | 0 |  | 2027-05-01 | 0 | 0 |  | 2028-05-01 | 0 | 0
| Total Segments Casted |  | 0
| Total Cable Segments Casted |  | 0

## Schedule 5
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
2-Jul-25 2-Jul-25
Schedule 5 - Wetland and Approach Viaduct Works | [7 empty] | IPC - 34
Measurement Sheet
Item No. | Item Description | UoM | Location | Executed Quantity | RFI No. / Letter No. / Period | Date | Bill No. | Remarks
501 | Construction of foundation
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/192 MPSB/Str/200 | 2024-12-13 | IPC - 09 | Km 11+284 - PL19/P1 | PL19/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/197 MPSB/Str/212 | 14-Dec-24 16-Dec-24 | IPC - 09 | Km 11+284 - PL19/P3 | PL19/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/198 MPSB/Str/220 | 16-Dec-24 18-Dec-24 | IPC - 09 | Km 11+320 - PL20/P2 | PL20/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/199 MPSB/Str/213 | 2024-12-16 | IPC - 09 | Km 11+320 - PL20/P4 | PL20/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/205 MPSB/Str/237 | 19-Dec-24 23-Dec-24 | IPC - 09 | Km 11+320 - PL20/P3 | PL20/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/193 MPSB/Str/201 | 2024-12-13 | IPC - 09 | Km 11+320 - PL20/P1 | PL20/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/213 MPSB/Str/243 | 2024-12-24 | IPC - 09 | Km 11+284 - PL19/P4 | PL19/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/208 MPSB/Str/244 | 20-Dec-24 24-Dec-24 | IPC - 09 | Km 11+320 - PR20/P1 | PR20/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/217 MPSB/Str/248 | 2024-12-25 | IPC - 09 | Km 11+284 - PL19/P2 | PL19/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/218 MPSB/Str/249 | 2024-12-25 | IPC - 09 | Km 11+320 - PR20/P3 | PR20/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/221 MPSB/Str/257 | 2024-12-26 | IPC - 09 | Km 11+212 - PR17/P2 | PR17/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/226 MPSB/Str/263 | 2024-12-28 | IPC - 09 | Km 11+212 - PR17/P4 | PR17/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/225 MPSB/Str/296 | 28-Dec-24 30-Dec-24 | IPC - 09 | Km 11+320 - PR20/P4 | PR20/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/230 MPSB/Str/273 | 2024-12-29 | IPC - 09 | Km 11+212 - PL17/P2 | PL17/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/232 MPSB/Str/275 | 2024-12-29 | IPC - 09 | Km 11+212 - PR17/P1 | PR17/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/231 MPSB/Str/274 | 2024-12-29 | IPC - 09 | Km 11+176 - PR16/P1 | PR16/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/242 MPSB/Str/285 | 2024-12-30 | IPC - 09 | Km 11+212 - PR17/P3 | PR17/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/254 MPSB/Str/313 | 2024-12-31 | IPC - 09 | Km 11+176 - PL16/P1 | PL16/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/234 MPSB/Str/283 | 2024-12-30 | IPC - 10 | Km 11+176 - PR16/P3 | PR16/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/255 MPSB/Str/314 | 2025-01-03 | IPC - 10 | Km 11+140 - PR15/P1 | PR15/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/256 MPSB/Str/315 | 2025-01-03 | IPC - 10 | Km 11+176 - PL16/P3 | PL16/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/258 MPSB/Str/317 | 2025-01-03 | IPC - 10 | Km 11+212 - PL17/P1 | PL17/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/257 MPSB/Str/322 | 3-Jan-25 6-Jan-25 | IPC - 10 | Km 11+140 - PL15/P1 | PL15/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/259 MPSB/Str/321 | 4-Jan-25 6-Jan-25 | IPC - 10 | Km 11+176 - PR16/P2 | PR16/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/261 MPSB/Str/323 | 2025-01-06 | IPC - 10 | Km 11+212 - PL17/P4 | PL17/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/266 MPSB/Str/320 | 7-Jan-25 6-Jan-25 | IPC - 10 | Km 11+140 - PR15/P2 | PR15/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/262 MPSB/Str/324 | 2025-01-07 | IPC - 10 | Km 11+104 - PL14/P1 | PL14/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/263 MPSB/Str/325 | 2025-01-07 | IPC - 10 | Km 11+176 - PL16/P2 | PL16/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/264 MPSB/Str/326 | 2025-01-07 | IPC - 10 | Km 11+176 - PR16/P4 | PR16/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/265 MPSB/Str/327 | 2025-01-07 | IPC - 10 | Km 11+140 - PR15/P5 | PR15/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/267 MPSB/Str/328 | 2025-01-08 | IPC - 10 | Km 11+140 - PL15/P2 | PL15/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/268 MPSB/Str/329 | 2025-01-08 | IPC - 10 | Km 11+104 - PR14/P2 | PR14/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/269 MPSB/Str/330 | 2025-01-08 | IPC - 10 | Km 11+176 - PL16/P4 | PL16/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/278 MPSB/Str/342 | 2025-01-10 | IPC - 10 | Km 11+104 - PL14/P2 | PL14/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/296 MPSB/Str/361 | 2025-01-13 | IPC - 10 | Km 11+140 - PR15/P3 | PR15/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/280 MPSB/Str/360 | 10-Jan-25 13-Jan-25 | IPC - 10 | Km 11+104 - PR14/P3 | PR14/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/349 MPSB/Str/415 | 2025-01-23 | IPC - 10 | Km 11+068 - PR13/P4 | PR13/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/302 MPSB/Str/364 | 2025-01-15 | IPC - 10 | Km 11+104 - PL14/P3 | PL14/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/298 MPSB/Str/362 | 2025-01-13 | IPC - 10 | Km 11+140 - PL15/P5 | PL15/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/303 MPSB/Str/365 | 2025-01-15 | IPC - 10 | Km 11+320 - PR20/P2 | PR20/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/304 MPSB/Str/368 | 2025-01-16 | IPC - 10 | Km 11+140 - PR15/P4 | PR15/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/305 MPSB/Str/369 | 2025-01-16 | IPC - 10 | Km 11+284 - PR19/P3 | PR19/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/318 MPSB/Str/379 | 2025-01-18 | IPC - 10 | Km 11+140 - PL15/P3 | PL15/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/311 MPSB/Str/373 | 2025-01-17 | IPC - 10 | Km 11+104 - PL14/P4 | PL14/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/332 MPSB/Str/393 | 2025-01-20 | IPC - 10 | Km 11+284 - PR19/P1 | PR19/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/338 MPSB/Str/402 | 2025-01-21 | IPC - 10 | Km 11+068 - PR13/P1 | PR13/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/330 MPSB/Str/404 | 20-Jan-25 22-Jan-25 | IPC - 10 | Km 11+104 - PR14/P1 | PR14/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/346 MPSB/Str/412 | 2025-01-23 | IPC - 10 | Km 11+284 - PR19/P2 | PR19/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/339 MPSB/Str/403 | 2025-01-22 | IPC - 10 | Km 11+284 - PR19/P4 | PR19/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/376 MPSB/Str/445 | 2025-01-28 | IPC - 10 | Km 11+068 - PL13/P3 | PL13/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/355 MPSB/Str/422 | 2025-01-24 | IPC - 10 | Km 11+032 - PR12/P3 | PR12/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/356 MPSB/Str/423 | 2025-01-24 | IPC - 10 | Km 11+032 - PL12/P4 | PL12/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/359 MPSB/Str/430 | 25-Jan-25 27-Jan-25 | IPC - 10 | Km 11+068 - PL13/P4 | PL13/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/363 MPSB/Str/428 | 2025-01-27 | IPC - 10 | Km 11+032 - PL12/P1 | PL12/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/364 MPSB/Str/429 | 2025-01-27 | IPC - 10 | Km 11+032 - PR12/P2 | PR12/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/381 MPSB/Str/451 | 2025-01-29 | IPC - 10 | Km 11+068 - PL13/P2 | PL13/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/383 MPSB/Str/453 | 2025-01-29 | IPC - 10 | Km 11+032 - PL12/P5 | PL12/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/384 MPSB/Str/454 | 2025-01-29 | IPC - 10 | Km 11+032 - PR12/P5 | PR12/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/388 MPSB/Str/463 | 2025-01-30 | IPC - 10 | Km 11+032 - PL12/P2 | PL12/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/315 MPSB/Str/372 | 2025-01-17 | IPC - 10 | Km 11+140 - PL15/P4 | PL15/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/319 MPSB/Str/378 | 2025-01-18 | IPC - 10 | Km 11+104 - PR14/P4 | PR14/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/253 MPSB/Str/312 | 2024-12-31 | IPC - 10 | Km 11+212 - PL17/P3 | PL17/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/375 MPSB/Str/440 | 2025-01-28 | IPC - 10 | Km 10+996 - PL11/P1 | PL11/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/382 MPSB/Str/452 | 2025-01-29 | IPC - 10 | Km 10+996 - PL11/P4 | PL11/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/377 MPSB/Str/446 | 2025-01-28 | IPC - 10 | Km 10+996 - PR11/P2 | PR11/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/337 MPSB/Str/419 | 21-Jan-25 23-Jan-25 | IPC - 10 | Km 11+068 - PL13/P1 | PL13/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/407 MPSB/Str/480 | 2025-02-03 | IPC - 11 | Km 10+996 - PR11/P3 | PR11/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/412 MPSB/Str/486 | 2025-02-04 | IPC - 11 | Km 10+996 - PL11/P2 | PL11/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/413 MPSB/Str/519 | 4-Feb-25 10-Feb-25 | IPC - 11 | Km 10+960 - PL10/P1 | PL10/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/414 MPSB/Str/488 | 2025-02-04 | IPC - 11 | Km 11+032 - PL12/P3 | PL12/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/429 MPSB/Str/520 | 7-Feb-25 10-Feb-25 | IPC - 11 | Km 10+996 - PR11/P1 | PR11/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/416 MPSB/Str/554 | 4-Feb-25 16-Feb-25 | IPC - 11 | Km 11+032 - PR12/P1 | PR12/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/430 MPSB/Str/498 | 2025-02-07 | IPC - 11 | Km 10+960 - PR10/P3 | PR10/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/472 MPSB/Str/551 | 2025-02-16 | IPC - 11 | Km 11+032 - PR12/P4 | PR12/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/439 MPSB/Str/518 | 8-Feb-25 10-Feb-25 | IPC - 11 | Km 10+996 - PL11/P3 | PL11/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/450 MPSB/Str/555 | 11-Feb-25 17-Feb-25 | IPC - 11 | Km 11+356 - PL21/P1 | PL21/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/451 MPSB/Str/553 | 11-Feb-25 16-Feb-25 | IPC - 11 | Km 11+356 - PR21/P1 | PR21/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/458 MPSB/Str/527 | 2025-02-12 | IPC - 11 | Km 11+068 - PR13/P3 | PR13/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/462 MPSB/Str/532 | 2025-02-13 | IPC - 11 | Km 10+996 - PR11/P4 | PR11/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/463 MPSB/Str/533 | 2025-02-13 | IPC - 11 | Km 10+960 - PR10/P2 | PR10/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/464 MPSB/Str/534 | 2025-02-13 | IPC - 11 | Km 11+068 - PR13/P2 | PR13/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/473 MPSB/Str/714 | 16-Feb-25 28-Feb-25 | IPC - 11 | Km 10+960 - PL10/P4 | PL10/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/478 MPSB/Str/556 | 2025-02-17 | IPC - 11 | Km 10+960 - PR10/P4 | PR10/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/479 MPSB/Str/557 | 2025-02-17 | IPC - 11 | Km 10+924 - PL9/P1 | PL9/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/497 MPSB/Str/567 | 2025-02-19 | IPC - 11 | Km 10+960 - PL10/P2 | PL10/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/522 MPSB/Str/582 | 2025-02-21 | IPC - 11 | Km 11+356 - PR21/P2 | PR21/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/513 MPSB/Str/580 | 2025-02-20 | IPC - 11 | Km 10+924 - PR9/P2 | PR9/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/514 MPSB/Str/581 | 2025-02-20 | IPC - 11 | Km 10+924 - PL9/P4 | PL9/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/516 MPSB/Str/583 | 2025-02-21 | IPC - 11 | Km 10+960 - PR10/P1 | PR10/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/517 MPSB/Str/611 | 21-Feb-25 24-Feb-25 | IPC - 11 | Km 10+924 - PL9/P5 | PL9/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/525 MPSB/Str/593 | 2025-02-22 | IPC - 11 | Km 10+924 - PR9/P3 | PR9/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Str/610 | 2025-02-24 | IPC - 11 | Km 10+888 - PL8/P4 | PL8/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/538 MPSB/Str/612 | 2025-02-24 | IPC - 11 | Km 11+356 - PL21/P2 | PL21/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/539 MPSB/Str/621 | 24-Feb-25 25-Feb-25 | IPC - 11 | Km 10+888 - PR8/P2 | PR8/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/540 MPSB/Str/622 | 24-Feb-25 25-Feb-25 | IPC - 11 | Km 10+924 - PR9/P5 | PR9/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/547 MPSB/Str/623 | 2025-02-25 | IPC - 11 | Km 10+924 - PL9/P2 | PL9/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/548 MPSB/Str/649 | 25-Feb-25 26-Feb-25 | IPC - 11 | Km 11+356 - PR21/P3 | PR21/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/565 MPSB/Str/646 | 2025-02-26 | IPC - 11 | Km 10+888 - PL8/P1 | PL8/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/566 MPSB/Str/647 | 2025-02-26 | IPC - 11 | Km 10+888 - PR8/P3 | PR8/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/567 MPSB/Str/648 | 2025-02-26 | IPC - 11 | Km 10+852 - PR7/P2 | PR7/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/586 MPSB/Str/662 | 2025-02-27 | IPC - 11 | Km 11+356 - PL21/P3 | PL21/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/635 MPSB/Str/720 | 2025-02-28 | IPC - 11 | Km 11+356 - PL21/P4 | PL21/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/587 MPSB/Str/663 | 2025-02-27 | IPC - 11 | Km 10+924 - PL9/P3 | PL9/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/588 MPSB/Str/664 | 2025-02-27 | IPC - 11 | Km 10+924 - PR9/P4 | PR9/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/589 MPSB/Str/665 | 2025-02-27 | IPC - 11 | Km 10+852 - PL7/P4 | PL7/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/630 MPSB/Str/715 | 2025-02-28 | IPC - 11 | Km 10+924 - PR9/P1 | PR9/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/827 MPSB/Str/948 | 2025-03-29 | IPC - 13 | Km 10+744 - PR4/P2 | PR4/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/850 MPSB/Str/984 | 2025-03-30 | IPC - 13 | Km 10+780 - PR5/P1 | PR5/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/826 MPSB/Str/945 | 2025-03-28 | IPC - 13 | Km 10+780 - PR5/P2 | PR5/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/830 MPSB/Str/951 | 2025-03-29 | IPC - 13 | Km 10+780 - PR5/P3 | PR5/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/866 MPSB/Str/1004 | 2025-03-31 | IPC - 13 | Km 10+780 - PR5/P4 | PR5/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/822 MPSB/Str/941 | 2025-03-28 | IPC - 13 | Km 10+780 - PL5/P1 | PL5/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/824 MPSB/Str/943 | 2025-03-28 | IPC - 13 | Km 10+780 - PL5/P4 | PL5/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/670 MPSB/Str/756 | 2025-03-08 | IPC - 13 | Km 10+816 - PL6/P1 | PL6/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/751 MPSB/Str/880 | 20-Mar-25 24-Mar-25 | IPC - 13 | Km 10+816 - PL6/P2 | PL6/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/782 MPSB/Str/891 | 2025-03-25 | IPC - 13 | Km 10+816 - PL6/P3 | PL6/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/704 MPSB/Str/809 | 12-Mar-25 17-Mar-25 | IPC - 13 | Km 10+816 - PL6/P4 | PL6/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/728 MPSB/Str/817 | 2025-03-18 | IPC - 13 | Km 10+816 - PL6/P5 | PL6/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/811 MPSB/Str/934 | 2025-03-27 | IPC - 13 | Km 10+816 - PR6/P1 | PR6/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/666 MPSB/Str/750 | 2025-03-07 | IPC - 13 | Km 10+816 - PR6/P2 | PR6/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/678 MPSB/Str/801 | 10-Mar-25 13-Mar-25 | IPC - 13 | Km 10+816 - PR6/P3 | PR6/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/815 MPSB/Str/938 | 2025-03-27 | IPC - 13 | Km 10+816 - PR6/P4 | PR6/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/794 MPSB/Str/909 | 2025-03-26 | IPC - 13 | Km 10+816 - PR6/P5 | PR6/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/665 MPSB/Str/749 | 2025-03-07 | IPC - 13 | Km 10+852 - PL7/P1 | PL7/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/669 MPSB/Str/755 | 2025-03-08 | IPC - 13 | Km 10+852 - PL7/P2 | PL7/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/677 MPSB/Str/765 | 2025-03-10 | IPC - 13 | Km 10+852 - PL7/P3 | PL7/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/742 MPSB/Str/834 | 2025-03-19 | IPC - 13 | Km 10+852 - PR7/P1 | PR7/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/659 MPSB/Str/740 | 2025-03-06 | IPC - 13 | Km 10+852 - PR7/P3 | PR7/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/752 MPSB/Str/879 | 21-Mar-25 24-Mar-25 | IPC - 13 | Km 10+852 - PR7/P4 | PR7/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/783 MPSB/Str/892 | 2025-03-25 | IPC - 13 | Km 10+888 - PL8/P2 | PL8/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/676 MPSB/Str/764 | 2025-03-10 | IPC - 13 | Km 10+888 - PL8/P3 | PL8/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/813 MPSB/Str/936 | 2025-03-27 | IPC - 13 | Km 10+888 - PR8/P1 | PR8/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/795 MPSB/Str/910 | 2025-03-26 | IPC - 13 | Km 10+888 - PR8/P4 | PR8/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/657 MPSB/Str/738 | 2025-03-06 | IPC - 13 | Km 10+960 - PL10/P3 | PL10/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/739 MPSB/Str/829 | 2025-03-18 | IPC - 13 | Km 11+248 - PL18/P1 | PL18/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/744 MPSB/Str/836 | 2025-03-20 | IPC - 13 | Km 11+248 - PL18/P2 | PL18/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/764 MPSB/Str/815 | 10-Mar-25 17-Mar-25 | IPC - 13 | Km 11+248 - PL18/P3 | PL18/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/792 MPSB/Str/907 | 2025-03-26 | IPC - 13 | Km 11+248 - PL18/P4 | PL18/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/781 MPSB/Str/890 | 2025-03-25 | IPC - 13 | Km 11+248 - PL18/P5 | PL18/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/753 MPSB/Str/847 | 2025-03-21 | IPC - 13 | Km 11+248 - PR18/P1 | PR18/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/776 MPSB/Str/908 | 24-Mar-25 26-Mar-25 | IPC - 13 | Km 11+248 - PR18/P2 | PR18/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/796 MPSB/Str/937 | 2025-03-27 | IPC - 13 | Km 11+248 - PR18/P3 | PR18/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/812 MPSB/Str/935 | 2025-03-27 | IPC - 13 | Km 11+248 - PR18/P4 | PR18/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/796 MPSB/Str/911 | 2025-03-26 | IPC - 13 | Km 11+248 - PR18/P5 | PR18/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/658 MPSB/Str/739 | 2025-03-06 | IPC - 13 | Km 11+356 - PL21/P5 | PL21/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/757 MPSB/Str/852 | 2025-03-22 | IPC - 13 | Km 11+356 - PL21/P6 | PL21/P6 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/748 MPSB/Str/843 | 2025-03-20 | IPC - 13 | Km 11+356 - PR21/P4 | PR21/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/729 MPSB/Str/818 | 2025-03-18 | IPC - 13 | Km 11+356 - PR21/P5 | PR21/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/689 MPSB/Str/777 | 2025-03-11 | IPC - 13 | Km 11+356 - PR21/P6 | PR21/P6 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/936 MPSB/Str/1065 | 2025-04-08 | IPC - 14 | Km 10+600 - PL0/P1 | PL0/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/956 MPSB/Str/1093 | 2025-04-10 | IPC - 14 | Km 10+600 - PL0/P5 | PL0/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/947 MPSB/Str/1081 | 2025-04-09 | IPC - 14 | Km 10+600 - PL0/P6 | PL0/P6 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1061 MPSB/Str/1229 | 2025-04-22 | IPC - 14 | Km 10+600 - PR0/P1 | PR0/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/953 MPSB/Str/1090 | 2025-04-10 | IPC - 14 | Km 10+600 - PR0/P2 | PR0/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/935 MPSB/Str/1064 | 2025-04-08 | IPC - 14 | Km 10+600 - PR0/P3 | PR0/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/937 MPSB/Str/1066 | 2025-04-08 | IPC - 14 | Km 10+600 - PR0/P4 | PR0/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/946 MPSB/Str/1080 | 2025-04-09 | IPC - 14 | Km 10+600 - PR0/P5 | PR0/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1014 MPSB/Str/1239 | 17-Apr-25 24-Apr-25 | IPC - 14 | Km 10+600 - PR0/P6 | PR0/P6 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/955 MPSB/Str/1092 | 2025-04-10 | IPC - 14 | Km 10+636 - PL1/P1 | PL1/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1012 MPSB/Str/1169 | 2025-04-17 | IPC - 14 | Km 10+636 - PL1/P2 | PL1/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1055 MPSB/Str/1213 | 2025-04-21 | IPC - 14 | Km 10+636 - PL1/P3 | PL1/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1005 MPSB/Str/1157 | 2025-04-16 | IPC - 14 | Km 10+636 - PL1/P4 | PL1/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1062 MPSB/Str/1230 | 2025-04-22 | IPC - 14 | Km 10+636 - PR1/P1 | PR1/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/954 MPSB/Str/1091 | 2025-04-10 | IPC - 14 | Km 10+636 - PR1/P2 | PR1/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/959 MPSB/Str/1144 | 11-Apr-25 15-Apr-25 | IPC - 14 | Km 10+636 - PR1/P3 | PR1/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1109 MPSB/Str/1282 | 2025-04-26 | IPC - 14 | Km 10+636 - PR1/P4 | PR1/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1094 MPSB/Str/1264 | 2025-04-25 | IPC - 14 | Km 10+672 - PR2/P2 | PR2/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1154 MPSB/Str/1344 | 2025-04-30 | IPC - 14 | Km 10+672 - PR2/P3 | PR2/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1025 MPSB/Str/1179 | 2025-04-18 | IPC - 14 | Km 10+708 - PL3/P1 | PL3/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1063 MPSB/Str/1237 | 22-Apr-25 24-Apr-25 | IPC - 14 | Km 10+708 - PL3/P2 | PL3/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1106 MPSB/Str/1279 | 2025-04-26 | IPC - 14 | Km 10+708 - PR3/P1 | PR3/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1053 MPSB/Str/1211 | 2025-04-21 | IPC - 14 | Km 10+708 - PR3/P2 | PR3/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1070 MPSB/Str/1236 | 2025-04-23 | IPC - 14 | Km 10+708 - PR3/P3 | PR3/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/960 MPSB/Str/1100 | 2025-04-11 | IPC - 14 | Km 10+744 - PL4/P1 | PL4/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1008 MPSB/Str/1163 | 2025-04-17 | IPC - 14 | Km 10+744 - PL4/P2 | PL4/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1013 MPSB/Str/1170 | 2025-04-17 | IPC - 14 | Km 10+744 - PL4/P3 | PL4/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/988 MPSB/Str/1129 | 2025-04-14 | IPC - 14 | Km 10+744 - PL4/P4 | PL4/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1024 MPSB/Str/1178 | 2025-04-18 | IPC - 14 | Km 10+744 - PR4/P1 | PR4/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/948 MPSB/Str/1082 | 2025-04-09 | IPC - 14 | Km 10+744 - PR4/P3 | PR4/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1011 MPSB/Str/1168 | 2025-04-17 | IPC - 14 | Km 10+744 - PR4/P4 | PR4/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/944 MPSB/Str/1073 | 2025-04-08 | IPC - 14 | Km 10+780 - PL5/P2 | PL5/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/945 MPSB/Str/1079 | 2025-04-09 | IPC - 14 | Km 10+780 - PL5/P3 | PL5/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1196 MPSB/Str/1408 | 2025-04-30 | IPC - 14 | Km 10+302 - PL2/P1 | PL2/P1 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1197 MPSB/Str/1409 | 2025-04-30 | IPC - 14 | Km 10+302 - PR2/P2 | PR2/P2 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1172 MPSB/Str/1375 | 2025-04-30 | IPC - 14 | Km 10+338 - PL3/P5 | PL3/P5 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1169 MPSB/Str/1371 | 2025-04-30 | IPC - 14 | Km 10+338 - PL3/P6 | PL3/P6 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1156 MPSB/Str/1348 | 2025-04-30 | IPC - 14 | Km 10+338 - PR3/P3 | PR3/P3 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1151 MPSB/Str/1341 | 2025-04-30 | IPC - 14 | Km 10+338 - PR3/P4 | PR3/P4 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1339 MPSB/Str/1572 | 24-May-25 26-May-25 | IPC - 15 | Km 10+672 - PR2/P1 | PR2/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1262 MPSB/Str/1511 | 12-May-25 17-May-25 | IPC - 15 | Km 10+672 - PR2/P4 | PR2/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1229 MPSB/Str/1433 | 2025-05-06 | IPC - 15 | Km 10+708 - PR3/P5 | PR3/P5 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1133 MPSB/Str/1307 | 2025-04-28 | IPC - 15 | Km 10+708 - PR3/P4 | PR3/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1350 MPSB/Str/1574 | 2025-05-26 | IPC - 15 | Km 10+230 - PL0/P4 | PL0/P4 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1370 MPSB/Str/1587 | 2025-05-28 | IPC - 15 | Km 10+230 - PL0/P5 | PL0/P5 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1369 MPSB/Str/1586 | 2025-05-28 | IPC - 15 | Km 10+230 - PR0/P6 | PR0/P6 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1363 MPSB/Str/1581 | 2025-05-27 | IPC - 15 | Km 10+266 - PL1/P1 | PL1/P1 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1330 MPSB/Str/1545 | 2025-05-22 | IPC - 15 | Km 10+266 - PL1/P2 | PL1/P2 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1320 MPSB/Str/1534 | 2025-05-20 | IPC - 15 | Km 10+266 - PL1/P3 | PL1/P3 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1367 MPSB/Str/1584 | 2025-05-28 | IPC - 15 | Km 10+266 - PL1/P4 | PL1/P4 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1110 MPSB/Str/1283 | 2025-04-26 | IPC - 15 | Km 10+266 - PL2/P2 | PL2/P2 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1220 MPSB/Str/1421 | 2025-05-06 | IPC - 15 | Km 10+302 - PL2/P3 | PL2/P3 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1242 MPSB/Str/1501 | 9-May-25 16-May-25 | IPC - 15 | Km 10+302 - PL2/P4 | PL2/P4 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1219 MPSB/Str/1420 | 2025-05-06 | IPC - 15 | Km 10+302 - PR2/P1 | PR2/P1 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1243 MPSB/Str/1452 | 2025-05-09 | IPC - 15 | Km 10+302 - PR2/P3 | PR2/P3 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1309 MPSB/Str/1524 | 2025-05-19 | IPC - 15 | Km 10+302 - PR2/P4 | PR2/P4 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1349 MPSB/Str/1573 | 2025-05-26 | IPC - 15 | Km 10+338 - PL3/P1 | PL3/P1 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1337 MPSB/Str/1558 | 2025-05-24 | IPC - 15 | Km 10+338 - PL3/P2 | PL3/P2 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1300 MPSB/Str/1527 | 17-May-25 19-May-25 | IPC - 15 | Km 10+338 - PL3/P3 | PL3/P3 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1221 MPSB/Str/1422 | 2025-05-13 | IPC - 15 | Km 10+338 - PL3/P4 | PL3/P4 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1308 MPSB/Str/1544 | 19-May-25 22-May-25 | IPC - 15 | Km 10+338 - PR3/P1 | PR3/P1 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1222 MPSB/Str/1450 | 2025-05-06 | IPC - 15 | Km 10+338 - PR3/P2 | PR3/P2 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1170 MPSB/Str/1423 | 2025-05-06 | IPC - 15 | Km 10+338 - PR3/P5 | PR3/P5 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1241 MPSB/Str/1502 | 9-May-25 16-May-25 | IPC - 15 | Km 10+338 - PR3/P6 | PR3/P6 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1431 MPSB/Str/1672 | 2025-06-17 | IPC - 16 | Km 10+230 - PL0/P1 | PL0/P1 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1415 MPSB/Str/1652 | 2025-06-14 | IPC - 16 | Km 10+230 - PL0/P2 | PL0/P2 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1408 MPSB/Str/1643 | 2025-06-09 | IPC - 16 | Km 10+230 - PL0/P3 | PL0/P3 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1405 MPSB/Str/1637 | 2025-06-06 | IPC - 16 | Km 10+230 - PL0/P6 | PL0/P6 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1432 MPSB/Str/1673 | 2025-06-17 | IPC - 16 | Km 10+230 - PR0/P1 | PR0/P1 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1422 MPSB/Str/1660 | 2025-06-14 | IPC - 16 | Km 10+230 - PR0/P2 | PR0/P2 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1414 MPSB/Str/1651 | 2025-06-11 | IPC - 16 | Km 10+230 - PR0/P3 | PR0/P3 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1389 MPSB/Str/1641 | 30-May-25 9-Jun-25 | IPC - 16 | Km 10+230 - PR0/P4 | PR0/P4 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1412 MPSB/Str/1649 | 2025-06-10 | IPC - 16 | Km 10+230 - PR0/P5 | PR0/P5 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1416 MPSB/Str/1655 | 2025-06-12 | IPC - 16 | Km 10+266 - PR1/P1 | PR1/P1 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1368 MPSB/Str/1642 | 28-May-25 9-Jun-25 | IPC - 16 | Km 10+266 - PR1/P2 | PR1/P2 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1413 MPSB/Str/1650 | 2025-06-10 | IPC - 16 | Km 10+266 - PR1/P3 | PR1/P3 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1421 MPSB/Str/1659 | 2025-06-14 | IPC - 16 | Km 10+266 - PR1/P4 | PR1/P4 - WV1
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1437 MPSB/Str/1679 | 2025-06-18 | IPC - 16 | Km 10+600 - PL0/P2 | PL0/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1446 MPSB/Str/1688 | 2025-06-21 | IPC - 16 | Km 10+600 - PL0/P3 | PL0/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1445 MPSB/Str/1687 | 2025-06-20 | IPC - 16 | Km 10+600 - PL0/P4 | PL0/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1440 MPSB/Str/1683 | 2025-06-19 | IPC - 16 | Km 10+672 - PL2/P1 | PL2/P1 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1459 MPSB/Str/1707 | 2025-06-27 | IPC - 16 | Km 10+672 - PL2/P2 | PL2/P2 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1465 MPSB/Str/1719 | 2025-06-28 | IPC - 16 | Km 10+672 - PL2/P3 | PL2/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1454 MPSB/Str/1704 | 23-Jun-25 26-Jun-25 | IPC - 16 | Km 10+672 - PL2/P4 | PL2/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1439 MPSB/Str/1682 | 2025-06-19 | IPC - 16 | Km 10+708 - PL3/P3 | PL3/P3 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1430 MPSB/Str/1671 | 2025-06-17 | IPC - 16 | Km 10+708 - PL3/P4 | PL3/P4 - WV2
501.a.1 | For Wetland Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1436 MPSB/Str/1678 | 2025-06-18 | IPC - 16 | Km 10+708 - PL3/P5 | PL3/P5 - WV2
| Cumulative paid upto this Bill | Nos. |  | 236
| Paid upto previous Bill | Nos. |  | 236
| To be paid in this Bill | Nos. |  | 0
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/860 MPSB/Sur/847 MPSB/Str/980 MPSB/Str/981 | 23-Mar-25 30-Mar-25 30-Mar-25 30-Mar-25 | IPC - 13 | Km 11+320 - PR20 - Pilecap | PR20 - Pilecap - WV2 | Excavation Survey checking Reinforcement Check Shuttering & Concreting
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/808 MPSB/Sur/786 MPSB/Str/898 MPSB/Str/899 | 17-Mar-25 26-Mar-25 26-Mar-25 26-Mar-25 | IPC - 13 | Km 11+320 - PL20 - Pilecap | PL20 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/861 MPSB/Sur/897 MPSB/Str/1014 MPSB/Str/1015 | 23-Mar-25 26-Mar-25 31-Mar-25 31-Mar-25 | IPC - 13 | Km 11+284 - PR19 - Pilecap | PR19 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/928 MPSB/Sur/958 MPSB/Str/1095 MPSB/Str/1096 | 7-Apr-25 10-Apr-25 10-Apr-25 10-Apr-25 | IPC - 14 | Km 11+212 - PR17 - Pilecap | PR17 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/929 MPSB/Sur/998 MPSB/Str/1138 MPSB/Str/1139 | 7-Apr-25 15-Apr-25 15-Apr-25 15-Apr-25 | IPC - 14 | Km 11+212 - PL17 - Pilecap | PL17 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/1033 MPSB/Sur/1052 MPSB/Str/1209 MPSB/Str/1210 | 2-Apr-25 21-Apr-25 21-Apr-25 21-Apr-25 | IPC - 14 | Km 11+176 - PR16 - Pilecap | PR16 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/1032 MPSB/Sur/931 MPSB/Str/1164 MPSB/Str/1165 | 2-Apr-25 7-Apr-25 17-Apr-25 17-Apr-25 | IPC - 14 | Km 11+176 - PL16 - Pilecap | PL16 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/932 MPSB/Sur/980 MPSB/Str/1119 MPSB/Str/1120 | 5-Apr-25 12-Apr-25 12-Apr-25 12-Apr-25 | IPC - 14 | Km 11+140 - PL15 - Pilecap | PL15 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1193 MPSB/Sur/1117 MPSB/Str/1291 MPSB/Str/1292 | 19-Apr-25 26-Apr-25 26-Apr-25 26-Apr-25 | IPC - 14 | Km 11+140 - PR15 - Pilecap | PR15 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/1045 MPSB/Sur/1010 MPSB/Str/1166 MPSB/Str/1167 | 5-Apr-25 17-Apr-25 17-Apr-25 17-Apr-25 | IPC - 14 | Km 11+104 - PR14 - Pilecap | PR14 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/1046 MPSB/Sur/1060 MPSB/Str/1254 MPSB/Str/1255 | 5-Apr-25 22-Apr-25 24-Apr-25 24-Apr-25 | IPC - 14 | Km 11+068 - PR13 - Pilecap | PR13 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/1182 MPSB/Sur/1027 MPSB/Str/1287 MPSB/Str/1288 | 18-Apr-25 18-Apr-25 26-Apr-25 26-Apr-25 | IPC - 14 | Km 10+996 - PR11 - Pilecap | PR11 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/1183 MPSB/Sur/1028 MPSB/Str/1389 MPSB/Str/1390 | 18-Apr-25 18-Apr-25 30-Apr-25 30-Apr-25 | IPC - 14 | Km 10+960 - PR10 - Pilecap | PR10 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/1184 MPSB/Sur/1344 MPSB/Str/1565 MPSB/Str/1566 | 18-Apr-25 24-May-25 24-May-25 24-May-25 | IPC - 15 | Km 11+248 - PR18 - Pilecap | PR18 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/1250 MPSB/Sur/1406 MPSB/Str/1638 MPSB/Str/1639 | 24-Apr-25 6-Jun-25 6-Jun-25 6-Jun-25 | IPC - 16 | Km 10+888 - PR8 - Pilecap | PR8 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Str/1251 MPSB/Sur/1246 MPSB/Str/1456 MPSB/Str/1457 | 24-Apr-25 9-May-25 9-May-25 9-May-25 | IPC - 16 | Km 10+924 - PR9 - Pilecap | PR9 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1495 MPSB/Str/1768 MPSB/Str/1769 | 7-Jul-25 7-Jul-25 7-Jul-25 | IPC - 18 | Km 10+852 - PR7 - Pilecap | PR7 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1638 MPSB/Str/1962 MPSB/Str/1963 | 2-Aug-25 2-Aug-25 2-Aug-25 | IPC - 19 | Km 11+248 - PL18 - Pilecap | PL18 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1718 MPSB/Str/2068 MPSB/Str/2069 | 23-Aug-25 23-Aug-25 23-Aug-25 | IPC - 19 | Km 10+672 - PR2 - Pilecap | PR2 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1747 MPSB/Str/2112 MPSB/Str/2113 | 30-Aug-25 30-Aug-25 30-Aug-25 | IPC - 19 | Km 10+636 - PR1 - Pilecap | PR1 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1784 MPSB/Str/2169 MPSB/Str/2170 | 6-Sep-25 6-Sep-25 6-Sep-25 | IPC - 20 | Km 11+356 - PR21 - Pilecap | PR21 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1808 MPSB/Str/2212 MPSB/Str/2213 | 11-Sep-25 11-Sep-25 11-Sep-25 | IPC - 20 | Km 11+356 - PL21 - Pilecap | PL21 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1889 MPSB/Str/2367 MPSB/Str/2368 | 30-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | Km 10+600 - PL0 - Pilecap | PL0 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1900 MPSB/Str/2369 MPSB/Str/2370 | 30-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | Km 11+104 - PL14 - Pilecap | PL14 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1942 MPSB/Str/2423 MPSB/Str/2424 | 08-Oct-25 08-Oct-25 08-Oct-25 | IPC - 22 | Km 11+284 - PL19 - Pilecap | PL19 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/1983 MPSB/Str/2473 MPSB/Str/2474 | 14-Oct-25 14-Oct-25 14-Oct-25 | IPC - 22 | Km 11+068 - PL13 - Pilecap | PL13 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2007 MPSB/Str/2516 MPSB/Str/2517 | 18-Oct-25 18-Oct-25 18-Oct-25 | IPC - 22 | Km 11+032 - PL12 - Pilecap | PL12 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2032 MPSB/Str/2554 MPSB/Str/2555 | 23-Oct-25 23-Oct-25 23-Oct-25 | IPC - 22 | Km 10+996 - PL11 - Pilecap | PL11 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2058 MPSB/Str/2595 MPSB/Str/2596 | 27-Oct-25 27-Oct-25 27-Oct-25 | IPC - 22 | Km 10+960 - PL10 - Pilecap | PL10 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2151 MPSB/Str/2740 MPSB/Str/2741 | 08-Nov-25 08-Nov-25 08-Nov-25 | IPC - 23 | Km 10+600 - PR0 - Pilecap | PR0 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2171 MPSB/Str/2768 MPSB/Str/2769 | 11-Nov-25 11-Nov-25 11-Nov-25 | IPC - 23 | Km 10+924 - PL9 - Pilecap | PL9 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2187 MPSB/Str/2798 MPSB/Str/2799 | 14-Nov-25 14-Nov-25 14-Nov-25 | IPC - 23 | Km 11+032 - PR12 - Pilecap | PR12 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2221 MPSB/Str/2849 MPSB/Str/2850 | 19-Nov-25 19-Nov-25 19-Nov-25 | IPC - 23 | Km 10+888 - PL8 - Pilecap | PL8 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2241 MPSB/Str/2879 MPSB/Str/2880 | 21-Nov-25 21-Nov-25 21-Nov-25 | IPC - 23 | Km 10+636 - PL1 - Pilecap | PL1 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2245 MPSB/Str/2888 MPSB/Str/2889 | 22-Nov-25 22-Nov-25 22-Nov-25 | IPC - 23 | Km 10+852 - PL7 - Pilecap | PL7 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2263 MPSB/Str/2919 MPSB/Str/2920 | 25-Nov-25 25-Nov-25 25-Nov-25 | IPC - 23 | Km 10+708 - PR3 - Pilecap | PR3 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2283 MPSB/Str/2945 MPSB/Str/2946 | 27-Nov-25 27-Nov-25 27-Nov-25 | IPC - 23 | Km 10+780 - PR5 - Pilecap | PR5 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2314 MPSB/Str/2999 MPSB/Str/3000 | 30-Nov-25 30-Nov-25 30-Nov-25 | IPC - 23 | Km 10+744 - PR4 - Pilecap | PR4 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2513 MPSB/Str/3293 MPSB/Str/3294 | 27-Dec-25 27-Dec-25 27-Dec-25 | IPC - 25 | Km 10+266 - PL1 - Pilecap | PL1 - Pilecap - WV1
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2407 MPSB/Str/3131 MPSB/Str/3132 | 13-Dec-25 13-Dec-25 13-Dec-25 | IPC - 25 | Km 10+338 - PR3 - Pilecap | PR3 - Pilecap - WV1
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2410 MPSB/Str/3138 MPSB/Str/3139 | 15-Dec-25 15-Dec-25 15-Dec-25 | IPC - 25 | Km 10+338 - PL3 - Pilecap | PL3 - Pilecap - WV1
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2411 MPSB/Str/3140 MPSB/Str/3141 | 15-Dec-25 15-Dec-25 15-Dec-25 | IPC - 25 | Km 10+302 - PR2 - Pilecap | PR2 - Pilecap - WV1
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2412 MPSB/Str/3142 MPSB/Str/3143 | 15-Dec-25 15-Dec-25 15-Dec-25 | IPC - 25 | Km 10+816 - PR6 - Pilecap | PR6 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2442 MPSB/Str/3184 MPSB/Str/3185 | 18-Dec-25 18-Dec-25 18-Dec-25 | IPC - 25 | Km 10+672 - PL2 - Pilecap | PL2 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2465 MPSB/Str/3225 MPSB/Str/3226 | 22-Dec-25 22-Dec-25 22-Dec-25 | IPC - 25 | Km 10+780 - PL5 - Pilecap | PL5 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2492 MPSB/Str/3267 MPSB/Str/3268 | 25-Dec-25 25-Dec-25 25-Dec-25 | IPC - 25 | Km 10+708 - PL3 - Pilecap | PL3 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2550 MPSB/Str/3348 MPSB/Str/3349 | 30-Dec-25 30-Dec-25 30-Dec-25 | IPC - 25 | Km 10+744 - PL4 - Pilecap | PL4 - Pilecap - WV2
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2709 MPSB/Str/3565 MPSB/Str/3566 | 19-Jan-26 19-Jan-26 19-Jan-26 | IPC - 26 | Km 10+266 - PR1 - Pilecap | PR1 - Pilecap - WV1
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2640 MPSB/Str/3473 MPSB/Str/3474 | 9-Jan-26 9-Jan-26 9-Jan-26 | IPC - 26 | Km 10+230 - PL0 - Pilecap | PL0 - Pilecap - WV1
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2682 MPSB/Str/3527 MPSB/Str/3528 | 15-Jan-26 15-Jan-26 15-Jan-26 | IPC - 26 | Km 10+230 - PR0 - Pilecap | PR0 - Pilecap - WV1
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2879 MPSB/Str/3777 MPSB/Str/3778 | 6-Feb-26 6-Feb-26 6-Feb-26 | IPC - 27 | Km 10+302 - PL2 - Pilecap | PL2 - Pilecap - WV1
501.a.2 | For Wetland Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2926 MPSB/Str/3851 MPSB/Str/3852 | 14-Feb-26 14-Feb-26 14-Feb-26 | IPC - 27 | Km 10+816 - PL6 - Pilecap | PL6 - Pilecap - WV2
| Cumulative paid upto this Bill | Nos. |  | 52
| Paid upto previous Bill | Nos. |  | 52
| To be paid in this Bill | Nos. |  | 0
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/31 MPSB/Str/24 | 2024-09-29 | IPC - 07 | Km 5+426 - PR1/P4 | PR1/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/40 MPSB/Str/33 | 2024-10-03 | IPC - 07 | Km 5+462 - PL2/P3 | PL2/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/43 MPSB/Str/36 | 2024-10-05 | IPC - 07 | Km 5+462 - PR2/P4 | PR2/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/42 MPSB/Str/39 | 5-Oct-24 8-Oct-24 | IPC - 07 | Km 5+462 - PL2/P4 | PL2/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/41 MPSB/Str/40 | 4-Oct-24 14-Oct-24 | IPC - 07 | Km 5+426 - PL1/P4 | PL1/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/44 MPSB/Str/41 | 8-Oct-24 14-Oct-24 | IPC - 07 | Km 5+462 - PR2/P3 | PR2/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/46 MPSB/Str/42 | 11-Oct-24 17-Oct-24 | IPC - 07 | Km 5+426 - PR1/P3 | PR1/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/47 MPSB/Str/43 | 16-Oct-24 17-Oct-24 | IPC - 07 | Km 5+426 - PL1/P3 | PL1/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/48 MPSB/Str/44 | 17-Oct-24 18-Oct-24 | IPC - 07 | Km 5+462 - PR2/P2 | PR2/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/50 MPSB/Str/45 | 2024-10-19 | IPC - 07 | Km 5+426 - PR1/P2 | PR1/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/51 MPSB/Str/46 | 2024-10-21 | IPC - 07 | Km 5+462 - PR2/P1 | PR2/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/51 MPSB/Str/51 | 21-Oct-24 25-Oct-24 | IPC - 07 | Km 5+426 - PR1/P1 | PR1/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/53 MPSB/Str/52 | 23-Oct-24 25-Oct-24 | IPC - 07 | Km 5+462 - PL2/P2 | PL2/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/55 MPSB/Str/54 | 24-Oct-24 25-Oct-24 | IPC - 07 | Km 5+426 - PL1/P2 | PL1/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/59 MPSB/Str/55 | 2024-10-28 | IPC - 07 | Km 9+224 - PR31/P3 | PR31/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/61 MPSB/Str/56 | 28-Oct-24 29-Oct-24 | IPC - 07 | Km 5+462 - PL2/P1 | PL2/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/65 MPSB/Str/59 | 2024-10-29 | IPC - 07 | Km 9+244 - PR31/P2 | PR31/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/63 MPSB/Str/61 | 29-Oct-24 30-Oct-24 | IPC - 07 | Km 5+426 - PR1/P5 | PR1/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/64 MPSB/Str/58 | 2024-10-29 | IPC - 07 | Km 9+244 - PL31/P2 | PL31/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/69 MPSB/Str/63 | 2024-10-30 | IPC - 07 | Km 9+244 - PR31/P4 | PR31/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/67 MPSB/Str/65 | 30-Oct-24 31-Oct-24 | IPC - 07 | Km 5+462 - PR2/P5 | PR2/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/72 MPSB/Str/76 | 31-Oct-24 8-Nov-24 | IPC - 08 | Km 5+426 - PL1/P5 | PL1/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/71 MPSB/Str/77 | 31-Oct-24 8-Nov-24 | IPC - 08 | Km 5+462 - PL2/P5 | PL2/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/83 MPSB/Str/78 | 2024-11-08 | IPC - 08 | Km 5+426 - PL1/P1 | PL1/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/84 MPSB/Str/79 | 2024-11-08 | IPC - 08 | Km 9+244 - PL31/P4 | PL31/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/85 MPSB/Str/80 | 2024-11-08 | IPC - 08 | Km 9+352 - PR34/P4 | PR34/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/86 MPSB/Str/82 | 9-Nov-24 11-Nov-24 | IPC - 08 | Km 9+352 - PR34/P2 | PR34/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/88 MPSB/Str/83 | 2024-11-11 | IPC - 08 | Km 9+244 - PR31/P5 | PR31/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/89 MPSB/Str/84 | 11-Nov-24 12-Nov-24 | IPC - 08 | Km 9+244 - PL31/P1 | PL31/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/91 MPSB/Str/85 | 12-Nov-24 13-Nov-24 | IPC - 08 | Km 9+352 - PL34/P4 | PL34/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/93 MPSB/Str/88 | 2024-11-13 | IPC - 08 | Km 9+244 - PL31/P3 | PL31/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/95 MPSB/Str/90 | 2024-11-13 | IPC - 08 | Km 9+244 - PR31/P1 | PR31/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/94 MPSB/Str/89 | 2024-11-13 | IPC - 08 | Km 9+352 - PR34/P3 | PR34/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/99 MPSB/Str/94 | 14-Nov-24 15-Nov-24 | IPC - 08 | Km 9+352 - PL34/P1 | PL34/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/98 MPSB/Str/93 | 14-Nov-24 16-Nov-24 | IPC - 08 | Km 9+244 - PL31/P5 | PL31/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/100 MPSB/Str/98 | 14-Nov-24 16-Nov-24 | IPC - 08 | Km 9+352 - PR34/P1 | PR34/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/104 MPSB/Str/102 | 2024-11-18 | IPC - 08 | Km 9+352 - PL34/P5 | PL34/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/105 MPSB/Str/103 | 2024-11-18 | IPC - 08 | Km 9+352 - PR34/P5 | PR34/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/106 MPSB/Str/111 | 18-Nov-24 19-Nov-24 | IPC - 08 | Km 9+280 - PL32/P1 | PL32/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/110 MPSB/Str/109 | 2024-11-19 | IPC - 08 | Km 9+280 - PL32/P3 | PL32/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/111 MPSB/Str/110 | 2024-11-19 | IPC - 08 | Km 9+280 - PR32/P1 | PR32/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/112 MPSB/Str/113 | 2024-11-20 | IPC - 08 | Km 9+352 - PL34/P2 | PL34/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/108 MPSB/Str/116 | 19-Nov-24 21-Nov-24 | IPC - 08 | Km 5+390 - PR0/P3 | PR0/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/101 MPSB/Str/119 | 15-Nov-24 21-Nov-24 | IPC - 08 | Km 5+390 - PL0/P1 | PL0/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/113 MPSB/Str/114 | 20-Nov-24 21-Nov-24 | IPC - 08 | Km 9+352 - PL34/P3 | PL34/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/109 MPSB/Str/120 | 19-Nov-24 22-Nov-24 | IPC - 08 | Km 5+390 - PR0/P5 | PR0/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/116 MPSB/Str/121 | 2024-11-22 | IPC - 08 | Km 5+390 - PL0/P7 | PL0/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/117 MPSB/Str/122 | 2024-11-22 | IPC - 08 | Km 9+280 - PL32/P6 | PL32/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/121 MPSB/Str/125 | 2024-11-23 | IPC - 08 | Km 5+390 - PR0/P4 | PR0/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/123 MPSB/Str/129 | 2024-11-23 | IPC - 08 | Km 9+388 - PR35/P6 | PR35/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/124 MPSB/Str/130 | 2024-11-25 | IPC - 08 | Km 5+390 - PL0/P8 | PL0/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/126 MPSB/Str/134 | 2024-11-25 | IPC - 08 | Km 9+280 - PL32/P4 | PL32/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/125 MPSB/Str/133 | 2024-11-25 | IPC - 08 | Km 9+388 - PR35/P5 | PR35/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/131 MPSB/Str/138 | 2024-11-26 | IPC - 08 | Km 5+390 - PR0/P6 | PR0/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/129 MPSB/Str/137 | 2024-11-26 | IPC - 08 | Km 9+316 - PL33/P2 | PL33/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/122 MPSB/Str/132 | 23-Nov-24 25-Nov-24 | IPC - 08 | Km 9+280 - PL32/P2 | PL32/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/128 MPSB/Str/136 | 26-Nov-24 27-Nov-24 | IPC - 08 | Km 9+388 - PR35/P1 | PR35/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/132 MPSB/Str/140 | 2024-11-27 | IPC - 08 | Km 5+390 - PL0/P6 | PL0/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/134 MPSB/Str/142 | 2024-11-27 | IPC - 08 | Km 9+280 - PL32/P5 | PL32/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/135 MPSB/Str/143 | 2024-11-27 | IPC - 08 | Km 9+280 - PR32/P6 | PR32/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/138 MPSB/Str/144 | 2024-11-28 | IPC - 08 | Km 5+390 - PR0/P2 | PR0/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/139 MPSB/Str/145 | 2024-11-28 | IPC - 08 | Km 5+390 - PL0/P5 | PL0/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/130 MPSB/Str/146 | 26-Nov-24 28-Nov-24 | IPC - 08 | Km 9+388 - PL35/P4 | PL35/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/136 MPSB/Str/147 | 27-Nov-24 28-Nov-24 | IPC - 08 | Km 9+388 - PL35/P6 | PL35/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/143 MPSB/Str/152 | 29-Nov-24 29-Nov-24 | IPC - 08 | Km 5+390 - PR0/P9 | PR0/P9 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/159 MPSB/Str/154 | 30-Nov-24 29-Nov-24 | IPC - 08 | Km 5+390 - PL0/P4 | PL0/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/161 MPSB/Str/169 | 2024-11-30 | IPC - 08 | Km 9+280 - PR32/P5 | PR32/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/165 MPSB/Str/174 | 2024-12-02 | IPC - 08 | Km 5+390 - PL0/P9 | PL0/P9 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/145 MPSB/Str/170 | 29-Nov-24 2-Dec-24 | IPC - 08 | Km 9+388 - PR35/P4 | PR35/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/171 MPSB/Str/178 | 2024-12-04 | IPC - 08 | Km 5+390 - PL0/P2 | PL0/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/160 MPSB/Str/180 | 30-Nov-24 4-Dec-24 | IPC - 08 | Km 9+280 - PR32/P3 | PR32/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/181 MPSB/Str/187 | 2024-12-07 | IPC - 08 | Km 5+390 - PR0/P8 | PR0/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/169 MPSB/Str/176 | 2024-12-03 | IPC - 09 | Km 9+280 - PR32/P4 | PR32/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/170 MPSB/Str/177 | 2024-12-03 | IPC - 09 | Km 9+388 - PL35/P1 | PL35/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/174 MPSB/Str/194 | 4-Dec-24 10-Dec-24 | IPC - 09 | Km 9+388 - PR35/P2 | PR35/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/178 MPSB/Str/191 | 6-Dec-24 9-Dec-24 | IPC - 09 | Km 9+388 - PL35/P3 | PL35/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/182 MPSB/Str/188 | 2024-12-08 | IPC - 09 | Km 5+390 - PL0/P3 | PL0/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/183 MPSB/Str/189 | 2024-12-08 | IPC - 09 | Km 5+390 - PR0/P1 | PR0/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/187 MPSB/Str/195 | 10-Dec-24 11-Dec-24 | IPC - 09 | Km 9+388 - PL35/P2 | PL35/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/164 MPSB/Str/173 | 2024-12-02 | IPC - 09 | Km 9+280 - PR32/P2 | PR32/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/162 MPSB/Str/171 | 2024-12-02 | IPC - 09 | Km 9+388 - PL35/P5 | PL35/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/166 MPSB/Str/180 | 2-Dec-24 4-Dec-24 | IPC - 10 | Km 5+390 - PR0/P7 | PR0/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/163 MPSB/Str/172 | 2024-12-02 | IPC - 10 | Km 9+388 - PR35/P3 | PR35/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1499 MPSB/Str/1775 | 2025-07-07 | IPC - 18 | Km 9+316 - PL33/P8 | PL33/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1500 MPSB/Str/1776 | 2025-07-07 | IPC - 18 | Km 9+316 - PR33/P7 | PR33/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1501 MPSB/Str/1777 | 2025-07-08 | IPC - 18 | Km 9+316 - PR33/P8 | PR33/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1504 MPSB/Str/1782 | 2025-07-09 | IPC - 18 | Km 9+316 - PR33/P3 | PR33/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1507 MPSB/Str/1787 | 2025-07-10 | IPC - 18 | Km 9+352 - PR34/P8 | PR34/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1510 MPSB/Str/1792 | 2025-07-11 | IPC - 18 | Km 9+316 - PR33/P2 | PR33/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1511 MPSB/Str/1793 | 2025-07-11 | IPC - 18 | Km 9+316 - PL33/P7 | PL33/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1514 MPSB/Str/1798 | 2025-07-12 | IPC - 18 | Km 9+316 - PR33/P6 | PR33/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1520 MPSB/Str/1809 | 2025-07-14 | IPC - 18 | Km 9+316 - PR33/P4 | PR33/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1521 MPSB/Str/1810 | 2025-07-14 | IPC - 18 | Km 9+352 - PR34/P7 | PR34/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1528 MPSB/Str/1814 | 2025-07-15 | IPC - 18 | Km 9+352 - PR34/P9 | PR34/P9 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1531 MPSB/Str/1820 | 2025-07-16 | IPC - 18 | Km 9+316 - PL33/P1 | PL33/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1533 MPSB/Str/1822 | 2025-07-16 | IPC - 18 | Km 9+352 - PR34/P6 | PR34/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1534 MPSB/Str/1823 | 2025-07-17 | IPC - 18 | Km 9+316 - PL33/P4 | PL33/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1535 MPSB/Str/1824 | 2025-07-17 | IPC - 18 | Km 9+316 - PL33/P5 | PL33/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1536 MPSB/Str/1829 | 2025-07-17 | IPC - 18 | Km 9+316 - PR33/P1 | PR33/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1539 MPSB/Str/1831 | 2025-07-18 | IPC - 18 | Km 9+316 - PL33/P3 | PL33/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1544 MPSB/Str/1841 | 2025-07-19 | IPC - 18 | Km 9+316 - PR33/P5 | PR33/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1545 MPSB/Str/1842 | 2025-07-19 | IPC - 18 | Km 9+316 - PL33/P6 | PL33/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1547 MPSB/Str/1843 | 2025-07-19 | IPC - 18 | Km 9+352 - PL34/P8 | PL34/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1563 MPSB/Str/1867 | 2025-07-23 | IPC - 18 | Km 9+424 - PL36/P8 | PL36/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1564 MPSB/Str/1868 | 2025-07-23 | IPC - 18 | Km 9+424 - PL36/P7 | PL36/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1572 MPSB/Str/1879 | 2025-07-24 | IPC - 18 | Km 9+424 - PL36/P10 | PL36/P10 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1578 MPSB/Str/1886 | 2025-07-25 | IPC - 18 | Km 9+424 - PL36/P9 | PL36/P9 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1579 MPSB/Str/1887 | 2025-07-25 | IPC - 18 | Km 9+424 - PR36/P1 | PR36/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1580 MPSB/Str/1888 | 2025-07-25 | IPC - 18 | Km 9+424 - PL36/P1 | PL36/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1585 MPSB/Str/1893 | 2025-07-25 | IPC - 18 | Km 9+424 - PR36/P2 | PR36/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1587 MPSB/Str/1896 | 2025-07-26 | IPC - 18 | Km 9+424 - PR36/P3 | PR36/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1588 MPSB/Str/1897 | 2025-07-26 | IPC - 18 | Km 9+424 - PL36/P12 | PL36/P12 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1593 MPSB/Str/1901 | 2025-07-27 | IPC - 18 | Km 9+424 - PL36/P2 | PL36/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1596 MPSB/Str/1904 | 2025-07-28 | IPC - 18 | Km 9+424 - PL36/P11 | PL36/P11 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1598 MPSB/Str/1906 | 2025-07-28 | IPC - 18 | Km 9+424 - PR36/P4 | PR36/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1602 MPSB/Str/1918 | 2025-07-29 | IPC - 18 | Km 9+424 - PR36/P11 | PR36/P11 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1606 MPSB/Str/1919 | 2025-07-30 | IPC - 18 | Km 9+424 - PR36/P10 | PR36/P10 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1619 MPSB/Str/1940 | 2025-07-31 | IPC - 18 | Km 9+424 - PL36/P3 | PL36/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1630 MPSB/Str/1949 | 2025-07-31 | IPC - 18 | Km 9+424 - PL36/P5 | PL36/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1618 MPSB/Str/1939 | 2025-07-31 | IPC - 18 | Km 9+424 - PR36/P5 | PR36/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1607 MPSB/Str/1920 | 2025-07-30 | IPC - 19 | Km 9+352 - PL34/P7 | PL34/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1631 MPSB/Str/1950 | 2025-07-31 | IPC - 19 | Km 5+428 - PR36/P12 | PR36/P12 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1620 MPSB/Str/1941 | 2025-07-31 | IPC - 19 | Km 9+424 - PL36/P4 | PL36/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1634 MPSB/Str/1956 | 2025-08-01 | IPC - 19 | Km 9+424 - PL36/P6 | PL36/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1637 MPSB/Str/1960 | 2025-08-02 | IPC - 19 | Km 9+424 - PR36/P6 | PR36/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1646 MPSB/Str/1975 | 2025-08-04 | IPC - 19 | Km 9+424 - PR36/P7 | PR36/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1649 MPSB/Str/1978 | 2025-08-05 | IPC - 19 | Km 9+424 - PR36/P9 | PR36/P9 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1650 MPSB/Str/1979 | 2025-08-05 | IPC - 19 | Km 9+424 - PR36/P8 | PR36/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/1659 MPSB/Str/1998 | 2025-08-07 | IPC - 19 | Km 9+352 - PL34/P9 | PL34/P9 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1733 MPSB/Str/2092 | 2025-08-26 | IPC - 19 | Km 5+428 - PR1/P3 | PR1/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1734 MPSB/Str/2116 | 26-Aug-25 30-Aug-25 | IPC - 19 | Km 5+428 - PL1/P3 | PL1/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1754 MPSB/Str/2121 | 2025-08-30 | IPC - 19 | Km 5+428 - PR1/P4 | PR1/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1755 MPSB/Str/2122 | 2025-08-31 | IPC - 22 | Km 5+428 - PL1/P6 | PL1/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1762 MPSB/Str/2140 | 2025-09-03 | IPC - 22 | Km 5+428 - PR1/P7 | PR1/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1767 MPSB/Str/2149 | 2025-09-04 | IPC - 22 | Km 5+428 - PR1/P2 | PR1/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1779 MPSB/Str/2161 | 2025-09-06 | IPC - 22 | Km 5+428 - PL1/P7 | PL1/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1790 MPSB/Str/2184 | 2025-09-08 | IPC - 22 | Km 5+428 - PR1R/P4 | PR1R/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1795 MPSB/Str/2189 | 2025-09-08 | IPC - 22 | Km 5+428 - PL1R/P4 | PL1R/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1801 MPSB/Str/2195 | 2025-09-10 | IPC - 22 | Km 5+428 - PL1R/P1 | PL1R/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1825 MPSB/Str/2240 | 2025-09-15 | IPC - 22 | Km 5+428 - PL1R/P3 | PL1R/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1839 MPSB/Str/2269 | 2025-09-19 | IPC - 22 | Km 5+428 - PL1R/P2 | PL1R/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1840 MPSB/Str/2270 | 2025-09-19 | IPC - 22 | Km 5+464 - PL2R/P4 | PL2R/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1850 MPSB/Str/2282 | 2025-09-22 | IPC - 22 | Km 5+464 - PR2R/P3 | PR2R/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1862 MPSB/Str/2303 | 2025-09-23 | IPC - 22 | Km 5+464 - PL2R/P3 | PL2R/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1863 MPSB/Str/2304 | 2025-09-23 | IPC - 22 | Km 5+464 - PR2R/P2 | PR2R/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1866 MPSB/Str/2305 | 2025-09-24 | IPC - 22 | Km 5+464 - PL2R/P2 | PL2R/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1873 MPSB/Str/2324 | 2025-09-26 | IPC - 22 | Km 5+464 - PR2R/P1 | PR2R/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1879 MPSB/Str/2333 | 2025-09-27 | IPC - 22 | Km 5+464 - PL2R/P1 | PL2R/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1880 MPSB/Str/2334 | 2025-09-27 | IPC - 22 | Km 5+428 - PR1R/P2 | PR1R/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1888 MPSB/Str/2352 | 2025-09-29 | IPC - 22 | Km 5+428 - PR1R/P1 | PR1R/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1910 MPSB/Str/2381 | 2025-10-03 | IPC - 22 | Km 5+500 - PL3/P3 | PL3/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1911 MPSB/Str/2382 | 2025-10-03 | IPC - 22 | Km 5+500 - PR3/P3 | PR3/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1922 MPSB/Str/2396 | 2025-10-04 | IPC - 22 | Km 5+500 - PR3/P4 | PR3/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1928 MPSB/Str/2404 | 2025-10-06 | IPC - 22 | Km 5+500 - PL3/P4 | PL3/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1929 MPSB/Str/2405 | 2025-10-07 | IPC - 22 | Km 5+500 - PR3/P5 | PR3/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1930 MPSB/Str/2406 | 2025-10-07 | IPC - 22 | Km 5+500 - PL3/P5 | PL3/P5 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1931 MPSB/Str/2407 | 2025-10-07 | IPC - 22 | Km 5+500 - PR3/P2 | PR3/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1945 MPSB/Str/2425 | 2025-10-08 | IPC - 22 | Km 5+500 - PL3/P1 | PL3/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1946 MPSB/Str/2426 | 2025-10-08 | IPC - 22 | Km 5+500 - PR3/P6 | PR3/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1950 MPSB/Str/2431 | 2025-10-09 | IPC - 22 | Km 5+428 - PR1R/P3 | PR1R/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1951 MPSB/Str/2432 | 2025-10-09 | IPC - 22 | Km 5+500 - PL3/P6 | PL3/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/1964 MPSB/Str/2444 | 2025-10-10 | IPC - 22 | Km 5+500 - PR3/P1 | PR3/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2493 MPSB/Str/3269 | 2025-12-25 | IPC - 25 | Km 9+388 - PL35/P7 | PL35/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2494 MPSB/Str/3270 | 2025-12-25 | IPC - 25 | Km 9+388 - PL35/P12 | PL35/P12 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2499 MPSB/Str/3278 | 2025-12-26 | IPC - 25 | Km 9+316 - PL33R/P1 | PL33R/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2500 MPSB/Str/3279 | 2025-12-26 | IPC - 25 | Km 9+388 - PL35/P8 | PL35/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2508 MPSB/Str/3290 | 2025-12-27 | IPC - 25 | Km 9+388 - PL35/P11 | PL35/P11 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2509 MPSB/Str/3291 | 2025-12-27 | IPC - 25 | Km 9+280 - PL32R/P4 | PL32R/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2519 MPSB/Str/3305 | 2025-12-28 | IPC - 25 | Km 9+388 - PL35/P9 | PL35/P9 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2520 MPSB/Str/3306 | 2025-12-28 | IPC - 25 | Km 9+316 - PL33R/P4 | PL33R/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2538 MPSB/Str/3329 | 2025-12-29 | IPC - 25 | Km 9+388 - PL35/P10 | PL35/P10 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2539 MPSB/Str/3330 | 2025-12-29 | IPC - 25 | Km 9+388 - PL32R/P11 | PL32R/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2540 MPSB/Str/3331 | 2025-12-29 | IPC - 25 | Km 9+316 - PL33R/P2 | PL33R/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2542 MPSB/Str/3334 | 2025-12-30 | IPC - 25 | Km 9+280 - PL32R/P3 | PL32R/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2543 MPSB/Str/3335 | 2025-12-30 | IPC - 25 | Km 9+316 - PL33R/P3 | PL33R/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2544 MPSB/Str/3336 | 2025-12-30 | IPC - 25 | Km 9+388 - PR35/P7 | PR35/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2563 MPSB/Str/3365 | 2025-12-31 | IPC - 25 | Km 9+280 - PL32R/P2 | PL32R/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2564 MPSB/Str/3366 | 2025-12-31 | IPC - 25 | Km 9+388 - PR35/P12 | PR35/P12 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2565 MPSB/Str/3367 | 2025-12-31 | IPC - 25 | Km 9+280 - PR32R/P3 | PR32R/P3 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2566 MPSB/Str/3368 | 2025-12-31 | IPC - 25 | Km 9+388 - PR35/P8 | PR35/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2600 MPSB/Str/3420 | 2026-01-04 | IPC - 26 | Km 9+280 - PR32R/P2 | PR32R/P2 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2607 MPSB/Str/3428 | 2026-01-05 | IPC - 26 | Km 9+388 - PR35/P11 | PR35/P11 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2608 MPSB/Str/3429 | 2026-01-05 | IPC - 26 | Km 9+280 - PR32R/P4 | PR32R/P4 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2621 MPSB/Str/3446 | 2026-01-07 | IPC - 26 | Km 9+280 - PR32R/P1 | PR32R/P1 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2622 MPSB/Str/3447 | 2026-01-07 | IPC - 26 | Km 9+388 - PR35/P9 | PR35/P9 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2632 MPSB/Str/3466 | 2026-01-09 | IPC - 26 | Km 9+280 - PL32/P12 | PL32/P12 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2633 MPSB/Str/3467 | 2026-01-09 | IPC - 26 | Km 9+388 - PR35/P10 | PR35/P10 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2656 MPSB/Str/3490 | 2026-01-12 | IPC - 26 | Km 9+280 - PL32/P7 | PL32/P7 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2675 MPSB/Str/3518 | 2026-01-14 | IPC - 26 | Km 9+280 - PL32/P8 | PL32/P8 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2684 MPSB/Str/3531 | 2026-01-15 | IPC - 26 | Km 9+280 - PL32/P10 | PL32/P10 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2689 MPSB/Str/3538 | 2026-01-16 | IPC - 26 | Km 9+352 - PL34/P6 | PL34/P6 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2688 MPSB/Str/3537 | 2026-01-16 | IPC - 26 | Km 9+280 - PL32/P9 | PL32/P9 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2698 MPSB/Str/3568 | 17-Jan-26 19-Jan-26 | IPC - 26 | Km 9+280 - PR32/P12 | PR32/P12 - AV
501.b.1 | For Approach Viaduct - On completion of Piles | Nos. | Sualkuchi | 1 | MPSB/Sur/2714 MPSB/Str/3571 | 2026-01-19 | IPC - 26 | Km 9+280 - PR32/P7 | PR32/P7 - AV
| Cumulative paid upto this Bill | Nos. |  | 194
| Paid upto previous Bill | Nos. |  | 194
| To be paid in this Bill | Nos. |  | 0
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 4.48 | MPSB/Str/1845 MPSB/Sur/1559 MPSB/Str/1862 MPSB/Sur/1613 | 19-Jul-24 22-Jul-25 22-Jun-25 30-Jul-25 | IPC - 18 | P5 - Well Curb | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 4.48 | MPSB/Str/1881 MPSB/Sur/1576 MPSB/Str/1882 | 25-Jul-25 25-Jul-25 25-Jul-25 | IPC - 18 | P4 - Well Curb | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/1999 MPSB/Sur/1660 MPSB/Str/2000 MPSB/Sur/1680 | 7-Aug-25 7-Aug-25 7-Aug-25 11-Aug-25 | IPC - 19 | P4 - 1st Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/1952 MPSB/Sur/1632 MPSB/Str/1953 MPSB/Sur/1662 | 31-Jul-25 31-Jul-25 31-Jul-25 7-Aug-25 | IPC - 19 | P5 - 1st Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2030 MPSB/Sur/1690 MPSB/Str/2031 MPSB/Sur/1702 | 16-Aug-25 16-Aug-25 16-Aug-25 20-Aug-25 | IPC - 19 | P4 - 2nd Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2015 MPSB/Sur/1678 MPSB/Str/2016 MPSB/Sur/1692 | 11-Aug-25 11-Aug-25 11-Aug-25 16-Aug-25 | IPC - 19 | P5 - 2nd Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2071 MPSB/Sur/1720 MPSB/Str/2072 | 23-Aug-25 23-Aug-25 23-Aug-25 | IPC - 19 | P4 - 3rd Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2060 MPSB/Sur/1711 MPSB/Str/2061 | 21-Aug-25 21-Aug-25 21-Aug-25 | IPC - 19 | P5 - 3rd Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2015 MPSB/Sur/1742 MPSB/Str/2016 | 28-Aug-25 28-Aug-25 28-Aug-25 | IPC - 19 | P4 - 4th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2082 MPSB/Sur/1729 MPSB/Str/2083 | 25-Aug-25 25-Aug-25 25-Aug-25 | IPC - 19 | P5 - 4th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2162 MPSB/Sur/1780 MPSB/Str/2163 | 6-Sep-25 6-Sep-25 6-Sep-25 | IPC - 20 | P4 - 5th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2151 MPSB/Sur/1768 MPSB/Str/2152 MPSB/Sur/1832 | 4-Sep-25 4-Sep-25 4-Sep-25 16-Sep-25 | IPC - 20 | P5 - 5th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2208 MPSB/Sur/1805 MPSB/Str/2209 | 11-Sep-25 11-Sep-25 11-Sep-25 | IPC - 20 | P4 - 6th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2187 MPSB/Sur/1792 MPSB/Str/2188 MPSB/Sur/1832 | 8-Sep-25 8-Sep-25 8-Sep-25 16-Sep-25 | IPC - 20 | P5 - 6th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2272 MPSB/Sur/1842 MPSB/Str/2273 | 19-Sep-25 19-Sep-25 19-Sep-25 | IPC - 20 | P4 - 7th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2306 MPSB/Sur/1867 MPSB/Str/2307 | 24-Sep-25 24-Sep-25 24-Sep-25 | IPC - 20 | P5 - 7th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 3.3 | MPSB/Str/2376 MPSB/Sur/1906 MPSB/Str/2377 | 30-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | P5 - 8th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 3.17 | MPSB/Str/2445 MPSB/Sur/1965 MPSB/Str/2446 | 10-Oct-25 10-Oct-25 10-Oct-25 | IPC - 22 | P4 - 8th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2495 MPSB/Sur/1995 MPSB/Str/2496 | 16-Oct-25 16-Oct-25 16-Oct-25 | IPC - 22 | P4 - 9th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2447 MPSB/Sur/1966 MPSB/Str/2448 | 11-Oct-25 11-Oct-25 11-Oct-25 | IPC - 22 | P5 - 9th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2588 MPSB/Sur/2052 MPSB/Str/2589 | 26-Oct-25 26-Oct-25 26-Oct-25 | IPC - 22 | P4 - 10th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2649 MPSB/Sur/2080 MPSB/Str/2650 | 30-Oct-25 30-Oct-25 30-Oct-25 | IPC - 22 | P5 - 10th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2734 MPSB/Sur/2145 MPSB/Str/2735 | 07-Nov-25 07-Nov-25 07-Nov-25 | IPC - 23 | P5 - 11th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2865 MPSB/Sur/2231 MPSB/Str/2866 | 20-Nov-25 20-Nov-25 20-Nov-25 | IPC - 23 | P4 - 11th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2892 MPSB/Sur/2247 MPSB/Str/2893 | 22-Nov-25 22-Nov-25 22-Nov-25 | IPC - 23 | P4 - 12th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/2968 MPSB/Sur/2294 MPSB/Str/2969 | 28-Nov-25 28-Nov-25 28-Nov-25 | IPC - 23 | P4 - 13th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/3127 MPSB/Sur/2404 MPSB/Str/3128 | 13-Dec-25 13-Dec-25 13-Dec-25 | IPC - 25 | P5 - 12th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/3187 MPSB/Sur/2444 MPSB/Str/3188 | 18-Dec-25 18-Dec-25 18-Dec-25 | IPC - 25 | P5 - 13th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/3297 MPSB/Sur/2517 MPSB/Str/3298 | 27-Dec-25 27-Dec-25 27-Dec-25 | IPC - 25 | P5 - 14th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/3666 MPSB/Sur/2791 MPSB/Str/3667 | 29-Jan-26 29-Jan-26 29-Jan-26 | IPC - 26 | P4 - 14th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/3723 MPSB/Sur/2822 MPSB/Str/3724 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | P4 - 15th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/4157 MPSB/Sur/3146 MPSB/Str/4158 | 19-Mar-26 19-Mar-26 19-Mar-26 | IPC - 29 | P5 - 15th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/4486 MPSB/Sur/3350 MPSB/Str/4566 | 25-Apr-26 25-Apr-26 30-Apr-26 | IPC - 30 | P5 - 16th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/4462 MPSB/Sur/3336 MPSB/Str/4461 | 21-Apr-26 21-Apr-26 21-Apr-26 | IPC - 31 | P4 - 16th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/4671 MPSB/Sur/3476 MPSB/Str/4672 | 14-May-26 14-May-26 14-May-26 | IPC - 31 | P4 - 17th Lift | P4
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/4624 MPSB/Sur/3447 MPSB/Str/4625 | 9-May-26 9-May-26 9-May-26 | IPC - 31 | P5 - 17th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.77 | MPSB/Str/4930 MPSB/Sur/3658 MPSB/Str/4931 | 17-Jun-26 17-Jun-26 17-Jun-26 | IPC - 33 | P5 - 18th Lift | P5
501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 1.05 | MPSB/Str/5133 MPSB/Sur/3760 MPSB/Str/5134 | 13-Jul-26 13-Jul-26 13-Jul-26 | IPC - 34 | P4 - 18th Lift | P4
| Cumulative paid upto this Bill | Rmt |  | 99.25
| Paid upto previous Bill | Rmt |  | 98.2
| To be paid in this Bill | Rmt |  | 1.05
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Str/167 MPSB/Sur/1474 MPSB/Str/1730 MPSB/Str/1731 | 30-Nov-24 29-Jun-25 29-Jun-25 29-Jun-25 | IPC - 16 | Km 5+464 - PL2 - Pilecap | PL2 - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/1487 MPSB/Str/1755 MPSB/Str/1756 | 03-Jul-25 03-Jul-25 03-Jul-26 | IPC - 18 | Km 5+464 - PR2 - Pilecap | PR2 - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/1821 MPSB/Str/2227 MPSB/Str/2247 | 13-Sep-25 13-Sep-25 16-Sep-25 | IPC - 20 | Km 5+392 - PL0 - Pilecap | PL0 - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/1874 MPSB/Str/2325 MPSB/Str/2326 | 26-Sep-25 26-Sep-25 26-Sep-25 | IPC - 20 | Km 5+392 - PR0 - Pilecap | PR0 - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2079 MPSB/Str/2646 MPSB/Str/2647 | 30-Oct-25 30-Oct-25 30-Oct-25 | IPC - 22 | Km 5+428 - PR1R - Pilecap | PR1R - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2097 MPSB/Str/2666 MPSB/Str/2667 | 31-Oct-25 31-Oct-25 31-Oct-25 | IPC - 22 | Km 5+428 - PL1 - Pilecap | PL1 - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2022 MPSB/Str/2546 MPSB/Str/2547 | 22-Oct-25 22-Oct-25 22-Oct-25 | IPC - 22 | Km 9+244 - PL31 - Pilecap | PL31 - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2203 MPSB/Str/2825 MPSB/Str/2826 | 17-Nov-25 17-Nov-25 17-Nov-25 | IPC - 23 | Km 9+244 - PR31 - Pilecap | PR31 - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2300 MPSB/Str/2977 MPSB/Str/2978 | 29-Nov-25 29-Nov-25 29-Nov-25 | IPC - 23 | Km 9+316 - PL33 - Pilecap | PL33 - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2163 MPSB/Str/2755 MPSB/Str/2756 | 10-Nov-25 10-Nov-25 10-Nov-25 | IPC - 23 | Km 9+424 - PL36 - Pilecap | PL36 - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2178 MPSB/Str/2784 MPSB/Str/2785 | 12-Nov-25 12-Nov-25 12-Nov-25 | IPC - 23 | Km 5+464 - PR2R - Pilecap | PR2R - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2211 MPSB/Str/2835 MPSB/Str/2836 | 18-Nov-25 18-Nov-25 18-Nov-25 | IPC - 23 | Km 5+500 - PR3 - Pilecap | PR3 - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2306 MPSB/Str/2988 MPSB/Str/2989 | 29-Nov-25 29-Nov-25 29-Nov-25 | IPC - 23 | Km 5+500 - PL3 - Pilecap | PL3 - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2307 MPSB/Str/2990 MPSB/Str/2991 | 29-Nov-25 29-Nov-25 29-Nov-25 | IPC - 23 | Km 5+464 - PL2R - Pilecap | PL2R - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2154 MPSB/Str/2747 MPSB/Str/2748 | 08-Nov-25 08-Nov-25 08-Nov-25 | IPC - 23 | Km 5+428 - PR1 - Pilecap | PR1 - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2060 MPSB/Str/2598 MPSB/Str/2599 | 27-Oct-25 27-Oct-25 27-Oct-25 | IPC - 23 | Km 5+428 - PL1R - Pilecap | PL1R - Pilecap - SAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2361 MPSB/Str/3076 MPSB/Str/3077 | 8-Dec-25 8-Dec-25 8-Dec-25 | IPC - 25 | Km 9+352 - PR34 - Pilecap | PR34 - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2470 MPSB/Str/3230 MPSB/Str/3231 | 22-Dec-25 22-Dec-25 22-Dec-25 | IPC - 25 | Km 9+424 - PR36 - Pilecap | PR36 - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2794 MPSB/Str/3669 MPSB/Str/3670 | 29-Jan-26 29-Jan-26 29-Jan-26 | IPC - 26 | Km 9+316 - PL33R - Pilecap | PL33R - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2811 MPSB/Str/3703 MPSB/Str/3704 | 30-Jan-26 30-Jan-26 30-Jan-26 | IPC - 26 | Km 9+280 - PL32R - Pilecap | PL32R - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2883 MPSB/Str/3789 MPSB/Str/3790 | 7-Feb-26 7-Feb-26 7-Feb-26 | IPC - 27 | Km 9+280 - PR32R - Pilecap | PR32R - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/2912 MPSB/Str/3831 MPSB/Str/3832 | 11-Feb-26 11-Feb-26 11-Feb-26 | IPC - 27 | Km 9+316 - PR33R - Pilecap | PR33R - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/3087 MPSB/Str/4082 MPSB/Str/4083 | 10-Mar-26 11-Mar-26 11-Mar-26 | IPC - 29 | Km 9+388 - PL35 - Pilecap | PL35 - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/3437 MPSB/Str/4606 MPSB/Str/4607 | 8-May-26 8-May-26 8-May-26 | IPC - 31 | Km 9+280 - PL32 - Pilecap | PL32 - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/3672 MPSB/Str/4964 MPSB/Str/4965 | 20-Jun-26 20-Jun-26 20-Jun-26 | IPC - 33 | Km 9+316 - PR33 - Pilecap | PR33 - Pilecap - NAV
501.b.3 | For Approach Viaduct - On completion of Pile Cap | Nos. | Sualkuchi | 1 | MPSB/Sur/3732 MPSB/Str/5097 MPSB/Str/5098 | 8-Jul-26 8-Jul-26 8-Jul-26 | IPC - 34 | Km 9+352 - PL34 - Pilecap | PL34 - Pilecap - NAV
| Cumulative paid upto this Bill | Nos. |  | 26
| Paid upto previous Bill | Nos. |  | 25
| To be paid in this Bill | Nos. |  | 1
502 & 503 | Construction of sub- structure; abutment/piers / lower pylon & Construction of pier- cap/ pier table
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1089 MPSB/Str/1258 MPSB/Str/1259 | 24-Apr-25 24-Apr-25 24-Apr-25 | IPC - 14 | Km 11+176 - PL16 - Pier | PL16 - Pier - WV2 | Survey checking Reinforcement Check Shuttering & Concreting
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1164 MPSB/Str/1365 MPSB/Str/1366 | 30-Apr-25 30-Apr-25 30-Apr-25 | IPC - 14 | Km 11+176 - PR16 - Pier | PR16 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1112 MPSB/Str/1285 MPSB/Str/1286 | 26-Apr-25 26-Apr-25 26-Apr-25 | IPC - 14 | Km 11+212 - PR17 - Pier | PR17 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1130 MPSB/Str/1303 MPSB/Str/1304 | 27-Apr-25 27-Apr-25 27-Apr-25 | IPC - 14 | Km 11+284 - PR19 - Pier | PR19 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1059 MPSB/Str/1225 MPSB/Str/1226 | 22-Apr-25 22-Apr-25 22-Apr-25 | IPC - 14 | Km 11+320 - PR20 - Pier | PR20 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1002 MPSB/Str/1150 MPSB/Str/1151 | 16-Apr-25 16-Apr-25 16-Apr-25 | IPC - 14 | Km 11+320 - PL20 - Pier | PL20 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1223 MPSB/Str/1424 MPSB/Str/1425 | 6-May-25 6-May-25 6-May-25 | IPC - 15 | Km 11+140 - PL15 - Pier | PL15 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1455 MPSB/Str/1697 MPSB/Str/1698 | 23-Jun-25 23-Jun-25 23-Jun-25 | IPC - 16 | Km 10+888 - PR8 - Pier | PR8 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1463 MPSB/Str/1710 MPSB/Str/1711 | 27-Jun-25 27-Jun-25 27-Jun-25 | IPC - 16 | Km 10+924 - PR9 - Pier | PR9 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1464 MPSB/Str/1712 MPSB/Str/1713 | 27-Jun-25 27-Jun-25 27-Jun-25 | IPC - 16 | Km 10+960 - PR10 - Pier | PR10 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1489 MPSB/Str/1758 MPSB/Str/1759 | 04-Jul-25 04-Jul-25 04-Jul-25 | IPC - 18 | Km 10+996 - PR11 - Pier | PR11-Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1513 MPSB/Str/1796 MPSB/Str/1797 | 12-Jul-25 12-Jul-25 12-Jul-25 | IPC - 18 | Km 10+852 - PR7 - Pier | PR7- Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1599 MPSB/Str/1907 MPSB/Str/1908 | 28-Jul-25 28-Jul-25 28-Jul-25 | IPC - 18 | Km 11+248 - PR18 - Pier | PR18-Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1655 MPSB/Str/1989 MPSB/Str/1990 | 6-Aug-25 6-Aug-25 6-Aug-25 | IPC - 19 | Km 11+068 - PR13 - Pier | PR13-Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1665 MPSB/Str/2005 MPSB/Str/2006 | 9-Aug-25 9-Aug-25 9-Aug-25 | IPC - 19 | Km 11+104 - PR14 - Pier | PR14-Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1683 MPSB/Str/2020 MPSB/Str/2021 | 12-Aug-25 12-Aug-25 12-Aug-25 | IPC - 19 | Km 11+140 - PR15 - Pier | PR15-Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1756 MPSB/Str/2124 MPSB/Str/2125 | 31-Aug-25 31-Aug-25 31-Aug-25 | IPC - 19 | Km 10+636 - PR1 - Pier | PR1-Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1746 MPSB/Str/2110 MPSB/Str/2111 | 30-Aug-25 30-Aug-25 30-Aug-25 | IPC - 19 | Km 10+672 - PR2 - Pier | PR2-Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1786 MPSB/Str/2179 MPSB/Str/2180 | 8-Sep-25 8-Sep-25 8-Sep-25 | IPC - 20 | Km 11+248 - PL18 - Pier | PL18 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1804 MPSB/Str/2204 MPSB/Str/2205 | 10-Sep-25 10-Sep-25 10-Sep-25 | IPC - 20 | Km 11+356 - PR21 - Pier | PR21 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1817 MPSB/Str/2225 MPSB/Str/2226 | 13-Sep-25 13-Sep-25 13-Sep-25 | IPC - 20 | Km 11+356 - PL21 - Pier | PL21 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1835 MPSB/Str/2262 MPSB/Str/2263 | 19-Sep-25 19-Sep-25 19-Sep-25 | IPC - 20 | Km 11+212 - PL17 - Pier | PL17 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1902 MPSB/Str/2372 MPSB/Str/2373 | 30-Sep-25 30-Sep-25 30-Sep-25 | IPC - 20 | Km 10+600 - PL0 - Pier | PL0 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1941 MPSB/Str/2421 MPSB/Str/2422 | 08-Oct-25 08-Oct-25 08-Oct-25 | IPC - 22 | Km 11+104 - PL14 - Pier | PL14 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/1959 MPSB/Str/2439 MPSB/Str/2440 | 10-Oct-25 10-Oct-25 10-Oct-25 | IPC - 22 | Km 11+284 - PL19 - Pier | PL19 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2035 MPSB/Str/2559 MPSB/Str/2560 | 23-Oct-25 23-Oct-25 23-Oct-25 | IPC - 22 | Km 11+068 - PL13 - Pier | PL13 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2039 MPSB/Str/2572 MPSB/Str/2608 | 24-Oct-25 24-Oct-25 27-Oct-25 | IPC - 22 | Km 11+032 - PL12 - Pier | PL12 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2077 MPSB/Str/2643 MPSB/Str/2644 | 30-Oct-25 30-Oct-25 30-Oct-25 | IPC - 22 | Km 10+996 - PL11 - Pier | PL11 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2089 MPSB/Str/2656 MPSB/Str/2657 | 31-Oct-25 31-Oct-25 31-Oct-25 | IPC - 22 | Km 10+960 - PL10 - Pier | PL10 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2186 MPSB/Str/2796 MPSB/Str/2797 | 13-Nov-25 13-Nov-25 13-Nov-25 | IPC - 23 | Km 10+600 - PR0 - Pier | PR0 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2197 MPSB/Str/2819 MPSB/Str/2820 | 15-Nov-25 15-Nov-25 15-Nov-25 | IPC - 23 | Km 10+924 - PL9 - Pier | PL9 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2318 MPSB/Str/3008 MPSB/Str/3009 | 30-Nov-25 30-Nov-25 30-Nov-25 | IPC - 23 | Km 11+032 - PR12 - Pier | PR12 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2319 MPSB/Str/3010 MPSB/Str/3011 | 30-Nov-25 30-Nov-25 30-Nov-25 | IPC - 23 | Km 10+888 - PL8 - Pier | PL8 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2323 MPSB/Str/3022 MPSB/Str/3023 | 30-Nov-25 30-Nov-25 30-Nov-25 | IPC - 23 | Km 10+636 - PL1 - Pier | PL1 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2334 MPSB/Str/3037 MPSB/Str/3038 | 4-Dec-25 4-Dec-25 4-Dec-25 | IPC - 25 | Km 10+852 - PL7 - Pier | PL7 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2338 MPSB/Str/3045 MPSB/Str/3046 | 5-Dec-25 5-Dec-25 5-Dec-25 | IPC - 25 | Km 10+708 - PR3 - Pier | PR3 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2350 MPSB/Str/3065 MPSB/Str/3066 | 6-Dec-25 6-Dec-25 6-Dec-25 | IPC - 25 | Km 10+744 - PR4 - Pier | PR4 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2351 MPSB/Str/3067 MPSB/Str/3068 | 6-Dec-25 6-Dec-25 6-Dec-25 | IPC - 25 | Km 10+780 - PR5 - Pier | PR5 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2471 MPSB/Str/3232 MPSB/Str/3233 | 23-Dec-25 23-Dec-25 23-Dec-25 | IPC - 25 | Km 10+672 - PL2 - Pier | PL2 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2514 MPSB/Str/3295 MPSB/Str/3296 | 27-Dec-25 27-Dec-25 27-Dec-25 | IPC - 25 | Km 10+338 - PR3 - Pier | PR3 - Pier - WV1
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2536 MPSB/Str/3326 MPSB/Str/3327 | 29-Dec-25 29-Dec-25 29-Dec-25 | IPC - 25 | Km 10+338 - PL3 - Pier | PL3 - Pier - WV1
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2546 MPSB/Str/3340 MPSB/Str/3341 | 30-Dec-25 30-Dec-25 30-Dec-25 | IPC - 25 | Km 10+302 - PR2 - Pier | PR2 - Pier - WV1
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2547 MPSB/Str/3342 MPSB/Str/3343 | 30-Dec-25 30-Dec-25 30-Dec-25 | IPC - 25 | Km 10+816 - PR6 - Pier | PR6 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2548 MPSB/Str/3344 MPSB/Str/3345 | 30-Dec-25 30-Dec-25 30-Dec-25 | IPC - 25 | Km 10+780 - PL5 - Pier | PL5 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2549 MPSB/Str/3346 MPSB/Str/3347 | 30-Dec-25 30-Dec-25 30-Dec-25 | IPC - 25 | Km 10+708 - PL3 - Pier | PL3 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2567 MPSB/Str/3369 MPSB/Str/3370 | 31-Dec-25 31-Dec-25 31-Dec-25 | IPC - 25 | Km 10+266 - PL1 - Pier | PL1 - Pier - WV1
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2605 MPSB/Str/3424 MPSB/Str/3425 | 5-Jan-26 5-Jan-26 5-Jan-26 | IPC - 26 | Km 10+744 - PL4 - Pier | PL4 - Pier - WV2
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2807 MPSB/Str/3697 MPSB/Str/3698 | 30-Jan-26 30-Jan-26 30-Jan-26 | IPC - 26 | Km 10+230 - PL0 - Pier | PL0 - Pier - WV1
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2808 MPSB/Str/3699 MPSB/Str/3700 | 30-Jan-26 30-Jan-26 30-Jan-26 | IPC - 26 | Km 10+230 - PR0 - Pier | PR0 - Pier - WV1
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2827 MPSB/Str/3734 MPSB/Str/3735 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | Km 10+266 - PR1 - Pier | PR1 - Pier - WV1
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2901 MPSB/Str/3816 MPSB/Str/3817 | 10-Feb-26 10-Feb-26 10-Feb-26 | IPC - 27 | Km 10+302 - PL2 - Pier | PL2 - Pier - WV1
502 & 503.a.1 | For Wetland Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2984 MPSB/Str/3940 MPSB/Str/3941 | 24-Feb-26 24-Feb-26 24-Feb-26 | IPC - 27 | Km 10+816 - PL6 - Pier | PL6 - Pier - WV2
| Cumulative paid upto this Bill | Nos. |  | 52
| Paid upto previous Bill | Nos. |  | 52
| To be paid in this Bill | Nos. |  | 0
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2419 MPSB/Str/3155 MPSB/Str/3156 | 16-Dec-25 16-Dec-25 16-Dec-25 | IPC - 25 | Km 11+356 - PR21 - Piercap | PR21 - Piercap - WV2 | Reinforcement & Profile Shutter & Concrete
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2455 MPSB/Str/3211 MPSB/Str/3212 | 20-Dec-25 20-Dec-25 20-Dec-25 | IPC - 25 | Km 11+284 - PL19 - Piercap | PL19 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2528 MPSB/Str/3315 MPSB/Str/3316 | 28-Dec-25 28-Dec-25 28-Dec-25 | IPC - 25 | Km 11+320 - PL20 - Piercap | PL20 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2568 MPSB/Str/3371 MPSB/Str/3372 | 31-Dec-25 31-Dec-25 31-Dec-25 | IPC - 25 | Km 11+212 - PL17 - Piercap | PL17 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2683 MPSB/Str/3529 MPSB/Str/3530 | 15-Jan-26 15-Jan-26 15-Jan-26 | IPC - 26 | Km 11+356 - PL21 - Piercap | PL21 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2754 MPSB/Str/3635 MPSB/Str/3636 | 24-Jan-26 24-Jan-26 24-Jan-26 | IPC - 26 | Km 11+320 - PR20 - Piercap | PR20 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2812 MPSB/Str/3707 MPSB/Str/3708 | 30-Jan-26 30-Jan-26 30-Jan-26 | IPC - 26 | Km 11+248 - PL18 - Piercap | PL18 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2824 MPSB/Str/3728 MPSB/Str/3729 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | Km 11+284 - PR19 - Piercap | PR19 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2825 MPSB/Str/3730 MPSB/Str/3731 | 31-Jan-26 31-Jan-26 31-Jan-26 | IPC - 26 | Km 11+212 - PR17 - Piercap | PR17 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2880 MPSB/Str/3782 MPSB/Str/3783 | 7-Feb-26 7-Feb-26 7-Feb-26 | IPC - 27 | Km 11+140 - PL15 - Piercap | PL15 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2918 MPSB/Str/3838 MPSB/Str/3839 | 12-Feb-26 12-Feb-26 12-Feb-26 | IPC - 27 | Km 11+176 - PR16 - Piercap | PR16 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2919 MPSB/Str/3840 MPSB/Str/3841 | 12-Feb-26 12-Feb-26 12-Feb-26 | IPC - 27 | Km 11+176 - PL16 - Piercap | PL16 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2970 MPSB/Str/3913 MPSB/Str/3914 | 21-Feb-26 21-Feb-26 21-Feb-26 | IPC - 27 | Km 11+068 - PL13 - Piercap | PL13 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/2972 MPSB/Str/3917 MPSB/Str/3918 | 21-Feb-26 21-Feb-26 21-Feb-26 | IPC - 27 | Km 11+104 - PL14 - Piercap | PL14 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3021 MPSB/Str/3989 MPSB/Str/3990 | 27-Feb-26 27-Feb-26 27-Feb-26 | IPC - 27 | Km 11+140 - PR15 - Piercap | PR15 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3022 MPSB/Str/3991 MPSB/Str/3992 | 27-Feb-26 27-Feb-26 27-Feb-26 | IPC - 27 | Km 10+996 - PL11 - Piercap | PL11 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3051 MPSB/Str/4020 MPSB/Str/4021 | 28-Feb-26 28-Feb-26 28-Feb-26 | IPC - 27 | Km 10+960 - PL10 - Piercap | PL10 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3076 MPSB/Str/4066 MPSB/Str/4067 | 7-Mar-26 7-Mar-26 7-Mar-26 | IPC - 29 | Km 11+248 - PR18 - Piercap | PR18 - Piercap - WV2 |  | P21 | 11.356
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3086 MPSB/Str/4080 MPSB/Str/4081 | 10-Mar-26 10-Mar-26 10-Mar-26 | IPC - 29 | Km 11+104 - PR14 - Piercap | PR14 - Piercap - WV2 |  | P20 | 11.32
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3143 MPSB/Str/4150 MPSB/Str/4151 | 18-Mar-26 18-Mar-26 18-Mar-26 | IPC - 29 | Km 11+032 - PL12 - Piercap | PL12 - Piercap - WV2 |  | P19 | 11.284
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3173 MPSB/Str/4206 MPSB/Str/4207 | 25-Mar-26 25-Mar-26 25-Mar-26 | IPC - 29 | Km 10+852 - PL7 - Piercap | PL7 - Piercap - WV2 |  | P18 | 11.248
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3200 MPSB/Str/4253 MPSB/Str/4254 | 30-Mar-26 30-Mar-26 30-Mar-26 | IPC - 29 | Km 10+888 - PL8 - Piercap | PL8 - Piercap - WV2 |  | P17 | 11.212
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3201 MPSB/Str/4255 MPSB/Str/4256 | 30-Mar-26 30-Mar-26 30-Mar-26 | IPC - 29 | Km 10+924 - PL9 - Piercap | PL9 - Piercap - WV2 |  | P16 | 11.176
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3215 MPSB/Str/4280 MPSB/Str/4281 | 31-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | Km 10+996 - PR11- Piercap | PR11 - Piercap - WV2 |  | P15 | 11.14
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3291 MPSB/Str/4383 MPSB/Str/4384 | 13-Apr-26 13-Apr-26 13-Apr-26 | IPC - 30 | Km 10+816 - PL6 - Piercap | PL6 - Piercap - WV2 |  | P14 | 11.104
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3301 MPSB/Str/4398 MPSB/Str/4399 | 14-Apr-26 14-Apr-26 14-Apr-26 | IPC - 30 | Km 10+780 - PL5 - Piercap | PL5 - Piercap - WV2 |  | P13 | 11.068
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3363 MPSB/Str/4495 MPSB/Str/4496 | 27-Apr-26 27-Apr-26 27-Apr-26 | IPC - 30 | Km 10+744 - PL4 - Piercap | PL4 - Piercap - WV2 |  | P12 | 11.032
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3388 MPSB/Str/4539 MPSB/Str/4540 | 30-Apr-26 30-Apr-26 30-Apr-26 | IPC - 30 | Km 11+032 - PR12 - Piercap | PR12 - Piercap - WV2 |  | P11 | 10.996
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3322 MPSB/Str/4431 MPSB/Str/4432 | 18-Apr-26 18-Apr-26 18-Apr-26 | IPC - 30 | Km 11+068 - PR13 - Piercap | PR13 - Piercap - WV2 |  | P10 | 10.96
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3334 MPSB/Str/4457 MPSB/Str/4458 | 21-Apr-26 21-Apr-26 21-Apr-26 | IPC - 30 | Km 10+924 - PR9 - Piercap | PR9 - Piercap - WV2 |  | P9 | 10.924
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3416 MPSB/Str/4578 MPSB/Str/4579 | 5-May-26 5-May-26 5-May-26 | IPC - 31 | Km 10+672 - PL2 - Piercap | PL2 - Piercap - WV2 |  | P8 | 10.888
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3429 MPSB/Str/4597 MPSB/Str/4598 | 7-May-26 7-May-26 7-May-26 | IPC - 31 | Km 10+600 - PL0 - Piercap | PL0 - Piercap - WV2 |  | P7 | 10.852
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3436 MPSB/Str/4604 MPSB/Str/4605 | 8-May-26 8-May-26 8-May-26 | IPC - 31 | Km 10+960 - PR10 - Piercap | PR10 - Piercap - WV2 |  | P6 | 10.816
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3448 MPSB/Str/4626 MPSB/Str/4627 | 9-May-26 9-May-26 9-May-26 | IPC - 31 | Km 10+636 - PL1 - Piercap | PL1 - Piercap - WV2 |  | P5 | 10.78
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3463 MPSB/Str/4645 MPSB/Str/4646 | 11-May-26 11-May-26 11-May-26 | IPC - 31 | Km 10+888 - PR8 - Piercap | PR8 - Piercap - WV2 |  | P4 | 10.744
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3485 MPSB/Str/4692 MPSB/Str/4693 | 16-May-26 16-May-26 16-May-26 | IPC - 31 | Km 10+780 - PR5 - Piercap | PR5 - Piercap - WV2 |  | P3 | 10.708
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3486 MPSB/Str/4694 MPSB/Str/4695 | 16-May-26 16-May-26 16-May-26 | IPC - 31 | Km 10+852 - PR7 - Piercap | PR7 - Piercap - WV2 |  | P2 | 10.672
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3495 MPSB/Str/4704 MPSB/Str/4705 | 17-May-26 17-May-26 17-May-26 | IPC - 31 | Km 10+708 - PL3 - Piercap | PL3 - Piercap - WV2 |  | P1 | 10.636
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3523 MPSB/Str/4736 MPSB/Str/4737 | 21-May-26 21-May-26 21-May-26 | IPC - 31 | Km 10+600 - PR0 - Piercap | PR0 - Piercap - WV2 |  | P0 | 10.6
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3524 MPSB/Str/4738 MPSB/Str/4739 | 21-May-26 21-May-26 21-May-26 | IPC - 31 | Km 10+672 - PR2 - Piercap | PR2 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3540 MPSB/Str/4769 MPSB/Str/4770 | 23-May-26 23-May-26 23-May-26 | IPC - 31 | Km 10+744 - PR4 - Piercap | PR4 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3541 MPSB/Str/4771 MPSB/Str/4772 | 23-May-26 23-May-26 23-May-26 | IPC - 31 | Km 10+266 - PL1 - Piercap | PL1 - Piercap - WV1
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3646 MPSB/Str/4898 MPSB/Str/4899 | 12-Jun-26 12-Jun-26 12-Jun-26 | IPC - 33 | Km 10+816 - PR6 - Piercap | PR6 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3691 MPSB/Str/5005 MPSB/Str/5006 | 25-Jun-26 25-Jun-26 25-Jun-26 | IPC - 33 | Km 10+708 - PR3 - Piercap | PR3 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3681 MPSB/Str/4986 MPSB/Str/4987 | 22-Jun-26 22-Jun-26 22-Jun-26 | IPC - 33 | Km 10+302 - PL2 - Piercap | PL2 - Piercap - WV1
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3682 MPSB/Str/4988 MPSB/Str/4989 | 22-Jun-26 22-Jun-26 22-Jun-26 | IPC - 33 | Km 10+338 - PR3 - Piercap | PR3 - Piercap - WV1
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3699 MPSB/Str/5026 MPSB/Str/5027 | 29-Jun-26 29-Jun-26 29-Jun-26 | IPC - 33 | Km 10+266 - PR1 - Piercap | PR1 - Piercap - WV1
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3708 MPSB/Str/5044 MPSB/Str/5045 | 30-Jun-26 30-Jun-26 30-Jun-26 | IPC - 33 | Km 10+338 - PL3 - Piercap | PL3 - Piercap - WV1
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3709 MPSB/Str/5046 MPSB/Str/5047 | 30-Jun-26 30-Jun-26 30-Jun-26 | IPC - 33 | Km 10+302 - PR2 - Piercap | PR2 - Piercap - WV1
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3673 MPSB/Str/4966 MPSB/Str/4967 | 20-Jun-26 20-Jun-26 20-Jun-26 | IPC - 34 | Km 10+636 - PR1 - Piercap | PR1 - Piercap - WV2
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3740 MPSB/Str/5111 MPSB/Str/5112 | 10-Jul-26 10-Jul-26 10-Jul-26 | IPC - 34 | Km 10+230 - PL0 - Piercap | PL0 - Piercap - WV1
502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Sur/3746 MPSB/Str/5117 MPSB/Str/5118 | 11-Jul-26 11-Jul-26 11-Jul-26 | IPC - 34 | Km 10+230 - PR0 - Piercap | PR0 - Piercap - WV1
| Cumulative paid upto this Bill | Nos. |  | 52
| Paid upto previous Bill | Nos. |  | 49
| To be paid in this Bill | Nos. |  | 3
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/1601 MPSB/Str/1916 MPSB/Str/1917 | 28-Jul-25 28-Jul-25 28-Jul-25 | IPC - 18 | Km 5+464 - PL2 - Pier | PL2 - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/1625 MPSB/Str/1947 MPSB/Str/1948 | 31-Jul-25 31-Jul-25 31-Jul-25 | IPC - 19 | Km 5+464 - PR2 - Pier | PR2 - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/2012 MPSB/Str/2525 MPSB/Str/2526 | 18-Oct-25 18-Oct-25 18-Oct-25 | IPC - 22 | Km 5+392 - PL0 - Pier | PL0 - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/1999 MPSB/Str/2507 MPSB/Str/2508 | 17-Oct-25 17-Oct-25 17-Oct-25 | IPC - 22 | Km 5+392 - PR0 - Pier | PR0 - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/2286 MPSB/Str/2948 MPSB/Str/2949 | 27-Nov-25 27-Nov-25 27-Nov-25 | IPC - 23 | Km 5+428 - PL1 - Pier | PL1 - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/2309 MPSB/Str/2993 MPSB/Str/2994 | 29-Nov-25 29-Nov-25 29-Nov-25 | IPC - 23 | Km 5+428 - PR1 - Pier | PR1 - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/2246 MPSB/Str/2890 MPSB/Str/2891 | 22-Nov-25 22-Nov-25 22-Nov-25 | IPC - 23 | Km 5+428 - PR1R - Pier | PR1R - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/2270 MPSB/Str/2927 MPSB/Str/2928 | 25-Nov-25 25-Nov-25 25-Nov-25 | IPC - 23 | Km 5+428 - PL1R - Pier | PL1R - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2397 MPSB/Str/3121 MPSB/Str/3122 | 12-Dec-25 12-Dec-25 12-Dec-25 | IPC - 25 | Km 9+244 - PR31 - Pier | PR31 - Pier - NAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/2434 MPSB/Str/3181 MPSB/Str/3182 | 17-Dec-25 17-Dec-25 17-Dec-25 | IPC - 25 | Km 5+464 - PL2R - Pier | PL2R - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2452 MPSB/Str/3206 MPSB/Str/3207 | 20-Dec-25 20-Dec-25 20-Dec-25 | IPC - 25 | Km 9+424 - PL36 - Pier | PL36 - Pier - NAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/2457 MPSB/Str/3214 MPSB/Str/3215 | 21-Dec-25 21-Dec-25 21-Dec-25 | IPC - 25 | Km 5+464 - PR2R - Pier | PR2R - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/2480 MPSB/Str/3244 MPSB/Str/3245 | 24-Dec-25 24-Dec-25 24-Dec-25 | IPC - 25 | Km 5+500 - PL3 - Pier | PL3 - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Palashbari | 1 | MPSB/Sur/2507 MPSB/Str/3288 MPSB/Str/3289 | 26-Dec-25 26-Dec-25 26-Dec-25 | IPC - 25 | Km 5+500 - PR3 - Pier | PR3 - Pier - SAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2623 MPSB/Str/3448 MPSB/Str/3449 | 7-Jan-26 7-Jan-26 7-Jan-26 | IPC - 26 | Km 9+424 - PR36 - Pier | PR36 - Pier - NAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2670 MPSB/Str/3512 MPSB/Str/3513 | 13-Jan-26 13-Jan-26 13-Jan-26 | IPC - 26 | Km 9+244 - PL31 - Pier | PL31 - Pier - NAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2707 MPSB/Str/3561 MPSB/Str/3562 | 18-Jan-26 18-Jan-26 18-Jan-26 | IPC - 26 | Km 9+352 - PR34 - Pier | PR34 - Pier - NAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2779 MPSB/Str/3655 MPSB/Str/3656 | 27-Jan-26 27-Jan-26 27-Jan-26 | IPC - 26 | Km 9+316 - PL33 - Pier | PL33 - Pier - NAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/2944 MPSB/Str/3876 MPSB/Str/3877 | 17-Feb-26 17-Feb-26 17-Feb-26 | IPC - 27 | Km 9+316 - PL33R - Pier | PL33R - Pier - NAV
502 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/3016 MPSB/Str/3973 MPSB/Str/3974 | 26-Feb-26 26-Feb-26 26-Feb-26 | IPC - 27 | Km 9+316 - PR33R - Pier | PR33R - Pier - NAV
503 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/3074 MPSB/Str/4062 MPSB/Str/4063 | 7-Mar-26 7-Mar-26 7-Mar-26 | IPC - 29 | Km 9+280 - PR32R - Pier | PR32R - Pier - NAV
503 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/3114 MPSB/Str/4139 MPSB/Str/4140 | 13-Mar-26 17-Mar-26 17-Mar-26 | IPC - 29 | Km 9+280 - PL32R - Pier | PL32R - Pier - NAV
503 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/3397 MPSB/Str/4590 MPSB/Str/4591 | 30-Apr-26 6-May-26 6-May-26 | IPC - 31 | Km 9+388 - PL35 - Pier | PL35 - Pier - NAV
503 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/3586 MPSB/Str/4845 MPSB/Str/4846 | 31-May-26 31-May-26 31-May-26 | IPC - 31 | Km 9+280 - PL32 - Pier | PL32 - Pier - NAV
503 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/3774 MPSB/Str/5157 MPSB/Str/5158 | 17-Jul-26 17-Jul-26 17-Jul-26 | IPC - 34 | Km 9+352 - PL34 - Pier | PL34 - Pier - NAV
503 & 503.b.1 | For Approach Viaduct - On completion of abutment / Pier / lower pylon | Nos. | Sualkuchi | 1 | MPSB/Sur/3788 MPSB/Str/5183 MPSB/Str/5184 | 23-Jul-26 23-Jul-26 23-Jul-26 | IPC - 34 | Km 9+316 - PR33 - Pier | PR33 - Pier - NAV
| Cumulative paid upto this Bill | Nos. |  | 26
| Paid upto previous Bill | Nos. |  | 24
| To be paid in this Bill | Nos. |  | 2
502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Sur/2988 MPSB/Str/3946 MPSB/Str/3947 | 24-Feb-26 24-Feb-26 24-Feb-26 | IPC - 27 | Km 5+392 - PR0 - Piercap | PR0 - Piercap - SAV
502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Sur/3055 MPSB/Str/4026 MPSB/Str/4027 | 28-Feb-26 28-Feb-26 28-Feb-26 | IPC - 27 | Km 5+392 - PL0 - Piercap | PL0 - Piercap - SAV
502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Str/4232 MPSB/Str/4233 | 28-Mar-26 28-Mar-26 28-Mar-26 | IPC - 29 | Km 5+428 - PR1- Piercap | PR1 - Piercap - SAV
502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Sur/3220 MPSB/Str/4299 MPSB/Str/4300 | 31-Mar-26 31-Mar-26 31-Mar-26 | IPC - 29 | Km 5+428 - PL1 - Piercap | PL1 - Piercap - SAV
502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Sur/3287 MPSB/Str/4378 MPSB/Str/4379 | 12-Apr-26 12-Apr-26 12-Apr-26 | IPC - 30 | Km 5+464 - PL2 - Piercap | PL2 - Piercap - SAV
502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Sur/3308 MPSB/Str/4409 MPSB/Str/4410 | 16-Apr-26 16-Apr-26 16-Apr-26 | IPC - 30 | Km 5+500 - PR3 - Piercap | PR3 - Piercap - SAV
502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Str/4444 MPSB/Str/4445 | 19-Apr-26 19-Apr-26 | IPC - 30 | Km 5+464 - PR2 - Piercap | PR2 - Piercap - SAV
502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Sur/3529 MPSB/Str/4752 MPSB/Str/4753 | 21-May-26 21-May-26 21-May-26 | IPC - 31 | Km 5+500 - PL3 - Piercap | PL3 - Piercap - SAV
502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Sur/3803 MPSB/Str/5227 MPSB/Str/5228 | 29-Jul-26 29-Jul-26 29-Jul-26 | IPC - 34 | Km 9+424 - PL36 - Piercap | PL36 - Piercap - NAV
| Cumulative paid upto this Bill | Nos. |  | 9
| Paid upto previous Bill | Nos. |  | 8
| To be paid in this Bill | Nos. |  | 1
504 | Construction of PSC Box girders/I-Girders in casting yard
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1349 MPSB/Str/1350 | 30-Apr-25 30-Apr-25 | IPC - 14 | WV2-P0-P1-G2 | 2025-04-01 | Reinforcement & Profile Shutter & Concrete
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1488 MPSB/Str/1508 | 13-May-25 17-May-25 | IPC - 15 | WV2-P1-P2-G2 | 2025-05-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1537 MPSB/Str/1578 | 20-May-25 26-May-25 | IPC - 15 | WV2-P0-P1-G3 | 2025-05-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1701 MPSB/Str/1715 | 25-Jun-25 28-Jun-25 | IPC - 16 | WV2-P16-P17-G6 | 2025-06-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1750 MPSB/Str/1771 | 02-Jul-25 07-Jul-25 | IPC - 18 | WV2-P16-P17-G2 | 2025-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1767 MPSB/Str/1786 | 05-Jul-25 09-Jul-25 | IPC - 18 | WV2-P15-P16-G6 | 2025-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1812 MPSB/Str/1813 | 14-Jul-25 15-Jul-25 | IPC - 18 | WV2-P15-P16-G7 | 2025-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1819 MPSB/Str/1833 | 16-Jul-25 18-Jul-25 | IPC - 18 | WV2-P15-P16-G2 | 2025-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1834 MPSB/Str/1850 | 18-Jul-25 20-Jul-25 | IPC - 18 | WV2-P16-P17-G3 | 2025-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1870 MPSB/Str/1898 | 23-Jul-25 26-Jul-25 | IPC - 18 | WV2-P16-P17-G1 | 2025-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1913 MPSB/Str/1922 | 28-Jul-25 30-Jul-25 | IPC - 18 | WV2-P15-P16-G3 | 2025-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/1972 MPSB/Str/1993 | 4-Aug-25 6-Aug-25 | IPC - 19 | WV2-P15-P16-G1 | 2025-08-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2014 MPSB/Str/2018 | 11-Aug-25 12-Aug-25 | IPC - 19 | WV2-P15-P16-G4 | 2025-08-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2027 MPSB/Str/2042 | 14-Aug-25 18-Aug-25 | IPC - 19 | WV2-P15-P16-G8 | 2025-08-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2054 MPSB/Str/2063 | 20-Aug-25 21-Aug-25 | IPC - 19 | WV2-P15-P16-G5 | 2025-08-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2055 MPSB/Str/2064 | 20-Aug-25 21-Aug-25 | IPC - 19 | WV2-P16-P17-G7 | 2025-08-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2067 MPSB/Str/2079 | 22-Aug-25 23-Aug-25 | IPC - 19 | WV2-P16-P17-G4 | 2025-08-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2100 MPSB/Str/2117 | 27-Aug-25 30-Aug-25 | IPC - 19 | WV2-P18-P19-G2 | 2025-08-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2096 MPSB/Str/2109 | 27-Aug-25 29-Aug-25 | IPC - 19 | WV2-P18-P19-G3 | 2025-08-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2119 MPSB/Str/2123 | 30-Aug-25 31-Aug-25 | IPC - 19 | WV2-P18-P19-G1 | 2025-08-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2138 MPSB/Str/2139 | 3-Sep-25 3-Sep-25 | IPC - 20 | WV2-P16-P17-G5 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2153 MPSB/Str/2156 | 4-Sep-25 5-Sep-25 | IPC - 20 | WV2-P20-P21-G6 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2157 MPSB/Str/2171 | 5-Sep-25 6-Sep-25 | IPC - 20 | WV2-P20-P21-G7 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2199 MPSB/Str/2218 | 10-Sep-25 11-Sep-25 | IPC - 20 | WV2-P18-P19-G4 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2217 MPSB/Str/2223 | 11-Sep-25 12-Sep-25 | IPC - 20 | WV2-P20-P21-G2 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2233 MPSB/Str/2235 | 14-Sep-25 15-Sep-25 | IPC - 20 | WV2-P20-P21-G3 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2261 MPSB/Str/2298 | 16-Sep-25 22-Sep-25 | IPC - 20 | WV2-P20-P21-G4 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2249 MPSB/Str/2250 | 18-Sep-25 18-Sep-25 | IPC - 20 | WV2-P19-P20-G1 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2300 MPSB/Str/2309 | 23-Sep-25 24-Sep-25 | IPC - 20 | WV2-P16-P17-G8 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2308 MPSB/Str/2311 | 24-Sep-25 24-Sep-25 | IPC - 20 | WV2-P19-P20-G3 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2310 MPSB/Str/2330 | 24-Sep-25 26-Sep-25 | IPC - 20 | WV2-P20-P21-G5 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2329 MPSB/Str/2342 | 26-Sep-25 29-Sep-25 | IPC - 20 | WV2-P20-P21-G8 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2335 MPSB/Str/2358 | 27-Sep-25 30-Sep-25 | IPC - 20 | WV2-P20-P21-G1 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2341 MPSB/Str/2359 | 29-Sep-25 30-Sep-25 | IPC - 20 | WV2-P17-P18-G1 | 2025-09-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2100 MPSB/Str/2117 | 27-Aug-25 30-Aug-25 | IPC - 22 | WV2-P19-P20-G2 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2397 MPSB/Str/2399 | 05-Oct-25 06-Oct-25 | IPC - 22 | WV2-P17-P18-G2 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2398 MPSB/Str/2400 | 05-Oct-25 06-Oct-25 | IPC - 22 | WV2-P19-P20-G4 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2417 MPSB/Str/2429 | 07-Oct-25 08-Oct-25 | IPC - 22 | WV2-P19-P20-G5 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2430 MPSB/Str/2433 | 08-Oct-25 09-Oct-25 | IPC - 22 | WV2-P17-P18-G3 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2454 MPSB/Str/2455 | 11-Oct-25 11-Oct-25 | IPC - 22 | WV2-P14-P15-G5 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2480 MPSB/Str/2493 | 15-Oct-25 16-Oct-25 | IPC - 22 | WV2-P17-P18-G4 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2501 MPSB/Str/2502 | 17-Oct-25 17-Oct-25 | IPC - 22 | WV2-P13-P14-G1 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2503 MPSB/Str/2539 | 17-Oct-25 20-Oct-25 | IPC - 22 | WV2-P14-P15-G8 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2533 MPSB/Str/2550 | 20-Oct-25 23-Oct-25 | IPC - 22 | WV2-P14-P15-G1 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2551 MPSB/Str/2575 | 23-Oct-25 25-Oct-25 | IPC - 22 | WV2-P14-P15-G2 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2600 MPSB/Str/2601 | 27-Oct-25 27-Oct-25 | IPC - 22 | WV2-P14-P15-G3 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2616 MPSB/Str/2617 | 28-Oct-25 28-Oct-25 | IPC - 22 | WV2-P19-P20-G6 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2630 MPSB/Str/2631 | 30-Oct-25 30-Oct-25 | IPC - 22 | WV2-P13-P14-G2 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2634 MPSB/Str/2635 | 30-Oct-25 30-Oct-25 | IPC - 22 | WV2-P14-P15-G7 | 2025-10-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2685 MPSB/Str/2686 | 02-Nov-25 02-Nov-25 | IPC - 23 | WV2-P13-P14-G3 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2687 MPSB/Str/2697 | 02-Nov-25 04-Nov-25 | IPC - 23 | WV2-P14-P15-G4 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2708 MPSB/Str/2718 | 05-Nov-25 06-Nov-25 | IPC - 23 | WV2-P14-P15-G6 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2717 MPSB/Str/2727 | 06-Nov-25 07-Nov-25 | IPC - 23 | WV2-P12-P13-G1 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2731 MPSB/Str/2753 | 07-Nov-25 09-Nov-25 | IPC - 23 | WV2-P12-P13-G2 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2764 MPSB/Str/2780 | 10-Nov-25 12-Nov-25 | IPC - 23 | WV2-P12-P13-G3 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2765 MPSB/Str/2774 | 10-Nov-25 11-Nov-25 | IPC - 23 | WV2-P13-P14-G4 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2809 MPSB/Str/2824 | 14-Nov-25 16-Nov-25 | IPC - 23 | WV2-P19-P20-G7 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2781 MPSB/Str/2795 | 12-Nov-25 13-Nov-25 | IPC - 23 | WV2-P12-P13-G5 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2815 MPSB/Str/2829 | 15-Nov-25 17-Nov-25 | IPC - 23 | WV2-P12-P13-G4 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2828 MPSB/Str/2844 | 17-Nov-25 18-Nov-25 | IPC - 23 | WV2-P10-P11-G1 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2878 MPSB/Str/2911 | 20-Nov-25 24-Nov-25 | IPC - 23 | WV2-P12-P13-G6 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2845 MPSB/Str/2877 | 18-Nov-25 20-Nov-25 | IPC - 23 | WV2-P11-P12-G2 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2898 MPSB/Str/2942 | 23-Nov-25 26-Nov-25 | IPC - 23 | WV2-P10-P11-G2 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2943 MPSB/Str/2984 | 26-Nov-25 29-Nov-25 | IPC - 23 | WV2-P12-P13-G7 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2954 MPSB/Str/2982 | 27-Nov-25 29-Nov-25 | IPC - 23 | WV2-P19-P20-G8 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2981 MPSB/Str/3012 | 29-Nov-25 30-Nov-25 | IPC - 23 | WV2-P10-P11-G3 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/2983 MPSB/Str/3013 | 29-Nov-25 30-Nov-25 | IPC - 23 | WV2-P11-P12-G6 | 2025-11-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3075 MPSB/Str/3080 | 7-Dec-25 8-Dec-25 | IPC - 25 | WV2-P10-P11-G4 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3079 MPSB/Str/3089 | 7-Dec-25 9-Dec-25 | IPC - 25 | WV2-P12-P13-G8 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3110 MPSB/Str/3111 | 11-Dec-25 11-Dec-25 | IPC - 25 | WV2-P13-P14-G5 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3124 MPSB/Str/3125 | 12-Dec-25 12-Dec-25 | IPC - 25 | WV2-P9-P10-G5 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3160 MPSB/Str/3161 | 16-Dec-25 16-Dec-25 | IPC - 25 | WV2-P11-P12-G3 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3189 MPSB/Str/3190 | 18-Dec-25 18-Dec-25 | IPC - 25 | WV2-P10-P11-G5 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3191 MPSB/Str/3200 | 18-Dec-25 19-Dec-25 | IPC - 25 | WV2-P11-P12-G8 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3216 MPSB/Str/3220 | 21-Dec-25 22-Dec-25 | IPC - 25 | WV2-P10-P11-G6 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3251 MPSB/Str/3280 | 24-Dec-25 26-Dec-25 | IPC - 25 | WV2-P18-P19-G5 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3313 MPSB/Str/3333 | 28-Dec-25 30-Dec-25 | IPC - 25 | WV2-P18-P19-G7 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3389 MPSB/Str/3391 | 31-Dec-25 31-Dec-25 | IPC - 25 | WV2-P18-P19-G6 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3299 MPSB/Str/3319 | 27-Dec-25 29-Dec-25 | IPC - 25 | WV2-P18-P19-G8 | 2025-12-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3435 MPSB/Str/3454 | 6-Jan-26 7-Jan-26 | IPC - 26 | WV2-P11-P12-G5 | 2026-01-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3461 MPSB/Str/3462 | 8-Jan-26 8-Jan-26 | IPC - 26 | WV2-P11-P12-G7 | 2026-01-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3507 MPSB/Str/3525 | 13-Jan-26 14-Jan-26 | IPC - 26 | WV2-P13-P14-G8 | 2026-01-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3523 MPSB/Str/3560 | 14-Jan-26 17-Jan-26 | IPC - 26 | WV2-P17-P18-G6 | 2026-01-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3540 MPSB/Str/3574 | 16-Jan-26 19-Jan-26 | IPC - 26 | WV2-P17-P18-G5 | 2026-01-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3602 MPSB/Str/3611 | 21-Jan-26 22-Jan-26 | IPC - 26 | WV2-P17-P18-G8 | 2026-01-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3603 MPSB/Str/3681 | 21-Jan-26 29-Jan-26 | IPC - 26 | WV2-P17-P18-G7 | 2026-01-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3800 MPSB/Str/3854 | 8-Feb-26 14-Feb-26 | IPC - 27 | WV2-P9-P10-G4 | 2026-02-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3893 MPSB/Str/3912 | 18-Feb-26 20-Feb-26 | IPC - 27 | WV2-P8-P9-G3 | 2026-02-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3927 MPSB/Str/3943 | 22-Feb-26 24-Feb-26 | IPC - 27 | WV2-P8-P9-G4 | 2026-02-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3942 MPSB/Str/3964 | 24-Feb-26 26-Feb-26 | IPC - 27 | WV2-P8-P9-G2 | 2026-02-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3985 MPSB/Str/3986 | 27-Feb-26 27-Feb-26 | IPC - 27 | WV2-P9-P10-G2 | 2026-02-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/3987 MPSB/Str/3988 | 27-Feb-26 27-Feb-26 | IPC - 27 | WV2-P13-P14-G6 | 2026-02-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4045 MPSB/Str/4048 | 6-Mar-26 6-Mar-26 | IPC - 29 | WV2-P6-P7-G4 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4046 MPSB/Str/4047 | 6-Mar-26 6-Mar-26 | IPC - 29 | WV2-P13-P14-G7 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4084 MPSB/Str/4085 | 10-Mar-26 10-Mar-26 | IPC - 29 | WV2-P8-P9-G1 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4059 MPSB/Str/4095 | 7-Mar-26 13-Mar-26 | IPC - 29 | WV2-P11-P12-G1 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4115 MPSB/Str/4116 | 14-Mar-26 14-Mar-26 | IPC - 29 | WV2-P9-P10-G3 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4123 MPSB/Str/4141 | 15-Mar-26 17-Mar-26 | IPC - 29 | WV2-P11-P12-G4 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4165 MPSB/Str/4180 | 20-Mar-26 20-Mar-26 | IPC - 29 | WV2-P9-P10-G1 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4203 MPSB/Str/4212 | 25-Mar-26 26-Mar-26 | IPC - 29 | WV2-P6-P7-G3 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4226 MPSB/Str/4230 | 28-Mar-26 28-Mar-26 | IPC - 29 | WV2-P6-P7-G2 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4248 MPSB/Str/4249 | 29-Mar-26 29-Mar-26 | IPC - 29 | WV2-P6-P7-G1 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4262 MPSB/Str/4263 | 30-Mar-26 30-Mar-26 | IPC - 29 | WV2-P7-P8-G4 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4283 MPSB/Str/4284 | 31-Mar-26 31-Mar-26 | IPC - 29 | WV2-P7-P8-G2 | 2026-03-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4356 MPSB/Str/4361 | 8-Apr-26 10-Apr-26 | IPC - 30 | WV2-P7-P8-G3 | 2026-04-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4381 MPSB/Str/4386 | 13-Apr-26 13-Apr-26 | IPC - 30 | WV2-P7-P8-G1 | 2026-04-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4419 MPSB/Str/4430 | 16-Apr-26 17-Apr-26 | IPC - 30 | WV2-P5-P6-G4 | 2026-04-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4436 MPSB/Str/4454 | 18-Apr-26 21-Apr-26 | IPC - 30 | WV2-P5-P6-G3 | 2026-04-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4472 MPSB/Str/4483 | 23-Apr-26 25-Apr-26 | IPC - 30 | WV2-P5-P6-G2 | 2026-04-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4510 MPSB/Str/4511 | 28-Apr-26 28-Apr-26 | IPC - 30 | WV2-P5-P6-G1 | 2026-04-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4535 MPSB/Str/4536 | 29-Apr-26 29-Apr-26 | IPC - 30 | WV2-P4-P5-G1 | 2026-04-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4614 MPSB/Str/4615 | 8-May-26 8-May-26 | IPC - 31 | WV2-P4-P5-G2 | 2026-05-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4665 MPSB/Str/4721 | 13-May-26 18-May-26 | IPC - 31 | WV2-P4-P5-G4 | 2026-05-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4747 MPSB/Str/4748 | 21-May-26 21-May-26 | IPC - 31 | WV2-P3-P4-G4 | 2026-05-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4796 MPSB/Str/4820 | 27-May-26 30-May-26 | IPC - 31 | WV2-P3-P4-G3 | 2026-05-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4762 MPSB/Str/4784 | 22-May-26 25-May-26 | IPC - 31 | WV2-P3-P4-G2 | 2026-05-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4821 MPSB/Str/4822 | 30-May-26 30-May-26 | IPC - 31 | WV2-P3-P4-G1 | 2026-05-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4768 MPSB/Str/4792 | 23-May-26 26-May-26 | IPC - 31 | WV2-P2-P3-G4 | 2026-05-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4880 MPSB/Str/4881 | 8-Jun-26 8-Jun-26 | IPC - 33 | WV2-P2-P3-G3 | 2026-06-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4890 MPSB/Str/4910 | 11-Jun-26 15-Jun-26 | IPC - 33 | WV2-P0-P1-G4 | 2026-06-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4911 MPSB/Str/4935 | 15-Jun-26 17-Jun-26 | IPC - 33 | WV2-P2-P3-G2 | 2026-06-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4983 MPSB/Str/5010 | 22-Jun-26 25-Jun-26 | IPC - 33 | WV2-P1-P2-G1 | 2026-06-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5022 MPSB/Str/5062 | 27-Jun-26 30-Jun-26 | IPC - 33 | WV2-P1-P2-G3 | 2026-06-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5030 MPSB/Str/5031 | 29-Jun-26 29-Jun-26 | IPC - 33 | WV2-P1-P2-G4 | 2026-06-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5032 MPSB/Str/5033 | 29-Jun-26 29-Jun-26 | IPC - 33 | WV2-P0-P1-G1 | 2026-06-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5221 MPSB/Str/5222 | 29-Jul-26 29-Jul-26 | IPC - 34 | WV1-P0-P1-G7 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5223 MPSB/Str/5224 | 29-Jul-26 29-Jul-26 | IPC - 34 | WV1-P0-P1-G3 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5099 MPSB/Str/5105 | 8-Jul-26 9-Jul-26 | IPC - 34 | WV1-P1-P2-G3 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5137 MPSB/Str/5138 | 14-Jul-26 14-Jul-26 | IPC - 34 | WV1-P1-P2-G2 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5163 MPSB/Str/5179 | 18-Jul-26 21-Jul-26 | IPC - 34 | WV1-P1-P2-G1 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5195 MPSB/Str/5216 | 25-Jul-26 28-Jul-26 | IPC - 34 | WV1-P1-P2-G4 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5104 MPSB/Str/5136 | 9-Jul-26 14-Jul-26 | IPC - 34 | WV1-P2-P3-G4 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5139 MPSB/Str/5177 | 14-Jul-26 21-Jul-26 | IPC - 34 | WV1-P2-P3-G8 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5185 MPSB/Str/5186 | 23-Jul-26 23-Jul-26 | IPC - 34 | WV1-P2-P3-G7 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5093 MPSB/Str/5161 | 7-Jul-26 18-Jul-26 | IPC - 34 | WV1-P2-P3-G2 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5187 MPSB/Str/5189 | 23-Jul-26 24-Jul-26 | IPC - 34 | WV1-P2-P3-G3 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5242 MPSB/Str/5243 | 31-Jul-26 31-Jul-26 | IPC - 34 | WV1-P2-P3-G6 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5246 MPSB/Str/5247 | 31-Jul-26 31-Jul-26 | IPC - 34 | WV1-P2-P3-G1 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5248 MPSB/Str/5249 | 31-Jul-26 31-Jul-26 | IPC - 34 | WV1-P2-P3-G5 | 2026-07-01
504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/5250 MPSB/Str/5251 | 31-Jul-26 31-Jul-26 | IPC - 34 | WV2-P10-P11-G8 | 2026-07-01
| Cumulative paid upto this Bill | Nos. |  | 140
| Paid upto previous Bill | Nos. |  | 125
| To be paid in this Bill | Nos. |  | 15
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 8 | MPSB/Str/3836 | 2026-02-11 | IPC - 27 | WV2-P20-P21 (G1 to G8) | BHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 8 | MPSB/Str/3868 | 2026-02-16 | IPC - 27 | WV2-P19-P20 (G1 to G8) | BHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/3903 | 2026-02-20 | IPC - 27 | WV2-P18-P19 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/3928 | 2026-02-23 | IPC - 27 | WV2-P17-P18 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/3933 | 2026-02-24 | IPC - 27 | WV2-P16-P17 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/3957 | 2026-02-26 | IPC - 27 | WV2-P15-P16 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4055 | 2026-03-07 | IPC - 29 | WV2-P14-P15 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4079 | 2026-03-10 | IPC - 29 | WV2-P13-P14 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4347 | 2026-04-07 | IPC - 30 | WV2-P12-P13 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4382 | 2026-04-13 | IPC - 30 | WV2-P11-P12 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4437 | 2026-04-18 | IPC - 30 | WV2-P10-P11 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4551 | 2026-04-30 | IPC - 30 | WV2-P9-P10 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4955 | 2026-06-19 | IPC - 33 | WV2-P18-P19 (G5 to G8) | RHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5039 | 2026-06-29 | IPC - 33 | WV2-P17-P18 (G5 to G8) | RHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5074 | 2026-06-30 | IPC - 33 | WV2-P16-P17 (G5 to G8) | RHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5091 | 2026-07-07 | IPC - 34 | WV2-P15-P16 (G5 to G8) | RHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5156 | 2026-07-17 | IPC - 34 | WV2-P6-P7 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5188 | 2026-07-24 | IPC - 34 | WV2-P5-P6 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5208 | 2026-07-28 | IPC - 34 | WV2-P4-P5 (G1 to G4) | LHS
504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/5229 | 2026-07-30 | IPC - 34 | WV2-P3-P4 (G1 to G4) | LHS
| Cumulative paid upto this Bill | Nos. |  | 88
| Paid upto previous Bill | Nos. |  | 68
| To be paid in this Bill | Nos. |  | 20
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3097 MPSB/Str/3098 | 10-Dec-25 10-Dec-25 | IPC - 25 | SAV-P0-P1-G4 | 2025-12-01 | Reinforcement & Profile Shutter & Concrete
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3311 MPSB/Str/3312 | 28-Dec-25 28-Dec-25 | IPC - 25 | SAV-P0-P1-G3 | 2025-12-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3377 MPSB/Str/3278 | 31-Dec-25 31-Dec-25 | IPC - 25 | SAV-P0-P1-G5 | 2025-12-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3450 MPSB/Str/3451 | 7-Jan-26 7-Jan-26 | IPC - 26 | SAV-P0-P1-G6 | 2026-01-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3483 MPSB/Str/3484 | 10-Jan-26 10-Jan-26 | IPC - 26 | SAV-P0-P1-G7 | 2026-01-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3514 MPSB/Str/3515 | 13-Jan-26 13-Jan-26 | IPC - 26 | SAV-P0-P1-G2 | 2026-01-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3558 MPSB/Str/3559 | 17-Jan-26 17-Jan-26 | IPC - 26 | SAV-P0-P1-G8 | 2026-01-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3721 MPSB/Str/3722 | 31-Jan-26 31-Jan-26 | IPC - 26 | SAV-P1-P2-G4 | 2026-01-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3622 MPSB/Str/3623 | 23-Jan-26 23-Jan-26 | IPC - 26 | SAV-P0-P1-G1 | 2026-01-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3663 MPSB/Str/3664 | 28-Jan-26 28-Jan-26 | IPC - 26 | SAV-P1-P2-G6 | 2026-01-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3711 MPSB/Str/3712 | 30-Jan-26 30-Jan-26 | IPC - 26 | SAV-P1-P2-G7 | 2026-01-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3719 MPSB/Str/3720 | 31-Jan-26 31-Jan-26 | IPC - 26 | SAV-P1-P2-G3 | 2026-01-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3581 MPSB/Str/3584 | 20-Jan-26 20-Jan-26 | IPC - 26 | SAV-P1-P2-G5 | 2026-01-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3818 MPSB/Str/3819 | 10-Feb-26 10-Feb-26 | IPC - 27 | SAV-P1R-P2R-G4 | 2026-02-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3857 MPSB/Str/3858 | 14-Feb-26 14-Feb-26 | IPC - 27 | SAV-P1R-P2R-G5 | 2026-02-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3882 MPSB/Str/3883 | 17-Feb-26 17-Feb-26 | IPC - 27 | SAV-P1R-P2R-G6 | 2026-02-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3906 MPSB/Str/3907 | 20-Feb-26 20-Feb-26 | IPC - 27 | SAV-P1-P2-G2 | 2026-02-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3924 MPSB/Str/3925 | 21-Feb-26 21-Feb-26 | IPC - 27 | SAV-P1-P2-G1 | 2026-02-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3949 MPSB/Str/3950 | 25-Feb-26 25-Feb-26 | IPC - 27 | SAV-P1R-P2R-G3 | 2026-02-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/3971 MPSB/Str/3972 | 26-Feb-26 26-Feb-26 | IPC - 27 | SAV-P1R-P2R-G2 | 2026-02-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4031 MPSB/Str/4032 | 28-Feb-26 28-Feb-26 | IPC - 27 | SAV-P2-P3-G8 | 2026-02-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4029 MPSB/Str/4030 | 28-Feb-26 28-Feb-26 | IPC - 27 | SAV-P1R-P2R-G1 | 2026-02-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4060 MPSB/Str/4061 | 7-Mar-26 7-Mar-26 | IPC - 29 | SAV-P2-P3-G7 | 2026-03-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4075 MPSB/Str/4076 | 10-Mar-26 10-Mar-26 | IPC - 29 | SAV-P2-P3-G6 | 2026-03-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4093 MPSB/Str/4094 | 13-Mar-26 13-Mar-26 | IPC - 29 | SAV-P2-P3-G5 | 2026-03-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4111 MPSB/Str/4112 | 14-Mar-26 14-Mar-26 | IPC - 29 | SAV-P2-P3-G4 | 2026-03-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4155 MPSB/Str/4156 | 19-Mar-26 19-Mar-26 | IPC - 29 | SAV-P2-P3-G3 | 2026-03-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/MB/1320 MPSB/MB/1321 | 20-Mar-26 20-Mar-26 | IPC - 29 | SAV-P2-P3-G2 | 2026-03-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4201 MPSB/Str/4202 | 25-Mar-26 25-Mar-26 | IPC - 29 | SAV-P2-P3-G1 | 2026-03-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4244 MPSB/Str/4245 | 29-Mar-26 29-Mar-26 | IPC - 29 | SAV-P3-P4-G1 | 2026-03-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4295 MPSB/Str/4296 | 31-Mar-26 31-Mar-26 | IPC - 29 | SAV-P3-P4-G2 | 2026-03-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4297 MPSB/Str/4298 | 31-Mar-26 31-Mar-26 | IPC - 29 | SAV-P3-P4-G3 | 2026-03-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4673 MPSB/Str/4674 | 14-May-26 14-May-26 | IPC - 31 | SAV-P3-P4-G4 | 2026-05-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4732 MPSB/Str/4733 | 19-May-26 19-May-26 | IPC - 31 | SAV-P3-P4-G5 | 2026-05-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4756 MPSB/Str/4757 | 22-May-26 22-May-26 | IPC - 31 | SAV-P3-P4-G6 | 2026-05-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4790 MPSB/Str/4791 | 25-May-26 25-May-26 | IPC - 31 | SAV-P3-P4-G7 | 2026-05-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4808 MPSB/Str/4809 | 29-May-26 29-May-26 | IPC - 31 | SAV-P3-P4-G8 | 2026-05-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4830 MPSB/Str/4831 | 31-May-26 31-May-26 | IPC - 31 | SAV-P4-P5-G1 | 2026-05-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4832 MPSB/Str/4833 | 31-May-26 31-May-26 | IPC - 31 | SAV-P4-P5-G2 | 2026-05-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4888 MPSB/Str/4889 | 11-Jun-26 11-Jun-26 | IPC - 33 | SAV-P4-P5-G3 | 2026-06-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4907 MPSB/Str/4908 | 15-Jun-26 15-Jun-26 | IPC - 33 | SAV-P4-P5-G4 | 2026-06-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4928 MPSB/Str/4929 | 17-Jun-26 17-Jun-26 | IPC - 33 | SAV-P4-P5-G5 | 2026-06-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/4969 MPSB/Str/4970 | 20-Jun-26 20-Jun-26 | IPC - 33 | SAV-P4-P5-G6 | 2026-06-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/5024 MPSB/Str/5025 | 27-Jun-26 27-Jun-26 | IPC - 33 | SAV-P4-P5-G7 | 2026-06-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/5066 MPSB/Str/5067 | 30-Jun-26 30-Jun-26 | IPC - 33 | SAV-P4-P5-G8 | 2026-06-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/5129 MPSB/Str/5130 | 13-Jul-26 13-Jul-26 | IPC - 34 | SAV-P5-P6-G8 | 2026-07-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/5159 MPSB/Str/5160 | 18-Jul-26 18-Jul-26 | IPC - 34 | SAV-P5-P6-G7 | 2026-07-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/5181 MPSB/Str/5182 | 22-Jul-26 22-Jul-26 | IPC - 34 | SAV-P5-P6-G6 | 2026-07-01
504.b.1 | For Approach Viaduct - Casting of Girders in the precast yard | Nos. | Palashbari | 1 | MPSB/Str/5193 MPSB/Str/5194 | 25-Jul-26 25-Jul-26 | IPC - 34 | SAV-P5-P6-G5 | 2026-07-01
| Cumulative paid upto this Bill | Nos. |  | 49
| Paid upto previous Bill | Nos. |  | 45
| To be paid in this Bill | Nos. |  | 4
505 | Procurement, testing and supply of post tensioning material to site
505.a.1 | For Wetland Viaduct - Supply of material at site for Girders | MT |  | 119.49 | MPSB/Str/1633 | 2025-05-31 | IPC - 15
505.a.1 | For Wetland Viaduct - Supply of material at site for Girders | MT |  | 168.42 | MPSB/Str/2380 | 2025-09-30 | IPC - 20
505.a.1 | For Wetland Viaduct - Supply of material at site for Girders | MT |  | 42.33 | MPSB/Str/3718 | 2026-01-31 | IPC - 26 | 42.33MT/64.722MT has been considered
| Cumulative paid upto this Bill | MT |  | 330.24
| Paid upto previous Bill | MT |  | 330.24
| To be paid in this Bill | MT |  | 0
505.a.2 | For Wetland Viaduct - Testing of Material | MT |  | 119.49 | HBT-1624-SO-TPT-2025-0767 HBT-1624-SO-APR-2025-0786 | 30-Jun-25 4-Jul-25 | IPC - 16
505.a.2 | For Wetland Viaduct - Testing of Material | MT |  | 168.42 | As per Annexures |  | IPC - 23
505.a.2 | For Wetland Viaduct - Testing of Material | MT |  | 42.33 | As per Annexures |  | IPC - 29
| Cumulative paid upto this Bill | MT |  | 330.24
| Paid upto previous Bill | MT |  | 330.24
| To be paid in this Bill | MT |  | 0
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/1466 MPSB/Str/1692 | 10-May-25 21-Jun-25 | IPC - 25 | WV2-P0-P1-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/1556 MPSB/Str/1703 | 23-May-25 26-Jun-25 | IPC - 25 | WV2-P1-P2-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/1635 MPSB/Str/1702 | 04-Jun-25 26-Jun-25 | IPC - 25 | WV2-P0-P1-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/1830 MPSB/Str/2491 | 18-Jul-25 16-Oct-25 | IPC - 25 | WV2-P15-P16-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/1866 MPSB/Str/2492 | 22-Jul-25 16-Oct-25 | IPC - 25 | WV2-P15-P16-G7
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/1964 MPSB/Str/2215 | 03-Aug-25 11-Sep-25 | IPC - 25 | WV2-P16-P17-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/1982 MPSB/Str/2214 | 05-Aug-25 11-Sep-25 | IPC - 25 | WV2-P16-P17-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2017 MPSB/Str/2222 | 12-Aug-25 12-Sep-25 | IPC - 25 | WV2-P15-P16-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2043 MPSB/Str/2636 | 18-Aug-25 30-Oct-25 | IPC - 25 | WV2-P15-P16-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2052 MPSB/Str/2198 | 19-Aug-25 10-Sep-25 | IPC - 25 | WV2-P15-P16-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2089 MPSB/Str/2638 | 25-Aug-25 30-Oct-25 | IPC - 25 | WV2-P15-P16-G8
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2182 MPSB/Str/2730 | 08-Sep-25 07-Nov-25 | IPC - 25 | WV2-P19-P20-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2099 MPSB/Str/2509 | 27-Aug-25 17-Oct-25 | IPC - 25 | WV2-P16-P17-G7
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2136 MPSB/Str/2700 | 02-Sep-25 04-Nov-25 | IPC - 25 | WV2-P16-P17-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2158 MPSB/Str/2744 | 05-Sep-25 08-Nov-25 | IPC - 25 | WV2-P18-P19-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2172 MPSB/Str/2729 | 06-Sep-25 07-Nov-25 | IPC - 25 | WV2-P18-P19-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2174 MPSB/Str/2783 | 07-Sep-25 12-Nov-25 | IPC - 25 | WV2-P18-P19-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2216 MPSB/Str/2674 | 11-Sep-25 01-Nov-25 | IPC - 25 | WV2-P16-P17-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2236 MPSB/Str/2817 | 15-Sep-25 15-Nov-25 | IPC - 25 | WV2-P20-P21-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2232 MPSB/Str/2621 | 14-Sep-25 29-Oct-25 | IPC - 25 | WV2-P20-P21-G7
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2296 MPSB/Str/2876 | 22-Sep-25 20-Nov-25 | IPC - 25 | WV2-P18-P19-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2299 MPSB/Str/2637 | 23-Sep-25 30-Oct-25 | IPC - 25 | WV2-P20-P21-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2465 MPSB/Str/2897 | 14-Oct-25 22-Nov-25 | IPC - 25 | WV2-P17-P18-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2548 MPSB/Str/2886 | 23-Oct-25 21-Nov-25 | IPC - 25 | WV2-P17-P18-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2393 MPSB/Str/3027 | 4-Oct-25 3-Dec-25 | IPC - 25 | WV2-P19-P20-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2302 MPSB/Str/3028 | 23-Sep-25 3-Dec-25 | IPC - 25 | WV2-P20-P21-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2394 MPSB/Str/3081 | 4-Oct-25 8-Dec-25 | IPC - 25 | WV2-P20-P21-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2401 MPSB/Str/3113 | 6-Oct-25 11-Dec-25 | IPC - 25 | WV2-P20-P21-G8
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2464 MPSB/Str/3082 | 13-Oct-25 8-Dec-25 | IPC - 25 | WV2-P17-P18-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2490 MPSB/Str/3083 | 16-Oct-25 8-Dec-25 | IPC - 25 | WV2-P19-P20-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2549 MPSB/Str/3260 | 23-Oct-25 24-Dec-25 | IPC - 25 | WV2-P14-P15-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2343 MPSB/Str/3258 | 29-Sep-25 24-Dec-25 | IPC - 25 | WV2-P19-P20-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2536 MPSB/Str/3115 | 20-Oct-25 11-Dec-25 | IPC - 25 | WV2-P19-P20-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2131 MPSB/Str/3150 | 1-Sep-25 15-Dec-25 | IPC - 25 | WV2-P15-P16-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2610 MPSB/Str/3221 | 27-Oct-25 22-Dec-25 | IPC - 25 | WV2-P17-P18-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2699 MPSB/Str/3235 | 4-Nov-25 23-Dec-25 | IPC - 25 | WV2-P14-P15-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2676 MPSB/Str/3223 | 1-Nov-25 22-Dec-25 | IPC - 25 | WV2-P14-P15-G8
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2728 MPSB/Str/3234 | 7-Nov-25 23-Dec-25 | IPC - 25 | WV2-P13-P14-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2779 MPSB/Str/3236 | 12-Nov-25 23-Dec-25 | IPC - 25 | WV2-P14-P15-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2743 MPSB/Str/3237 | 8-Nov-25 23-Dec-25 | IPC - 25 | WV2-P14-P15-G7
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2807 MPSB/Str/3321 | 14-Nov-25 29-Dec-25 | IPC - 25 | WV2-P14-P15-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2808 MPSB/Str/3322 | 14-Nov-25 29-Dec-25 | IPC - 25 | WV2-P12-P13-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2490 MPSB/Str/2985 | 16-Oct-25 29-Nov-25 | IPC - 26 | WV2-P20-P21-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2387 MPSB/Str/3014 | 3-Oct-25 30-Nov-25 | IPC - 26 | WV2-P16-P17-G8
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2913 MPSB/Str/3061 | 24-Nov-25 5-Dec-25 | IPC - 26 | WV2-P20-P21-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2675 MPSB/Str/3222 | 1-Nov-25 22-Dec-25 | IPC - 26 | WV2-P14-P15-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2875 MPSB/Str/3412 | 20-Nov-25 3-Jan-26 | IPC - 26 | WV2-P13-P14-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2894 MPSB/Str/3443 | 22-Nov-25 7-Jan-26 | IPC - 26 | WV2-P19-P20-G7
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3199 MPSB/Str/3442 | 19-Dec-25 7-Jan-26 | IPC - 26 | WV2-P12-P13-G8
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3112 MPSB/Str/3455 | 11-Dec-25 8-Jan-26 | IPC - 26 | WV2-P11-P12-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3208 MPSB/Str/3413 | 20-Dec-25 3-Jan-26 | IPC - 26 | WV2-P09-P10-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3320 MPSB/Str/3456 | 29-Dec-25 8-Jan-26 | IPC - 26 | WV2-P11-P12-G8
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2912 MPSB/Str/3470 | 24-Nov-25 9-Jan-26 | IPC - 26 | WV2-P12-P13-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2974 MPSB/Str/3469 | 28-Nov-25 9-Jan-26 | IPC - 26 | WV2-P11-P12-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3029 MPSB/Str/3479 | 3-Dec-25 10-Jan-26 | IPC - 26 | WV2-P12-P13-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3071 MPSB/Str/3480 | 6-Dec-25 10-Jan-26 | IPC - 26 | WV2-P12-P13-G7
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3169 MPSB/Str/3488 | 17-Dec-25 11-Jan-26 | IPC - 26 | WV2-P19-P20-G8
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3030 MPSB/Str/3489 | 3-Dec-25 11-Jan-26 | IPC - 26 | WV2-P10-P11-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3314 MPSB/Str/3532 | 28-Dec-25 15-Jan-26 | IPC - 26 | WV2-P10-P11-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2613 MPSB/Str/3575 | 10-Nov-25 19-Jan-26 | IPC - 26 | WV2-P13-P14-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2698 MPSB/Str/3576 | 4-Nov-25 19-Jan-26 | IPC - 26 | WV2-P14-P15-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2742 MPSB/Str/3577 | 8-Nov-25 19-Jan-26 | IPC - 26 | WV2-P19-P20-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2773 MPSB/Str/3585 | 11-Nov-25 20-Jan-26 | IPC - 26 | WV2-P13-P14-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2940 MPSB/Str/3586 | 26-Nov-25 20-Jan-26 | IPC - 26 | WV2-P10-P11-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3091 MPSB/Str/3609 | 9-Dec-25 22-Jan-26 | IPC - 26 | WV2-P10-P11-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3209 MPSB/Str/3610 | 20-Dec-25 22-Jan-26 | IPC - 26 | WV2-P13-P14-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3198 MPSB/Str/3652 | 19-Dec-25 27-Jan-26 | IPC - 26 | WV2-P10-P11-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/1921 MPSB/Str/3763 | 30-Jul-25 5-Feb-26 | IPC - 27 | WV2-P16-P17-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/1938 MPSB/Str/3744 | 31-Jul-25 31-Jan-26 | IPC - 27 | WV2-P15-P16-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2827 MPSB/Str/3966 | 17-Nov-25 26-Feb-26 | IPC - 27 | WV2-P12-P13-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/2900 MPSB/Str/3752 | 23-Nov-25 2-Feb-26 | IPC - 27 | WV2-P12-P13-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3275 MPSB/Str/3786 | 25-Dec-25 7-Feb-26 | IPC - 27 | WV2-P11-P12-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3421 MPSB/Str/3787 | 4-Jan-26 7-Feb-26 | IPC - 27 | WV2-P18-P19-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3453 MPSB/Str/3779 | 7-Jan-26 6-Feb-26 | IPC - 27 | WV2-P18-P19-G8
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3482 MPSB/Str/3814 | 10-Jan-26 9-Feb-26 | IPC - 27 | WV2-P18-P19-G7
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3541 MPSB/Str/3899 | 16-Jan-26 19-Feb-26 | IPC - 27 | WV2-P18-P19-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3661 MPSB/Str/3965 | 28-Jan-26 26-Feb-26 | IPC - 27 | WV2-P11-P12-G7
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3542 MPSB/Str/3815 | 16-Jan-26 9-Feb-26 | IPC - 27 | WV2-P11-P12-G5
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3651 MPSB/Str/3944 | 27-Jan-26 24-Feb-26 | IPC - 27 | WV2-P13-P14-G8
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3760 MPSB/Str/3945 | 4-Feb-26 24-Feb-26 | IPC - 27 | WV2-P17-P18-G8
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/1959 MPSB/Str/4039 | 1-Aug-25 3-Mar-26 | IPC - 29 | WV2-P16-P17-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3751 MPSB/Str/4040 | 2-Feb-26 3-Mar-26 | IPC - 29 | WV2-P17-P18-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/3414 MPSB/Str/4069 | 3-Jan-26 8-Mar-26 | IPC - 29 | WV2-P10-P11-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4229 MPSB/Str/4289 | 28-Mar-26 31-Mar-26 | IPC - 29 | WV2-P11-P12-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4227 MPSB/Str/4290 | 28-Mar-26 31-Mar-26 | IPC - 29 | WV2-P11-P12-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4228 MPSB/Str/4308 | 28-Mar-26 1-Apr-26 | IPC - 30 | WV2-P13-P14-G7
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4267 MPSB/Str/4313 | 30-Mar-26 2-Apr-26 | IPC - 30 | WV2-P13-P14-G6
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4426 MPSB/Str/4467 | 17-Apr-26 22-Apr-26 | IPC - 30 | WV2-P9-P10-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4424 MPSB/Str/4469 | 17-Apr-26 22-Apr-26 | IPC - 30 | WV2-P9-P10-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4389 MPSB/Str/4453 | 13-Apr-26 20-Apr-26 | IPC - 30 | WV2-P9-P10-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4471 MPSB/Str/4477 | 23-Apr-26 24-Apr-26 | IPC - 30 | WV2-P9-P10-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4478 MPSB/Str/4489 | 24-Apr-26 25-Apr-26 | IPC - 30 | WV2-P8-P9-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4479 MPSB/Str/4490 | 24-Apr-26 25-Apr-26 | IPC - 30 | WV2-P8-P9-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4480 MPSB/Str/4491 | 24-Apr-26 26-Apr-26 | IPC - 30 | WV2-P8-P9-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4481 MPSB/Str/4492 | 24-Apr-26 26-Apr-26 | IPC - 30 | WV2-P8-P9-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4518 MPSB/Str/4529 | 28-Apr-26 29-Apr-26 | IPC - 30 | WV2-P7-P8-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4622 MPSB/Str/4623 | 9-May-26 9-May-26 | IPC - 31 | WV2-P7-P8-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4622 MPSB/Str/4623 | 9-May-26 9-May-26 | IPC - 31 | WV2-P7-P8-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4622 MPSB/Str/4623 | 9-May-26 9-May-26 | IPC - 31 | WV2-P7-P8-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4653 | 2026-05-12 | IPC - 31 | WV2-P6-P7-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4654 | 2026-05-12 | IPC - 31 | WV2-P6-P7-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4696 MPSB/Str/4697 | 16-May-26 16-May-26 | IPC - 31 | WV2-P5-P6-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4865 MPSB/Str/4866 | 4-Jun-26 4-Jun-26 | IPC - 33 | WV2-P5-P6-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4865 MPSB/Str/4866 | 4-Jun-26 4-Jun-26 | IPC - 33 | WV2-P5-P6-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4876 MPSB/Str/4877 | 6-Jun-26 6-Jun-26 | IPC - 33 | WV2-P4-P5-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4913 MPSB/Str/4914 | 15-Jun-26 15-Jun-26 | IPC - 33 | WV2-P4-P5-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/5015 MPSB/Str/5016 | 25-Jun-26 25-Jun-26 | IPC - 33 | WV2-P4-P5-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4961 MPSB/Str/4962 | 20-Jun-26 20-Jun-26 | IPC - 33 | WV2-P5-P6-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/5013 MPSB/Str/5014 | 25-Jun-26 25-Jun-26 | IPC - 33 | WV2-P3-P4-G4
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/5077 | 2026-07-02 | IPC - 34 | WV2-P3-P4-G2
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/5092 | 2026-07-07 | IPC - 34 | WV2-P3-P4-G3
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/5225 | 2026-07-29 | IPC - 34 | WV2-P3-P4-G1
505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/5226 | 2026-07-29 | IPC - 34 | WV2-P1-P2-G1
| Cumulative paid upto this Bill | Nos. |  | 113
| Paid upto previous Bill | Nos. |  | 109
| To be paid in this Bill | Nos. |  | 4
505.b.1 | For Approach Viaduct - Supply of material at site for Girders | MT |  | 152.054 | MPSB/Str/3718 MPSB/Str/3743 | 2026-01-31 | IPC - 26 | 22.392/64.722MT has been considered along with 129.662MT
| Cumulative paid upto this Bill | MT |  | 152.054
| Paid upto previous Bill | MT |  | 152.054
| To be paid in this Bill | MT |  | 0
505.b.2 | For Approach Viaduct - Testing of material | MT |  | 152.054 | As per Annexures |  | IPC - 29
| Cumulative paid upto this Bill | MT |  | 152.054
| Paid upto previous Bill | MT |  | 152.054
| To be paid in this Bill | MT |  | 0
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4373 MPSB/Str/4403 | 11-Apr-26 14-Apr-26 | IPC - 30 | SAV-P0-P1-G5
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4374 MPSB/Str/4404 | 11-Apr-26 14-Apr-26 | IPC - 30 | SAV-P0-P1-G6
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4401 MPSB/Str/4411 | 14-Apr-26 16-Apr-26 | IPC - 30 | SAV-P0-P1-G7
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4402 MPSB/Str/4412 | 14-Apr-26 16-Apr-26 | IPC - 30 | SAV-P0-P1-G8
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4630 MPSB/Str/4631 | 10-May-26 10-May-26 | IPC - 31 | SAV-P0-P1-G4
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4680 MPSB/Str/4681 | 14-May-26 14-May-26 | IPC - 31 | SAV-P1-P2-G1
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4682 MPSB/Str/4683 | 14-May-26 14-May-26 | IPC - 31 | SAV-P1-P2-G2
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4727 MPSB/Str/4728 | 19-May-26 19-May-26 | IPC - 31 | SAV-P1-P2-G3
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4729 MPSB/Str/4730 | 19-May-26 19-May-26 | IPC - 31 | SAV-P1-P2-G4
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4797 MPSB/Str/4798 | 28-May-26 28-May-26 | IPC - 31 | SAV-P1-P2-G5
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4799 MPSB/Str/4800 | 28-May-26 28-May-26 | IPC - 31 | SAV-P1-P2-G6
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4825 MPSB/Str/4826 | 31-May-26 31-May-26 | IPC - 31 | SAV-P1-P2-G7
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4827 MPSB/Str/4828 | 31-May-26 31-May-26 | IPC - 31 | SAV-P1-P2-G8
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4918 MPSB/Str/4919 | 16-Jun-26 16-Jun-26 | IPC - 33 | SAV-P2-P3-G8
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4920 MPSB/Str/4921 | 16-Jun-26 16-Jun-26 | IPC - 33 | SAV-P2-P3-G7
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4933 MPSB/Str/4934 | 17-Jun-26 17-Jun-26 | IPC - 33 | SAV-P2-P3-G6
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/4999 MPSB/Str/5000 | 24-Jun-26 24-Jun-26 | IPC - 33 | SAV-P2-P3-G5
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/5148 | 2026-07-15 | IPC - 34 | SAV-P2-P3-G1
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/5149 | 2026-07-15 | IPC - 34 | SAV-P2-P3-G2
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/5191 | 2026-07-25 | IPC - 34 | SAV-P1R-P2R-G2
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/5192 | 2026-07-25 | IPC - 34 | SAV-P1R-P2R-G3
505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. | Palashbari | 1 | MPSB/Str/5211 | 2026-07-28 | IPC - 34 | SAV-P1R-P2R-G1
| Cumulative paid upto this Bill | Nos. |  | 22
| Paid upto previous Bill | Nos. |  | 17
| To be paid in this Bill | Nos. |  | 5
506 | Installation of PSC Box girders/I-Girders at site including installation of Post Tensioning for completion of deck
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/3753 | 2026-02-02 | IPC - 27 | PL19 to PL20
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/3808 | 2026-02-09 | IPC - 27 | PL20 to PL21
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/3889 | 2026-02-18 | IPC - 27 | PR20 to PR21
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4225 | 2026-03-28 | IPC - 29 | PL18 to PL19
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4247 | 2026-03-29 | IPC - 29 | PL17 to PL18
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4261 | 2026-03-30 | IPC - 29 | PL16 to PL17
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4282 | 2026-03-31 | IPC - 29 | PL15 to PL16
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4501 | 2026-04-28 | IPC - 30 | PL14 to PL15
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4531 | 2026-04-29 | IPC - 30 | PL13 to PL14
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4493 | 2026-04-26 | IPC - 30 | PL12 to PL13
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4677 | 2026-05-14 | IPC - 31 | PL11 to PL12
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4745 | 2026-05-21 | IPC - 31 | PL9 to PL10
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4879 | 2026-06-08 | IPC - 33 | PL8 to PL9
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4992 | 2026-06-23 | IPC - 33 | PL7 to PL8
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4932 | 2026-06-17 | IPC - 33 | PL6 to PL7
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4991 | 2026-06-22 | IPC - 33 | PL5 to PL6
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5009 | 2026-06-25 | IPC - 33 | PL4 to PL5
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5034 | 2026-06-29 | IPC - 33 | PL3 to PL4
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5056 | 2026-06-30 | IPC - 33 | PL2 to PL3
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4959 | 2026-06-20 | IPC - 34 | PL10 to PL11
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5081 | 2026-07-03 | IPC - 34 | PL1 to PL2
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5135 | 2026-07-14 | IPC - 34 | PL0 to PL1
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5144 | 2026-07-15 | IPC - 34 | PR19 to PR20
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5213 | 2026-07-28 | IPC - 34 | PR18 to PR19
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5212 | 2026-07-28 | IPC - 34 | PR17 to PR18
506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/5254 | 2026-07-31 | IPC - 34 | PR16 to PR17
| Cumulative paid upto this Bill | Span |  | 26
| Paid upto previous Bill | Span |  | 19
| To be paid in this Bill | Span |  | 7
506.a.2 | For Wetland Viaduct - Deck Panel Erection | Span | Sualkuchi | 3 | MPSB/Str/4502 | 2026-04-28 | IPC - 30 | PL18 to PL21
506.a.2 | For Wetland Viaduct - Deck Panel Erection | Span | Sualkuchi | 3 | MPSB/Str/4503 | 2026-04-28 | IPC - 30 | PL15 to PL18
506.a.2 | For Wetland Viaduct - Deck Panel Erection | Span | Sualkuchi | 3 | MPSB/Str/5058 | 2026-06-30 | IPC - 33 | PL12 to PL15
506.a.2 | For Wetland Viaduct - Deck Panel Erection | Span | Sualkuchi | 3 | MPSB/Str/5079 | 2026-07-03 | IPC - 34 | PL9 to PL12
| Cumulative paid upto this Bill | Span |  | 12
| Paid upto previous Bill | Span |  | 9
| To be paid in this Bill | Span |  | 3
506.a.3 | For Wetland Viaduct - Deck Slab casting | Span | Sualkuchi | 3 | MPSB/Str/4844 | 2026-05-31 | IPC - 31 | PL18 to PL21
506.a.3 | For Wetland Viaduct - Deck Slab casting | Span | Sualkuchi | 3 | MPSB/Str/5019 | 2026-06-26 | IPC - 33 | PL15 to PL18
506.a.3 | For Wetland Viaduct - Deck Slab casting | Span | Sualkuchi | 3 | MPSB/Str/5059 | 2026-06-30 | IPC - 33 | PL12 to PL15
506.a.3 | For Wetland Viaduct - Deck Slab casting | Span | Sualkuchi | 3 | MPSB/Str/5197 | 2026-07-25 | IPC - 34 | PL9 to PL12
| Cumulative paid upto this Bill | Span |  | 12
| Paid upto previous Bill | Span |  | 9
| To be paid in this Bill | Span |  | 3
506.b.1 | For Approach Viaduct - Casting of Deck Panel | Span | Palashbari | 1 | MPSB/Str/4208 MPSB/Str/4236 | 26-Mar-26 28-Mar-26 | IPC - 29 | PL0 to PL1
506.b.1 | For Approach Viaduct - Casting of Deck Panel | Span | Palashbari | 1 | MPSB/Str/4246 MPSB/Str/4301 | 29-Mar-26 31-Mar-26 | IPC - 29 | PR0 to PR1
506.b.1 | For Approach Viaduct - Casting of Deck Panel | Span | Palashbari | 1 | MPSB/Str/5001 | 2026-06-24 | IPC - 33 | PL1 to PL2
506.b.1 | For Approach Viaduct - Casting of Deck Panel | Span | Palashbari | 1 | MPSB/Str/5068 | 2026-06-30 | IPC - 33 | PL2 to PL3
| Cumulative paid upto this Bill | Span |  | 4
| Paid upto previous Bill | Span |  | 4
| To be paid in this Bill | Span |  | 0
507 | Installation of bearings and expansion joints
507.a.1 | For Wetland Viaduct - Bearings - Material Testing and Procurement | Nos. |  | 52 | MPSB/L&T/TIIC/2026/1502 | 2026-03-14 | IPC - 29
507.a.1 | For Wetland Viaduct - Bearings - Material Testing and Procurement | Nos. |  | 60 | As per attachments |  | IPC - 30
507.a.1 | For Wetland Viaduct - Bearings - Material Testing and Procurement | Nos. |  | 16 | As per attachments |  | IPC - 33
| Cumulative paid upto this Bill | Nos. |  | 128
| Paid upto previous Bill | Nos. |  | 128
| To be paid in this Bill | Nos. |  | 0
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3112 | 2026-03-13 | IPC - 29 | PL21
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3261 | 2026-04-08 | IPC - 30 | PL20
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3262 | 2026-04-08 | IPC - 30 | PL18
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3278 | 2026-04-11 | IPC - 30 | PL19
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3375 | 2026-04-28 | IPC - 30 | PL16
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3262 | 2026-04-08 | IPC - 31 | PL18
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 4 | MPSB/Sur/3419 | 2026-05-06 | IPC - 31 | PL15
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3438 | 2026-05-08 | IPC - 31 | PL13
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3445 | 2026-05-09 | IPC - 31 | PL11
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3450 | 2026-05-10 | IPC - 31 | PL8
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 4 | MPSB/Sur/3451 | 2026-05-10 | IPC - 31 | PL9
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 4 | MPSB/Sur/3452 | 2026-05-11 | IPC - 31 | PL12
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3468 | 2026-05-12 | IPC - 31 | PL5
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 4 | MPSB/Sur/3469 | 2026-05-12 | IPC - 31 | PL6
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3483 | 2026-05-15 | IPC - 31 | PL10
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3496 | 2026-05-17 | IPC - 31 | PL17
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3521 | 2026-05-20 | IPC - 31 | PR17
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3637 | 2026-06-11 | IPC - 33 | PL14
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3653 | 2026-06-15 | IPC - 33 | PL7
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3660 | 2026-06-17 | IPC - 33 | PR19
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3687 | 2026-06-24 | IPC - 33 | PL4
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3725 | 2026-07-03 | IPC - 34 | PR20
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3726 | 2026-07-03 | IPC - 34 | PR21
507.a.2 | For Wetland Viaduct - Bearings - Installation | Nos. | Sualkuchi | 4 | MPSB/Sur/3761 | 2026-07-14 | IPC - 34 | PR18
| Cumulative paid upto this Bill | Nos. |  | 58
| Paid upto previous Bill | Nos. |  | 50
| To be paid in this Bill | Nos. |  | 8

## Girder Abs.
Girders - Scope Vs Casting
| LHS | [6 empty] | RHS
Girder ID | G1 | G2 | G3 | G4 | G5 | G6 | G7 | G8
WV1-P0-P1 | - | - | 2026-07-01 | - | - | - | 2026-07-01 | - | WV1-P0-P1-G1 | WV1-P0-P1-G2 | WV1-P0-P1-G3 | WV1-P0-P1-G4 | WV1-P0-P1-G5 | WV1-P0-P1-G6 | WV1-P0-P1-G7 | WV1-P0-P1-G8 | - | - | 2026-07-01 | - | - | - | 2026-07-01 | -
WV1-P1-P2 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | - | - | - | - | WV1-P1-P2-G1 | WV1-P1-P2-G2 | WV1-P1-P2-G3 | WV1-P1-P2-G4 | WV1-P1-P2-G5 | WV1-P1-P2-G6 | WV1-P1-P2-G7 | WV1-P1-P2-G8 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | - | - | - | -
WV1-P2-P3 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | WV1-P2-P3-G1 | WV1-P2-P3-G2 | WV1-P2-P3-G3 | WV1-P2-P3-G4 | WV1-P2-P3-G5 | WV1-P2-P3-G6 | WV1-P2-P3-G7 | WV1-P2-P3-G8 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01
[17 empty] | - | - | - | - | - | - | - | -
WV2-P0-P1 | 2026-06-01 | 2025-04-01 | 2025-05-01 | 2026-06-01 | - | - | - | - | WV2-P0-P1-G1 | WV2-P0-P1-G2 | WV2-P0-P1-G3 | WV2-P0-P1-G4 | WV2-P0-P1-G5 | WV2-P0-P1-G6 | WV2-P0-P1-G7 | WV2-P0-P1-G8 | 2026-06-01 | 2025-04-01 | 2025-05-01 | 2026-06-01 | - | - | - | -
WV2-P1-P2 | 2026-06-01 | 2025-05-01 | 2026-06-01 | 2026-06-01 | - | - | - | - | WV2-P1-P2-G1 | WV2-P1-P2-G2 | WV2-P1-P2-G3 | WV2-P1-P2-G4 | WV2-P1-P2-G5 | WV2-P1-P2-G6 | WV2-P1-P2-G7 | WV2-P1-P2-G8 | 2026-06-01 | 2025-05-01 | 2026-06-01 | 2026-06-01 | - | - | - | -
WV2-P2-P3 | - | 2026-06-01 | 2026-06-01 | 2026-05-01 | - | - | - | - | WV2-P2-P3-G1 | WV2-P2-P3-G2 | WV2-P2-P3-G3 | WV2-P2-P3-G4 | WV2-P2-P3-G5 | WV2-P2-P3-G6 | WV2-P2-P3-G7 | WV2-P2-P3-G8 | - | 2026-06-01 | 2026-06-01 | 2026-05-01 | - | - | - | -
WV2-P3-P4 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | - | - | - | - | WV2-P3-P4-G1 | WV2-P3-P4-G2 | WV2-P3-P4-G3 | WV2-P3-P4-G4 | WV2-P3-P4-G5 | WV2-P3-P4-G6 | WV2-P3-P4-G7 | WV2-P3-P4-G8 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | - | - | - | -
WV2-P4-P5 | 2026-04-01 | 2026-05-01 | - | 2026-05-01 | - | - | - | - | WV2-P4-P5-G1 | WV2-P4-P5-G2 | WV2-P4-P5-G3 | WV2-P4-P5-G4 | WV2-P4-P5-G5 | WV2-P4-P5-G6 | WV2-P4-P5-G7 | WV2-P4-P5-G8 | 2026-04-01 | 2026-05-01 | - | 2026-05-01 | - | - | - | -
WV2-P5-P6 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | - | - | - | - | WV2-P5-P6-G1 | WV2-P5-P6-G2 | WV2-P5-P6-G3 | WV2-P5-P6-G4 | WV2-P5-P6-G5 | WV2-P5-P6-G6 | WV2-P5-P6-G7 | WV2-P5-P6-G8 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | - | - | - | -
WV2-P6-P7 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | - | - | - | - | WV2-P6-P7-G1 | WV2-P6-P7-G2 | WV2-P6-P7-G3 | WV2-P6-P7-G4 | WV2-P6-P7-G5 | WV2-P6-P7-G6 | WV2-P6-P7-G7 | WV2-P6-P7-G8 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | - | - | - | -
WV2-P7-P8 | 2026-04-01 | 2026-03-01 | 2026-04-01 | 2026-03-01 | - | - | - | - | WV2-P7-P8-G1 | WV2-P7-P8-G2 | WV2-P7-P8-G3 | WV2-P7-P8-G4 | WV2-P7-P8-G5 | WV2-P7-P8-G6 | WV2-P7-P8-G7 | WV2-P7-P8-G8 | 2026-04-01 | 2026-03-01 | 2026-04-01 | 2026-03-01 | - | - | - | -
WV2-P8-P9 | 2026-03-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | - | - | - | - | WV2-P8-P9-G1 | WV2-P8-P9-G2 | WV2-P8-P9-G3 | WV2-P8-P9-G4 | WV2-P8-P9-G5 | WV2-P8-P9-G6 | WV2-P8-P9-G7 | WV2-P8-P9-G8 | 2026-03-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | - | - | - | -
WV2-P9-P10 | 2026-03-01 | 2026-02-01 | 2026-03-01 | 2026-02-01 | 2025-12-01 | - | - | - | WV2-P9-P10-G1 | WV2-P9-P10-G2 | WV2-P9-P10-G3 | WV2-P9-P10-G4 | WV2-P9-P10-G5 | WV2-P9-P10-G6 | WV2-P9-P10-G7 | WV2-P9-P10-G8 | 2026-03-01 | 2026-02-01 | 2026-03-01 | 2026-02-01 | 2025-12-01 | - | - | -
WV2-P10-P11 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | - | 2026-07-01 | WV2-P10-P11-G1 | WV2-P10-P11-G2 | WV2-P10-P11-G3 | WV2-P10-P11-G4 | WV2-P10-P11-G5 | WV2-P10-P11-G6 | WV2-P10-P11-G7 | WV2-P10-P11-G8 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | - | 2026-07-01
WV2-P11-P12 | 2026-03-01 | 2025-11-01 | 2025-12-01 | 2026-03-01 | 2026-01-01 | 2025-11-01 | 2026-01-01 | 2025-12-01 | WV2-P11-P12-G1 | WV2-P11-P12-G2 | WV2-P11-P12-G3 | WV2-P11-P12-G4 | WV2-P11-P12-G5 | WV2-P11-P12-G6 | WV2-P11-P12-G7 | WV2-P11-P12-G8 | 2026-03-01 | 2025-11-01 | 2025-12-01 | 2026-03-01 | 2026-01-01 | 2025-11-01 | 2026-01-01 | 2025-12-01
WV2-P12-P13 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | WV2-P12-P13-G1 | WV2-P12-P13-G2 | WV2-P12-P13-G3 | WV2-P12-P13-G4 | WV2-P12-P13-G5 | WV2-P12-P13-G6 | WV2-P12-P13-G7 | WV2-P12-P13-G8 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WV2-P13-P14 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2026-02-01 | 2026-03-01 | 2026-01-01 | WV2-P13-P14-G1 | WV2-P13-P14-G2 | WV2-P13-P14-G3 | WV2-P13-P14-G4 | WV2-P13-P14-G5 | WV2-P13-P14-G6 | WV2-P13-P14-G7 | WV2-P13-P14-G8 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2026-02-01 | 2026-03-01 | 2026-01-01
WV2-P14-P15 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-01 | WV2-P14-P15-G1 | WV2-P14-P15-G2 | WV2-P14-P15-G3 | WV2-P14-P15-G4 | WV2-P14-P15-G5 | WV2-P14-P15-G6 | WV2-P14-P15-G7 | WV2-P14-P15-G8 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-11-01 | 2025-10-01 | 2025-10-01
WV2-P15-P16 | 2025-08-01 | 2025-07-01 | 2025-07-01 | 2025-08-01 | 2025-08-01 | 2025-07-01 | 2025-07-01 | 2025-08-01 | WV2-P15-P16-G1 | WV2-P15-P16-G2 | WV2-P15-P16-G3 | WV2-P15-P16-G4 | WV2-P15-P16-G5 | WV2-P15-P16-G6 | WV2-P15-P16-G7 | WV2-P15-P16-G8 | 2025-08-01 | 2025-07-01 | 2025-07-01 | 2025-08-01 | 2025-08-01 | 2025-07-01 | 2025-07-01 | 2025-08-01
WV2-P16-P17 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-06-01 | 2025-08-01 | 2025-09-01 | WV2-P16-P17-G1 | WV2-P16-P17-G2 | WV2-P16-P17-G3 | WV2-P16-P17-G4 | WV2-P16-P17-G5 | WV2-P16-P17-G6 | WV2-P16-P17-G7 | WV2-P16-P17-G8 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-06-01 | 2025-08-01 | 2025-09-01
WV2-P17-P18 | 2025-09-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | WV2-P17-P18-G1 | WV2-P17-P18-G2 | WV2-P17-P18-G3 | WV2-P17-P18-G4 | WV2-P17-P18-G5 | WV2-P17-P18-G6 | WV2-P17-P18-G7 | WV2-P17-P18-G8 | 2025-09-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01
WV2-P18-P19 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-09-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | WV2-P18-P19-G1 | WV2-P18-P19-G2 | WV2-P18-P19-G3 | WV2-P18-P19-G4 | WV2-P18-P19-G5 | WV2-P18-P19-G6 | WV2-P18-P19-G7 | WV2-P18-P19-G8 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-09-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01
WV2-P19-P20 | 2025-09-01 | 2025-10-01 | 2025-09-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | WV2-P19-P20-G1 | WV2-P19-P20-G2 | WV2-P19-P20-G3 | WV2-P19-P20-G4 | WV2-P19-P20-G5 | WV2-P19-P20-G6 | WV2-P19-P20-G7 | WV2-P19-P20-G8 | 2025-09-01 | 2025-10-01 | 2025-09-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-11-01
WV2-P20-P21 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | WV2-P20-P21-G1 | WV2-P20-P21-G2 | WV2-P20-P21-G3 | WV2-P20-P21-G4 | WV2-P20-P21-G5 | WV2-P20-P21-G6 | WV2-P20-P21-G7 | WV2-P20-P21-G8 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-01
[17 empty] | - | - | - | - | - | - | - | -
SAV-P0-P1 | 2026-01-01 | 2026-01-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | SAV-P0-P1-G1 | SAV-P0-P1-G2 | SAV-P0-P1-G3 | SAV-P0-P1-G4 | SAV-P0-P1-G5 | SAV-P0-P1-G6 | SAV-P0-P1-G7 | SAV-P0-P1-G8 | 2026-01-01 | 2026-01-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-01-01 | 2026-01-01
SAV-P1-P2 | 2026-02-01 | 2026-02-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | - | SAV-P1-P2-G1 | SAV-P1-P2-G2 | SAV-P1-P2-G3 | SAV-P1-P2-G4 | SAV-P1-P2-G5 | SAV-P1-P2-G6 | SAV-P1-P2-G7 | SAV-P1-P2-G8 | 2026-02-01 | 2026-02-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | -
SAV-P1R-P2R | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | - | - | SAV-P1R-P2R-G1 | SAV-P1R-P2R-G2 | SAV-P1R-P2R-G3 | SAV-P1R-P2R-G4 | SAV-P1R-P2R-G5 | SAV-P1R-P2R-G6 | SAV-P1R-P2R-G7 | SAV-P1R-P2R-G8 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | - | -
SAV-P2-P3 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-02-01 | SAV-P2-P3-G1 | SAV-P2-P3-G2 | SAV-P2-P3-G3 | SAV-P2-P3-G4 | SAV-P2-P3-G5 | SAV-P2-P3-G6 | SAV-P2-P3-G7 | SAV-P2-P3-G8 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-02-01
SAV-P3-P4 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | SAV-P3-P4-G1 | SAV-P3-P4-G2 | SAV-P3-P4-G3 | SAV-P3-P4-G4 | SAV-P3-P4-G5 | SAV-P3-P4-G6 | SAV-P3-P4-G7 | SAV-P3-P4-G8 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01
SAV-P4-P5 | 2026-05-01 | 2026-05-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | SAV-P4-P5-G1 | SAV-P4-P5-G2 | SAV-P4-P5-G3 | SAV-P4-P5-G4 | SAV-P4-P5-G5 | SAV-P4-P5-G6 | SAV-P4-P5-G7 | SAV-P4-P5-G8 | 2026-05-01 | 2026-05-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01
SAV-P5-P6 | - | - | - | - | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | SAV-P5-P6-G1 | SAV-P5-P6-G2 | SAV-P5-P6-G3 | SAV-P5-P6-G4 | SAV-P5-P6-G5 | SAV-P5-P6-G6 | SAV-P5-P6-G7 | SAV-P5-P6-G8 | - | - | - | - | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01
[17 empty] | - | - | - | - | - | - | - | -
NAV-P30-31 | [8 empty] | NAV-P30-31-G1 | NAV-P30-31-G2 | NAV-P30-31-G3 | NAV-P30-31-G4 | NAV-P30-31-G5 | NAV-P30-31-G6 | NAV-P30-31-G7 | NAV-P30-31-G8 | - | - | - | - | - | - | - | - | bar: 2026-05-01 to 2026-06-01
NAV-P31-32 | [8 empty] | NAV-P31-32-G1 | NAV-P31-32-G2 | NAV-P31-32-G3 | NAV-P31-32-G4 | NAV-P31-32-G5 | NAV-P31-32-G6 | NAV-P31-32-G7 | NAV-P31-32-G8 | - | - | - | - | - | - | - | - | bar: 2026-05-01 to 2026-06-01
NAV-P32-33 | [8 empty] | NAV-P32-33-G1 | NAV-P32-33-G2 | NAV-P32-33-G3 | NAV-P32-33-G4 | NAV-P32-33-G5 | NAV-P32-33-G6 | NAV-P32-33-G7 | NAV-P32-33-G8 | - | - | - | - | - | - | - | - | bar: 2026-05-01 to 2026-06-01
NAV-P32R-P33R | [8 empty] | NAV-P32R-P33R-G1 | NAV-P32R-P33R-G2 | NAV-P32R-P33R-G3 | NAV-P32R-P33R-G4 | NAV-P32R-P33R-G5 | NAV-P32R-P33R-G6 | NAV-P32R-P33R-G7 | NAV-P32R-P33R-G8 | - | - | - | - | - | - | - | - | bar: 2026-05-01 to 2026-06-01
NAV-P33-34 | [8 empty] | NAV-P33-34-G1 | NAV-P33-34-G2 | NAV-P33-34-G3 | NAV-P33-34-G4 | NAV-P33-34-G5 | NAV-P33-34-G6 | NAV-P33-34-G7 | NAV-P33-34-G8 | - | - | - | - | - | - | - | - | bar: 2026-05-01 to 2026-06-01
NAV-P34-35 | [8 empty] | NAV-P34-35-G1 | NAV-P34-35-G2 | NAV-P34-35-G3 | NAV-P34-35-G4 | NAV-P34-35-G5 | NAV-P34-35-G6 | NAV-P34-35-G7 | NAV-P34-35-G8 | - | - | - | - | - | - | - | - | bar: 2026-05-01 to 2026-06-01
NAV-P35-36 | [8 empty] | NAV-P35-36-G1 | NAV-P35-36-G2 | NAV-P35-36-G3 | NAV-P35-36-G4 | NAV-P35-36-G5 | NAV-P35-36-G6 | NAV-P35-36-G7 | NAV-P35-36-G8 | - | - | - | - | - | - | - | - | bar: 2026-05-01 to 2026-06-01
[17 empty] | - | - | - | - | - | - | - | -
VUP- A1-P2 | [8 empty] | VUP- A1-P2-G1 | VUP- A1-P2-G2 | VUP- A1-P2-G3 | VUP- A1-P2-G4 | VUP- A1-P2-G5 | VUP- A1-P2-G6 | VUP- A1-P2-G7 | VUP- A1-P2-G8 | - | - | - | - | - | - | - | - | bar: 2026-05-01 to 2026-06-01
VUP- P1-P2 | [8 empty] | VUP- P1-P2-G1 | VUP- P1-P2-G2 | VUP- P1-P2-G3 | VUP- P1-P2-G4 | VUP- P1-P2-G5 | VUP- P1-P2-G6 | VUP- P1-P2-G7 | VUP- P1-P2-G8 | - | - | - | - | - | - | - | - | bar: 2026-05-01 to 2026-06-01
VUP- P2-A2 | [8 empty] | VUP- P2-A2-G1 | VUP- P2-A2-G2 | VUP- P2-A2-G3 | VUP- P2-A2-G4 | VUP- P2-A2-G5 | VUP- P2-A2-G6 | VUP- P2-A2-G7 | VUP- P2-A2-G8 | - | - | - | - | - | - | - | - | bar: 2026-05-01 to 2026-06-01
| Month | No. of Girders Casted |  |  | Month | No. of Girders Casted
| 2025-04-01 | 1 |  |  | 2026-06-01 | 13
| 2025-05-01 | 2 |  |  | 2026-07-01 | 19
| 2025-06-01 | 1 |  |  | 2026-08-01 | 0
| 2025-07-01 | 7 |  |  | 2026-09-01 | 0
| 2025-08-01 | 9 |  |  | 2026-10-01 | 0
| 2025-09-01 | 14 |  |  | 2026-11-01 | 0
| 2025-10-01 | 15 |  |  | 2026-12-01 | 0
| 2025-11-01 | 18 |  |  | 2027-01-01 | 0
| 2025-12-01 | 15 |  |  | 2027-02-01 | 0
| 2026-01-01 | 17 |  |  | 2027-03-01 | 0
| 2026-02-01 | 15 |  |  | 2027-04-01 | 0
| 2026-03-01 | 22 |  |  | 2027-05-01 | 0
| 2026-04-01 | 7 |  |  | 2027-06-01 | 0
| 2026-05-01 | 14 |  |  | 2027-07-01 | 0
|  |  | Total Girders Casted |  | 189

## Schedule 6
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
2-Jul-25 2-Jul-25
Schedule 6 - Wetland and Approach Viaduct Works | [7 empty] | IPC - 34
Measurement Sheet
Item No. | Item Description | UoM | Location | Executed Quantity | RFI No. / Letter No. / Period | Date | Bill No. | Remarks
603 | Construction of foundation
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2004 MPSB/Str/2511 | 2025-10-17 | IPC - 22 | 4+480 - LA1/P1
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2003 MPSB/Str/2510 | 2025-10-17 | IPC - 22 | 4+480 - RA1/P2
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2020 MPSB/Str/2544 | 2025-10-22 | IPC - 22 | 4+480 - RA1/P3
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2033 MPSB/Str/2557 | 2025-10-23 | IPC - 22 | 4+480 - RA1/P1
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2040 MPSB/Str/2574 | 2025-10-24 | IPC - 22 | 4+480 - LA1/P4
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2038 MPSB/Str/2571 | 2025-10-24 | IPC - 22 | 4+480 - RA1/P4
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2047 MPSB/Str/2584 | 2025-10-25 | IPC - 22 | 4+480 - LA1/P3
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2059 MPSB/Str/2597 | 2025-10-27 | IPC - 22 | 4+480 - LA1/P2
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2067 MPSB/Str/2625 | 2025-10-29 | IPC - 22 | 4+480 - LP2/P1
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2091 MPSB/Str/2659 | 2025-10-29 | IPC - 22 | 4+480 - LP2/P6
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2092 MPSB/Str/2660 | 2025-10-31 | IPC - 22 | 4+480 - RP2/P1
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2090 MPSB/Str/2658 | 2025-10-31 | IPC - 22 | 4+480 - RP2/P6
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2095 MPSB/Str/2663 | 2025-10-31 | IPC - 22 | 4+480 - LP2/P5
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2094 MPSB/Str/2662 | 2025-10-31 | IPC - 22 | 4+480 - RP2/P5
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2093 MPSB/Str/2661 | 2025-10-31 | IPC - 22 | 4+480 - LP2/P2
603.a | For Vehicular Underpass - On completion of Piles | Nos. | Palashbari | 1 | MPSB/Sur/2123 MPSB/Str/2701 | 2025-11-04 | IPC - 23 | 4+480 - RP2/P2
| Cumulative paid upto this Bill | Nos. |  | 16
| Paid upto previous Bill | Nos. |  | 16
| To be paid in this Bill | Nos. |  | 0
603.b | For Vehicular Underpass - Construction of Raft | Nos. | Palashbari | 0.5 | MPSB/Sur/2537 MPSB/Str/3328 | 2025-12-29 | IPC - 25 | Km 3+061 - RHS
603.b | For Vehicular Underpass - Construction of Raft | Nos. | Palashbari | 0.5 | MPSB/Sur/2580 MPSB/Str/3393 | 2025-12-31 | IPC - 25 | Km 3+061 - LHS
603.b | For Vehicular Underpass - Construction of Raft | Nos. | Palashbari | 0.5 | MPSB/Sur/2748 MPSB/Str/3621 | 2026-01-23 | IPC - 26 | Km 0+814 - RHS
603.b | For Vehicular Underpass - Construction of Raft | Nos. | Palashbari | 0.5 | MPSB/Str/3683 | 2026-01-29 | IPC - 26 | Km 0+814 - LHS
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
603.c | For Vehicular Underpass - Construction of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2408 MPSB/Str/3133 MPSB/Str/3134 | 2025-12-13 | IPC - 25 | Km 4+480 - LHS - A2
603.c | For Vehicular Underpass - Construction of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2447 MPSB/Str/3196 MPSB/Str/3197 | 2025-12-19 | IPC - 25 | Km 4+480 - RHS - A2
603.c | For Vehicular Underpass - Construction of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2557 MPSB/Str/3358 MPSB/Str/3359 | 2025-12-30 | IPC - 25 | Km 4+480 - LHS - A1
603.c | For Vehicular Underpass - Construction of Pile Cap | Nos. | Palashbari | 1 | MPSB/Sur/2558 MPSB/Str/3360 MPSB/Str/3361 | 2025-12-30 | IPC - 25 | Km 4+480 - RHS - A1
| Cumulative paid upto this Bill | Nos. |  | 4
| Paid upto previous Bill | Nos. |  | 4
| To be paid in this Bill | Nos. |  | 0
604 | Construction of sub-structure; abutment/ piers/ lower pylon
604.a | For Vehicular Underpass - Construction of Abutment / Pier | Nos. | Palashbari | 0.5 | MPSB/Sur/2527 MPSB/Str/3309 MPSB/Str/3310 | 2025-12-28 | IPC - 25 | Km 4+480 - LHS - A2
604.a | For Vehicular Underpass - Construction of Abutment / Pier | Nos. | Palashbari | 0.5 | MPSB/Sur/2559 MPSB/Str/3362 MPSB/Str/3363 | 2025-12-30 | IPC - 25 | Km 4+480 - RHS - A2
604.a | For Vehicular Underpass - Construction of Abutment / Pier | Nos. | Palashbari | 0.5 | MPSB/Sur/2569 MPSB/Str/3373 MPSB/Str/3374 | 2025-12-31 | IPC - 25 | Km 4+480 - LHS - A1
604.a | For Vehicular Underpass - Construction of Abutment / Pier | Nos. | Palashbari | 0.5 | MPSB/Sur/2570 MPSB/Str/3375 MPSB/Str/3376 | 2025-12-31 | IPC - 25 | Km 4+480 - RHS - A1
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
604.b | For Vehicular Underpass - Construction of Wall | Nos. | Palashbari | 1 | MPSB/Str/3583 | 2026-01-19 | IPC - 26 | Km 3+061 - RHS - A1 & A2
604.b | For Vehicular Underpass - Construction of Wall | Nos. | Palashbari | 1 | MPSB/Str/3659 | 2026-01-27 | IPC - 26 | Km 3+061 - LHS - A1 & A2
604.b | For Vehicular Underpass - Construction of Wall | Nos. | Palashbari | 1 | MPSB/Str/3686 | 2025-01-30 | IPC - 26 | Km 0+814 - BHS - A1 & A2
604.b | For Vehicular Underpass - Construction of Wall | Nos. | Palashbari | 0.375 | MPSB/Str/3921 | 2026-02-21 | IPC - 27 | Km 0+814 - LHS - A1 & A2 - 75% Completed
604.b | For Vehicular Underpass - Construction of Wall | Nos. | Palashbari | 0.375 | MPSB/Str/3982 | 2026-02-27 | IPC - 27 | Km 0+814 - RHS - A1 & A2 - 75% Completed
604.b | For Vehicular Underpass - Construction of Wall | Nos. | Palashbari | 0.25 | MPSB/Str/4099 | 2026-03-13 | IPC - 29 | Km 0+814 - BHS - A1 & A2 - 25% Completed
| Cumulative paid upto this Bill | Nos. |  | 4
| Paid upto previous Bill | Nos. |  | 4
| To be paid in this Bill | Nos. |  | 0
604.c | For Vehicular Underpass - Construction of Abutment / Pier Cap | Nos. | Palashbari | 0.5 | MPSB/Sur/3402 MPSB/Str/4558 MPSB/Str/4559 | 30-Apr-26 30-Apr-26 30-Apr-26 | IPC - 30 | Km 4+480 - LHS - A2 - Piercap
604.c | For Vehicular Underpass - Construction of Abutment / Pier Cap | Nos. | Palashbari | 0.5 | MPSB/Sur/3403 MPSB/Str/4560 MPSB/Str/4561 | 30-Apr-26 30-Apr-26 30-Apr-26 | IPC - 30 | Km 4+480 - RHS - A2 - Piercap
604.c | For Vehicular Underpass - Construction of Abutment / Pier Cap | Nos. | Palashbari | 0.5 | MPSB/Sur/3475 MPSB/Str/4668 MPSB/Str/4669 | 13-May-26 13-May-26 13-May-26 | IPC - 31 | Km 4+480 - LHS - A1 - Piercap
604.c | For Vehicular Underpass - Construction of Abutment / Pier Cap | Nos. | Palashbari | 0.5 | MPSB/Sur/3494 MPSB/Str/4702 MPSB/Str/4703 | 17-May-26 17-May-26 17-May-26 | IPC - 31 | Km 4+480 - RHS - A1 - Piercap
| Cumulative paid upto this Bill | Nos. |  | 2
| Paid upto previous Bill | Nos. |  | 2
| To be paid in this Bill | Nos. |  | 0
606 | Construction of superstructure
606.d | For Vehicular Underpass - Completion of Box Slab | Nos. | Palashbari | 1 | MPSB/Str/3885 | 2026-02-17 | IPC - 27 | Km 3+061 - RHS
606.d | For Vehicular Underpass - Completion of Box Slab | Nos. | Palashbari | 1 | MPSB/Str/4194 | 2026-03-24 | IPC - 29 | Km 3+061 - LHS
606.d | For Vehicular Underpass - Completion of Box Slab | Nos. | Palashbari | 1 | MPSB/Str/4556 | 2026-04-30 | IPC - 30 | Km 0+814 - LHS
606.d | For Vehicular Underpass - Completion of Box Slab | Nos. | Palashbari | 1 | MPSB/Str/4662 | 2026-05-13 | IPC - 31 | Km 0+814 - RHS
| Cumulative paid upto this Bill | Nos. |  | 4
| Paid upto previous Bill | Nos. |  | 4
| To be paid in this Bill | Nos. |  | 0

## Schedule 7
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
2-Jul-25 2-Jul-25
Schedule 7 - Approach Road Works | [11 empty] | IPC - 34
Measurement Sheet
Item No. | Item Description | UoM | Location | From | To | Side | Executed Quantity | RFI No. | Date | Bill No. | Layer | Remarks
701 | Earthwork up to top of the sub-grade
701.a | Embankment | Kms | Palashbari | 1800 | 2000 | BHS | 0.4 | MPSB/Road/05 MPSB/Road/06 MPSB/Road/43 | 9-Jan-25 14-Jan-25 24-Feb-25 | IPC - 11 | Top | 701.a.11.1 |  | C&G FDD & OGL Checking Emb - Layer
701.a | Embankment | Kms | Palashbari | 3250 | 4210 | BHS | 1.92 | MPSB/Road/02 MPSB/Road/03 MPSB/Road/44 | 28-Dec-24 3-Jan-25 24-Feb-25 | IPC - 11 | Top | 701.a.11.2
701.a | Embankment | Kms | Palashbari | 4830 | 5170 | BHS | 0.68 | MPSB/Road/09 MPSB/Road/10 MPSB/Road/46 | 28-Jan-25 31-Jan-25 25-Feb-25 | IPC - 11 | Top | 701.a.11.3
701.a | Embankment | Kms | Palashbari | 2220 | 2350 | BHS | 0.13 | MPSB/Road/56 MPSB/Road/72 MPSB/Road/157 | 07-Mar-25 08-Mar-25 29-Mar-25 | IPC - 13 | 8 | 701.a.13.1
701.a | Embankment | Kms | Palashbari | 2450 | 2600 | LHS | 0.12 | MPSB/Road/49 MPSB/Road/50 MPSB/Road/159 | 06-Mar-25 06-Mar-25 29-Mar-25 | IPC - 13 | 8 | 701.a.13.2
701.a | Embankment | Kms | Palashbari | 2600 | 2650 | BHS | 0.075 | MPSB/Road/53 MPSB/Road/54 MPSB/Road/119 | 06-Mar-25 06-Mar-25 13-Mar-25 | IPC - 13 | 6 | 701.a.13.3
701.a | Embankment | Kms | Palashbari | 2700 | 2900 | BHS | 0.25455 | MPSB/Road/51 MPSB/Road/52 MPSB/Road/156 | 06-Mar-25 06-Mar-25 29-Mar-25 | IPC - 13 | 7 | 701.a.13.4
701.a | Embankment | Kms | Palashbari | 3070 | 3250 | BHS | 0.11077 | MPSB/Road/55 MPSB/Road/68 MPSB/Road/158 | 07-Mar-25 08-Mar-25 29-Mar-25 | IPC - 13 | 8 | 701.a.13.5
701.a | Embankment | Kms | Sualkuchi | 9630 | 9740 | LHS | 0.031429 | MPSB/Road/31 MPSB/Road/37 MPSB/Road/139 | 08-Feb-25 14-Feb-25 24-Mar-25 | IPC - 13 | 4 | 701.a.13.6
701.a | Embankment | Kms | Sualkuchi | 9740 | 9780 | LHS | 0.017778 | MPSB/Road/31 MPSB/Road/126 MPSB/Road/139 | 08-Feb-25 15-Mar-25 24-Mar-25 | IPC - 13 | 4 | 701.a.13.8
701.a | Embankment | Kms | Sualkuchi | 9780 | 10000 | LHS | 0.097778 | MPSB/Road/31 MPSB/Road/37 MPSB/Road/139 | 08-Feb-25 14-Mar-25 24-Mar-25 | IPC - 13 | 4 | 701.a.13.9
701.a | Embankment | Kms | Sualkuchi | 9650 | 9750 | RHS | 0.03 | MPSB/Road/35 MPSB/Road/38 MPSB/Road/121 | 14-Feb-25 15-Feb-25 15-Mar-25 | IPC - 13 | 3 | 701.a.13.7
701.a | Embankment | Kms | Sualkuchi | 10000 | 10100 | BHS | 0.028571 | MPSB/Road/39 MPSB/Road/59 MPSB/Road/123 | 18-Feb-25 07-Mar-25 15-Mar-25 | IPC - 13 | 2 | 701.a.13.10
701.a | Embankment | Kms | Sualkuchi | 10338 | 10450 | BHS | 0.024889 | MPSB/Road/40 MPSB/Road/41 MPSB/Road/124 | 18-Feb-25 18-Feb-25 15-Mar-25 | IPC - 13 | 2 | 701.a.13.11
701.a | Embankment | Kms | Sualkuchi | 10450 | 10550 | BHS | 0.023529 | MPSB/Road/40 MPSB/Road/41 MPSB/Road/125 | 18-Feb-25 18-Feb-25 15-Mar-25 | IPC - 13 | 2 | 701.a.13.12
701.a | Embankment | Kms | Sualkuchi | 11800 | 12000 | RHS | 0.06 | MPSB/Road/58 MPSB/Road/86 MPSB/Road/148 | 07-Mar-25 10-Mar-25 29-Mar-25 | IPC - 13 | 3 | 701.a.13.13
701.a | Embankment | Kms | Sualkuchi | 11800 | 11900 | LHS | 0.025 | MPSB/Road/58 MPSB/Road/86 MPSB/Road/149 | 07-Mar-25 10-Mar-25 29-Mar-25 | IPC - 13 | 2 | 701.a.13.14 |  |  | Since inception
701.a | Embankment | Kms | Sualkuchi | 11950 | 12000 | LHS | 0.01875 | MPSB/Road/58 MPSB/Road/86 MPSB/Road/162 | 07-Mar-25 10-Mar-25 31-Mar-25 | IPC - 13 | 3 | 701.a.13.15 |  |  | 9600 | 10170 | BHS | 570 | 1140
701.a | Embankment | Kms | Sualkuchi | 12000 | 12040 | BHS | 0.022857 | MPSB/Road/134 MPSB/Road/135 MPSB/Road/163 | 24-Mar-25 24-Mar-25 31-Mar-25 | IPC - 13 | 2 | 701.a.13.16 |  |  | 10180 | 10600 | BHS | 312 | 624
701.a | Embankment | Kms | Palashbari | 4620 | 4830 | BHS | 0.015 | MPSB/Road/92 MPSB/Road/93 MPSB/Road/187 | 10-Mar-25 10-Mar-25 20-Apr-25 | IPC - 14 | 1 | 701.a.14.1 |  |  | 11360 | 11775 | BHS | 207.5 | 415
701.a | Embankment | Kms | Palashbari | 5170 | 5200 | BHS | 0.0021429 | MPSB/Road/94 MPSB/Road/104 MPSB/Road/188 | 11-Mar-25 12-Mar-25 20-Apr-25 | IPC - 14 | 1 | 701.a.14.2 | [6 empty] | 2179
701.a | Embankment | Kms | Sualkuchi | 9650 | 9750 | RHS | 0.02 | MPSB/Road/183 | 2025-04-11 | IPC - 14 | 5 | 701.a.14.3
701.a | Embankment | Kms | Sualkuchi | 9750 | 10000 | RHS | 0.13889 | MPSB/Road/183 | 2025-04-11 | IPC - 14 | 5 | 701.a.14.4 |  |  | 1800 | 2190 | BHS | 390 | 780
701.a | Embankment | Kms | Sualkuchi | 10338 | 10450 | BHS | 0.012444 | MPSB/Road/181 & 182 | 2025-04-10 | IPC - 14 | 3 | 701.a.14.5 |  |  | 0 | 300 | BHS | 300 | 600
701.a | Embankment | Kms | Sualkuchi | 10450 | 10550 | BHS | 0.011765 | MPSB/Road/181 & 182 | 2025-04-10 | IPC - 14 | 3 | 701.a.14.6 |  |  | 1100 | 1270 | BHS | 85 | 170
701.a | Embankment | Kms | Sualkuchi | 11800 | 12000 | RHS | 0.02 | MPSB/Road/179 | 2025-04-09 | IPC - 14 | 4 | 701.a.14.7 |  |  | 1330 | 1430 | BHS | 100 | 200
701.a | Embankment | Kms | Sualkuchi | 11800 | 11900 | LHS | 0.0125 | MPSB/Road/180 | 2025-04-09 | IPC - 14 | 3 | 701.a.14.8 |  |  | 2450 | 2600 | BHS | 150 | 300
701.a | Embankment | Kms | Palashbari | 0 | 290 | BHS | 0.48333 | MPSB/Road/0584 | 2026-02-28 | IPC - 27 | 5 | 701.a.27.1 |  |  | 2300 | 2400 | BHS | 100 | 200
701.a | Embankment | Kms | Palashbari | 480 | 680 | BHS | 0.21053 | MPSB/Road/0572 | 2026-02-26 | IPC - 27 | 10 | 701.a.27.2 |  |  | 2650 | 2800 | BHS | 150 | 300
701.a | Embankment | Kms | Palashbari | 2000 | 2170 | BHS | 0.29143 | MPSB/Road/0583 | 2026-02-28 | IPC - 27 | 12 | 701.a.27.3 |  |  | 3240 | 3760 | BHS | 520 | 1040
701.a | Embankment | Kms | Palashbari | 2220 | 2350 | BHS | 0.065 | MPSB/Road/0583 | 2026-02-28 | IPC - 27 | 12 | 701.a.27.4
701.a | Embankment | Kms | Palashbari | 2450 | 2600 | LHS | 0.015 | MPSB/Road/0549 | 2026-02-24 | IPC - 27 | 9 | 701.a.27.5 |  |  | 3800 | 4240 | BHS | 440 | 880
701.a | Embankment | Kms | Palashbari | 2700 | 2900 | BHS | 0.10909 | MPSB/Road/0580 | 2026-02-27 | IPC - 27 | 10 | 701.a.27.6 |  |  | 4680 | 5190 | BHS | 340 | 680 |  |  | 6/9 layers
701.a | Embankment | Kms | Palashbari | 3070 | 3250 | BHS | 0.027692 | MPSB/Road/0580 | 2026-02-27 | IPC - 27 | 10 | 701.a.27.7
701.a | Embankment | Kms | Palashbari | 4210 | 4350 | BHS | 0.1037 | MPSB/Road/0579 | 2026-02-27 | IPC - 27 | 10 | 701.a.27.8
701.a | Embankment | Kms | Palashbari | 4620 | 4830 | BHS | 0.135 | MPSB/Road/0579 | 2026-02-27 | IPC - 27 | 10 | 701.a.27.9
701.a | Embankment | Kms | Sualkuchi | 9630 | 10000 | LHS | 0.037 | MPSB/Road/0184 | 2025-04-15 | IPC - 27 | 5 | 701.a.27.10
701.a | Embankment | Kms | Sualkuchi | 9650 | 10060 | BHS | 0.41 | MPSB/Road/0499 | 2026-02-17 | IPC - 27 | 10 | 701.a.27.11
701.a | Embankment | Kms | Sualkuchi | 10000 | 10060 | BHS | 0.025714 | MPSB/Road/0483 | 2026-02-12 | IPC - 27 | 5 | 701.a.27.12
701.a | Embankment | Kms | Sualkuchi | 10110 | 10170 | BHS | 0.12 | MPSB/Road/0543 | 2026-02-24 | IPC - 27 | 17 | 701.a.27.13
701.a | Embankment | Kms | Sualkuchi | 10170 | 10230 | BHS | 0.024 | MPSB/Road/0564 | 2026-02-25 | IPC - 27 | 4 | 701.a.27.14
701.a | Embankment | Kms | Sualkuchi | 10338 | 10550 | LHS | 0.023556 | MPSB/Road/0346 | 2026-01-08 | IPC - 27 | 5 | 701.a.27.15
701.a | Embankment | Kms | Sualkuchi | 10338 | 10550 | RHS | 0.023556 | MPSB/Road/0347 | 2026-01-08 | IPC - 27 | 5 | 701.a.27.16
701.a | Embankment | Kms | Sualkuchi | 10338 | 10600 | BHS | 0.37844 | MPSB/Road/0525 | 2026-02-21 | IPC - 27 | 18 | 701.a.27.17
701.a | Embankment | Kms | Sualkuchi | 10550 | 10600 | BHS | 0.027778 | MPSB/Road/0483 | 2026-02-12 | IPC - 27 | 5 | 701.a.27.18
701.a | Embankment | Kms | Sualkuchi | 11356 | 11570 | BHS | 0.428 | MPSB/Road/0563 | 2026-02-25 | IPC - 27 | 15 | 701.a.27.19
701.a | Embankment | Kms | Sualkuchi | 11590 | 11770 | BHS | 0.36 | MPSB/Road/0507 | 2026-02-18 | IPC - 27 | 10 | 701.a.27.20
[5 empty] | Cumulative paid upto this Bill | Kms | 7.602
[5 empty] | Paid upto previous Bill | Kms | 7.602
[5 empty] | To be paid in this Bill | Kms | 0
706 | Construction of earth retaining structures, culvert & minor structures
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Sualkuchi | 11580 |  | LHS | 0.5 | MPSB/Str/919 MPSB/Str/1041 MPSB/Str/1309 | 27-Mar-25 3-Apr-25 28-Apr-25 | IPC - 14 |  | Km 11+580
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Sualkuchi | 11580 |  | RHS | 0.5 | MPSB/Str/1263 MPSB/Str/1468 MPSB/Str/1568 | 25-Apr-25 11-May-25 26-May-25 | IPC - 15 |  | Km 11+580
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Sualkuchi | 11+775 |  | LHS | 0.5 | MPSB/Str/1417 MPSB/Str/1636 MPSB/Str/1714 | 4-May-25 5-Jun-25 28-Jun-25 | IPC - 16 |  | Km 11+775
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Sualkuchi | 11+775 |  | RHS | 0.5 | MPSB/Str/1512 MPSB/Str/1648 MPSB/Str/1686 | 18-May-25 10-Jun-25 20-Jun-25 | IPC - 16 |  | Km 11+775 | Sl.No. | Description of Item | Unit | MCW | SR | Total Quantity
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 3+760 |  | LHS | 0.5 | MPSB/Str/1494 MPSB/Str/1666 MPSB/Str/1791 | 15-May-25 16-Jun-25 11-Jul-25 | IPC - 22 |  | Km 3+760 | 1 | Embankment | Cum | 753187.89 | 50361.03 | 803548.92 | 225000 | 20.63% | 3 | 64019803.2088
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 3+760 |  | RHS | 0.5 | MPSB/Str/1569 MPSB/Str/1693 MPSB/Str/1974 | 26-May-25 23-Jun-25 4-Aug-25 | IPC - 22 |  | Km 3+760 | 2 | Sub grade | Cum | 125913.15 | 12113.1 | 138026.25
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Sualkuchi | 10+100 |  | LHS | 0.5 | MPSB/Str/1790 MPSB/Str/1872 MPSB/Str/1942 | 11-Jul-25 23-Jul-25 31-Jul-25 | IPC - 26 |  | Km 10+100 |  | RE Wall Approaches
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Sualkuchi | 10+100 |  | RHS | 0.5 | MPSB/Str/1482 MPSB/Str/2004 MPSB/Str/2053 | 18-May-25 9-Aug-25 19-Aug-25 | IPC - 26 |  | Km 10+100 | 3 | Silver Sand Fill | Cum | 287256.12 |  | 287256.12 | 1090805.04 | 14.5032
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Sualkuchi | 12+040 |  | LHS | 0.5 | MPSB/Str/3485 MPSB/Str/3582 MPSB/Str/3684 | 11-Jan-26 19-Jan-26 30-Jan-26 | IPC - 26 |  | Km 12+040
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Sualkuchi | 12+040 |  | RHS | 0.5 | MPSB/Str/3813 MPSB/Str/3869 MPSB/Str/3948 | 9-Feb-26 16-Feb-26 25-Feb-26 | IPC - 27 |  | Km 12+040 |  |  |  | 1166357.16 | 62474.13 | 1228831.29
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 3+205 |  | LHS | 0.5 | MPSB/Str/3665 MPSB/Str/3780 MPSB/Str/3811 MPSB/Str/3898 | 28-Jan-26 6-Feb-26 9-Feb-26 19-Feb-26 | IPC - 27 |  | Km 3+205
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 4+154 |  | LHS | 0.5 | MPSB/Str/3616 MPSB/Str/3875 MPSB/Str/4022 | 22-Jan-26 17-Feb-26 28-Feb-26 | IPC - 27 |  | Km 4+154
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 1+751 |  | RHS | 0.5 | MPSB/Str/3755 MPSB/Str/3850 MPSB/Str/4005 | 3-Feb-26 13-Feb-26 28-Feb-26 | IPC - 27 |  | Km 1+751
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 1+751 |  | LHS | 0.5 | MPSB/Str/3755 MPSB/Str/3896 MPSB/Str/4161 | 3-Feb-26 19-Feb-26 19-Mar-26 | IPC - 29 |  | Km 1+751
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 0+298 |  | LHS | 0.5 | MPSB/Str/3866 MPSB/Str/4041 MPSB/Str/4271 | 16-Feb-26 5-Mar-26 31-Mar-26 | IPC - 29 |  | Km 0+298
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 0+298 |  | RHS | 0.5 | MPSB/Str/3837 MPSB/Str/3958 MPSB/Str/4214 | 12-Feb-26 26-Feb-26 26-Mar-26 | IPC - 29 |  | Km 0+298
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 4+914 |  | LHS | 0.5 | MPSB/Road/622 MPSB/Str/4199 MPSB/Str/4438 | 12-Mar-26 24-Mar-26 18-Apr-26 | IPC - 30 |  | Km 4+914
706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 4+154 |  | RHS | 0.5 | MPSB/Str/4852 MPSB/Str/4968 MPSB/Str/5143 | 31-May-26 19-Jun-26 14-Jul-26 | IPC - 34 |  | Km 4+154
[5 empty] | Cumulative paid upto this Bill | Nos. | 9
[5 empty] | Paid upto previous Bill | Nos. | 8.5
[5 empty] | To be paid in this Bill | Nos. | 0.5

## Emb-Backup
Embankment RFI Details
S.No. | Code | Activity | From | To | Side | Length (Mts | Top Layer | Layer Executed | Effective Layer | Effective Length (Mts) | RFI No. | Date | Bill No. | Code | From | To | Side | Effective Length
1 | 701.a.11.1 | Embankment | 1800 | 2000 | BHS | 400 | 10 | 1 | 0.1 | 40 | MPSB/Road/07 | 2025-01-17 | IPC -11 | 701.a.11.1 | 1800 | 2000 | BHS | 0.4
2 | 701.a.11.1 | Embankment | 1800 | 2000 | BHS | 400 | 10 | 2 | 0.1 | 40 | MPSB/Road/12 | 2025-02-05 | IPC -11 | 701.a.11.2 | 3250 | 4210 | BHS | 1.92
3 | 701.a.11.1 | Embankment | 1800 | 2000 | BHS | 400 | 10 | 3 | 0.1 | 40 | MPSB/Road/15 | 2025-02-06 | IPC -11 | 701.a.11.3 | 4830 | 5170 | BHS | 0.68
4 | 701.a.11.1 | Embankment | 1800 | 2000 | BHS | 400 | 10 | 4 | 0.1 | 40 | MPSB/Road/18 | 2025-02-06 | IPC -11 |  |  |  |  | 3
5 | 701.a.11.1 | Embankment | 1800 | 2000 | BHS | 400 | 10 | 5 | 0.1 | 40 | MPSB/Road/21 | 2025-02-06 | IPC -11
6 | 701.a.11.1 | Embankment | 1800 | 2000 | BHS | 400 | 10 | 6 | 0.1 | 40 | MPSB/Road/24 | 2025-02-07 | IPC -11
7 | 701.a.11.1 | Embankment | 1800 | 2000 | BHS | 400 | 10 | 7 | 0.1 | 40 | MPSB/Road/27 | 2025-02-07 | IPC -11
8 | 701.a.11.1 | Embankment | 1800 | 2000 | BHS | 400 | 10 | 8 | 0.1 | 40 | MPSB/Road/30 | 2025-02-07 | IPC -11
9 | 701.a.11.1 | Embankment | 1800 | 2000 | BHS | 400 | 10 | 9 | 0.1 | 40 | MPSB/Road/34 | 2025-02-10 | IPC -11
10 | 701.a.11.1 | Embankment | 1800 | 2000 | BHS | 400 | 10 | 10 | 0.1 | 40 | MPSB/Road/43 | 2025-02-24 | IPC -11
11 | 701.a.11.2 | Embankment | 3250 | 4210 | BHS | 1920 | 10 | 1 | 0.1 | 192 | MPSB/Road/04 | 2025-01-09 | IPC -11
12 | 701.a.11.2 | Embankment | 3250 | 4210 | BHS | 1920 | 10 | 2 | 0.1 | 192 | MPSB/Road/08 | 2025-01-18 | IPC -11
13 | 701.a.11.2 | Embankment | 3250 | 4210 | BHS | 1920 | 10 | 3 | 0.1 | 192 | MPSB/Road/14 | 2025-02-05 | IPC -11
14 | 701.a.11.2 | Embankment | 3250 | 4210 | BHS | 1920 | 10 | 4 | 0.1 | 192 | MPSB/Road/17 | 2025-02-06 | IPC -11
15 | 701.a.11.2 | Embankment | 3250 | 4210 | BHS | 1920 | 10 | 5 | 0.1 | 192 | MPSB/Road/20 | 2025-02-06 | IPC -11
16 | 701.a.11.2 | Embankment | 3250 | 4210 | BHS | 1920 | 10 | 6 | 0.1 | 192 | MPSB/Road/23 | 2025-02-07 | IPC -11
17 | 701.a.11.2 | Embankment | 3250 | 4210 | BHS | 1920 | 10 | 7 | 0.1 | 192 | MPSB/Road/26 | 2025-02-07 | IPC -11
18 | 701.a.11.2 | Embankment | 3250 | 4210 | BHS | 1920 | 10 | 8 | 0.1 | 192 | MPSB/Road/29 | 2025-02-07 | IPC -11
19 | 701.a.11.2 | Embankment | 3250 | 4210 | BHS | 1920 | 10 | 9 | 0.1 | 192 | MPSB/Road/33 | 2025-02-08 | IPC -11
20 | 701.a.11.2 | Embankment | 3250 | 4210 | BHS | 1920 | 10 | 10 | 0.1 | 192 | MPSB/Road/44 | 2025-02-24 | IPC -11
21 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 1 | 0.090909 | 61.8182 | MPSB/Road/11 | 2025-02-03 | IPC -11
22 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 2 | 0.090909 | 61.8182 | MPSB/Road/13 | 2025-02-05 | IPC -11
23 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 3 | 0.090909 | 61.8182 | MPSB/Road/16 | 2025-02-06 | IPC -11
24 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 4 | 0.090909 | 61.8182 | MPSB/Road/19 | 2025-02-06 | IPC -11
25 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 5 | 0.090909 | 61.8182 | MPSB/Road/22 | 2025-02-07 | IPC -11
26 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 6 | 0.090909 | 61.8182 | MPSB/Road/25 | 2025-02-07 | IPC -11
27 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 7 | 0.090909 | 61.8182 | MPSB/Road/28 | 2025-02-07 | IPC -11
28 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 8 | 0.090909 | 61.8182 | MPSB/Road/32 | 2025-02-08 | IPC -11
29 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 9 | 0.090909 | 61.8182 | MPSB/Road/42 | 2025-02-23 | IPC -11
30 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 10 | 0.090909 | 61.8182 | MPSB/Road/45 | 2025-02-25 | IPC -11
31 | 701.a.11.3 | Embankment | 4830 | 5170 | BHS | 680 | 11 | 11 | 0.090909 | 61.8182 | MPSB/Road/46 | 2025-02-25 | IPC -11
1 | 701.a.13.1 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 1 | 0.0625 | 16.25 | MPSB/Road/0073 | 2025-03-08 | IPC -13 | 701.a.13.1 | 2220 | 2350 | BHS | 0.13
2 | 701.a.13.1 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 2 | 0.0625 | 16.25 | MPSB/Road/0075 | 2025-03-09 | IPC -13 | 701.a.13.2 | 2450 | 2600 | LHS | 0.12
3 | 701.a.13.1 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 3 | 0.0625 | 16.25 | MPSB/Road/0080 | 2025-03-10 | IPC -13 | 701.a.13.3 | 2600 | 2650 | BHS | 0.075
4 | 701.a.13.1 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 4 | 0.0625 | 16.25 | MPSB/Road/0097 | 2025-03-11 | IPC -13 | 701.a.13.4 | 2700 | 2900 | BHS | 0.25455
5 | 701.a.13.1 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 5 | 0.0625 | 16.25 | MPSB/Road/0108 | 2025-03-12 | IPC -13 | 701.a.13.5 | 3070 | 3250 | BHS | 0.11077
6 | 701.a.13.1 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 6 | 0.0625 | 16.25 | MPSB/Road/0116 | 2025-03-13 | IPC -13 | 701.a.13.6 | 9630 | 9740 | LHS | 0.031429
7 | 701.a.13.1 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 7 | 0.0625 | 16.25 | MPSB/Road/0141 | 2025-03-25 | IPC -13 | 701.a.13.7 | 9650 | 10000 | RHS | 0.03
8 | 701.a.13.1 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 8 | 0.0625 | 16.25 | MPSB/Road/0157 | 2025-03-29 | IPC -13 | 701.a.13.8 | 9740 | 9780 | LHS | 0.017778
9 | 701.a.13.2 | Embankment | 2450 | 2600 | LHS | 150 | 10 | 1 | 0.1 | 15 | MPSB/Road/0070 | 2025-03-08 | IPC -13 | 701.a.13.9 | 9780 | 10000 | LHS | 0.097778
10 | 701.a.13.2 | Embankment | 2450 | 2600 | LHS | 150 | 10 | 2 | 0.1 | 15 | MPSB/Road/0077 | 2025-03-09 | IPC -13 | 701.a.13.10 | 10000 | 10100 | BHS | 0.028571
11 | 701.a.13.2 | Embankment | 2450 | 2600 | LHS | 150 | 10 | 3 | 0.1 | 15 | MPSB/Road/0082 | 2025-03-10 | IPC -13 | 701.a.13.11 | 10338 | 10450 | BHS | 0.024889
12 | 701.a.13.2 | Embankment | 2450 | 2600 | LHS | 150 | 10 | 4 | 0.1 | 15 | MPSB/Road/0099 | 2025-03-11 | IPC -13 | 701.a.13.12 | 10450 | 10550 | BHS | 0.023529
13 | 701.a.13.2 | Embankment | 2450 | 2600 | LHS | 150 | 10 | 5 | 0.1 | 15 | MPSB/Road/0110 | 2025-03-12 | IPC -13 | 701.a.13.13 | 11800 | 12000 | RHS | 0.06
14 | 701.a.13.2 | Embankment | 2450 | 2600 | LHS | 150 | 10 | 6 | 0.1 | 15 | MPSB/Road/0118 | 2025-03-13 | IPC -13 | 701.a.13.14 | 11800 | 11900 | LHS | 0.025
15 | 701.a.13.2 | Embankment | 2450 | 2600 | LHS | 150 | 10 | 7 | 0.1 | 15 | MPSB/Road/0143 | 2025-03-27 | IPC -13 | 701.a.13.15 | 11950 | 12000 | LHS | 0.01875
16 | 701.a.13.2 | Embankment | 2450 | 2600 | LHS | 150 | 10 | 8 | 0.1 | 15 | MPSB/Road/0159 | 2025-03-29 | IPC -13 | 701.a.13.16 | 12000 | 12040 | BHS | 0.022857
17 | 701.a.13.3 | Embankment | 2600 | 2650 | BHS | 100 | 8 | 1 | 0.125 | 12.5 | MPSB/Road/0071 | 2025-03-08 | IPC -13 |  |  |  |  | 1.0709
18 | 701.a.13.3 | Embankment | 2600 | 2650 | BHS | 100 | 8 | 2 | 0.125 | 12.5 | MPSB/Road/0078 | 2025-03-09 | IPC -13
19 | 701.a.13.3 | Embankment | 2600 | 2650 | BHS | 100 | 8 | 3 | 0.125 | 12.5 | MPSB/Road/0083 | 2025-03-10 | IPC -13
20 | 701.a.13.3 | Embankment | 2600 | 2650 | BHS | 100 | 8 | 4 | 0.125 | 12.5 | MPSB/Road/0100 | 2025-03-11 | IPC -13
21 | 701.a.13.3 | Embankment | 2600 | 2650 | BHS | 100 | 8 | 5 | 0.125 | 12.5 | MPSB/Road/0111 | 2025-03-12 | IPC -13
22 | 701.a.13.3 | Embankment | 2600 | 2650 | BHS | 100 | 8 | 6 | 0.125 | 12.5 | MPSB/Road/0119 | 2025-03-13 | IPC -13
23 | 701.a.13.4 | Embankment | 2700 | 2900 | BHS | 400 | 11 | 1 | 0.090909 | 36.3636 | MPSB/Road/0057 | 2025-03-07 | IPC -13
24 | 701.a.13.4 | Embankment | 2700 | 2900 | BHS | 400 | 11 | 2 | 0.090909 | 36.3636 | MPSB/Road/0067 | 2025-03-08 | IPC -13
25 | 701.a.13.4 | Embankment | 2700 | 2900 | BHS | 400 | 11 | 3 | 0.090909 | 36.3636 | MPSB/Road/0074 | 2025-03-09 | IPC -13
26 | 701.a.13.4 | Embankment | 2700 | 2900 | BHS | 400 | 11 | 4 | 0.090909 | 36.3636 | MPSB/Road/0079 | 2025-03-10 | IPC -13
27 | 701.a.13.4 | Embankment | 2700 | 2900 | BHS | 400 | 11 | 5 | 0.090909 | 36.3636 | MPSB/Road/0096 | 2025-03-11 | IPC -13
28 | 701.a.13.4 | Embankment | 2700 | 2900 | BHS | 400 | 11 | 6 | 0.090909 | 36.3636 | MPSB/Road/0107 | 2025-03-12 | IPC -13
29 | 701.a.13.4 | Embankment | 2700 | 2900 | BHS | 400 | 11 | 7 | 0.090909 | 36.3636 | MPSB/Road/0156 | 2025-03-29 | IPC -13
30 | 701.a.13.5 | Embankment | 3070 | 3250 | BHS | 360 | 26 | 1 | 0.038462 | 13.8462 | MPSB/Road/0069 | 2025-03-08 | IPC -13
31 | 701.a.13.5 | Embankment | 3070 | 3250 | BHS | 360 | 26 | 2 | 0.038462 | 13.8462 | MPSB/Road/0076 | 2025-03-09 | IPC -13
32 | 701.a.13.5 | Embankment | 3070 | 3250 | BHS | 360 | 26 | 3 | 0.038462 | 13.8462 | MPSB/Road/0081 | 2025-03-10 | IPC -13
33 | 701.a.13.5 | Embankment | 3070 | 3250 | BHS | 360 | 26 | 4 | 0.038462 | 13.8462 | MPSB/Road/0098 | 2025-03-11 | IPC -13
34 | 701.a.13.5 | Embankment | 3070 | 3250 | BHS | 360 | 26 | 5 | 0.038462 | 13.8462 | MPSB/Road/0109 | 2025-03-12 | IPC -13
35 | 701.a.13.5 | Embankment | 3070 | 3250 | BHS | 360 | 26 | 6 | 0.038462 | 13.8462 | MPSB/Road/0117 | 2025-03-13 | IPC -13
36 | 701.a.13.5 | Embankment | 3070 | 3250 | BHS | 360 | 26 | 7 | 0.038462 | 13.8462 | MPSB/Road/0144 | 2025-03-27 | IPC -13
37 | 701.a.13.5 | Embankment | 3070 | 3250 | BHS | 360 | 26 | 8 | 0.038462 | 13.8462 | MPSB/Road/0158 | 2025-03-29 | IPC -13
38 | 701.a.13.6 | Embankment | 9630 | 9740 | LHS | 110 | 14 | 1 | 0.071429 | 7.8571 | MPSB/Road/0060 | 2025-03-07 | IPC -13
39 | 701.a.13.6 | Embankment | 9630 | 9740 | LHS | 110 | 14 | 2 | 0.071429 | 7.8571 | MPSB/Road/0089 | 2025-03-10 | IPC -13
40 | 701.a.13.6 | Embankment | 9630 | 9740 | LHS | 110 | 14 | 3 | 0.071429 | 7.8571 | MPSB/Road/0120 | 2025-03-15 | IPC -13
41 | 701.a.13.6 | Embankment | 9630 | 9740 | LHS | 110 | 14 | 4 | 0.071429 | 7.8571 | MPSB/Road/0139 | 2025-03-24 | IPC -13
42 | 701.a.13.8 | Embankment | 9740 | 9780 | LHS | 40 | 9 | 1 | 0.11111 | 4.4444 | MPSB/Road/0127 | 15-03-2025 | IPC -13
43 | 701.a.13.8 | Embankment | 9740 | 9780 | LHS | 40 | 9 | 2 | 0.11111 | 4.4444 | MPSB/Road/0130 | 22-03-2025 | IPC -13
44 | 701.a.13.8 | Embankment | 9740 | 9780 | LHS | 40 | 9 | 3 | 0.11111 | 4.4444 | MPSB/Road/0131 | 22-03-2025 | IPC -13
45 | 701.a.13.8 | Embankment | 9740 | 9780 | LHS | 40 | 9 | 4 | 0.11111 | 4.4444 | MPSB/Road/0139 | 2025-03-24 | IPC -13
46 | 701.a.13.9 | Embankment | 9780 | 10000 | LHS | 220 | 9 | 1 | 0.11111 | 24.4444 | MPSB/Road/0061 | 2025-03-07 | IPC -13
47 | 701.a.13.9 | Embankment | 9780 | 10000 | LHS | 220 | 9 | 2 | 0.11111 | 24.4444 | MPSB/Road/0065 | 2025-03-07 | IPC -13
48 | 701.a.13.9 | Embankment | 9780 | 10000 | LHS | 220 | 9 | 3 | 0.11111 | 24.4444 | MPSB/Road/0133 | 2025-03-22 | IPC -13
49 | 701.a.13.9 | Embankment | 9780 | 10000 | LHS | 220 | 9 | 4 | 0.11111 | 24.4444 | MPSB/Road/0139 | 2025-03-24 | IPC -13
50 | 701.a.13.7 | Embankment | 9650 | 9750 | RHS | 100 | 10 | 1 | 0.1 | 10 | MPSB/Road/0062 | 2025-03-07 | IPC -13
51 | 701.a.13.7 | Embankment | 9650 | 9750 | RHS | 100 | 10 | 2 | 0.1 | 10 | MPSB/Road/0088 | 2025-03-10 | IPC -13
52 | 701.a.13.7 | Embankment | 9650 | 9750 | RHS | 100 | 10 | 3 | 0.1 | 10 | MPSB/Road/121 | 2025-03-15 | IPC -13
53 | 701.a.13.10 | Embankment | 10000 | 10100 | BHS | 200 | 14 | 1 | 0.071429 | 14.2857 | MPSB/Road/0087 | 2025-03-10 | IPC -13
54 | 701.a.13.10 | Embankment | 10000 | 10100 | BHS | 200 | 14 | 2 | 0.071429 | 14.2857 | MPSB/Road/0123 | 2025-03-15 | IPC -13
55 | 701.a.13.11 | Embankment | 10338 | 10450 | BHS | 224 | 18 | 1 | 0.055556 | 12.4444 | MPSB/Road/63 | 2025-03-07 | IPC -13
56 | 701.a.13.11 | Embankment | 10338 | 10450 | BHS | 224 | 18 | 2 | 0.055556 | 12.4444 | MPSB/Road/124 | 2025-03-15 | IPC -13
57 | 701.a.13.12 | Embankment | 10450 | 10550 | BHS | 200 | 17 | 1 | 0.058824 | 11.7647 | MPSB/Road/64 | 2025-03-07 | IPC -13
58 | 701.a.13.12 | Embankment | 10450 | 10550 | BHS | 200 | 17 | 2 | 0.058824 | 11.7647 | MPSB/Road/125 | 2025-03-15 | IPC -13
59 | 701.a.13.13 | Embankment | 11800 | 12000 | RHS | 200 | 10 | 1 | 0.1 | 20 | MPSB/Road/138 | 2025-03-24 | IPC -13
60 | 701.a.13.13 | Embankment | 11800 | 12000 | RHS | 200 | 10 | 2 | 0.1 | 20 | MPSB/Road/145 | 2025-03-27 | IPC -13
61 | 701.a.13.13 | Embankment | 11800 | 12000 | RHS | 200 | 10 | 3 | 0.1 | 20 | MPSB/Road/148 | 2025-03-29 | IPC -13
62 | 701.a.13.14 | Embankment | 11800 | 11900 | LHS | 100 | 8 | 1 | 0.125 | 12.5 | MPSB/Road/136 | 2025-03-24 | IPC -13
63 | 701.a.13.14 | Embankment | 11800 | 11900 | LHS | 100 | 8 | 2 | 0.125 | 12.5 | MPSB/Road/149 | 2025-03-29 | IPC -13
64 | 701.a.13.15 | Embankment | 11950 | 12000 | LHS | 50 | 8 | 1 | 0.125 | 6.25 | MPSB/Road/137 | 2025-03-24 | IPC -13
65 | 701.a.13.15 | Embankment | 11950 | 12000 | LHS | 50 | 8 | 2 | 0.125 | 6.25 | MPSB/Road/150 | 2025-03-29 | IPC -13
66 | 701.a.13.15 | Embankment | 11950 | 12000 | LHS | 50 | 8 | 3 | 0.125 | 6.25 | MPSB/Road/162 | 2025-03-31 | IPC -13
67 | 701.a.13.16 | Embankment | 12000 | 12040 | BHS | 80 | 7 | 1 | 0.14286 | 11.4286 | MPSB/Road/151 | 2025-03-29 | IPC -13
68 | 701.a.13.16 | Embankment | 12000 | 12040 | BHS | 80 | 7 | 2 | 0.14286 | 11.4286 | MPSB/Road/163 | 2025-03-31 | IPC -13
1 | 701.a.14.1 | Embankment | 4620 | 4830 | BHS | 420 | 28 | 1 | 0.035714 | 15 | MPSB/Road/187 | 2025-04-20 | IPC -14 | 701.a.14.1 | 4620 | 4830 | BHS | 0.015
2 | 701.a.14.2 | Embankment | 5170 | 5200 | BHS | 60 | 28 | 1 | 0.035714 | 2.1429 | MPSB/Road/188 | 2025-04-20 | IPC -14 | 701.a.14.2 | 5170 | 5200 | BHS | 0.0021429
3 | 701.a.14.3 | Embankment | 9650 | 9750 | RHS | 100 | 10 | 4 | 0.1 | 10 | MPSB/Road/174 | 2025-04-04 | IPC -14 | 701.a.14.3 | 9650 | 9750 | RHS | 0.02
4 | 701.a.14.3 | Embankment | 9650 | 9750 | RHS | 100 | 10 | 5 | 0.1 | 10 | MPSB/Road/183 | 2025-04-11 | IPC -14 | 701.a.14.4 | 9750 | 10000 | RHS | 0.13889
5 | 701.a.14.4 | Embankment | 9750 | 10000 | RHS | 250 | 9 | 1 | 0.11111 | 27.7778 | MPSB/Road/48 | 2025-03-03 | IPC -14 | 701.a.14.5 | 10338 | 10450 | BHS | 0.012444
6 | 701.a.14.4 | Embankment | 9750 | 10000 | RHS | 250 | 9 | 2 | 0.11111 | 27.7778 | MPSB/Road/88 | 2025-03-10 | IPC -14 | 701.a.14.6 | 10450 | 10550 | BHS | 0.011765
7 | 701.a.14.4 | Embankment | 9750 | 10000 | RHS | 250 | 9 | 3 | 0.11111 | 27.7778 | MPSB/Road/121 & 122 | 2025-03-15 | IPC -14 | 701.a.14.7 | 11800 | 11900 | LHS | 0.02
8 | 701.a.14.4 | Embankment | 9750 | 10000 | RHS | 250 | 9 | 4 | 0.11111 | 27.7778 | MPSB/Road/174 | 2025-04-04 | IPC -14 | 701.a.14.8 | 11800 | 11900 | LHS | 0.0125
9 | 701.a.14.4 | Embankment | 9750 | 10000 | RHS | 250 | 9 | 5 | 0.11111 | 27.7778 | MPSB/Road/183 | 2025-04-11 | IPC -14 |  |  |  |  | 0.23274
10 | 701.a.14.5 | Embankment | 10338 | 10450 | BHS | 224 | 18 | 3 | 0.055556 | 12.4444 | MPSB/Road/181 & 182 | 2025-04-10 | IPC -14
11 | 701.a.14.6 | Embankment | 10450 | 10550 | BHS | 200 | 17 | 3 | 0.058824 | 11.7647 | MPSB/Road/181 & 182 | 2025-04-10 | IPC -14
12 | 701.a.14.7 | Embankment | 11800 | 12000 | RHS | 200 | 10 | 4 | 0.1 | 20 | MPSB/Road/179 | 2025-04-09 | IPC -14
13 | 701.a.14.8 | Embankment | 11800 | 11900 | LHS | 100 | 8 | 3 | 0.125 | 12.5 | MPSB/Road/180 | 2025-04-09 | IPC -14
1 | 701.a.27.1 | Embankment | 0 | 290 | BHS | 580 | 6 | 1 | 0.16667 | 96.6667 | MPSB/Road/0553 | 2026-02-24 | IPC -27 | 701.a.27.1 | 0 | 290 | BHS | 0.48333 | MPSB/Road/0584
2 | 701.a.27.1 | Embankment | 0 | 290 | BHS | 580 | 6 | 2 | 0.16667 | 96.6667 | MPSB/Road/0559 | 2026-02-25 | IPC -27 | 701.a.27.2 | 480 | 680 | BHS | 0.21053 | MPSB/Road/0572
3 | 701.a.27.1 | Embankment | 0 | 290 | BHS | 580 | 6 | 3 | 0.16667 | 96.6667 | MPSB/Road/0571 | 2026-02-26 | IPC -27 | 701.a.27.3 | 2000 | 2170 | BHS | 0.29143 | MPSB/Road/0583
4 | 701.a.27.1 | Embankment | 0 | 290 | BHS | 580 | 6 | 4 | 0.16667 | 96.6667 | MPSB/Road/0582 | 2026-02-27 | IPC -27 | 701.a.27.4 | 2220 | 2350 | BHS | 0.065 | MPSB/Road/0583
5 | 701.a.27.1 | Embankment | 0 | 290 | BHS | 580 | 6 | 5 | 0.16667 | 96.6667 | MPSB/Road/0584 | 2026-02-28 | IPC -27 | 701.a.27.5 | 2450 | 2600 | LHS | 0.015 | MPSB/Road/0549
6 | 701.a.27.2 | Embankment | 480 | 680 | BHS | 400 | 19 | 1 | 0.052632 | 21.0526 | MPSB/Road/0486 | 2026-02-14 | IPC -27 | 701.a.27.6 | 2700 | 2900 | BHS | 0.10909 | MPSB/Road/0580
7 | 701.a.27.2 | Embankment | 480 | 680 | BHS | 400 | 19 | 2 | 0.052632 | 21.0526 | MPSB/Road/0488 | 2026-02-15 | IPC -27 | 701.a.27.7 | 3070 | 3250 | BHS | 0.027692 | MPSB/Road/0580
8 | 701.a.27.2 | Embankment | 480 | 680 | BHS | 400 | 19 | 3 | 0.052632 | 21.0526 | MPSB/Road/0489 | 2026-02-15 | IPC -27 | 701.a.27.8 | 4210 | 4350 | BHS | 0.1037 | MPSB/Road/0579
9 | 701.a.27.2 | Embankment | 480 | 680 | BHS | 400 | 19 | 4 | 0.052632 | 21.0526 | MPSB/Road/0494 | 2026-02-16 | IPC -27 | 701.a.27.9 | 4620 | 4830 | BHS | 0.135 | MPSB/Road/0579
10 | 701.a.27.2 | Embankment | 480 | 680 | BHS | 400 | 19 | 5 | 0.052632 | 21.0526 | MPSB/Road/0496 | 2026-02-16 | IPC -27 | 701.a.27.10 | 9630 | 10000 | LHS | 0.037 | MPSB/Road/0184
11 | 701.a.27.2 | Embankment | 480 | 680 | BHS | 400 | 19 | 6 | 0.052632 | 21.0526 | MPSB/Road/0501 | 2026-02-18 | IPC -27 | 701.a.27.11 | 9650 | 10060 | BHS | 0.41 | MPSB/Road/0499
12 | 701.a.27.2 | Embankment | 480 | 680 | BHS | 400 | 19 | 7 | 0.052632 | 21.0526 | MPSB/Road/0547 | 2026-02-24 | IPC -27 | 701.a.27.12 | 10000 | 10060 | BHS | 0.025714 | MPSB/Road/0483
13 | 701.a.27.2 | Embankment | 480 | 680 | BHS | 400 | 19 | 8 | 0.052632 | 21.0526 | MPSB/Road/0551 | 2026-02-24 | IPC -27 | 701.a.27.13 | 10110 | 10170 | BHS | 0.12 | MPSB/Road/0543
14 | 701.a.27.2 | Embankment | 480 | 680 | BHS | 400 | 19 | 9 | 0.052632 | 21.0526 | MPSB/Road/0556 | 2026-02-25 | IPC -27 | 701.a.27.14 | 10170 | 10230 | BHS | 0.024 | MPSB/Road/0564
15 | 701.a.27.2 | Embankment | 480 | 680 | BHS | 400 | 19 | 10 | 0.052632 | 21.0526 | MPSB/Road/0572 | 2026-02-26 | IPC -27 | 701.a.27.15 | 10338 | 10550 | LHS | 0.023556 | MPSB/Road/0346
16 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 1 | 0.071429 | 24.2857 | MPSB/Road/0486 | 2026-02-14 | IPC -27 | 701.a.27.16 | 10338 | 10550 | RHS | 0.023556 | MPSB/Road/0347
17 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 2 | 0.071429 | 24.2857 | MPSB/Road/0488 | 2026-02-15 | IPC -27 | 701.a.27.17 | 10338 | 10600 | BHS | 0.37844 | MPSB/Road/0525
18 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 3 | 0.071429 | 24.2857 | MPSB/Road/0489 | 2026-02-15 | IPC -27 | 701.a.27.18 | 10550 | 10600 | BHS | 0.027778 | MPSB/Road/0483
19 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 4 | 0.071429 | 24.2857 | MPSB/Road/0494 | 2026-02-16 | IPC -27 | 701.a.27.19 | 11356 | 11570 | BHS | 0.428 | MPSB/Road/0563
20 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 5 | 0.071429 | 24.2857 | MPSB/Road/0496 | 2026-02-16 | IPC -27 | 701.a.27.20 | 11590 | 11770 | BHS | 0.36 | MPSB/Road/0507
21 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 6 | 0.071429 | 24.2857 | MPSB/Road/0501 | 2026-02-18 | IPC -27
22 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 7 | 0.071429 | 24.2857 | MPSB/Road/0547 | 2026-02-24 | IPC -27
23 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 8 | 0.071429 | 24.2857 | MPSB/Road/0551 | 2026-02-24 | IPC -27 |  |  |  |  | 3.2988
24 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 9 | 0.071429 | 24.2857 | MPSB/Road/0556 | 2026-02-25 | IPC -27
25 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 10 | 0.071429 | 24.2857 | MPSB/Road/0572 | 2026-02-26 | IPC -27
26 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 11 | 0.071429 | 24.2857 | MPSB/Road/0581 | 2026-02-27 | IPC -27
27 | 701.a.27.3 | Embankment | 2000 | 2170 | BHS | 340 | 14 | 12 | 0.071429 | 24.2857 | MPSB/Road/0583 | 2026-02-28 | IPC -27
28 | 701.a.27.4 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 9 | 0.0625 | 16.25 | MPSB/Road/0552 | 2026-02-24 | IPC -27
29 | 701.a.27.4 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 10 | 0.0625 | 16.25 | MPSB/Road/0557 | 2026-02-25 | IPC -27
30 | 701.a.27.4 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 11 | 0.0625 | 16.25 | MPSB/Road/0581 | 2026-02-27 | IPC -27
31 | 701.a.27.4 | Embankment | 2220 | 2350 | BHS | 260 | 16 | 12 | 0.0625 | 16.25 | MPSB/Road/0583 | 2026-02-28 | IPC -27
32 | 701.a.27.5 | Embankment | 2450 | 2600 | LHS | 150 | 10 | 9 | 0.1 | 15 | MPSB/Road/0549 | 2026-02-24 | IPC -27
33 | 701.a.27.6 | Embankment | 2700 | 2900 | BHS | 400 | 11 | 8 | 0.090909 | 36.3636 | MPSB/Road/0548 | 2026-02-24 | IPC -27
34 | 701.a.27.6 | Embankment | 2700 | 2900 | BHS | 400 | 11 | 9 | 0.090909 | 36.3636 | MPSB/Road/0570 | 2026-02-26 | IPC -27
35 | 701.a.27.6 | Embankment | 2700 | 2900 | BHS | 400 | 11 | 10 | 0.090909 | 36.3636 | MPSB/Road/0580 | 2026-02-27 | IPC -27
36 | 701.a.27.7 | Embankment | 3070 | 3250 | BHS | 360 | 26 | 9 | 0.038462 | 13.8462 | MPSB/Road/0570 | 2026-02-26 | IPC -27
37 | 701.a.27.7 | Embankment | 3070 | 3250 | BHS | 360 | 26 | 10 | 0.038462 | 13.8462 | MPSB/Road/0580 | 2026-02-27 | IPC -27
38 | 701.a.27.8 | Embankment | 4210 | 4350 | BHS | 280 | 27 | 1 | 0.037037 | 10.3704 | MPSB/Road/0471 | 2026-02-08 | IPC -27
39 | 701.a.27.8 | Embankment | 4210 | 4350 | BHS | 280 | 27 | 2 | 0.037037 | 10.3704 | MPSB/Road/0482 | 2026-02-12 | IPC -27
40 | 701.a.27.8 | Embankment | 4210 | 4350 | BHS | 280 | 27 | 3 | 0.037037 | 10.3704 | MPSB/Road/0485 | 2026-02-14 | IPC -27
41 | 701.a.27.8 | Embankment | 4210 | 4350 | BHS | 280 | 27 | 4 | 0.037037 | 10.3704 | MPSB/Road/0490 | 2026-02-15 | IPC -27
42 | 701.a.27.8 | Embankment | 4210 | 4350 | BHS | 280 | 27 | 5 | 0.037037 | 10.3704 | MPSB/Road/0493 | 2026-02-16 | IPC -27
43 | 701.a.27.8 | Embankment | 4210 | 4350 | BHS | 280 | 27 | 6 | 0.037037 | 10.3704 | MPSB/Road/0502 | 2026-02-18 | IPC -27
44 | 701.a.27.8 | Embankment | 4210 | 4350 | BHS | 280 | 27 | 7 | 0.037037 | 10.3704 | MPSB/Road/0550 | 2026-02-24 | IPC -27
45 | 701.a.27.8 | Embankment | 4210 | 4350 | BHS | 280 | 27 | 8 | 0.037037 | 10.3704 | MPSB/Road/0558 | 2026-02-25 | IPC -27
46 | 701.a.27.8 | Embankment | 4210 | 4350 | BHS | 280 | 27 | 9 | 0.037037 | 10.3704 | MPSB/Road/0573 | 2026-02-26 | IPC -27
47 | 701.a.27.8 | Embankment | 4210 | 4350 | BHS | 280 | 27 | 10 | 0.037037 | 10.3704 | MPSB/Road/0579 | 2026-02-27 | IPC -27
48 | 701.a.27.9 | Embankment | 4620 | 4830 | BHS | 420 | 28 | 2 | 0.035714 | 15 | MPSB/Road/0482 | 2026-02-12 | IPC -27
49 | 701.a.27.9 | Embankment | 4620 | 4830 | BHS | 420 | 28 | 3 | 0.035714 | 15 | MPSB/Road/0485 | 2026-02-14 | IPC -27
50 | 701.a.27.9 | Embankment | 4620 | 4830 | BHS | 420 | 28 | 4 | 0.035714 | 15 | MPSB/Road/0490 | 2026-02-15 | IPC -27
51 | 701.a.27.9 | Embankment | 4620 | 4830 | BHS | 420 | 28 | 5 | 0.035714 | 15 | MPSB/Road/0493 | 2026-02-16 | IPC -27
52 | 701.a.27.9 | Embankment | 4620 | 4830 | BHS | 420 | 28 | 6 | 0.035714 | 15 | MPSB/Road/0502 | 2026-02-18 | IPC -27
53 | 701.a.27.9 | Embankment | 4620 | 4830 | BHS | 420 | 28 | 7 | 0.035714 | 15 | MPSB/Road/0550 | 2026-02-24 | IPC -27
54 | 701.a.27.9 | Embankment | 4620 | 4830 | BHS | 420 | 28 | 8 | 0.035714 | 15 | MPSB/Road/0558 | 2026-02-25 | IPC -27
55 | 701.a.27.9 | Embankment | 4620 | 4830 | BHS | 420 | 28 | 9 | 0.035714 | 15 | MPSB/Road/0573 | 2026-02-26 | IPC -27
56 | 701.a.27.9 | Embankment | 4620 | 4830 | BHS | 420 | 28 | 10 | 0.035714 | 15 | MPSB/Road/0579 | 2026-02-27 | IPC -27
57 | 701.a.27.10 | Embankment | 9630 | 10000 | LHS | 370 | 10 | 5 | 0.1 | 37 | MPSB/Road/0184 | 2025-04-15 | IPC -27
58 | 701.a.27.11 | Embankment | 9650 | 10060 | BHS | 820 | 10 | 6 | 0.1 | 82 | MPSB/Road/0484 | 2026-02-12 | IPC -27
59 | 701.a.27.11 | Embankment | 9650 | 10060 | BHS | 820 | 10 | 7 | 0.1 | 82 | MPSB/Road/0491 | 2026-02-15 | IPC -27
60 | 701.a.27.11 | Embankment | 9650 | 10060 | BHS | 820 | 10 | 8 | 0.1 | 82 | MPSB/Road/0492 | 2026-02-15 | IPC -27
61 | 701.a.27.11 | Embankment | 9650 | 10060 | BHS | 820 | 10 | 9 | 0.1 | 82 | MPSB/Road/0498 | 2026-02-17 | IPC -27
62 | 701.a.27.11 | Embankment | 9650 | 10060 | BHS | 820 | 10 | 10 | 0.1 | 82 | MPSB/Road/0499 | 2026-02-17 | IPC -27
63 | 701.a.27.12 | Embankment | 10000 | 10060 | BHS | 120 | 14 | 3 | 0.071429 | 8.5714 | MPSB/Road/0175 | 2025-04-07 | IPC -27
64 | 701.a.27.12 | Embankment | 10000 | 10060 | BHS | 120 | 14 | 4 | 0.071429 | 8.5714 | MPSB/Road/0477 | 2026-02-11 | IPC -27
65 | 701.a.27.12 | Embankment | 10000 | 10060 | BHS | 120 | 14 | 5 | 0.071429 | 8.5714 | MPSB/Road/0483 | 2026-02-12 | IPC -27
66 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 1 | 0.058824 | 7.0588 | MPSB/Road/0473 | 2026-02-08 | IPC -27
67 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 2 | 0.058824 | 7.0588 | MPSB/Road/0474 | 2026-02-08 | IPC -27
68 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 3 | 0.058824 | 7.0588 | MPSB/Road/0507 | 2026-02-18 | IPC -27
69 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 4 | 0.058824 | 7.0588 | MPSB/Road/0508 | 2026-02-18 | IPC -27
70 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 5 | 0.058824 | 7.0588 | MPSB/Road/0509 | 2026-02-18 | IPC -27
71 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 6 | 0.058824 | 7.0588 | MPSB/Road/0515 | 2026-02-19 | IPC -27
72 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 7 | 0.058824 | 7.0588 | MPSB/Road/0516 | 2026-02-19 | IPC -27
73 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 8 | 0.058824 | 7.0588 | MPSB/Road/0519 | 2026-02-20 | IPC -27
74 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 9 | 0.058824 | 7.0588 | MPSB/Road/0522 | 2026-02-21 | IPC -27
75 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 10 | 0.058824 | 7.0588 | MPSB/Road/0523 | 2026-02-21 | IPC -27
76 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 11 | 0.058824 | 7.0588 | MPSB/Road/0526 | 2026-02-21 | IPC -27
77 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 12 | 0.058824 | 7.0588 | MPSB/Road/0533 | 2026-02-23 | IPC -27
78 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 13 | 0.058824 | 7.0588 | MPSB/Road/0534 | 2026-02-23 | IPC -27
79 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 14 | 0.058824 | 7.0588 | MPSB/Road/0536 | 2026-02-23 | IPC -27
80 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 15 | 0.058824 | 7.0588 | MPSB/Road/0537 | 2026-02-23 | IPC -27
81 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 16 | 0.058824 | 7.0588 | MPSB/Road/0542 | 2026-02-24 | IPC -27
82 | 701.a.27.13 | Embankment | 10110 | 10170 | BHS | 120 | 17 | 17 | 0.058824 | 7.0588 | MPSB/Road/0543 | 2026-02-24 | IPC -27
83 | 701.a.27.14 | Embankment | 10170 | 10230 | BHS | 120 | 20 | 1 | 0.05 | 6 | MPSB/Road/0522 | 2026-02-21 | IPC -27
84 | 701.a.27.14 | Embankment | 10170 | 10230 | BHS | 120 | 20 | 2 | 0.05 | 6 | MPSB/Road/0542 | 2026-02-24 | IPC -27
85 | 701.a.27.14 | Embankment | 10170 | 10230 | BHS | 120 | 20 | 3 | 0.05 | 6 | MPSB/Road/0563 | 2026-02-25 | IPC -27
86 | 701.a.27.14 | Embankment | 10170 | 10230 | BHS | 120 | 20 | 4 | 0.05 | 6 | MPSB/Road/0564 | 2026-02-25 | IPC -27
87 | 701.a.27.15 | Embankment | 10338 | 10550 | LHS | 212 | 18 | 4 | 0.055556 | 11.7778 | MPSB/Road/0201 | 2025-06-12 | IPC -27
88 | 701.a.27.16 | Embankment | 10338 | 10550 | RHS | 212 | 18 | 4 | 0.055556 | 11.7778 | MPSB/Road/0202 | 2025-06-12 | IPC -27
89 | 701.a.27.15 | Embankment | 10338 | 10550 | LHS | 212 | 18 | 5 | 0.055556 | 11.7778 | MPSB/Road/0346 | 2026-01-08 | IPC -27
90 | 701.a.27.16 | Embankment | 10338 | 10550 | RHS | 212 | 18 | 5 | 0.055556 | 11.7778 | MPSB/Road/0347 | 2026-01-08 | IPC -27
91 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 6 | 0.055556 | 29.1111 | MPSB/Road/0484 | 2026-02-12 | IPC -27
92 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 7 | 0.055556 | 29.1111 | MPSB/Road/0491 | 2026-02-15 | IPC -27
93 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 8 | 0.055556 | 29.1111 | MPSB/Road/0492 | 2026-02-15 | IPC -27
94 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 9 | 0.055556 | 29.1111 | MPSB/Road/0498 | 2026-02-17 | IPC -27
95 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 10 | 0.055556 | 29.1111 | MPSB/Road/0499 | 2026-02-17 | IPC -27
96 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 11 | 0.055556 | 29.1111 | MPSB/Road/0506 | 2026-02-18 | IPC -27
97 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 12 | 0.055556 | 29.1111 | MPSB/Road/0507 | 2026-02-18 | IPC -27
98 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 13 | 0.055556 | 29.1111 | MPSB/Road/0508 | 2026-02-18 | IPC -27
99 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 14 | 0.055556 | 29.1111 | MPSB/Road/0509 | 2026-02-18 | IPC -27
100 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 15 | 0.055556 | 29.1111 | MPSB/Road/0515 | 2026-02-19 | IPC -27
101 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 16 | 0.055556 | 29.1111 | MPSB/Road/0516 | 2026-02-19 | IPC -27
102 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 17 | 0.055556 | 29.1111 | MPSB/Road/0523 | 2026-02-21 | IPC -27
103 | 701.a.27.17 | Embankment | 10338 | 10600 | BHS | 524 | 18 | 18 | 0.055556 | 29.1111 | MPSB/Road/0525 | 2026-02-21 | IPC -27
106 | 701.a.27.18 | Embankment | 10550 | 10600 | BHS | 100 | 18 | 1 | 0.055556 | 5.5556 | MPSB/Road/0473 | 2026-02-08 | IPC -27
107 | 701.a.27.18 | Embankment | 10550 | 10600 | BHS | 100 | 18 | 2 | 0.055556 | 5.5556 | MPSB/Road/0474 | 2026-02-08 | IPC -27
108 | 701.a.27.18 | Embankment | 10550 | 10600 | BHS | 100 | 18 | 3 | 0.055556 | 5.5556 | MPSB/Road/0476 | 2026-02-11 | IPC -27
109 | 701.a.27.18 | Embankment | 10550 | 10600 | BHS | 100 | 18 | 4 | 0.055556 | 5.5556 | MPSB/Road/0477 | 2026-02-11 | IPC -27
110 | 701.a.27.18 | Embankment | 10550 | 10600 | BHS | 100 | 18 | 5 | 0.055556 | 5.5556 | MPSB/Road/0483 | 2026-02-12 | IPC -27
111 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 1 | 0.066667 | 28.5333 | MPSB/Road/0473 | 2026-02-08 | IPC -27
112 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 2 | 0.066667 | 28.5333 | MPSB/Road/0474 | 2026-02-08 | IPC -27
113 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 3 | 0.066667 | 28.5333 | MPSB/Road/0476 | 2026-02-11 | IPC -27
114 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 4 | 0.066667 | 28.5333 | MPSB/Road/0506 | 2026-02-18 | IPC -27
115 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 5 | 0.066667 | 28.5333 | MPSB/Road/0508 | 2026-02-18 | IPC -27
116 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 6 | 0.066667 | 28.5333 | MPSB/Road/0509 | 2026-02-18 | IPC -27
117 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 7 | 0.066667 | 28.5333 | MPSB/Road/0515 | 2026-02-19 | IPC -27
118 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 8 | 0.066667 | 28.5333 | MPSB/Road/0516 | 2026-02-19 | IPC -27
119 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 9 | 0.066667 | 28.5333 | MPSB/Road/0519 | 2026-02-20 | IPC -27
120 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 10 | 0.066667 | 28.5333 | MPSB/Road/0522 | 2026-02-21 | IPC -27
121 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 11 | 0.066667 | 28.5333 | MPSB/Road/0523 | 2026-02-21 | IPC -27
122 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 12 | 0.066667 | 28.5333 | MPSB/Road/0525 | 2026-02-21 | IPC -27
123 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 13 | 0.066667 | 28.5333 | MPSB/Road/0526 | 2026-02-21 | IPC -27
124 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 14 | 0.066667 | 28.5333 | MPSB/Road/0536 | 2026-02-23 | IPC -27
125 | 701.a.27.19 | Embankment | 11356 | 11570 | BHS | 428 | 15 | 15 | 0.066667 | 28.5333 | MPSB/Road/0563 | 2026-02-25 | IPC -27
126 | 701.a.27.20 | Embankment | 11590 | 11770 | BHS | 360 | 10 | 1 | 0.1 | 36 | MPSB/Road/0476 | 2026-02-11 | IPC -27
127 | 701.a.27.20 | Embankment | 11590 | 11770 | BHS | 360 | 10 | 2 | 0.1 | 36 | MPSB/Road/0477 | 2026-02-11 | IPC -27
128 | 701.a.27.20 | Embankment | 11590 | 11770 | BHS | 360 | 10 | 3 | 0.1 | 36 | MPSB/Road/0483 | 2026-02-12 | IPC -27
129 | 701.a.27.20 | Embankment | 11590 | 11770 | BHS | 360 | 10 | 4 | 0.1 | 36 | MPSB/Road/0484 | 2026-02-12 | IPC -27
130 | 701.a.27.20 | Embankment | 11590 | 11770 | BHS | 360 | 10 | 5 | 0.1 | 36 | MPSB/Road/0491 | 2026-02-15 | IPC -27
131 | 701.a.27.20 | Embankment | 11590 | 11770 | BHS | 360 | 10 | 6 | 0.1 | 36 | MPSB/Road/0492 | 2026-02-15 | IPC -27
132 | 701.a.27.20 | Embankment | 11590 | 11770 | BHS | 360 | 10 | 7 | 0.1 | 36 | MPSB/Road/0498 | 2026-02-17 | IPC -27
133 | 701.a.27.20 | Embankment | 11590 | 11770 | BHS | 360 | 10 | 8 | 0.1 | 36 | MPSB/Road/0499 | 2026-02-17 | IPC -27
134 | 701.a.27.20 | Embankment | 11590 | 11770 | BHS | 360 | 10 | 9 | 0.1 | 36 | MPSB/Road/0506 | 2026-02-18 | IPC -27
135 | 701.a.27.20 | Embankment | 11590 | 11770 | BHS | 360 | 10 | 10 | 0.1 | 36 | MPSB/Road/0507 | 2026-02-18 | IPC -27
Cumulative paid upto this Bill | [9 empty] | 7.602 | Kms
Paid upto previous Bill | [9 empty] | 7.602 | Kms
To be paid in this Bill | [9 empty] | 0 | Kms
Note on H106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be changed from 7 to 10
Note on H107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be changed from 7 to 10

## Schedule 8
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
2-Jul-25 2-Jul-25
Schedule 8 - Provisional Sum | [7 empty] | IPC - 34
Measurement Sheet
Item No. | Item Description | UoM | Location | Executed Quantity | RFI No. / Letter No. / Period | Date | Bill No. | Remarks
802 | Dispute Board (DB) cost and expenses
802.a | Dispute Board | LS |  | 0.08263 | - | - | IPC - 22 | As per attachment
802.a | Dispute Board | LS |  | 0.091816 | - | - | IPC - 25 | As per attachment
802.a | Dispute Board | LS |  | 0.074405 | - | - | IPC - 29 | As per attachment
802.a | Dispute Board | LS |  | 0.074419 | - | - | IPC - 33 | As per attachment
| Cumulative paid upto this Bill | Nos. |  | 0.32327
| Paid upto previous Bill | Nos. |  | 0.32327
| To be paid in this Bill | Nos. |  | 0

## DAAB
Dispute Board Expenses
Q | S.No. | Description | UOM | Shri. Dinesh Kumar - Chairperson | [5 empty] | Shri. S K Nirmal - PWD Member | [5 empty] | Brigadier Vinod Nakra - L&T side | [5 empty] | Total
|  |  |  | From | To | Quantity | Rate | Amount | Remarks | From | To | Quantity | Rate | Amount | Remarks | From | To | Quantity | Rate | Amount | Remarks
Jun'25 - Sep'25 | 1 | Retainer-ship Fee, Secreterial Assitance and Incident Charges (Telephone, Fax, Postage, etc.) | Per Month | 2025-06-23 | 2025-09-30 | 3.267 | 50000 | 163350 | 8 Days in June + 3 Months | 2025-06-23 | 2025-09-30 | 3.267 | 50000 | 163350 | 8 Days in June + 3 Months | 2025-06-23 | 2025-09-30 | 3.267 | 50000 | 163350 | 8 Days in June + 3 Months | 490050
| 2(i) | For Project Site Visit or meeting at site office | Per Day | 2025-08-25 | 2025-08-26 | 2 | 25000 | 50000 | 2 Days | 2025-08-25 | 2025-08-26 | 2 | 25000 | 50000 | 2 Days |  |  |  | 25000 | 0 | - | 100000
| 2(ii) | Fee for meetings / hearings not at site | Per Day | 2025-07-22 |  | 1 | 10000 | 10000 | 1 Day | 2025-07-22 |  | 1 | 10000 | 10000 | 1 Day | 2025-07-22 |  | 1 | 10000 | 10000 | 1 Day | 30000
| 3 | Travelling Expenses | [19 empty] | 0
|  | Day 1 | @ Actuals | 2025-08-25 |  | 1 | 6966 | 6966 | Delhi - Guwahati | 2025-08-25 |  | 1 | 6966 | 6966 | Delhi - Guwahati | - |  | 0 | 0 | 0 |  | 13932
|  | Day 2 | @ Actuals | 2025-08-26 |  | 1 | 9135 | 9135 | Guwahati - Delhi | 2025-08-26 |  | 1 | 9135 | 9135 | Guwahati - Delhi | - |  | 0 | 0 | 0 |  | 18270
| 4 | Lodging & Boarding | Per Day | 2025-08-25 | 2025-08-26 | 2 | 10000 | 20000 | - | 2025-08-25 | 2025-08-26 | 2 | 10000 | 20000 | - | - | - | 0 | 10000 | 0 | - | 40000
| 5 | Extra charges for days other than hearing / meeting days (travel days maximum of 2 days on each occasion) | Per Day | - | - | 0 | 5000 | 0 | - | - | - | 0 | 5000 | 0 | - | - | - | 0 | 5000 | 0 | - | 0
| 6 | Local Conveyance | Per Day | 2025-08-25 | 2025-08-26 | 2 | 2000 | 4000 | - | 2025-08-25 | 2025-08-26 | 2 | 2000 | 4000 | - | - | - | 0 | 2000 | 0 | - | 8000 | 826297
Oct'25 - Dec'25 | 1 | Retainer-ship Fee, Secreterial Assitance and Incident Charges (Telephone, Fax, Postage, etc.) | Per Month | 2025-10-01 | 2025-12-31 | 3 | 50000 | 150000 | 3 Months | 2025-10-01 | 2025-12-31 | 3 | 50000 | 150000 | 3 Months | 2025-10-01 | 2025-12-31 | 3 | 50000 | 150000 | 3 Months | 450000
| 2(i) | For Project Site Visit or meeting at site office | Per Day | 2025-11-14 | 2025-11-15 | 2 | 25000 | 50000 | 2 Days | 2025-11-14 | 2025-11-15 | 2 | 25000 | 50000 | 2 Days | 2025-11-14 | 2025-11-15 | 2 | 25000 | 50000 | 2 Days | 150000
| 2(ii) | Fee for meetings / hearings not at site | Per Day | 6-Oct-25 & 10-Oct-25 |  | 2 | 10000 | 20000 | 2 Days | 6-Oct-25 & 10-Oct-25 |  | 2 | 10000 | 20000 | 2 Days | 6-Oct-25 & 10-Oct-25 |  | 2 | 10000 | 20000 | 2 Days | 60000
| 3 | Travelling Expenses | [19 empty] | 0
|  | Day 1 | @ Actuals | 2025-11-14 |  | 1 | 8626 | 8626 | Delhi - Guwahati | 2025-11-14 |  | 1 | 7292 | 7292 | Delhi - Guwahati | 2025-11-14 |  | 1 | 7292 | 7292 | Delhi - Guwahati | 23210
|  | Day 2 | @ Actuals | 2025-11-15 |  | 1 | 7631 | 7631 | Guwahati - Delhi | 2025-11-15 |  | 1 | 7631 | 7631 | Guwahati - Delhi | 2025-11-15 |  | 1 | 7631 | 7631 | Guwahati - Delhi | 22893
| 4 | Lodging & Boarding | Per Day | 2025-11-14 | 2025-11-15 | 2 | 10000 | 20000 | - | 2025-11-14 | 2025-11-15 | 2 | 10000 | 20000 | - | 2025-11-14 | 2025-11-15 | 2 | 10000 | 20000 | - | 60000
| 5 | Extra charges for days other than hearing / meeting days (travel days maximum of 2 days on each occasion) | Per Day | - | - | 0 | 5000 | 0 | - | - | - | 0 | 5000 | 0 | - | - | - | 0 | 5000 | 0 | - | 0
| 6 | Local Conveyance | Per Day | 2025-11-14 | 2025-11-15 | 2 | 2000 | 4000 | - | 2025-11-14 | 2025-11-15 | 2 | 2000 | 4000 | - | 2025-11-14 | 2025-11-15 | 2 | 2000 | 4000 | - | 12000 | 918162
Jan'26 - Mar-26 | 1 | Retainer-ship Fee, Secreterial Assitance and Incident Charges (Telephone, Fax, Postage, etc.) | Per Month | 2026-01-01 | 2026-03-31 | 3 | 50000 | 150000 | 3 Months | 2026-01-01 | 2026-03-31 | 3 | 50000 | 150000 | 3 Months | 2026-01-01 | 2026-03-31 | 3 | 50000 | 150000 | 3 Months | 450000
| 2(i) | For Project Site Visit or meeting at site office | Per Day | 2026-02-20 | 2026-02-21 | 2 | 25000 | 50000 | 2 Days | 2026-02-21 | 2026-02-22 | 2 | 25000 | 50000 | 2 Days | - | - | 0 | 25000 | 0 | - | 100000
| 2(ii) | Fee for meetings / hearings not at site | Per Day | - |  | 0 | 10000 | 0 | - | - |  | 0 | 10000 | 0 | - | - |  | 0 | 10000 | 0 | - | 0
| 3 | Travelling Expenses | [19 empty] | 0
|  | Day 1 | @ Actuals | 2026-02-20 |  | 1 | 6202 | 6202 | Delhi - Guwahati | 2026-02-21 |  | 1 | 6202 | 6202 | Delhi - Guwahati | - |  | 0 | 0 | 0 | - | 12404
|  | Day 2 | @ Actuals | 2026-02-21 |  | 1 | 10074 | 10074 | Guwahati - Delhi | 2026-02-22 |  | 1 | 10074 | 10074 | Guwahati - Delhi | - |  | 0 | 0 | 0 | - | 20148
| 4 | Lodging & Boarding | Per Day | 2026-02-20 | 2026-02-21 | 2 | 10000 | 20000 | - | 2026-02-21 | 2026-02-22 | 2 | 10000 | 20000 | - | - | - | 0 | 10000 | 0 | - | 40000
| 5 | Extra charges for days other than hearing / meeting days (travel days maximum of 2 days on each occasion) | Per Day | - | - | 0 | 5000 | 0 | - | - | - | 0 | 5000 | 0 | - | - | - | 0 | 5000 | 0 | - | 0
| 6 | Local Conveyance | Per Day | 2026-02-20 | 2026-02-21 | 2 | 2000 | 4000 | - | 2026-02-21 | 2026-02-22 | 2 | 2000 | 4000 | - | - | - | 0 | 2000 | 0 | - | 8000 | 744051
Apr'26 - Jun-26 | 1 | Retainer-ship Fee, Secreterial Assitance and Incident Charges (Telephone, Fax, Postage, etc.) | Per Month | 2026-04-01 | 2026-06-30 | 3 | 50000 | 150000 | 3 Months | 2026-01-01 | 2026-03-31 | 3 | 50000 | 150000 | 3 Months | 2026-01-01 | 2026-03-31 | 3 | 50000 | 150000 | 3 Months | 450000
| 2(i) | For Project Site Visit or meeting at site office | Per Day | 2026-06-04 | 2026-06-05 | 2 | 25000 | 50000 | 2 Days | 2026-06-04 | 2026-06-05 | 2 | 25000 | 50000 | 2 Days | - | - | 0 | 25000 | 0 | - | 100000
| 2(ii) | Fee for meetings / hearings not at site | Per Day | - |  | 0 | 10000 | 0 | - | - |  | 0 | 10000 | 0 | - | - |  | 0 | 10000 | 0 | - | 0
| 3 | Travelling Expenses | [19 empty] | 0
|  | Day 1 | @ Actuals | 2026-06-04 |  | 1 | 8038 | 8038 | Delhi - Guwahati | 2026-06-04 |  | 1 | 8038 | 8038 | Delhi - Guwahati | - |  | 0 | 0 | 0 | - | 16076
|  | Day 2 | @ Actuals | 2026-06-05 |  | 1 | 8202 | 8202 | Guwahati - Delhi | 2026-06-05 |  | 1 | 8388 | 8388 | Guwahati - Delhi | - |  | 0 | 0 | 0 | - | 16590
| 4 | Lodging & Boarding | Per Day | 2026-06-04 | 2026-06-05 | 2 | 10000 | 20000 | - | 2026-06-04 | 2026-06-05 | 2 | 10000 | 20000 | - | - | - | 0 | 10000 | 0 | - | 40000
| 5 | Extra charges for days other than hearing / meeting days (travel days maximum of 2 days on each occasion) | Per Day | - | - | 0 | 5000 | 0 | - | - | - | 0 | 5000 | 0 | - | - | - | 0 | 5000 | 0 | - | 0
| 6 | Local Conveyance | Per Day | 2026-06-04 | 2026-06-05 | 2 | 2000 | 4000 | - | 2026-06-04 | 2026-06-05 | 2 | 2000 | 4000 | - | - | - | 0 | 2000 | 0 | - | 8000 | 744186
Total | [7 empty] | 1004224 | [5 empty] | 1003076 | [5 empty] | 732273 |  | 2739573
Add GST | [7 empty] | 180760.32 | [5 empty] | 180553.68 | [5 empty] | 131809.14 |  | 493123.14
Grand Total | [7 empty] | 1184984.32 | [5 empty] | 1183629.68 | [5 empty] | 864082.14 |  | 3232696.14
Employers Share to be paid
Cum. Up to this IPC | [7 empty] | 592492.16 | [5 empty] | 591814.84 | [5 empty] | 432041.07 |  | 1616348
Up to Previous IPC | [7 empty] | 592492.16 | [5 empty] | 591814.84 | [5 empty] | 432041.07 |  | 1616348
This IPC | [7 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 |  | 0
0.32327

## Price Adj. - Breakup
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
General Conditions of Contract - Clause 14.4 - Schedule of Payments - Road Works / Structure Works
[9 empty] | Period of bill : |  | 1st Jul'26 to 31st Jul'26
Schedule No | Description | Schedule Cost (% of the Contract Price) |  | Item No | Item Description | UOM | Percentage | Amount (INR) | Cumulative Bill | Upto Previous Bill | This Bill | Road / Structure Works
|  | Weightage % | Amount (Rs.) | [5 empty] | Amount (INR) | Amount (INR) | Amount (INR)
Schedule 1 | Preliminaries & General Items | 2.5% | 670750000 | 101 | Provision (construction) of office facilities for the Employer | LS | 30.5% | 204578750 | 204578753 | 204578753 | 0 | Structure Works
|  |  |  | 102 | Provision (construction) of contractor’s site office, site laboratories, labor camps etc | LS | 27.9% | 187139250 | 187139254 | 187139254 | 0 | Structure Works
|  |  |  | 103 | Operation and Maintenance of all temporary facilities including those mentioned in Item 101 & 102 | LS | 12.3% | 82502250 | 41251127 | 41251127 | 0 | Structure Works
|  |  |  | 104 | Compliance of Environmental Management Plan (EMP) | LS | 22.5% | 150918750 | 79747987 | 79747987 | 0 | Structure Works
|  |  |  | 105 | Demobilization of the Site on completion of the Works as per the General Specifications | LS | 6.8% | 45611000 | 0 | 0 | 0 | Structure Works
Preliminaries & General Items | [8 empty] | 512717121 | 512717121 | 0
Schedule 2 | Validation of Survey Data, Investigation, Design and As-Built Drawings | 3% | 804900000 | 201 | Site survey, establishment of bench marks, validation of ROW, identification of borrow areas. | LS | 4.8% | 38635200 | 38635200 | 38635200 | 0 | Structure Works
|  |  |  | 202 | Site data collection, Detailed Geotechnical and Hydrological investigations and report submission & approval | LS | 9.8% | 78880200 | 78880200 | 78880200 | 0 | Structure Works
|  |  |  | 203 | Preliminary Design of the approach formations, retaining structures, drainage system, bridges, major and /or minor structure and miscellaneous work. | LS | 29.4% | 236640600 | 229778023 | 229778023 | 0 | Structure Works
|  |  |  | 204 | Final Technical Design of the approach formation, retaining structures, drainage system, bridges, major and /or minor structures and miscellaneous work | LS | 41% | 330009000 | 304016666 | 303191643 | 825023 | Structure Works
|  |  |  | 205 | Setting out of the Final Alignment with location of all structures, approach formation work and Miscellaneous work | LS | 10% | 80490000 | 80490000 | 80490000 | 0 | Structure Works
|  |  |  | 206 | Preparation of As-Built Drawings | LS | 5% | 40245000 | 0 | 0 | 0 | Structure Works
Validation of Survey Data, Investigation, Design and As-Built Drawings | [8 empty] | 731800089 | 730975066 | 825023
Schedule 3 | Enabling Works for Main Works | 4.5% | 1207350000 | 301 | Construction of temporary jetties/ platforms (TAB) / load out jetties etc for marine working | LS | 17.9% | 216115650 | 216115650 | 216115650 | 0 | Structure Works
|  |  |  | 302 | Establishment of batching plant, crusher (if any), rebar yards, formwork shops, fabrication shops etc for main works | LS | 12.1% | 146089350 | 146089351 | 146089351 | 0 | Structure Works
|  |  |  | 303 | Establishment of Casting yards for casting of PSC Box girders, I-Girders etc as per requirement | LS | 27.9% | 336850650 | 336850651 | 336850651 | 0 | Structure Works
|  |  |  | 304 | Supply and installation of moulds, gantries etc for precast works | LS | 17.9% | 216115650 | 216115651 | 216115651 | 0 | Structure Works
|  |  |  | 305 | Supply and commissioning of Bridge Builders/Launchers for erection of bridge deck | LS | 8% | 96588000 | 28976400 | 28976400 | 0 | Structure Works
|  |  |  | 306 | Procurement/Mobilization of Marine Equipment’s (Barges/Tugs etc) for working in water | LS | 14% | 169029000 | 169029000 | 169029000 | 0 | Structure Works
|  |  |  | 307 | Removal of temporary jetties, platforms, load out jetties and casting yards | LS | 2.2% | 26561700 | 0 | 0 | 0 | Structure Works
Enabling Works for Main Works | [8 empty] | 1113176703 | 1113176703 | 0
Schedule 4 | Main Extradosed Bridge Works | 67% | 17976100000 | 401 | On ground clearance, preparatory works for start of foundation works such as cutting edge, shutters, scaffoldings etc | Nos | 0.4% | 71904400 | 2765554 | 70245068 | -67479514 | Structure Works
|  |  |  | 402 | Construction of foundation | LS | 37.2% | 6687109200 | 132818227 | 5437692865 | -5304874638 | Structure Works
|  |  |  | 403 | Construction of sub- structure; abutment/ piers / lower pylon | Rmt | 2.1% | 377498100 | 1733376 | 39500173 | -37766797 | Structure Works
|  |  |  | 404 | Construction of pier-cap/ pier table | Nos | 1.5% | 269641500 | 0 | 0 | 0 | Structure Works
|  |  |  | 405 | Construction of upper pylon | Rmt | 1.1% | 197737100 | 0 | 0 | 0 | Structure Works
|  |  |  | 406 | Construction of PSC Box girders in casting yard | Nos | 18.8% | 3379506800 | 13121257658 | 1026570614 | 12094687044 | Structure Works
|  |  |  | 407 | Procurement, testing and supply of post tensioning material to site | LS | 3.9% | 701067900 | 725856807 | 56789013 | 669067794 | Structure Works
|  |  |  | 408 | Procurement, testing and supply of Stay Cables to site | LS | 7.9% | 1420111900 | 246721183 | 365992198 | -119271015 | Structure Works
|  |  |  | 409 | Installation of PSC Box girders at site including installation of Stay Cable, Post Tensioning for completion of deck | Nos | 22.8% | 4098550800 | 0 | 0 | 0 | Structure Works
|  |  |  | 410 | Installation of bearings and expansion joints, Bridge Health Monitoring Equipments | LS | 0.6% | 107856600 | 0 | 0 | 0 | Structure Works
|  |  |  | 411 | Construction of Crash Barriers & Hand Railling | LS | 0.7% | 125832700 | 0 | 0 | 0 | Structure Works
|  |  |  | 412 | Completion of bridge pavement | LS | 0.4% | 71904400 | 0 | 0 | 0 | Road Works
|  |  |  | 413 | Completion of bridge lighting and electrical works | Span | 0.3% | 53928300 | 0 | 0 | 0 | Structure Works
|  |  |  | 414 | Completion of balance ancillary and miscellaneous works for handing over | Span | 0.6% | 107856600 | 0 | 0 | 0 | Structure Works
|  |  |  | 415 | Drainage works for bridge downtake | Span | 1.7% | 305593700 | 0 | 0 | 0 | Structure Works
Main Extradosed Bridge Works | [8 empty] | 14231152805 | 6996789931 | 7234362874
Schedule 5 | Wetland and Approach Viaduct Works | 14.5% | 3890350000 | 501 | Construction of foundation | LS | 49.5% | 1925723250 | 1898974828 | 1894955421 | 4019407 | Structure Works
|  |  |  | 502 & 503 | Construction of sub- structure; abutment/piers / lower pylon & Construction of pier- cap/ pier table | LS | 12.1% | 470732350 | 428251626 | 414474093 | 13777533 | Structure Works
|  |  |  | 504 | Construction of PSC Box girders/I-Girders in casting yard | LS | 15.3% | 595223550 | 334912451 | 296818144 | 38094307 | Structure Works
|  |  |  | 505 | Procurement, testing and supply of post tensioning material to site | LS | 3.4% | 132271900 | 110809810 | 110016179 | 793631 | Structure Works
|  |  |  | 506 | Installation of PSC Box girders/I-Girders at site including installation of Post Tensioning for completion of deck | LS | 16.2% | 630236700 | 152307204 | 115543395 | 36763809 | Structure Works
|  |  |  | 507 | Installation of bearings and expansion joints | LS | 0.7% | 27232450 | 2893448 | 2841078 | 52370 | Structure Works
|  |  |  | 508 | Construction of Crash Barriers and Hand Railings | LS | 1.2% | 46684200 | 0 | 0 | 0 | Structure Works
|  |  |  | 509 | Completion of bridge pavement | LS | 0.5% | 19451750 | 0 | 0 | 0 | Road Works
|  |  |  | 510 | Completion of bridge lighting and electrical works | LS | 0.6% | 23342100 | 0 | 0 | 0 | Structure Works
|  |  |  | 511 | Completion of balance ancillary and river training work, Embankment/ abutment protection works and other miscellaneous works for handing over | LS | 0.5% | 19451750 | 0 | 0 | 0 | Structure Works
Wetland and Approach Viaduct Works | [8 empty] | 2928149367 | 2834648310 | 93501057
Schedule 6 | Underpass Works | 2.5% | 670750000 | 601 | Subbase Course & Base Course | Nos | 1% | 6707500 | 0 | 0 | 0 | Road Works
|  |  |  | 602 | Bituminous Base Course | Nos | 0.1% | 670750 | 0 | 0 | 0 | Road Works
|  |  |  | 603 | Construction of foundation | Nos | 49% | 328667500 | 328667500 | 328667500 | 0 | Structure Works
|  |  |  | 604 | Construction of sub-structure; abutment/ piers/ lower pylon | LS | 37.8% | 253543500 | 253543500 | 253543500 | 0 | Structure Works
|  |  |  | 605 | Procurement, testing and supply of post tensioning material to site | LS | 0.9% | 6036750 | 0 | 0 | 0 | Structure Works
|  |  |  | 606 | Construction of superstructure | Nos | 10.1% | 67745750 | 10839320 | 10839320 | 0 | Structure Works
|  |  |  | 607 | Installation of bearings and expansion joints | LS | 0.7% | 4695250 | 0 | 0 | 0 | Structure Works
|  |  |  | 608 | Construction of Crash Barriers & Hand Railing | LS | 0.4% | 2683000 | 0 | 0 | 0 | Structure Works
Underpass Works | [8 empty] | 593050320 | 593050320 | 0
Schedule 7 | Approach road Works | 6% | 1609800000 | 701 | Earthwork up to top of the sub-grade | Kms | 24.1% | 387961800 | 162683303 | 162683303 | 0 | Road Works
|  |  |  | 702 | Sub Base Course | Kms | 7.7% | 123954600 | 0 | 0 | 0 | Road Works
|  |  |  | 703 | Non-Bituminous Base Course | Kms | 8.2% | 132003600 | 0 | 0 | 0 | Road Works
|  |  |  | 704 | Bituminous Base Course | Kms | 12.3% | 198005400 | 0 | 0 | 0 | Road Works
|  |  |  | 705 | Wearing Coat | Kms | 5.5% | 88539000 | 0 | 0 | 0 | Road Works
|  |  |  | 706 | Construction of earth retaining structures, culvert & minor structures | LS | 33.8% | 544112400 | 54411240 | 51388393 | 3022847 | Road Works
|  |  |  | 707 | Completion of other balance works e.g. marking, signage’s, lighting etc | Kms | 8.4% | 135223200 | 0 | 0 | 0 | Road Works
Approach road Works | [8 empty] | 217094543 | 214071696 | 3022847
Schedule 8 | Provisional Sum |  | 55400000 | 801 | Institutional Strengthening, Trainings and Capacity Building as per Employers Requirement, Seminar, Workshop, Exhibitions | LS | 100% | 50400000 | 0 | 0 | 0 | Provisional Sum
|  |  |  | 802 | Dispute Board (DB) cost and expenses | LS | 100% | 5000000 | 1616348 | 1616348 | 0 | Provisional Sum
Provisional Sum | [8 empty] | 1616348 | 1616348 | 0
Total Amount (Excl. Provisional Sum) | [8 empty] | 20327140948 | 12995429147 | 7331711801
Total Amount of Provisional Sum | [8 empty] | 1616348 | 1616348 | 0
Total Amount | [8 empty] | 20328757296 | 12997045495 | 7331711801
[8 empty] | Description | Cumulative Bill | Upto Previous Bill | This Bill
[8 empty] | Road Works | 217094543 | 214071696 | 3022847
[8 empty] | Structure Works | 20110046405 | 12781357451 | 7328688954
[8 empty] | Provisional Sum | 1616348 | 1616348 | 0
11691264986
8635875962

## Price Adj.
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
General Conditions of Contract - Clause 13.7 - Adjustments for Changes in Cost
[11 empty] | Base Month |  | 2023-12-01 | % Of Component (a) |  | 0.15 | Period of bill : |  | 1st Jul'26 to 31st Jul'26
S.No. | IPC No. | Work Done Month | Month Index Applicable | Work done Value (W) | Labour - CPI, Assam, Guwahati |  | Steel - WPI, Mild Steel - Long Products |  | Cement - WPI, Ordinary Portland Cement |  | Bitumen - VG40 - Haldia Refinery, West Bengal |  | Fuel and Lubricants - IOCL, Guwahati |  | Other Materials - WPI, All Commodities |  | Const. Machinery - WPI, Machinery for Mining, Quarrying and Const. |  | Total Adjusted Factor (Pn = a+B+C+D+E+F+G+H) | Adjustments for Change in Cost (Pn*W)
[5 empty] | Base Index (Lo) | 151.3 | Base Index (So) | 139.7 | Base Index (Co) | 135.9 | Base Index (Bo) | 46102 | Base Index (Fo)-Retail | 90.33 | Base Index (Oo) | 151.8 | Base Index (Mo) | 88.6
[13 empty] | Bulk(B) | 90.54
% of Component
[5 empty] | Road Works (b) | 0.1 | Road Works (c) | 0.02 | Road Works (d) | 0.08 | Road Works (e) | 0.25 | Road Works (f) | 0.15 | Road Works (g) | 0.15 | Road Works (h) | 0.1
[5 empty] | Structure Works (b) | 0.1 | Structure Works (c) | 0.23 | Structure Works (d) | 0.15 | Structure Works (e) | 0 | Structure Works (f) | 0.12 | Structure Works (g) | 0.15 | Structure Works (h) | 0.1
[5 empty] | Current Index (Ln) | Adjusted Factor B=b*(Ln/Lo) | Current Index (Sn) | Adjusted Factor C=c*(Sn/So) | Current Index (Cn) | Adjusted Factor D=d*(Cn/Co) | Current Index (Bn) | Adjusted Factor E=e*(Bn/Bo) | Current Index (Fn) | Adjusted Factor F=f*(Fn/Fo) | Current Index (On) | Adjusted Factor G=g*(On/Oo) | Current Index (Mn) | Adjusted Factor H=g*(Mn/Mo)
Road Works
1 | IPC - 02 | 2024-06-30 | 2024-05-12 | 0 | 151.6 | 0.1002 | 144.5 | 0.020687 | 129.3 | 0.076115 | 43782 | 0.23742 | 88.38 | 0.14676 | 153.5 | 0.15168 | 89.7 | 0.10124 | 0.9841 | 0 | 0
2 | IPC - 03 | 2024-07-31 | 2024-06-12 | 0 | 152.2 | 0.10059 | 143.6 | 0.020558 | 126.8 | 0.074643 | 42922 | 0.23276 | 89.25 | 0.14821 | 154 | 0.15217 | 89.4 | 0.1009 | 0.97984 | 0 | 0
3 | IPC - 04 | 2024-08-31 | 2024-07-13 | 0 | 154.5 | 0.10212 | 139.7 | 0.02 | 124 | 0.072995 | 43532 | 0.23606 | 89.38 | 0.14842 | 155.3 | 0.15346 | 89 | 0.10045 | 0.98351 | 0 | 0
4 | IPC - 05 | 2024-09-30 | 2024-08-12 | 0 | 155.5 | 0.10278 | 138.6 | 0.019843 | 122.6 | 0.072171 | 46062 | 0.24978 | 89.38 | 0.14842 | 154.4 | 0.15257 | 88.8 | 0.10023 | 0.99579 | 0 | 0
5 | IPC - 07 | 2024-10-31 | 2024-09-12 | 0 | 156 | 0.10311 | 138.9 | 0.019885 | 125 | 0.073584 | 45432 | 0.24637 | 89.38 | 0.14842 | 154.7 | 0.15287 | 88.8 | 0.10023 | 0.99446 | 0 | 0
6 | IPC - 08 | 2024-11-30 | 2024-10-12 | 0 | 157.7 | 0.10423 | 140 | 0.020043 | 124.6 | 0.073348 | 43092 | 0.23368 | 89.38 | 0.14842 | 156.7 | 0.15484 | 89.2 | 0.10068 | 0.98524 | 0 | 0
7 | IPC - 09 | 2024-12-31 | 2024-11-12 | 0 | 157.7 | 0.10423 | 140.2 | 0.020072 | 125.3 | 0.07376 | 47332 | 0.25667 | 89.42 | 0.14849 | 156.4 | 0.15455 | 89.5 | 0.10102 | 1.0088 | 0 | 0
8 | IPC - 10 | 2025-01-31 | 2024-12-13 | 0 | 156.2 | 0.10324 | 139.5 | 0.019971 | 127.9 | 0.075291 | 49122 | 0.26638 | 89.42 | 0.14849 | 155.7 | 0.15385 | 90 | 0.10158 | 1.0188 | 0 | 0
9 | IPC - 11 | 2025-02-28 | 2025-01-10 | 64200199 | 157.9 | 0.10436 | 138.5 | 0.019828 | 128.2 | 0.075467 | 51602 | 0.27983 | 89.42 | 0.14849 | 155 | 0.15316 | 91 | 0.10271 | 1.0338 | 66372898 | 2172699
10 | IPC - 13 | 2025-03-31 | 2025-02-10 | 22917238 | 155.4 | 0.10271 | 138.7 | 0.019857 | 128.9 | 0.075879 | 51152 | 0.27738 | 89.42 | 0.14849 | 154.9 | 0.15306 | 91.4 | 0.10316 | 1.0305 | 23617207 | 699969
11 | IPC - 14 | 2025-04-30 | 2025-03-12 | 8182495 | 154.7 | 0.10225 | 140 | 0.020043 | 129.3 | 0.076115 | 50882 | 0.27592 | 89.5 | 0.14862 | 154.8 | 0.15296 | 91.6 | 0.10339 | 1.0293 | 8422225 | 239730
12 | IPC - 15 | 2025-05-31 | 2025-04-12 | 3022846 | 153.8 | 0.10165 | 140.8 | 0.020157 | 127.6 | 0.075114 | 52422 | 0.28427 | 89.5 | 0.14862 | 154.2 | 0.15237 | 92.3 | 0.10418 | 1.0364 | 3132772 | 109926
13 | IPC - 16 | 2025-06-30 | 2025-05-12 | 6045694 | 152.6 | 0.10086 | 138.7 | 0.019857 | 131 | 0.077116 | 51912 | 0.28151 | 89.53 | 0.14867 | 153.7 | 0.15188 | 92.5 | 0.1044 | 1.0343 | 6252993 | 207299
14 | IPC - 18 | 2025-07-31 | 2025-06-12 | 0 | 151.2 | 0.099934 | 137.2 | 0.019642 | 131.3 | 0.077292 | 52152 | 0.28281 | 89.53 | 0.14867 | 153.7 | 0.15188 | 92.7 | 0.10463 | 1.0349 | 0 | 0
15 | IPC - 19 | 2025-08-31 | 2025-07-13 | 0 | 153.4 | 0.10139 | 135.3 | 0.01937 | 130.7 | 0.076939 | 50832 | 0.27565 | 89.53 | 0.14867 | 154.4 | 0.15257 | 93.1 | 0.10508 | 1.0297 | 0 | 0
16 | IPC - 20 | 2025-09-30 | 2025-08-12 | 0 | 154.4 | 0.10205 | 135.2 | 0.019356 | 130.7 | 0.076939 | 50102 | 0.27169 | 89.475 | 0.14858 | 155.2 | 0.15336 | 92.9 | 0.10485 | 1.0268 | 0 | 0
17 | IPC - 22 | 2025-10-31 | 2025-09-12 | 6045693 | 155.9 | 0.10304 | 135.6 | 0.019413 | 128.4 | 0.075585 | 49012 | 0.26578 | 89.42 | 0.14849 | 155 | 0.15316 | 92.9 | 0.10485 | 1.0203 | 6168558 | 122865
18 | IPC - 23 | 2025-11-30 | 2025-10-12 | 0 | 156.7 | 0.10357 | 133.8 | 0.019155 | 126.7 | 0.074584 | 49012 | 0.26578 | 89.42 | 0.14849 | 155.1 | 0.15326 | 93 | 0.10497 | 1.0198 | 0 | 0 | Start | End | No. of days | Rate | Avg. Rate
19 | IPC - 25 | 2025-12-31 | 2025-11-12 | 0 | 155.4 | 0.10271 | 133.3 | 0.019084 | 126.7 | 0.074584 | 44152 | 0.23943 | 89.42 | 0.14849 | 156.2 | 0.15435 | 93.3 | 0.1053 | 0.99394 | 0 | 0 | 2026-03-01 | 2026-03-25 | 25 | 89.42 | 94.29
20 | IPC - 26 | 2026-01-31 | 2025-12-13 | 9068540 | 155.4 | 0.10271 | 133.2 | 0.019069 | 127.5 | 0.075055 | 46622 | 0.25282 | 89.42 | 0.14849 | 157.2 | 0.15534 | 93.1 | 0.10508 | 1.0086 | 9146150 | 77610 | 2026-03-26 | 2026-03-31 | 6 | 114.55
21 | IPC - 27 | 2026-02-28 | 2026-01-10 | 82497605 | 156.7 | 0.10357 | 137.6 | 0.019699 | 130.1 | 0.076586 | 50292 | 0.27272 | 89.42 | 0.14849 | 157.6 | 0.15573 | 93.5 | 0.10553 | 1.0323 | 85164429 | 2666824 | 2026-04-01 | 2026-04-07 | 7 | 114.55 | 136.54
22 | IPC - 29 | 2026-03-31 | 2026-02-10 | 9068540 | 158.2 | 0.10456 | 140.8 | 0.020157 | 131.3 | 0.077292 | 49892 | 0.27055 | 89.42 | 0.14849 | 158.4 | 0.15652 | 93.5 | 0.10553 | 1.0331 | 9368740 | 300200 | 2026-04-08 | 2026-04-21 | 14 | 143.23
23 | IPC - 30 (B) | 2026-04-30 | 2026-03-12 | 3022846 | 158.4 | 0.10469 | 141.8 | 0.020301 | 132.1 | 0.077763 | 50102 | 0.27169 | 94.29 | 0.15621 | 161.2 | 0.15929 | 93.6 | 0.10564 | 1.0456 | 3160664 | 137818 | 2026-04-22 | 2026-04-30 | 9 | 143.23
24 | IPC - 31 (B) | 2026-05-31 | 2026-04-12 | 0 | 159.7 | 0.10555 | 144.4 | 0.020673 | 133 | 0.078293 | 70862 | 0.38427 | 136.54 | 0.22621 | 167 | 0.16502 | 93.4 | 0.10542 | 1.2354 | 0 | 0 | 2026-05-01 | 2026-05-17 | 17 | 143.23 | 141.85
25 | IPC - 33 (B) | 2026-06-30 | 2026-05-12 | 0 | 160 | 0.10575 | 147.108 | 0.021061 | 130.468 | 0.076802 | 87122 | 0.47244 | 141.85 | 0.23501 | 169.3338 | 0.16733 | 94.176 | 0.10629 | 1.3347 | 0 | 0 | 2026-05-18 | 2026-05-31 | 14 | 140.16
26 | IPC - 34 | 2026-07-31 | 2026-06-12 | 3022847 | 160.8 | 0.10628 | 144.812 | 0.020732 | 130.468 | 0.076802 | 80552 | 0.43681 | 97.23 | 0.16146 | 169.4876 | 0.16748 | 93.8272 | 0.1059 | 1.2255 | 3704386 | 681539 | 2026-06-01 | 2026-06-15 | 15 | 140.7413 | 133.41
[22 empty] | 2026-06-16 | 2026-06-30 | 15 | 126.077
Total Road Works |  |  |  | 217094543 | [15 empty] | 224511022
Structure Works (Extradosed Bridge and all structural works)
1 | IPC - 02 | 2024-06-30 | 2024-05-12 | 470736501 | 151.6 | 0.1002 | 144.5 | 0.2379 | 129.3 | 0.14272 | 43782 | 0 | 88.38 | 0.11741 | 153.5 | 0.15168 | 89.7 | 0.10124 | 1.0011 | 471276453 | 539952
2 | IPC - 03 | 2024-07-31 | 2024-06-12 | 203129138 | 152.2 | 0.10059 | 143.6 | 0.23642 | 126.8 | 0.13996 | 42922 | 0 | 89.25 | 0.11857 | 154 | 0.15217 | 89.4 | 0.1009 | 0.99861 | 202847541 | -281597
3 | IPC - 04 | 2024-08-31 | 2024-07-13 | 201867989 | 154.5 | 0.10212 | 139.7 | 0.23 | 124 | 0.13687 | 43532 | 0 | 89.38 | 0.11874 | 155.3 | 0.15346 | 89 | 0.10045 | 0.99163 | 200178005 | -1689984
4 | IPC - 05 | 2024-09-30 | 2024-08-12 | 208660127 | 155.5 | 0.10278 | 138.6 | 0.22819 | 122.6 | 0.13532 | 46062 | 0 | 89.38 | 0.11874 | 154.4 | 0.15257 | 88.8 | 0.10023 | 0.98782 | 206118202 | -2541925
5 | IPC - 07 | 2024-10-31 | 2024-09-12 | 255093701 | 156 | 0.10311 | 138.9 | 0.22868 | 125 | 0.13797 | 45432 | 0 | 89.38 | 0.11874 | 154.7 | 0.15287 | 88.8 | 0.10023 | 0.99159 | 252947778 | -2145923
6 | IPC - 08 | 2024-11-30 | 2024-10-12 | 433437094 | 157.7 | 0.10423 | 140 | 0.23049 | 124.6 | 0.13753 | 43092 | 0 | 89.38 | 0.11874 | 156.7 | 0.15484 | 89.2 | 0.10068 | 0.99651 | 431923781 | -1513313
7 | IPC - 09 | 2024-12-31 | 2024-11-12 | 513652087 | 157.7 | 0.10423 | 140.2 | 0.23082 | 125.3 | 0.1383 | 47332 | 0 | 89.42 | 0.11879 | 156.4 | 0.15455 | 89.5 | 0.10102 | 0.99771 | 512473654 | -1178433
8 | IPC - 10 | 2025-01-31 | 2024-12-13 | 657308943 | 156.2 | 0.10324 | 139.5 | 0.22967 | 127.9 | 0.14117 | 49122 | 0 | 89.42 | 0.11879 | 155.7 | 0.15385 | 90 | 0.10158 | 0.9983 | 656194337 | -1114606
9 | IPC - 11 | 2025-02-28 | 2025-01-10 | 790952363 | 157.9 | 0.10436 | 138.5 | 0.22802 | 128.2 | 0.1415 | 51602 | 0 | 89.42 | 0.11879 | 155 | 0.15316 | 91 | 0.10271 | 0.99855 | 789805161 | -1147202
10 | IPC - 13 | 2025-03-31 | 2025-02-10 | 821743742 | 155.4 | 0.10271 | 138.7 | 0.22835 | 128.9 | 0.14227 | 51152 | 0 | 89.42 | 0.11879 | 154.9 | 0.15306 | 91.4 | 0.10316 | 0.99835 | 820389348 | -1354394
11 | IPC - 14 | 2025-04-30 | 2025-03-12 | 789550802 | 154.7 | 0.10225 | 140 | 0.23049 | 129.3 | 0.14272 | 50882 | 0 | 89.5 | 0.1189 | 154.8 | 0.15296 | 91.6 | 0.10339 | 1.0007 | 790106761 | 555959
12 | IPC - 15 | 2025-05-31 | 2025-04-12 | 544357066 | 153.8 | 0.10165 | 140.8 | 0.23181 | 127.6 | 0.14084 | 52422 | 0 | 89.5 | 0.1189 | 154.2 | 0.15237 | 92.3 | 0.10418 | 0.99975 | 544219459 | -137607
13 | IPC - 16 | 2025-06-30 | 2025-05-12 | 378928137 | 152.6 | 0.10086 | 138.7 | 0.22835 | 131 | 0.14459 | 51912 | 0 | 89.53 | 0.11894 | 153.7 | 0.15188 | 92.5 | 0.1044 | 0.99902 | 378557148 | -370989
14 | IPC - 18 | 2025-07-31 | 2025-06-12 | 472419452 | 151.2 | 0.099934 | 137.2 | 0.22588 | 131.3 | 0.14492 | 52152 | 0 | 89.53 | 0.11894 | 153.7 | 0.15188 | 92.7 | 0.10463 | 0.99618 | 470616189 | -1803263
15 | IPC - 19 | 2025-08-31 | 2025-07-13 | 407791059 | 153.4 | 0.10139 | 135.3 | 0.22276 | 130.7 | 0.14426 | 50832 | 0 | 89.53 | 0.11894 | 154.4 | 0.15257 | 93.1 | 0.10508 | 0.99499 | 405747932 | -2043127
16 | IPC - 20 | 2025-09-30 | 2025-08-12 | 488824208 | 154.4 | 0.10205 | 135.2 | 0.22259 | 130.7 | 0.14426 | 50102 | 0 | 89.475 | 0.11886 | 155.2 | 0.15336 | 92.9 | 0.10485 | 0.99598 | 486858051 | -1966157
17 | IPC - 22 | 2025-10-31 | 2025-09-12 | 546099464.5 | 155.9 | 0.10304 | 135.6 | 0.22325 | 128.4 | 0.14172 | 49012 | 0 | 89.42 | 0.11879 | 155 | 0.15316 | 92.9 | 0.10485 | 0.99482 | 543269807 | -2829657.5
18 | IPC - 23 | 2025-11-30 | 2025-10-12 | 581366059 | 156.7 | 0.10357 | 133.8 | 0.22029 | 126.7 | 0.13985 | 49012 | 0 | 89.42 | 0.11879 | 155.1 | 0.15326 | 93 | 0.10497 | 0.99072 | 575970389 | -5395670
19 | IPC - 25 | 2025-12-31 | 2025-11-12 | 873173510 | 155.4 | 0.10271 | 133.3 | 0.21946 | 126.7 | 0.13985 | 44152 | 0 | 89.42 | 0.11879 | 156.2 | 0.15435 | 93.3 | 0.1053 | 0.99046 | 864845289 | -8328221
20 | IPC - 26 | 2026-01-31 | 2025-12-13 | 601725386 | 155.4 | 0.10271 | 133.2 | 0.2193 | 127.5 | 0.14073 | 46622 | 0 | 89.42 | 0.11879 | 157.2 | 0.15534 | 93.1 | 0.10508 | 0.99194 | 596877222 | -4848164
21 | IPC - 27 | 2026-02-28 | 2026-01-10 | 608913185 | 156.7 | 0.10357 | 137.6 | 0.22654 | 130.1 | 0.1436 | 50292 | 0 | 89.42 | 0.11879 | 157.6 | 0.15573 | 93.5 | 0.10553 | 1.0038 | 611204338 | 2291153
22 | IPC - 29 | 2026-03-31 | 2026-02-10 | 629241867.5 | 158.2 | 0.10456 | 140.8 | 0.23181 | 131.3 | 0.14492 | 49892 | 0 | 89.42 | 0.11879 | 158.4 | 0.15652 | 93.5 | 0.10553 | 1.0121 | 636879322 | 7637454.5
23 | IPC - 30 (B) | 2026-04-30 | 2026-03-12 | 441675199 | 158.4 | 0.10469 | 141.8 | 0.23346 | 132.1 | 0.14581 | 50102 | 0 | 94.29 | 0.12497 | 161.2 | 0.15929 | 93.6 | 0.10564 | 1.0239 | 452212628 | 10537429
24 | IPC - 31 (B) | 2026-05-31 | 2026-04-12 | 497100394 | 159.7 | 0.10555 | 144.4 | 0.23774 | 133 | 0.1468 | 70862 | 0 | 136.54 | 0.18097 | 167 | 0.16502 | 93.4 | 0.10542 | 1.0915 | 542582052 | 45481658
25 | IPC - 33 (B) | 2026-06-30 | 2026-05-12 | 363609977 | 160 | 0.10575 | 147.108 | 0.2422 | 130.468 | 0.144 | 87122 | 0 | 141.85 | 0.18801 | 169.3338 | 0.16733 | 94.176 | 0.10629 | 1.1036 | 401271115 | 37661138
26 | IPC - 34 | 2026-07-31 | 2026-06-12 | 7328688954 | 160.8 | 0.10628 | 144.812 | 0.23842 | 130.468 | 0.144 | 80552 | 0 | 97.23 | 0.12917 | 169.4876 | 0.16748 | 93.8272 | 0.1059 | 1.0412 | 7630951067 | 302262113
Total Structure Works |  |  |  | 20110046405 | [15 empty] | 20476323029
Total Amount |  |  |  | 20327140948 | [15 empty] | 20700834051
Cumulative Price Adjustment | [19 empty] | 373693103
Price Adjustment up to previous Bill | [19 empty] | 71027937
Price Adjustment this Bill | [19 empty] | 302665166
71027937
638310407.5
231637229
Formulas:
Month Index Applicable = [Work Done Month]-49

## Indices Cal.
Indices Calculation
Month | Mild Steel - Long Products / Bars and Rods of Mild steel |  |  |  | Ordinary Portland Cement |  |  |  | All Commodities |  |  |  | Manufacture of machinery for mining, quarrying and construction
| Old Series 2011-12 | New Series 2022-23 | Linking Factor | To be used for Calculation | Old Series 2011-12 | New Series 2022-23 | Linking Factor | To be used for Calculation | Old Series 2011-12 | New Series 2022-23 | Linking Factor | To be used for Calculation | Old Series 2011-12 | New Series 2022-23 | Linking Factor | To be used for Calculation
Avg. | 137.3167 | 83.75 | 1.64 |  | 129.9583 | 96.1583 | 1.352 |  | 157.0583 | 102.1417 | 1.538 |  | 93.125 | 106.7583 | 0.872
2025-05-01 | 138.7 | 87.4 |  |  | 131 | 98.3 |  |  | 153.7 | 100.2 |  |  | 92.5 | 106.2
2025-06-01 | 137.2 | 85.4 |  |  | 131.3 | 98.1 |  |  | 153.7 | 100.3 |  |  | 92.7 | 106.2
2025-07-01 | 135.3 | 82.3 |  |  | 130.7 | 97.4 |  |  | 154.4 | 100.2 |  |  | 93.1 | 107.2
2025-08-01 | 135.2 | 81.5 |  |  | 130.7 | 96.6 |  |  | 155.2 | 100.8 |  |  | 92.9 | 106.6
2025-09-01 | 135.6 | 80.5 |  |  | 128.4 | 95.8 |  |  | 155 | 101 |  |  | 92.9 | 106.5
2025-10-01 | 133.8 | 79.3 |  |  | 126.7 | 95 |  |  | 155.1 | 100.9 |  |  | 93 | 106.2
2025-11-01 | 133.3 | 78.6 |  |  | 126.7 | 95.2 |  |  | 156.2 | 101.5 |  |  | 93.3 | 106.5
2025-12-01 | 133.2 | 79.8 |  |  | 127.5 | 94.8 |  |  | 157.2 | 101.9 |  |  | 93.1 | 106.9
2026-01-01 | 137.6 | 84.4 |  |  | 130.1 | 94.8 |  |  | 157.6 | 102.3 |  |  | 93.5 | 106.9
2026-02-01 | 140.8 | 86.9 |  |  | 131.3 | 95 |  |  | 158.4 | 103.1 |  |  | 93.5 | 107.2
2026-03-01 | 142.7 | 88.7 |  |  | 132.1 | 95.8 |  |  | 161.2 | 104.6 |  |  | 93.6 | 107.4
2026-04-01 | 144.4 | 90.2 |  |  | 133 | 97.1 |  |  | 167 | 108.9 |  |  | 93.4 | 107.3
2026-05-01 |  | 89.7 | 1.64 | 147.108 |  | 96.5 | 1.352 | 130.468 |  | 110.1 | 1.538 | 169.3338 |  | 108 | 0.872 | 94.176
2026-06-01 |  | 88.3 | 1.64 | 144.812 |  | 96.5 | 1.352 | 130.468 |  | 110.2 | 1.538 | 169.4876 |  | 107.6 | 0.872 | 93.8272

## Withheld-Release
Withheld / Release of Withhled Amount Details
S.No. | Schedule No. | Description | Item No. | Item Description | UOM | Amount Payable per Unit | Quantity Certified | Amount Certified | Withheld |  |  |  |  | Release of Withheld |  |  |  |  | Balance
[9 empty] | IPC No. | Criteria | Quantity | Amount | Remarks | IPC No. | Criteria | Quantity | Amount | Remarks | Quantity | Amount
1 | Schedule 5 | Wetland and Approach Viaduct Works | 501.b.1 | On completion of Piles - Approach Viaduct | Nos. | 5106084.375 | 21 | 107227771.875 | 7 | 35% | 21 | 37529720.1562 | Due to non-approval of GFC Drawings | 22 | 35% | 21 | 37529720.1562 | As per Approvals | 0 | 0
2 | Schedule 5 | Wetland and Approach Viaduct Works | 501.b.1 | On completion of Piles - Approach Viaduct | Nos. | 5106084.375 | 51 | 260410303.125 | 8 | 35% | 51 | 91143606.0937 | Due to non-approval of GFC Drawings | 22 | 35% | 51 | 91143606.0937 | As per Approvals | 0 | 0
3 | Schedule 5 | Wetland and Approach Viaduct Works | 501.a.1 | On completion of Piles - Wetland Viaduct | Nos. | 2641998.3613 | 18 | 47555970.503 | 9 | 35% | 18 | 16644589.6761 | Due to non-approval of GFC Drawings | 14 | 35% | 18 | 16644589.6761 | As per Approvals | 0 | 0
4 | Schedule 5 | Wetland and Approach Viaduct Works | 501.b.1 | On completion of Piles - Approach Viaduct | Nos. | 5106084.375 | 9 | 45954759.375 | 9 | 35% | 9 | 16084165.7812 | Due to non-approval of GFC Drawings | 22 | 35% | 9 | 16084165.7812 | As per Approvals | 0 | 0
5 | Schedule 5 | Wetland and Approach Viaduct Works | 501.a.1 | On completion of Piles - Wetland Viaduct | Nos. | 2641998.3613 | 48 | 126815921.3415 | 10 | 35% | 48 | 44385572.4695 | Due to non-approval of GFC Drawings | 14 | 35% | 48 | 44385572.4695 | As per Approvals | 0 | 0
6 | Schedule 5 | Wetland and Approach Viaduct Works | 501.b.1 | On completion of Piles - Approach Viaduct | Nos. | 5106084.375 | 2 | 10212168.75 | 10 | 35% | 2 | 3574259.0625 | Due to non-approval of GFC Drawings | 22 | 35% | 2 | 3574259.0625 | As per Approvals | 0 | 0
7 | Schedule 5 | Wetland and Approach Viaduct Works | 501.a.1 | On completion of Piles - Wetland Viaduct | Nos. | 3671929.9258 | 40 | 214852680 | 11 | 35% | 40 | 75198438 | Due to non-approval of GFC Drawings | 14 | 35% | 33 | 62038711.35 | As per Approvals | 0 | 0
[14 empty] | 15 | 35% | 7 | 13159726.65 | As per Approvals
8 | Schedule 5 | Wetland and Approach Viaduct Works | 501.a.1 | On completion of Piles - Wetland Viaduct | Nos. | 3671929.9258 | 43 | 157892986.8114 | 13 | 35% | 43 | 55262545.384 | Due to non-approval of GFC Drawings | 14 | 35% | 38 | 48836668.0138 | As per Approvals | 0 | 0
[14 empty] | 15 | 35% | 5 | 6425877.3702 | As per Approvals
9 | Schedule 5 | Wetland and Approach Viaduct Works | 501.a.2 | On completion of Pile Cap | Nos. | 1851656.9712 | 3 | 5554970.9135 | 13 | 35% | 3 | 1944239.8197 | Due to non-approval of GFC Drawings | 14 | 35% | 3 | 1944239.8197 | As per Approvals | 0 | 0
10 | Schedule 3 | Enabling Works for Main Works | 304.b | Moulds - Fabrication & Commissioning | Nos. | 10805782.5 | 2.2177 | 23963937.7658 | 14 | 5% | 4 | 2161156.5 | For pending commissioning works | 16 | 5% | 4 | 2161156.5 | Pending works has been completed | 0 | 0
11 | Schedule 5 | Wetland and Approach Viaduct Works | 501.a.1 | On completion of Piles - Wetland Viaduct | Nos. | 3671929.9258 | 39 | 143205267.1081 | 14 | 35% | 15 | 19277632.1107 | Due to non-approval of GFC Drawings | 15 | 35% | 9 | 11566579.2664 | As per Approvals | 0 | 0
[14 empty] | 16 | 35% | 6 | 7711052.8443 | As per Approvals
12 | Schedule 5 | Wetland and Approach Viaduct Works | 501.a.1 | On completion of Piles - Wetland Viaduct | Nos. | 3671929.9258 | 25 | 91798248 | 15 | 35% | 21 | 26988684.955 | Due to non-approval of GFC Drawings | 16 | 35% | 21 | 26988684.955 | As per Approvals | 0 | 0
13 | Schedule 3 | Enabling Works for Main Works | 303.a.v | Construction of Casting Yard - Finishing and Commissioning of Casting yard | Nos. | 42106331.25 | 2 | 84212662.5 | 16 | 12.5% | 2 | 10526582.8125 | For Pending Finishing Works | 18 | 12.5% | 2 | 10526582.8125 | Pending works has been completed | 0 | 0
14 | Schedule 5 | Wetland and Approach Viaduct Works | 501.b.1 | On completion of Piles - Approach Viaduct | Nos. | 5106084.375 | 37 | 188925121.875 | 18 | 35% | 37 | 66123792.6562 | Due to non-approval of GFC Drawings | 22 | 35% | 37 | 66123792.6562 | As per Approvals | 0 | 0
15 | Schedule 5 | Wetland and Approach Viaduct Works | 501.b.2 | On completion of Well - Approach Viaduct | Rmt | 2048641.7553 | 8.96 | 18355830.1277 | 18 | 35% | 8.96 | 6424540.5447 | Due to non-approval of GFC Drawings | 19 | 35% | 8.96 | 6424540.5447 | As per Approvals | 0 | 0
16 | Schedule 5 | Wetland and Approach Viaduct Works | 504.a.1 | Casting of Girders in the precast yard - For Wetland Viaduct | Nos. | 1587262.8 | 7 | 11110839.6 | 18 | 50% | 1 | 793631.4 | Due to non-submission of Test report | 31 | 50% | 1 | 793631.4 | As per Approvals | 0 | 0
17 | Schedule 5 | Wetland and Approach Viaduct Works | 501.b.1 | On completion of Piles - Approach Viaduct | Nos. | 5106084.375 | 12 | 61273012.5 | 19 | 35% | 9 | 16084165.7812 | Due to non-approval of GFC Drawings | 22 | 35% | 9 | 16084165.7812 | As per Approvals | 0 | 0
18 | Schedule 7 | Approach Road Works | 706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | 6045693.3333 | 1 | 6045693.3333 | 22 | 10% | 1 | 604569.3333 | For Pending works - Km 3+760 | 26 | 10% | 1 | 604569.3333 | As per Approvals | 0 | 0
19 | Schedule 4 | Main Extradosed Bridge Works | 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | 4029137.5334 | 43.91 | 176919429.0925 | 26 | 5% | 19.48 | 3924379.9576 | Due to non-approval of GFC Drawings - P14(N) | 30 | 5% | 19.48 | 3924379.9576 | As per Approvals | 0 | 0
20 | Schedule 7 | Approach Road Works | 706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | 6045693.3333 | 1.5 | 9068540 | 26 | 10% | 1 | 604569.3333 | For Pending works - Km 10+100 | 31 | 10% | 1 | 604569.3333 | As per Approvals | 0 | 0
21 | Schedule 4 | Main Extradosed Bridge Works | 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | 4029137.5334 | 52.77 | 176919429.0925 | 27 | 5% | 5.82 | 1172479.0222 | Due to non-approval of GFC Drawings - P14(N) | 30 | 5% | 5.82 | 1172479.0222 | As per Approvals | 0 | 0
22 | Schedule 4 | Main Extradosed Bridge Works | 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | 4029137.5334 | 30.15 | 121478496 | 29 | 5% | 7.5 | 1510926.575 | Due to non-approval of GFC Drawings - P14(N) | 30 | 5% | 7.5 | 1510926.575 | As per Approvals | 0 | 0
[7 empty] | Cumulative Amount up to this IPC |  |  |  |  | 497964247 |  |  |  |  | 497964247 |  |  | 0
[7 empty] | Up to Previous Bill |  |  |  |  | 497964247 |  |  |  |  | 497964247
[7 empty] | This Bill |  |  |  |  | 0 |  |  |  |  | 0

## Withheld Release Details
Release of Withhled Details
S.No. | Item Description | Location | Scope | Withhled | [6 empty] | Release |  |  |  | Balance | IPC | ID | Group | Location | IPC | ID | Group | Location
|  |  |  | IPC - 09 | IPC - 10 | IPC - 11 | IPC - 13 | IPC - 14 | IPC - 15 | Total | IPC - 14 | IPC - 15 | IPC - 16 | Total |  | IPC - 09 | PL19/P1 - WV2 | P19 | Wetland Viaduct - 2 | IPC - 07 | PR1/P4 - AV | P1 | Approach Viaduct - 1
1 | Wetland Viaduct - 2 | P0 | 12 | 0 | 0 | 0 | 0 | 9 | 0 | 9 | 0 | 9 | 0 | 9 | 0 | IPC - 09 | PL19/P3 - WV2 | P19 | Wetland Viaduct - 2 | IPC - 07 | PL2/P3 - AV | P2 | Approach Viaduct - 1
2 | Wetland Viaduct - 2 | P1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IPC - 09 | PL20/P2 - WV2 | P20 | Wetland Viaduct - 2 | IPC - 07 | PR2/P4 - AV | P2 | Approach Viaduct - 1
3 | Wetland Viaduct - 2 | P2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IPC - 09 | PL20/P4 - WV2 | P20 | Wetland Viaduct - 2 | IPC - 07 | PL2/P4 - AV | P2 | Approach Viaduct - 1
4 | Wetland Viaduct - 2 | P3 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | IPC - 09 | PL20/P3 - WV2 | P20 | Wetland Viaduct - 2 | IPC - 07 | PL1/P4 - AV | P1 | Approach Viaduct - 1
5 | Wetland Viaduct - 2 | P4 | 8 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | IPC - 09 | PL20/P1 - WV2 | P20 | Wetland Viaduct - 2 | IPC - 07 | PR2/P3 - AV | P2 | Approach Viaduct - 1
6 | Wetland Viaduct - 2 | P5 | 8 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | 0 | IPC - 09 | PL19/P4 - WV2 | P19 | Wetland Viaduct - 2 | IPC - 07 | PR1/P3 - AV | P1 | Approach Viaduct - 1
7 | Wetland Viaduct - 2 | P6 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 0 | IPC - 09 | PR20/P1 - WV2 | P20 | Wetland Viaduct - 2 | IPC - 07 | PL1/P3 - AV | P1 | Approach Viaduct - 1
8 | Wetland Viaduct - 2 | P7 | 8 | 0 | 0 | 2 | 6 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | IPC - 09 | PL19/P2 - WV2 | P19 | Wetland Viaduct - 2 | IPC - 07 | PR2/P2 - AV | P2 | Approach Viaduct - 1
9 | Wetland Viaduct - 2 | P8 | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | IPC - 09 | PR20/P3 - WV2 | P20 | Wetland Viaduct - 2 | IPC - 07 | PR1/P2 - AV | P1 | Approach Viaduct - 1
10 | Wetland Viaduct - 2 | P9 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 0 | IPC - 09 | PR17/P2 - WV2 | P17 | Wetland Viaduct - 2 | IPC - 07 | PR2/P1 - AV | P2 | Approach Viaduct - 1
11 | Wetland Viaduct - 2 | P10 | 8 | 0 | 0 | 7 | 1 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | IPC - 09 | PR17/P4 - WV2 | P17 | Wetland Viaduct - 2 | IPC - 07 | PR1/P1 - AV | P1 | Approach Viaduct - 1
12 | Wetland Viaduct - 2 | P11 | 8 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 0 | IPC - 09 | PR20/P4 - WV2 | P20 | Wetland Viaduct - 2 | IPC - 07 | PL2/P2 - AV | P2 | Approach Viaduct - 1
13 | Wetland Viaduct - 2 | P12 | 10 | 0 | 7 | 3 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 0 | IPC - 09 | PL17/P2 - WV2 | P17 | Wetland Viaduct - 2 | IPC - 07 | PL1/P2 - AV | P1 | Approach Viaduct - 1
14 | Wetland Viaduct - 2 | P13 | 8 | 0 | 5 | 2 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 7 | 0 | IPC - 09 | PR17/P1 - WV2 | P17 | Wetland Viaduct - 2 | IPC - 07 | PR31/P3 - AV | P31 | Approach Viaduct - 2
15 | Wetland Viaduct - 2 | P14 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | IPC - 09 | PR16/P1 - WV2 | P16 | Wetland Viaduct - 2 | IPC - 07 | PL2/P1 - AV | P2 | Approach Viaduct - 1
16 | Wetland Viaduct - 2 | P15 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 0 | IPC - 09 | PR17/P3 - WV2 | P17 | Wetland Viaduct - 2 | IPC - 07 | PR31/P2 - AV | P31 | Approach Viaduct - 2
17 | Wetland Viaduct - 2 | P16 | 8 | 2 | 6 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | IPC - 09 | PL16/P1 - WV2 | P16 | Wetland Viaduct - 2 | IPC - 07 | PR1/P5 - AV | P1 | Approach Viaduct - 1
18 | Wetland Viaduct - 2 | P17 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | IPC - 10 | PR16/P3 - WV2 | P16 | Wetland Viaduct - 2 | IPC - 07 | PL31/P2 - AV | P31 | Approach Viaduct - 2
19 | Wetland Viaduct - 2 | P18 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 0 | IPC - 10 | PR15/P1 - WV2 | P15 | Wetland Viaduct - 2 | IPC - 07 | PR31/P4 - AV | P31 | Approach Viaduct - 2
20 | Wetland Viaduct - 2 | P19 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | IPC - 10 | PL16/P3 - WV2 | P16 | Wetland Viaduct - 2 | IPC - 07 | PR2/P5 - AV | P2 | Approach Viaduct - 1
21 | Wetland Viaduct - 2 | P20 | 8 | 7 | 1 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | IPC - 10 | PL17/P1 - WV2 | P17 | Wetland Viaduct - 2 | IPC - 08 | PL1/P5 - AV | P1 | Approach Viaduct - 1
22 | Wetland Viaduct - 2 | P21 | 12 | 0 | 0 | 7 | 5 | 0 | 0 | 12 | 0 | 12 | 0 | 12 | 0 | IPC - 10 | PL15/P1 - WV2 | P15 | Wetland Viaduct - 2 | IPC - 08 | PL2/P5 - AV | P2 | Approach Viaduct - 1
[16 empty] | IPC - 10 | PR16/P2 - WV2 | P16 | Wetland Viaduct - 2 | IPC - 08 | PL1/P1 - AV | P1 | Approach Viaduct - 1
1 | Wetland Viaduct - 1 | P0 | 12 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 3 | 0 | IPC - 10 | PL17/P4 - WV2 | P17 | Wetland Viaduct - 2 | IPC - 08 | PL31/P4 - AV | P31 | Approach Viaduct - 2
2 | Wetland Viaduct - 1 | P1 | 8 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | IPC - 10 | PR15/P2 - WV2 | P15 | Wetland Viaduct - 2 | IPC - 08 | PR34/P4 - AV | P34 | Approach Viaduct - 2
3 | Wetland Viaduct - 1 | P2 | 8 | 0 | 0 | 0 | 0 | 2 | 6 | 8 | 0 | 0 | 8 | 8 | 0 | IPC - 10 | PL14/P1 - WV2 | P14 | Wetland Viaduct - 2 | IPC - 08 | PR34/P2 - AV | P34 | Approach Viaduct - 2
4 | Wetland Viaduct - 1 | P3 | 12 | 0 | 0 | 0 | 0 | 4 | 8 | 12 | 0 | 0 | 12 | 12 | 0 | IPC - 10 | PL16/P2 - WV2 | P16 | Wetland Viaduct - 2 | IPC - 08 | PR31/P5 - AV | P31 | Approach Viaduct - 2
[16 empty] | IPC - 10 | PR16/P4 - WV2 | P16 | Wetland Viaduct - 2 | IPC - 08 | PL31/P1 - AV | P31 | Approach Viaduct - 2
| Total |  | 236 | 18 | 44 | 38 | 43 | 15 | 21 | 179 | 131 | 21 | 27 | 179 | 0 | IPC - 10 | PR15/P5 - WV2 | P15 | Wetland Viaduct - 2 | IPC - 08 | PL34/P4 - AV | P34 | Approach Viaduct - 2
[16 empty] | IPC - 10 | PL15/P2 - WV2 | P15 | Wetland Viaduct - 2 | IPC - 08 | PL31/P3 - AV | P31 | Approach Viaduct - 2
S.No. | Item Description | Location | Scope | Withhled | [6 empty] | Release |  |  |  | Balance | IPC - 10 | PR14/P2 - WV2 | P14 | Wetland Viaduct - 2 | IPC - 08 | PR31/P1 - AV | P31 | Approach Viaduct - 2
|  |  |  | IPC - 07 | IPC - 08 | IPC - 09 | IPC - 10 | IPC - 18 | IPC - 19 | Total | IPC - 22 |  |  | Total |  | IPC - 10 | PL16/P4 - WV2 | P16 | Wetland Viaduct - 2 | IPC - 08 | PR34/P3 - AV | P34 | Approach Viaduct - 2
1 | Approach Viaduct - 1 | P0 | 18 | 0 | 15 | 2 | 1 | 0 | 0 | 18 | 18 |  |  | 18 | 0 | IPC - 10 | PL14/P2 - WV2 | P14 | Wetland Viaduct - 2 | IPC - 08 | PL34/P1 - AV | P34 | Approach Viaduct - 2
2 | Approach Viaduct - 1 | P1 | 16 | 8 | 2 | 0 | 0 | 0 | 3 | 13 | 13 |  |  | 13 | 0 | IPC - 10 | PR15/P3 - WV2 | P15 | Wetland Viaduct - 2 | IPC - 08 | PL31/P5 - AV | P31 | Approach Viaduct - 2
3 | Approach Viaduct - 1 | P2 | 10 | 9 | 1 | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0 | IPC - 10 | PR14/P3 - WV2 | P14 | Wetland Viaduct - 2 | IPC - 08 | PR34/P1 - AV | P34 | Approach Viaduct - 2
4 | Approach Viaduct - 1 | P3 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | IPC - 10 | PR13/P4 - WV2 | P13 | Wetland Viaduct - 2 | IPC - 08 | PL34/P5 - AV | P34 | Approach Viaduct - 2
5 | Approach Viaduct - 1 | P1R | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | IPC - 10 | PL14/P3 - WV2 | P14 | Wetland Viaduct - 2 | IPC - 08 | PR34/P5 - AV | P34 | Approach Viaduct - 2
6 | Approach Viaduct - 1 | P2R | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | IPC - 10 | PL15/P5 - WV2 | P15 | Wetland Viaduct - 2 | IPC - 08 | PL32/P1 - AV | P32 | Approach Viaduct - 2
[15 empty] | 0 | IPC - 10 | PR20/P2 - WV2 | P20 | Wetland Viaduct - 2 | IPC - 08 | PL32/P3 - AV | P32 | Approach Viaduct - 2
1 | Approach Viaduct - 2 | P31 | 10 | 4 | 6 | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0 | IPC - 10 | PR15/P4 - WV2 | P15 | Wetland Viaduct - 2 | IPC - 08 | PR32/P1 - AV | P32 | Approach Viaduct - 2
2 | Approach Viaduct - 2 | P32 | 20 | 0 | 10 | 2 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0 | IPC - 10 | PR19/P3 - WV2 | P19 | Wetland Viaduct - 2 | IPC - 08 | PL34/P2 - AV | P34 | Approach Viaduct - 2
3 | Approach Viaduct - 2 | P33 | 16 | 0 | 1 | 0 | 0 | 15 | 0 | 16 | 16 |  |  | 16 | 0 | IPC - 10 | PL15/P3 - WV2 | P15 | Wetland Viaduct - 2 | IPC - 08 | PR0/P3 - AV | P0 | Approach Viaduct - 1
4 | Approach Viaduct - 2 | P34 | 16 | 0 | 10 | 0 | 0 | 5 | 1 | 16 | 16 |  |  | 16 | 0 | IPC - 10 | PL14/P4 - WV2 | P14 | Wetland Viaduct - 2 | IPC - 08 | PL0/P1 - AV | P0 | Approach Viaduct - 1
5 | Approach Viaduct - 2 | P35 | 20 | 0 | 6 | 5 | 1 | 0 | 0 | 12 | 12 |  |  | 12 | 0 | IPC - 10 | PR19/P1 - WV2 | P19 | Wetland Viaduct - 2 | IPC - 08 | PL34/P3 - AV | P34 | Approach Viaduct - 2
6 | Approach Viaduct - 2 | P36 | 24 | 0 | 0 | 0 | 0 | 17 | 5 | 22 | 22 |  |  | 22 | 0 | IPC - 10 | PR13/P1 - WV2 | P13 | Wetland Viaduct - 2 | IPC - 08 | PR0/P5 - AV | P0 | Approach Viaduct - 1
7 | Approach Viaduct - 2 | P32R | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | IPC - 10 | PR14/P1 - WV2 | P14 | Wetland Viaduct - 2 | IPC - 08 | PL0/P7 - AV | P0 | Approach Viaduct - 1
8 | Approach Viaduct - 2 | P33R | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | IPC - 10 | PR19/P2 - WV2 | P19 | Wetland Viaduct - 2 | IPC - 08 | PL32/P6 - AV | P32 | Approach Viaduct - 2
[16 empty] | IPC - 10 | PR19/P4 - WV2 | P19 | Wetland Viaduct - 2 | IPC - 08 | PR0/P4 - AV | P0 | Approach Viaduct - 1
|  |  | 194 | 21 | 51 | 9 | 2 | 37 | 9 | 129 | 129 |  |  | 129 | 0 | IPC - 10 | PL13/P3 - WV2 | P13 | Wetland Viaduct - 2 | IPC - 08 | PR35/P6 - AV | P35 | Approach Viaduct - 2
[16 empty] | IPC - 10 | PR12/P3 - WV2 | P12 | Wetland Viaduct - 2 | IPC - 08 | PL0/P8 - AV | P0 | Approach Viaduct - 1
[16 empty] | IPC - 10 | PL12/P4 - WV2 | P12 | Wetland Viaduct - 2 | IPC - 08 | PL32/P4 - AV | P32 | Approach Viaduct - 2
[9 empty] | P0 | [6 empty] | IPC - 10 | PL13/P4 - WV2 | P13 | Wetland Viaduct - 2 | IPC - 08 | PR35/P5 - AV | P35 | Approach Viaduct - 2
[9 empty] | P1 | [6 empty] | IPC - 10 | PL12/P1 - WV2 | P12 | Wetland Viaduct - 2 | IPC - 08 | PR0/P6 - AV | P0 | Approach Viaduct - 1
[9 empty] | P1R | [6 empty] | IPC - 10 | PR12/P2 - WV2 | P12 | Wetland Viaduct - 2 | IPC - 08 | PL33/P2 - AV | P33 | Approach Viaduct - 2
[9 empty] | P2 | [6 empty] | IPC - 10 | PL13/P2 - WV2 | P13 | Wetland Viaduct - 2 | IPC - 08 | PL32/P2 - AV | P32 | Approach Viaduct - 2
[9 empty] | P2R | [6 empty] | IPC - 10 | PL12/P5 - WV2 | P12 | Wetland Viaduct - 2 | IPC - 08 | PR35/P1 - AV | P35 | Approach Viaduct - 2
[9 empty] | P3 | [6 empty] | IPC - 10 | PR12/P5 - WV2 | P12 | Wetland Viaduct - 2 | IPC - 08 | PL0/P6 - AV | P0 | Approach Viaduct - 1
[9 empty] | P31 | [6 empty] | IPC - 10 | PL12/P2 - WV2 | P12 | Wetland Viaduct - 2 | IPC - 08 | PL32/P5 - AV | P32 | Approach Viaduct - 2
[9 empty] | P32 | [6 empty] | IPC - 10 | PL15/P4 - WV2 | P15 | Wetland Viaduct - 2 | IPC - 08 | PR32/P6 - AV | P32 | Approach Viaduct - 2
[9 empty] | P33 | [6 empty] | IPC - 10 | PR14/P4 - WV2 | P14 | Wetland Viaduct - 2 | IPC - 08 | PR0/P2 - AV | P0 | Approach Viaduct - 1
[9 empty] | P34 | [6 empty] | IPC - 10 | PL17/P3 - WV2 | P17 | Wetland Viaduct - 2 | IPC - 08 | PL0/P5 - AV | P0 | Approach Viaduct - 1
[9 empty] | P35 | [6 empty] | IPC - 11 | PL10/P1 - WV2 | P10 | Wetland Viaduct - 2 | IPC - 08 | PL35/P4 - AV | P35 | Approach Viaduct - 2
[9 empty] | P36 | [6 empty] | IPC - 11 | PL12/P3 - WV2 | P12 | Wetland Viaduct - 2 | IPC - 08 | PL35/P6 - AV | P35 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR11/P1 - WV2 | P11 | Wetland Viaduct - 2 | IPC - 08 | PR0/P9 - AV | P0 | Approach Viaduct - 1
[16 empty] | IPC - 11 | PR12/P1 - WV2 | P12 | Wetland Viaduct - 2 | IPC - 08 | PL0/P4 - AV | P0 | Approach Viaduct - 1
[16 empty] | IPC - 11 | PR10/P3 - WV2 | P10 | Wetland Viaduct - 2 | IPC - 08 | PR32/P5 - AV | P32 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR12/P4 - WV2 | P12 | Wetland Viaduct - 2 | IPC - 08 | PL0/P9 - AV | P0 | Approach Viaduct - 1
[16 empty] | IPC - 11 | PL11/P3 - WV2 | P11 | Wetland Viaduct - 2 | IPC - 08 | PR35/P4 - AV | P35 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL21/P1 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 08 | PL0/P2 - AV | P0 | Approach Viaduct - 1
[16 empty] | IPC - 11 | PR21/P1 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 08 | PR32/P3 - AV | P32 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR13/P3 - WV2 | P13 | Wetland Viaduct - 2 | IPC - 08 | PR0/P8 - AV | P0 | Approach Viaduct - 1
[16 empty] | IPC - 11 | PR11/P4 - WV2 | P11 | Wetland Viaduct - 2 | IPC - 09 | PR32/P4 - AV | P32 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR10/P2 - WV2 | P10 | Wetland Viaduct - 2 | IPC - 09 | PL35/P1 - AV | P35 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR13/P2 - WV2 | P13 | Wetland Viaduct - 2 | IPC - 09 | PR35/P2 - AV | P35 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL10/P4 - WV2 | P10 | Wetland Viaduct - 2 | IPC - 09 | PL35/P3 - AV | P35 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR10/P4 - WV2 | P10 | Wetland Viaduct - 2 | IPC - 09 | PL0/P3 - AV | P0 | Approach Viaduct - 1
[16 empty] | IPC - 11 | PL9/P1 - WV2 | P9 | Wetland Viaduct - 2 | IPC - 09 | PR0/P1 - AV | P0 | Approach Viaduct - 1
[16 empty] | IPC - 11 | PL10/P2 - WV2 | P10 | Wetland Viaduct - 2 | IPC - 09 | PL35/P2 - AV | P35 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR21/P2 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 09 | PR32/P2 - AV | P32 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR9/P2 - WV2 | P9 | Wetland Viaduct - 2 | IPC - 09 | PL35/P5 - AV | P35 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL9/P4 - WV2 | P9 | Wetland Viaduct - 2 | IPC - 10 | PR0/P7 - AV | P0 | Approach Viaduct - 1
[16 empty] | IPC - 11 | PR10/P1 - WV2 | P10 | Wetland Viaduct - 2 | IPC - 10 | PR35/P3 - AV | P35 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL9/P5 - WV2 | P9 | Wetland Viaduct - 2 | IPC - 18 | PL33/P8 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR9/P3 - WV2 | P9 | Wetland Viaduct - 2 | IPC - 18 | PR33/P7 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL8/P4 - WV2 | P8 | Wetland Viaduct - 2 | IPC - 18 | PR33/P8 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL21/P2 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 18 | PR33/P3 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR8/P2 - WV2 | P8 | Wetland Viaduct - 2 | IPC - 18 | PR34/P8 - AV | P34 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR9/P5 - WV2 | P9 | Wetland Viaduct - 2 | IPC - 18 | PR33/P2 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL9/P2 - WV2 | P9 | Wetland Viaduct - 2 | IPC - 18 | PL33/P7 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR21/P3 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 18 | PR33/P6 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL8/P1 - WV2 | P8 | Wetland Viaduct - 2 | IPC - 18 | PR33/P4 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR8/P3 - WV2 | P8 | Wetland Viaduct - 2 | IPC - 18 | PR34/P7 - AV | P34 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR7/P2 - WV2 | P7 | Wetland Viaduct - 2 | IPC - 18 | PR34/P9 - AV | P34 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL21/P3 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 18 | PL33/P1 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL21/P4 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 18 | PR34/P6 - AV | P34 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL9/P3 - WV2 | P9 | Wetland Viaduct - 2 | IPC - 18 | PL33/P4 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR9/P4 - WV2 | P9 | Wetland Viaduct - 2 | IPC - 18 | PL33/P5 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PL7/P4 - WV2 | P7 | Wetland Viaduct - 2 | IPC - 18 | PR33/P1 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 11 | PR9/P1 - WV2 | P9 | Wetland Viaduct - 2 | IPC - 18 | PL33/P3 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR4/P2 - WV2 | P4 | Wetland Viaduct - 2 | IPC - 18 | PR33/P5 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR5/P1 - WV2 | P5 | Wetland Viaduct - 2 | IPC - 18 | PL33/P6 - AV | P33 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR5/P2 - WV2 | P5 | Wetland Viaduct - 2 | IPC - 18 | PL34/P8 - AV | P34 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR5/P3 - WV2 | P5 | Wetland Viaduct - 2 | IPC - 18 | PL36/P8 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR5/P4 - WV2 | P5 | Wetland Viaduct - 2 | IPC - 18 | PL36/P7 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL5/P1 - WV2 | P5 | Wetland Viaduct - 2 | IPC - 18 | PL36/P10 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL5/P4 - WV2 | P5 | Wetland Viaduct - 2 | IPC - 18 | PL36/P9 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL6/P1 - WV2 | P6 | Wetland Viaduct - 2 | IPC - 18 | PR36/P1 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL6/P2 - WV2 | P6 | Wetland Viaduct - 2 | IPC - 18 | PL36/P1 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL6/P3 - WV2 | P6 | Wetland Viaduct - 2 | IPC - 18 | PR36/P2 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL6/P4 - WV2 | P6 | Wetland Viaduct - 2 | IPC - 18 | PR36/P3 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL6/P5 - WV2 | P6 | Wetland Viaduct - 2 | IPC - 18 | PL36/P12 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR6/P1 - WV2 | P6 | Wetland Viaduct - 2 | IPC - 18 | PL36/P2 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR6/P2 - WV2 | P6 | Wetland Viaduct - 2 | IPC - 18 | PL36/P11 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR6/P3 - WV2 | P6 | Wetland Viaduct - 2 | IPC - 18 | PR36/P4 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR6/P4 - WV2 | P6 | Wetland Viaduct - 2 | IPC - 18 | PR36/P11 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR6/P5 - WV2 | P6 | Wetland Viaduct - 2 | IPC - 18 | PR36/P10 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL7/P1 - WV2 | P7 | Wetland Viaduct - 2 | IPC - 18 | PL36/P3 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL7/P2 - WV2 | P7 | Wetland Viaduct - 2 | IPC - 18 | PL36/P5 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL7/P3 - WV2 | P7 | Wetland Viaduct - 2 | IPC - 18 | PR36/P5 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR7/P1 - WV2 | P7 | Wetland Viaduct - 2 | IPC - 19 | PL34/P7 - AV | P34 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR7/P3 - WV2 | P7 | Wetland Viaduct - 2 | IPC - 19 | PR36/P12 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR7/P4 - WV2 | P7 | Wetland Viaduct - 2 | IPC - 19 | PL36/P4 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL8/P2 - WV2 | P8 | Wetland Viaduct - 2 | IPC - 19 | PL36/P6 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL8/P3 - WV2 | P8 | Wetland Viaduct - 2 | IPC - 19 | PR36/P6 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR8/P1 - WV2 | P8 | Wetland Viaduct - 2 | IPC - 19 | PR36/P7 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PR8/P4 - WV2 | P8 | Wetland Viaduct - 2 |  | PR36/P9 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL10/P3 - WV2 | P10 | Wetland Viaduct - 2 |  | PR36/P8 - AV | P36 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL18/P1 - WV2 | P18 | Wetland Viaduct - 2 |  | PL34/P9 - AV | P34 | Approach Viaduct - 2
[16 empty] | IPC - 13 | PL18/P2 - WV2 | P18 | Wetland Viaduct - 2 | IPC - 19 | PR1/P3 - AV | P1 | Approach Viaduct - 1
[16 empty] | IPC - 13 | PL18/P3 - WV2 | P18 | Wetland Viaduct - 2 | IPC - 19 | PL1/P3 - AV | P1 | Approach Viaduct - 1
[16 empty] | IPC - 13 | PL18/P4 - WV2 | P18 | Wetland Viaduct - 2 | IPC - 19 | PR1/P4 - AV | P1 | Approach Viaduct - 1
[16 empty] | IPC - 13 | PL18/P5 - WV2 | P18 | Wetland Viaduct - 2 | IPC - 22 | PL1/P6 - AV | P1 | Approach Viaduct - 1
[16 empty] | IPC - 13 | PR18/P1 - WV2 | P18 | Wetland Viaduct - 2 | IPC - 22 | PR1/P7 - AV | P1 | Approach Viaduct - 1
[16 empty] | IPC - 13 | PR18/P2 - WV2 | P18 | Wetland Viaduct - 2 | IPC - 22 | PR1/P2 - AV | P1 | Approach Viaduct - 1
[16 empty] | IPC - 13 | PR18/P3 - WV2 | P18 | Wetland Viaduct - 2 | IPC - 22 | PL1/P7 - AV | P1 | Approach Viaduct - 1
[16 empty] | IPC - 13 | PR18/P4 - WV2 | P18 | Wetland Viaduct - 2 | IPC - 22 | PR1R/P4 - AV | P1R | Approach Viaduct - 1
[16 empty] | IPC - 13 | PR18/P5 - WV2 | P18 | Wetland Viaduct - 2 | IPC - 22 | PL1R/P4 - AV | P1R | Approach Viaduct - 1
[16 empty] | IPC - 13 | PL21/P5 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 22 | PL1R/P1 - AV | P1R | Approach Viaduct - 1
[16 empty] | IPC - 13 | PL21/P6 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 22 | PL1R/P3 - AV | P1R | Approach Viaduct - 1
[16 empty] | IPC - 13 | PR21/P4 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 22 | PL1R/P2 - AV | P1R | Approach Viaduct - 1
[16 empty] | IPC - 13 | PR21/P5 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 22 | PL2R/P4 - AV | P2R | Approach Viaduct - 1
[16 empty] | IPC - 13 | PR21/P6 - WV2 | P21 | Wetland Viaduct - 2 | IPC - 22 | PR2R/P3 - AV | P2R | Approach Viaduct - 1
[16 empty] | IPC - 14 | PL0/P1 - WV2 | P0 | Wetland Viaduct - 2 | IPC - 22 | PL2R/P3 - AV | P2R | Approach Viaduct - 1
[16 empty] | IPC - 14 | PL0/P5 - WV2 | P0 | Wetland Viaduct - 2 | IPC - 22 | PR2R/P2 - AV | P2R | Approach Viaduct - 1
[16 empty] | IPC - 14 | PL0/P6 - WV2 | P0 | Wetland Viaduct - 2 | IPC - 22 | PL2R/P2 - AV | P2R | Approach Viaduct - 1
[16 empty] | IPC - 14 | PR0/P1 - WV2 | P0 | Wetland Viaduct - 2 | IPC - 22 | PR2R/P1 - AV | P2R | Approach Viaduct - 1
[16 empty] | IPC - 14 | PR0/P2 - WV2 | P0 | Wetland Viaduct - 2 | IPC - 22 | PL2R/P1 - AV | P2R | Approach Viaduct - 1
[16 empty] | IPC - 14 | PR0/P3 - WV2 | P0 | Wetland Viaduct - 2 | IPC - 22 | PR1R/P2 - AV | P1R | Approach Viaduct - 1
[16 empty] | IPC - 14 | PR0/P4 - WV2 | P0 | Wetland Viaduct - 2 | IPC - 22 | PR1R/P1 - AV | P1R | Approach Viaduct - 1
[16 empty] | IPC - 14 | PR0/P5 - WV2 | P0 | Wetland Viaduct - 2 | IPC - 22 | PL3/P3 - AV | P3 | Approach Viaduct - 1
[16 empty] | IPC - 14 | PR0/P6 - WV2 | P0 | Wetland Viaduct - 2 | IPC - 22 | PR3/P3 - AV | P3 | Approach Viaduct - 1
[17 empty] | PL1/P1 - WV2 | P1 | Wetland Viaduct - 2 | IPC - 22 | PR3/P4 - AV | P3 | Approach Viaduct - 1
[17 empty] | PL1/P2 - WV2 | P1 | Wetland Viaduct - 2 | IPC - 22 | PL3/P4 - AV | P3 | Approach Viaduct - 1
[17 empty] | PL1/P3 - WV2 | P1 | Wetland Viaduct - 2 | IPC - 22 | PR3/P5 - AV | P3 | Approach Viaduct - 1
[17 empty] | PL1/P4 - WV2 | P1 | Wetland Viaduct - 2 | IPC - 22 | PL3/P5 - AV | P3 | Approach Viaduct - 1
[17 empty] | PR1/P1 - WV2 | P1 | Wetland Viaduct - 2 | IPC - 22 | PR3/P2 - AV | P3 | Approach Viaduct - 1
[17 empty] | PR1/P2 - WV2 | P1 | Wetland Viaduct - 2 | IPC - 22 | PL3/P1 - AV | P3 | Approach Viaduct - 1
[17 empty] | PR1/P3 - WV2 | P1 | Wetland Viaduct - 2 | IPC - 22 | PR3/P6 - AV | P3 | Approach Viaduct - 1
[17 empty] | PR1/P4 - WV2 | P1 | Wetland Viaduct - 2 | IPC - 22 | PR1R/P3 - AV | P1R | Approach Viaduct - 1
[17 empty] | PR2/P2 - WV2 | P2 | Wetland Viaduct - 2 | IPC - 22 | PL3/P6 - AV | P3 | Approach Viaduct - 1
[17 empty] | PR2/P3 - WV2 | P2 | Wetland Viaduct - 2 | IPC - 22 | PR3/P1 - AV | P3 | Approach Viaduct - 1
[17 empty] | PL3/P1 - WV2 | P3 | Wetland Viaduct - 2
[17 empty] | PL3/P2 - WV2 | P3 | Wetland Viaduct - 2
[17 empty] | PR3/P1 - WV2 | P3 | Wetland Viaduct - 2
[17 empty] | PR3/P2 - WV2 | P3 | Wetland Viaduct - 2
[17 empty] | PR3/P3 - WV2 | P3 | Wetland Viaduct - 2
[17 empty] | PL4/P1 - WV2 | P4 | Wetland Viaduct - 2
[17 empty] | PL4/P2 - WV2 | P4 | Wetland Viaduct - 2
[17 empty] | PL4/P3 - WV2 | P4 | Wetland Viaduct - 2
[17 empty] | PL4/P4 - WV2 | P4 | Wetland Viaduct - 2
[17 empty] | PR4/P1 - WV2 | P4 | Wetland Viaduct - 2
[17 empty] | PR4/P3 - WV2 | P4 | Wetland Viaduct - 2
[17 empty] | PR4/P4 - WV2 | P4 | Wetland Viaduct - 2
[17 empty] | PL5/P2 - WV2 | P5 | Wetland Viaduct - 2
[17 empty] | PL5/P3 - WV2 | P5 | Wetland Viaduct - 2
[16 empty] | IPC - 14 | PL2/P1 - WV1 | P2 | Wetland Viaduct - 1
[16 empty] | IPC - 14 | PR2/P2 - WV1 | P2 | Wetland Viaduct - 1
[16 empty] | IPC - 14 | PL3/P5 - WV1 | P3 | Wetland Viaduct - 1
[16 empty] | IPC - 14 | PL3/P6 - WV1 | P3 | Wetland Viaduct - 1
[16 empty] | IPC - 14 | PR3/P3 - WV1 | P3 | Wetland Viaduct - 1
[16 empty] | IPC - 14 | PR3/P4 - WV1 | P3 | Wetland Viaduct - 1
[17 empty] | PR2/P1 - WV2 | P2 | Wetland Viaduct - 2
[17 empty] | PR2/P4 - WV2 | P2 | Wetland Viaduct - 2
[17 empty] | PR3/P5 - WV2 | P3 | Wetland Viaduct - 2
[17 empty] | PR3/P4 - WV2 | P3 | Wetland Viaduct - 2
[16 empty] | IPC - 15 | PL0/P4 - WV1 | P0 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL0/P5 - WV1 | P0 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PR0/P6 - WV1 | P0 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL1/P1 - WV1 | P1 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL1/P2 - WV1 | P1 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL1/P3 - WV1 | P1 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL1/P4 - WV1 | P1 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL2/P2 - WV1 | P2 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL2/P3 - WV1 | P2 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL2/P4 - WV1 | P2 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PR2/P1 - WV1 | P2 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PR2/P3 - WV1 | P2 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PR2/P4 - WV1 | P2 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL3/P1 - WV1 | P3 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL3/P2 - WV1 | P3 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL3/P3 - WV1 | P3 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PL3/P4 - WV1 | P3 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PR3/P1 - WV1 | P3 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PR3/P2 - WV1 | P3 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PR3/P5 - WV1 | P3 | Wetland Viaduct - 1
[16 empty] | IPC - 15 | PR3/P6 - WV1 | P3 | Wetland Viaduct - 1
P3 - WV1

## Retention Release
Release of Retention Amount
IPC No. | Invoice Type | Amount Certified |  |  | Withheld of Retention Amount - 6% | Release of Retention Amount - 5% | Withheld Amount
|  | Main Works | Change in Cost | Total
IPC - 02 | Main Works & Price Adjustment | 470736501 | 51237 | 470787738 | 28247264.28 | 0 | 0
IPC - 03 | Main Works & Price Adjustment | 203129138 | 236610 | 203365748 | 12201944.88 | 0 | 0
IPC - 04 | Main Works & Price Adjustment | 201867989 | -1524979 | 200343010 | 12020580.6 | 0 | 0
IPC - 05 | Main Works & Price Adjustment | 208660127 | -2110581 | 206549546 | 12392972.76 | 0 | 0
IPC - 07 | Main Works & Price Adjustment | 255093701 | -2771764 | 252321937 | 15139316.22 | 0 | 0
IPC - 08 | Main Works & Price Adjustment | 433437094 | -1513313 | 431923781 | 25915426.86 | 0 | 0
IPC - 09 | Main Works & Price Adjustment | 513652087 | -1832165 | 511819922 | 30709195.32 | 0 | 0
IPC - 10 | Main Works & Price Adjustment | 657308943 | -1308684 | 656000259 | 39360015.54 | 0 | 0
IPC - 11 | Main Works & Price Adjustment | 855152562 | -1245369 | 853907193 | 51234431.58 | 0 | 0
IPC - 12 | Retention Money Release up to IPC - 11 | 0 | 0 | 0 | 0 | 189350956.7 | 37870191.34
IPC - 13 | Main Works & Price Adjustment | 844660980 | 938736 | 845599716 | 50735982.96 | 0 | 0
IPC - 14 | Main Works & Price Adjustment | 797733297 | 601907 | 798335204 | 47900112.24 | 0 | 0
IPC - 15 | Main Works & Price Adjustment | 547379912 | 899459 | 548279371 | 32896762.26 | 0 | 0
IPC - 16 | Main Works & Price Adjustment | 384973831 | 944932 | 385918763 | 23155125.78 | 0 | 0
IPC - 17 | Retention Money Release from IPC - 13 to 15 | 0 | 0 | 0 | 0 | 109610714.55 | 21922142.91
IPC - 18 | Main Works & Price Adjustment | 472419452 | -2583258 | 469836194 | 28190171.64 | 0 | 0
IPC - 19 | Main Works & Price Adjustment | 407791059 | -1243415 | 406547644 | 24392858.64 | 0 | 0
IPC - 20 | Main Works & Price Adjustment | 488824208 | -1285702 | 487538506 | 29252310.36 | 0 | 0
IPC - 21 | Retention Money Release from IPC - 16, 18 to 20 | 0 | 0 | 0 | 0 | 87492055.35 | 17498411.07
IPC - 22 | Main Works & Price Adjustment | 552558306 | -2047912 | 550510394 | 33030623.64 | 0 | 0
IPC - 23 | Main Works & Price Adjustment | 581366059 | -4600110 | 576765949 | 34605956.94 | 0 | 0
IPC - 24 | Retention Money Release from IPC - 22 & 23 | 0 | 0 | 0 | 0 | 56363817.15 | 11272763.43
IPC - 25 | Main Works & Price Adjustment | 873632591 | -7677382 | 865955209 | 51957312.54 | 0 | 0
IPC - 26 | Main Works & Price Adjustment | 610793926 | -5092113 | 605701813 | 36342108.78 | 0 | 0
IPC - 27 | Main Works & Price Adjustment | 691410790 | -362532 | 691048258 | 41462895.48 | 0 | 0
IPC - 28 | Retention Money Release from IPC - 25 & 26 | 0 | 0 | 0 | 0 | 73582851.1 | 14716570.22
IPC - 29 | Main Works & Price Adjustment | 638682433 | 14049929 | 652732362 | 39163941.72 | 0 | 0 |  | 1791957224
IPC - 30 | Main Works & Price Adjustment | 444698045 | 3478559 | 448176604 | 26890596.24 | 0 | 0
IPC - 31 | Main Works & Price Adjustment | 497100394 | 15423797 | 512524191 | 30751451.46 | 0 | 0 |  | 89597861.2
IPC - 32 | Retention Money Release from IPC - 27, 29 & 30 | 0 | 0 | 0 | 0 | 89597861.2 | 48671023.7
IPC - 33 | Main Works & Price Adjustment | 363982070 | 71602050 | 435584120 | 26135047.2 | 0 | 26135047.2
Total |  | 12997045495 | 71027937 | 13068073432 | 784084405.92 | 605998256.05 | 178086149.87 | 653403671.6 | 47405415.55 | 2.225
[8 empty] | 178086149.87 |  | 6.71
|  |  | Cumulative Amount up to this IPC |  |  | 605998256
|  |  | Up to Previous IPC |  |  | 605998256 |  | 653403671.6
|  |  | This IPC |  |  | 0 |  | 718744038.76

## ABG Reduction
Reduction of Advance Bank Guarantee Amount
IPC No. | Invoice Type | Mobiloization Advance | Amount Certified |  |  | Recovery of Mobilization Advance - 15% | Reduction of ABG Amount | Revised ABG Amount submitted
|  |  | Main Works | Change in Cost | Total
IPC - 01 | Mobilization Advance - 1st Installment | 1344270000 | 0 | 0 | 0 | 0 | 0 | 0
IPC - 02 | Main Works & Price Adjustment | 0 | 470736501 | 51237 | 470787738 | 70618160.7 | 0 | 0
IPC - 03 | Main Works & Price Adjustment | 0 | 203129138 | 236610 | 203365748 | 30504862.2 | 0 | 0
IPC - 04 | Main Works & Price Adjustment | 0 | 201867989 | -1524979 | 200343010 | 30051451.5 | 0 | 0
IPC - 05 | Main Works & Price Adjustment | 0 | 208660127 | -2110581 | 206549546 | 30982431.9 | 0 | 0
IPC - 06 | Mobilization Advance - 2nd Installment | 1344270000 | 0 | 0 | 0 | 0 | 0 | 793666603.2
IPC - 07 | Main Works & Price Adjustment | 0 | 255093701 | -2771764 | 252321937 | 37848290.55 | 0 | 0
IPC - 08 | Main Works & Price Adjustment | 0 | 433437094 | -1513313 | 431923781 | 64788567.15 | 0 | 0
IPC - 09 | Main Works & Price Adjustment | 0 | 513652087 | -1832165 | 511819922 | 76772988.3 | 0 | 0
IPC - 10 | Main Works & Price Adjustment | 0 | 657308943 | -1308684 | 656000259 | 98400038.85 | 0 | 0
IPC - 11 | Main Works & Price Adjustment | 0 | 855152562 | -1245369 | 853907193 | 128086078.95 | 0 | 0
IPC - 13 | Main Works & Price Adjustment | 0 | 844660980 | 938736 | 845599716 | 126839957.4 | 694892827.5 | 0
IPC - 14 | Main Works & Price Adjustment | 0 | 797733297 | 601907 | 798335204 | 119750280.6 | 0 | 0
IPC - 15 | Main Works & Price Adjustment | 0 | 547379912 | 899459 | 548279371 | 82241905.65 | 0 | 0
IPC - 16 | Main Works & Price Adjustment | 0 | 384973831 | 944932 | 385918763 | 57887814.45 | 0 | 0
IPC - 18 | Main Works & Price Adjustment | 0 | 472419452 | -2583258 | 469836194 | 70475429.1 | 0 | 0
IPC - 19 | Main Works & Price Adjustment | 0 | 407791059 | -1243415 | 406547644 | 60982146.6 | 391337576.4 | 0
IPC - 20 | Main Works & Price Adjustment | 0 | 488824208 | -1285702 | 487538506 | 73130775.9 | 0 | 0
IPC - 22 | Main Works & Price Adjustment | 0 | 552558306 | -2047912 | 550510394 | 82576559.1 | 0 | 0
IPC - 23 | Main Works & Price Adjustment | 0 | 581366059 | -4600110 | 576765949 | 86514892.35 | 242222227.35 | 0
IPC - 25 | Main Works & Price Adjustment | 0 | 873632591 | -7677382 | 865955209 | 129893281.35 | 0 | 0
IPC - 26 | Main Works & Price Adjustment | 0 | 610793926 | -5092113 | 605701813 | 90855271.95 | 0 | 0
IPC - 27 | Main Works & Price Adjustment | 0 | 691410790 | -362532 | 691048258 | 103657238.7 | 324405792
IPC - 29 | Main Works & Price Adjustment | 0 | 638682433 | 14049929 | 652732362 | 97909854.3 | 0 | 0
IPC - 30 | Main Works & Price Adjustment | 0 | 444698045 | 3478559 | 448176604 | 67226490.6 | 0 | 0
IPC - 31 | Main Works & Price Adjustment | 0 | 497100394 | 15423797 | 512524191 | 76878628.65 | 242014973.55 | 0
IPC - 33 | Main Works & Price Adjustment | 0 | 363982070 | 71602050 | 435584120 | 65337618 | 0 | 0
Total |  | 2688540000 | 12997045495 | 71027937 | 13068073432 | 1960211014.8 | 1894873396.8 | 793666603.2
| Value of ABG given initially | 873033263.52
| Adjusted Advance as on IPC 13 | -764382110.25
| ABG - 1st amendement | 108651153.27
| To be adjusted advance from IPC 14 to IPC 15 | -430471334.04
| ABG - 2nd amendement to be done | -321820180.77

## Summary-Royalty
Reconciliation of Forest Royalty Payments / Adjustments
S.No. | IPC No. | Month | Certified IPC Amount | Forest Royalty to be deducted from IPC (A) |  |  |  | Forest Royalty deducted from IPC (B) |  |  |  | Adjusted in IPC's (C) = (A)-(B) | Actual Claimed in IPC (D) | Balance to be adjusted (E) = (D)-(C)
|  |  |  | Certified | Income Tax | MMDRRF, DMFT & SMET | Total | Certified | Income Tax | MMDRRF, DMFT & SMET | Total
1 | IPC - 02 | 2024-06-01 | 470787738 | 7822993.32 | 195574.833 | 1564598.664 | 9583166.817 | 7822993.32 | 195574.833 | 1564598.664 | 9583166.817 | 0 | 0 | 0
2 | IPC - 03 | 2024-07-01 | 203365748 | 3379291.2596 | 84482.2815 | 675858.2519 | 4139631.793 | 3379291.2596 | 84482.2815 | 675858.2519 | 4139631.793 | 0 | 0 | 0
3 | IPC - 04 | 2024-08-01 | 200343010 | 3329062.9777 | 83226.5744 | 665812.5955 | 4078102.1477 | 3329062.9777 | 83226.5744 | 665812.5955 | 4078102.1477 | 0 | 0 | 0
4 | IPC - 05 | 2024-09-01 | 206549546 | 3432195.8458 | 85804.8961 | 686439.1692 | 4204439.9111 | 3432195.8458 | 85804.8961 | 686439.1692 | 4204439.9111 | 0 | 0 | 0
5 | IPC - 07 | 2024-10-01 | 252321937 | 4192787.2549 | 104819.6814 | 838557.451 | 5136164.3873 | 2392792 | 59819.8 | 478558.4 | 2931170.2 | 2204994.1873 | 2163495 | -41499.1873
6 | IPC - 08 | 2024-11-01 | 431923781 | 7177198.0891 | 179429.9522 | 1435439.6178 | 8792067.6591 | 0 | 0 | 0 | 0 | 8792067.6591 | 9161457 | 369389.3409
7 | IPC - 09 | 2024-12-01 | 511819922 | 8504817.5806 | 212620.4395 | 1700963.5161 | 10418401.5362 | 1257011 | 437050 | 251402.2 | 1945463.2 | 8472938.3362 | 8892400 | 419461.6638 |  | To be decuted | Deducted | Adjutsment made
8 | IPC - 10 | 2025-01-01 | 656000259 | 10900635.7428 | 272515.8936 | 2180127.1486 | 13353278.7849 | 8375636 | 272516 | 1675127.2 | 10323279.2 | 3029999.5849 | 3036500 | 6500.4151 | Forest Royalty | 208279243.0874 | 102492509.006 | 105786734.0814
9 | IPC - 11 | 2025-02-01 | 853907193 | 14189218.8933 | 354730.4723 | 2837843.7787 | 17381793.1443 | 14189218.8933 | 354730.4723 | 2837843.7787 | 17381793.1443 | 0 | 0 | 0 | Income Tax on FR | 5206981.0772 | 4925740.7501 | 281240.327
10 | IPC - 13 | 2025-03-01 | 845599716 | 14051175.0748 | 351279.3769 | 2810236.015 | 17212690.4666 | 2151175 | 351279 | 430236 | 2932690 | 14280000.4666 | 14295000 |  | MMDRF, DMFT, SMET | 41947144.4865 | 20702996.4012 | 21244148.0853
11 | IPC - 14 | 2025-04-01 | 798335204 | 13265789.3652 | 331644.7341 | 2653157.873 | 16250591.9724 | 7965789 | 331645 | 1593157.8 | 9890591.8 | 6360000.1724 | 7097350 |  | Total | 255433368.6511 | 128121246.1573 | 127312122.4938
12 | IPC - 15 | 2025-05-01 | 548279371 | 9110657.544 | 227766.4386 | 1822131.5088 | 11160555.4914 | 1710658 | 227766 | 342131.6 | 2280555.6 | 8879999.8914 | 8888500
13 | IPC - 16 | 2025-06-01 | 385918763 | 6412741.1599 | 160318.529 | 1282548.232 | 7855607.9208 | 0 | 160319 | 0 | 160319 | 7695288.9208 | 8599500
14 | IPC - 18 | 2025-07-01 | 469836194 | 7807181.6883 | 195179.5422 | 1561436.3377 | 9563797.5681 | 459923 | 195180 | 91983.6 | 747086.6 | 8816710.9681 | 7927500
15 | IPC - 19 | 2025-08-01 | 406547644 | 6755527.4842 | 168888.1871 | 1351105.4968 | 8275521.1682 | 2335527 | 168888 | 467106 | 2971521 | 5304000.1682 | 5306500
16 | IPC - 20 | 2025-09-01 | 487538506 | 8101337.7534 | 202533.4438 | 1620267.5507 | 9924138.7479 | 5188668 | 202533 | 1037734 | 6428935 | 3495203.7479 | 3497704
17 | IPC - 22 | 2025-10-01 | 550510394 | 9147730.0432 | 228693.2511 | 1829546.0086 | 11205969.3029 | 897730 | 228693 | 179546 | 1305969 | 9900000.3029 | 10027475
18 | IPC - 23 | 2025-11-01 | 576765949 | 9584013.7753 | 239600.3444 | 1916802.7551 | 11740416.8748 | 3554014 | 239600 | 710802 | 4504416 | 7236000.8748 | 7241000
19 | IPC - 25 | 2025-12-01 | 865955209 | 14389418.561 | 359735.464 | 2877883.7122 | 17627037.7372 | 9319419 | 359735 | 1863884 | 11543038 | 6083999.7372 | 6086500
20 | IPC - 26 | 2026-01-01 | 605701813 | 10064835.7095 | 251620.8927 | 2012967.1419 | 12329423.7442 | 10064835.7095 | 251620.8927 | 2012967.1419 | 12329423.7442 | 0 | 0
21 | IPC - 27 | 2026-02-01 | 691048258 | 11483021.901 | 287075.5475 | 2296604.3802 | 14066701.8287 | 0 | 0 | 0 | 0 | 14066701.8287 | 16991248
22 | IPC - 29 | 2026-03-01 | 638682433 | 10612868.6108 | 265321.7153 | 2122573.7222 | 13000764.0483 | 6807826 | 271158 | 1361566 | 8440550 | 4560214.0483 | 1651588
23 | IPC - 31 | 2026-05-01 | 512524191 | 8516520.2891 | 212913.0072 | 1873634.4636 | 10603067.76 | 2510520 | 212913 | 599634 | 3323067 | 7280000.76 | 7287000
24 | IPC - 33 | 2026-06-01 | 363982070 | 6048223.1638 | 151205.5791 | 1330609.096 | 7530037.839 | 5348223 | 151206 | 1176608 | 6676037 | 854000.839 | 856000
|  |  | 12534244849 | 208279243.0874 | 5206981.0772 | 41947144.4865 | 255433368.6511 | 102492509.006 | 4925740.7501 | 20702996.4012 | 128121246.1573 | 127312122.4938 | 129006717 | 753852.2325

## Royalty Details
Forest Royalty Payments by the Contractor
S.No. | Payment Date | Paid By | To | Permit No. | Quantity Paid (Cum) | Amount Paid | [8 empty] | Type of Material | Released in IPC
[6 empty] | Forest Royalty | Income Tax | MMDRRF & DMFT | SMET | Processing Fee | GST @ 5% | TCSS @ 2.55% | AMDCL Charge | Total
1 | 2024-07-31 | PWRD, Assam | DFO-Rangia |  |  | 2161848 | 54046.2 | 432370 | 0 | 0 | 0 | 0 | 0 | 2648264.2 | - | -
2 | 2024-10-07 | L&T Ltd. | DFO-Rangia | 7474030128 | 11111 | 499995 | 0 | 100000 | 0 | 1000 | 0 | 0 | 0 | 600995 | Ordinary Earth | IPC - 07 | 599995 | 599995
3 | 2024-10-17 | L&T Ltd. | DFO-Dhansiri | 5977850497 | 5000 | 1300000 | 0 | 260000 | 0 | 2500 | 0 | 0 | 0 | 1562500 | Stone | IPC - 07 | 1560000 | 2159995 | 2204994.1873 | -44999.1873
4 | 2024-11-11 | L&T Ltd. | DFO-Dhansiri | 9451769614 | 20000 | 5200000 | 0 | 1040000 | 0 | 2500 | 0 | 0 | 0 | 6242500 | Stone | IPC - 08 | 6240000 | 6240000
5 | 2024-11-11 | L&T Ltd. | DFO-Goalpara | 2305703110 | 5000 | 700000 | 0 | 140000 | 0 | 2000 | 0 | 0 | 0 | 842000 | River Sand | IPC - 08 | 840000 | 7080000
6 | 2024-11-19 | L&T Ltd. | DFO-Rangia | 2638811974 | 13889 | 625005 | 0 | 125002 | 0 | 2000 | 0 | 0 | 0 | 752007 | Ordinary Earth | IPC - 08 | 750007 | 7830007
7 | 2024-11-27 | L&T Ltd. | AMDCL |  | 30000 | 900000 | 0 | 180000 | 0 | 0 | 45000 | 22950 | 177000 | 1324950 | Clay | IPC - 08 | 1080000 | 8910007 | 8792067.6591 | 117939.3409
8 | 2024-11-27 | L&T Ltd. | AMDCL |  | 60000 | 1800000 | 0 | 360000 | 0 | 0 | 90000 | 45900 | 354000 | 2649900 | Clay | IPC - 09 | 2160000 | 2160000
9 | 2024-12-06 | L&T Ltd. | DFO-Dhansiri | 2636086540 | 20000 | 5200000 | 0 | 1040000 | 0 | 2500 | 0 | 0 | 0 | 6242500 | Stone | IPC - 09 | 6240000 | 8400000 | 8472938.3362 | -72938.3362
10 | 2025-01-04 | L&T Ltd. | DFO-Goalpara | 4053503456 | 5000 | 700000 | 0 | 140000 | 0 | 2000 | 0 | 0 | 0 | 842000 | River Sand | IPC - 10 | 840000 | 840000
11 | 2025-01-10 | L&T Ltd. | DFO-Rangia | 1474487445 | 25000 | 1125000 | 0 | 225000 | 0 | 2500 | 0 | 0 | 0 | 1352500 | Ordinary Earth | IPC - 10 | 1350000 | 2190000
12 | 2025-01-24 | L&T Ltd. | DFO-Goalpara | 1143848580 | 5000 | 700000 | 0 | 140000 | 0 | 2000 | 0 | 0 | 0 | 842000 | River Sand | IPC - 10 | 840000 | 3030000 | 3029999.5849 | 0.4151
13 | 2025-03-01 | L&T Ltd. | DFO-Goalpara | 6494109329 | 10000 | 1400000 | 0 | 280000 | 0 | 2500 | 0 | 0 | 0 | 1682500 | River Sand | IPC - 13 | 1680000 | 1680000
14 | 2025-03-01 | L&T Ltd. | DFO-Baksha | 8325234869 | 5000 | 1300000 | 0 | 260000 | 0 | 2500 | 0 | 0 | 0 | 1562500 | Stone | IPC - 13 | 1560000 | 3240000
15 | 2025-03-01 | L&T Ltd. | DFO-Baksha | 6914431254 | 5000 | 1300000 | 0 | 260000 | 0 | 2500 | 0 | 0 | 0 | 1562500 | Stone | IPC - 13 | 1560000 | 4800000
16 | 2025-03-12 | L&T Ltd. | DFO-Goalpara | 9140100683 | 25000 | 3500000 | 0 | 700000 | 0 | 2500 | 0 | 0 | 0 | 4202500 | River Sand | IPC - 13 | 4200000 | 9000000
17 | 2025-03-18 | L&T Ltd. | DFO-Rangia | 3205637620 | 40000 | 1800000 | 0 | 360000 | 0 | 2500 | 0 | 0 | 0 | 2162500 | Ordinary Earth | IPC - 13 | 2160000 | 11160000
18 | 2025-03-25 | L&T Ltd. | DFO-Baksha | 7248757805 | 10000 | 2600000 | 0 | 520000 | 0 | 2500 | 0 | 0 | 0 | 3122500 | Stone | IPC - 13 | 3120000 | 14280000 | 14280000.4666 | -0.4666
19 | 2025-04-18 | L&T Ltd. | DFO-Baksha | 1514854451 | 10000 | 2600000 | 0 | 520000 | 0 | 2500 | 0 | 0 | 0 | 3122500 | Stone | IPC - 14 | 3120000 | 3120000
20 | 2025-04-17 | L&T Ltd. | AMDCL |  | 90000 | 2700000 | 0 | 540000 | 0 | 0 | 135000 | 68850 | 531000 | 3974850 | Clay | IPC - 14 | 3240000 | 6360000 | 6360000.1724 | -0.17242
21 | 2025-05-03 | L&T Ltd. | DFO-Goalpara | 9369405249 | 15000 | 2100000 | 0 | 420000 | 0 | 2500 | 0 | 0 | 0 | 2522500 | River Sand | IPC - 15 | 2520000 | 2520000
22 | 2025-05-15 | L&T Ltd. | DFO-Baksha | 8720379797 | 10000 | 2600000 | 0 | 520000 | 0 | 2500 | 0 | 0 | 0 | 3122500 | Stone | IPC - 15 | 3120000 | 5640000
23 | 2025-05-15 | L&T Ltd. | DFO-Rangia | 5749288870 | 50000 | 2250000 | 0 | 450000 | 0 | 2500 | 0 | 0 | 0 | 2702500 | Ordinary Earth | IPC - 15 | 2700000 | 8340000
24 | 2025-05-22 | L&T Ltd. | DFO-Rangia | 9645617363 | 10000 | 450000 | 0 | 90000 | 0 | 1000 | 0 | 0 | 0 | 541000 | Ordinary Earth | IPC - 15 | 540000 | 8880000 | 8879999.8914 | 0.10856
25 | 2025-05-28 | L&T Ltd. | DFO-Goalpara | 9804362617 | 14000 | 1960000 | 0 | 392000 | 0 | 2500 | 0 | 0 | 0 | 2354500 | River Sand | IPC - 16 | 2352000 | 2352000
26 | 2025-06-09 | L&T Ltd. | DFO-Baksha | 7413133545 | 10000 | 2600000 | 0 | 520000 | 0 | 2500 | 0 | 0 | 0 | 3122500 | Stone | IPC - 16 | 3120000 | 5472000
27 | 2025-06-09 | L&T Ltd. | DFO-Baksha | 2643108455 | 10000 | 2600000 | 0 | 520000 | 0 | 2500 | 0 | 0 | 0 | 3122500 | Stone | IPC - 16 | 3120000 | 8592000 | 7695288.9208 | 896711.0792
28 | 2025-07-02 | L&T Ltd. | DFO-Baksha | 2220741541 | 10000 | 2600000 | 0 | 520000 | 0 | 2500 | 0 | 0 | 0 | 3122500 | Stone | IPC - 18 | 3120000 | 3120000
29 | 2025-07-07 | L&T Ltd. | DFO-Baksha | 4429530092 | 10000 | 2600000 | 0 | 520000 | 0 | 2500 | 0 | 0 | 0 | 3122500 | Stone | IPC - 18 | 3120000 | 6240000
30 | 2025-07-14 | L&T Ltd. | DFO-Goalpara | 7190601569 | 10000 | 1400000 | 0 | 280000 | 0 | 2500 | 0 | 0 | 0 | 1682500 | River Sand | IPC - 18 | 1680000 | 7920000 | 8816710.9681 | -896710.9681
31 | 2025-08-04 | L&T Ltd. | DFO-Dhansiri | 3158163759 | 17000 | 4420000 | 0 | 884000 | 0 | 2500 | 0 | 0 | 0 | 5306500 | Stone | IPC - 19 | 5304000 | 5304000 | 5304000.1682 | -0.16816
32 | 2025-09-18 | L&T Ltd. | DFO-Rangia | 6158275376 | 64726 | 2912670 | 0 | 582534 | 0 | 2500 | 0 | 0 | 0 | 3497704 | Ordinary Earth | IPC - 20 | 3495204 | 3495204 | 3495203.7479 | 0.25208
33 | 2025-09-08 | L&T Ltd. | AMDCL |  | 15000 | 450000 | 0 | 90000 | 0 | 0 | 22500 | 11475 | 88500 | 662475 | Clay | IPC - 22 | 540000 | 540000
34 | 2025-10-08 | L&T Ltd. | DFO-Baksha | 4774200624 | 20000 | 5200000 | 0 | 1040000 | 0 | 2500 | 0 | 0 | 0 | 6242500 | Stone | IPC - 22 | 6240000 | 6780000
35 | 2025-10-10 | L&T Ltd. | DFO-Baksha | 4108867108 | 10000 | 2600000 | 0 | 520000 | 0 | 2500 | 0 | 0 | 0 | 3122500 | Stone | IPC - 22 | 3120000 | 9900000 | 9900000.3029 | -0.30292
36 | 2025-11-01 | L&T Ltd. | DFO-Goalpara | 8416519404 | 24500 | 3430000 | 0 | 686000 | 0 | 2500 | 0 | 0 | 0 | 4118500 | River Sand | IPC - 23 | 4116000 | 4116000
37 | 2025-11-21 | L&T Ltd. | DFO-Baksha | 7944631444 | 10000 | 2600000 | 0 | 520000 | 0 | 2500 | 0 | 0 | 0 | 3122500 | Stone | IPC - 23 | 3120000 | 7236000 | 7236000.8748 | -0.87479
38 | 2025-12-11 | L&T Ltd. | DFO-Baksha | 1437774053 | 19500 | 5070000 | 0 | 1014000 | 0 | 2500 | 0 | 0 | 0 | 6086500 | Stone | IPC - 25 | 6084000 | 6084000 | 6083999.7372 | 0.26279
39 | 2026-01-28 | L&T Ltd. | DFO-Goalpara | 9996665839 | 5000 | 700000 | 0 | 140000 | 0 | 2000 | 0 | 0 | 0 | 842000 | River Sand | IPC - 27 | 840000 | 840000
40 | 2026-01-28 | L&T Ltd. | DFO-Goalpara | 3600846227 | 5000 | 700000 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 840000 | River Sand | IPC - 27 | 840000 | 1680000
41 | 2026-02-06 | L&T Ltd. | DFO-Baksha | 7751373921 | 10000 | 1820000 | 0 | 364000 | 0 | 2500 | 0 | 0 | 0 | 2186500 | Stone | IPC - 27 | 2184000 | 3864000
42 | 2026-02-18 | L&T Ltd. | DFO-Basishta | 1991327083 | 65243 | 1957290 | 0 | 391458 | 0 | 2500 | 0 | 0 | 0 | 2351248 | Clay | IPC - 27 | 2348748 | 6212748
43 | 2026-02-18 | L&T Ltd. | DFO-Basishta | 2332831449 | 65000 | 1950000 | 0 | 390000 | 0 | 2500 | 0 | 0 | 0 | 2342500 | Clay | IPC - 27 | 2340000 | 8552748
44 | 2026-02-25 | L&T Ltd. | DFO-Baksha | 9168593023 | 10000 | 1820000 | 0 | 364000 | 0 | 2500 | 0 | 0 | 0 | 2186500 | River Sand | IPC - 27 | 2184000 | 10736748
45 | 2026-02-25 | L&T Ltd. | DFO-Dhansiri | 3993683650 | 20000 | 5200000 | 0 | 1040000 | 0 | 2500 | 0 | 0 | 0 | 6242500 | Stone | IPC - 27 | 6240000 | 16976748 | 14066701.8287 | 2910046.1713
46 | 2026-03-17 | L&T Ltd. | DFO-Rangia | 9221276196 | 45808 | 1374240 | 0 | 274848 | 0 | 2500 | 0 | 0 | 0 | 1651588 | Ordinary Earth | IPC - 29 | 1649088 | 1649088 | 4560214.0483 | -2911126.0483
47 | 2026-05-06 | L&T Ltd. | DFO-Baksha | 4819348618 | 10000 | 1820000 | 0 | 364000 | 0 | 2500 | 0 | 0 | 0 | 2186500 | Sand | IPC - 31 | 2184000 | 2184000
48 | 2026-05-06 | L&T Ltd. | DFO-Baksha | 8779692876 | 3000 | 546000 | 0 | 109200 | 0 | 2000 | 0 | 0 | 0 | 657200 | Sand | IPC - 31 | 655200 | 2839200
49 | 2026-05-18 | L&T Ltd. | DFO-Udalgiri | 5722892266 | 20000 | 3640000 | 0 | 728000 | 72800 | 2500 | 0 | 0 | 0 | 4443300 | Sand | IPC - 31 | 4440800 | 7280000 | 7280000.76 | -0.75997
50 | 2026-06-23 | L&T Ltd. | DFO-Goalpara | 5776005000 | 5000 | 700000 | 0 | 140000 | 14000 | 2000 | 0 | 0 | 0 | 856000 | Sand | IPC - 33 | 854000 | 854000
51 | 2026-07-01 | L&T Ltd. | DFO-Dhansiri | 9070305952 | 10500 | 2730000 | 0 | 546000 | 54600 | 2500 | 599508 | 0 | 0 | 3932608 | Stone
52 | 2026-07-01 | L&T Ltd. | DFO-Dhansiri | 5278883871 | 3920 | 1019200 | 0 | 203840 | 20384 | 2500 | 223816.32 | 0 | 0 | 1469740.32 | Stone
53 | 2026-07-01 | L&T Ltd. | DFO-Dhansiri | 6000185414 | 5000 | 910000 | 0 | 182000 | 18200 | 2000 | 199836 | 0 | 0 | 1312036 | Sand
54 | 2026-07-17 | L&T Ltd. | DFO-Goalpara | 5102995962 | 10000 | 1400000 | 0 | 280000 | 28000 | 2500 | 307440 | 0 | 0 | 2017940 | River Sand
|  | Total |  |  |  | 112079400 | 0 | 22415882 | 207984 | 113000 | 1623100.32 | 149175 | 1150500 | 137739041.32 |  |  | 127311042 |  | 126458121.6548 | -1078.8948
[11 empty] | Cumulative Amount up to this IPC |  |  | 137739041.32 |  |  |  |  | 852920.3452
[11 empty] | Paid up to Previous IPC |  |  | 127312122.4938
[11 empty] | This IPC |  |  | 10426918.8262
134703266
127312122.4938
7391143.5062

## Checklist_Old (hidden)
Item No | Item Description | UOM | Tentative Scope | To be claimed in the month
|  |  |  | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | Check
103 | Operation and Maintenance of all temporary facilities including those mentioned in Item 101 & 102
a | Employer's Office | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
b | Vehicles
i | Bolero & Scorpio | No.-Quarterly | 96 |  |  | 6 |  |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  | 6 | 0
ii | Speed Boat | No.-Quarterly | 32 |  |  |  |  | 2 |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  | 2 | 0
iii | Rescue Boat | No.-Quarterly | 16 |  |  |  |  | 1 |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
c | Contractor's Office | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
d | Site Laboratory | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
e | Labour Camps | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
104 | Compliance of Environmental Management Plan (EMP)
a | Environmental Management Plan Implementation | Half Yearly | 8 | [6 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | 0
b | Implementation of Environmental Monitoring Program
i | Ambient Air Quality | Bi-Monthly | 24 |  | 1 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  | 1 | 1
ii | Noise Level | Bi-Monthly | 24 |  | 1 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  | 1 | 1
iii | Water Quality | Bi-Monthly | 24 |  | 1 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  | 1 | 1
iv | Soil Quality | Half Yearly | 8 | [6 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | 0
v | Ecology and Biodiversity | Half Yearly | 8 | [6 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | 0
c | Compliance of Environmental Clearance Conditions - EC identification no. EC22B039AS197455 | Half Yearly | 8 | [6 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | 0
d | Implementation of Environmental Management Plan - For Aquatic Ecology and Dolphin Conservation | Half Yearly | 8 | [6 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | 0
e | Dolphin Pinger for Dolphin Safety
ii | Maintenace of Equipment | No.-Quarterly | 480 |  |  | 30 |  |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  | 30 | 0
g | EMP provisions - During Construction Phase
i | Solid Waste Management accessories | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
ii | Health and Occupational Safety Management Plan | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
iii | Environmental Training Plan | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
iv | Traffic Management Plan | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
v | Emergency Preparedness Plan | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
vi | Miscellaneous (repair and maintenance) | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0
h | Provision for establishment of Sewage and Water Treatment Plant
i | Sewage Treatment Plant
2 | Maintenance | No.-Quarterly | 64 |  |  | 4 |  |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  | 4 | 0
ii | Waste Water Treatment Plant | [50 empty] | 0
2 | Maintenance | No.-Quarterly | 64 |  |  | 4 |  |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  | 4 | 0
iii | Silt Sedimentation Tank | [50 empty] | 0
2 | Maintenance | No.-Quarterly | 64 |  |  | 4 |  |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 |  | 4 | 0
iv | Effluent Treatment Plant | [50 empty] | 0
2 | Maintenance | No.-Quarterly | 32 |  |  | 2 |  |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  | 2 | 0
v | Toilets | [50 empty] | 0
2 | Maintenance | No.-Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 0

## MB Entry (hidden)
[13 empty] | 8876745246 | 33.02%
| Item No. | Item Description | UoM | Location | Executed Quantity | RFI No. / Letter No. | Date | IPC No. | Signed date | Remarks
| 204.d.ii.3 | Wetland Viaduct - Substructure - Documents & Reports - Issue of GFC Drawings | Nos. |  | 0.84615 | HBT/1624/SO/DGV/2026/1386 | 2026-02-05 | IPC - 30 | 2026-02-05 | 22/ 26 Nos. - Approved - WV2 - P0 to P21 - Balance 50% released |  |  |  | 33.02%
| 204.i.ii | Substructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.16 | HBT/1624/SO/DGV/2026/1396 | 2026-02-10 | IPC - 30 | 2026-02-10 | 4 / 25 Nos. - Approved - P27 to P30 |  |  |  | 33.02%
| 204.d.ii.3 | Wetland Viaduct - Substructure - Documents & Reports - Issue of GFC Drawings | Nos. |  | 0.15385 | HBT/1624/SO/LTR/2026/1452 | 2026-03-09 | IPC - 30 | 2026-03-09 | 4 / 26 Nos. - Approved- WV1 - P0 to P3 - Balance 50% released |  |  |  | 33.02%
| 204.j.iii | Superstructure of Main Bridge - Issue of GFC Drawings | Nos. |  | 0.16667 | HBT/1624/SO/DGV/2026/1464 | 2026-03-14 | IPC - 30 | 2026-03-14 | 4 / 24 Nos. - Submitted - P27 to P30 |  |  |  | 33.02%
| 408.b | Testing of Material | MT |  | 450.478 | MPSB/L&T/TIIC/2026/1543 | 2026-03-31 | IPC - 30 | 2026-03-31 |  |  |  |  | 33.02%
To be signed by RE | 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4308 | 2026-04-01 | IPC - 30 | 2026-04-01 | WV2-P13-P14-G7 | Suman |  |  | 33.02%
| 403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 0.525 | MPSB/Str/4311 | 2026-04-01 | IPC - 30 | 2026-04-02 | P8 - Lower Pylon - Starter |  |  |  | 33.02%
| 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4313 | 2026-04-02 | IPC - 30 | 2026-04-02 | WV2-P13-P14-G6 |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4323 | 2026-04-04 | IPC - 30 | 2026-04-05 | P14(N) - 12th Lift |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1449 | 2026-04-06 | IPC - 30 | 2026-04-07 | P8-BP-S16-M© |  |  |  | 33.02%
| 403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 0.515 | MPSB/Str/4319 | 2026-04-04 | IPC - 30 | 2026-04-08 | P26 - Lower Pylon - Starter |  |  |  | 33.02%
Ye to receive | 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1446 | 2026-04-06 | IPC - 30 | 2026-04-08 | P24-BP-S09-M |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1450 | 2026-04-06 | IPC - 30 | 2026-04-08 | P8-KS-S04-M |  |  |  | 33.02%
| 403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 0.63 | MPSB/Str/4333 | 2026-04-06 | IPC - 30 | 2026-04-08 | P22 - Lower Pylon - Starter |  |  |  | 33.02%
| 507.a.2 | Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3261 | 2026-04-08 | IPC - 30 | 2026-04-08 | PL20 |  |  |  | 33.02%
| 507.a.2 | Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3262 | 2026-04-08 | IPC - 30 | 2026-04-08 | PL18 |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1445 | 2026-04-06 | IPC - 30 | 2026-04-09 | P21-KS-S12-O |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1453 | 2026-04-07 | IPC - 30 | 2026-04-09 | P9-BP-S22a-O |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1467 | 2026-04-07 | IPC - 30 | 2026-04-09 | P23-KS-S08a-O |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1472 | 2026-04-08 | IPC - 30 | 2026-04-10 | P23-BP-S33-O© |  |  |  | 33.02%
| 403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 4 | MPSB/Str/4328 | 2026-04-05 | IPC - 30 | 2026-04-11 | P8 - Lower Pylon - 1st Lift |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.7 | MPSB/Str/4346 | 2026-04-07 | IPC - 30 | 2026-04-11 | P11 - 9th Lift |  |  |  | 33.02%
| 504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4347 | 2026-04-07 | IPC - 30 | 2026-04-11 | WV2-P12-P13 (G1 to G4) |  |  |  | 33.02%
| 504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4361 | 2026-04-10 | IPC - 30 | 2026-04-11 | WV2-P7-P8-G3 |  |  |  | 33.02%
| 507.a.2 | Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3278 | 2026-04-11 | IPC - 30 | 2026-04-11 | PL19 |  |  |  | 33.02%
Ye to receive | 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1486 | 2026-04-10 | IPC - 30 | 2026-04-12 | P24-BP-S10-M© |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1487 | 2026-04-10 | IPC - 30 | 2026-04-12 | P21-KS-S13-O© |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1490 | 2026-04-10 | IPC - 30 | 2026-04-12 | P9-KS-S09-O© |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1493 | 2026-04-11 | IPC - 30 | 2026-04-12 | P9-BP-S23a-O© |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4360 | 2026-04-10 | IPC - 30 | 2026-04-13 | P13 - 9th Lift |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.05 | MPSB/Str/4377 | 2026-04-11 | IPC - 30 | 2026-04-13 | P21 - 21st Lift |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1510 | 2026-04-12 | IPC - 30 | 2026-04-13 | P8-KS-S05-M |  |  |  | 33.02%
| 204.i.ii | Substructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.08 | HBT/1624/SO/DGV/2026/1547 | 2026-04-13 | IPC - 30 | 2026-04-13 | 2/25 Nos. - Approved - P13 to P14 |  |  |  | 33.02%
| 204.i.ii | Substructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.16 | HBT/1624/SO/DGV/2026/1548 | 2026-04-13 | IPC - 30 | 2026-04-13 | 4/25 Nos. - Approved - P15 to P18 |  |  |  | 33.02%
| 204.i.ii | Substructure of Main Bridge - Documents & Reports - Approval | Nos. |  | 0.12 | HBT/1624/SO/DGV/2026/1549 | 2026-04-13 | IPC - 30 | 2026-04-13 | 3/ 25 Nos. - Approved - P10 to P12A |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1500 | 2026-04-11 | IPC - 30 | 2026-04-14 | P23-BP-S34-O |  |  |  | 33.02%
| 502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Str/4379 | 2026-04-12 | IPC - 30 | 2026-04-14 | Km 5+464 - PL2 - Piercap |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1517 | 2026-04-13 | IPC - 30 | 2026-04-14 | P8-BP-S17-M |  |  |  | 33.02%
| 505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. |  | 1 | MPSB/Str/4403 | 2026-04-14 | IPC - 30 | 2026-04-14 | SAV-P0-P1-G5 |  |  |  | 33.02%
| 505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. |  | 1 | MPSB/Str/4404 | 2026-04-14 | IPC - 30 | 2026-04-14 | SAV-P0-P1-G6 |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4368 | 2026-04-11 | IPC - 30 | 2026-04-15 | P11 - 10th Lift |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1511 | 2026-04-13 | IPC - 30 | 2026-04-15 | P21-KS-S14-O |  |  |  | 33.02%
| 502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Str/4384 | 2026-04-13 | IPC - 30 | 2026-04-15 | Km 10+816 - PL6 - Piercap |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.2 | MPSB/Str/4394 | 2026-04-13 | IPC - 30 | 2026-04-15 | P14(N) - 13th Lift |  |  |  | 33.02%
Ye to receive | 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1513 | 2026-04-13 | IPC - 30 | 2026-04-16 | P24-BP-S11-M |  |  |  | 33.02%
| 504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4386 | 2026-04-13 | IPC - 30 | 2026-04-16 | WV2-P7-P8-G1 |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1524 | 2026-04-14 | IPC - 30 | 2026-04-16 | P9-BP-S24a-O |  |  |  | 33.02%
| 403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 2 | MPSB/Str/4408 | 2026-04-15 | IPC - 30 | 2026-04-16 | P8 - Lower Pylon - 2nd Lift |  |  |  | 33.02%
| 502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Str/4410 | 2026-04-16 | IPC - 30 | 2026-04-16 | Km 5+500 - PR3 - Piercap |  |  |  | 33.02%
| 505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. |  | 1 | MPSB/Str/4411 | 2026-04-16 | IPC - 30 | 2026-04-16 | SAV-P0-P1-G7 |  |  |  | 33.02%
| 505.b.3 | For Approach Viaduct - Final Stressing of Girders at site | Nos. |  | 1 | MPSB/Str/4412 | 2026-04-16 | IPC - 30 | 2026-04-16 | SAV-P0-P1-G8 |  |  |  | 33.02%
| 504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4382 | 2026-04-13 | IPC - 30 | 2026-04-17 | WV2-P11-P12 (G1 to G4) |  |  |  | 33.02%
| 502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Str/4399 | 2026-04-14 | IPC - 30 | 2026-04-17 | Km 10+780 - PL5 - Piercap |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1534 | 2026-04-15 | IPC - 30 | 2026-04-17 | P9-KS-S10-O |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1544 | 2026-04-16 | IPC - 30 | 2026-04-17 | P8-KS-S06-M |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1556 | 2026-04-17 | IPC - 30 | 2026-04-18 | P8-BP-S18-M |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1557 | 2026-04-17 | IPC - 30 | 2026-04-18 | P9-BP-S25a-O© |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1561 | 2026-04-17 | IPC - 30 | 2026-04-18 | P24-BP-S12-M© |  |  |  | 33.02%
| 402.b | Well Bottom Plugging | Nos. | Sualkuchi | 1 | MPSB/Str/4435 | 2026-04-18 | IPC - 30 | 2026-04-18 | P25 - Bottom Plugging |  |  |  | 33.02%
Ye to receive | 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1566 | 2026-04-17 | IPC - 30 | 2026-04-19 | P25-BP-S01a-O |  |  |  | 33.02%
| 504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4430 | 2026-04-17 | IPC - 30 | 2026-04-19 | WV2-P5-P6-G4 |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4417 | 2026-04-16 | IPC - 30 | 2026-04-20 | P13 - 10th Lift |  |  |  | 33.02%
| 502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Str/4432 | 2026-04-18 | IPC - 30 | 2026-04-20 | Km 11+068 - PR13 - Piercap |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1573 | 2026-04-18 | IPC - 30 | 2026-04-21 | P9-KS-S11-O© |  |  |  | 33.02%
| 706.a | Completion of the main structural works excluding finishing works - Culverts | Nos. | Palashbari | 0.5 | MPSB/Str/4438 | 2026-04-18 | IPC - 30 | 2026-04-21 | Km 4+914 - LHS |  |  |  | 33.02%
| 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4453 | 2026-04-20 | IPC - 30 | 2026-04-21 | WV2-P9-P10-G1 |  |  |  | 33.02%
| 104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/65 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30 | 2026-04-21 |  |  |  |  | 33.02%
| 104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/65 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30 | 2026-04-21 |  |  |  |  | 33.02%
| 104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Palashbari | 0.5 | MPSB/HSE/65 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30 | 2026-04-21 |  |  |  |  | 33.02%
| 104.b.i | Implementation of Environmental Monitoring Program - Ambient Air Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/66 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30 | 2026-04-21 |  |  |  |  | 33.02%
| 104.b.ii | Implementation of Environmental Monitoring Program - Noise Level | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/66 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30 | 2026-04-21 |  |  |  |  | 33.02%
| 104.b.iii | Implementation of Environmental Monitoring Program - Water Quality | Bi-Monthly | Sualkuchi | 0.5 | MPSB/HSE/66 Mar'26 - Apr'26 | 2026-04-21 | IPC - 30 | 2026-04-21 |  |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1570 | 2026-04-18 | IPC - 30 | 2026-04-22 | P8-KS-S07-M |  |  |  | 33.02%
| 502 & 503.b.2 | For Approach Viaduct - On completion of pier-cap / pier table | Nos. | Palashbari | 1 | MPSB/Str/4445 | 2026-04-19 | IPC - 30 | 2026-04-22 | Km 5+464 - PR2 - Piercap |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1585 | 2026-04-20 | IPC - 30 | 2026-04-22 | P9-BP-S26a-O |  |  |  | 33.02%
| 504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4454 | 2026-04-21 | IPC - 30 | 2026-04-22 | WV2-P5-P6-G3 |  |  |  | 33.02%
| 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4467 | 2026-04-22 | IPC - 30 | 2026-04-22 | WV2-P9-P10-G4 |  |  |  | 33.02%
| 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4469 | 2026-04-22 | IPC - 30 | 2026-04-22 | WV2-P9-P10-G2 |  |  |  | 33.02%
| 504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4437 | 2026-04-18 | IPC - 30 | 2026-04-23 | WV2-P10-P11 (G1 to G4)
| 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1594 | 2026-04-20 | IPC - 30 | 2026-04-23 | P24-BP-S13-M |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.6 | MPSB/Str/4443 | 2026-04-20 | IPC - 30 | 2026-04-23 | P15 - 19th Lift |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1606 | 2026-04-21 | IPC - 30 | 2026-04-23 | P9-KS-S12-O |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.8 | MPSB/Str/4456 | 2026-04-21 | IPC - 30 | 2026-04-24 | P14(N) - 14th Lift |  |  |  | 33.02%
| 502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Str/4458 | 2026-04-21 | IPC - 30 | 2026-04-24 | Km 10+924 - PR9 - Piercap |  |  |  | 33.02%
| 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4477 | 2026-04-24 | IPC - 30 | 2026-04-24 | WV2-P9-P10-G3 |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1618 | 2026-04-23 | IPC - 30 | 2026-04-25 | P9-BP-S27a-O© |  |  |  | 33.02%
| 403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 4 | MPSB/Str/4429 | 2026-04-17 | IPC - 30 | 2026-04-26 | P22 - Lower Pylon - 1st Lift |  |  |  | 33.02%
| 402.c | Well Cap | Nos. | Sualkuchi | 1 | MPSB/Str/4470 | 2026-04-23 | IPC - 30 | 2026-04-26 | P19 - Well Cap |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1621 | 2026-04-24 | IPC - 30 | 2026-04-26 | P9-KS-S13-O© |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1630 | 2026-04-24 | IPC - 30 | 2026-04-26 | P24-BP-S14-M© |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 1.85 | MPSB/Str/4476 | 2026-04-24 | IPC - 30 | 2026-04-26 | P17 - 20th Lift |  |  |  | 33.02%
| 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4489 | 2026-04-25 | IPC - 30 | 2026-04-26 | WV2-P8-P9-G1 |  |  |  | 33.02%
| 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4490 | 2026-04-25 | IPC - 30 | 2026-04-26 | WV2-P8-P9-G2 |  |  |  | 33.02%
| 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4491 | 2026-04-26 | IPC - 30 | 2026-04-26 | WV2-P8-P9-G3 |  |  |  | 33.02%
| 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4492 | 2026-04-26 | IPC - 30 | 2026-04-26 | WV2-P8-P9-G4 |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4474 | 2026-04-24 | IPC - 30 | 2026-04-27 | P11 - 11th Lift |  |  |  | 33.02%
| 504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4483 | 2026-04-25 | IPC - 30 | 2026-04-27 | WV2-P5-P6-G2 |  |  |  | 33.02%
| 506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4493 | 2026-04-26 | IPC - 30 | 2026-04-27 | PL12 to PL13 |  |  |  | 33.02%
| 204.c.ii | Drainage - Documents & Reports - Approval | Kms |  | 0.15 | HBT/1624/SO/DGV/2026/1577 | 2026-04-27 | IPC - 30 | 2026-04-27 | Km 0+950 to Km 1+100 |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1639 | 2026-04-25 | IPC - 30 | 2026-04-28 | P8-BP-S01-M |  |  |  | 33.02%
| 506.a.2 | For Wetland Viaduct - Deck Panel Erection | Span | Sualkuchi | 3 | MPSB/Str/4502 | 2026-04-28 | IPC - 30 | 2026-04-28 | PL18 to PL21 |  |  |  | 33.02%
| 506.a.2 | For Wetland Viaduct - Deck Panel Erection | Span | Sualkuchi | 3 | MPSB/Str/4503 | 2026-04-28 | IPC - 30 | 2026-04-28 | PL15 to PL18 |  |  |  | 33.02%
| 403.a | Construction of abutment / piers / lower pylon | Rmt | Palashbari | 2 | MPSB/Str/4515 | 2026-04-28 | IPC - 30 | 2026-04-28 | P8 - Lower Pylon - 3rd Lift |  |  |  | 33.02%
| 507.a.2 | Bearings - Installation | Nos. | Sualkuchi | 2 | MPSB/Sur/3375 | 2026-04-28 | IPC - 30 | 2026-04-28 | PL16 |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1645 | 2026-04-27 | IPC - 30 | 2026-04-29 | P24-BP-S15-M |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1652 | 2026-04-27 | IPC - 30 | 2026-04-29 | P9-KS-S14-O |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1653 | 2026-04-27 | IPC - 30 | 2026-04-29 | P9-BP-S28a-O |  |  |  | 33.02%
| 506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4501 | 2026-04-28 | IPC - 30 | 2026-04-29 | PL14 to PL15 |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1646 | 2026-04-27 | IPC - 30 | 2026-04-30 | P21-BP-S09a-O© |  |  |  | 33.02%
| 502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Str/4496 | 2026-04-27 | IPC - 30 | 2026-04-30 | Km 10+744 - PL4 - Piercap |  |  |  | 33.02%
| 504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4511 | 2026-04-28 | IPC - 30 | 2026-04-30 | WV2-P5-P6-G1 |  |  |  | 33.02%
| 403.a | Construction of abutment / piers / lower pylon | Rmt | Sualkuchi | 4 | MPSB/Str/4524 | 2026-04-28 | IPC - 30 | 2026-04-30 | P26 - Lower Pylon - 1st Lift |  |  |  | 33.02%
Ye to receive | 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1663 | 2026-04-29 | IPC - 30 | 2026-04-30 | P25-BP-S02a-O |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1665 | 2026-04-29 | IPC - 30 | 2026-04-30 | P8-BP-S02-M |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1667 | 2026-04-29 | IPC - 30 | 2026-04-30 | P9-KS-S22-O |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.7 | MPSB/Str/4528 | 2026-04-29 | IPC - 30 | 2026-04-30 | P13 - 11th Lift |  |  |  | 33.02%
| 505.a.3 | For Wetland Viaduct - Final stressing of Girders at site | Nos. | Sualkuchi | 1 | MPSB/Str/4529 | 2026-04-29 | IPC - 30 | 2026-04-30 | WV2-P7-P8-G4 |  |  |  | 33.02%
| 506.a.1 | For Wetland Viaduct - Casting of Deck Panel | Span | Sualkuchi | 1 | MPSB/Str/4531 | 2026-04-29 | IPC - 30 | 2026-04-30 | PL13 to PL14 |  |  |  | 33.02%
| 504.a.1 | For Wetland Viaduct - Casting of Girders in the precast yard | Nos. | Sualkuchi | 1 | MPSB/Str/4536 | 2026-04-29 | IPC - 30 | 2026-04-30 | WV2-P4-P5-G1 |  |  |  | 33.02%
Ye to receive | 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1671 | 2026-04-30 | IPC - 30 | 2026-04-30 | P25-BP-S03a-O |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1674 | 2026-04-30 | IPC - 30 | 2026-04-30 | P24-BP-S16-M© |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1675 | 2026-04-30 | IPC - 30 | 2026-04-30 | P24-BP-S17-M |  |  |  | 33.02%
| 406.a / 407.c | Precast - Box girder segments | Nos. | Sualkuchi | 1 | MPSB/MB/1676 | 2026-04-30 | IPC - 30 | 2026-04-30 | P21-BP-S10a-O |  |  |  | 33.02%
| 406.a / 407.c / 408.c | Precast - Box girder segments | Nos. | Palashbari | 1 | MPSB/MB/1680 | 2026-04-30 | IPC - 30 | 2026-04-30 | P9-KS-S15-O© |  |  |  | 33.02%
| 104.e.i | Dolphin Pinger for Dolphin Safety - Equipment Provision | Nos. |  | 10 | MPSB/Misc./99 | 2026-04-30 | IPC - 30 | 2026-04-30 |  |  |  |  | 33.02%
| 502 & 503.a.2 | For Wetland Viaduct - On completion of pier-cap / pier table | Nos. | Sualkuchi | 1 | MPSB/Str/4540 | 2026-04-30 | IPC - 30 | 2026-04-30 | Km 11+032 - PR12 - Piercap |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4544 | 2026-04-30 | IPC - 30 | 2026-04-30 | P13 - 12th Lift |  |  |  | 33.02%
| 504.a.2 | For Wetland Viaduct - Erection of Girders at site | Nos. | Sualkuchi | 4 | MPSB/Str/4551 | 2026-04-30 | IPC - 30 | 2026-04-30 | WV2-P9-P10 (G1 to G4) | Suman |  |  | 33.02%
| 606.d | For Vehicular Underpass - Completion of Box Slab | Nos. | Palashbari | 1 | MPSB/Str/4556 | 2026-04-30 | IPC - 30 | 2026-04-30 | Km 0+814 - LHS |  |  |  | 33.02%
| 604.c | For Vehicular Underpass - Construction of Abutment / Pier Cap | Nos. | Palashbari | 0.5 | MPSB/Str/4559 | 2026-04-30 | IPC - 30 | 2026-04-30 | Km 4+480 - LHS - A2 - Piercap |  |  |  | 33.02%
| 604.c | For Vehicular Underpass - Construction of Abutment / Pier Cap | Nos. | Palashbari | 0.5 | MPSB/Str/4561 | 2026-04-30 | IPC - 30 | 2026-04-30 | Km 4+480 - RHS - A2 - Piercap |  |  |  | 33.02%
| 402.b | Well Bottom Plugging | Nos. | Palashbari | 1 | MPSB/Str/4565 | 2026-04-30 | IPC - 30 | 2026-04-30 | P7 - Bottom Plugging |  |  |  | 33.02%
| 501.b.2 | For Approach Viaduct - On completion of Well | Rmt | Palashbari | 2.5 | MPSB/Str/4566 | 2026-04-30 | IPC - 30 | 2026-04-30 | P5 - 16th Lift |  |  |  | 33.02%
| 402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | Palashbari | 2.5 | MPSB/Str/4568 | 2026-04-30 | IPC - 30 | 2026-04-30 | P30 - 17th Lift |  |  |  | 33.02%
| 507.a.1 | Bearings - Material Testing and Procurement | Nos. |  | 60 | As per attachments |  | IPC - 30 | [5 empty] | 33.02%
33.02%
[5 empty] | 45 | [8 empty] | 33.02%
[5 empty] | 16 | [8 empty] | 33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
To be signed by RE | [13 empty] | 33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
To be signed by RE | [13 empty] | 33.02%
33.02%
33.02%
To be signed by RE | [13 empty] | 33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
33.02%
[12 empty] | 0 | 0 | 33.02%
[12 empty] | 0 | 0 | 33.02%
[12 empty] | 0 | 0 | 33.02%
[12 empty] | 0 | 0 | 33.02%
[12 empty] | 0 | 0 | 33.02%
[12 empty] | 0 | 0 | 33.02%
[12 empty] | 0 | 0 | 33.02%
[12 empty] | 0 | 0 | 33.02%

## Checklist_New
Item No | Item Description | UOM | Tentative Scope | To be claimed in the month
|  |  |  | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | Check
103 | Operation and Maintenance of all temporary facilities including those mentioned in Item 101 & 102
a | Employer's Office | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
b | Vehicles
i | Bolero & Scorpio | Nos.-Quarterly | 96 |  |  | 6 |  |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  |  | 6 | 0
ii | Speed Boat | Nos.-Quarterly | 32 |  |  |  |  | 2 |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 | 0
iii | Rescue Boat | Nos.-Quarterly | 16 |  |  |  |  | 1 |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
c | Contractor's Office | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
d | Site Laboratory | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
e | Labour Camps | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
104 | Compliance of Environmental Management Plan (EMP)
a | Environmental Management Plan Implementation | Half Yearly | 8 | [6 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 0
b | Implementation of Environmental Monitoring Program
i | Ambient Air Quality | Bi-Monthly | 24 |  | 1 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 0
ii | Noise Level | Bi-Monthly | 24 |  | 1 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 0
iii | Water Quality | Bi-Monthly | 24 |  | 1 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 0
iv | Soil Quality | Half Yearly | 8 | [6 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 0
v | Ecology and Biodiversity | Half Yearly | 8 | [6 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 0
c | Compliance of Environmental Clearance Conditions - EC identification no. EC22B039AS197455 | Half Yearly | 8 | [6 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 0
d | Implementation of Environmental Management Plan - For Aquatic Ecology and Dolphin Conservation | Half Yearly | 8 | [6 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | [5 empty] | 1 | 0
e | Dolphin Pinger for Dolphin Safety
ii | Maintenace of Equipment | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
g | EMP provisions - During Construction Phase
i | Solid Waste Management accessories | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
ii | Health and Occupational Safety Management Plan | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
iii | Environmental Training Plan | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
iv | Traffic Management Plan | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
v | Emergency Preparedness Plan | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
vi | Miscellaneous (repair and maintenance) | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
h | Provision for establishment of Sewage and Water Treatment Plant
i | Sewage Treatment Plant
2 | Maintenance | Quarterly | 15 | [6 empty] | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
ii | Waste Water Treatment Plant
2 | Maintenance | Quarterly | 10 | [21 empty] | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0
iii | Silt Sedimentation Tank
2 | Maintenance | Quarterly | 12 | [9 empty] | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 0
iv | Effluent Treatment Plant
2 | Maintenance | Quarterly | 4 | [36 empty] | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  | 0
v | Toilets
2 | Maintenance | Quarterly | 16 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 0

## Pile Details
|  | X | Y
P0 | 12 | Km 10+600 - PL0/P1 | PL0/P1 - WV2 | P0 | Km 10+230 - PL0/P1 | PL0/P1 - WV1
P1 | 8 | Km 10+600 - PL0/P2 | PL0/P2 - WV2 | P0 | Km 10+230 - PL0/P2 | PL0/P2 - WV1
P2 | 8 | Km 10+600 - PL0/P3 | PL0/P3 - WV2 | P0 | Km 10+230 - PL0/P3 | PL0/P3 - WV1
P3 | 10 | Km 10+600 - PL0/P4 | PL0/P4 - WV2 | P0 | Km 10+230 - PL0/P4 | PL0/P4 - WV1
P4 | 8 | Km 10+600 - PL0/P5 | PL0/P5 - WV2 | P0 | Km 10+230 - PL0/P5 | PL0/P5 - WV1
P5 | 8 | Km 10+600 - PL0/P6 | PL0/P6 - WV2 | P0 | Km 10+230 - PL0/P6 | PL0/P6 - WV1
P6 | 10 | Km 10+600 - PR0/P1 | PR0/P1 - WV2 | P0 | Km 10+230 - PR0/P1 | PR0/P1 - WV1
P7 | 8 | Km 10+600 - PR0/P2 | PR0/P2 - WV2 | P0 | Km 10+230 - PR0/P2 | PR0/P2 - WV1
P8 | 8 | Km 10+600 - PR0/P3 | PR0/P3 - WV2 | P0 | Km 10+230 - PR0/P3 | PR0/P3 - WV1
P9 | 10 | Km 10+600 - PR0/P4 | PR0/P4 - WV2 | P0 | Km 10+230 - PR0/P4 | PR0/P4 - WV1
P10 | 8 | Km 10+600 - PR0/P5 | PR0/P5 - WV2 | P0 | Km 10+230 - PR0/P5 | PR0/P5 - WV1
P11 | 8 | Km 10+600 - PR0/P6 | PR0/P6 - WV2 | P0 | Km 10+230 - PR0/P6 | PR0/P6 - WV1
P12 | 10 | Km 10+636 - PL1/P1 | PL1/P1 - WV2 | P1 | Km 10+266 - PL1/P1 | PL1/P1 - WV1
P13 | 8 | Km 10+636 - PL1/P2 | PL1/P2 - WV2 | P1 | Km 10+266 - PL1/P2 | PL1/P2 - WV1
P14 | 8 | Km 10+636 - PL1/P3 | PL1/P3 - WV2 | P1 | Km 10+266 - PL1/P3 | PL1/P3 - WV1
P15 | 10 | Km 10+636 - PL1/P4 | PL1/P4 - WV2 | P1 | Km 10+266 - PL1/P4 | PL1/P4 - WV1
P16 | 8 | Km 10+636 - PR1/P1 | PR1/P1 - WV2 | P1 | Km 10+266 - PL2/P2 | PL2/P2 - WV1
P17 | 8 | Km 10+636 - PR1/P2 | PR1/P2 - WV2 | P1 | Km 10+266 - PR1/P1 | PR1/P1 - WV1
P18 | 10 | Km 10+636 - PR1/P3 | PR1/P3 - WV2 | P1 | Km 10+266 - PR1/P2 | PR1/P2 - WV1
P19 | 8 | Km 10+636 - PR1/P4 | PR1/P4 - WV2 | P1 | Km 10+266 - PR1/P3 | PR1/P3 - WV1
P20 | 8 | Km 10+672 - PL2/P1 | PL2/P1 - WV2 | P2 | Km 10+266 - PR1/P4 | PR1/P4 - WV1
P21 | 12 | Km 10+672 - PL2/P2 | PL2/P2 - WV2 | P2 | Km 10+302 - PL2/P1 | PL2/P1 - WV1
|  | Km 10+672 - PL2/P3 | PL2/P3 - WV2 | P2 | Km 10+302 - PL2/P3 | PL2/P3 - WV1
|  | Km 10+672 - PL2/P4 | PL2/P4 - WV2 | P2 | Km 10+302 - PL2/P4 | PL2/P4 - WV1
|  | Km 10+672 - PR2/P1 | PR2/P1 - WV2 | P2 | Km 10+302 - PR2/P1 | PR2/P1 - WV1
|  | Km 10+672 - PR2/P2 | PR2/P2 - WV2 | P2 | Km 10+302 - PR2/P2 | PR2/P2 - WV1
|  | Km 10+672 - PR2/P3 | PR2/P3 - WV2 | P2 | Km 10+302 - PR2/P3 | PR2/P3 - WV1
|  | Km 10+672 - PR2/P4 | PR2/P4 - WV2 | P2 | Km 10+302 - PR2/P4 | PR2/P4 - WV1
|  | Km 10+708 - PL3/P1 | PL3/P1 - WV2 | P3 | Km 10+338 - PL3/P1 | PL3/P1 - WV1
|  | Km 10+708 - PL3/P2 | PL3/P2 - WV2 | P3 | Km 10+338 - PL3/P2 | PL3/P2 - WV1
|  | Km 10+708 - PL3/P3 | PL3/P3 - WV2 | P3 | Km 10+338 - PL3/P3 | PL3/P3 - WV1
|  | Km 10+708 - PL3/P4 | PL3/P4 - WV2 | P3 | Km 10+338 - PL3/P4 | PL3/P4 - WV1
|  | Km 10+708 - PL3/P5 | PL3/P5 - WV2 | P3 | Km 10+338 - PL3/P5 | PL3/P5 - WV1
|  | Km 10+708 - PR3/P1 | PR3/P1 - WV2 | P3 | Km 10+338 - PL3/P6 | PL3/P6 - WV1
|  | Km 10+708 - PR3/P2 | PR3/P2 - WV2 | P3 | Km 10+338 - PR3/P1 | PR3/P1 - WV1
|  | Km 10+708 - PR3/P3 | PR3/P3 - WV2 | P3 | Km 10+338 - PR3/P2 | PR3/P2 - WV1
|  | Km 10+708 - PR3/P4 | PR3/P4 - WV2 | P3 | Km 10+338 - PR3/P3 | PR3/P3 - WV1
|  | Km 10+708 - PR3/P5 | PR3/P5 - WV2 | P3 | Km 10+338 - PR3/P4 | PR3/P4 - WV1
|  | Km 10+744 - PL4/P1 | PL4/P1 - WV2 | P4 | Km 10+338 - PR3/P5 | PR3/P5 - WV1
|  | Km 10+744 - PL4/P2 | PL4/P2 - WV2 | P4 | Km 10+338 - PR3/P6 | PR3/P6 - WV1
|  | Km 10+744 - PL4/P3 | PL4/P3 - WV2 | P4
|  | Km 10+744 - PL4/P4 | PL4/P4 - WV2 | P4
|  | Km 10+744 - PR4/P1 | PR4/P1 - WV2 | P4
|  | Km 10+744 - PR4/P2 | PR4/P2 - WV2 | P4
|  | Km 10+744 - PR4/P3 | PR4/P3 - WV2 | P4
|  | Km 10+744 - PR4/P4 | PR4/P4 - WV2 | P4
|  | Km 10+780 - PL5/P1 | PL5/P1 - WV2 | P5
|  | Km 10+780 - PL5/P2 | PL5/P2 - WV2 | P5
|  | Km 10+780 - PL5/P3 | PL5/P3 - WV2 | P5
|  | Km 10+780 - PL5/P4 | PL5/P4 - WV2 | P5
|  | Km 10+780 - PR5/P1 | PR5/P1 - WV2 | P5
|  | Km 10+780 - PR5/P2 | PR5/P2 - WV2 | P5
|  | Km 10+780 - PR5/P3 | PR5/P3 - WV2 | P5
|  | Km 10+780 - PR5/P4 | PR5/P4 - WV2 | P5
|  | Km 10+816 - PL6/P1 | PL6/P1 - WV2 | P6
|  | Km 10+816 - PL6/P2 | PL6/P2 - WV2 | P6
|  | Km 10+816 - PL6/P3 | PL6/P3 - WV2 | P6
|  | Km 10+816 - PL6/P4 | PL6/P4 - WV2 | P6
|  | Km 10+816 - PL6/P5 | PL6/P5 - WV2 | P6
|  | Km 10+816 - PR6/P1 | PR6/P1 - WV2 | P6
|  | Km 10+816 - PR6/P2 | PR6/P2 - WV2 | P6
|  | Km 10+816 - PR6/P3 | PR6/P3 - WV2 | P6
|  | Km 10+816 - PR6/P4 | PR6/P4 - WV2 | P6
|  | Km 10+816 - PR6/P5 | PR6/P5 - WV2 | P6
|  | Km 10+852 - PL7/P1 | PL7/P1 - WV2 | P7
|  | Km 10+852 - PL7/P2 | PL7/P2 - WV2 | P7
|  | Km 10+852 - PL7/P3 | PL7/P3 - WV2 | P7
|  | Km 10+852 - PL7/P4 | PL7/P4 - WV2 | P7
|  | Km 10+852 - PR7/P1 | PR7/P1 - WV2 | P7
|  | Km 10+852 - PR7/P2 | PR7/P2 - WV2 | P7
|  | Km 10+852 - PR7/P3 | PR7/P3 - WV2 | P7
|  | Km 10+852 - PR7/P4 | PR7/P4 - WV2 | P7
|  | Km 10+888 - PL8/P1 | PL8/P1 - WV2 | P8
|  | Km 10+888 - PL8/P2 | PL8/P2 - WV2 | P8
|  | Km 10+888 - PL8/P3 | PL8/P3 - WV2 | P8
|  | Km 10+888 - PL8/P4 | PL8/P4 - WV2 | P8
|  | Km 10+888 - PR8/P1 | PR8/P1 - WV2 | P8
|  | Km 10+888 - PR8/P2 | PR8/P2 - WV2 | P8
|  | Km 10+888 - PR8/P3 | PR8/P3 - WV2 | P8
|  | Km 10+888 - PR8/P4 | PR8/P4 - WV2 | P8
|  | Km 10+924 - PL9/P1 | PL9/P1 - WV2 | P9
|  | Km 10+924 - PL9/P2 | PL9/P2 - WV2 | P9
|  | Km 10+924 - PL9/P3 | PL9/P3 - WV2 | P9
|  | Km 10+924 - PL9/P4 | PL9/P4 - WV2 | P9
|  | Km 10+924 - PL9/P5 | PL9/P5 - WV2 | P9
|  | Km 10+924 - PR9/P1 | PR9/P1 - WV2 | P9
|  | Km 10+924 - PR9/P2 | PR9/P2 - WV2 | P9
|  | Km 10+924 - PR9/P3 | PR9/P3 - WV2 | P9
|  | Km 10+924 - PR9/P4 | PR9/P4 - WV2 | P9
|  | Km 10+924 - PR9/P5 | PR9/P5 - WV2 | P9
|  | Km 10+960 - PL10/P1 | PL10/P1 - WV2 | P10
|  | Km 10+960 - PL10/P2 | PL10/P2 - WV2 | P10
|  | Km 10+960 - PL10/P3 | PL10/P3 - WV2 | P10
|  | Km 10+960 - PL10/P4 | PL10/P4 - WV2 | P10
|  | Km 10+960 - PR10/P1 | PR10/P1 - WV2 | P10
|  | Km 10+960 - PR10/P2 | PR10/P2 - WV2 | P10
|  | Km 10+960 - PR10/P3 | PR10/P3 - WV2 | P10
|  | Km 10+960 - PR10/P4 | PR10/P4 - WV2 | P10
|  | Km 10+996 - PL11/P1 | PL11/P1 - WV2 | P11
|  | Km 10+996 - PL11/P2 | PL11/P2 - WV2 | P11
|  | Km 10+996 - PL11/P3 | PL11/P3 - WV2 | P11
|  | Km 10+996 - PL11/P4 | PL11/P4 - WV2 | P11
|  | Km 10+996 - PR11/P1 | PR11/P1 - WV2 | P11
|  | Km 10+996 - PR11/P2 | PR11/P2 - WV2 | P11
|  | Km 10+996 - PR11/P3 | PR11/P3 - WV2 | P11
|  | Km 10+996 - PR11/P4 | PR11/P4 - WV2 | P11
|  | Km 11+032 - PL12/P1 | PL12/P1 - WV2 | P12
|  | Km 11+032 - PL12/P2 | PL12/P2 - WV2 | P12
|  | Km 11+032 - PL12/P3 | PL12/P3 - WV2 | P12
|  | Km 11+032 - PL12/P4 | PL12/P4 - WV2 | P12
|  | Km 11+032 - PL12/P5 | PL12/P5 - WV2 | P12
|  | Km 11+032 - PR12/P1 | PR12/P1 - WV2 | P12
|  | Km 11+032 - PR12/P2 | PR12/P2 - WV2 | P12
|  | Km 11+032 - PR12/P3 | PR12/P3 - WV2 | P12
|  | Km 11+032 - PR12/P4 | PR12/P4 - WV2 | P12
|  | Km 11+032 - PR12/P5 | PR12/P5 - WV2 | P12
|  | Km 11+068 - PL13/P1 | PL13/P1 - WV2 | P13
|  | Km 11+068 - PL13/P2 | PL13/P2 - WV2 | P13
|  | Km 11+068 - PL13/P3 | PL13/P3 - WV2 | P13
|  | Km 11+068 - PL13/P4 | PL13/P4 - WV2 | P13
|  | Km 11+068 - PR13/P1 | PR13/P1 - WV2 | P13
|  | Km 11+068 - PR13/P2 | PR13/P2 - WV2 | P13
|  | Km 11+068 - PR13/P3 | PR13/P3 - WV2 | P13
|  | Km 11+068 - PR13/P4 | PR13/P4 - WV2 | P13
|  | Km 11+104 - PL14/P1 | PL14/P1 - WV2 | P14
|  | Km 11+104 - PL14/P2 | PL14/P2 - WV2 | P14
|  | Km 11+104 - PL14/P3 | PL14/P3 - WV2 | P14
|  | Km 11+104 - PL14/P4 | PL14/P4 - WV2 | P14
|  | Km 11+104 - PR14/P1 | PR14/P1 - WV2 | P14
|  | Km 11+104 - PR14/P2 | PR14/P2 - WV2 | P14
|  | Km 11+104 - PR14/P3 | PR14/P3 - WV2 | P14
|  | Km 11+104 - PR14/P4 | PR14/P4 - WV2 | P14
|  | Km 11+140 - PL15/P1 | PL15/P1 - WV2 | P15
|  | Km 11+140 - PL15/P2 | PL15/P2 - WV2 | P15
|  | Km 11+140 - PL15/P3 | PL15/P3 - WV2 | P15
|  | Km 11+140 - PL15/P4 | PL15/P4 - WV2 | P15
|  | Km 11+140 - PL15/P5 | PL15/P5 - WV2 | P15
|  | Km 11+140 - PR15/P1 | PR15/P1 - WV2 | P15
|  | Km 11+140 - PR15/P2 | PR15/P2 - WV2 | P15
|  | Km 11+140 - PR15/P3 | PR15/P3 - WV2 | P15
|  | Km 11+140 - PR15/P4 | PR15/P4 - WV2 | P15
|  | Km 11+140 - PR15/P5 | PR15/P5 - WV2 | P15
|  | Km 11+176 - PL16/P1 | PL16/P1 - WV2 | P16
|  | Km 11+176 - PL16/P2 | PL16/P2 - WV2 | P16
|  | Km 11+176 - PL16/P3 | PL16/P3 - WV2 | P16
|  | Km 11+176 - PL16/P4 | PL16/P4 - WV2 | P16
|  | Km 11+176 - PR16/P1 | PR16/P1 - WV2 | P16
|  | Km 11+176 - PR16/P2 | PR16/P2 - WV2 | P16
|  | Km 11+176 - PR16/P3 | PR16/P3 - WV2 | P16
|  | Km 11+176 - PR16/P4 | PR16/P4 - WV2 | P16
|  | Km 11+212 - PL17/P1 | PL17/P1 - WV2 | P17
|  | Km 11+212 - PL17/P2 | PL17/P2 - WV2 | P17
|  | Km 11+212 - PL17/P3 | PL17/P3 - WV2 | P17
|  | Km 11+212 - PL17/P4 | PL17/P4 - WV2 | P17
|  | Km 11+212 - PR17/P1 | PR17/P1 - WV2 | P17
|  | Km 11+212 - PR17/P2 | PR17/P2 - WV2 | P17
|  | Km 11+212 - PR17/P3 | PR17/P3 - WV2 | P17
|  | Km 11+212 - PR17/P4 | PR17/P4 - WV2 | P17
|  | Km 11+248 - PL18/P1 | PL18/P1 - WV2 | P18
|  | Km 11+248 - PL18/P2 | PL18/P2 - WV2 | P18
|  | Km 11+248 - PL18/P3 | PL18/P3 - WV2 | P18
|  | Km 11+248 - PL18/P4 | PL18/P4 - WV2 | P18
|  | Km 11+248 - PL18/P5 | PL18/P5 - WV2 | P18
|  | Km 11+248 - PR18/P1 | PR18/P1 - WV2 | P18
|  | Km 11+248 - PR18/P2 | PR18/P2 - WV2 | P18
|  | Km 11+248 - PR18/P3 | PR18/P3 - WV2 | P18
|  | Km 11+248 - PR18/P4 | PR18/P4 - WV2 | P18
|  | Km 11+248 - PR18/P5 | PR18/P5 - WV2 | P18
|  | Km 11+284 - PL19/P1 | PL19/P1 - WV2 | P19
|  | Km 11+284 - PL19/P2 | PL19/P2 - WV2 | P19
|  | Km 11+284 - PL19/P3 | PL19/P3 - WV2 | P19
|  | Km 11+284 - PL19/P4 | PL19/P4 - WV2 | P19
|  | Km 11+284 - PR19/P1 | PR19/P1 - WV2 | P19
|  | Km 11+284 - PR19/P2 | PR19/P2 - WV2 | P19
|  | Km 11+284 - PR19/P3 | PR19/P3 - WV2 | P19
|  | Km 11+284 - PR19/P4 | PR19/P4 - WV2 | P19
|  | Km 11+320 - PL20/P1 | PL20/P1 - WV2 | P20
|  | Km 11+320 - PL20/P2 | PL20/P2 - WV2 | P20
|  | Km 11+320 - PL20/P3 | PL20/P3 - WV2 | P20
|  | Km 11+320 - PL20/P4 | PL20/P4 - WV2 | P20
|  | Km 11+320 - PR20/P1 | PR20/P1 - WV2 | P20
|  | Km 11+320 - PR20/P2 | PR20/P2 - WV2 | P20
|  | Km 11+320 - PR20/P3 | PR20/P3 - WV2 | P20
|  | Km 11+320 - PR20/P4 | PR20/P4 - WV2 | P20
|  | Km 11+356 - PL21/P1 | PL21/P1 - WV2 | P21
|  | Km 11+356 - PL21/P2 | PL21/P2 - WV2 | P21
|  | Km 11+356 - PL21/P3 | PL21/P3 - WV2 | P21
|  | Km 11+356 - PL21/P4 | PL21/P4 - WV2 | P21
|  | Km 11+356 - PL21/P5 | PL21/P5 - WV2 | P21
|  | Km 11+356 - PL21/P6 | PL21/P6 - WV2 | P21
|  | Km 11+356 - PR21/P1 | PR21/P1 - WV2 | P21
|  | Km 11+356 - PR21/P2 | PR21/P2 - WV2 | P21
|  | Km 11+356 - PR21/P3 | PR21/P3 - WV2 | P21
|  | Km 11+356 - PR21/P4 | PR21/P4 - WV2 | P21
|  | Km 11+356 - PR21/P5 | PR21/P5 - WV2 | P21
|  | Km 11+356 - PR21/P6 | PR21/P6 - WV2 | P21

## Expl.
Construction of 4-lane Extra-dosed PSC Bridge over river Brahmaputra connecting Palashbari and Sualkuchi including Viaduct, Approaches and River Training works etc on EPC mode
Statement on dedcution against P12 & P14 Toppled Well Foundations
Item No. | Item Description | UOM | Unit Rate | Work Done & Measured Qty |  |  |  | Deducted against toppled P12 & P14 Well foundations |  | Cumulative Qty. certified in IPC-26
|  |  |  | Up to Dec'25 | Jan'26 | Cumulative | Amoumt | Qty | Amount | Qty | Amount
|  |  | A | B | C | D = B+C | E = A*D | F | G = A*F | H | I = A*H
401.a | Fabrication of Cutting Edge | Nos. | 1150470.4 | 1 | 1 | 2 | 2300940.8 | -2 | -2300940.8 | 0 | 0
401.b | Ground preparation and placing of Cutting Edge | Nos. | 287617.6 | 1 | 3 | 4 | 1150470.4 | -2 | -575235.2 | 2 | 575235.2
401.c | Shuttering and scaffolding | Nos. | 1438088 | 1 | 3 | 4 | 5752352 | -2 | -2876176 | 2 | 2876176
402.a | Well Steining - Casting & Sinking (Including Well curb) | Rmt | 4029137.5334 | 1 | 87.64 | 88.64 | 357142750.9625 | -43.73 | -176194184.3365 | 44.91 | 180948566.6259
| Total | [5 empty] | 366346514.1625 |  | -181946536.3365 |  | 184399977.8259

## Mandate Documents (hidden)
Documents required for Interim Payment Certificate
Item No. | Sub-Item No. | Item Description | Mandate Documents
101 | a,b,c,d,e | Provision (construction) of office facilities for the Employer | Layout Submission
Layout Approval
Approved RFI's for each activity
Land Agreement Copies
| f.i | Completion of Finishing Works - Office Furniture | Invoice of Furniture
| f.ii | Completion of Finishing Works - Office Equipment | Invoice of Equipment
| f.iii | Completion of Finishing Works - Vehicles | Invoice of Vehicles
102 | a,b,c,d,e,f | Provision (construction) of contractor’s site office, site laboratories, labor camps etc | Layout Submission
Layout Approval
Approved RFI's for each activity
Land Agreement Copies
| f.i | Completion of Finishing Works - Office | Furniture Receipt
| f.ii | Completion of Finishing Works - Laboratory | Lab equipment receipt
103 |  | Operation and Maintenance of all temporary facilities including those mentioned in Item 101 & 102
| a | Employer's Office
| b | Vehicles | Availability of Vehicles
| c | Contractor's Office
| d | Site Laboratory | Availability of Equipment with Calibration
| e | Labour Camps
104 |  | Compliance of Environmental Management Plan (EMP)
| a | Environmental Management Plan Implementation - Preconstruction / Construction / Operation Phase of the project | EMP Submission
EMP Approval
EMP Adherence
| b | Implementation of Environmental Monitoring Program | Submission of Air, Water, Noise, Soil, Ecology and Biodiversity reports as per the frequency
| c | Compliance of Environmental Clearance Conditions - EC identification no. EC22B039AS197455
| d | Implementation of Environmental Management Plan - For Aquatic Ecology and Dolphin Conservation | Status of Implementation
| e | Dolphin Pinger for Dolphin Safety | Inspection of Pinger at stores
Installation of Pinger at site
| f | Wetland Restoration - Clearance of Eutrophication, Water area, etc | Restoration Plan submission
Restoration Plan Approval
| g | EMP provisions - During Construction Phase
| i | Solid Waste Management accessories | Inspection of accessories received
| ii | Health and Occupational Safety Management Plan | PPE's adherence / Health Checkup details / Fire management / Sign boards
| iii | Environmental Training Plan | Induction Register / Followed by training register
| iv | Traffic Management Plan | Traffic Plan submission and management at site
| v | Emergency Preparedness Plan | Emergency Plan submission and preparedness at site
| vi | Miscellaneous (repair and maintenance)
| h | Provision for establishment of Sewage and Water Treatment Plant
| i | Sewage Treatment Plant | Inspection of Plant receipt at site / Installation of the same
| ii | Waste Water Treatment Plant | Inspection of Plant receipt at site / Installation of the same
| iii | Silt Sedimentation Tank | RFIs for construction of Sedimentation tank
| iv | Effluent Treatment Plant | Inspection of Plant receipt at site / Installation of the same
| v | Toilets | RFIs for construction of Toilets
105 |  | Demobilization of the Site on completion of the Works as per the General Specifications
| a | Employer's Office | Upon dismantling and demobilization
| b | Contractor's Office
| c | Site Laboratory
| d | Labour Camps
201 |  | Site survey, establishment of bench marks, validation of ROW, identification of borrow areas.
| a | Establishment of Bench Marks | RFIs for the activity, for the entire stretch
| b | Completion of Site Survey | RFIs for the activity, for the entire stretch
| c | Validation of ROW | RFIs for the activity, for the entire stretch
| d | Identification of Borrow Areas
202 |  | Site data collection, Detailed Geotechnical and Hydrological investigations and report submission & approval
| a | Completion of Topographical Survey (Site data collection) | RFI's for the activity, for the entire stretch / Submission / Approval
| b | Detailed Geotechnical Investigation | RFI's for the activity, for the entire stretch / Submission / Approval
| c | Detailed Hydrological Investigation | RFI's for the activity, for the entire stretch / Submission
203 |  | Preliminary Design of the approach formations, retaining structures, drainage system, bridges, major and /or minor structure and miscellaneous work.
| a | Approach Formations (GAD / P&P) | Drawings Submission / Approval
| b | Retaining Structures (GAD / P&P)
| c | Drainage (GAD / P&P)
| d | Wetland Viaducts (GAD / P&P)
| e | Approach Viaducts (GAD / P&P)
| f | Vehicular Underpass (GAD / P&P)
| g | Culverts (GAD)
| h | Major Bridge (GAD)
| i | Miscellaneous Works
204 |  | Final Technical Design of the approach formation, retaining structures, drainage system, bridges, major and /or minor structures and miscellaneous work
| a | Approach Formations | Drawings Submission / Approval / GFC Issuance
| b | Retaining Structures
| c | Drainage
| d | Wetland Viaducts
| e | Approach Viaducts
| f | Vehicular Underpass
| g | Culverts
| h | Foundation of Major Bridge
| i | Substructure of Major Bridge
| j | Superstructure of Major Bridge
| k | Miscellaneous works
205 |  | Setting out of the Final Alignment with location of all structures, approach formation work and Miscellaneous work | Drawings Submission / Approval / GFC Issuance
206 |  | Preparation of As-Built Drawings | Drawings Submission
301 |  | Construction of temporary jetties/ platforms (TAB) / load out jetties etc for marine working | Drawings Submission
Drawings Approval
Inspection of material receipt at site
Method Statement for execution of TAB
RFIs for installation of TAB
302 |  | Establishment of batching plant, crusher (if any), rebar yards, formwork shops, fabrication shops etc for main works
| a | Establishment of Batching Plants | Inspection of Batching Plant receipt at site / RFIs for completion of foundation / Installation & commissioning of Batching Plant
| b | Establishment of Crusher Plant | Inspection of Crusher Plant receipt at site / RFIs for completion of foundation / Installation & commissioning of Crusher Plant
| c | Commissioning of Rebar & Formwork Yard
| d | Commissioning of Fabrication Yard
303 |  | Establishment of Casting yards for casting of PSC Box girders, I-Girders etc as per requirement | RFIs for Area Development / Foundation of Gantry track / Casting bed foundation / Stacking bed foundation / Finishing and commissioning
304 |  | Supply and installation of moulds, gantries etc for precast works
| a | Moulds | Inspection of material receipt at site / RFIs for fabrication and commissioning
| b | Gantry | Inspection of equipment receipt at site / Installation and commissioning
305 |  | Supply and commissioning of Bridge Builders/Launchers for erection of bridge deck | Inspection of equipment receipt at site / Installation and commissioning
306 |  | Procurement/Mobilization of Marine Equipment’s (Barges/Tugs etc) for working in water | Inspection of equipment receipt at site / Installation and commissioning
307 |  | Removal of temporary jetties, platforms, load out jetties and casting yards | Upon dismantling and demobilization