## README
Palashbari–Sualkuchi Extradosed Bridge · Schedule 4 RFI → IFC element register
Built from IPC-34 MB ENTRY (period 1–31 Jul 2026). Generated 25-Sep-2026 by rfi_to_model_status.py
WHAT THIS IS
Element_Register lists EVERY element that will exist in the IFC model (1,116 segments, every well lift, plug, cap, lower-pylon lift), not only the ones with RFIs.
Each element has one Element_Key. Put that exact key into the Revit element as a shared parameter (e.g. "RFI_Key"), export IFC, and the viewer joins on it.
Fill IFC_GlobalId / Revit_ElementId (yellow) after export only if you want a frozen lookup table; the key in the model is the real link.
HOW A SITE ROW BECOMES A KEY
"P22 - Well Curb" → P22-WELL-L00
"P22 - 7th Lift" → P22-WELL-L07
"P26 - Bottom Plugging" → P26-WELL-PLUG "P26 - Well Cap" → P26-WELL-CAP
"P8 - Lower Pylon - Starter" → P8-LPYL-L00 "... - 3rd Lift" → P8-LPYL-L03
"P17-BP-S09a-O©" → P17-BP-S09a-O (© kept as Cable_Segment = Y)
Replacement wells keep their suffix: P12(A)-WELL-L05, P14(N)-WELL-L03. Toppled P12 / P14 lifts are listed with status "Reversed (toppled)".
SEGMENT ID GRAMMAR P17 - BP - S09 a - O ©
P17 pier whose cantilever the segment hangs from
KS/BP arm direction: KS = Kaita Sidhi (towards lower pier numbers, P6 end), BP = Bathan Pam (towards higher pier numbers, P30 end)
S09 segment number counted outwards from the pier (S01 = next to the pier table)
a marks the SIDE-SPAN arm of an outer pylon (the arm facing the EJ pier). EJ piers also carry one S01a-E starter segment per arm
E/O/M segment family: E = EJ pier arm (7), O = outer pylon arm (34), M = middle pylon arm (18)
© stay-cable anchor segment: odd S09–S33 on outer arms (13 per arm), even S08–S16 on middle arms (5 per arm) = 372 in total
Module = EJ–Outer–Middle–Outer–EJ, e.g. Module 1 = P6–P10. 186 segments per module × 6 = 1,116.
Module 1 left to right: P6-BP S01a-E,S01-E…S06-E ¦ P7-KS S34a…S01a-O ¦ P7 ¦ P7-BP S01…S34-O ¦ P8-KS S18…S01-M ¦ P8 ¦ P8-BP S01…S18-M ¦ P9-KS S34…S01-O ¦ P9 ¦ P9-BP S01a…S34a-O ¦ P10-KS S06…S01-E,S01a-E
WELL LIFTS — WHY A FIXED 20-SLICE MODEL WILL NOT MATCH
Completed wells have 19 to 22 lifts on top of the curb, with heights from 0.35 m to 3.63 m. Short lifts are used to land exactly on the transition (taper) level.
So the lift heights come from the RFIs, not from the drawing. Z_Bottom_m / Z_Top_m give each lift's position above the cutting edge, so the model can be sliced to match.
Rows marked PLANNED are estimates at 2.5 m for wells still sinking; they will be replaced by the real heights when the RFIs arrive.
SHEETS
Element_Register one row per model element + current status + RFIs
Pier_Summary live formulas over the register: well depth %, lifts, plug, cap, lower pylon, segments cast
RFI_Log one row per RFI number (an element usually closes with 3–5 RFIs: Str = structure, Sur = survey, MB = casting yard)
Status_Legend the lifecycle states and suggested viewer colours
Anomalies things in the IPC file that will break an automatic link, or that look like billing errors
EDIT
Yellow cells (IFC_GlobalId, Revit_ElementId) are the only input cells. Everything else is regenerated each month from the new IPC file.

## Pier_Summary
Pier-wise progress · IPC-34 (formulas read Element_Register — no hardcoded results)
Unit_ID | Pier | Role | Well shape | Well design depth (m) | Well cast & sunk (m) | Well % | Lifts done | Lifts still to come (est.) | Bottom plug | Well cap | Lower pylon scope (m) | Lower pylon cast (m) | Lower pylon % | Segments in scope | Segments cast (yard) | KS arm cast | BP arm cast | Cable (©) cast | Note
P6 | P6 | EJ pier | Circular | 50.55 | 50.55 | 100% | 20 | 0 |  |  | 21.624 | 0 | 0% | 7 | 7 | 0 | 7 | 0
P7 | P7 | Outer pylon | Double-D | 54.05 | 54.05 | 100% | 20 | 0 | Done | Done | 21.324 | 6.525 | 30.6% | 68 | 68 | 34 | 34 | 26
P8 | P8 | Middle pylon | Circular | 54.05 | 54.05 | 100% | 21 | 0 | Done | Done | 21.624 | 21.624 | 100% | 36 | 36 | 18 | 18 | 10
P9 | P9 | Outer pylon | Double-D | 54.05 | 54.05 | 100% | 21 | 0 |  |  | 21.324 | 0 | 0% | 68 | 68 | 34 | 34 | 26
P10 | P10 | EJ pier | Circular | 50.55 | 50.55 | 100% | 20 | 0 |  |  | 21.624 | 0 | 0% | 14 | 7 | 7 | 0 | 0
P11 | P11 | Outer pylon | Double-D | 54.05 | 44.2 | 81.78% | 16 | 4 |  |  | 21.324 | 0 | 0% | 68 | 0 | 0 | 0 | 0
P12 | P12 | Middle pylon | Circular | 0 | 0 | 0% | 0 | 0 | [10 empty] | Abandoned (toppled)
P12(A) | P12 | Middle pylon | Circular | 54.05 | 47.13 | 87.2% | 16 | 3 |  |  | 21.624 | 0 | 0% | 36 | 0 | 0 | 0 | 0
P12(N) | P12 | Middle pylon | Circular | 54.05 | 0 | 0% | 0 | 21 | [10 empty] | Assumed — confirm
P13 | P13 | Outer pylon | Double-D | 54.05 | 41.4 | 76.6% | 15 | 6 |  |  | 21.324 | 0 | 0% | 68 | 0 | 0 | 0 | 0
P14 | P14 | EJ pier | Circular | 0 | 0 | 0% | 0 | 0 | [10 empty] | Abandoned (toppled)
P14(N) | P14 | EJ pier | Circular | 50.55 | 48.1 | 95.15% | 18 | 1 |  |  | 21.624 | 0 | 0% | 14 | 0 | 0 | 0 | 0
P15 | P15 | Outer pylon | Double-D | 54.05 | 54.05 | 100% | 21 | 0 |  |  | 21.324 | 0 | 0% | 68 | 9 | 2 | 7 | 4
P16 | P16 | Middle pylon | Circular | 54.05 | 54.05 | 100% | 21 | 0 |  |  | 21.624 | 0 | 0% | 36 | 18 | 7 | 11 | 9
P17 | P17 | Outer pylon | Double-D | 54.05 | 52.91 | 97.89% | 21 | 1 |  |  | 21.324 | 0 | 0% | 68 | 52 | 26 | 26 | 26
P18 | P18 | EJ pier | Circular | 50.55 | 50.55 | 100% | 20 | 0 |  |  | 21.624 | 0 | 0% | 14 | 7 | 7 | 0 | 0
P19 | P19 | Outer pylon | Double-D | 54.05 | 54.05 | 100% | 21 | 0 | Done | Done | 21.324 | 4.63 | 21.71% | 68 | 1 | 1 | 0 | 1
P20 | P20 | Middle pylon | Circular | 54.05 | 54.05 | 100% | 21 | 0 | Done | Done | 21.624 | 6.515 | 30.13% | 36 | 0 | 0 | 0 | 0
P21 | P21 | Outer pylon | Double-D | 54.05 | 54.05 | 100% | 22 | 0 |  |  | 21.324 | 0 | 0% | 68 | 49 | 26 | 23 | 25
P22 | P22 | EJ pier | Circular | 50.55 | 51.55 | 102% | 22 | 0 | Done | Done | 21.624 | 10.63 | 49.16% | 14 | 7 | 0 | 7 | 0
P23 | P23 | Outer pylon | Double-D | 54.05 | 54.05 | 100% | 23 | 0 | Done |  | 21.324 | 0 | 0% | 68 | 68 | 34 | 34 | 26
P24 | P24 | Middle pylon | Circular | 54.05 | 54.05 | 100% | 22 | 0 | Done | Done | 21.624 | 0 | 0% | 36 | 26 | 15 | 11 | 10
P25 | P25 | Outer pylon | Double-D | 54.05 | 54.05 | 100% | 21 | 0 | Done | Done | 21.324 | -0.395 | -1.852% | 68 | 66 | 33 | 33 | 26
P26 | P26 | EJ pier | Circular | 50.55 | 50.55 | 100% | 21 | 0 | Done | Done | 21.624 | 16.01 | 74.04% | 14 | 7 | 7 | 0 | 0
P27 | P27 | Outer pylon | Double-D | 54.05 | 54.05 | 100% | 21 | 0 |  |  | 21.324 | 0 | 0% | 68 | 0 | 0 | 0 | 0
P28 | P28 | Middle pylon | Circular | 54.05 | 54.05 | 100% | 22 | 0 |  |  | 21.624 | 0 | 0% | 36 | 0 | 0 | 0 | 0
P29 | P29 | Outer pylon | Double-D | 54.05 | 54.05 | 100% | 21 | 0 | Done | Done | 21.324 | 6.745 | 31.63% | 68 | 0 | 0 | 0 | 0
P30 | P30 | EJ pier | Circular | 50.55 | 45.28 | 89.57% | 18 | 3 |  |  | 21.624 | 0 | 0% | 7 | 0 | 0 | 0 | 0
Total |  |  |  | 1380.8 | 1289.47 | 93.39% | 505 | 39 | 10 | 9 | 537 | 72.284 | 13.46% | 1116 | 496 | 251 | 245 | 189
Blue = design inputs from drawings / Well Cal. / Pylon Cal. (EJ well 50.55 m, middle & outer 54.05 m; lower pylon 21.624 m EJ/middle, 21.324 m outer). Toppled P12 / P14 set to 0 design depth. P12(N) is assumed from the May-2026 cutting edge and Pylon Cal. — confirm.
Check vs Schedule 4: well steining cumulative 1,289.47 Rmt; segments 496; cable segments 189. Lower pylon here includes P19 1st lift (4.0 m) that the Schedule 4 SUM range misses, and P25 2nd lift as billed (−3.14) — see Anomalies.

## Anomalies
Severity | Schedule 4 row | Element / text | What is wrong | Why it matters for the model link
High | - | P12(A)-WELL-L12, P13-WELL-L12 | 3 RFIs (MPSB/Str/4543, MPSB/Sur/3394, MPSB/Str/4544) are quoted for both elements — looks like a copy-pasted RFI chain; both rows are billed | Cannot be tied to one element — reported, not linked.
High | 16 | P12 | New work (item 401.a) booked as plain 'P12' after P12 was written off — clashes with the toppled well's keys; label it P12(N) or similar | Would light up the toppled well in the model instead of the new one.
High | 683 | P19 - Lower Pylon - 1st Lift | Row is outside the cumulative total =SUM(F684:F715) (row 716) — its 4 is NOT counted in the bill | Model will show the lift as done (RFIs exist) but the bill does not pay for it — or pays a negative amount.
High | 693 | P25 - Lower Pylon - 2nd Lift | Negative quantity (-3.140) on a row that carries real RFIs — likely a broken formula | Model will show the lift as done (RFIs exist) but the bill does not pay for it — or pays a negative amount.
Medium | - | P24-WELL-L03, P6-WELL-L03 | MPSB/Sur/295 is quoted for two different piers — one is probably a typo | The same RFI would light up two elements. One is wrong.
Medium | - | P8-KS-S18-M, P9-KS-S01-O | MPSB/MB/943 is quoted for two different piers — one is probably a typo | The same RFI would light up two elements. One is wrong.
Medium | - | P25-BP-S32a-O, P9-BP-S18a-O | MPSB/Sur/3062 is quoted for two different piers — one is probably a typo | The same RFI would light up two elements. One is wrong.
Medium | - | P22 | Well steining billed 51.55 m, drawing depth for a EJ pier well is 50.55 m (+1.00 m). The BOQ tentative scope (1,381.80 Rmt) is exactly 1.00 m above the drawing total, so this may be an accepted revised founding level — confirm and update the model depth | Cannot be tied to one element — reported, not linked.
Medium | 66 | P19 | RFI date 28-Dec-2025 is months after the rest of IPC - 10 (typical Jan-2025) — date typo? | 4D playback would place this element at the wrong date.
Medium | 302 | P12 - 7th Lift | Quantity formula =-F291 points at row(s) [291] (P30 - 6th Lift) — rows were re-sorted after the formula was written | Sorting the sheet silently changes quantities. Hard-type quantities in element rows.
Medium | 306 | P14 - 7th Lift | Quantity formula =-F295 points at row(s) [295] (P11 - 6th Lift) — rows were re-sorted after the formula was written | Sorting the sheet silently changes quantities. Hard-type quantities in element rows.
Medium | 693 | P25 - Lower Pylon - 2nd Lift | Quantity formula =4.86-F689-F688 points at row(s) [689, 688] (P22 - Lower Pylon - 2nd Lift; P22 - Lower Pylon - 1st Lift) — rows were re-sorted after the formula was written | Sorting the sheet silently changes quantities. Hard-type quantities in element rows.
Medium | 914 | P7-KS-S01a-O | RFI date 30-Dec-2026 is in the future — typo? | 4D playback would place this element at the wrong date.
Medium | 915 | P7-BP-S28-O | RFI date 30-Dec-2026 is in the future — typo? | 4D playback would place this element at the wrong date.
Medium | 922 | P8-KS-S16-M© | Cable segment (©) billed without 408.c in the item column | Stay-cable material count (408.c) and model cable-segment count will not agree.
Low | 9 | Circular - 8 Nos. Double D - 6 Nos. | Row cannot be tied to one element (element text not in a known pattern) | Cannot be tied to one element — reported, not linked.
Low | 10 | Double D - 1 No. | Row cannot be tied to one element (element text not in a known pattern) | Cannot be tied to one element — reported, not linked.
Low | 11 | Double D - 1 No. | Row cannot be tied to one element (element text not in a known pattern) | Cannot be tied to one element — reported, not linked.
Low | 12 | Circular - 5 Nos. Double D - 4 Nos. | Row cannot be tied to one element (element text not in a known pattern) | Cannot be tied to one element — reported, not linked.
Low | 13 | Toppling of P12 & P14 | Row cannot be tied to one element (element text not in a known pattern) | Cannot be tied to one element — reported, not linked.
Low | 47 | Toppling of P12 & P14 | Row cannot be tied to one element (element text not in a known pattern) | Cannot be tied to one element — reported, not linked.
Low | 80 | Toppling of P12 & P14 | Row cannot be tied to one element (element text not in a known pattern) | Cannot be tied to one element — reported, not linked.
Low | 215 | P18 - 4th Lift | 3 RFI numbers but 1 dates — date column incomplete | Stage dates cannot be assigned to each RFI; the element completion date is still usable.
Low | 721 | P17-BP-S09a-O© | 3 RFI numbers but 1 dates — date column incomplete | Stage dates cannot be assigned to each RFI; the element completion date is still usable.
Info | — | Curb heights | Later wells bill the curb as 6.20 m (outer) / 4.48 m (EJ, middle) against 6.04 / 4.32 m on the drawing (+0.16 m). Totals still close at design depth, so the lifts above absorb it. | Slice the model from the RFI heights (Z columns), not from the drawing curb height.
Info | — | P12(A) lifts | Cast Jan–Apr 2026 but billed only in IPC-33 (and cutting edge RFI of 7-Jan-26 billed in IPC-33). | Use RFI dates for 4D progress and IPC only for money — they can be months apart.
Info | — | Segments | Precast segment RFIs (406.a) are for CASTING IN THE YARD. No erection (406.b) has been billed yet. | Colour them as "cast in yard", not as built on the bridge.
Info | — | Column K / L | Column K holds the pier for wells but the casting MONTH for segments; column L stage names appear only on the first row of each block (and stray pier names on P25 / P26 lower pylon rows). | The parser ignores K and L; rely on columns B, F, G, H, I, J only.

## Element_Register
Element_Key | Site_Text | Element_Type | Pier | Unit_ID | Pier_Role | Well_Shape | Module | Span | Arm | Seg_No | Side_Span_Arm | Cable_Segment | Along_Bridge_Order | Lift_No | Height_m | Z_Bottom_m | Z_Top_m | Design_Zone | Status | Status_Date | IPC | RFI_Count | RFI_Nos | Shared_RFI | IFC_GlobalId | Revit_ElementId | Notes
P6-WELL-CE | P6 | Cutting edge | P6 | P6 | EJ pier | Circular | [12 empty] | Shutter & scaffold done | 2024-11-21 | IPC - 08 | 2 | MPSB/Sur/80 · MPSB/Sur/115
P6-WELL-L00 | P6 - Well Curb | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Cast & sunk | 2024-12-06 | IPC - 08 | 5 | MPSB/Str/148 · MPSB/Sur/157 · MPSB/Str/164 · MPSB/Sur/179 · MPSB/Str/184
P6-WELL-L01 | P6 - 1st Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 1 | 2.65 | 4.32 | 6.97 | Below transition | Cast & sunk | 2024-12-18 | IPC - 09 | 3 | MPSB/Str/207 · MPSB/Str/208 · MPSB/Str/221
P6-WELL-L02 | P6 - 2nd Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 2 | 2.5 | 6.97 | 9.47 | Below transition | Cast & sunk | 2024-12-25 | IPC - 09 | 4 | MPSB/Sur/211 · MPSB/Str/233 · MPSB/Str/234 · MPSB/Str/247
P6-WELL-L03 | P6 - 3rd Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 3 | 2.5 | 9.47 | 11.97 | Below transition | Cast & sunk | 2024-12-31 | IPC - 09 | 3 | MPSB/Sur/295 · MPSB/Str/295 · MPSB/Sur/243 | Y
P6-WELL-L04 | P6 - 4th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 4 | 2.5 | 11.97 | 14.47 | Below transition | Cast & sunk | 2025-01-11 | IPC - 10 | 4 | MPSB/Str/297 · MPSB/Str/333 · MPSB/Sur/274 · MPSB/Sur/290
P6-WELL-L05 | P6 - 5th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 5 | 2.5 | 14.47 | 16.97 | Below transition | Cast & sunk | 2025-01-26 | IPC - 10 | 3 | MPSB/Str/376 · MPSB/Str/377 · MPSB/Sur/362
P6-WELL-L06 | P6 - 6th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 6 | 2.5 | 16.97 | 19.47 | Below transition | Cast & sunk | 2025-01-31 | IPC - 10 | 4 | MPSB/Str/410 · MPSB/Sur/350 · MPSB/Str/416 · MPSB/Sur/393
P6-WELL-L07 | P6 - 7th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 7 | 2.5 | 19.47 | 21.97 | Below transition | Cast & sunk | 2025-02-19 | IPC - 11 | 4 | MPSB/Str/547 · MPSB/Sur/459 · MPSB/Str/548 · MPSB/Sur/507
P6-WELL-L08 | P6 - 8th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 8 | 0.5 | 21.97 | 22.47 | Below transition → Transition | Cast & sunk | 2025-02-27 | IPC - 11 | 3 | MPSB/Str/654 · MPSB/Sur/570 · MPSB/Str/655
P6-WELL-L09 | P6 - 9th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 9 | 2.5 | 22.47 | 24.97 | Transition | Cast & sunk | 2025-02-28 | IPC - 11 | 3 | MPSB/Str/712 · MPSB/Sur/627 · MPSB/Str/713
P6-WELL-L10 | P6 - 10th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 10 | 2.66 | 24.97 | 27.63 | Transition → Above transition | Cast & sunk | 2025-03-31 | IPC - 13 | 3 | MPSB/Str/1016 · MPSB/Sur/843 · MPSB/Str/1017
P6-WELL-L11 | P6 - 11th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 11 | 2.5 | 27.63 | 30.13 | Above transition | Cast & sunk | 2025-04-12 | IPC - 14 | 3 | MPSB/Str/1115 · MPSB/Sur/978 · MPSB/Str/1116
P6-WELL-L12 | P6 - 12th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 12 | 2.5 | 30.13 | 32.63 | Above transition | Cast & sunk | 2025-04-24 | IPC - 14 | 4 | MPSB/Str/1196 · MPSB/Sur/1040 · MPSB/Str/1197 · MPSB/Sur/1091
P6-WELL-L13 | P6 - 13th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 13 | 2.5 | 32.63 | 35.13 | Above transition | Cast & sunk | 2025-05-19 | IPC - 15 | 3 | MPSB/Str/1521 · MPSB/Sur/1307 · MPSB/Str/1522
P6-WELL-L14 | P6 - 14th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 14 | 2.57 | 35.13 | 37.7 | Above transition | Cast & sunk | 2025-05-27 | IPC - 15 | 3 | MPSB/Str/1582 · MPSB/Sur/1364 · MPSB/Str/1583
P6-WELL-L15 | P6 - 15th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 15 | 2.5 | 37.7 | 40.2 | Above transition | Cast & sunk | 2025-06-26 | IPC - 16 | 3 | MPSB/Str/1705 · MPSB/Sur/1458 · MPSB/Str/1706
P6-WELL-L16 | P6 - 16th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 16 | 2.5 | 40.2 | 42.7 | Above transition | Cast & sunk | 2025-06-29 | IPC - 16 | 3 | MPSB/Str/1732 · MPSB/Sur/1473 · MPSB/Str/1733
P6-WELL-L17 | P6 - 17th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 17 | 2.5 | 42.7 | 45.2 | Above transition | Cast & sunk | 2025-07-27 | IPC - 18 | 3 | MPSB/Str/1902 · MPSB/Sur/1594 · MPSB/Str/1903
P6-WELL-L18 | P6 - 18th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 18 | 2.4 | 45.2 | 47.6 | Above transition | Cast & sunk | 2025-08-20 | IPC - 19 | 4 | MPSB/Str/2010 · MPSB/Sur/1668 · MPSB/Str/2011 · MPSB/Sur/1704
P6-WELL-L19 | P6 - 19th Lift | Well lift | P6 | P6 | EJ pier | Circular | [7 empty] | 19 | 2.95 | 47.6 | 50.55 | Above transition | Cast & sunk | 2025-09-25 | IPC - 20 | 3 | MPSB/Str/2321 · MPSB/Sur/1871 · MPSB/Str/2322
P6-WELL-PLUG | P6 - Bottom Plugging | Bottom plug | P6 | P6 | EJ pier | Circular | [12 empty] | Not started |  |  | 0
P6-WELL-CAP | P6 - Well Cap | Well cap | P6 | P6 | EJ pier | Circular | [12 empty] | Not started |  |  | 0
P6-LPYL-REST | P6 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P6 | P6 | EJ pier | [8 empty] | 0 | 21.624 | 0 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P7-WELL-CE | P7 | Cutting edge | P7 | P7 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2024-12-19 | IPC - 09 | 2 | MPSB/Sur/120 · MPSB/Sur/204
P7-WELL-L00 | P7 - Well Curb | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 0 | 6.04 | 0 | 6.04 | Curb | Cast & sunk | 2025-01-17 | IPC - 10 | 4 | MPSB/Str/299 · MPSB/Str/334 · MPSB/Sur/316 · MPSB/Sur/317
P7-WELL-L01 | P7 - 1st Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 1 | 3.31 | 6.04 | 9.35 | Below transition | Cast & sunk | 2025-01-30 | IPC - 10 | 3 | MPSB/Str/450 · MPSB/Str/467 · MPSB/Sur/390
P7-WELL-L02 | P7 - 2nd Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 2 | 2.5 | 9.35 | 11.85 | Below transition | Cast & sunk | 2025-02-21 | IPC - 11 | 3 | MPSB/Str/585 · MPSB/Sur/518 · MPSB/Str/586
P7-WELL-L03 | P7 - 3rd Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 3 | 2.4 | 11.85 | 14.25 | Below transition | Cast & sunk | 2025-03-17 | IPC - 13 | 4 | MPSB/Str/791 · MPSB/Str/792 · MPSB/Sur/703 · MPSB/Sur/727
P7-WELL-L04 | P7 - 4th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 14.25 | 16.75 | Below transition | Cast & sunk | 2025-03-27 | IPC - 13 | 3 | MPSB/Str/932 · MPSB/Str/933 · MPSB/Sur/809
P7-WELL-L05 | P7 - 5th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 5 | 2.6 | 16.75 | 19.35 | Below transition | Cast & sunk | 2025-04-12 | IPC - 14 | 3 | MPSB/Str/1117 · MPSB/Sur/979 · MPSB/Str/1118
P7-WELL-L06 | P7 - 6th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 19.35 | 21.85 | Below transition | Cast & sunk | 2025-04-21 | IPC - 14 | 3 | MPSB/Str/1201 · MPSB/Sur/1044 · MPSB/Str/1202
P7-WELL-L07 | P7 - 7th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 21.85 | 24.35 | Below transition | Cast & sunk | 2025-05-29 | IPC - 15 | 4 | MPSB/Str/1504 · MPSB/Sur/1294 · MPSB/Str/1505 · MPSB/Sur/1384
P7-WELL-L08 | P7 - 8th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 8 | 2.5 | 24.35 | 26.85 | Below transition → Transition | Cast & sunk | 2025-06-17 | IPC - 16 | 4 | MPSB/Str/1644 · MPSB/Sur/1409 · MPSB/Str/1645 · MPSB/Sur/1434
P7-WELL-L09 | P7 - 9th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 9 | 2.7 | 26.85 | 29.55 | Transition | Cast & sunk | 2025-07-12 | IPC - 18 | 3 | MPSB/Str/1803 · MPSB/Sur/1517 · MPSB/Str/1804
P7-WELL-L10 | P7 - 10th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 10 | 2.95 | 29.55 | 32.5 | Transition → Above transition | Cast & sunk | 2025-07-21 | IPC - 18 | 3 | MPSB/Str/1853 · MPSB/Sur/1556 · MPSB/Str/1854
P7-WELL-L11 | P7 - 11th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 11 | 2.5 | 32.5 | 35 | Above transition | Cast & sunk | 2025-08-23 | IPC - 19 | 3 | MPSB/Str/2073 · MPSB/Sur/1721 · MPSB/Str/2074
P7-WELL-L12 | P7 - 12th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 12 | 2.5 | 35 | 37.5 | Above transition | Cast & sunk | 2025-08-31 | IPC - 20 | 3 | MPSB/Str/2126 · MPSB/Sur/1757 · MPSB/Str/2127
P7-WELL-L13 | P7 - 13th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 37.5 | 40 | Above transition | Cast & sunk | 2025-09-24 | IPC - 20 | 4 | MPSB/Str/2229 · MPSB/Sur/1822 · MPSB/Str/2230 · MPSB/Sur/1869
P7-WELL-L14 | P7 - 14th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 40 | 42.5 | Above transition | Cast & sunk | 2025-10-13 | IPC - 22 | 3 | MPSB/Str/2461 · MPSB/Sur/1975 · MPSB/Str/2462
P7-WELL-L15 | P7 - 15th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 42.5 | 45 | Above transition | Cast & sunk | 2025-10-24 | IPC - 22 | 3 | MPSB/Str/2569 · MPSB/Sur/2037 · MPSB/Str/2570
P7-WELL-L16 | P7 - 16th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 45 | 47.5 | Above transition | Cast & sunk | 2025-11-20 | IPC - 23 | 3 | MPSB/Str/2867 · MPSB/Sur/2232 · MPSB/Str/2868
P7-WELL-L17 | P7 - 17th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 47.5 | 50 | Above transition | Cast & sunk | 2025-11-26 | IPC - 23 | 3 | MPSB/Str/2938 · MPSB/Sur/2278 · MPSB/Str/2939
P7-WELL-L18 | P7 - 18th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 18 | 2.5 | 50 | 52.5 | Above transition | Cast & sunk | 2025-12-28 | IPC - 25 | 4 | MPSB/Str/3054 · MPSB/Sur/2346 · MPSB/Str/3055 · MPSB/Sur/2522
P7-WELL-L19 | P7 - 19th Lift | Well lift | P7 | P7 | Outer pylon | Double-D | [7 empty] | 19 | 1.55 | 52.5 | 54.05 | Above transition | Cast & sunk | 2026-02-10 | IPC - 27 | 3 | MPSB/Str/3820 · MPSB/Sur/2902 · MPSB/Str/3821
P7-WELL-PLUG | P7 - Bottom Plugging | Bottom plug | P7 | P7 | Outer pylon | Double-D | [12 empty] | Plugged | 2026-04-30 | IPC - 30 | 1 | MPSB/Str/4565
P7-WELL-CAP | P7 - Well Cap | Well cap | P7 | P7 | Outer pylon | Double-D | [12 empty] | Cast | 2026-05-31 | IPC - 31 | 2 | MPSB/Sur/3584 · MPSB/Str/4837
P7-LPYL-L00 | P7 - Lower Pylon - Starter | Lower pylon / pier lift | P7 | P7 | Outer pylon | [8 empty] | 0 | 0.525 | 0 | 0.525 |  | Cast | 2026-06-10 | IPC - 33 | 3 | MPSB/Str/4886 · MPSB/Sur/3625 · MPSB/Str/4887
P7-LPYL-L01 | P7 - Lower Pylon - 1st Lift | Lower pylon / pier lift | P7 | P7 | Outer pylon | [8 empty] | 1 | 4 | 0.525 | 4.525 |  | Cast | 2026-06-21 | IPC - 33 | 3 | MPSB/Str/4927 · MPSB/Sur/3675 · MPSB/Str/4976
P7-LPYL-L02 | P7 - Lower Pylon - 2nd Lift | Lower pylon / pier lift | P7 | P7 | Outer pylon | [8 empty] | 2 | 2 | 4.525 | 6.525 |  | Cast | 2026-07-09 | IPC - 34 | 3 | MPSB/Str/5107 · MPSB/Sur/3738 · MPSB/Str/5108
P7-LPYL-REST | P7 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P7 | P7 | Outer pylon | [8 empty] | 3 | 14.799 | 6.525 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P8-WELL-CE | P8 | Cutting edge | P8 | P8 | Middle pylon | Circular | [12 empty] | Shutter & scaffold done | 2024-12-20 | IPC - 09 | 2 | MPSB/Sur/189 · MPSB/Sur/207
P8-WELL-L00 | P8 - Well Curb | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Cast & sunk | 2024-12-31 | IPC - 09 | 4 | MPSB/Str/261 · MPSB/Str/271 · MPSB/Sur/245 · MPSB/Sur/246
P8-WELL-L01 | P8 - 1st Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 1 | 2.65 | 4.32 | 6.97 | Below transition | Cast & sunk | 2025-01-14 | IPC - 10 | 4 | MPSB/Str/335 · MPSB/Str/352 · MPSB/Sur/288 · MPSB/Sur/300
P8-WELL-L02 | P8 - 2nd Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 2 | 2.5 | 6.97 | 9.47 | Below transition | Cast & sunk | 2025-01-31 | IPC - 10 | 4 | MPSB/Str/392 · MPSB/Sur/345 · MPSB/Str/409 · MPSB/Sur/394
P8-WELL-L03 | P8 - 3rd Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 3 | 2.5 | 9.47 | 11.97 | Below transition | Cast & sunk | 2025-01-31 | IPC - 10 | 4 | MPSB/Str/432 · MPSB/Sur/379 · MPSB/Str/449 · MPSB/Sur/395
P8-WELL-L04 | P8 - 4th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 4 | 2.5 | 11.97 | 14.47 | Below transition | Cast & sunk | 2025-02-23 | IPC - 11 | 4 | MPSB/Str/509 · MPSB/Sur/455 · MPSB/Str/525 · MPSB/Sur/537
P8-WELL-L05 | P8 - 5th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 5 | 2.5 | 14.47 | 16.97 | Below transition | Cast & sunk | 2025-02-25 | IPC - 11 | 4 | MPSB/Str/575 · MPSB/Sur/506 · MPSB/Str/576 · MPSB/Sur/554
P8-WELL-L06 | P8 - 6th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 6 | 2.5 | 16.97 | 19.47 | Below transition | Cast & sunk | 2025-02-28 | IPC - 11 | 3 | MPSB/Str/702 · MPSB/Sur/610 · MPSB/Str/703
P8-WELL-L07 | P8 - 7th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 7 | 2.51 | 19.47 | 21.98 | Below transition | Cast & sunk | 2025-03-18 | IPC - 13 | 3 | MPSB/Str/825 · MPSB/Str/826 · MPSB/Sur/737
P8-WELL-L08 | P8 - 8th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 8 | 2.5 | 21.98 | 24.48 | Below transition | Cast & sunk | 2025-03-30 | IPC - 13 | 3 | MPSB/Str/987 · MPSB/Str/988 · MPSB/Sur/856
P8-WELL-L09 | P8 - 9th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 9 | 2.5 | 24.48 | 26.98 | Below transition | Cast & sunk | 2025-04-26 | IPC - 14 | 3 | MPSB/Str/1276 · MPSB/Sur/1104 · MPSB/Str/1277
P8-WELL-L10 | P8 - 10th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 10 | 2.25 | 26.98 | 29.23 | Below transition | Cast & sunk | 2025-04-30 | IPC - 14 | 3 | MPSB/Str/1380 · MPSB/Sur/1176 · MPSB/Str/1381
P8-WELL-L11 | P8 - 11th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 11 | 2.75 | 29.23 | 31.98 | Below transition | Cast & sunk | 2025-05-29 | IPC - 15 | 4 | MPSB/Str/1554 · MPSB/Sur/1334 · MPSB/Str/1555 · MPSB/Sur/1383
P8-WELL-L12 | P8 - 12th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 12 | 2.5 | 31.98 | 34.48 | Below transition | Cast & sunk | 2025-06-16 | IPC - 16 | 3 | MPSB/Str/1669 · MPSB/Sur/1427 · MPSB/Str/1670
P8-WELL-L13 | P8 - 13th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 13 | 3.15 | 34.48 | 37.63 | Below transition → Transition → Above transition | Cast & sunk | 2025-07-22 | IPC - 18 | 4 | MPSB/Str/1765 · MPSB/Sur/1494 · MPSB/Str/1766 · MPSB/Sur/1562 | Y
P8-WELL-L14 | P8 - 14th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 14 | 2.5 | 37.63 | 40.13 | Above transition | Cast & sunk | 2025-07-22 | IPC - 18 | 4 | MPSB/Str/1805 · MPSB/Sur/1518 · MPSB/Str/1806 · MPSB/Sur/1562 | Y
P8-WELL-L15 | P8 - 15th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 15 | 2.5 | 40.13 | 42.63 | Above transition | Cast & sunk | 2025-08-21 | IPC - 19 | 4 | MPSB/Str/1968 · MPSB/Sur/1642 · MPSB/Str/1969 · MPSB/Sur/1710 | Y
P8-WELL-L16 | P8 - 16th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 16 | 2.5 | 42.63 | 45.13 | Above transition | Cast & sunk | 2025-08-21 | IPC - 19 | 4 | MPSB/Str/2047 · MPSB/Sur/1700 · MPSB/Str/2048 · MPSB/Sur/1710 | Y
P8-WELL-L17 | P8 - 17th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 17 | 2.5 | 45.13 | 47.63 | Above transition | Cast & sunk | 2025-09-09 | IPC - 20 | 3 | MPSB/Str/2190 · MPSB/Sur/1796 · MPSB/Str/2191
P8-WELL-L18 | P8 - 18th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 18 | 2.5 | 47.63 | 50.13 | Above transition | Cast & sunk | 2025-09-22 | IPC - 20 | 3 | MPSB/Str/2286 · MPSB/Sur/1853 · MPSB/Str/2287
P8-WELL-L19 | P8 - 19th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 19 | 2.5 | 50.13 | 52.63 | Above transition | Cast & sunk | 2025-09-30 | IPC - 20 | 3 | MPSB/Str/2360 · MPSB/Sur/1891 · MPSB/Str/2361
P8-WELL-L20 | P8 - 20th Lift | Well lift | P8 | P8 | Middle pylon | Circular | [7 empty] | 20 | 1.42 | 52.63 | 54.05 | Above transition | Cast & sunk | 2025-10-25 | IPC - 22 | 3 | MPSB/Str/2578 · MPSB/Sur/2046 · MPSB/Str/2579
P8-WELL-PLUG | P8 - Bottom Plugging | Bottom plug | P8 | P8 | Middle pylon | Circular | [12 empty] | Plugged | 2026-02-06 | IPC - 27 | 1 | MPSB/Str/3781
P8-WELL-CAP | P8 - Well Cap | Well cap | P8 | P8 | Middle pylon | Circular | [12 empty] | Cast | 2026-02-28 | IPC - 27 | 2 | MPSB/Str/4033 · MPSB/Str/4034
P8-LPYL-L00 | P8 - Lower Pylon - Starter | Lower pylon / pier lift | P8 | P8 | Middle pylon | [8 empty] | 0 | 0.525 | 0 | 0.525 |  | Cast | 2026-04-01 | IPC - 30 | 3 | MPSB/Str/4310 · MPSB/Sur/3233 · MPSB/Str/4311
P8-LPYL-L01 | P8 - Lower Pylon - 1st Lift | Lower pylon / pier lift | P8 | P8 | Middle pylon | [8 empty] | 1 | 4 | 0.525 | 4.525 |  | Cast | 2026-04-05 | IPC - 30 | 3 | MPSB/Str/4337 · MPSB/Sur/3243 · MPSB/Str/4328
P8-LPYL-L02 | P8 - Lower Pylon - 2nd Lift | Lower pylon / pier lift | P8 | P8 | Middle pylon | [8 empty] | 2 | 2 | 4.525 | 6.525 |  | Cast | 2026-04-15 | IPC - 30 | 3 | MPSB/Str/4407 · MPSB/Sur/3303 · MPSB/Str/4408
P8-LPYL-L03 | P8 - Lower Pylon - 3rd Lift | Lower pylon / pier lift | P8 | P8 | Middle pylon | [8 empty] | 3 | 2 | 6.525 | 8.525 |  | Cast | 2026-04-28 | IPC - 30 | 3 | MPSB/Str/4514 · MPSB/Sur/3370 · MPSB/Str/4515
P8-LPYL-L04 | P8 - Lower Pylon - 4th Lift | Lower pylon / pier lift | P8 | P8 | Middle pylon | [8 empty] | 4 | 3.65 | 8.525 | 12.175 |  | Cast | 2026-05-15 | IPC - 31 | 3 | MPSB/Str/4690 · MPSB/Sur/3484 · MPSB/Str/4691
P8-LPYL-L05 | P8 - Lower Pylon - 5th Lift | Lower pylon / pier lift | P8 | P8 | Middle pylon | [8 empty] | 5 | 0.67 | 12.175 | 12.845 |  | Cast | 2026-05-27 | IPC - 31 | 3 | MPSB/Str/4793 · MPSB/Sur/3556 · MPSB/Str/4794
P8-LPYL-L06 | P8 - Lower Pylon - 6th Lift | Lower pylon / pier lift | P8 | P8 | Middle pylon | [8 empty] | 6 | 4.45 | 12.845 | 17.295 |  | Cast | 2026-06-24 | IPC - 33 | 3 | MPSB/Str/4997 · MPSB/Sur/3689 · MPSB/Str/4998
P8-LPYL-L07 | P8 - Lower Pylon - 7th Lift | Lower pylon / pier lift | P8 | P8 | Middle pylon | [8 empty] | 7 | 4.329 | 17.295 | 21.624 |  | Cast | 2026-07-15 | IPC - 34 | 3 | MPSB/Str/5150 · MPSB/Sur/3767 · MPSB/Str/5151
P9-WELL-CE | P9 | Cutting edge | P9 | P9 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2025-01-11 | IPC - 11 | 2 | MPSB/Sur/216 · MPSB/Sur/289
P9-WELL-L00 | P9 - Well Curb | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 0 | 6.04 | 0 | 6.04 | Curb | Cast & sunk | 2025-01-31 | IPC - 10 | 4 | MPSB/Str/408 · MPSB/Str/424 · MPSB/Sur/396 · MPSB/Sur/397
P9-WELL-L01 | P9 - 1st Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 1 | 2 | 6.04 | 8.04 | Below transition | Cast & sunk | 2025-02-23 | IPC - 11 | 4 | MPSB/Str/538 · MPSB/Sur/471 · MPSB/Str/549 · MPSB/Sur/534
P9-WELL-L02 | P9 - 2nd Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 2 | 1.05 | 8.04 | 9.09 | Below transition | Cast & sunk | 2025-02-23 | IPC - 11 | 4 | MPSB/Str/563 · MPSB/Sur/488 · MPSB/Str/564 · MPSB/Sur/535
P9-WELL-L03 | P9 - 3rd Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 3 | 2.5 | 9.09 | 11.59 | Below transition | Cast & sunk | 2025-02-28 | IPC - 11 | 3 | MPSB/Str/704 · MPSB/Sur/613 · MPSB/Str/705
P9-WELL-L04 | P9 - 4th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 4 | 2.61 | 11.59 | 14.2 | Below transition | Cast & sunk | 2025-03-30 | IPC - 13 | 4 | MPSB/Str/827 · MPSB/Str/828 · MPSB/Sur/738 · MPSB/Sur/855
P9-WELL-L05 | P9 - 5th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 14.2 | 16.7 | Below transition | Cast & sunk | 2025-04-11 | IPC - 14 | 4 | MPSB/Str/1048 · MPSB/Sur/919 · MPSB/Str/1049 · MPSB/Sur/969
P9-WELL-L06 | P9 - 6th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 16.7 | 19.2 | Below transition | Cast & sunk | 2025-04-16 | IPC - 14 | 3 | MPSB/Str/1155 · MPSB/Sur/1004 · MPSB/Str/1156
P9-WELL-L07 | P9 - 7th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 7 | 2.6 | 19.2 | 21.8 | Below transition | Cast & sunk | 2025-04-26 | IPC - 14 | 3 | MPSB/Str/1274 · MPSB/Sur/1103 · MPSB/Str/1275
P9-WELL-L08 | P9 - 8th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 8 | 2.5 | 21.8 | 24.3 | Below transition | Cast & sunk | 2025-04-30 | IPC - 14 | 3 | MPSB/Str/1386 · MPSB/Sur/1179 · MPSB/Str/1387
P9-WELL-L09 | P9 - 9th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 9 | 2.5 | 24.3 | 26.8 | Below transition → Transition | Cast & sunk | 2025-06-16 | IPC - 16 | 3 | MPSB/Str/1667 · MPSB/Sur/1426 · MPSB/Str/1668
P9-WELL-L10 | P9 - 10th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 10 | 2.7 | 26.8 | 29.5 | Transition | Cast & sunk | 2025-08-20 | IPC - 19 | 4 | MPSB/Str/1976 · MPSB/Sur/1648 · MPSB/Str/1977 · MPSB/Sur/1706
P9-WELL-L11 | P9 - 11th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 11 | 2.8 | 29.5 | 32.3 | Transition → Above transition | Cast & sunk | 2025-08-22 | IPC - 19 | 4 | MPSB/Str/2012 · MPSB/Sur/1669 · MPSB/Str/2013 · MPSB/Sur/1717
P9-WELL-L12 | P9 - 12th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 12 | 2.5 | 32.3 | 34.8 | Above transition | Cast & sunk | 2025-09-06 | IPC - 20 | 3 | MPSB/Str/2166 · MPSB/Sur/1782 · MPSB/Str/2167
P9-WELL-L13 | P9 - 13th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 34.8 | 37.3 | Above transition | Cast & sunk | 2025-09-22 | IPC - 20 | 3 | MPSB/Str/2288 · MPSB/Sur/1854 · MPSB/Str/2289
P9-WELL-L14 | P9 - 14th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 37.3 | 39.8 | Above transition | Cast & sunk | 2025-09-30 | IPC - 20 | 3 | MPSB/Str/2378 · MPSB/Sur/1907 · MPSB/Str/2379
P9-WELL-L15 | P9 - 15th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 39.8 | 42.3 | Above transition | Cast & sunk | 2025-10-31 | IPC - 22 | 3 | MPSB/Str/2664 · MPSB/Sur/2096 · MPSB/Str/2665
P9-WELL-L16 | P9 - 16th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 42.3 | 44.8 | Above transition | Cast & sunk | 2025-11-12 | IPC - 23 | 3 | MPSB/Str/2777 · MPSB/Sur/2176 · MPSB/Str/2778
P9-WELL-L17 | P9 - 17th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 17 | 2.3 | 44.8 | 47.1 | Above transition | Cast & sunk | 2025-12-16 | IPC - 25 | 3 | MPSB/Str/3165 · MPSB/Sur/2424 · MPSB/Str/3166
P9-WELL-L18 | P9 - 18th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 18 | 2.7 | 47.1 | 49.8 | Above transition | Cast & sunk | 2025-12-24 | IPC - 25 | 3 | MPSB/Str/3246 · MPSB/Sur/2481 · MPSB/Str/3247
P9-WELL-L19 | P9 - 19th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 19 | 2.5 | 49.8 | 52.3 | Above transition | Cast & sunk | 2025-12-31 | IPC - 25 | 3 | MPSB/Str/3379 · MPSB/Sur/2571 · MPSB/Str/3380
P9-WELL-L20 | P9 - 20th Lift | Well lift | P9 | P9 | Outer pylon | Double-D | [7 empty] | 20 | 1.75 | 52.3 | 54.05 | Above transition | Cast & sunk | 2026-01-23 | IPC - 26 | 3 | MPSB/Str/3624 · MPSB/Sur/2750 · MPSB/Str/3625 |  |  |  | Net of correction row(s): -0.050 (IPC - 27)
P9-WELL-PLUG | P9 - Bottom Plugging | Bottom plug | P9 | P9 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P9-WELL-CAP | P9 - Well Cap | Well cap | P9 | P9 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P9-LPYL-REST | P9 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P9 | P9 | Outer pylon | [8 empty] | 0 | 21.324 | 0 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P10-WELL-CE | P10 | Cutting edge | P10 | P10 | EJ pier | Circular | [12 empty] | Shutter & scaffold done | 2025-01-27 | IPC - 10 | 2 | MPSB/Sur/357 · MPSB/Sur/368
P10-WELL-L00 | P10 - Well Curb | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Cast & sunk | 2025-02-11 | IPC - 11 | 5 | MPSB/Str/489 · MPSB/Sur/426 · MPSB/Str/494 · MPSB/Sur/453 · MPSB/Sur/454
P10-WELL-L01 | P10 - 1st Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 1 | 2.5 | 4.32 | 6.82 | Below transition | Cast & sunk | 2025-02-24 | IPC - 11 | 4 | MPSB/Str/577 · MPSB/Sur/508 · MPSB/Str/578 · MPSB/Sur/545
P10-WELL-L02 | P10 - 2nd Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 2 | 2.5 | 6.82 | 9.32 | Below transition | Cast & sunk | 2025-02-27 | IPC - 11 | 3 | MPSB/Str/659 · MPSB/Sur/580 · MPSB/Str/660
P10-WELL-L03 | P10 - 3rd Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 3 | 2.5 | 9.32 | 11.82 | Below transition | Cast & sunk | 2025-02-28 | IPC - 11 | 3 | MPSB/Str/666 · MPSB/Sur/590 · MPSB/Str/667
P10-WELL-L04 | P10 - 4th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 4 | 2.615 | 11.82 | 14.435 | Below transition | Cast & sunk | 2025-03-20 | IPC - 13 | 3 | MPSB/Str/837 · MPSB/Str/838 · MPSB/Sur/745
P10-WELL-L05 | P10 - 5th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 5 | 2.32 | 14.435 | 16.755 | Below transition | Cast & sunk | 2025-03-26 | IPC - 13 | 3 | MPSB/Str/914 · MPSB/Str/915 · MPSB/Sur/798
P10-WELL-L06 | P10 - 6th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 6 | 2.5 | 16.755 | 19.255 | Below transition | Cast & sunk | 2025-03-31 | IPC - 13 | 3 | MPSB/Str/991 · MPSB/Str/992 · MPSB/Sur/859
P10-WELL-L07 | P10 - 7th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 7 | 2.5 | 19.255 | 21.755 | Below transition | Cast & sunk | 2025-04-15 | IPC - 14 | 4 | MPSB/Str/1102 · MPSB/Sur/964 · MPSB/Str/1103 · MPSB/Sur/1000
P10-WELL-L08 | P10 - 8th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 8 | 0.545 | 21.755 | 22.3 | Below transition | Cast & sunk | 2025-04-21 | IPC - 14 | 3 | MPSB/Str/1216 · MPSB/Sur/1057 · MPSB/Str/1217
P10-WELL-L09 | P10 - 9th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 9 | 2.81 | 22.3 | 25.11 | Transition → Above transition | Cast & sunk | 2025-04-24 | IPC - 14 | 3 | MPSB/Str/1248 · MPSB/Sur/1077 · MPSB/Str/1249
P10-WELL-L10 | P10 - 10th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 10 | 2.5 | 25.11 | 27.61 | Above transition | Cast & sunk | 2025-05-16 | IPC - 15 | 4 | MPSB/Str/1472 · MPSB/Sur/1253 · MPSB/Str/1473 · MPSB/Sur/1291
P10-WELL-L11 | P10 - 11th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 11 | 2.5 | 27.61 | 30.11 | Above transition | Cast & sunk | 2025-05-24 | IPC - 15 | 3 | MPSB/Str/1561 · MPSB/Sur/1342 · MPSB/Str/1562
P10-WELL-L12 | P10 - 12th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 12 | 2.2 | 30.11 | 32.31 | Above transition | Cast & sunk | 2025-05-29 | IPC - 15 | 3 | MPSB/Str/1600 · MPSB/Sur/1385 · MPSB/Str/1601
P10-WELL-L13 | P10 - 13th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 13 | 2.8 | 32.31 | 35.11 | Above transition | Cast & sunk | 2025-06-27 | IPC - 16 | 3 | MPSB/Str/1674 · MPSB/Str/1675 · MPSB/Sur/1462 | Y
P10-WELL-L14 | P10 - 14th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 14 | 2.7 | 35.11 | 37.81 | Above transition | Cast & sunk | 2025-06-27 | IPC - 16 | 4 | MPSB/Str/1694 · MPSB/Sur/1451 · MPSB/Str/1695 · MPSB/Sur/1462 | Y
P10-WELL-L15 | P10 - 15th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 15 | 2.5 | 37.81 | 40.31 | Above transition | Cast & sunk | 2025-06-28 | IPC - 16 | 3 | MPSB/Str/1720 · MPSB/Sur/1466 · MPSB/Str/1721
P10-WELL-L16 | P10 - 16th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 16 | 2.5 | 40.31 | 42.81 | Above transition | Cast & sunk | 2025-07-19 | IPC - 18 | 4 | MPSB/Str/1807 · MPSB/Sur/1519 · MPSB/Str/1808 · MPSB/Sur/1550
P10-WELL-L17 | P10 - 17th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 17 | 2.5 | 42.81 | 45.31 | Above transition | Cast & sunk | 2025-07-31 | IPC - 18 | 3 | MPSB/Str/1930 · MPSB/Sur/1615 · MPSB/Str/1931
P10-WELL-L18 | P10 - 18th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 18 | 2.66 | 45.31 | 47.97 | Above transition | Cast & sunk | 2025-11-12 | IPC - 23 | 3 | MPSB/Str/2775 · MPSB/Sur/2175 · MPSB/Str/2776
P10-WELL-L19 | P10 - 19th Lift | Well lift | P10 | P10 | EJ pier | Circular | [7 empty] | 19 | 2.58 | 47.97 | 50.55 | Above transition | Cast & sunk | 2025-11-29 | IPC - 23 | 3 | MPSB/Str/2979 · MPSB/Sur/2301 · MPSB/Str/2980
P10-WELL-PLUG | P10 - Bottom Plugging | Bottom plug | P10 | P10 | EJ pier | Circular | [12 empty] | Not started |  |  | 0
P10-WELL-CAP | P10 - Well Cap | Well cap | P10 | P10 | EJ pier | Circular | [12 empty] | Not started |  |  | 0
P10-LPYL-REST | P10 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P10 | P10 | EJ pier | [8 empty] | 0 | 21.624 | 0 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P11-WELL-CE | P11 | Cutting edge | P11 | P11 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2026-01-09 | IPC - 26 | 2 | MPSB/Sur/2561 · MPSB/Sur/2637
P11-WELL-L00 | P11 - Well Curb | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 0 | 6.2 | 0 | 6.2 | Curb → Below transition | Cast & sunk | 2026-01-29 | IPC - 26 | 5 | MPSB/Str/3534 · MPSB/Sur/2710 · MPSB/Str/3567 · MPSB/Sur/2782 · MPSB/Sur/2793
P11-WELL-L01 | P11 - 1st Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 1 | 2.5 | 6.2 | 8.7 | Below transition | Cast & sunk | 2026-01-31 | IPC - 26 | 3 | MPSB/Str/3715 · MPSB/Sur/2818 · MPSB/Str/3716
P11-WELL-L02 | P11 - 2nd Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 2 | 2.5 | 8.7 | 11.2 | Below transition | Cast & sunk | 2026-02-13 | IPC - 27 | 4 | MPSB/Str/3809 · MPSB/Sur/2894 · MPSB/Str/3810 · MPSB/Sur/2924
P11-WELL-L03 | P11 - 3rd Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 3 | 2.5 | 11.2 | 13.7 | Below transition | Cast & sunk | 2026-02-19 | IPC - 27 | 4 | MPSB/Str/3859 · MPSB/Sur/2934 · MPSB/Str/3860 · MPSB/Sur/2957
P11-WELL-L04 | P11 - 4th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 13.7 | 16.2 | Below transition | Cast & sunk | 2026-02-28 | IPC - 27 | 4 | MPSB/Str/3919 · MPSB/Sur/2973 · MPSB/Str/3920 · MPSB/Sur/3041 | Y
P11-WELL-L05 | P11 - 5th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 16.2 | 18.7 | Below transition | Cast & sunk | 2026-02-28 | IPC - 27 | 4 | MPSB/Str/3960 · MPSB/Sur/3009 · MPSB/Str/3961 · MPSB/Sur/3041 | Y
P11-WELL-L06 | P11 - 6th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 18.7 | 21.2 | Below transition | Cast & sunk | 2026-03-10 | IPC - 29 | 3 | MPSB/Str/4077 · MPSB/Sur/3084 · MPSB/Str/4078
P11-WELL-L07 | P11 - 7th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 21.2 | 23.7 | Below transition | Cast & sunk | 2026-03-15 | IPC - 29 | 3 | MPSB/Str/4120 · MPSB/Sur/3123 · MPSB/Str/4119
P11-WELL-L08 | P11 - 8th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 8 | 2.5 | 23.7 | 26.2 | Below transition → Transition | Cast & sunk | 2026-03-27 | IPC - 29 | 3 | MPSB/Str/4215 · MPSB/Sur/3180 · MPSB/Str/4216
P11-WELL-L09 | P11 - 9th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 9 | 2.7 | 26.2 | 28.9 | Transition | Cast & sunk | 2026-04-07 | IPC - 30 | 3 | MPSB/Str/4345 · MPSB/Sur/3255 · MPSB/Str/4346 | Y
P11-WELL-L10 | P11 - 10th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 10 | 2.8 | 28.9 | 31.7 | Transition → Above transition | Cast & sunk | 2026-04-11 | IPC - 30 | 3 | MPSB/Str/4367 · MPSB/Sur/3255 · MPSB/Str/4368 | Y
P11-WELL-L11 | P11 - 11th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 11 | 2.5 | 31.7 | 34.2 | Above transition | Cast & sunk | 2026-04-24 | IPC - 30 | 3 | MPSB/Str/4473 · MPSB/Sur/3344 · MPSB/Str/4474
P11-WELL-L12 | P11 - 12th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 12 | 2.5 | 34.2 | 36.7 | Above transition | Cast & sunk | 2026-05-08 | IPC - 31 | 3 | MPSB/Str/4602 · MPSB/Sur/3433 · MPSB/Str/4603
P11-WELL-L13 | P11 - 13th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 36.7 | 39.2 | Above transition | Cast & sunk | 2026-05-15 | IPC - 31 | 3 | MPSB/Str/4684 · MPSB/Sur/3480 · MPSB/Str/4685
P11-WELL-L14 | P11 - 14th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 39.2 | 41.7 | Above transition | Cast & sunk | 2026-06-12 | IPC - 33 | 3 | MPSB/Str/4896 · MPSB/Sur/3640 · MPSB/Str/4897
P11-WELL-L15 | P11 - 15th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 41.7 | 44.2 | Above transition | Cast & sunk | 2026-06-25 | IPC - 33 | 3 | MPSB/Str/5002 · MPSB/Sur/3690 · MPSB/Str/5003
P11-WELL-L16 | P11 - 16th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 44.2 | 46.7 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P11-WELL-L17 | P11 - 17th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 46.7 | 49.2 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P11-WELL-L18 | P11 - 18th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 18 | 2.5 | 49.2 | 51.7 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P11-WELL-L19 | P11 - 19th Lift | Well lift | P11 | P11 | Outer pylon | Double-D | [7 empty] | 19 | 2.35 | 51.7 | 54.05 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P11-WELL-PLUG | P11 - Bottom Plugging | Bottom plug | P11 | P11 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P11-WELL-CAP | P11 - Well Cap | Well cap | P11 | P11 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P11-LPYL-REST | P11 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P11 | P11 | Outer pylon | [8 empty] | 0 | 21.324 | 0 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P12-WELL-CE | P12 | Cutting edge | P12 | P12 | Middle pylon | Circular | [12 empty] | Shutter & scaffold done | 2025-02-19 | IPC - 11 | 3 | MPSB/MB/1794 · MPSB/Sur/477 · MPSB/Sur/501 |  |  |  | Abandoned (toppled)
P12-WELL-L00 | P12 - Well Curb | Well lift | P12 | P12 | Middle pylon | Circular | [7 empty] | 0 | 0 |  |  |  | Reversed (toppled) | 2025-02-27 | IPC - 11 | 3 | MPSB/Str/628 · MPSB/Sur/581 · MPSB/Str/661 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P12-WELL-L01 | P12 - 1st Lift | Well lift | P12 | P12 | Middle pylon | Circular | [7 empty] | 1 | 0 |  |  |  | Reversed (toppled) | 2025-03-15 | IPC - 13 | 4 | MPSB/Sur/682 · MPSB/Str/771 · MPSB/Str/772 · MPSB/Sur/718 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P12-WELL-L02 | P12 - 2nd Lift | Well lift | P12 | P12 | Middle pylon | Circular | [7 empty] | 2 | 0 |  |  |  | Reversed (toppled) | 2025-03-28 | IPC - 13 | 4 | MPSB/Str/839 · MPSB/Str/840 · MPSB/Sur/746 · MPSB/Sur/845 | Y |  |  | Cast, then reversed in IPC-26 (toppled well)
P12-WELL-L03 | P12 - 3rd Lift | Well lift | P12 | P12 | Middle pylon | Circular | [7 empty] | 3 | 0 |  |  |  | Reversed (toppled) | 2025-03-29 | IPC - 13 | 4 | MPSB/Str/893 · MPSB/Str/894 · MPSB/Sur/784 · MPSB/Sur/845 | Y |  |  | Cast, then reversed in IPC-26 (toppled well)
P12-WELL-L04 | P12 - 4th Lift | Well lift | P12 | P12 | Middle pylon | Circular | [7 empty] | 4 | 0 |  |  |  | Reversed (toppled) | 2025-03-31 | IPC - 13 | 3 | MPSB/Str/999 · MPSB/Str/1000 · MPSB/Sur/863 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P12-WELL-L05 | P12 - 5th Lift | Well lift | P12 | P12 | Middle pylon | Circular | [7 empty] | 5 | 0 |  |  |  | Reversed (toppled) | 2025-04-17 | IPC - 14 | 4 | MPSB/Str/1109 · MPSB/Sur/985 · MPSB/Str/1110 · MPSB/Sur/1022 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P12-WELL-L06 | P12 - 6th Lift | Well lift | P12 | P12 | Middle pylon | Circular | [7 empty] | 6 | 0 |  |  |  | Reversed (toppled) | 2025-04-24 | IPC - 14 | 4 | MPSB/Str/1199 · MPSB/Sur/1043 · MPSB/Str/1200 · MPSB/Sur/1079 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P12-WELL-L07 | P12 - 7th Lift | Well lift | P12 | P12 | Middle pylon | Circular | [7 empty] | 7 | 0 |  |  |  | Reversed (toppled) | 2025-04-25 | IPC - 14 | 3 | MPSB/Str/1272 · MPSB/Sur/1102 · MPSB/Str/1273 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P12(A)-WELL-CE | P12(A) | Cutting edge | P12 | P12(A) | Middle pylon | Circular | [12 empty] | Shutter & scaffold done | 2026-01-28 | IPC - 33 | 3 | MPSB/MB/0660 · MPSB/Sur/2755 · MPSB/Sur/2783
P12(A)-WELL-L00 | P12(A) - Well Curb | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 0 | 4.48 | 0 | 4.48 | Curb → Below transition | Cast & sunk | 2026-02-04 | IPC - 33 | 5 | MPSB/Str/3668 · MPSB/Sur/2802 · MPSB/Str/3685 · MPSB/Sur/2848 · MPSB/Sur/2853
P12(A)-WELL-L01 | P12(A) - 1st Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 1 | 2.8 | 4.48 | 7.28 | Below transition | Cast & sunk | 2026-02-11 | IPC - 33 | 4 | MPSB/Str/3784 · MPSB/Sur/2881 · MPSB/Str/3785 · MPSB/Sur/2905
P12(A)-WELL-L02 | P12(A) - 2nd Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 2 | 2.8 | 7.28 | 10.08 | Below transition | Cast & sunk | 2026-02-14 | IPC - 33 | 4 | MPSB/Str/3827 · MPSB/Sur/2906 · MPSB/Str/3828 · MPSB/Sur/2928
P12(A)-WELL-L03 | P12(A) - 3rd Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 3 | 2.8 | 10.08 | 12.88 | Below transition | Cast & sunk | 2026-02-20 | IPC - 33 | 4 | MPSB/Str/3864 · MPSB/Sur/2939 · MPSB/Str/3865 · MPSB/Sur/2962
P12(A)-WELL-L04 | P12(A) - 4th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 4 | 2.8 | 12.88 | 15.68 | Below transition | Cast & sunk | 2026-03-10 | IPC - 33 | 4 | MPSB/Str/3929 · MPSB/Sur/2976 · MPSB/Str/3930 · MPSB/Sur/3083 | Y
P12(A)-WELL-L05 | P12(A) - 5th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 5 | 2.8 | 15.68 | 18.48 | Below transition | Cast & sunk | 2026-03-10 | IPC - 33 | 4 | MPSB/Str/3962 · MPSB/Sur/3010 · MPSB/Str/3963 · MPSB/Sur/3083 | Y
P12(A)-WELL-L06 | P12(A) - 6th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 6 | 2.8 | 18.48 | 21.28 | Below transition | Cast & sunk | 2026-03-14 | IPC - 33 | 4 | MPSB/Str/4086 · MPSB/Sur/3091 · MPSB/Str/4087 · MPSB/Sur/3118
P12(A)-WELL-L07 | P12(A) - 7th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 7 | 2.8 | 21.28 | 24.08 | Below transition | Cast & sunk | 2026-04-03 | IPC - 33 | 4 | MPSB/Str/4153 · MPSB/Sur/3145 · MPSB/Str/4154 · MPSB/Sur/3237 | Y
P12(A)-WELL-L08 | P12(A) - 8th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 8 | 3.45 | 24.08 | 27.53 | Below transition | Cast & sunk | 2026-04-03 | IPC - 33 | 4 | MPSB/Str/4257 · MPSB/Sur/3202 · MPSB/Str/4258 · MPSB/Sur/3237 | Y
P12(A)-WELL-L09 | P12(A) - 9th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 9 | 2.8 | 27.53 | 30.33 | Below transition | Cast & sunk | 2026-04-17 | IPC - 33 | 4 | MPSB/Str/4362 · MPSB/Sur/3269 · MPSB/Str/4363 · MPSB/Sur/3321 | Y
P12(A)-WELL-L10 | P12(A) - 10th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 10 | 2.8 | 30.33 | 33.13 | Below transition | Cast & sunk | 2026-04-17 | IPC - 33 | 4 | MPSB/Str/4396 · MPSB/Sur/3296 · MPSB/Str/4397 · MPSB/Sur/3321 | Y
P12(A)-WELL-L11 | P12(A) - 11th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 11 | 2.8 | 33.13 | 35.93 | Below transition → Transition | Cast & sunk | 2026-05-08 | IPC - 33 | 4 | MPSB/Str/4525 · MPSB/Sur/3381 · MPSB/Str/4526 · MPSB/Sur/3435 | Y
P12(A)-WELL-L12 | P12(A) - 12th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 12 | 2.8 | 35.93 | 38.73 | Transition → Above transition | Cast & sunk | 2026-05-08 | IPC - 33 | 4 | MPSB/Str/4543 · MPSB/Sur/3394 · MPSB/Str/4544 · MPSB/Sur/3435 | Y
P12(A)-WELL-L13 | P12(A) - 13th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 13 | 2.8 | 38.73 | 41.53 | Above transition | Cast & sunk | 2026-05-18 | IPC - 33 | 3 | MPSB/Str/4716 · MPSB/Sur/3501 · MPSB/Str/4717
P12(A)-WELL-L14 | P12(A) - 14th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 14 | 2.8 | 41.53 | 44.33 | Above transition | Cast & sunk | 2026-06-06 | IPC - 33 | 3 | MPSB/Str/4874 · MPSB/Sur/3614 · MPSB/Str/4875
P12(A)-WELL-L15 | P12(A) - 15th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 15 | 2.8 | 44.33 | 47.13 | Above transition | Cast & sunk | 2026-06-22 | IPC - 33 | 3 | MPSB/Str/4978 · MPSB/Sur/3676 · MPSB/Str/4979
P12(A)-WELL-L16 | P12(A) - 16th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 16 | 2.5 | 47.13 | 49.63 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(A)-WELL-L17 | P12(A) - 17th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 17 | 2.5 | 49.63 | 52.13 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(A)-WELL-L18 | P12(A) - 18th Lift | Well lift | P12 | P12(A) | Middle pylon | Circular | [7 empty] | 18 | 1.92 | 52.13 | 54.05 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(A)-WELL-PLUG | P12(A) - Bottom Plugging | Bottom plug | P12 | P12(A) | Middle pylon | Circular | [12 empty] | Not started |  |  | 0
P12(N)-WELL-CE | P12(N) | Cutting edge | P12 | P12(N) | Middle pylon | Circular | [12 empty] | Not started |  |  | 0 |  |  |  |  | Assumed — confirm
P12(N)-WELL-L00 | P12(N) - Well Curb | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L01 | P12(N) - 1st Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 1 | 2.5 | 4.32 | 6.82 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L02 | P12(N) - 2nd Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 2 | 2.5 | 6.82 | 9.32 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L03 | P12(N) - 3rd Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 3 | 2.5 | 9.32 | 11.82 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L04 | P12(N) - 4th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 4 | 2.5 | 11.82 | 14.32 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L05 | P12(N) - 5th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 5 | 2.5 | 14.32 | 16.82 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L06 | P12(N) - 6th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 6 | 2.5 | 16.82 | 19.32 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L07 | P12(N) - 7th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 7 | 2.5 | 19.32 | 21.82 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L08 | P12(N) - 8th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 8 | 2.5 | 21.82 | 24.32 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L09 | P12(N) - 9th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 9 | 2.5 | 24.32 | 26.82 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L10 | P12(N) - 10th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 10 | 2.5 | 26.82 | 29.32 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L11 | P12(N) - 11th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 11 | 2.5 | 29.32 | 31.82 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L12 | P12(N) - 12th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 12 | 2.5 | 31.82 | 34.32 | Below transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L13 | P12(N) - 13th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 13 | 2.5 | 34.32 | 36.82 | Below transition → Transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L14 | P12(N) - 14th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 14 | 2.5 | 36.82 | 39.32 | Transition → Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L15 | P12(N) - 15th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 15 | 2.5 | 39.32 | 41.82 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L16 | P12(N) - 16th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 16 | 2.5 | 41.82 | 44.32 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L17 | P12(N) - 17th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 17 | 2.5 | 44.32 | 46.82 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L18 | P12(N) - 18th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 18 | 2.5 | 46.82 | 49.32 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L19 | P12(N) - 19th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 19 | 2.5 | 49.32 | 51.82 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-L20 | P12(N) - 20th Lift | Well lift | P12 | P12(N) | Middle pylon | Circular | [7 empty] | 20 | 2.23 | 51.82 | 54.05 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P12(N)-WELL-PLUG | P12(N) - Bottom Plugging | Bottom plug | P12 | P12(N) | Middle pylon | Circular | [12 empty] | Not started |  |  | 0 |  |  |  |  | Assumed — confirm
P12(A)-WELL-CAP | P12(A) - Well Cap | Well cap | P12 | P12(A) | Middle pylon | Circular | [12 empty] | Not started |  |  | 0
P12(A)-LPYL-REST | P12(A) - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P12 | P12(A) | Middle pylon | [8 empty] | 0 | 21.624 | 0 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P13-WELL-CE | P13 | Cutting edge | P13 | P13 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2026-01-16 | IPC - 26 | 2 | MPSB/Sur/2645 · MPSB/Sur/2686
P13-WELL-L00 | P13 - Well Curb | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 0 | 6.2 | 0 | 6.2 | Curb → Below transition | Cast & sunk | 2026-01-31 | IPC - 26 | 4 | MPSB/Str/3607 · MPSB/Sur/2756 · MPSB/Str/3637 · MPSB/Sur/2819
P13-WELL-L01 | P13 - 1st Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 1 | 2.5 | 6.2 | 8.7 | Below transition | Cast & sunk | 2026-02-11 | IPC - 27 | 4 | MPSB/Str/3771 · MPSB/Sur/2866 · MPSB/Str/3772 · MPSB/Sur/2908
P13-WELL-L02 | P13 - 2nd Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 2 | 2.5 | 8.7 | 11.2 | Below transition | Cast & sunk | 2026-02-17 | IPC - 27 | 4 | MPSB/Str/3848 · MPSB/Sur/2922 · MPSB/Str/3849 · MPSB/Sur/2948
P13-WELL-L03 | P13 - 3rd Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 3 | 2.5 | 11.2 | 13.7 | Below transition | Cast & sunk | 2026-02-23 | IPC - 27 | 4 | MPSB/Str/3894 · MPSB/Sur/2955 · MPSB/Str/3895 · MPSB/Sur/2978
P13-WELL-L04 | P13 - 4th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 13.7 | 16.2 | Below transition | Cast & sunk | 2026-02-27 | IPC - 27 | 3 | MPSB/Str/3979 · MPSB/Sur/3019 · MPSB/Str/3980
P13-WELL-L05 | P13 - 5th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 16.2 | 18.7 | Below transition | Cast & sunk | 2026-03-07 | IPC - 29 | 3 | MPSB/Str/4056 · MPSB/Sur/3069 · MPSB/Str/4057
P13-WELL-L06 | P13 - 6th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 18.7 | 21.2 | Below transition | Cast & sunk | 2026-03-18 | IPC - 29 | 3 | MPSB/Str/4143 · MPSB/Sur/3142 · MPSB/Str/4144
P13-WELL-L07 | P13 - 7th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 21.2 | 23.7 | Below transition | Cast & sunk | 2026-03-24 | IPC - 29 | 3 | MPSB/Str/4191 · MPSB/Sur/3164 · MPSB/Str/4192
P13-WELL-L08 | P13 - 8th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 8 | 2.5 | 23.7 | 26.2 | Below transition → Transition | Cast & sunk | 2026-03-31 | IPC - 29 | 3 | MPSB/Str/4272 · MPSB/Sur/3209 · MPSB/Str/4273
P13-WELL-L09 | P13 - 9th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 9 | 2.5 | 26.2 | 28.7 | Transition | Cast & sunk | 2026-04-10 | IPC - 30 | 3 | MPSB/Str/4359 · MPSB/Sur/3264 · MPSB/Str/4360
P13-WELL-L10 | P13 - 10th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 10 | 2.5 | 28.7 | 31.2 | Transition → Above transition | Cast & sunk | 2026-04-16 | IPC - 30 | 3 | MPSB/Str/4416 · MPSB/Sur/3307 · MPSB/Str/4417
P13-WELL-L11 | P13 - 11th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 11 | 2.7 | 31.2 | 33.9 | Above transition | Cast & sunk | 2026-04-29 | IPC - 30 | 3 | MPSB/Str/4527 · MPSB/Sur/3382 · MPSB/Str/4528
P13-WELL-L12 | P13 - 12th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 12 | 2.5 | 33.9 | 36.4 | Above transition | Cast & sunk | 2026-04-30 | IPC - 30 | 3 | MPSB/Str/4543 · MPSB/Sur/3394 · MPSB/Str/4544 | Y
P13-WELL-L13 | P13 - 13th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 36.4 | 38.9 | Above transition | Cast & sunk | 2026-05-23 | IPC - 31 | 3 | MPSB/Str/4764 · MPSB/Sur/3536 · MPSB/Str/4765
P13-WELL-L14 | P13 - 14th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 38.9 | 41.4 | Above transition | Cast & sunk | 2026-06-18 | IPC - 33 | 3 | MPSB/Str/4943 · MPSB/Sur/3664 · MPSB/Str/4944
P13-WELL-L15 | P13 - 15th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 41.4 | 43.9 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P13-WELL-L16 | P13 - 16th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 43.9 | 46.4 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P13-WELL-L17 | P13 - 17th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 46.4 | 48.9 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P13-WELL-L18 | P13 - 18th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 18 | 2.5 | 48.9 | 51.4 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P13-WELL-L19 | P13 - 19th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 19 | 2.5 | 51.4 | 53.9 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P13-WELL-L20 | P13 - 20th Lift | Well lift | P13 | P13 | Outer pylon | Double-D | [7 empty] | 20 | 0.15 | 53.9 | 54.05 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P13-WELL-PLUG | P13 - Bottom Plugging | Bottom plug | P13 | P13 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P13-WELL-CAP | P13 - Well Cap | Well cap | P13 | P13 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P13-LPYL-REST | P13 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P13 | P13 | Outer pylon | [8 empty] | 0 | 21.324 | 0 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P14-WELL-CE | P14 | Cutting edge | P14 | P14 | EJ pier | Circular | [12 empty] | Shutter & scaffold done | 2025-02-12 | IPC - 11 | 2 | MPSB/Sur/441 · MPSB/Sur/460 |  |  |  | Abandoned (toppled)
P14-WELL-L00 | P14 - Well Curb | Well lift | P14 | P14 | EJ pier | Circular | [7 empty] | 0 | 0 |  |  |  | Reversed (toppled) | 2025-02-25 | IPC - 11 | 5 | MPSB/Str/566 · MPSB/Sur/500 · MPSB/Str/592 · MPSB/Sur/551 · MPSB/Sur/552 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P14-WELL-L01 | P14 - 1st Lift | Well lift | P14 | P14 | EJ pier | Circular | [7 empty] | 1 | 0 |  |  |  | Reversed (toppled) | 2025-02-28 | IPC - 11 | 3 | MPSB/Str/668 · MPSB/Sur/591 · MPSB/Str/669 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P14-WELL-L02 | P14 - 2nd Lift | Well lift | P14 | P14 | EJ pier | Circular | [7 empty] | 2 | 0 |  |  |  | Reversed (toppled) | 2025-03-13 | IPC - 13 | 3 | MPSB/Str/799 · MPSB/Str/800 · MPSB/Sur/707 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P14-WELL-L03 | P14 - 3rd Lift | Well lift | P14 | P14 | EJ pier | Circular | [7 empty] | 3 | 0 |  |  |  | Reversed (toppled) | 2025-03-22 | IPC - 13 | 3 | MPSB/Str/858 · MPSB/Str/859 · MPSB/Sur/765 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P14-WELL-L04 | P14 - 4th Lift | Well lift | P14 | P14 | EJ pier | Circular | [7 empty] | 4 | 0 |  |  |  | Reversed (toppled) | 2025-03-29 | IPC - 13 | 3 | MPSB/Str/926 · MPSB/Str/927 · MPSB/Sur/841 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P14-WELL-L05 | P14 - 5th Lift | Well lift | P14 | P14 | EJ pier | Circular | [7 empty] | 5 | 0 |  |  |  | Reversed (toppled) | 2025-03-31 | IPC - 13 | 3 | MPSB/Sur/861 · MPSB/Str/995 · MPSB/Str/996 |  |  |  | Cast, then reversed in IPC-26 (toppled well)
P14-WELL-L06 | P14 - 6th Lift | Well lift | P14 | P14 | EJ pier | Circular | [7 empty] | 6 | 0 |  |  |  | Reversed (toppled) | 2025-04-26 | IPC - 14 | 4 | MPSB/Str/1142 · MPSB/Sur/1001 · MPSB/Str/1143 · MPSB/Sur/1120 | Y |  |  | Cast, then reversed in IPC-26 (toppled well)
P14-WELL-L07 | P14 - 7th Lift | Well lift | P14 | P14 | EJ pier | Circular | [7 empty] | 7 | 0 |  |  |  | Reversed (toppled) | 2025-04-26 | IPC - 14 | 4 | MPSB/Str/1214 · MPSB/Sur/1056 · MPSB/Str/1215 · MPSB/Sur/1120 | Y |  |  | Cast, then reversed in IPC-26 (toppled well)
P14(N)-WELL-CE | P14(N) | Cutting edge | P14 | P14(N) | EJ pier | Circular | [12 empty] | Shutter & scaffold done | 2025-12-22 | IPC - 26 | 3 | MPSB/MB/457 · MPSB/Sur/2435 · MPSB/Sur/2466
P14(N)-WELL-L00 | P14(N) - Well Curb | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 0 | 4.48 | 0 | 4.48 | Curb → Below transition | Cast & sunk | 2026-01-03 | IPC - 26 | 5 | MPSB/Str/3229 · MPSB/Sur/2510 · MPSB/Str/3292 · MPSB/Sur/2582 · MPSB/Sur/2592
P14(N)-WELL-L01 | P14(N) - 1st Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 1 | 2.5 | 4.48 | 6.98 | Below transition | Cast & sunk | 2026-01-09 | IPC - 26 | 4 | MPSB/Str/3422 · MPSB/Sur/2603 · MPSB/Str/3423 · MPSB/Sur/2636
P14(N)-WELL-L02 | P14(N) - 2nd Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 2 | 2.5 | 6.98 | 9.48 | Below transition | Cast & sunk | 2026-01-17 | IPC - 26 | 4 | MPSB/Str/3477 · MPSB/Sur/2646 · MPSB/Str/3478 · MPSB/Sur/2704 | Y
P14(N)-WELL-L03 | P14(N) - 3rd Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 3 | 2.5 | 9.48 | 11.98 | Below transition | Cast & sunk | 2026-01-17 | IPC - 26 | 4 | MPSB/Str/3519 · MPSB/Sur/2676 · MPSB/Str/3520 · MPSB/Sur/2704 | Y
P14(N)-WELL-L04 | P14(N) - 4th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 4 | 2.5 | 11.98 | 14.48 | Below transition | Cast & sunk | 2026-01-21 | IPC - 26 | 3 | MPSB/Str/3597 · MPSB/Sur/2732 · MPSB/Str/3598
P14(N)-WELL-L05 | P14(N) - 5th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 5 | 2.5 | 14.48 | 16.98 | Below transition | Cast & sunk | 2026-01-27 | IPC - 26 | 3 | MPSB/Str/3657 · MPSB/Sur/2780 · MPSB/Str/3658
P14(N)-WELL-L06 | P14(N) - 6th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 6 | 2.5 | 16.98 | 19.48 | Below transition | Cast & sunk | 2026-01-31 | IPC - 26 | 3 | MPSB/Str/3713 · MPSB/Sur/2817 · MPSB/Str/3714
P14(N)-WELL-L07 | P14(N) - 7th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 7 | 2.5 | 19.48 | 21.98 | Below transition | Cast & sunk | 2026-02-11 | IPC - 27 | 4 | MPSB/Str/3758 · MPSB/Sur/2852 · MPSB/Str/3759 · MPSB/Sur/2910
P14(N)-WELL-L08 | P14(N) - 8th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 8 | 3.32 | 21.98 | 25.3 | Below transition → Transition → Above transition | Cast & sunk | 2026-02-27 | IPC - 27 | 3 | MPSB/Str/3977 · MPSB/Sur/3018 · MPSB/Str/3978
P14(N)-WELL-L09 | P14(N) - 9th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 9 | 2.5 | 25.3 | 27.8 | Above transition | Cast & sunk | 2026-03-13 | IPC - 29 | 3 | MPSB/Str/4097 · MPSB/Sur/3109 · MPSB/Str/4096
P14(N)-WELL-L10 | P14(N) - 10th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 10 | 2.5 | 27.8 | 30.3 | Above transition | Cast & sunk | 2026-03-20 | IPC - 29 | 3 | MPSB/Str/4162 · MPSB/Sur/3151 · MPSB/Str/4163
P14(N)-WELL-L11 | P14(N) - 11th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 11 | 2.5 | 30.3 | 32.8 | Above transition | Cast & sunk | 2026-03-30 | IPC - 29 | 3 | MPSB/Str/4259 · MPSB/Sur/3203 · MPSB/Str/4260
P14(N)-WELL-L12 | P14(N) - 12th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 12 | 2.8 | 32.8 | 35.6 | Above transition | Cast & sunk | 2026-04-04 | IPC - 30 | 3 | MPSB/Str/4322 · MPSB/Sur/3240 · MPSB/Str/4323
P14(N)-WELL-L13 | P14(N) - 13th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 13 | 2.2 | 35.6 | 37.8 | Above transition | Cast & sunk | 2026-04-13 | IPC - 30 | 3 | MPSB/Str/4395 · MPSB/Sur/3295 · MPSB/Str/4394
P14(N)-WELL-L14 | P14(N) - 14th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 14 | 2.8 | 37.8 | 40.6 | Above transition | Cast & sunk | 2026-04-21 | IPC - 30 | 3 | MPSB/Str/4455 · MPSB/Sur/3333 · MPSB/Str/4456
P14(N)-WELL-L15 | P14(N) - 15th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 15 | 2.5 | 40.6 | 43.1 | Above transition | Cast & sunk | 2026-05-13 | IPC - 31 | 3 | MPSB/Str/4666 · MPSB/Sur/3474 · MPSB/Str/4667
P14(N)-WELL-L16 | P14(N) - 16th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 16 | 2.5 | 43.1 | 45.6 | Above transition | Cast & sunk | 2026-05-25 | IPC - 31 | 3 | MPSB/Str/4779 · MPSB/Sur/3545 · MPSB/Str/4780
P14(N)-WELL-L17 | P14(N) - 17th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 17 | 2.5 | 45.6 | 48.1 | Above transition | Cast & sunk | 2026-06-12 | IPC - 33 | 3 | MPSB/Str/4894 · MPSB/Sur/3639 · MPSB/Str/4895
P14(N)-WELL-L18 | P14(N) - 18th Lift | Well lift | P14 | P14(N) | EJ pier | Circular | [7 empty] | 18 | 2.45 | 48.1 | 50.55 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P14(N)-WELL-PLUG | P14(N) - Bottom Plugging | Bottom plug | P14 | P14(N) | EJ pier | Circular | [12 empty] | Not started |  |  | 0
P14(N)-WELL-CAP | P14(N) - Well Cap | Well cap | P14 | P14(N) | EJ pier | Circular | [12 empty] | Not started |  |  | 0
P14(N)-LPYL-REST | P14(N) - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P14 | P14(N) | EJ pier | [8 empty] | 0 | 21.624 | 0 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P15-WELL-CE | P15 | Cutting edge | P15 | P15 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2025-01-27 | IPC - 10 | 2 | MPSB/Sur/333 · MPSB/Sur/367
P15-WELL-L00 | P15 - Well Curb | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 0 | 6.2 | 0 | 6.2 | Curb → Below transition | Cast & sunk | 2025-02-23 | IPC - 11 | 5 | MPSB/Str/508 · MPSB/Sur/457 · MPSB/Str/526 · MPSB/Sur/515 · MPSB/Sur/536
P15-WELL-L01 | P15 - 1st Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 1 | 2.66 | 6.2 | 8.86 | Below transition | Cast & sunk | 2025-02-28 | IPC - 11 | 3 | MPSB/Str/670 · MPSB/Sur/592 · MPSB/Str/671
P15-WELL-L02 | P15 - 2nd Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 2 | 2.49 | 8.86 | 11.35 | Below transition | Cast & sunk | 2025-03-18 | IPC - 13 | 4 | MPSB/Str/797 · MPSB/Str/798 · MPSB/Sur/706 · MPSB/Sur/734
P15-WELL-L03 | P15 - 3rd Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 3 | 2.5 | 11.35 | 13.85 | Below transition | Cast & sunk | 2025-03-24 | IPC - 13 | 3 | MPSB/Str/886 · MPSB/Str/887 · MPSB/Sur/777
P15-WELL-L04 | P15 - 4th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 13.85 | 16.35 | Below transition | Cast & sunk | 2025-03-31 | IPC - 13 | 3 | MPSB/Str/997 · MPSB/Str/998 · MPSB/Sur/862
P15-WELL-L05 | P15 - 5th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 16.35 | 18.85 | Below transition | Cast & sunk | 2025-04-12 | IPC - 14 | 3 | MPSB/Str/1107 · MPSB/Sur/971 · MPSB/Str/1108
P15-WELL-L06 | P15 - 6th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 18.85 | 21.35 | Below transition | Cast & sunk | 2025-04-17 | IPC - 14 | 3 | MPSB/Str/1176 · MPSB/Sur/1023 · MPSB/Str/1177
P15-WELL-L07 | P15 - 7th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 21.35 | 23.85 | Below transition | Cast & sunk | 2025-04-23 | IPC - 14 | 3 | MPSB/Str/1234 · MPSB/Sur/1067 · MPSB/Str/1235
P15-WELL-L08 | P15 - 8th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 8 | 2.5 | 23.85 | 26.35 | Below transition → Transition | Cast & sunk | 2025-05-16 | IPC - 15 | 4 | MPSB/Str/1474 · MPSB/Sur/1254 · MPSB/Str/1475 · MPSB/Sur/1289
P15-WELL-L09 | P15 - 9th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 9 | 2.5 | 26.35 | 28.85 | Transition | Cast & sunk | 2025-05-26 | IPC - 15 | 4 | MPSB/Str/1538 · MPSB/Sur/1325 · MPSB/Str/1539 · MPSB/Sur/1347
P15-WELL-L10 | P15 - 10th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 10 | 2.5 | 28.85 | 31.35 | Transition → Above transition | Cast & sunk | 2025-05-30 | IPC - 15 | 3 | MPSB/Str/1604 · MPSB/Sur/1388 · MPSB/Str/1605
P15-WELL-L11 | P15 - 11th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 11 | 2.34 | 31.35 | 33.69 | Above transition | Cast & sunk | 2025-10-27 | IPC - 22 | 3 | MPSB/Str/2591 · MPSB/Sur/2054 · MPSB/Str/2592
P15-WELL-L12 | P15 - 12th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 12 | 3.17 | 33.69 | 36.86 | Above transition | Cast & sunk | 2025-10-31 | IPC - 23 | 3 | MPSB/Str/2654 · MPSB/Sur/2088 · MPSB/Str/2655
P15-WELL-L13 | P15 - 13th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 36.86 | 39.36 | Above transition | Cast & sunk | 2025-12-10 | IPC - 25 | 3 | MPSB/Str/3094 · MPSB/Sur/2378 · MPSB/Str/3095
P15-WELL-L14 | P15 - 14th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 39.36 | 41.86 | Above transition | Cast & sunk | 2025-12-19 | IPC - 25 | 3 | MPSB/Str/3194 · MPSB/Sur/2446 · MPSB/Str/3195
P15-WELL-L15 | P15 - 15th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 41.86 | 44.36 | Above transition | Cast & sunk | 2025-12-29 | IPC - 25 | 3 | MPSB/Str/3317 · MPSB/Sur/2529 · MPSB/Str/3318
P15-WELL-L16 | P15 - 16th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 44.36 | 46.86 | Above transition | Cast & sunk | 2026-01-07 | IPC - 26 | 3 | MPSB/Str/3444 · MPSB/Sur/2620 · MPSB/Str/3445
P15-WELL-L17 | P15 - 17th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 46.86 | 49.36 | Above transition | Cast & sunk | 2026-02-25 | IPC - 27 | 4 | MPSB/Str/3886 · MPSB/Sur/2951 · MPSB/Str/3887 · MPSB/Sur/2990
P15-WELL-L18 | P15 - 18th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 18 | 2 | 49.36 | 51.36 | Above transition | Cast & sunk | 2026-03-12 | IPC - 29 | 3 | MPSB/Str/4091 · MPSB/Sur/3105 · MPSB/Str/4092
P15-WELL-L19 | P15 - 19th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 19 | 1.6 | 51.36 | 52.96 | Above transition | Cast & sunk | 2026-04-20 | IPC - 30 | 3 | MPSB/Str/4442 · MPSB/Sur/3329 · MPSB/Str/4443
P15-WELL-L20 | P15 - 20th Lift | Well lift | P15 | P15 | Outer pylon | Double-D | [7 empty] | 20 | 1.09 | 52.96 | 54.05 | Above transition | Cast & sunk | 2026-05-11 | IPC - 31 | 3 | MPSB/Str/4637 · MPSB/Sur/3455 · MPSB/Str/4638
P15-WELL-PLUG | P15 - Bottom Plugging | Bottom plug | P15 | P15 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P15-WELL-CAP | P15 - Well Cap | Well cap | P15 | P15 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P15-LPYL-REST | P15 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P15 | P15 | Outer pylon | [8 empty] | 0 | 21.324 | 0 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P16-WELL-CE | P16 | Cutting edge | P16 | P16 | Middle pylon | Circular | [12 empty] | Shutter & scaffold done | 2024-12-14 | IPC - 09 | 2 | MPSB/Sur/185 · MPSB/Sur/205
P16-WELL-L00 | P16 - Well Curb | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Cast & sunk | 2024-12-29 | IPC - 09 | 4 | MPSB/Str/235 · MPSB/Str/236 · MPSB/Str/276 · MPSB/Str/277
P16-WELL-L01 | P16 - 1st Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 1 | 2.65 | 4.32 | 6.97 | Below transition | Cast & sunk | 2025-01-17 | IPC - 10 | 4 | MPSB/Str/331 · MPSB/Sur/270 · MPSB/Str/349 · MPSB/Sur/309
P16-WELL-L02 | P16 - 2nd Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 2 | 2.5 | 6.97 | 9.47 | Below transition | Cast & sunk | 2025-01-21 | IPC - 10 | 3 | MPSB/Str/394 · MPSB/Sur/334 · MPSB/Str/395
P16-WELL-L03 | P16 - 3rd Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 3 | 2.5 | 9.47 | 11.97 | Below transition | Cast & sunk | 2025-01-30 | IPC - 10 | 4 | MPSB/Str/431 · MPSB/Sur/366 · MPSB/Str/441 · MPSB/Sur/389
P16-WELL-L04 | P16 - 4th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 4 | 2.5 | 11.97 | 14.47 | Below transition | Cast & sunk | 2025-02-18 | IPC - 11 | 4 | MPSB/Str/492 · MPSB/Sur/437 · MPSB/Str/503 · MPSB/Sur/489 | Y
P16-WELL-L05 | P16 - 5th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 5 | 2.5 | 14.47 | 16.97 | Below transition | Cast & sunk | 2025-02-18 | IPC - 11 | 4 | MPSB/Str/540 · MPSB/Sur/466 · MPSB/Str/539 · MPSB/Sur/489 | Y
P16-WELL-L06 | P16 - 6th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 6 | 2.5 | 16.97 | 19.47 | Below transition | Cast & sunk | 2025-02-25 | IPC - 11 | 3 | MPSB/Str/616 · MPSB/Sur/549 · MPSB/Str/624
P16-WELL-L07 | P16 - 7th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 7 | 2.51 | 19.47 | 21.98 | Below transition | Cast & sunk | 2025-03-11 | IPC - 13 | 4 | MPSB/Sur/679 · MPSB/Str/767 · MPSB/Str/768 · MPSB/Sur/699
P16-WELL-L08 | P16 - 8th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 8 | 2.8 | 21.98 | 24.78 | Below transition | Cast & sunk | 2025-03-26 | IPC - 13 | 3 | MPSB/Str/912 · MPSB/Str/913 · MPSB/Sur/797
P16-WELL-L09 | P16 - 9th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 9 | 2.8 | 24.78 | 27.58 | Below transition | Cast & sunk | 2025-03-31 | IPC - 13 | 3 | MPSB/Str/989 · MPSB/Str/990 · MPSB/Sur/858
P16-WELL-L10 | P16 - 10th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 10 | 2.5 | 27.58 | 30.08 | Below transition | Cast & sunk | 2025-05-07 | IPC - 15 | 3 | MPSB/Str/1436 · MPSB/Sur/1230 · MPSB/Str/1437
P16-WELL-L11 | P16 - 11th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 11 | 2.5 | 30.08 | 32.58 | Below transition | Cast & sunk | 2025-05-20 | IPC - 15 | 4 | MPSB/Str/1491 · MPSB/Sur/1278 · MPSB/Str/1492 · MPSB/Sur/1319
P16-WELL-L12 | P16 - 12th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 12 | 2.5 | 32.58 | 35.08 | Below transition → Transition | Cast & sunk | 2025-07-03 | IPC - 18 | 3 | MPSB/Str/1753 · MPSB/Sur/1484 · MPSB/Str/1754
P16-WELL-L13 | P16 - 13th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 13 | 3.15 | 35.08 | 38.23 | Transition → Above transition | Cast & sunk | 2025-07-25 | IPC - 18 | 3 | MPSB/Str/1883 · MPSB/Sur/1577 · MPSB/Str/1884
P16-WELL-L14 | P16 - 14th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 14 | 2.5 | 38.23 | 40.73 | Above transition | Cast & sunk | 2025-08-26 | IPC - 19 | 4 | MPSB/Str/1970 · MPSB/Sur/1643 · MPSB/Str/1971 · MPSB/Sur/1732
P16-WELL-L15 | P16 - 15th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 15 | 2.5 | 40.73 | 43.23 | Above transition | Cast & sunk | 2025-08-27 | IPC - 19 | 3 | MPSB/Str/2094 · MPSB/Sur/1735 · MPSB/Str/2095
P16-WELL-L16 | P16 - 16th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 16 | 2.5 | 43.23 | 45.73 | Above transition | Cast & sunk | 2025-09-08 | IPC - 20 | 4 | MPSB/Str/2147 · MPSB/Sur/1766 · MPSB/Str/2148 · MPSB/Sur/1788
P16-WELL-L17 | P16 - 17th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 17 | 2.5 | 45.73 | 48.23 | Above transition | Cast & sunk | 2025-09-22 | IPC - 20 | 3 | MPSB/Str/2290 · MPSB/Sur/1855 · MPSB/Str/2291
P16-WELL-L18 | P16 - 18th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 18 | 2.5 | 48.23 | 50.73 | Above transition | Cast & sunk | 2025-09-29 | IPC - 20 | 3 | MPSB/Str/2337 · MPSB/Sur/1884 · MPSB/Str/2338
P16-WELL-L19 | P16 - 19th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 19 | 2.5 | 50.73 | 53.23 | Above transition | Cast & sunk | 2025-10-13 | IPC - 22 | 3 | MPSB/Str/2458 · MPSB/Sur/1971 · MPSB/Str/2459
P16-WELL-L20 | P16 - 20th Lift | Well lift | P16 | P16 | Middle pylon | Circular | [7 empty] | 20 | 0.82 | 53.23 | 54.05 | Above transition | Cast & sunk | 2025-10-20 | IPC - 22 | 3 | MPSB/Str/2530 · MPSB/Sur/2016 · MPSB/Str/2531
P16-WELL-PLUG | P16 - Bottom Plugging | Bottom plug | P16 | P16 | Middle pylon | Circular | [12 empty] | Not started |  |  | 0
P16-WELL-CAP | P16 - Well Cap | Well cap | P16 | P16 | Middle pylon | Circular | [12 empty] | Not started |  |  | 0
P16-LPYL-REST | P16 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P16 | P16 | Middle pylon | [8 empty] | 0 | 21.624 | 0 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P17-WELL-CE | P17 | Cutting edge | P17 | P17 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2025-01-13 | IPC - 10 | 2 | MPSB/Sur/202 · MPSB/Sur/294
P17-WELL-L00 | P17 - Well Curb | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 0 | 6.04 | 0 | 6.04 | Curb | Cast & sunk | 2025-01-30 | IPC - 10 | 2 | MPSB/Str/439 · MPSB/Str/455
P17-WELL-L01 | P17 - 1st Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 1 | 2.16 | 6.04 | 8.2 | Below transition | Cast & sunk | 2025-02-27 | IPC - 11 | 4 | MPSB/Str/602 · MPSB/Sur/529 · MPSB/Str/603 · MPSB/Sur/583
P17-WELL-L02 | P17 - 2nd Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 2 | 1.15 | 8.2 | 9.35 | Below transition | Cast & sunk | 2025-02-27 | IPC - 11 | 4 | MPSB/Str/604 · MPSB/Sur/530 · MPSB/Str/605 · MPSB/Sur/585
P17-WELL-L03 | P17 - 3rd Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 3 | 2.5 | 9.35 | 11.85 | Below transition | Cast & sunk | 2025-02-28 | IPC - 11 | 3 | MPSB/Str/674 · MPSB/Sur/594 · MPSB/Str/675
P17-WELL-L04 | P17 - 4th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 11.85 | 14.35 | Below transition | Cast & sunk | 2025-03-15 | IPC - 13 | 4 | MPSB/Str/769 · MPSB/Str/770 · MPSB/Sur/680 · MPSB/Sur/720
P17-WELL-L05 | P17 - 5th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 14.35 | 16.85 | Below transition | Cast & sunk | 2025-03-21 | IPC - 13 | 4 | MPSB/Str/810 · MPSB/Str/811 · MPSB/Sur/722 · MPSB/Sur/756
P17-WELL-L06 | P17 - 6th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 16.85 | 19.35 | Below transition | Cast & sunk | 2025-03-31 | IPC - 13 | 3 | MPSB/Str/993 · MPSB/Str/994 · MPSB/Sur/860
P17-WELL-L07 | P17 - 7th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 19.35 | 21.85 | Below transition | Cast & sunk | 2025-04-23 | IPC - 14 | 4 | MPSB/Str/1088 · MPSB/Sur/952 · MPSB/Str/1089 · MPSB/Sur/1069
P17-WELL-L08 | P17 - 8th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 8 | 2.5 | 21.85 | 24.35 | Below transition | Cast & sunk | 2025-04-19 | IPC - 14 | 3 | MPSB/Str/1189 · MPSB/Sur/1032 · MPSB/Str/1190
P17-WELL-L09 | P17 - 9th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 9 | 1.05 | 24.35 | 25.4 | Below transition | Cast & sunk | 2025-05-10 | IPC - 15 | 3 | MPSB/Str/1462 · MPSB/Sur/1249 · MPSB/Str/1463
P17-WELL-L10 | P17 - 10th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 10 | 1.88 | 25.4 | 27.28 | Below transition → Transition | Cast & sunk | 2025-05-28 | IPC - 15 | 3 | MPSB/Str/1588 · MPSB/Sur/1371 · MPSB/Str/1589
P17-WELL-L11 | P17 - 11th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 11 | 3.63 | 27.28 | 30.91 | Transition → Above transition | Cast & sunk | 2025-06-18 | IPC - 16 | 3 | MPSB/Str/1676 · MPSB/Sur/1435 · MPSB/Str/1677
P17-WELL-L12 | P17 - 12th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 12 | 2.65 | 30.91 | 33.56 | Above transition | Cast & sunk | 2025-08-28 | IPC - 19 | 3 | MPSB/Str/2101 · MPSB/Sur/1737 · MPSB/Str/2102
P17-WELL-L13 | P17 - 13th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 33.56 | 36.06 | Above transition | Cast & sunk | 2025-09-19 | IPC - 20 | 4 | MPSB/Str/2220 · MPSB/Sur/1813 · MPSB/Str/2221 · MPSB/Sur/1837
P17-WELL-L14 | P17 - 14th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 36.06 | 38.56 | Above transition | Cast & sunk | 2025-09-30 | IPC - 20 | 3 | MPSB/Str/2365 · MPSB/Sur/1894 · MPSB/Str/2366
P17-WELL-L15 | P17 - 15th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 38.56 | 41.06 | Above transition | Cast & sunk | 2025-10-18 | IPC - 22 | 3 | MPSB/Str/2512 · MPSB/Sur/2005 · MPSB/Str/2513
P17-WELL-L16 | P17 - 16th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 41.06 | 43.56 | Above transition | Cast & sunk | 2025-10-28 | IPC - 22 | 3 | MPSB/Str/2611 · MPSB/Sur/2062 · MPSB/Str/2612
P17-WELL-L17 | P17 - 17th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 43.56 | 46.06 | Above transition | Cast & sunk | 2026-01-24 | IPC - 26 | 4 | MPSB/Str/3569 · MPSB/Sur/2711 · MPSB/Str/3570 · MPSB/Sur/2767
P17-WELL-L18 | P17 - 18th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 18 | 2.5 | 46.06 | 48.56 | Above transition | Cast & sunk | 2026-02-28 | IPC - 27 | 4 | MPSB/Str/3797 · MPSB/Sur/2887 · MPSB/Str/3798 · MPSB/Sur/3053 | Y
P17-WELL-L19 | P17 - 19th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 19 | 2.5 | 48.56 | 51.06 | Above transition | Cast & sunk | 2026-02-28 | IPC - 27 | 4 | MPSB/Str/3922 · MPSB/Sur/2974 · MPSB/Str/3923 · MPSB/Sur/3053 | Y
P17-WELL-L20 | P17 - 20th Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 20 | 1.85 | 51.06 | 52.91 | Above transition | Cast & sunk | 2026-04-24 | IPC - 30 | 3 | MPSB/Str/4475 · MPSB/Sur/3347 · MPSB/Str/4476
P17-WELL-L21 | P17 - 21st Lift | Well lift | P17 | P17 | Outer pylon | Double-D | [7 empty] | 21 | 1.14 | 52.91 | 54.05 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P17-WELL-PLUG | P17 - Bottom Plugging | Bottom plug | P17 | P17 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P17-WELL-CAP | P17 - Well Cap | Well cap | P17 | P17 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P17-LPYL-REST | P17 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P17 | P17 | Outer pylon | [8 empty] | 0 | 21.324 | 0 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P18-WELL-CE | P18 | Cutting edge | P18 | P18 | EJ pier | Circular | [12 empty] | Shutter & scaffold done | 2024-12-14 | IPC - 09 | 2 | MPSB/Sur/167 · MPSB/Sur/191
P18-WELL-L00 | P18 - Well Curb | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Cast & sunk | 2024-12-31 | IPC - 09 | 4 | MPSB/Str/250 · MPSB/Str/264 · MPSB/Str/301 · MPSB/Str/302
P18-WELL-L01 | P18 - 1st Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 1 | 2.65 | 4.32 | 6.97 | Below transition | Cast & sunk | 2025-01-16 | IPC - 10 | 4 | MPSB/Str/346 · MPSB/Sur/284 · MPSB/Str/353 · MPSB/Sur/306
P18-WELL-L02 | P18 - 2nd Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 2 | 2.5 | 6.97 | 9.47 | Below transition | Cast & sunk | 2025-01-25 | IPC - 10 | 4 | MPSB/Str/385 · MPSB/Sur/325 · MPSB/Str/386 · MPSB/Sur/361
P18-WELL-L03 | P18 - 3rd Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 3 | 2.5 | 9.47 | 11.97 | Below transition | Cast & sunk | 2025-01-27 | IPC - 10 | 3 | MPSB/Str/435 · MPSB/Sur/372 · MPSB/Str/436
P18-WELL-L04 | P18 - 4th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 4 | 2.5 | 11.97 | 14.47 | Below transition | Cast & sunk | 2025-01-31 | IPC - 10 | 3 | MPSB/Str/474 · MPSB/Sur/404 · MPSB/Str/475
P18-WELL-L05 | P18 - 5th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 5 | 2.5 | 14.47 | 16.97 | Below transition | Cast & sunk | 2025-02-17 | IPC - 11 | 3 | MPSB/Str/530 · MPSB/Str/537 · MPSB/Sur/482
P18-WELL-L06 | P18 - 6th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 6 | 2.5 | 16.97 | 19.47 | Below transition | Cast & sunk | 2025-02-25 | IPC - 11 | 4 | MPSB/Str/598 · MPSB/Sur/527 · MPSB/Str/599 · MPSB/Sur/556
P18-WELL-L07 | P18 - 7th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 7 | 2.51 | 19.47 | 21.98 | Below transition | Cast & sunk | 2025-03-11 | IPC - 13 | 4 | MPSB/Str/746 · MPSB/Sur/664 · MPSB/Str/747 · MPSB/Sur/686
P18-WELL-L08 | P18 - 8th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 8 | 0.5 | 21.98 | 22.48 | Below transition → Transition | Cast & sunk | 2025-03-27 | IPC - 13 | 3 | MPSB/Str/928 · MPSB/Sur/807 · MPSB/Str/929
P18-WELL-L09 | P18 - 9th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 9 | 2.8 | 22.48 | 25.28 | Transition → Above transition | Cast & sunk | 2025-03-28 | IPC - 13 | 3 | MPSB/Str/939 · MPSB/Str/940 · MPSB/Sur/818
P18-WELL-L10 | P18 - 10th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 10 | 2.5 | 25.28 | 27.78 | Above transition | Cast & sunk | 2025-04-21 | IPC - 14 | 3 | MPSB/Str/1191 · MPSB/Sur/1037 · MPSB/Str/1220
P18-WELL-L11 | P18 - 11th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 11 | 2.5 | 27.78 | 30.28 | Above transition | Cast & sunk | 2025-04-24 | IPC - 14 | 3 | MPSB/Str/1240 · MPSB/Sur/1074 · MPSB/Str/1241
P18-WELL-L12 | P18 - 12th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 12 | 2.5 | 30.28 | 32.78 | Above transition | Cast & sunk | 2025-07-24 | IPC - 18 | 4 | MPSB/Str/1751 · MPSB/Sur/1483 · MPSB/Str/1752 · MPSB/Sur/1574 | Y
P18-WELL-L13 | P18 - 13th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 13 | 2.5 | 32.78 | 35.28 | Above transition | Cast & sunk | 2025-07-24 | IPC - 18 | 4 | MPSB/Str/1784 · MPSB/Sur/1505 · MPSB/Str/1785 · MPSB/Sur/1574 | Y
P18-WELL-L14 | P18 - 14th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 14 | 2.5 | 35.28 | 37.78 | Above transition | Cast & sunk | 2025-07-15 | IPC - 18 | 3 | MPSB/Str/1815 · MPSB/Sur/1529 · MPSB/Str/1816
P18-WELL-L15 | P18 - 15th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 15 | 2.3 | 37.78 | 40.08 | Above transition | Cast & sunk | 2025-08-11 | IPC - 19 | 4 | MPSB/Str/1928 · MPSB/Sur/1614 · MPSB/Str/1929 · MPSB/Sur/1677 | Y
P18-WELL-L16 | P18 - 16th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 16 | 2.6 | 40.08 | 42.68 | Above transition | Cast & sunk | 2025-08-11 | IPC - 19 | 4 | MPSB/Str/1996 · MPSB/Sur/1658 · MPSB/Str/1997 · MPSB/Sur/1677 | Y
P18-WELL-L17 | P18 - 17th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 17 | 2.5 | 42.68 | 45.18 | Above transition | Cast & sunk | 2025-08-29 | IPC - 19 | 3 | MPSB/Str/2107 · MPSB/Sur/1745 · MPSB/Str/2108
P18-WELL-L18 | P18 - 18th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 18 | 2.6 | 45.18 | 47.78 | Above transition | Cast & sunk | 2025-09-06 | IPC - 20 | 3 | MPSB/Str/2159 · MPSB/Sur/1777 · MPSB/Str/2160
P18-WELL-L19 | P18 - 19th Lift | Well lift | P18 | P18 | EJ pier | Circular | [7 empty] | 19 | 2.77 | 47.78 | 50.55 | Above transition | Cast & sunk | 2025-09-29 | IPC - 20 | 3 | MPSB/Str/2339 · MPSB/Sur/1885 · MPSB/Str/2340
P18-WELL-PLUG | P18 - Bottom Plugging | Bottom plug | P18 | P18 | EJ pier | Circular | [12 empty] | Not started |  |  | 0
P18-WELL-CAP | P18 - Well Cap | Well cap | P18 | P18 | EJ pier | Circular | [12 empty] | Not started |  |  | 0
P18-LPYL-REST | P18 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P18 | P18 | EJ pier | [8 empty] | 0 | 21.624 | 0 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P19-WELL-CE | P19 | Cutting edge | P19 | P19 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2025-12-28 | IPC - 10 | 2 | MPSB/Sur/176 · MPSB/Sur/228
P19-WELL-L00 | P19 - Well Curb | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 0 | 6.04 | 0 | 6.04 | Curb | Cast & sunk | 2025-01-28 | IPC - 10 | 3 | MPSB/Str/359 · MPSB/Str/381 · MPSB/Sur/380
P19-WELL-L01 | P19 - 1st Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 1 | 2.65 | 6.04 | 8.69 | Below transition | Cast & sunk | 2025-02-20 | IPC - 11 | 4 | MPSB/Str/546 · MPSB/Sur/480 · MPSB/Str/562 · MPSB/Sur/511
P19-WELL-L02 | P19 - 2nd Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 2 | 2.5 | 8.69 | 11.19 | Below transition | Cast & sunk | 2025-02-27 | IPC - 11 | 4 | MPSB/Str/629 · MPSB/Sur/557 · MPSB/Str/630 · MPSB/Sur/572
P19-WELL-L03 | P19 - 3rd Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 3 | 2.51 | 11.19 | 13.7 | Below transition | Cast & sunk | 2025-03-12 | IPC - 13 | 4 | MPSB/Str/758 · MPSB/Sur/673 · MPSB/Str/759 · MPSB/Sur/701 | Y
P19-WELL-L04 | P19 - 4th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 13.7 | 16.2 | Below transition | Cast & sunk | 2025-03-26 | IPC - 13 | 4 | MPSB/Str/853 · MPSB/Sur/673 · MPSB/Str/854 · MPSB/Sur/788 | Y
P19-WELL-L05 | P19 - 5th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 16.2 | 18.7 | Below transition | Cast & sunk | 2025-03-31 | IPC - 13 | 4 | MPSB/Str/954 · MPSB/Sur/832 · MPSB/Str/955 · MPSB/Sur/876
P19-WELL-L06 | P19 - 6th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 18.7 | 21.2 | Below transition | Cast & sunk | 2025-04-12 | IPC - 14 | 4 | MPSB/Str/1069 · MPSB/Sur/940 · MPSB/Str/1070 · MPSB/Sur/977
P19-WELL-L07 | P19 - 7th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 21.2 | 23.7 | Below transition | Cast & sunk | 2025-04-21 | IPC - 14 | 4 | MPSB/Str/1134 · MPSB/Sur/996 · MPSB/Str/1135 · MPSB/Sur/1050
P19-WELL-L08 | P19 - 8th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 8 | 2 | 23.7 | 25.7 | Below transition | Cast & sunk | 2025-04-30 | IPC - 14 | 3 | MPSB/Str/1351 · MPSB/Sur/1157 · MPSB/Str/1352
P19-WELL-L09 | P19 - 9th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 9 | 2.7 | 25.7 | 28.4 | Below transition → Transition | Cast & sunk | 2025-05-26 | IPC - 15 | 4 | MPSB/Str/1506 · MPSB/Sur/1295 · MPSB/Str/1507 · MPSB/Sur/1355
P19-WELL-L10 | P19 - 10th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 10 | 2.8 | 28.4 | 31.2 | Transition → Above transition | Cast & sunk | 2025-05-22 | IPC - 15 | 3 | MPSB/Str/1548 · MPSB/Sur/1331 · MPSB/Str/1549
P19-WELL-L11 | P19 - 11th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 11 | 2.5 | 31.2 | 33.7 | Above transition | Cast & sunk | 2025-11-23 | IPC - 23 | 4 | MPSB/Str/2839 · MPSB/Sur/2213 · MPSB/Str/2840 · MPSB/Sur/2255
P19-WELL-L12 | P19 - 12th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 12 | 2.5 | 33.7 | 36.2 | Above transition | Cast & sunk | 2025-11-29 | IPC - 23 | 3 | MPSB/Str/2986 · MPSB/Sur/2302 · MPSB/Str/2987
P19-WELL-L13 | P19 - 13th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 36.2 | 38.7 | Above transition | Cast & sunk | 2025-12-20 | IPC - 25 | 4 | MPSB/Str/3148 · MPSB/Sur/2417 · MPSB/Str/3149 · MPSB/Sur/2454
P19-WELL-L14 | P19 - 14th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 38.7 | 41.2 | Above transition | Cast & sunk | 2025-12-26 | IPC - 25 | 4 | MPSB/Str/3261 · MPSB/Sur/2488 · MPSB/Str/3262 · MPSB/Sur/2504
P19-WELL-L15 | P19 - 15th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 41.2 | 43.7 | Above transition | Cast & sunk | 2025-12-30 | IPC - 25 | 3 | MPSB/Str/3352 · MPSB/Sur/2554 · MPSB/Str/3353
P19-WELL-L16 | P19 - 16th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 43.7 | 46.2 | Above transition | Cast & sunk | 2026-01-13 | IPC - 26 | 4 | MPSB/Str/3475 · MPSB/Sur/2641 · MPSB/Str/3476 · MPSB/Sur/2668
P19-WELL-L17 | P19 - 17th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 46.2 | 48.7 | Above transition | Cast & sunk | 2026-01-20 | IPC - 26 | 4 | MPSB/Str/3545 · MPSB/Sur/2697 · MPSB/Str/3546 · MPSB/Sur/2725
P19-WELL-L18 | P19 - 18th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 18 | 2.5 | 48.7 | 51.2 | Above transition | Cast & sunk | 2026-01-28 | IPC - 26 | 4 | MPSB/Str/3642 · MPSB/Sur/2758 · MPSB/Str/3643 · MPSB/Sur/2789
P19-WELL-L19 | P19 - 19th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 19 | 1.85 | 51.2 | 53.05 | Above transition | Cast & sunk | 2026-02-25 | IPC - 27 | 4 | MPSB/Str/3795 · MPSB/Sur/2886 · MPSB/Str/3796 · MPSB/Sur/2994 | Y
P19-WELL-L20 | P19 - 20th Lift | Well lift | P19 | P19 | Outer pylon | Double-D | [7 empty] | 20 | 1 | 53.05 | 54.05 | Above transition | Cast & sunk | 2026-02-25 | IPC - 27 | 4 | MPSB/Str/3880 · MPSB/Sur/2949 · MPSB/Str/3881 · MPSB/Sur/2994 | Y
P19-WELL-PLUG | P19 - Bottom Plugging | Bottom plug | P19 | P19 | Outer pylon | Double-D | [12 empty] | Plugged | 2026-03-28 | IPC - 29 | 1 | MPSB/Str/4231
P19-WELL-CAP | P19 - Well Cap | Well cap | P19 | P19 | Outer pylon | Double-D | [12 empty] | Cast | 2026-04-23 | IPC - 30 | 2 | MPSB/Sur/3342 · MPSB/Str/4470
P19-LPYL-L00 | P19 - Lower Pylon - Starter | Lower pylon / pier lift | P19 | P19 | Outer pylon | [8 empty] | 0 | 0.63 | 0 | 0.63 |  | Cast | 2026-05-06 | IPC - 31 | 3 | MPSB/Str/4588 · MPSB/Sur/3421 · MPSB/Str/4589
P19-LPYL-L01 | P19 - Lower Pylon - 1st Lift | Lower pylon / pier lift | P19 | P19 | Outer pylon | [8 empty] | 1 | 4 | 0.63 | 4.63 |  | Cast | 2026-05-19 | IPC - 31 | 3 | MPSB/Str/4725 · MPSB/Sur/3510 · MPSB/Str/4726
P19-LPYL-REST | P19 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P19 | P19 | Outer pylon | [8 empty] | 2 | 16.694 | 4.63 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P20-WELL-CE | P20 | Cutting edge | P20 | P20 | Middle pylon | Circular | [12 empty] | Shutter & scaffold done | 2024-11-25 | IPC - 08 | 2 | MPSB/Sur/103 · MPSB/Sur/127
P20-WELL-L00 | P20 - Well Curb | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Cast & sunk | 2024-12-22 | IPC - 09 | 4 | MPSB/Str/209 · MPSB/Str/210 · MPSB/Sur/210 · MPSB/Str/231
P20-WELL-L01 | P20 - 1st Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 1 | 2.65 | 4.32 | 6.97 | Below transition | Cast & sunk | 2024-12-29 | IPC - 09 | 4 | MPSB/Sur/219 · MPSB/Str/251 · MPSB/Str/252 · MPSB/Str/280
P20-WELL-L02 | P20 - 2nd Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 2 | 2.5 | 6.97 | 9.47 | Below transition | Cast & sunk | 2024-12-30 | IPC - 09 | 3 | MPSB/Sur/237 · MPSB/Str/287 · MPSB/Str/288
P20-WELL-L03 | P20 - 3rd Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 3 | 2.5 | 9.47 | 11.97 | Below transition | Cast & sunk | 2025-01-17 | IPC - 10 | 4 | MPSB/Str/338 · MPSB/Sur/272 · MPSB/Str/339 · MPSB/Sur/312
P20-WELL-L04 | P20 - 4th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 4 | 2.5 | 11.97 | 14.47 | Below transition | Cast & sunk | 2025-01-29 | IPC - 10 | 4 | MPSB/Str/420 · MPSB/Sur/352 · MPSB/Str/421 · MPSB/Sur/392
P20-WELL-L05 | P20 - 5th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 5 | 2.5 | 14.47 | 16.97 | Below transition | Cast & sunk | 2025-01-30 | IPC - 10 | 3 | MPSB/Str/456 · MPSB/Sur/385 · MPSB/Str/457
P20-WELL-L06 | P20 - 6th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 6 | 2.5 | 16.97 | 19.47 | Below transition | Cast & sunk | 2025-02-17 | IPC - 11 | 4 | MPSB/Str/506 · MPSB/Sur/440 · MPSB/Str/550 · MPSB/Sur/484
P20-WELL-L07 | P20 - 7th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 7 | 2.5 | 19.47 | 21.97 | Below transition | Cast & sunk | 2025-02-24 | IPC - 11 | 4 | MPSB/Str/587 · MPSB/Sur/521 · MPSB/Str/588 · MPSB/Sur/544
P20-WELL-L08 | P20 - 8th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 8 | 2.5 | 21.97 | 24.47 | Below transition | Cast & sunk | 2025-02-27 | IPC - 11 | 4 | MPSB/Str/631 · MPSB/Sur/558 · MPSB/Str/632 · MPSB/Sur/574
P20-WELL-L09 | P20 - 9th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 9 | 2.51 | 24.47 | 26.98 | Below transition | Cast & sunk | 2025-03-20 | IPC - 13 | 4 | MPSB/Str/812 · MPSB/Sur/725 · MPSB/Str/813 · MPSB/Sur/750
P20-WELL-L10 | P20 - 10th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 10 | 2.5 | 26.98 | 29.48 | Below transition | Cast & sunk | 2025-03-28 | IPC - 13 | 4 | MPSB/Str/865 · MPSB/Sur/769 · MPSB/Str/866 · MPSB/Sur/817
P20-WELL-L11 | P20 - 11th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 11 | 2.5 | 29.48 | 31.98 | Below transition | Cast & sunk | 2025-03-31 | IPC - 13 | 3 | MPSB/Str/1008 · MPSB/Sur/870 · MPSB/Str/1009
P20-WELL-L12 | P20 - 12th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 12 | 2.5 | 31.98 | 34.48 | Below transition | Cast & sunk | 2025-05-17 | IPC - 15 | 4 | MPSB/Str/1476 · MPSB/Sur/1259 · MPSB/Str/1477 · MPSB/Sur/1297
P20-WELL-L13 | P20 - 13th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 13 | 3.3 | 34.48 | 37.78 | Below transition → Transition → Above transition | Cast & sunk | 2025-06-21 | IPC - 16 | 3 | MPSB/Str/1690 · MPSB/Sur/1448 · MPSB/Str/1691
P20-WELL-L14 | P20 - 14th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 14 | 2.5 | 37.78 | 40.28 | Above transition | Cast & sunk | 2025-10-10 | IPC - 22 | 4 | MPSB/Str/2402 · MPSB/Sur/1923 · MPSB/Str/2403 · MPSB/Sur/1962
P20-WELL-L15 | P20 - 15th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 15 | 2.5 | 40.28 | 42.78 | Above transition | Cast & sunk | 2025-10-23 | IPC - 22 | 4 | MPSB/Str/2518 · MPSB/Sur/2008 · MPSB/Str/2519 · MPSB/Sur/2031
P20-WELL-L16 | P20 - 16th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 16 | 2.5 | 42.78 | 45.28 | Above transition | Cast & sunk | 2025-10-30 | IPC - 22 | 3 | MPSB/Str/2628 · MPSB/Sur/2069 · MPSB/Str/2629
P20-WELL-L17 | P20 - 17th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 17 | 2.5 | 45.28 | 47.78 | Above transition | Cast & sunk | 2025-11-18 | IPC - 23 | 4 | MPSB/Str/2811 · MPSB/Sur/2193 · MPSB/Str/2812 · MPSB/Sur/2215
P20-WELL-L18 | P20 - 18th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 18 | 2.7 | 47.78 | 50.48 | Above transition | Cast & sunk | 2025-11-27 | IPC - 23 | 3 | MPSB/Str/2962 · MPSB/Sur/2289 · MPSB/Str/2963
P20-WELL-L19 | P20 - 19th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 19 | 2.5 | 50.48 | 52.98 | Above transition | Cast & sunk | 2025-12-24 | IPC - 25 | 4 | MPSB/Str/3175 · MPSB/Sur/2430 · MPSB/Str/3176 · MPSB/Sur/2485
P20-WELL-L20 | P20 - 20th Lift | Well lift | P20 | P20 | Middle pylon | Circular | [7 empty] | 20 | 1.07 | 52.98 | 54.05 | Above transition | Cast & sunk | 2026-01-22 | IPC - 26 | 3 | MPSB/Str/3613 · MPSB/Sur/2742 · MPSB/Str/3614
P20-WELL-PLUG | P20 - Bottom Plugging | Bottom plug | P20 | P20 | Middle pylon | Circular | [12 empty] | Plugged | 2026-03-20 | IPC - 29 | 1 | MPSB/Str/4164
P20-WELL-CAP | P20 - Well Cap | Well cap | P20 | P20 | Middle pylon | Circular | [12 empty] | Cast | 2026-03-29 | IPC - 29 | 2 | MPSB/Sur/3195 · MPSB/Str/4237
P20-LPYL-L00 | P20 - Lower Pylon - Starter | Lower pylon / pier lift | P20 | P20 | Middle pylon | [8 empty] | 0 | 0.515 | 0 | 0.515 |  | Cast | 2026-05-12 | IPC - 31 | 3 | MPSB/Str/4660 · MPSB/Sur/3470 · MPSB/Str/4661
P20-LPYL-L01 | P20 - Lower Pylon - 1st Lift | Lower pylon / pier lift | P20 | P20 | Middle pylon | [8 empty] | 1 | 4 | 0.515 | 4.515 |  | Cast | 2026-05-22 | IPC - 31 | 3 | MPSB/Str/4754 · MPSB/Sur/3530 · MPSB/Str/4755
P20-LPYL-L02 | P20 - Lower Pylon - 2nd Lift | Lower pylon / pier lift | P20 | P20 | Middle pylon | [8 empty] | 2 | 2 | 4.515 | 6.515 |  | Cast | 2026-06-23 | IPC - 33 | 3 | MPSB/Str/4993 · MPSB/Sur/3685 · MPSB/Str/4994
P20-LPYL-REST | P20 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P20 | P20 | Middle pylon | [8 empty] | 3 | 15.109 | 6.515 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P21-WELL-CE | P21 | Cutting edge | P21 | P21 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2025-01-17 | IPC - 10 | 2 | MPSB/Sur/153 · MPSB/Sur/314
P21-WELL-L00 | P21 - Well Curb | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 0 | 6.2 | 0 | 6.2 | Curb → Below transition | Cast & sunk | 2025-02-28 | IPC - 11 | 4 | MPSB/Str/513 · MPSB/Str/615 · MPSB/Sur/600 · MPSB/Sur/601
P21-WELL-L01 | P21 - 1st Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 1 | 2 | 6.2 | 8.2 | Below transition | Cast & sunk | 2025-03-22 | IPC - 13 | 4 | MPSB/Str/802 · MPSB/Sur/712 · MPSB/Str/816 · MPSB/Sur/760
P21-WELL-L02 | P21 - 2nd Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 2 | 1.15 | 8.2 | 9.35 | Below transition | Cast & sunk | 2025-03-22 | IPC - 13 | 4 | MPSB/Str/804 · MPSB/Sur/713 · MPSB/Str/820 · MPSB/Sur/762
P21-WELL-L03 | P21 - 3rd Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 3 | 2.5 | 9.35 | 11.85 | Below transition | Cast & sunk | 2025-03-31 | IPC - 13 | 4 | MPSB/Str/888 · MPSB/Sur/780 · MPSB/Str/889 · MPSB/Sur/880
P21-WELL-L04 | P21 - 4th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 11.85 | 14.35 | Below transition | Cast & sunk | 2025-04-15 | IPC - 14 | 4 | MPSB/Str/1111 · MPSB/Sur/973 · MPSB/Str/1112 · MPSB/Sur/995
P21-WELL-L05 | P21 - 5th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 14.35 | 16.85 | Below transition | Cast & sunk | 2025-04-25 | IPC - 14 | 4 | MPSB/Str/1205 · MPSB/Sur/1048 · MPSB/Str/1206 · MPSB/Sur/1100
P21-WELL-L06 | P21 - 6th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 16.85 | 19.35 | Below transition | Cast & sunk | 2025-04-28 | IPC - 14 | 3 | MPSB/Str/1312 · MPSB/Sur/1135 · MPSB/Str/1313
P21-WELL-L07 | P21 - 7th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 19.35 | 21.85 | Below transition | Cast & sunk | 2025-05-16 | IPC - 15 | 4 | MPSB/Str/1470 · MPSB/Sur/1252 · MPSB/Str/1471 · MPSB/Sur/1285
P21-WELL-L08 | P21 - 8th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 8 | 2.5 | 21.85 | 24.35 | Below transition | Cast & sunk | 2025-08-30 | IPC - 19 | 4 | MPSB/Str/2065 · MPSB/Sur/1715 · MPSB/Str/2066 · MPSB/Sur/1750
P21-WELL-L09 | P21 - 9th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 9 | 1.3 | 24.35 | 25.65 | Below transition | Cast & sunk | 2025-09-30 | IPC - 20 | 3 | MPSB/Str/2374 · MPSB/Sur/1903 · MPSB/Str/2375
P21-WELL-L10 | P21 - 10th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 10 | 2.7 | 25.65 | 28.35 | Below transition → Transition | Cast & sunk | 2025-11-26 | IPC - 23 | 3 | MPSB/Str/2934 · MPSB/Sur/2276 · MPSB/Str/2935
P21-WELL-L11 | P21 - 11th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 11 | 2.8 | 28.35 | 31.15 | Transition → Above transition | Cast & sunk | 2025-11-30 | IPC - 23 | 3 | MPSB/Str/2995 · MPSB/Sur/2312 · MPSB/Str/2996
P21-WELL-L12 | P21 - 12th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 12 | 2.5 | 31.15 | 33.65 | Above transition | Cast & sunk | 2025-12-24 | IPC - 25 | 4 | MPSB/Str/3227 · MPSB/Sur/2467 · MPSB/Str/3228 · MPSB/Sur/2487
P21-WELL-L13 | P21 - 13th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 33.65 | 36.15 | Above transition | Cast & sunk | 2025-12-29 | IPC - 25 | 3 | MPSB/Str/3323 · MPSB/Sur/2533 · MPSB/Str/3324
P21-WELL-L14 | P21 - 14th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 36.15 | 38.65 | Above transition | Cast & sunk | 2026-01-11 | IPC - 26 | 4 | MPSB/Str/3438 · MPSB/Sur/2618 · MPSB/Str/3439 · MPSB/Sur/2650
P21-WELL-L15 | P21 - 15th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 38.65 | 41.15 | Above transition | Cast & sunk | 2026-01-19 | IPC - 26 | 4 | MPSB/Str/3521 · MPSB/Sur/2677 · MPSB/Str/3522 · MPSB/Sur/2713
P21-WELL-L16 | P21 - 16th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 41.15 | 43.65 | Above transition | Cast & sunk | 2026-01-25 | IPC - 26 | 4 | MPSB/Str/3617 · MPSB/Sur/2746 · MPSB/Str/3618 · MPSB/Sur/2772
P21-WELL-L17 | P21 - 17th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 43.65 | 46.15 | Above transition | Cast & sunk | 2026-01-30 | IPC - 26 | 3 | MPSB/Str/3693 · MPSB/Sur/2805 · MPSB/Str/3694
P21-WELL-L18 | P21 - 18th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 18 | 2.5 | 46.15 | 48.65 | Above transition | Cast & sunk | 2026-02-25 | IPC - 27 | 4 | MPSB/Str/3855 · MPSB/Sur/2931 · MPSB/Str/3856 · MPSB/Sur/2999
P21-WELL-L19 | P21 - 19th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 19 | 2.5 | 48.65 | 51.15 | Above transition | Cast & sunk | 2026-02-27 | IPC - 27 | 3 | MPSB/Str/3975 · MPSB/Sur/3017 · MPSB/Str/3976
P21-WELL-L20 | P21 - 20th Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 20 | 1.85 | 51.15 | 53 | Above transition | Cast & sunk | 2026-03-16 | IPC - 29 | 3 | MPSB/Str/4128 · MPSB/Sur/3131 · MPSB/Str/4129
P21-WELL-L21 | P21 - 21st Lift | Well lift | P21 | P21 | Outer pylon | Double-D | [7 empty] | 21 | 1.05 | 53 | 54.05 | Above transition | Cast & sunk | 2026-04-11 | IPC - 30 | 3 | MPSB/Str/4376 · MPSB/Sur/3279 · MPSB/Str/4377
P21-WELL-PLUG | P21 - Bottom Plugging | Bottom plug | P21 | P21 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P21-WELL-CAP | P21 - Well Cap | Well cap | P21 | P21 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P21-LPYL-REST | P21 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P21 | P21 | Outer pylon | [8 empty] | 0 | 21.324 | 0 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P22-WELL-CE | P22 | Cutting edge | P22 | P22 | EJ pier | Circular | [12 empty] | Shutter & scaffold done | 2024-11-13 | IPC - 08 | 2 | MPSB/Sur/60 · MPSB/Sur/92
P22-WELL-L00 | P22 - Well Curb | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Cast & sunk | 2024-12-04 | IPC - 08 | 5 | MPSB/Str/135 · MPSB/Sur/137 · MPSB/Str/153 · MPSB/Sur/175 · MPSB/Str/182
P22-WELL-L01 | P22 - 1st Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 1 | 2.65 | 4.32 | 6.97 | Below transition | Cast & sunk | 2024-12-12 | IPC - 09 | 4 | MPSB/Sur/180 · MPSB/Str/192 · MPSB/Str/193 · MPSB/Str/199
P22-WELL-L02 | P22 - 2nd Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 2 | 2.5 | 6.97 | 9.47 | Below transition | Cast & sunk | 2024-12-16 | IPC - 09 | 4 | MPSB/Sur/195 · MPSB/Str/203 · MPSB/Str/204 · MPSB/Str/214
P22-WELL-L03 | P22 - 3rd Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 3 | 2.5 | 9.47 | 11.97 | Below transition | Cast & sunk | 2024-12-28 | IPC - 09 | 4 | MPSB/Sur/209 · MPSB/Str/229 · MPSB/Str/230 · MPSB/Str/270
P22-WELL-L04 | P22 - 4th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 4 | 2.5 | 11.97 | 14.47 | Below transition | Cast & sunk | 2024-12-29 | IPC - 09 | 4 | MPSB/Sur/223 · MPSB/Str/259 · MPSB/Str/260 · MPSB/Str/281
P22-WELL-L05 | P22 - 5th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 5 | 2.5 | 14.47 | 16.97 | Below transition | Cast & sunk | 2024-12-30 | IPC - 09 | 3 | MPSB/Sur/239 · MPSB/Str/290 · MPSB/Str/291
P22-WELL-L06 | P22 - 6th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 6 | 2.5 | 16.97 | 19.47 | Below transition | Cast & sunk | 2025-01-14 | IPC - 10 | 4 | MPSB/Str/340 · MPSB/Sur/277 · MPSB/Str/341 · MPSB/Sur/299
P22-WELL-L07 | P22 - 7th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 7 | 2.5 | 19.47 | 21.97 | Below transition | Cast & sunk | 2025-01-31 | IPC - 10 | 4 | MPSB/Str/437 · MPSB/Sur/374 · MPSB/Str/438 · MPSB/Sur/400
P22-WELL-L08 | P22 - 8th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 8 | 1.31 | 21.97 | 23.28 | Below transition → Transition | Cast & sunk | 2025-03-13 | IPC - 13 | 4 | MPSB/Str/760 · MPSB/Sur/674 · MPSB/Str/761 · MPSB/Sur/711
P22-WELL-L09 | P22 - 9th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 9 | 0.5 | 23.28 | 23.78 | Transition | Cast & sunk | 2025-04-21 | IPC - 14 | 3 | MPSB/Str/1203 · MPSB/Sur/1047 · MPSB/Str/1204
P22-WELL-L10 | P22 - 10th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 10 | 2.8 | 23.78 | 26.58 | Transition → Above transition | Cast & sunk | 2025-04-27 | IPC - 14 | 3 | MPSB/Str/1267 · MPSB/Sur/1127 · MPSB/Str/1300
P22-WELL-L11 | P22 - 11th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 11 | 2.5 | 26.58 | 29.08 | Above transition | Cast & sunk | 2025-05-12 | IPC - 15 | 4 | MPSB/Str/1464 · MPSB/Sur/1250 · MPSB/Str/1465 · MPSB/Sur/1256
P22-WELL-L12 | P22 - 12th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 12 | 2.5 | 29.08 | 31.58 | Above transition | Cast & sunk | 2025-05-21 | IPC - 15 | 4 | MPSB/Str/1528 · MPSB/Sur/1312 · MPSB/Str/1529 · MPSB/Sur/1328
P22-WELL-L13 | P22 - 13th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 13 | 2.5 | 31.58 | 34.08 | Above transition | Cast & sunk | 2025-06-14 | IPC - 16 | 3 | MPSB/Sur/1360 · MPSB/Str/1662 · MPSB/Str/1663
P22-WELL-L14 | P22 - 14th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 14 | 2.5 | 34.08 | 36.58 | Above transition | Cast & sunk | 2025-07-28 | IPC - 18 | 3 | MPSB/Str/1889 · MPSB/Sur/1583 · MPSB/Str/1915
P22-WELL-L15 | P22 - 15th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 15 | 2.5 | 36.58 | 39.08 | Above transition | Cast & sunk | 2025-08-28 | IPC - 19 | 3 | MPSB/Str/2103 · MPSB/Sur/1738 · MPSB/Str/2104
P22-WELL-L16 | P22 - 16th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 16 | 2.57 | 39.08 | 41.65 | Above transition | Cast & sunk | 2025-09-29 | IPC - 20 | 3 | MPSB/Str/2356 · MPSB/Sur/1890 · MPSB/Str/2357
P22-WELL-L17 | P22 - 17th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 17 | 2.5 | 41.65 | 44.15 | Above transition | Cast & sunk | 2025-10-18 | IPC - 22 | 4 | MPSB/Str/2475 · MPSB/Sur/1984 · MPSB/Str/2476 · MPSB/Sur/2010
P22-WELL-L18 | P22 - 18th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 18 | 2 | 44.15 | 46.15 | Above transition | Cast & sunk | 2025-10-30 | IPC - 22 | 4 | MPSB/Str/2593 · MPSB/Sur/2056 · MPSB/Str/2594 · MPSB/Sur/2072
P22-WELL-L19 | P22 - 19th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 19 | 2.5 | 46.15 | 48.65 | Above transition | Cast & sunk | 2025-11-25 | IPC - 23 | 4 | MPSB/Str/2873 · MPSB/Sur/2240 · MPSB/Str/2874 · MPSB/Sur/2267
P22-WELL-L20 | P22 - 20th Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 20 | 2 | 48.65 | 50.65 | Above transition | Cast & sunk | 2025-12-18 | IPC - 25 | 4 | MPSB/Str/3136 · MPSB/Sur/2409 · MPSB/Str/3137 · MPSB/Sur/2437
P22-WELL-L21 | P22 - 21st Lift | Well lift | P22 | P22 | EJ pier | Circular | [7 empty] | 21 | 0.9 | 50.65 | 51.55 |  | Cast & sunk | 2025-12-26 | IPC - 25 | 3 | MPSB/Str/3263 · MPSB/Sur/2489 · MPSB/Str/3283
P22-WELL-PLUG | P22 - Bottom Plugging | Bottom plug | P22 | P22 | EJ pier | Circular | [12 empty] | Plugged | 2026-02-25 | IPC - 27 | 1 | MPSB/Str/3952
P22-WELL-CAP | P22 - Well Cap | Well cap | P22 | P22 | EJ pier | Circular | [12 empty] | Cast | 2026-03-14 | IPC - 29 | 2 | MPSB/Sur/3119 · MPSB/Str/4108
P22-LPYL-L00 | P22 - Lower Pylon - Starter | Lower pylon / pier lift | P22 | P22 | EJ pier | [8 empty] | 0 | 0.63 | 0 | 0.63 |  | Cast | 2026-04-06 | IPC - 30 | 3 | MPSB/Str/4332 · MPSB/Sur/3247 · MPSB/Str/4333
P22-LPYL-L01 | P22 - Lower Pylon - 1st Lift | Lower pylon / pier lift | P22 | P22 | EJ pier | [8 empty] | 1 | 4 | 0.63 | 4.63 |  | Cast | 2026-04-17 | IPC - 30 | 3 | MPSB/Str/4428 · MPSB/Sur/3318 · MPSB/Str/4429
P22-LPYL-L02 | P22 - Lower Pylon - 2nd Lift | Lower pylon / pier lift | P22 | P22 | EJ pier | [8 empty] | 2 | 4 | 4.63 | 8.63 |  | Cast | 2026-05-14 | IPC - 31 | 3 | MPSB/Str/4678 · MPSB/Sur/3479 · MPSB/Str/4679
P22-LPYL-L03 | P22 - Lower Pylon - 3rd Lift | Lower pylon / pier lift | P22 | P22 | EJ pier | [8 empty] | 3 | 2 | 8.63 | 10.63 |  | Cast | 2026-06-25 | IPC - 33 | 3 | MPSB/Str/5007 · MPSB/Sur/3692 · MPSB/Str/5008
P22-LPYL-REST | P22 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P22 | P22 | EJ pier | [8 empty] | 4 | 10.994 | 10.63 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P23-WELL-CE | P23 | Cutting edge | P23 | P23 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2025-02-12 | IPC - 11 | 2 | MPSB/Sur/77 · MPSB/Sur/461
P23-WELL-L00 | P23 - Well Curb | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 0 | 6.2 | 0 | 6.2 | Curb → Below transition | Cast & sunk | 2025-02-28 | IPC - 11 | 2 | MPSB/Str/633 · MPSB/Str/686
P23-WELL-L01 | P23 - 1st Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 1 | 2 | 6.2 | 8.2 | Below transition | Cast & sunk | 2025-03-31 | IPC - 13 | 4 | MPSB/Str/956 · MPSB/Sur/833 · MPSB/Str/957 · MPSB/Sur/884
P23-WELL-L02 | P23 - 2nd Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 2 | 1.15 | 8.2 | 9.35 | Below transition | Cast & sunk | 2025-03-31 | IPC - 13 | 4 | MPSB/Str/958 · MPSB/Sur/834 · MPSB/Str/959 · MPSB/Sur/886
P23-WELL-L03 | P23 - 3rd Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 3 | 2.5 | 9.35 | 11.85 | Below transition | Cast & sunk | 2025-04-20 | IPC - 14 | 4 | MPSB/Str/1136 · MPSB/Sur/997 · MPSB/Str/1137 · MPSB/Sur/1042
P23-WELL-L04 | P23 - 4th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 11.85 | 14.35 | Below transition | Cast & sunk | 2025-04-27 | IPC - 14 | 3 | MPSB/Str/1269 · MPSB/Sur/1128 · MPSB/Str/1301
P23-WELL-L05 | P23 - 5th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 14.35 | 16.85 | Below transition | Cast & sunk | 2025-05-12 | IPC - 15 | 4 | MPSB/Str/1440 · MPSB/Sur/1232 · MPSB/Str/1441 · MPSB/Sur/1258
P23-WELL-L06 | P23 - 6th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 16.85 | 19.35 | Below transition | Cast & sunk | 2025-05-26 | IPC - 15 | 4 | MPSB/Str/1552 · MPSB/Sur/1333 · MPSB/Str/1553 · MPSB/Sur/1357
P23-WELL-L07 | P23 - 7th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 19.35 | 21.85 | Below transition | Cast & sunk | 2025-07-30 | IPC - 18 | 4 | MPSB/Str/1877 · MPSB/Sur/1571 · MPSB/Str/1878 · MPSB/Sur/1609
P23-WELL-L08 | P23 - 8th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 8 | 2.5 | 21.85 | 24.35 | Below transition | Cast & sunk | 2025-09-03 | IPC - 20 | 4 | MPSB/Str/2058 · MPSB/Sur/1726 · MPSB/Str/2075 · MPSB/Sur/1761
P23-WELL-L09 | P23 - 9th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 9 | 1.3 | 24.35 | 25.65 | Below transition | Cast & sunk | 2025-09-30 | IPC - 20 | 4 | MPSB/Str/2243 · MPSB/Sur/1828 · MPSB/Str/2244 · MPSB/Sur/1905
P23-WELL-L10 | P23 - 10th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 10 | 2.8 | 25.65 | 28.45 | Below transition → Transition | Cast & sunk | 2025-10-23 | IPC - 22 | 3 | MPSB/Str/2552 · MPSB/Sur/2025 · MPSB/Str/2553
P23-WELL-L11 | P23 - 11th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 11 | 2.7 | 28.45 | 31.15 | Transition → Above transition | Cast & sunk | 2025-10-27 | IPC - 22 | 3 | MPSB/Str/2602 · MPSB/Sur/2061 · MPSB/Str/2603
P23-WELL-L12 | P23 - 12th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 12 | 2.5 | 31.15 | 33.65 | Above transition | Cast & sunk | 2025-11-19 | IPC - 23 | 4 | MPSB/Str/2793 · MPSB/Sur/2183 · MPSB/Str/2794 · MPSB/Sur/2223
P23-WELL-L13 | P23 - 13th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 33.65 | 36.15 | Above transition | Cast & sunk | 2025-11-25 | IPC - 23 | 3 | MPSB/Str/2921 · MPSB/Sur/2264 · MPSB/Str/2922
P23-WELL-L14 | P23 - 14th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 36.15 | 38.65 | Above transition | Cast & sunk | 2025-12-12 | IPC - 25 | 4 | MPSB/Str/3087 · MPSB/Sur/2369 · MPSB/Str/3088 · MPSB/Sur/2401
P23-WELL-L15 | P23 - 15th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 38.65 | 41.15 | Above transition | Cast & sunk | 2025-12-23 | IPC - 25 | 4 | MPSB/Str/3177 · MPSB/Sur/2431 · MPSB/Str/3203 · MPSB/Sur/2474
P23-WELL-L16 | P23 - 16th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 41.15 | 43.65 | Above transition | Cast & sunk | 2025-12-26 | IPC - 25 | 3 | MPSB/Str/3284 · MPSB/Sur/2506 · MPSB/Str/3285
P23-WELL-L17 | P23 - 17th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 43.65 | 46.15 | Above transition | Cast & sunk | 2025-12-31 | IPC - 25 | 3 | MPSB/Str/3387 · MPSB/Sur/2575 · MPSB/Str/3388
P23-WELL-L18 | P23 - 18th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 18 | 2.5 | 46.15 | 48.65 | Above transition | Cast & sunk | 2026-01-16 | IPC - 26 | 4 | MPSB/Str/3508 · MPSB/Sur/2666 · MPSB/Str/3509 · MPSB/Sur/2695
P23-WELL-L19 | P23 - 19th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 19 | 2.5 | 48.65 | 51.15 | Above transition | Cast & sunk | 2026-01-25 | IPC - 26 | 4 | MPSB/Str/3591 · MPSB/Sur/2727 · MPSB/Str/3592 · MPSB/Sur/2770
P23-WELL-L20 | P23 - 20th Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 20 | 0.35 | 51.15 | 51.5 | Above transition | Cast & sunk | 2026-01-29 | IPC - 26 | 3 | MPSB/Str/3672 · MPSB/Sur/2795 · MPSB/Str/3673
P23-WELL-L21 | P23 - 21st Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 21 | 1.55 | 51.5 | 53.05 | Above transition | Cast & sunk | 2026-02-25 | IPC - 27 | 4 | MPSB/Str/3767 · MPSB/Sur/2863 · MPSB/Str/3768 · MPSB/Sur/3001 | Y
P23-WELL-L22 | P23 - 22nd Lift | Well lift | P23 | P23 | Outer pylon | Double-D | [7 empty] | 22 | 1 | 53.05 | 54.05 | Above transition | Cast & sunk | 2026-02-25 | IPC - 27 | 4 | MPSB/Str/3904 · MPSB/Sur/2963 · MPSB/Str/3905 · MPSB/Sur/3001 | Y
P23-WELL-PLUG | P23 - Bottom Plugging | Bottom plug | P23 | P23 | Outer pylon | Double-D | [12 empty] | Plugged | 2026-06-30 | IPC - 33 | 1 | MPSB/Str/5073
P23-WELL-CAP | P23 - Well Cap | Well cap | P23 | P23 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P23-LPYL-REST | P23 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P23 | P23 | Outer pylon | [8 empty] | 0 | 21.324 | 0 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P24-WELL-CE | P24 | Cutting edge | P24 | P24 | Middle pylon | Circular | [12 empty] | Shutter & scaffold done | 2024-11-16 | IPC - 08 | 2 | MPSB/Sur/57 · MPSB/Sur/102
P24-WELL-L00 | P24 - Well Curb | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Cast & sunk | 2024-12-25 | IPC - 09 | 4 | MPSB/Str/215 · MPSB/Str/223 · MPSB/Str/253 · MPSB/Str/254
P24-WELL-L01 | P24 - 1st Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 1 | 2.65 | 4.32 | 6.97 | Below transition | Cast & sunk | 2024-12-30 | IPC - 09 | 4 | MPSB/Sur/227 · MPSB/Str/265 · MPSB/Str/266 · MPSB/Str/294
P24-WELL-L02 | P24 - 2nd Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 2 | 2.5 | 6.97 | 9.47 | Below transition | Cast & sunk | 2025-01-10 | IPC - 10 | 4 | MPSB/Str/305 · MPSB/Sur/250 · MPSB/Str/306 · MPSB/Sur/283
P24-WELL-L03 | P24 - 3rd Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 3 | 2.5 | 9.47 | 11.97 | Below transition | Cast & sunk | 2025-01-27 | IPC - 10 | 4 | MPSB/Str/357 · MPSB/Sur/295 · MPSB/Str/367 · MPSB/Sur/370 | Y
P24-WELL-L04 | P24 - 4th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 4 | 2.5 | 11.97 | 14.47 | Below transition | Cast & sunk | 2025-01-27 | IPC - 10 | 4 | MPSB/Str/396 · MPSB/Sur/335 · MPSB/Str/397 · MPSB/Sur/371
P24-WELL-L05 | P24 - 5th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 5 | 2.5 | 14.47 | 16.97 | Below transition | Cast & sunk | 2025-01-30 | IPC - 10 | 3 | MPSB/Str/458 · MPSB/Sur/386 · MPSB/Str/459
P24-WELL-L06 | P24 - 6th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 6 | 2.5 | 16.97 | 19.47 | Below transition | Cast & sunk | 2025-02-16 | IPC - 11 | 4 | MPSB/Str/514 · MPSB/Sur/465 · MPSB/Str/535 · MPSB/Sur/476
P24-WELL-L07 | P24 - 7th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 7 | 2.5 | 19.47 | 21.97 | Below transition | Cast & sunk | 2025-02-24 | IPC - 11 | 4 | MPSB/Str/573 · MPSB/Sur/504 · MPSB/Str/574 · MPSB/Sur/542
P24-WELL-L08 | P24 - 8th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 8 | 2.5 | 21.97 | 24.47 | Below transition | Cast & sunk | 2025-02-27 | IPC - 11 | 4 | MPSB/Str/635 · MPSB/Sur/559 · MPSB/Str/636 · MPSB/Sur/576
P24-WELL-L09 | P24 - 9th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 9 | 2.51 | 24.47 | 26.98 | Below transition | Cast & sunk | 2025-03-15 | IPC - 13 | 4 | MPSB/Str/773 · MPSB/Sur/687 · MPSB/Str/774 · MPSB/Sur/716
P24-WELL-L10 | P24 - 10th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 10 | 2.5 | 26.98 | 29.48 | Below transition | Cast & sunk | 2025-03-26 | IPC - 13 | 3 | MPSB/Str/904 · MPSB/Sur/790 · MPSB/Str/905
P24-WELL-L11 | P24 - 11th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 11 | 2.5 | 29.48 | 31.98 | Below transition | Cast & sunk | 2025-05-15 | IPC - 15 | 4 | MPSB/Str/1458 · MPSB/Sur/1247 · MPSB/Str/1459 · MPSB/Sur/1282
P24-WELL-L12 | P24 - 12th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 12 | 2.5 | 31.98 | 34.48 | Below transition | Cast & sunk | 2025-08-12 | IPC - 19 | 3 | MPSB/Str/2024 · MPSB/Sur/1687 · MPSB/Str/2025
P24-WELL-L13 | P24 - 13th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 13 | 0.5 | 34.48 | 34.98 | Below transition → Transition | Cast & sunk | 2025-10-26 | IPC - 22 | 4 | MPSB/Str/2483 · MPSB/Sur/1989 · MPSB/Str/2484 · MPSB/Sur/2051 | Y
P24-WELL-L14 | P24 - 14th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 14 | 2.8 | 34.98 | 37.78 | Transition → Above transition | Cast & sunk | 2025-10-26 | IPC - 22 | 4 | MPSB/Str/2537 · MPSB/Sur/2017 · MPSB/Str/2538 · MPSB/Sur/2051 | Y
P24-WELL-L15 | P24 - 15th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 15 | 2.5 | 37.78 | 40.28 | Above transition | Cast & sunk | 2025-11-06 | IPC - 23 | 3 | MPSB/Str/2709 · MPSB/Sur/2134 · MPSB/Str/2710
P24-WELL-L16 | P24 - 16th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 16 | 2.5 | 40.28 | 42.78 | Above transition | Cast & sunk | 2025-11-25 | IPC - 23 | 3 | MPSB/Str/2923 · MPSB/Sur/2265 · MPSB/Str/2924
P24-WELL-L17 | P24 - 17th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 17 | 2.5 | 42.78 | 45.28 | Above transition | Cast & sunk | 2025-12-11 | IPC - 25 | 4 | MPSB/Str/3085 · MPSB/Sur/2368 · MPSB/Str/3086 · MPSB/Sur/2388
P24-WELL-L18 | P24 - 18th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 18 | 2.5 | 45.28 | 47.78 | Above transition | Cast & sunk | 2025-12-31 | IPC - 25 | 4 | MPSB/Str/3300 · MPSB/Sur/2518 · MPSB/Str/3301 · MPSB/Sur/2577
P24-WELL-L19 | P24 - 19th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 19 | 2.5 | 47.78 | 50.28 | Above transition | Cast & sunk | 2026-01-12 | IPC - 26 | 4 | MPSB/Str/3459 · MPSB/Sur/2627 · MPSB/Str/3460 · MPSB/Sur/2660
P24-WELL-L20 | P24 - 20th Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 20 | 2.5 | 50.28 | 52.78 | Above transition | Cast & sunk | 2026-01-24 | IPC - 26 | 4 | MPSB/Str/3572 · MPSB/Sur/2715 · MPSB/Str/3573 · MPSB/Sur/2761
P24-WELL-L21 | P24 - 21st Lift | Well lift | P24 | P24 | Middle pylon | Circular | [7 empty] | 21 | 1.27 | 52.78 | 54.05 | Above transition | Cast & sunk | 2026-01-30 | IPC - 26 | 3 | MPSB/Str/3709 · MPSB/Sur/2816 · MPSB/Str/3710
P24-WELL-PLUG | P24 - Bottom Plugging | Bottom plug | P24 | P24 | Middle pylon | Circular | [12 empty] | Plugged | 2026-06-21 | IPC - 33 | 1 | MPSB/Str/4975
P24-WELL-CAP | P24 - Well Cap | Well cap | P24 | P24 | Middle pylon | Circular | [12 empty] | Cast | 2026-07-29 | IPC - 34 | 2 | MPSB/Sur/3801 · MPSB/Str/5219
P24-LPYL-REST | P24 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P24 | P24 | Middle pylon | [8 empty] | 0 | 21.624 | 0 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P25-WELL-CE | P25 | Cutting edge | P25 | P25 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2024-12-11 | IPC - 09 | 2 | MPSB/Sur/76 · MPSB/Sur/196
P25-WELL-L00 | P25 - Well Curb | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 0 | 6.04 | 0 | 6.04 | Curb | Cast & sunk | 2024-12-30 | IPC - 09 | 2 | MPSB/Str/267 · MPSB/Str/289
P25-WELL-L01 | P25 - 1st Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 1 | 3.31 | 6.04 | 9.35 | Below transition | Cast & sunk | 2025-01-24 | IPC - 10 | 4 | MPSB/Str/388 · MPSB/Sur/328 · MPSB/Str/389 · MPSB/Sur/354
P25-WELL-L02 | P25 - 2nd Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 2 | 2.5 | 9.35 | 11.85 | Below transition | Cast & sunk | 2025-01-30 | IPC - 10 | 3 | MPSB/Str/447 · MPSB/Sur/378 · MPSB/Str/469
P25-WELL-L03 | P25 - 3rd Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 3 | 2.5 | 11.85 | 14.35 | Below transition | Cast & sunk | 2025-02-19 | IPC - 11 | 4 | MPSB/Str/544 · MPSB/Sur/469 · MPSB/Str/545 · MPSB/Sur/503
P25-WELL-L04 | P25 - 4th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 14.35 | 16.85 | Below transition | Cast & sunk | 2025-02-25 | IPC - 11 | 4 | MPSB/Str/600 · MPSB/Sur/528 · MPSB/Str/601 · MPSB/Sur/561
P25-WELL-L05 | P25 - 5th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 16.85 | 19.35 | Below transition | Cast & sunk | 2025-02-26 | IPC - 11 | 3 | MPSB/Str/652 · MPSB/Str/653 · MPSB/Sur/569
P25-WELL-L06 | P25 - 6th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 19.35 | 21.85 | Below transition | Cast & sunk | 2025-03-18 | IPC - 13 | 4 | MPSB/Str/806 · MPSB/Sur/714 · MPSB/Str/807 · MPSB/Sur/732
P25-WELL-L07 | P25 - 7th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 21.85 | 24.35 | Below transition | Cast & sunk | 2025-03-27 | IPC - 13 | 4 | MPSB/Str/863 · MPSB/Sur/771 · MPSB/Str/864 · MPSB/Sur/806
P25-WELL-L08 | P25 - 8th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 8 | 1.3 | 24.35 | 25.65 | Below transition | Cast & sunk | 2025-04-19 | IPC - 14 | 4 | MPSB/Str/1132 · MPSB/Sur/993 · MPSB/Str/1133 · MPSB/Sur/1036
P25-WELL-L09 | P25 - 9th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 9 | 2.7 | 25.65 | 28.35 | Below transition → Transition | Cast & sunk | 2025-04-24 | IPC - 14 | 3 | MPSB/Str/1244 · MPSB/Sur/1076 · MPSB/Str/1245
P25-WELL-L10 | P25 - 10th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 10 | 2.8 | 28.35 | 31.15 | Transition → Above transition | Cast & sunk | 2025-04-30 | IPC - 14 | 3 | MPSB/Str/1357 · MPSB/Sur/1160 · MPSB/Str/1358
P25-WELL-L11 | P25 - 11th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 11 | 2.5 | 31.15 | 33.65 | Above transition | Cast & sunk | 2025-05-20 | IPC - 15 | 4 | MPSB/Str/1513 · MPSB/Sur/1302 · MPSB/Str/1514 · MPSB/Sur/1323
P25-WELL-L12 | P25 - 12th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 12 | 2.5 | 33.65 | 36.15 | Above transition | Cast & sunk | 2025-05-26 | IPC - 15 | 3 | MPSB/Str/1575 · MPSB/Sur/1351 · MPSB/Str/1576
P25-WELL-L13 | P25 - 13th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 36.15 | 38.65 | Above transition | Cast & sunk | 2025-09-15 | IPC - 20 | 4 | MPSB/Str/2193 · MPSB/Sur/1797 · MPSB/Str/2194 · MPSB/Sur/1824
P25-WELL-L14 | P25 - 14th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 38.65 | 41.15 | Above transition | Cast & sunk | 2025-09-29 | IPC - 20 | 3 | MPSB/Str/2350 · MPSB/Sur/1887 · MPSB/Str/2351
P25-WELL-L15 | P25 - 15th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 41.15 | 43.65 | Above transition | Cast & sunk | 2025-10-23 | IPC - 22 | 4 | MPSB/Str/2488 · MPSB/Sur/1991 · MPSB/Str/2489 · MPSB/Sur/2029
P25-WELL-L16 | P25 - 16th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 43.65 | 46.15 | Above transition | Cast & sunk | 2025-10-29 | IPC - 22 | 3 | MPSB/Str/2619 · MPSB/Sur/2066 · MPSB/Str/2620
P25-WELL-L17 | P25 - 17th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 46.15 | 48.65 | Above transition | Cast & sunk | 2025-11-15 | IPC - 23 | 4 | MPSB/Str/2749 · MPSB/Sur/2161 · MPSB/Str/2750 · MPSB/Sur/2199
P25-WELL-L18 | P25 - 18th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 18 | 2.5 | 48.65 | 51.15 | Above transition | Cast & sunk | 2025-11-28 | IPC - 23 | 4 | MPSB/Str/2895 · MPSB/Sur/2250 · MPSB/Str/2896 · MPSB/Sur/2297
P25-WELL-L19 | P25 - 19th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 19 | 1.9 | 51.15 | 53.05 | Above transition | Cast & sunk | 2025-11-30 | IPC - 23 | 3 | MPSB/Str/3001 · MPSB/Sur/2315 · MPSB/Str/3002
P25-WELL-L20 | P25 - 20th Lift | Well lift | P25 | P25 | Outer pylon | Double-D | [7 empty] | 20 | 1 | 53.05 | 54.05 | Above transition | Cast & sunk | 2025-12-30 | IPC - 25 | 3 | MPSB/Str/3356 · MPSB/Sur/2556 · MPSB/Str/3357
P25-WELL-PLUG | P25 - Bottom Plugging | Bottom plug | P25 | P25 | Outer pylon | Double-D | [12 empty] | Plugged | 2026-04-18 | IPC - 30 | 1 | MPSB/Str/4435
P25-WELL-CAP | P25 - Well Cap | Well cap | P25 | P25 | Outer pylon | Double-D | [12 empty] | Cast | 2026-05-18 | IPC - 31 | 2 | MPSB/Sur/3497 · MPSB/Str/4709
P25-LPYL-L00 | P25 - Lower Pylon - Starter | Lower pylon / pier lift | P25 | P25 | Outer pylon | [8 empty] | 0 | 0.63 | 0 | 0.63 |  | Cast | 2026-06-14 | IPC - 33 | 3 | MPSB/Str/4902 · MPSB/Sur/3651 · MPSB/Str/4903
P25-LPYL-L01 | P25 - Lower Pylon - 1st Lift | Lower pylon / pier lift | P25 | P25 | Outer pylon | [8 empty] | 1 | 2.115 | 0.63 | 2.745 |  | Cast | 2026-06-26 | IPC - 33 | 3 | MPSB/Str/5017 · MPSB/Sur/3693 · MPSB/Str/5018
P25-LPYL-L02 | P25 - Lower Pylon - 2nd Lift | Lower pylon / pier lift | P25 | P25 | Outer pylon | [8 empty] | 2 | -3.14 | 2.745 | -0.395 |  | Cast | 2026-07-09 | IPC - 34 | 3 | MPSB/Str/5100 · MPSB/Sur/3733 · MPSB/Str/5101 |  |  |  | CHECK: negative height — see Anomalies
P25-LPYL-REST | P25 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P25 | P25 | Outer pylon | [8 empty] | 3 | 18.579 | 2.745 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P26-WELL-CE | P26 | Cutting edge | P26 | P26 | EJ pier | Circular | [12 empty] | Shutter & scaffold done | 2024-11-09 | IPC - 08 | 2 | MPSB/Sur/56 · MPSB/Sur/87
P26-WELL-L00 | P26 - Well Curb | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Cast & sunk | 2024-12-13 | IPC - 09 | 5 | MPSB/Str/99 · MPSB/Sur/184 · MPSB/Str/190 · MPSB/Sur/194 · MPSB/Str/202 |  | 2EjqfCRAz07gd2_buxFMoo | 1760315
P26-WELL-L01 | P26 - 1st Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 1 | 2.65 | 4.32 | 6.97 | Below transition | Cast & sunk | 2024-12-22 | IPC - 09 | 4 | MPSB/Sur/206 · MPSB/Str/224 · MPSB/Str/225 · MPSB/Str/232 |  | 2EjqfCRAz07gd2_buxFMpC | 1760325
P26-WELL-L02 | P26 - 2nd Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 2 | 2.5 | 6.97 | 9.47 | Below transition | Cast & sunk | 2024-12-29 | IPC - 09 | 4 | MPSB/Sur/220 · MPSB/Str/255 · MPSB/Str/256 · MPSB/Str/282 |  | 2EjqfCRAz07gd2_buxFMp6 | 1760335
P26-WELL-L03 | P26 - 3rd Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 3 | 2.5 | 9.47 | 11.97 | Below transition | Cast & sunk | 2025-01-09 | IPC - 10 | 4 | MPSB/Str/292 · MPSB/Sur/240 · MPSB/Str/293 · MPSB/Sur/276 |  | 2EjqfCRAz07gd2_buxFMpG | 1760345
P26-WELL-L04 | P26 - 4th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 4 | 2.5 | 11.97 | 14.47 | Below transition | Cast & sunk | 2025-01-18 | IPC - 10 | 4 | MPSB/Str/355 · MPSB/Sur/292 · MPSB/Str/366 · MPSB/Sur/322 |  | 2EjqfCRAz07gd2_buxFMpg | 1760355
P26-WELL-L05 | P26 - 5th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 5 | 2.5 | 14.47 | 16.97 | Below transition | Cast & sunk | 2025-01-27 | IPC - 10 | 4 | MPSB/Str/406 · MPSB/Sur/344 · MPSB/Str/407 · MPSB/Sur/373 |  | 2EjqfCRAz07gd2_buxFMpa | 1760365
P26-WELL-L06 | P26 - 6th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 6 | 2.5 | 16.97 | 19.47 | Below transition | Cast & sunk | 2025-01-31 | IPC - 10 | 3 | MPSB/Str/470 · MPSB/Sur/402 · MPSB/Str/471 |  | 2EjqfCRAz07gd2_buxFMp_ | 1760375
P26-WELL-L07 | P26 - 7th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 7 | 2.5 | 19.47 | 21.97 | Below transition | Cast & sunk | 2025-02-18 | IPC - 11 | 4 | MPSB/Str/516 · MPSB/Sur/467 · MPSB/Str/541 · MPSB/Sur/492 |  | 2EjqfCRAz07gd2_buxFMm8 | 1760385
P26-WELL-L08 | P26 - 8th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 8 | 0.51 | 21.97 | 22.48 | Below transition → Transition | Cast & sunk | 2025-03-31 | IPC - 13 | 4 | MPSB/Str/855 · MPSB/Sur/763 · MPSB/Str/862 · MPSB/Sur/888 |  | 2EjqfCRAz07gd2_buxFMm2 | 1760395
P26-WELL-L09 | P26 - 9th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 9 | 2.8 | 22.48 | 25.28 | Transition → Above transition | Cast & sunk | 2025-03-31 | IPC - 13 | 4 | MPSB/Str/930 · MPSB/Sur/808 · MPSB/Str/931 · MPSB/Sur/890 |  | 2EjqfCRAz07gd2_buxFMmS | 1760405
P26-WELL-L10 | P26 - 10th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 10 | 2.5 | 25.28 | 27.78 | Above transition | Cast & sunk | 2025-04-22 | IPC - 14 | 4 | MPSB/Str/1153 · MPSB/Sur/1003 · MPSB/Str/1154 · MPSB/Sur/1066 |  | 2EjqfCRAz07gd2_buxFMmM | 1760415
P26-WELL-L11 | P26 - 11th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 11 | 2.5 | 27.78 | 30.28 | Above transition | Cast & sunk | 2025-04-27 | IPC - 14 | 4 | MPSB/Str/1242 · MPSB/Sur/1075 · MPSB/Str/1243 · MPSB/Sur/1126 |  | 2EjqfCRAz07gd2_buxFMmW | 1760425
P26-WELL-L12 | P26 - 12th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 12 | 2.5 | 30.28 | 32.78 | Above transition | Cast & sunk | 2025-04-28 | IPC - 14 | 3 | MPSB/Str/1314 · MPSB/Sur/1136 · MPSB/Str/1315 |  | 2EjqfCRAz07gd2_buxFMmw | 1760435
P26-WELL-L13 | P26 - 13th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 13 | 2.5 | 32.78 | 35.28 | Above transition | Cast & sunk | 2025-04-30 | IPC - 14 | 3 | MPSB/Str/1359 · MPSB/Sur/1161 · MPSB/Str/1360 |  | 2EjqfCRAz07gd2_buxFMmq | 1760445
P26-WELL-L14 | P26 - 14th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 14 | 2.5 | 35.28 | 37.78 | Above transition | Cast & sunk | 2025-05-19 | IPC - 15 | 4 | MPSB/Str/1495 · MPSB/Sur/1280 · MPSB/Str/1496 · MPSB/Sur/1316 |  | 2EjqfCRAz07gd2_buxFMnE | 1760455
P26-WELL-L15 | P26 - 15th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 15 | 2.5 | 37.78 | 40.28 | Above transition | Cast & sunk | 2025-05-26 | IPC - 15 | 4 | MPSB/Str/1550 · MPSB/Sur/1332 · MPSB/Str/1551 · MPSB/Sur/1359 |  | 2EjqfCRAz07gd2_buxFMnO | 1760465
P26-WELL-L16 | P26 - 16th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 16 | 2.5 | 40.28 | 42.78 | Above transition | Cast & sunk | 2025-06-29 | IPC - 16 | 3 | MPSB/Str/1728 · MPSB/Sur/1472 · MPSB/Str/1729 |  | 2EjqfCRAz07gd2_buxFMnI | 1760475
P26-WELL-L17 | P26 - 17th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 17 | 2.5 | 42.78 | 45.28 | Above transition | Cast & sunk | 2025-07-31 | IPC - 18 | 4 | MPSB/Str/1857 · MPSB/Sur/1557 · MPSB/Str/1858 · MPSB/Sur/1628 |  | 2EjqfCRAz07gd2_buxFMni | 1760485
P26-WELL-L18 | P26 - 18th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 18 | 1.85 | 45.28 | 47.13 | Above transition | Cast & sunk | 2025-08-05 | IPC - 19 | 3 | MPSB/Str/1985 · MPSB/Sur/1654 · MPSB/Str/1986 |  | 2EjqfCRAz07gd2_buxFMnc | 1760495
P26-WELL-L19 | P26 - 19th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 19 | 2.5 | 47.13 | 49.63 | Above transition | Cast & sunk | 2025-09-12 | IPC - 20 | 4 | MPSB/Str/2154 · MPSB/Sur/1773 · MPSB/Str/2155 · MPSB/Sur/1815 |  | 2EjqfCRAz07gd2_buxFMnm | 1760505
P26-WELL-L20 | P26 - 20th Lift | Well lift | P26 | P26 | EJ pier | Circular | [7 empty] | 20 | 0.92 | 49.63 | 50.55 | Above transition | Cast & sunk | 2025-10-09 | IPC - 22 | 3 | MPSB/Str/2435 · MPSB/Sur/1956 · MPSB/Str/2436
P26-WELL-PLUG | P26 - Bottom Plugging | Bottom plug | P26 | P26 | EJ pier | Circular | [12 empty] | Plugged | 2026-02-03 | IPC - 27 | 1 | MPSB/Str/3754
P26-WELL-CAP | P26 - Well Cap | Well cap | P26 | P26 | EJ pier | Circular | [12 empty] | Cast | 2026-02-25 | IPC - 27 | 1 | MPSB/Str/3951 |  | 2EjqfCRAz07gd2_buxFMno | 1760507
P26-LPYL-L00 | P26 - Lower Pylon - Starter | Lower pylon / pier lift | P26 | P26 | EJ pier | [8 empty] | 0 | 0.515 | 0 | 0.515 |  | Cast | 2026-04-04 | IPC - 30 | 3 | MPSB/Str/4318 · MPSB/Sur/3238 · MPSB/Str/4319
P26-LPYL-L01 | P26 - Lower Pylon - 1st Lift | Lower pylon / pier lift | P26 | P26 | EJ pier | [8 empty] | 1 | 4 | 0.515 | 4.515 |  | Cast | 2026-04-28 | IPC - 30 | 3 | MPSB/Str/4523 · MPSB/Sur/3378 · MPSB/Str/4524
P26-LPYL-L02 | P26 - Lower Pylon - 2nd Lift | Lower pylon / pier lift | P26 | P26 | EJ pier | [8 empty] | 2 | 4 | 4.515 | 8.515 |  | Cast | 2026-05-21 | IPC - 31 | 3 | MPSB/Str/4741 · MPSB/Sur/3526 · MPSB/Str/4742
P26-LPYL-L03 | P26 - Lower Pylon - 3rd Lift | Lower pylon / pier lift | P26 | P26 | EJ pier | [8 empty] | 3 | 2.115 | 8.515 | 10.63 |  | Cast | 2026-06-15 | IPC - 33 | 3 | MPSB/Str/4904 · MPSB/Sur/3652 · MPSB/Str/4905
P26-LPYL-L04 | P26 - Lower Pylon - 4th Lift | Lower pylon / pier lift | P26 | P26 | EJ pier | [8 empty] | 4 | 5.38 | 10.63 | 16.01 |  | Cast | 2026-07-30 | IPC - 34 | 3 | MPSB/Str/5234 · MPSB/Sur/3806 · MPSB/Str/5235
P26-LPYL-REST | P26 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P26 | P26 | EJ pier | [8 empty] | 5 | 5.614 | 16.01 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P27-WELL-CE | P27 | Cutting edge | P27 | P27 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2025-02-20 | IPC - 11 | 2 | MPSB/Sur/495 · MPSB/Sur/512
P27-WELL-L00 | P27 - Well Curb | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 0 | 6.2 | 0 | 6.2 | Curb → Below transition | Cast & sunk | 2025-03-28 | IPC - 13 | 4 | MPSB/Str/748 · MPSB/Str/832 · MPSB/Sur/819 · MPSB/Sur/821 |  | 2EjqfCRAz07gd2_buxFM9u | 1757937
P27-WELL-L01 | P27 - 1st Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 1 | 2.5 | 6.2 | 8.7 | Below transition | Cast & sunk | 2025-03-29 | IPC - 13 | 3 | MPSB/Str/962 · MPSB/Sur/836 · MPSB/Str/963 |  | 2EjqfCRAz07gd2_buxFM7y | 1757557
P27-WELL-L02 | P27 - 2nd Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 2 | 2.5 | 8.7 | 11.2 | Below transition | Cast & sunk | 2025-04-23 | IPC - 14 | 4 | MPSB/Str/1172 · MPSB/Sur/1015 · MPSB/Str/1198 · MPSB/Sur/1072 |  | 2EjqfCRAz07gd2_buxFM40 | 1757577
P27-WELL-L03 | P27 - 3rd Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 3 | 2.5 | 11.2 | 13.7 | Below transition | Cast & sunk | 2025-04-29 | IPC - 14 | 4 | MPSB/Str/1289 · MPSB/Sur/1114 · MPSB/Str/1290 · MPSB/Sur/1143 |  | 2EjqfCRAz07gd2_buxFM4K | 1757597
P27-WELL-L04 | P27 - 4th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 13.7 | 16.2 | Below transition | Cast & sunk | 2025-04-30 | IPC - 14 | 3 | MPSB/Str/1361 · MPSB/Sur/1162 · MPSB/Str/1362 |  | 2EjqfCRAz07gd2_buxFM4u | 1757617
P27-WELL-L05 | P27 - 5th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 16.2 | 18.7 | Below transition | Cast & sunk | 2025-05-13 | IPC - 15 | 4 | MPSB/Str/1444 · MPSB/Sur/1235 · MPSB/Str/1445 · MPSB/Sur/1273 |  | 2EjqfCRAz07gd2_buxFM5C | 1757637
P27-WELL-L06 | P27 - 6th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 18.7 | 21.2 | Below transition | Cast & sunk | 2025-05-23 | IPC - 15 | 4 | MPSB/Str/1532 · MPSB/Sur/1314 · MPSB/Str/1533 · MPSB/Sur/1336 |  | 2EjqfCRAz07gd2_buxFM5G | 1757657
P27-WELL-L07 | P27 - 7th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 21.2 | 23.7 | Below transition | Cast & sunk | 2025-05-28 | IPC - 15 | 3 | MPSB/Str/1590 · MPSB/Sur/1372 · MPSB/Str/1591 |  | 2EjqfCRAz07gd2_buxFM5a | 1757677
P27-WELL-L08 | P27 - 8th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 8 | 2 | 23.7 | 25.7 | Below transition | Cast & sunk | 2025-06-28 | IPC - 16 | 4 | MPSB/Str/1699 · MPSB/Sur/1457 · MPSB/Str/1700 · MPSB/Sur/1470 |  | 2EjqfCRAz07gd2_buxFMA8 | 1757697
P27-WELL-L09 | P27 - 9th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 9 | 2.7 | 25.7 | 28.4 | Below transition → Transition | Cast & sunk | 2025-07-30 | IPC - 18 | 3 | MPSB/Str/1924 · MPSB/Sur/1610 · MPSB/Str/1925 |  | 2EjqfCRAz07gd2_buxFMAS | 1757717
P27-WELL-L10 | P27 - 10th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 10 | 2.8 | 28.4 | 31.2 | Transition → Above transition | Cast & sunk | 2025-08-14 | IPC - 19 | 4 | MPSB/Str/1994 · MPSB/Sur/1656 · MPSB/Str/1995 · MPSB/Sur/1689 |  | 2EjqfCRAz07gd2_buxFMAW | 1757737
P27-WELL-L11 | P27 - 11th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 11 | 2.5 | 31.2 | 33.7 | Above transition | Cast & sunk | 2025-09-20 | IPC - 20 | 4 | MPSB/Str/2200 · MPSB/Sur/1803 · MPSB/Str/2201 · MPSB/Sur/1848 |  | 2EjqfCRAz07gd2_buxFMAq | 1757757
P27-WELL-L12 | P27 - 12th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 12 | 2.5 | 33.7 | 36.2 | Above transition | Cast & sunk | 2025-09-28 | IPC - 20 | 3 | MPSB/Str/2348 · MPSB/Sur/1886 · MPSB/Str/2349 |  | 2EjqfCRAz07gd2_buxFMBO | 1757777
P27-WELL-L13 | P27 - 13th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 36.2 | 38.7 | Above transition | Cast & sunk | 2025-10-25 | IPC - 22 | 4 | MPSB/Str/2481 · MPSB/Sur/1988 · MPSB/Str/2482 · MPSB/Sur/2042 |  | 2EjqfCRAz07gd2_buxFMBi | 1757797
P27-WELL-L14 | P27 - 14th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 38.7 | 41.2 | Above transition | Cast & sunk | 2025-11-13 | IPC - 23 | 4 | MPSB/Str/2706 · MPSB/Sur/2128 · MPSB/Str/2707 · MPSB/Sur/2185 |  | 2EjqfCRAz07gd2_buxFMBm | 1757817
P27-WELL-L15 | P27 - 15th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 41.2 | 43.7 | Above transition | Cast & sunk | 2025-11-24 | IPC - 23 | 4 | MPSB/Str/2871 · MPSB/Sur/2239 · MPSB/Str/2872 · MPSB/Sur/2260 |  | 2EjqfCRAz07gd2_buxFM84 | 1757837
P27-WELL-L16 | P27 - 16th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 43.7 | 46.2 | Above transition | Cast & sunk | 2025-11-30 | IPC - 23 | 3 | MPSB/Str/3003 · MPSB/Sur/2316 · MPSB/Str/3004 |  | 2EjqfCRAz07gd2_buxFM8e | 1757857
P27-WELL-L17 | P27 - 17th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 46.2 | 48.7 | Above transition | Cast & sunk | 2025-12-29 | IPC - 25 | 3 | MPSB/Str/3281 · MPSB/Sur/2505 · MPSB/Str/3325 |  | 2EjqfCRAz07gd2_buxFM8y | 1757877
P27-WELL-L18 | P27 - 18th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 18 | 2.5 | 48.7 | 51.2 | Above transition | Cast & sunk | 2026-01-30 | IPC - 26 | 3 | MPSB/Str/3695 · MPSB/Sur/2806 · MPSB/Str/3696 |  | 2EjqfCRAz07gd2_buxFM90 | 1757897
P27-WELL-L19 | P27 - 19th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 19 | 1.55 | 51.2 | 52.75 | Above transition | Cast & sunk | 2026-02-24 | IPC - 27 | 3 | MPSB/Str/3934 · MPSB/Sur/2981 · MPSB/Str/3935 |  | 2EjqfCRAz07gd2_buxFM9K | 1757917
P27-WELL-L20 | P27 - 20th Lift | Well lift | P27 | P27 | Outer pylon | Double-D | [7 empty] | 20 | 1.3 | 52.75 | 54.05 | Above transition | Cast & sunk | 2026-03-09 | IPC - 29 | 3 | MPSB/Str/4073 · MPSB/Sur/3081 · MPSB/Str/4074
P27-WELL-PLUG | P27 - Bottom Plugging | Bottom plug | P27 | P27 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0
P27-WELL-CAP | P27 - Well Cap | Well cap | P27 | P27 | Outer pylon | Double-D | [12 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM9x | 1757938
P27-LPYL-REST | P27 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P27 | P27 | Outer pylon | [8 empty] | 0 | 21.324 | 0 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P28-WELL-CE | P28 | Cutting edge | P28 | P28 | Middle pylon | Circular | [12 empty] | Shutter & scaffold done | 2024-12-11 | IPC - 08 | 2 | MPSB/Sur/168 · MPSB/Sur/190
P28-WELL-L00 | P28 - Well Curb | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 0 | 4.32 | 0 | 4.32 | Curb | Cast & sunk | 2024-12-28 | IPC - 09 | 4 | MPSB/Str/238 · MPSB/Str/242 · MPSB/Str/268 · MPSB/Str/269 |  | 2EjqfCRAz07gd2_buxFMlg | 1760099
P28-WELL-L01 | P28 - 1st Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 1 | 2.65 | 4.32 | 6.97 | Below transition | Cast & sunk | 2025-01-12 | IPC - 10 | 4 | MPSB/Str/336 · MPSB/Sur/271 · MPSB/Str/337 · MPSB/Sur/291 |  | 2EjqfCRAz07gd2_buxFMla | 1760109
P28-WELL-L02 | P28 - 2nd Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 2 | 2.5 | 6.97 | 9.47 | Below transition | Cast & sunk | 2025-01-20 | IPC - 10 | 4 | MPSB/Str/374 · MPSB/Sur/313 · MPSB/Str/375 · MPSB/Sur/326 |  | 2EjqfCRAz07gd2_buxFMl_ | 1760119
P28-WELL-L03 | P28 - 3rd Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 3 | 2.5 | 9.47 | 11.97 | Below transition | Cast & sunk | 2025-01-31 | IPC - 10 | 4 | MPSB/Str/433 · MPSB/Sur/369 · MPSB/Str/434 · MPSB/Sur/401 |  | 2EjqfCRAz07gd2_buxFMi8 | 1760129
P28-WELL-L04 | P28 - 4th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 4 | 2.5 | 11.97 | 14.47 | Below transition | Cast & sunk | 2025-01-31 | IPC - 10 | 3 | MPSB/Str/472 · MPSB/Sur/403 · MPSB/Str/473 |  | 2EjqfCRAz07gd2_buxFMi2 | 1760139
P28-WELL-L05 | P28 - 5th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 5 | 2.5 | 14.47 | 16.97 | Below transition | Cast & sunk | 2025-02-23 | IPC - 11 | 4 | MPSB/Str/542 · MPSB/Sur/468 · MPSB/Str/561 · MPSB/Sur/533 |  | 2EjqfCRAz07gd2_buxFMiS | 1760149
P28-WELL-L06 | P28 - 6th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 6 | 2.5 | 16.97 | 19.47 | Below transition | Cast & sunk | 2025-02-27 | IPC - 11 | 4 | MPSB/Str/641 · MPSB/Sur/563 · MPSB/Str/642 · MPSB/Sur/578 |  | 2EjqfCRAz07gd2_buxFMiM | 1760159
P28-WELL-L07 | P28 - 7th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 7 | 2.51 | 19.47 | 21.98 | Below transition | Cast & sunk | 2025-03-13 | IPC - 13 | 4 | MPSB/Str/762 · MPSB/Sur/675 · MPSB/Str/763 · MPSB/Sur/709 |  | 2EjqfCRAz07gd2_buxFMiW | 1760169
P28-WELL-L08 | P28 - 8th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 8 | 2.5 | 21.98 | 24.48 | Below transition | Cast & sunk | 2025-03-23 | IPC - 13 | 4 | MPSB/Str/830 · MPSB/Sur/743 · MPSB/Str/831 · MPSB/Sur/767 |  | 2EjqfCRAz07gd2_buxFMiw | 1760179
P28-WELL-L09 | P28 - 9th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 9 | 2.5 | 24.48 | 26.98 | Below transition | Cast & sunk | 2025-03-30 | IPC - 13 | 4 | MPSB/Str/902 · MPSB/Sur/789 · MPSB/Str/903 · MPSB/Sur/854 |  | 2EjqfCRAz07gd2_buxFMiq | 1760189
P28-WELL-L10 | P28 - 10th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 10 | 2.5 | 26.98 | 29.48 | Below transition | Cast & sunk | 2025-04-19 | IPC - 14 | 4 | MPSB/Str/1123 · MPSB/Sur/982 · MPSB/Str/1124 · MPSB/Sur/1034 |  | 2EjqfCRAz07gd2_buxFMjE | 1760199
P28-WELL-L11 | P28 - 11th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 11 | 2.5 | 29.48 | 31.98 | Below transition | Cast & sunk | 2025-04-29 | IPC - 14 | 3 | MPSB/Str/1327 · MPSB/Sur/1144 · MPSB/Str/1328 |  | 2EjqfCRAz07gd2_buxFMjO | 1760209
P28-WELL-L12 | P28 - 12th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 12 | 2.5 | 31.98 | 34.48 | Below transition | Cast & sunk | 2025-05-24 | IPC - 15 | 4 | MPSB/Str/1535 · MPSB/Sur/1321 · MPSB/Str/1536 · MPSB/Sur/1341 |  | 2EjqfCRAz07gd2_buxFMjI | 1760219
P28-WELL-L13 | P28 - 13th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 13 | 0.5 | 34.48 | 34.98 | Below transition → Transition | Cast & sunk | 2025-08-23 | IPC - 19 | 4 | MPSB/Str/2008 · MPSB/Sur/1666 · MPSB/Str/2009 · MPSB/Sur/1723 | Y | 2EjqfCRAz07gd2_buxFMji | 1760229
P28-WELL-L14 | P28 - 14th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 14 | 2.8 | 34.98 | 37.78 | Transition → Above transition | Cast & sunk | 2025-08-23 | IPC - 19 | 4 | MPSB/Str/2038 · MPSB/Sur/1697 · MPSB/Str/2039 · MPSB/Sur/1723 | Y | 2EjqfCRAz07gd2_buxFMjc | 1760239
P28-WELL-L15 | P28 - 15th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 15 | 2.5 | 37.78 | 40.28 | Above transition | Cast & sunk | 2025-09-11 | IPC - 20 | 4 | MPSB/Str/2175 · MPSB/Sur/1785 · MPSB/Str/2176 · MPSB/Sur/1810 |  | 2EjqfCRAz07gd2_buxFMjm | 1760249
P28-WELL-L16 | P28 - 16th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 16 | 2.5 | 40.28 | 42.78 | Above transition | Cast & sunk | 2025-09-25 | IPC - 20 | 3 | MPSB/Str/2292 · MPSB/Sur/1856 · MPSB/Str/2315 |  | 2EjqfCRAz07gd2_buxFMoA | 1760259
P28-WELL-L17 | P28 - 17th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 17 | 2.5 | 42.78 | 45.28 | Above transition | Cast & sunk | 2025-10-17 | IPC - 22 | 4 | MPSB/Str/2442 · MPSB/Sur/1960 · MPSB/Str/2460 · MPSB/Sur/2001 |  | 2EjqfCRAz07gd2_buxFMo4 | 1760269
P28-WELL-L18 | P28 - 18th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 18 | 2.5 | 45.28 | 47.78 | Above transition | Cast & sunk | 2025-10-30 | IPC - 22 | 3 | MPSB/Str/2632 · MPSB/Sur/2070 · MPSB/Str/2633 |  | 2EjqfCRAz07gd2_buxFMoU | 1760279
P28-WELL-L19 | P28 - 19th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 19 | 2.5 | 47.78 | 50.28 | Above transition | Cast & sunk | 2025-11-26 | IPC - 23 | 3 | MPSB/Str/2936 · MPSB/Sur/2277 · MPSB/Str/2937 |  | 2EjqfCRAz07gd2_buxFMoe | 1760289
P28-WELL-L20 | P28 - 20th Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 20 | 2.5 | 50.28 | 52.78 | Above transition | Cast & sunk | 2025-12-23 | IPC - 25 | 4 | MPSB/Str/3179 · MPSB/Sur/2432 · MPSB/Str/3180 · MPSB/Sur/2476
P28-WELL-L21 | P28 - 21st Lift | Well lift | P28 | P28 | Middle pylon | Circular | [7 empty] | 21 | 1.27 | 52.78 | 54.05 | Above transition | Cast & sunk | 2026-01-11 | IPC - 26 | 3 | MPSB/Str/3486 · MPSB/Sur/2648 · MPSB/Str/3487
P28-WELL-PLUG | P28 - Bottom Plugging | Bottom plug | P28 | P28 | Middle pylon | Circular | [12 empty] | Not started |  |  | 0
P28-WELL-CAP | P28 - Well Cap | Well cap | P28 | P28 | Middle pylon | Circular | [12 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFMog | 1760291
P28-LPYL-REST | P28 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P28 | P28 | Middle pylon | [8 empty] | 0 | 21.624 | 0 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P29-WELL-CE | P29 | Cutting edge | P29 | P29 | Outer pylon | Double-D | [12 empty] | Shutter & scaffold done | 2025-01-22 | IPC - 10 | 2 | MPSB/Sur/241 · MPSB/Sur/343
P29-WELL-L00 | P29 - Well Curb | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 0 | 6.2 | 0 | 6.2 | Curb → Below transition | Cast & sunk | 2025-02-18 | IPC - 11 | 4 | MPSB/Str/500 · MPSB/Str/523 · MPSB/Sur/487 · MPSB/Sur/493 |  | 2EjqfCRAz07gd2_buxFMHJ | 1758426
P29-WELL-L01 | P29 - 1st Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 1 | 2 | 6.2 | 8.2 | Below transition | Cast & sunk | 2025-02-27 | IPC - 11 | 3 | MPSB/Str/657 · MPSB/Sur/579 · MPSB/Str/658 |  | 2EjqfCRAz07gd2_buxFMFN | 1758046
P29-WELL-L02 | P29 - 2nd Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 2 | 1.15 | 8.2 | 9.35 | Below transition | Cast & sunk | 2025-02-28 | IPC - 11 | 3 | MPSB/Str/695 · MPSB/Sur/606 · MPSB/Str/696 |  | 2EjqfCRAz07gd2_buxFMFx | 1758066
P29-WELL-L03 | P29 - 3rd Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 3 | 2.5 | 9.35 | 11.85 | Below transition | Cast & sunk | 2025-03-16 | IPC - 13 | 4 | MPSB/Str/784 · MPSB/Sur/702 · MPSB/Str/785 · MPSB/Sur/724 |  | 2EjqfCRAz07gd2_buxFMCF | 1758086
P29-WELL-L04 | P29 - 4th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 4 | 2.5 | 11.85 | 14.35 | Below transition | Cast & sunk | 2025-03-25 | IPC - 13 | 4 | MPSB/Str/848 · MPSB/Sur/754 · MPSB/Str/849 · MPSB/Sur/779 |  | 2EjqfCRAz07gd2_buxFMCJ | 1758106
P29-WELL-L05 | P29 - 5th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 5 | 2.5 | 14.35 | 16.85 | Below transition | Cast & sunk | 2025-03-31 | IPC - 13 | 4 | MPSB/Str/964 · MPSB/Sur/837 · MPSB/Str/965 · MPSB/Sur/894 |  | 2EjqfCRAz07gd2_buxFMCd | 1758126
P29-WELL-L06 | P29 - 6th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 6 | 2.5 | 16.85 | 19.35 | Below transition | Cast & sunk | 2025-04-17 | IPC - 14 | 4 | MPSB/Str/1121 · MPSB/Sur/981 · MPSB/Str/1122 · MPSB/Sur/1018 |  | 2EjqfCRAz07gd2_buxFMDB | 1758146
P29-WELL-L07 | P29 - 7th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 7 | 2.5 | 19.35 | 21.85 | Below transition | Cast & sunk | 2025-04-21 | IPC - 14 | 3 | MPSB/Str/1207 · MPSB/Sur/1051 · MPSB/Str/1208 |  | 2EjqfCRAz07gd2_buxFMDV | 1758166
P29-WELL-L08 | P29 - 8th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 8 | 2.5 | 21.85 | 24.35 | Below transition | Cast & sunk | 2025-05-18 | IPC - 15 | 4 | MPSB/Str/1418 · MPSB/Sur/1218 · MPSB/Str/1419 · MPSB/Sur/1303 |  | 2EjqfCRAz07gd2_buxFMDZ | 1758186
P29-WELL-L09 | P29 - 9th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 9 | 2.2 | 24.35 | 26.55 | Below transition → Transition | Cast & sunk | 2025-05-20 | IPC - 15 | 4 | MPSB/Str/1489 · MPSB/Sur/1275 · MPSB/Str/1490 · MPSB/Sur/1324 |  | 2EjqfCRAz07gd2_buxFMDt | 1758206
P29-WELL-L10 | P29 - 10th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 10 | 2.8 | 26.55 | 29.35 | Transition | Cast & sunk | 2025-05-27 | IPC - 15 | 4 | MPSB/Str/1563 · MPSB/Sur/1343 · MPSB/Str/1564 · MPSB/Sur/1362 |  | 2EjqfCRAz07gd2_buxFMIR | 1758226
P29-WELL-L11 | P29 - 11th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 11 | 2.7 | 29.35 | 32.05 | Transition → Above transition | Cast & sunk | 2025-06-27 | IPC - 16 | 3 | MPSB/Str/1708 · MPSB/Sur/1460 · MPSB/Str/1709 |  | 2EjqfCRAz07gd2_buxFMIl | 1758246
P29-WELL-L12 | P29 - 12th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 12 | 2.8 | 32.05 | 34.85 | Above transition | Cast & sunk | 2025-07-25 | IPC - 18 | 4 | MPSB/Str/1760 · MPSB/Sur/1490 · MPSB/Str/1761 · MPSB/Sur/1582 |  | 2EjqfCRAz07gd2_buxFMIp | 1758266
P29-WELL-L13 | P29 - 13th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 13 | 2.5 | 34.85 | 37.35 | Above transition | Cast & sunk | 2025-08-30 | IPC - 19 | 3 | MPSB/Str/2114 · MPSB/Sur/1748 · MPSB/Str/2115 |  | 2EjqfCRAz07gd2_buxFMJ7 | 1758286
P29-WELL-L14 | P29 - 14th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 14 | 2.5 | 37.35 | 39.85 | Above transition | Cast & sunk | 2025-09-20 | IPC - 20 | 3 | MPSB/Str/2280 · MPSB/Sur/1846 · MPSB/Str/2281 |  | 2EjqfCRAz07gd2_buxFMJh | 1758306
P29-WELL-L15 | P29 - 15th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 15 | 2.5 | 39.85 | 42.35 | Above transition | Cast & sunk | 2025-10-13 | IPC - 22 | 4 | MPSB/Str/2413 · MPSB/Sur/1935 · MPSB/Str/2414 · MPSB/Sur/1974 |  | 2EjqfCRAz07gd2_buxFMJ$ | 1758326
P29-WELL-L16 | P29 - 16th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 16 | 2.5 | 42.35 | 44.85 | Above transition | Cast & sunk | 2025-10-25 | IPC - 22 | 3 | MPSB/Str/2586 · MPSB/Sur/2049 · MPSB/Str/2587 |  | 2EjqfCRAz07gd2_buxFMG3 | 1758346
P29-WELL-L17 | P29 - 17th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 17 | 2.5 | 44.85 | 47.35 | Above transition | Cast & sunk | 2025-10-31 | IPC - 22 | 3 | MPSB/Str/2652 · MPSB/Sur/2082 · MPSB/Str/2653 |  | 2EjqfCRAz07gd2_buxFMGN | 1758366
P29-WELL-L18 | P29 - 18th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 18 | 2.55 | 47.35 | 49.9 | Above transition | Cast & sunk | 2025-11-28 | IPC - 23 | 3 | MPSB/Str/2972 · MPSB/Sur/2296 · MPSB/Str/2973 |  | 2EjqfCRAz07gd2_buxFMGx | 1758386
P29-WELL-L19 | P29 - 19th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 19 | 3.15 | 49.9 | 53.05 | Above transition | Cast & sunk | 2025-12-12 | IPC - 25 | 3 | MPSB/Str/3092 · MPSB/Sur/2371 · MPSB/Str/3123 |  | 2EjqfCRAz07gd2_buxFMHF | 1758406
P29-WELL-L20 | P29 - 20th Lift | Well lift | P29 | P29 | Outer pylon | Double-D | [7 empty] | 20 | 1 | 53.05 | 54.05 | Above transition | Cast & sunk | 2026-02-02 | IPC - 27 | 3 | MPSB/Str/3746 · MPSB/Sur/2844 · MPSB/Str/3747
P29-WELL-PLUG | P29 - Bottom Plugging | Bottom plug | P29 | P29 | Outer pylon | Double-D | [12 empty] | Plugged | 2026-05-28 | IPC - 31 | 1 | MPSB/Str/4803
P29-WELL-CAP | P29 - Well Cap | Well cap | P29 | P29 | Outer pylon | Double-D | [12 empty] | Cast | 2026-06-29 | IPC - 33 | 2 | MPSB/Sur/3700 · MPSB/Str/5029 |  | 2EjqfCRAz07gd2_buxFMHI | 1758427
P29-LPYL-L00 | P29 - Lower Pylon - Starter | Lower pylon / pier lift | P29 | P29 | Outer pylon | [8 empty] | 0 | 0.63 | 0 | 0.63 |  | Cast | 2026-07-13 | IPC - 34 | 3 | MPSB/Str/5127 · MPSB/Sur/3752 · MPSB/Str/5128
P29-LPYL-L01 | P29 - Lower Pylon - 1st Lift | Lower pylon / pier lift | P29 | P29 | Outer pylon | [8 empty] | 1 | 2.115 | 0.63 | 2.745 |  | Cast | 2026-07-21 | IPC - 34 | 3 | MPSB/Str/5175 · MPSB/Sur/3781 · MPSB/Str/5176
P29-LPYL-L02 | P29 - Lower Pylon - 2nd Lift | Lower pylon / pier lift | P29 | P29 | Outer pylon | [8 empty] | 2 | 4 | 2.745 | 6.745 |  | Cast | 2026-07-30 | IPC - 34 | 3 | MPSB/Str/5230 · MPSB/Sur/3804 · MPSB/Str/5231
P29-LPYL-REST | P29 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P29 | P29 | Outer pylon | [8 empty] | 3 | 14.579 | 6.745 | 21.324 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P30-WELL-CE | P30 | Cutting edge | P30 | P30 | EJ pier | Circular | [12 empty] | Shutter & scaffold done | 2025-11-01 | IPC - 23 | 2 | MPSB/Sur/2068 · MPSB/Sur/2110
P30-WELL-L00 | P30 - Well Curb | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 0 | 4.48 | 0 | 4.48 | Curb → Below transition | Cast & sunk | 2025-11-19 | IPC - 23 | 4 | MPSB/Str/2757 · MPSB/Sur/2164 · MPSB/Str/2758 · MPSB/Sur/2225 |  | 2EjqfCRAz07gd2_buxFMs5 | 1760524
P30-WELL-L01 | P30 - 1st Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 1 | 2.5 | 4.48 | 6.98 | Below transition | Cast & sunk | 2025-11-26 | IPC - 23 | 4 | MPSB/Str/2901 · MPSB/Sur/2251 · MPSB/Str/2902 · MPSB/Sur/2275 |  | 2EjqfCRAz07gd2_buxFMsV | 1760534
P30-WELL-L02 | P30 - 2nd Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 2 | 2.5 | 6.98 | 9.48 | Below transition | Cast & sunk | 2025-11-28 | IPC - 23 | 3 | MPSB/Str/2970 · MPSB/Sur/2295 · MPSB/Str/2971 |  | 2EjqfCRAz07gd2_buxFMsf | 1760544
P30-WELL-L03 | P30 - 3rd Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 3 | 2.5 | 9.48 | 11.98 | Below transition | Cast & sunk | 2025-11-30 | IPC - 23 | 3 | MPSB/Str/2997 · MPSB/Sur/2313 · MPSB/Str/2998 |  | 2EjqfCRAz07gd2_buxFMsZ | 1760554
P30-WELL-L04 | P30 - 4th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 4 | 2.5 | 11.98 | 14.48 | Below transition | Cast & sunk | 2025-12-09 | IPC - 25 | 4 | MPSB/Str/3069 · MPSB/Sur/2353 · MPSB/Str/3070 · MPSB/Sur/2373 |  | 2EjqfCRAz07gd2_buxFMsz | 1760564
P30-WELL-L05 | P30 - 5th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 5 | 2.5 | 14.48 | 16.98 | Below transition | Cast & sunk | 2025-12-10 | IPC - 25 | 3 | MPSB/Str/3099 · MPSB/Sur/2382 · MPSB/Str/3100 |  | 2EjqfCRAz07gd2_buxFMst | 1760574
P30-WELL-L06 | P30 - 6th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 6 | 2.5 | 16.98 | 19.48 | Below transition | Cast & sunk | 2025-12-18 | IPC - 25 | 4 | MPSB/Str/3152 · MPSB/Sur/2418 · MPSB/Str/3153 · MPSB/Sur/2439 |  | 2EjqfCRAz07gd2_buxFMt1 | 1760584
P30-WELL-L07 | P30 - 7th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 7 | 2.5 | 19.48 | 21.98 | Below transition | Cast & sunk | 2025-12-22 | IPC - 25 | 4 | MPSB/Str/3201 · MPSB/Sur/2448 · MPSB/Str/3202 · MPSB/Sur/2469 |  | 2EjqfCRAz07gd2_buxFMtR | 1760594
P30-WELL-L08 | P30 - 8th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 8 | 0.5 | 21.98 | 22.48 | Below transition → Transition | Cast & sunk | 2025-12-28 | IPC - 25 | 3 | MPSB/Str/3307 · MPSB/Sur/2526 · MPSB/Str/3308 |  | 2EjqfCRAz07gd2_buxFMtL | 1760604
P30-WELL-L09 | P30 - 9th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 9 | 2.8 | 22.48 | 25.28 | Transition → Above transition | Cast & sunk | 2025-12-30 | IPC - 25 | 3 | MPSB/Str/3354 · MPSB/Sur/2555 · MPSB/Str/3355 |  | 2EjqfCRAz07gd2_buxFMtl | 1760614
P30-WELL-L10 | P30 - 10th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 10 | 2.5 | 25.28 | 27.78 | Above transition | Cast & sunk | 2026-01-17 | IPC - 26 | 4 | MPSB/Str/3510 · MPSB/Sur/2669 · MPSB/Str/3511 · MPSB/Sur/2700 |  | 2EjqfCRAz07gd2_buxFMtv | 1760624
P30-WELL-L11 | P30 - 11th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 11 | 2.5 | 27.78 | 30.28 | Above transition | Cast & sunk | 2026-01-22 | IPC - 26 | 4 | MPSB/Str/3589 · MPSB/Sur/2726 · MPSB/Str/3590 · MPSB/Sur/2744 |  | 2EjqfCRAz07gd2_buxFMtp | 1760634
P30-WELL-L12 | P30 - 12th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 12 | 2.5 | 30.28 | 32.78 | Above transition | Cast & sunk | 2026-01-25 | IPC - 26 | 4 | MPSB/Str/3640 · MPSB/Sur/2757 · MPSB/Str/3641 · MPSB/Sur/2774 |  | 2EjqfCRAz07gd2_buxFMqD | 1760644
P30-WELL-L13 | P30 - 13th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 13 | 2.5 | 32.78 | 35.28 | Above transition | Cast & sunk | 2026-01-30 | IPC - 26 | 4 | MPSB/Str/3653 · MPSB/Sur/2778 · MPSB/Str/3654 · MPSB/Sur/2801 |  | 2EjqfCRAz07gd2_buxFMq7 | 1760654
P30-WELL-L14 | P30 - 14th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 14 | 2.5 | 35.28 | 37.78 | Above transition | Cast & sunk | 2026-01-31 | IPC - 26 | 3 | MPSB/Str/3732 · MPSB/Sur/2826 · MPSB/Str/3733 |  | 2EjqfCRAz07gd2_buxFMqH | 1760664
P30-WELL-L15 | P30 - 15th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 15 | 2.5 | 37.78 | 40.28 | Above transition | Cast & sunk | 2026-02-15 | IPC - 27 | 4 | MPSB/Str/3834 · MPSB/Sur/2914 · MPSB/Str/3835 · MPSB/Sur/2936 |  | 2EjqfCRAz07gd2_buxFMqh | 1760674
P30-WELL-L16 | P30 - 16th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 16 | 2.5 | 40.28 | 42.78 | Above transition | Cast & sunk | 2026-02-26 | IPC - 27 | 3 | MPSB/Str/3955 · MPSB/Sur/3008 · MPSB/Str/3956 |  | 2EjqfCRAz07gd2_buxFMqb | 1760684
P30-WELL-L17 | P30 - 17th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 17 | 2.5 | 42.78 | 45.28 | Above transition | Cast & sunk | 2026-04-30 | IPC - 30 | 3 | MPSB/Str/4567 · MPSB/Sur/3406 · MPSB/Str/4568 |  | 2EjqfCRAz07gd2_buxFMq$ | 1760694
P30-WELL-L18 | P30 - 18th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 18 | 2.5 | 45.28 | 47.78 | Above transition | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFMr9 | 1760704 | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P30-WELL-L19 | P30 - 19th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 19 | 2.5 | 47.78 | 50.28 | Above transition | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFMr3 | 1760714 | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P30-WELL-L20 | P30 - 20th Lift | Well lift | P30 | P30 | EJ pier | Circular | [7 empty] | 20 | 0.27 | 50.28 | 50.55 | Above transition | Not started |  |  | 0 |  |  |  |  | PLANNED — height estimated at 2.5 m; real height comes from the RFI
P30-WELL-PLUG | P30 - Bottom Plugging | Bottom plug | P30 | P30 | EJ pier | Circular | [12 empty] | Not started |  |  | 0
P30-WELL-CAP | P30 - Well Cap | Well cap | P30 | P30 | EJ pier | Circular | [12 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFMr5 | 1760716
P30-LPYL-REST | P30 - Lower Pylon - (lifts to come) | Lower pylon / pier lift | P30 | P30 | EJ pier | [8 empty] | 0 | 21.624 | 0 | 21.624 |  | Not started |  |  | 0 |  |  |  |  | PLANNED — balance height as one block; split when lift RFIs arrive
P6-BP-S01a-E | P6-BP-S01a-E | Precast segment | P6 | P6 | EJ pier |  | 1 | P6-P7 | BP | 1 | Y |  | 1 | [5 empty] | Cast in yard | 2026-01-13 | IPC - 26 | 2 | MPSB/Sur/2672 · MPSB/MB/712
P6-BP-S01-E | P6-BP-S01-E | Precast segment | P6 | P6 | EJ pier |  | 1 | P6-P7 | BP | 1 |  |  | 2 | [5 empty] | Cast in yard | 2026-01-16 | IPC - 26 | 3 | MPSB/MB/735 · MPSB/Sur/2690 · MPSB/MB/737
P6-BP-S02-E | P6-BP-S02-E | Precast segment | P6 | P6 | EJ pier |  | 1 | P6-P7 | BP | 2 |  |  | 3 | [5 empty] | Cast in yard | 2026-01-20 | IPC - 26 | 3 | MPSB/MB/756 · MPSB/Sur/2721 · MPSB/MB/763
P6-BP-S03-E | P6-BP-S03-E | Precast segment | P6 | P6 | EJ pier |  | 1 | P6-P7 | BP | 3 |  |  | 4 | [5 empty] | Cast in yard | 2026-01-27 | IPC - 26 | 3 | MPSB/MB/789 · MPSB/Sur/2776 · MPSB/MB/810
P6-BP-S04-E | P6-BP-S04-E | Precast segment | P6 | P6 | EJ pier |  | 1 | P6-P7 | BP | 4 |  |  | 5 | [5 empty] | Cast in yard | 2026-01-30 | IPC - 26 | 2 | MPSB/Sur/2815 · MPSB/MB/841
P6-BP-S05-E | P6-BP-S05-E | Precast segment | P6 | P6 | EJ pier |  | 1 | P6-P7 | BP | 5 |  |  | 6 | [5 empty] | Cast in yard | 2026-02-03 | IPC - 27 | 3 | MPSB/MB/853 · MPSB/Sur/2850 · MPSB/MB/892
P6-BP-S06-E | P6-BP-S06-E | Precast segment | P6 | P6 | EJ pier |  | 1 | P6-P7 | BP | 6 |  |  | 7 | [5 empty] | Cast in yard | 2026-02-08 | IPC - 27 | 3 | MPSB/MB/910 · MPSB/Sur/2888 · MPSB/MB/937
P7-KS-S34a-O | P7-KS-S34a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 34 | Y |  | 8 | [5 empty] | Cast in yard | 2026-03-26 | IPC - 29 | 3 | MPSB/MB/1344 · MPSB/Sur/3177 · MPSB/MB/1362
P7-KS-S33a-O | P7-KS-S33a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 33 | Y | Y | 9 | [5 empty] | Cast in yard | 2026-03-19 | IPC - 29 | 3 | MPSB/MB/1298 · MPSB/Sur/3144 · MPSB/MB/1303
P7-KS-S32a-O | P7-KS-S32a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 32 | Y |  | 10 | [5 empty] | Cast in yard | 2026-03-14 | IPC - 29 | 3 | MPSB/MB/1244 · MPSB/Sur/3122 · MPSB/Str/4118
P7-KS-S31a-O | P7-KS-S31a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 31 | Y | Y | 11 | [5 empty] | Cast in yard | 2026-03-10 | IPC - 29 | 3 | MPSB/MB/1200 · MPSB/Sur/3085 · MPSB/MB/1206
P7-KS-S30a-O | P7-KS-S30a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 30 | Y |  | 12 | [5 empty] | Cast in yard | 2026-03-06 | IPC - 29 | 3 | MPSB/MB/1090 · MPSB/Sur/3065 · MPSB/MB/1161
P7-KS-S29a-O | P7-KS-S29a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 29 | Y | Y | 13 | [5 empty] | Cast in yard | 2026-02-26 | IPC - 27 | 3 | MPSB/MB/1082 · MPSB/Sur/3011 · MPSB/MB/1089
P7-KS-S28a-O | P7-KS-S28a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 28 | Y |  | 14 | [5 empty] | Cast in yard | 2026-02-24 | IPC - 27 | 3 | MPSB/MB/923 · MPSB/Sur/2987 · MPSB/MB/1073
P7-KS-S27a-O | P7-KS-S27a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 27 | Y | Y | 15 | [5 empty] | Cast in yard | 2026-02-19 | IPC - 27 | 3 | MPSB/MB/1000 · MPSB/Sur/2959 · MPSB/MB/1030
P7-KS-S26a-O | P7-KS-S26a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 26 | Y |  | 16 | [5 empty] | Cast in yard | 2026-02-16 | IPC - 27 | 3 | MPSB/MB/980 · MPSB/Sur/2941 · MPSB/MB/999
P7-KS-S25a-O | P7-KS-S25a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 25 | Y | Y | 17 | [5 empty] | Cast in yard | 2026-02-09 | IPC - 27 | 3 | MPSB/MB/931 · MPSB/Sur/2896 · MPSB/MB/942
P7-KS-S24a-O | P7-KS-S24a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 24 | Y |  | 18 | [5 empty] | Cast in yard | 2026-01-31 | IPC - 27 | 3 | MPSB/MB/867 · MPSB/Sur/2832 · MPSB/MB/875
P7-KS-S23a-O | P7-KS-S23a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 23 | Y | Y | 19 | [5 empty] | Cast in yard | 2026-01-30 | IPC - 26 | 3 | MPSB/MB/833 · MPSB/Sur/2813 · MPSB/MB/838
P7-KS-S22a-O | P7-KS-S22a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 22 | Y |  | 20 | [5 empty] | Cast in yard | 2026-01-27 | IPC - 26 | 3 | MPSB/MB/806 · MPSB/Sur/2777 · MPSB/MB/811
P7-KS-S21a-O | P7-KS-S21a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 21 | Y | Y | 21 | [5 empty] | Cast in yard | 2026-01-16 | IPC - 26 | 3 | MPSB/MB/726 · MPSB/Sur/2692 · MPSB/MB/739
P7-KS-S20a-O | P7-KS-S20a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 20 | Y |  | 22 | [5 empty] | Cast in yard | 2026-01-12 | IPC - 26 | 3 | MPSB/MB/686 · MPSB/Sur/2662 · MPSB/MB/700
P7-KS-S19a-O | P7-KS-S19a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 19 | Y | Y | 23 | [5 empty] | Cast in yard | 2026-01-06 | IPC - 26 | 3 | MPSB/MB/630 · MPSB/Sur/2615 · MPSB/MB/654
P7-KS-S18a-O | P7-KS-S18a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 18 | Y |  | 24 | [5 empty] | Cast in yard | 2025-12-30 | IPC - 25 | 3 | MPSB/MB/601 · MPSB/Sur/2552 · MPSB/MB/604
P7-KS-S17a-O | P7-KS-S17a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 17 | Y | Y | 25 | [5 empty] | Cast in yard | 2025-12-24 | IPC - 25 | 3 | MPSB/MB/535 · MPSB/Sur/2491 · MPSB/MB/554
P7-KS-S16a-O | P7-KS-S16a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 16 | Y |  | 26 | [5 empty] | Cast in yard | 2025-12-17 | IPC - 25 | 3 | MPSB/MB/501 · MPSB/Sur/2428 · MPSB/MB/514
P7-KS-S15a-O | P7-KS-S15a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 15 | Y | Y | 27 | [5 empty] | Cast in yard | 2025-12-13 | IPC - 25 | 3 | MPSB/MB/484 · MPSB/Sur/2405 · MPSB/MB/493
P7-KS-S14a-O | P7-KS-S14a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 14 | Y |  | 28 | [5 empty] | Cast in yard | 2025-12-10 | IPC - 25 | 3 | MPSB/MB/466 · MPSB/Sur/2379 · MPSB/MB/473
P7-KS-S13a-O | P7-KS-S13a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 13 | Y | Y | 29 | [5 empty] | Cast in yard | 2025-12-05 | IPC - 25 | 3 | MPSB/MB/444 · MPSB/Sur/2344 · MPSB/MB/451
P7-KS-S12a-O | P7-KS-S12a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 12 | Y |  | 30 | [5 empty] | Cast in yard | 2025-11-29 | IPC - 23 | 3 | MPSB/MB/420 · MPSB/Sur/2304 · MPSB/MB/423
P7-KS-S11a-O | P7-KS-S11a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 11 | Y | Y | 31 | [5 empty] | Cast in yard | 2025-11-27 | IPC - 23 | 3 | MPSB/MB/404 · MPSB/Sur/2285 · MPSB/MB/411
P7-KS-S10a-O | P7-KS-S10a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 10 | Y |  | 32 | [5 empty] | Cast in yard | 2025-11-22 | IPC - 23 | 3 | MPSB/MB/384 · MPSB/Sur/2249 · MPSB/MB/391
P7-KS-S09a-O | P7-KS-S09a-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 9 | Y | Y | 33 | [5 empty] | Cast in yard | 2025-11-17 | IPC - 23 | 3 | MPSB/MB/354 · MPSB/Sur/2205 · MPSB/MB/361
P7-KS-S08a-O | P7-KS-S08a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 8 | Y |  | 34 | [5 empty] | Cast in yard | 2026-01-30 | IPC - 26 | 3 | MPSB/MB/831 · MPSB/Sur/2814 · MPSB/MB/839
P7-KS-S07a-O | P7-KS-S07a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 7 | Y |  | 35 | [5 empty] | Cast in yard | 2026-01-24 | IPC - 26 | 3 | MPSB/MB/787 · MPSB/Sur/2762 · MPSB/MB/793
P7-KS-S06a-O | P7-KS-S06a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 6 | Y |  | 36 | [5 empty] | Cast in yard | 2026-01-20 | IPC - 26 | 3 | MPSB/MB/755 · MPSB/Sur/2722 · MPSB/MB/764
P7-KS-S05a-O | P7-KS-S05a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 5 | Y |  | 37 | [5 empty] | Cast in yard | 2026-01-16 | IPC - 26 | 3 | MPSB/MB/734 · MPSB/Sur/2691 · MPSB/MB/738
P7-KS-S04a-O | P7-KS-S04a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 4 | Y |  | 38 | [5 empty] | Cast in yard | 2026-01-13 | IPC - 26 | 3 | MPSB/MB/710 · MPSB/Sur/2671 · MPSB/MB/711
P7-KS-S03a-O | P7-KS-S03a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 3 | Y |  | 39 | [5 empty] | Cast in yard | 2026-01-11 | IPC - 26 | 3 | MPSB/MB/665 · MPSB/Sur/2665 · MPSB/MB/695
P7-KS-S02a-O | P7-KS-S02a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 2 | Y |  | 40 | [5 empty] | Cast in yard | 2026-01-05 | IPC - 26 | 3 | MPSB/MB/628 · MPSB/Sur/2611 · MPSB/MB/636
P7-KS-S01a-O | P7-KS-S01a-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P6-P7 | KS | 1 | Y |  | 41 | [5 empty] | Cast in yard | 2026-12-30 | IPC - 26 | 3 | MPSB/MB/603 · MPSB/Sur/2587 · MPSB/MB/615
P7-BP-S01-O | P7-BP-S01-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 1 |  |  | 42 | [5 empty] | Cast in yard | 2025-11-17 | IPC - 23 | 3 | MPSB/MB/351 · MPSB/Sur/2207 · MPSB/MB/363
P7-BP-S02-O | P7-BP-S02-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 2 |  |  | 43 | [5 empty] | Cast in yard | 2025-11-24 | IPC - 23 | 3 | MPSB/MB/383 · MPSB/Sur/2258 · MPSB/MB/397
P7-BP-S03-O | P7-BP-S03-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 3 |  |  | 44 | [5 empty] | Cast in yard | 2025-11-29 | IPC - 23 | 3 | MPSB/MB/412 · MPSB/Sur/2303 · MPSB/MB/422
P7-BP-S04-O | P7-BP-S04-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 4 |  |  | 45 | [5 empty] | Cast in yard | 2025-12-06 | IPC - 25 | 3 | MPSB/MB/445 · MPSB/Sur/2352 · MPSB/MB/454
P7-BP-S05-O | P7-BP-S05-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 5 |  |  | 46 | [5 empty] | Cast in yard | 2025-12-10 | IPC - 25 | 3 | MPSB/MB/467 · MPSB/Sur/2380 · MPSB/MB/474
P7-BP-S06-O | P7-BP-S06-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 6 |  |  | 47 | [5 empty] | Cast in yard | 2025-12-17 | IPC - 25 | 3 | MPSB/MB/496 · MPSB/Sur/2427 · MPSB/MB/513
P7-BP-S07-O | P7-BP-S07-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 7 |  |  | 48 | [5 empty] | Cast in yard | 2025-12-22 | IPC - 25 | 3 | MPSB/MB/512 · MPSB/Sur/2463 · MPSB/MB/537
P7-BP-S08-O | P7-BP-S08-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 8 |  |  | 49 | [5 empty] | Cast in yard | 2025-12-27 | IPC - 25 | 3 | MPSB/MB/545 · MPSB/Sur/2515 · MPSB/MB/576
P7-BP-S09-O | P7-BP-S09-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 9 |  | Y | 50 | [5 empty] | Cast in yard | 2025-11-12 | IPC - 23 | 3 | MPSB/MB/338 · MPSB/Sur/2177 · MPSB/MB/352
P7-BP-S10-O | P7-BP-S10-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 10 |  |  | 51 | [5 empty] | Cast in yard | 2025-11-17 | IPC - 23 | 3 | MPSB/MB/358 · MPSB/Sur/2206 · MPSB/MB/362
P7-BP-S11-O | P7-BP-S11-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 11 |  | Y | 52 | [5 empty] | Cast in yard | 2025-11-20 | IPC - 23 | 3 | MPSB/MB/367 · MPSB/Sur/2238 · MPSB/MB/382
P7-BP-S12-O | P7-BP-S12-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 12 |  |  | 53 | [5 empty] | Cast in yard | 2025-11-24 | IPC - 23 | 3 | MPSB/MB/368 · MPSB/Sur/2257 · MPSB/MB/396
P7-BP-S13-O | P7-BP-S13-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 13 |  | Y | 54 | [5 empty] | Cast in yard | 2025-11-27 | IPC - 23 | 3 | MPSB/MB/403 · MPSB/Sur/2291 · MPSB/MB/415
P7-BP-S14-O | P7-BP-S14-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 14 |  |  | 55 | [5 empty] | Cast in yard | 2025-11-28 | IPC - 23 | 2 | MPSB/MB/398 · MPSB/MB/419
P7-BP-S15-O | P7-BP-S15-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 15 |  | Y | 56 | [5 empty] | Cast in yard | 2025-12-04 | IPC - 25 | 3 | MPSB/MB/440 · MPSB/Sur/2337 · MPSB/MB/448
P7-BP-S16-O | P7-BP-S16-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 16 |  |  | 57 | [5 empty] | Cast in yard | 2025-12-10 | IPC - 25 | 3 | MPSB/MB/458 · MPSB/Sur/2381 · MPSB/MB/468
P7-BP-S17-O | P7-BP-S17-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 17 |  | Y | 58 | [5 empty] | Cast in yard | 2025-12-15 | IPC - 25 | 3 | MPSB/MB/476 · MPSB/Sur/2415 · MPSB/MB/504
P7-BP-S18-O | P7-BP-S18-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 18 |  |  | 59 | [5 empty] | Cast in yard | 2025-12-17 | IPC - 25 | 3 | MPSB/MB/511 · MPSB/Sur/2429 · MPSB/MB/515
P7-BP-S19-O | P7-BP-S19-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 19 |  | Y | 60 | [5 empty] | Cast in yard | 2025-12-22 | IPC - 25 | 3 | MPSB/MB/531 · MPSB/Sur/2464 · MPSB/MB/538
P7-BP-S20-O | P7-BP-S20-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 20 |  |  | 61 | [5 empty] | Cast in yard | 2025-12-25 | IPC - 25 | 3 | MPSB/MB/552 · MPSB/Sur/2495 · MPSB/MB/559
P7-BP-S21-O | P7-BP-S21-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 21 |  | Y | 62 | [5 empty] | Cast in yard | 2025-12-30 | IPC - 25 | 2 | MPSB/Sur/2531 · MPSB/MB/584
P7-BP-S22-O | P7-BP-S22-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 22 |  |  | 63 | [5 empty] | Cast in yard | 2025-12-08 | IPC - 25 | 3 | MPSB/MB/459 · MPSB/Sur/2367 · MPSB/MB/465
P7-BP-S23-O | P7-BP-S23-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 23 |  | Y | 64 | [5 empty] | Cast in yard | 2025-12-12 | IPC - 25 | 3 | MPSB/MB/477 · MPSB/Sur/2399 · MPSB/MB/489
P7-BP-S24-O | P7-BP-S24-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 24 |  |  | 65 | [5 empty] | Cast in yard | 2025-12-16 | IPC - 25 | 3 | MPSB/MB/502 · MPSB/Sur/2421 · MPSB/MB/510
P7-BP-S25-O | P7-BP-S25-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 25 |  | Y | 66 | [5 empty] | Cast in yard | 2025-12-19 | IPC - 25 | 3 | MPSB/MB/521 · MPSB/Sur/2449 · MPSB/MB/525
P7-BP-S26-O | P7-BP-S26-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 26 |  |  | 67 | [5 empty] | Cast in yard | 2025-12-24 | IPC - 25 | 3 | MPSB/MB/543 · MPSB/Sur/2490 · MPSB/MB/553
P7-BP-S27-O | P7-BP-S27-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 27 |  | Y | 68 | [5 empty] | Cast in yard | 2025-12-29 | IPC - 25 | 3 | MPSB/MB/578 · MPSB/Sur/2530 · MPSB/MB/583
P7-BP-S28-O | P7-BP-S28-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 28 |  |  | 69 | [5 empty] | Cast in yard | 2026-12-30 | IPC - 26 | 3 | MPSB/MB/602 · MPSB/Sur/2586 · MPSB/MB/614
P7-BP-S29-O | P7-BP-S29-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 29 |  | Y | 70 | [5 empty] | Cast in yard | 2026-01-06 | IPC - 26 | 3 | MPSB/MB/629 · MPSB/Sur/2616 · MPSB/MB/655
P7-BP-S30-O | P7-BP-S30-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 30 |  |  | 71 | [5 empty] | Cast in yard | 2026-01-09 | IPC - 26 | 3 | MPSB/MB/657 · MPSB/Sur/2639 · MPSB/MB/678
P7-BP-S31-O | P7-BP-S31-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 31 |  | Y | 72 | [5 empty] | Cast in yard | 2026-01-14 | IPC - 26 | 3 | MPSB/MB/689 · MPSB/Sur/2679 · MPSB/MB/727
P7-BP-S32-O | P7-BP-S32-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 32 |  |  | 73 | [5 empty] | Cast in yard | 2026-01-19 | IPC - 26 | 3 | MPSB/MB/741 · MPSB/Sur/2719 · MPSB/MB/757
P7-BP-S33-O | P7-BP-S33-O© | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 33 |  | Y | 74 | [5 empty] | Cast in yard | 2026-01-22 | IPC - 26 | 3 | MPSB/MB/770 · MPSB/Sur/2739 · MPSB/MB/774
P7-BP-S34-O | P7-BP-S34-O | Precast segment | P7 | P7 | Outer pylon |  | 1 | P7-P8 | BP | 34 |  |  | 75 | [5 empty] | Cast in yard | 2026-01-29 | IPC - 26 | 3 | MPSB/MB/808 · MPSB/Sur/2797 · MPSB/MB/829
P8-KS-S18-M | P8-KS-S18-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 18 |  |  | 76 | [5 empty] | Cast in yard | 2026-02-14 | IPC - 27 | 3 | MPSB/MB/943 · MPSB/Sur/2930 · MPSB/MB/989 | Y
P8-KS-S17-M | P8-KS-S17-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 17 |  |  | 77 | [5 empty] | Cast in yard | 2026-02-07 | IPC - 27 | 3 | MPSB/MB/912 · MPSB/Sur/2882 · MPSB/MB/932
P8-KS-S16-M | P8-KS-S16-M© | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 16 |  | Y | 78 | [5 empty] | Cast in yard | 2026-01-31 | IPC - 26 | 3 | MPSB/MB/854 · MPSB/Sur/2831 · MPSB/MB/874
P8-KS-S15-M | P8-KS-S15-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 15 |  |  | 79 | [5 empty] | Cast in yard | 2026-01-29 | IPC - 26 | 3 | MPSB/MB/807 · MPSB/Sur/2798 · MPSB/MB/830
P8-KS-S14-M | P8-KS-S14-M© | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 14 |  | Y | 80 | [5 empty] | Cast in yard | 2026-01-22 | IPC - 26 | 3 | MPSB/MB/769 · MPSB/Sur/2740 · MPSB/MB/775
P8-KS-S13-M | P8-KS-S13-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 13 |  |  | 81 | [5 empty] | Cast in yard | 2026-01-19 | IPC - 26 | 3 | MPSB/MB/745 · MPSB/Sur/2720 · MPSB/MB/758
P8-KS-S12-M | P8-KS-S12-M© | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 12 |  | Y | 82 | [5 empty] | Cast in yard | 2026-01-14 | IPC - 26 | 3 | MPSB/MB/705 · MPSB/Sur/2678 · MPSB/MB/721
P8-KS-S11-M | P8-KS-S11-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 11 |  |  | 83 | [5 empty] | Cast in yard | 2026-01-08 | IPC - 26 | 3 | MPSB/MB/656 · MPSB/Sur/2625 · MPSB/MB/666
P8-KS-S10-M | P8-KS-S10-M© | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 10 |  | Y | 84 | [5 empty] | Cast in yard | 2026-01-05 | IPC - 26 | 3 | MPSB/MB/619 · MPSB/Sur/2610 · MPSB/MB/631
P8-KS-S09-M | P8-KS-S09-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 9 |  |  | 85 | [5 empty] | Cast in yard | 2025-12-27 | IPC - 25 | 2 | MPSB/Sur/2516 · MPSB/MB/577
P8-KS-S08-M | P8-KS-S08-M© | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 8 |  | Y | 86 | [5 empty] | Cast in yard | 2025-12-23 | IPC - 25 | 3 | MPSB/MB/530 · MPSB/Sur/2477 · MPSB/MB/542
P8-KS-S07-M | P8-KS-S07-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 7 |  |  | 87 | [5 empty] | Cast in yard | 2026-04-18 | IPC - 30 | 3 | MPSB/MB/1569 · MPSB/Sur/3325 · MPSB/MB/1570
P8-KS-S06-M | P8-KS-S06-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 6 |  |  | 88 | [5 empty] | Cast in yard | 2026-04-16 | IPC - 30 | 3 | MPSB/MB/1525 · MPSB/Sur/3298 · MPSB/MB/1544
P8-KS-S05-M | P8-KS-S05-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 5 |  |  | 89 | [5 empty] | Cast in yard | 2026-04-12 | IPC - 30 | 3 | MPSB/MB/1473 · MPSB/Sur/3280 · MPSB/MB/1510
P8-KS-S04-M | P8-KS-S04-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 4 |  |  | 90 | [5 empty] | Cast in yard | 2026-04-06 | IPC - 30 | 3 | MPSB/MB/1421 · MPSB/Sur/3254 · MPSB/MB/1450
P8-KS-S03-M | P8-KS-S03-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 3 |  |  | 91 | [5 empty] | Cast in yard | 2026-03-31 | IPC - 29 | 3 | MPSB/MB/1388 · MPSB/Sur/3211 · MPSB/MB/1401
P8-KS-S02-M | P8-KS-S02-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 2 |  |  | 92 | [5 empty] | Cast in yard | 2026-03-26 | IPC - 29 | 3 | MPSB/MB/1345 · MPSB/Sur/3175 · MPSB/MB/1358
P8-KS-S01-M | P8-KS-S01-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P7-P8 | KS | 1 |  |  | 93 | [5 empty] | Cast in yard | 2026-03-17 | IPC - 29 | 3 | MPSB/MB/1265 · MPSB/Sur/3134 · MPSB/MB/1275
P8-BP-S01-M | P8-BP-S01-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 1 |  |  | 94 | [5 empty] | Cast in yard | 2026-04-25 | IPC - 30 | 3 | MPSB/MB/1622 · MPSB/Sur/3349 · MPSB/MB/1639
P8-BP-S02-M | P8-BP-S02-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 2 |  |  | 95 | [5 empty] | Cast in yard | 2026-04-29 | IPC - 30 | 3 | MPSB/MB/1651 · MPSB/Sur/3385 · MPSB/MB/1665
P8-BP-S03-M | P8-BP-S03-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 3 |  |  | 96 | [5 empty] | Cast in yard | 2026-05-04 | IPC - 31 | 3 | MPSB/MB/1687 · MPSB/Sur/3414 · MPSB/MB/1696
P8-BP-S04-M | P8-BP-S04-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 4 |  |  | 97 | [5 empty] | Cast in yard | 2026-05-07 | IPC - 31 | 3 | MPSB/MB/1700 · MPSB/Sur/3426 · MPSB/MB/1713
P8-BP-S05-M | P8-BP-S05-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 5 |  |  | 98 | [5 empty] | Cast in yard | 2026-05-13 | IPC - 31 | 3 | MPSB/MB/1742 · MPSB/Sur/3473 · MPSB/MB/1752
P8-BP-S06-M | P8-BP-S06-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 6 |  |  | 99 | [5 empty] | Cast in yard | 2026-05-20 | IPC - 31 | 3 | MPSB/MB/1785 · MPSB/Sur/3518 · MPSB/MB/1806
P8-BP-S07-M | P8-BP-S07-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 7 |  |  | 100 | [5 empty] | Cast in yard | 2026-05-23 | IPC - 31 | 3 | MPSB/MB/1825 · MPSB/Sur/3539 · MPSB/MB/1837
P8-BP-S08-M | P8-BP-S08-M© | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 8 |  | Y | 101 | [5 empty] | Cast in yard | 2026-02-25 | IPC - 27 | 3 | MPSB/MB/1048 · MPSB/Sur/3005 · MPSB/MB/1081
P8-BP-S09-M | P8-BP-S09-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 9 |  |  | 102 | [5 empty] | Cast in yard | 2026-02-27 | IPC - 27 | 3 | MPSB/MB/1095 · MPSB/Sur/3023 · MPSB/MB/1101
P8-BP-S10-M | P8-BP-S10-M© | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 10 |  | Y | 103 | [5 empty] | Cast in yard | 2026-03-07 | IPC - 29 | 3 | MPSB/MB/1160 · MPSB/Sur/3072 · MPSB/MB/1176
P8-BP-S11-M | P8-BP-S11-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 11 |  |  | 104 | [5 empty] | Cast in yard | 2026-03-12 | IPC - 29 | 3 | MPSB/MB/1231 · MPSB/Sur/3107 · MPSB/MB/1247
P8-BP-S12-M | P8-BP-S12-M© | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 12 |  | Y | 105 | [5 empty] | Cast in yard | 2026-03-17 | IPC - 29 | 3 | MPSB/MB/1278 · MPSB/Sur/3139 · MPSB/MB/1288
P8-BP-S13-M | P8-BP-S13-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 13 |  |  | 106 | [5 empty] | Cast in yard | 2026-03-24 | IPC - 29 | 3 | MPSB/MB/1335 · MPSB/Sur/3165 · MPSB/MB/1341
P8-BP-S14-M | P8-BP-S14-M© | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 14 |  | Y | 107 | [5 empty] | Cast in yard | 2026-03-29 | IPC - 29 | 3 | MPSB/MB/1370 · MPSB/Sur/3192 · MPSB/MB/1389
P8-BP-S15-M | P8-BP-S15-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 15 |  |  | 108 | [5 empty] | Cast in yard | 2026-03-31 | IPC - 29 | 3 | MPSB/MB/1399 · MPSB/Sur/3229 · MPSB/MB/1419
P8-BP-S16-M | P8-BP-S16-M© | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 16 |  | Y | 109 | [5 empty] | Cast in yard | 2026-04-06 | IPC - 30 | 3 | MPSB/MB/1422 · MPSB/Sur/3253 · MPSB/MB/1449
P8-BP-S17-M | P8-BP-S17-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 17 |  |  | 110 | [5 empty] | Cast in yard | 2026-04-13 | IPC - 30 | 3 | MPSB/MB/1452 · MPSB/Sur/3290 · MPSB/MB/1517
P8-BP-S18-M | P8-BP-S18-M | Precast segment | P8 | P8 | Middle pylon |  | 1 | P8-P9 | BP | 18 |  |  | 111 | [5 empty] | Cast in yard | 2026-04-17 | IPC - 30 | 3 | MPSB/MB/1532 · MPSB/Sur/3312 · MPSB/MB/1556
P9-KS-S34-O | P9-KS-S34-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 34 |  |  | 112 | [5 empty] | Cast in yard | 2026-07-21 | IPC - 34 | 3 | MPSB/MB/2161 · MPSB/Sur/3783 · MPSB/MB/2171
P9-KS-S33-O | P9-KS-S33-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 33 |  | Y | 113 | [5 empty] | Cast in yard | 2026-07-15 | IPC - 34 | 3 | MPSB/MB/2131 · MPSB/Sur/3766 · MPSB/MB/2140
P9-KS-S32-O | P9-KS-S32-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 32 |  |  | 114 | [5 empty] | Cast in yard | 2026-07-10 | IPC - 34 | 3 | MPSB/MB/2097 · MPSB/Sur/3741 · MPSB/MB/2101
P9-KS-S31-O | P9-KS-S31-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 31 |  | Y | 115 | [5 empty] | Cast in yard | 2026-06-29 | IPC - 33 | 3 | MPSB/MB/2019 · MPSB/Sur/3702 · MPSB/MB/2053
P9-KS-S30-O | P9-KS-S30-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 30 |  |  | 116 | [5 empty] | Cast in yard | 2026-06-22 | IPC - 33 | 3 | MPSB/MB/1989 · MPSB/Sur/3678 · MPSB/MB/2004
P9-KS-S29-O | P9-KS-S29-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 29 |  | Y | 117 | [5 empty] | Cast in yard | 2026-06-17 | IPC - 33 | 3 | MPSB/MB/1969 · MPSB/Sur/3661 · MPSB/MB/1984
P9-KS-S28-O | P9-KS-S28-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 28 |  |  | 118 | [5 empty] | Cast in yard | 2026-06-12 | IPC - 33 | 3 | MPSB/MB/1943 · MPSB/Sur/3645 · MPSB/MB/1961
P9-KS-S27-O | P9-KS-S27-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 27 |  | Y | 119 | [5 empty] | Cast in yard | 2026-06-05 | IPC - 33 | 3 | MPSB/MB/1908 · MPSB/Sur/3610 · MPSB/MB/1910
P9-KS-S26-O | P9-KS-S26-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 26 |  |  | 120 | [5 empty] | Cast in yard | 2026-05-26 | IPC - 31 | 3 | MPSB/MB/1836 · MPSB/Sur/3553 · MPSB/MB/1852
P9-KS-S25-O | P9-KS-S25-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 25 |  | Y | 121 | [5 empty] | Cast in yard | 2026-05-18 | IPC - 31 | 3 | MPSB/MB/1784 · MPSB/Sur/3505 · MPSB/MB/1795
P9-KS-S24-O | P9-KS-S24-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 24 |  |  | 122 | [5 empty] | Cast in yard | 2026-05-12 | IPC - 31 | 3 | MPSB/MB/1741 · MPSB/Sur/3467 · MPSB/MB/1748
P9-KS-S23-O | P9-KS-S23-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 23 |  | Y | 123 | [5 empty] | Cast in yard | 2026-05-07 | IPC - 31 | 3 | MPSB/MB/1698 · MPSB/Sur/3425 · MPSB/MB/1712
P9-KS-S22-O | P9-KS-S22-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 22 |  |  | 124 | [5 empty] | Cast in yard | 2026-04-29 | IPC - 30 | 3 | MPSB/MB/1637 · MPSB/Sur/3386 · MPSB/MB/1667
P9-KS-S21-O | P9-KS-S21-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 21 |  | Y | 125 | [5 empty] | Cast in yard | 2026-06-11 | IPC - 33 | 3 | MPSB/MB/1854 · MPSB/Sur/3638 · MPSB/MB/1957
P9-KS-S20-O | P9-KS-S20-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 20 |  |  | 126 | [5 empty] | Cast in yard | 2026-06-08 | IPC - 33 | 3 | MPSB/Sur/1842 · MPSB/Sur/3619 · MPSB/MB/1935
P9-KS-S19-O | P9-KS-S19-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 19 |  | Y | 127 | [5 empty] | Cast in yard | 2026-05-21 | IPC - 31 | 3 | MPSB/MB/1807 · MPSB/Sur/3525 · MPSB/MB/1817
P9-KS-S18-O | P9-KS-S18-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 18 |  |  | 128 | [5 empty] | Cast in yard | 2026-05-16 | IPC - 31 | 3 | MPSB/MB/1758 · MPSB/Sur/3487 · MPSB/MB/1776
P9-KS-S17-O | P9-KS-S17-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 17 |  | Y | 129 | [5 empty] | Cast in yard | 2026-05-11 | IPC - 31 | 3 | MPSB/MB/1721 · MPSB/Sur/3459 · MPSB/MB/1743
P9-KS-S16-O | P9-KS-S16-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 16 |  |  | 130 | [5 empty] | Cast in yard | 2026-05-05 | IPC - 31 | 3 | MPSB/MB/1686 · MPSB/Sur/3417 · MPSB/MB/1701
P9-KS-S15-O | P9-KS-S15-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 15 |  | Y | 131 | [5 empty] | Cast in yard | 2026-04-30 | IPC - 30 | 3 | MPSB/MB/1668 · MPSB/Sur/3401 · MPSB/MB/1680
P9-KS-S14-O | P9-KS-S14-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 14 |  |  | 132 | [5 empty] | Cast in yard | 2026-04-27 | IPC - 30 | 3 | MPSB/MB/1636 · MPSB/Sur/3365 · MPSB/MB/1652
P9-KS-S13-O | P9-KS-S13-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 13 |  | Y | 133 | [5 empty] | Cast in yard | 2026-04-24 | IPC - 30 | 3 | MPSB/MB/1619 · MPSB/Sur/3345 · MPSB/MB/1621
P9-KS-S12-O | P9-KS-S12-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 12 |  |  | 134 | [5 empty] | Cast in yard | 2026-04-21 | IPC - 30 | 3 | MPSB/MB/1605 · MPSB/Sur/3335 · MPSB/MB/1606
P9-KS-S11-O | P9-KS-S11-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 11 |  | Y | 135 | [5 empty] | Cast in yard | 2026-04-18 | IPC - 30 | 3 | MPSB/MB/1558 · MPSB/Sur/3326 · MPSB/MB/1573
P9-KS-S10-O | P9-KS-S10-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 10 |  |  | 136 | [5 empty] | Cast in yard | 2026-04-15 | IPC - 30 | 3 | MPSB/MB/1531 · MPSB/Sur/3306 · MPSB/MB/1534
P9-KS-S09-O | P9-KS-S09-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 9 |  | Y | 137 | [5 empty] | Cast in yard | 2026-04-10 | IPC - 30 | 3 | MPSB/MB/1474 · MPSB/Sur/3272 · MPSB/MB/1490
P9-KS-S08-O | P9-KS-S08-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 8 |  |  | 138 | [5 empty] | Cast in yard | 2026-03-07 | IPC - 29 | 3 | MPSB/MB/1158 · MPSB/Sur/3066 · MPSB/MB/1162
P9-KS-S07-O | P9-KS-S07-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 7 |  |  | 139 | [5 empty] | Cast in yard | 2026-02-28 | IPC - 27 | 3 | MPSB/MB/1102 · MPSB/Sur/3049 · MPSB/MB/1126
P9-KS-S06-O | P9-KS-S06-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 6 |  |  | 140 | [5 empty] | Cast in yard | 2026-02-26 | IPC - 27 | 3 | MPSB/MB/1091 · MPSB/Sur/3013 · MPSB/MB/1096
P9-KS-S05-O | P9-KS-S05-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 5 |  |  | 141 | [5 empty] | Cast in yard | 2026-02-25 | IPC - 27 | 3 | MPSB/MB/1050 · MPSB/Sur/3004 · MPSB/MB/1080
P9-KS-S04-O | P9-KS-S04-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 4 |  |  | 142 | [5 empty] | Cast in yard | 2026-02-21 | IPC - 27 | 3 | MPSB/MB/1028 · MPSB/Sur/2975 · MPSB/MB/1042
P9-KS-S03-O | P9-KS-S03-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 3 |  |  | 143 | [5 empty] | Cast in yard | 2026-02-17 | IPC - 27 | 3 | MPSB/MB/1003 · MPSB/Sur/2946 · MPSB/MB/1009
P9-KS-S02-O | P9-KS-S02-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 2 |  |  | 144 | [5 empty] | Cast in yard | 2026-02-11 | IPC - 27 | 3 | MPSB/MB/944 · MPSB/Sur/2917 · MPSB/MB/964
P9-KS-S01-O | P9-KS-S01-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P8-P9 | KS | 1 |  |  | 145 | [5 empty] | Cast in yard | 2026-02-09 | IPC - 27 | 3 | MPSB/MB/943 · MPSB/Sur/2859 · MPSB/MB/911 | Y
P9-BP-S01a-O | P9-BP-S01a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 1 | Y |  | 146 | [5 empty] | Cast in yard | 2026-06-24 | IPC - 33 | 3 | MPSB/MB/2002 · MPSB/Sur/3686 · MPSB/MB/2022
P9-BP-S02a-O | P9-BP-S02a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 2 | Y |  | 147 | [5 empty] | Cast in yard | 2026-06-28 | IPC - 33 | 3 | MPSB/MB/2035 · MPSB/Sur/3698 · MPSB/MB/2046
P9-BP-S03a-O | P9-BP-S03a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 3 | Y |  | 148 | [5 empty] | Cast in yard | 2026-06-30 | IPC - 33 | 3 | MPSB/MB/2044 · MPSB/Sur/3707 · MPSB/MB/2056
P9-BP-S04a-O | P9-BP-S04a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 4 | Y |  | 149 | [5 empty] | Cast in yard | 2026-07-09 | IPC - 34 | 3 | MPSB/MB/2084 · MPSB/Sur/3736 · MPSB/MB/2090
P9-BP-S05a-O | P9-BP-S05a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 5 | Y |  | 150 | [5 empty] | Cast in yard | 2026-07-14 | IPC - 34 | 3 | MPSB/MB/2099 · MPSB/Sur/3762 · MPSB/MB/2133
P9-BP-S06a-O | P9-BP-S06a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 6 | Y |  | 151 | [5 empty] | Cast in yard | 2026-07-20 | IPC - 34 | 3 | MPSB/MB/2150 · MPSB/Sur/3779 · MPSB/MB/2166
P9-BP-S07a-O | P9-BP-S07a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 7 | Y |  | 152 | [5 empty] | Cast in yard | 2026-07-23 | IPC - 34 | 3 | MPSB/MB/2169 · MPSB/Sur/3787 · MPSB/MB/2183
P9-BP-S08a-O | P9-BP-S08a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 8 | Y |  | 153 | [5 empty] | Cast in yard | 2026-07-28 | IPC - 34 | 3 | MPSB/MB/2201 · MPSB/Sur/3800 · MPSB/MB/2218
P9-BP-S09a-O | P9-BP-S09a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 9 | Y | Y | 154 | [5 empty] | Cast in yard | 2026-02-09 | IPC - 27 | 3 | MPSB/MB/930 · MPSB/Sur/2895 · MPSB/MB/941
P9-BP-S10a-O | P9-BP-S10a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 10 | Y |  | 155 | [5 empty] | Cast in yard | 2026-02-14 | IPC - 27 | 3 | MPSB/MB/895 · MPSB/Sur/2929 · MPSB/MB/988
P9-BP-S11a-O | P9-BP-S11a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 11 | Y | Y | 156 | [5 empty] | Cast in yard | 2026-02-17 | IPC - 27 | 3 | MPSB/MB/1002 · MPSB/Sur/2945 · MPSB/MB/1008
P9-BP-S12a-O | P9-BP-S12a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 12 | Y |  | 157 | [5 empty] | Cast in yard | 2026-02-19 | IPC - 27 | 3 | MPSB/MB/1019 · MPSB/Sur/2958 · MPSB/MB/1029
P9-BP-S13a-O | P9-BP-S13a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 13 | Y | Y | 158 | [5 empty] | Cast in yard | 2026-02-24 | IPC - 27 | 3 | MPSB/MB/1049 · MPSB/Sur/2986 · MPSB/MB/1072
P9-BP-S14a-O | P9-BP-S14a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 14 | Y |  | 159 | [5 empty] | Cast in yard | 2026-02-26 | IPC - 27 | 3 | MPSB/MB/1083 · MPSB/Sur/3012 · MPSB/MB/1092
P9-BP-S15a-O | P9-BP-S15a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 15 | Y | Y | 160 | [5 empty] | Cast in yard | 2026-02-28 | IPC - 27 | 3 | MPSB/MB/1093 · MPSB/Sur/3047 · MPSB/MB/1124
P9-BP-S16a-O | P9-BP-S16a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 16 | Y |  | 161 | [5 empty] | Cast in yard | 2026-03-08 | IPC - 29 | 3 | MPSB/MB/1177 · MPSB/Sur/3077 · MPSB/MB/1191
P9-BP-S17a-O | P9-BP-S17a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 17 | Y | Y | 162 | [5 empty] | Cast in yard | 2026-03-11 | IPC - 29 | 3 | MPSB/MB/1190 · MPSB/Sur/3100 · MPSB/MB/1232
P9-BP-S18a-O | P9-BP-S18a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 18 | Y |  | 163 | [5 empty] | Cast in yard | 2026-03-14 | IPC - 29 | 3 | MPSB/MB/1257 · MPSB/Sur/3062 · MPSB/str/4107 | Y
P9-BP-S19a-O | P9-BP-S19a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 19 | Y | Y | 164 | [5 empty] | Cast in yard | 2026-03-20 | IPC - 29 | 3 | MPSB/MB/1302 · MPSB/Sur/3153 · MPSB/MB/1311
P9-BP-S20a-O | P9-BP-S20a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 20 | Y |  | 165 | [5 empty] | Cast in yard | 2026-03-26 | IPC - 29 | 3 | MPSB/MB/1343 · MPSB/Sur/3176 · MPSB/MB/1360
P9-BP-S21a-O | P9-BP-S21a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 21 | Y | Y | 166 | [5 empty] | Cast in yard | 2026-03-31 | IPC - 29 | 3 | MPSB/MB/1387 · MPSB/Sur/3210 · MPSB/MB/1398
P9-BP-S22a-O | P9-BP-S22a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 22 | Y |  | 167 | [5 empty] | Cast in yard | 2026-04-07 | IPC - 30 | 3 | MPSB/MB/1451 · MPSB/Sur/3256 · MPSB/MB/1453
P9-BP-S23a-O | P9-BP-S23a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 23 | Y | Y | 168 | [5 empty] | Cast in yard | 2026-04-11 | IPC - 30 | 3 | MPSB/MB/1471 · MPSB/Sur/3275 · MPSB/MB/1493
P9-BP-S24a-O | P9-BP-S24a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 24 | Y |  | 169 | [5 empty] | Cast in yard | 2026-04-14 | IPC - 30 | 3 | MPSB/MB/1516 · MPSB/Sur/3297 · MPSB/MB/1524
P9-BP-S25a-O | P9-BP-S25a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 25 | Y | Y | 170 | [5 empty] | Cast in yard | 2026-04-17 | IPC - 30 | 3 | MPSB/MB/1545 · MPSB/Sur/3313 · MPSB/MB/1557
P9-BP-S26a-O | P9-BP-S26a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 26 | Y |  | 171 | [5 empty] | Cast in yard | 2026-04-20 | IPC - 30 | 3 | MPSB/MB/1578 · MPSB/Sur/3330 · MPSB/MB/1585
P9-BP-S27a-O | P9-BP-S27a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 27 | Y | Y | 172 | [5 empty] | Cast in yard | 2026-04-23 | IPC - 30 | 3 | MPSB/MB/1607 · MPSB/Sur/3343 · MPSB/MB/1618
P9-BP-S28a-O | P9-BP-S28a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 28 | Y |  | 173 | [5 empty] | Cast in yard | 2026-04-27 | IPC - 30 | 3 | MPSB/MB/1638 · MPSB/Sur/3366 · MPSB/MB/1653
P9-BP-S29a-O | P9-BP-S29a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 29 | Y | Y | 174 | [5 empty] | Cast in yard | 2026-05-04 | IPC - 31 | 3 | MPSB/MB/1681 · MPSB/Sur/3412 · MPSB/MB/1691
P9-BP-S30a-O | P9-BP-S30a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 30 | Y |  | 175 | [5 empty] | Cast in yard | 2026-05-09 | IPC - 31 | 3 | MPSB/MB/1720 · MPSB/Sur/3442 · MPSB/MB/1729
P9-BP-S31a-O | P9-BP-S31a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 31 | Y | Y | 176 | [5 empty] | Cast in yard | 2026-05-16 | IPC - 31 | 3 | MPSB/MB/1753 · MPSB/Sur/3493 · MPSB/MB/1783
P9-BP-S32a-O | P9-BP-S32a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 32 | Y |  | 177 | [5 empty] | Cast in yard | 2026-05-22 | IPC - 31 | 3 | MPSB/MB/1808 · MPSB/Sur/3531 · MPSB/MB/1824
P9-BP-S33a-O | P9-BP-S33a-O© | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 33 | Y | Y | 178 | [5 empty] | Cast in yard | 2026-05-31 | IPC - 31 | 3 | MPSB/MB/1843 · MPSB/Sur/3592 · MPSB/MB/1888
P9-BP-S34a-O | P9-BP-S34a-O | Precast segment | P9 | P9 | Outer pylon |  | 1 | P9-P10 | BP | 34 | Y |  | 179 | [5 empty] | Cast in yard | 2026-06-10 | IPC - 33 | 3 | MPSB/MB/1920 · MPSB/Sur/3626 · MPSB/MB/1942
P10-KS-S06-E | P10-KS-S06-E | Precast segment | P10 | P10 | EJ pier |  | 1 | P9-P10 | KS | 6 |  |  | 180 | [5 empty] | Cast in yard | 2026-03-31 | IPC - 29 | 3 | MPSB/MB/1400 · MPSB/Sur/3227 · MPSB/MB/1417
P10-KS-S05-E | P10-KS-S05-E | Precast segment | P10 | P10 | EJ pier |  | 1 | P9-P10 | KS | 5 |  |  | 181 | [5 empty] | Cast in yard | 2026-03-28 | IPC - 29 | 3 | MPSB/MB/1361 · MPSB/Sur/3183 · MPSB/MB/1377
P10-KS-S04-E | P10-KS-S04-E | Precast segment | P10 | P10 | EJ pier |  | 1 | P9-P10 | KS | 4 |  |  | 182 | [5 empty] | Cast in yard | 2026-03-24 | IPC - 29 | 3 | MPSB/MB/1336 · MPSB/Sur/3166 · MPSB/MB/1342
P10-KS-S03-E | P10-KS-S03-E | Precast segment | P10 | P10 | EJ pier |  | 1 | P9-P10 | KS | 3 |  |  | 183 | [5 empty] | Cast in yard | 2026-03-17 | IPC - 29 | 3 | MPSB/MB/1277 · MPSB/Sur/3140 · MPSB/MB/1289
P10-KS-S02-E | P10-KS-S02-E | Precast segment | P10 | P10 | EJ pier |  | 1 | P9-P10 | KS | 2 |  |  | 184 | [5 empty] | Cast in yard | 2026-03-12 | IPC - 29 | 3 | MPSB/MB/1230 · MPSB/Sur/3106 · MPSB/MB/1246
P10-KS-S01-E | P10-KS-S01-E | Precast segment | P10 | P10 | EJ pier |  | 1 | P9-P10 | KS | 1 |  |  | 185 | [5 empty] | Cast in yard | 2026-03-06 | IPC - 29 | 3 | MPSB/MB/1159 · MPSB/Sur/3067 · MPSB/MB/1163
P10-KS-S01a-E | P10-KS-S01a-E | Precast segment | P10 | P10 | EJ pier |  | 1 | P9-P10 | KS | 1 | Y |  | 186 | [5 empty] | Cast in yard | 2026-02-28 | IPC - 27 | 3 | MPSB/MB/1094 · MPSB/Sur/3024 · MPSB/MB/1125
P10-BP-S01a-E | P10-BP-S01a-E | Precast segment | P10 | P10 | EJ pier |  | 2 | P10-P11 | BP | 1 | Y |  | 187 | [5 empty] | Not started |  |  | 0
P10-BP-S01-E | P10-BP-S01-E | Precast segment | P10 | P10 | EJ pier |  | 2 | P10-P11 | BP | 1 |  |  | 188 | [5 empty] | Not started |  |  | 0
P10-BP-S02-E | P10-BP-S02-E | Precast segment | P10 | P10 | EJ pier |  | 2 | P10-P11 | BP | 2 |  |  | 189 | [5 empty] | Not started |  |  | 0
P10-BP-S03-E | P10-BP-S03-E | Precast segment | P10 | P10 | EJ pier |  | 2 | P10-P11 | BP | 3 |  |  | 190 | [5 empty] | Not started |  |  | 0
P10-BP-S04-E | P10-BP-S04-E | Precast segment | P10 | P10 | EJ pier |  | 2 | P10-P11 | BP | 4 |  |  | 191 | [5 empty] | Not started |  |  | 0
P10-BP-S05-E | P10-BP-S05-E | Precast segment | P10 | P10 | EJ pier |  | 2 | P10-P11 | BP | 5 |  |  | 192 | [5 empty] | Not started |  |  | 0
P10-BP-S06-E | P10-BP-S06-E | Precast segment | P10 | P10 | EJ pier |  | 2 | P10-P11 | BP | 6 |  |  | 193 | [5 empty] | Not started |  |  | 0
P11-KS-S34a-O | P11-KS-S34a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 34 | Y |  | 194 | [5 empty] | Not started |  |  | 0
P11-KS-S33a-O | P11-KS-S33a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 33 | Y | Y | 195 | [5 empty] | Not started |  |  | 0
P11-KS-S32a-O | P11-KS-S32a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 32 | Y |  | 196 | [5 empty] | Not started |  |  | 0
P11-KS-S31a-O | P11-KS-S31a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 31 | Y | Y | 197 | [5 empty] | Not started |  |  | 0
P11-KS-S30a-O | P11-KS-S30a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 30 | Y |  | 198 | [5 empty] | Not started |  |  | 0
P11-KS-S29a-O | P11-KS-S29a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 29 | Y | Y | 199 | [5 empty] | Not started |  |  | 0
P11-KS-S28a-O | P11-KS-S28a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 28 | Y |  | 200 | [5 empty] | Not started |  |  | 0
P11-KS-S27a-O | P11-KS-S27a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 27 | Y | Y | 201 | [5 empty] | Not started |  |  | 0
P11-KS-S26a-O | P11-KS-S26a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 26 | Y |  | 202 | [5 empty] | Not started |  |  | 0
P11-KS-S25a-O | P11-KS-S25a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 25 | Y | Y | 203 | [5 empty] | Not started |  |  | 0
P11-KS-S24a-O | P11-KS-S24a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 24 | Y |  | 204 | [5 empty] | Not started |  |  | 0
P11-KS-S23a-O | P11-KS-S23a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 23 | Y | Y | 205 | [5 empty] | Not started |  |  | 0
P11-KS-S22a-O | P11-KS-S22a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 22 | Y |  | 206 | [5 empty] | Not started |  |  | 0
P11-KS-S21a-O | P11-KS-S21a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 21 | Y | Y | 207 | [5 empty] | Not started |  |  | 0
P11-KS-S20a-O | P11-KS-S20a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 20 | Y |  | 208 | [5 empty] | Not started |  |  | 0
P11-KS-S19a-O | P11-KS-S19a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 19 | Y | Y | 209 | [5 empty] | Not started |  |  | 0
P11-KS-S18a-O | P11-KS-S18a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 18 | Y |  | 210 | [5 empty] | Not started |  |  | 0
P11-KS-S17a-O | P11-KS-S17a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 17 | Y | Y | 211 | [5 empty] | Not started |  |  | 0
P11-KS-S16a-O | P11-KS-S16a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 16 | Y |  | 212 | [5 empty] | Not started |  |  | 0
P11-KS-S15a-O | P11-KS-S15a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 15 | Y | Y | 213 | [5 empty] | Not started |  |  | 0
P11-KS-S14a-O | P11-KS-S14a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 14 | Y |  | 214 | [5 empty] | Not started |  |  | 0
P11-KS-S13a-O | P11-KS-S13a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 13 | Y | Y | 215 | [5 empty] | Not started |  |  | 0
P11-KS-S12a-O | P11-KS-S12a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 12 | Y |  | 216 | [5 empty] | Not started |  |  | 0
P11-KS-S11a-O | P11-KS-S11a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 11 | Y | Y | 217 | [5 empty] | Not started |  |  | 0
P11-KS-S10a-O | P11-KS-S10a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 10 | Y |  | 218 | [5 empty] | Not started |  |  | 0
P11-KS-S09a-O | P11-KS-S09a-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 9 | Y | Y | 219 | [5 empty] | Not started |  |  | 0
P11-KS-S08a-O | P11-KS-S08a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 8 | Y |  | 220 | [5 empty] | Not started |  |  | 0
P11-KS-S07a-O | P11-KS-S07a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 7 | Y |  | 221 | [5 empty] | Not started |  |  | 0
P11-KS-S06a-O | P11-KS-S06a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 6 | Y |  | 222 | [5 empty] | Not started |  |  | 0
P11-KS-S05a-O | P11-KS-S05a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 5 | Y |  | 223 | [5 empty] | Not started |  |  | 0
P11-KS-S04a-O | P11-KS-S04a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 4 | Y |  | 224 | [5 empty] | Not started |  |  | 0
P11-KS-S03a-O | P11-KS-S03a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 3 | Y |  | 225 | [5 empty] | Not started |  |  | 0
P11-KS-S02a-O | P11-KS-S02a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 2 | Y |  | 226 | [5 empty] | Not started |  |  | 0
P11-KS-S01a-O | P11-KS-S01a-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P10-P11 | KS | 1 | Y |  | 227 | [5 empty] | Not started |  |  | 0
P11-BP-S01-O | P11-BP-S01-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 1 |  |  | 228 | [5 empty] | Not started |  |  | 0
P11-BP-S02-O | P11-BP-S02-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 2 |  |  | 229 | [5 empty] | Not started |  |  | 0
P11-BP-S03-O | P11-BP-S03-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 3 |  |  | 230 | [5 empty] | Not started |  |  | 0
P11-BP-S04-O | P11-BP-S04-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 4 |  |  | 231 | [5 empty] | Not started |  |  | 0
P11-BP-S05-O | P11-BP-S05-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 5 |  |  | 232 | [5 empty] | Not started |  |  | 0
P11-BP-S06-O | P11-BP-S06-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 6 |  |  | 233 | [5 empty] | Not started |  |  | 0
P11-BP-S07-O | P11-BP-S07-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 7 |  |  | 234 | [5 empty] | Not started |  |  | 0
P11-BP-S08-O | P11-BP-S08-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 8 |  |  | 235 | [5 empty] | Not started |  |  | 0
P11-BP-S09-O | P11-BP-S09-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 9 |  | Y | 236 | [5 empty] | Not started |  |  | 0
P11-BP-S10-O | P11-BP-S10-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 10 |  |  | 237 | [5 empty] | Not started |  |  | 0
P11-BP-S11-O | P11-BP-S11-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 11 |  | Y | 238 | [5 empty] | Not started |  |  | 0
P11-BP-S12-O | P11-BP-S12-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 12 |  |  | 239 | [5 empty] | Not started |  |  | 0
P11-BP-S13-O | P11-BP-S13-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 13 |  | Y | 240 | [5 empty] | Not started |  |  | 0
P11-BP-S14-O | P11-BP-S14-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 14 |  |  | 241 | [5 empty] | Not started |  |  | 0
P11-BP-S15-O | P11-BP-S15-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 15 |  | Y | 242 | [5 empty] | Not started |  |  | 0
P11-BP-S16-O | P11-BP-S16-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 16 |  |  | 243 | [5 empty] | Not started |  |  | 0
P11-BP-S17-O | P11-BP-S17-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 17 |  | Y | 244 | [5 empty] | Not started |  |  | 0
P11-BP-S18-O | P11-BP-S18-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 18 |  |  | 245 | [5 empty] | Not started |  |  | 0
P11-BP-S19-O | P11-BP-S19-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 19 |  | Y | 246 | [5 empty] | Not started |  |  | 0
P11-BP-S20-O | P11-BP-S20-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 20 |  |  | 247 | [5 empty] | Not started |  |  | 0
P11-BP-S21-O | P11-BP-S21-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 21 |  | Y | 248 | [5 empty] | Not started |  |  | 0
P11-BP-S22-O | P11-BP-S22-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 22 |  |  | 249 | [5 empty] | Not started |  |  | 0
P11-BP-S23-O | P11-BP-S23-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 23 |  | Y | 250 | [5 empty] | Not started |  |  | 0
P11-BP-S24-O | P11-BP-S24-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 24 |  |  | 251 | [5 empty] | Not started |  |  | 0
P11-BP-S25-O | P11-BP-S25-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 25 |  | Y | 252 | [5 empty] | Not started |  |  | 0
P11-BP-S26-O | P11-BP-S26-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 26 |  |  | 253 | [5 empty] | Not started |  |  | 0
P11-BP-S27-O | P11-BP-S27-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 27 |  | Y | 254 | [5 empty] | Not started |  |  | 0
P11-BP-S28-O | P11-BP-S28-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 28 |  |  | 255 | [5 empty] | Not started |  |  | 0
P11-BP-S29-O | P11-BP-S29-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 29 |  | Y | 256 | [5 empty] | Not started |  |  | 0
P11-BP-S30-O | P11-BP-S30-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 30 |  |  | 257 | [5 empty] | Not started |  |  | 0
P11-BP-S31-O | P11-BP-S31-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 31 |  | Y | 258 | [5 empty] | Not started |  |  | 0
P11-BP-S32-O | P11-BP-S32-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 32 |  |  | 259 | [5 empty] | Not started |  |  | 0
P11-BP-S33-O | P11-BP-S33-O© | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 33 |  | Y | 260 | [5 empty] | Not started |  |  | 0
P11-BP-S34-O | P11-BP-S34-O | Precast segment | P11 | P11 | Outer pylon |  | 2 | P11-P12 | BP | 34 |  |  | 261 | [5 empty] | Not started |  |  | 0
P12-KS-S18-M | P12-KS-S18-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 18 |  |  | 262 | [5 empty] | Not started |  |  | 0
P12-KS-S17-M | P12-KS-S17-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 17 |  |  | 263 | [5 empty] | Not started |  |  | 0
P12-KS-S16-M | P12-KS-S16-M© | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 16 |  | Y | 264 | [5 empty] | Not started |  |  | 0
P12-KS-S15-M | P12-KS-S15-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 15 |  |  | 265 | [5 empty] | Not started |  |  | 0
P12-KS-S14-M | P12-KS-S14-M© | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 14 |  | Y | 266 | [5 empty] | Not started |  |  | 0
P12-KS-S13-M | P12-KS-S13-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 13 |  |  | 267 | [5 empty] | Not started |  |  | 0
P12-KS-S12-M | P12-KS-S12-M© | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 12 |  | Y | 268 | [5 empty] | Not started |  |  | 0
P12-KS-S11-M | P12-KS-S11-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 11 |  |  | 269 | [5 empty] | Not started |  |  | 0
P12-KS-S10-M | P12-KS-S10-M© | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 10 |  | Y | 270 | [5 empty] | Not started |  |  | 0
P12-KS-S09-M | P12-KS-S09-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 9 |  |  | 271 | [5 empty] | Not started |  |  | 0
P12-KS-S08-M | P12-KS-S08-M© | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 8 |  | Y | 272 | [5 empty] | Not started |  |  | 0
P12-KS-S07-M | P12-KS-S07-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 7 |  |  | 273 | [5 empty] | Not started |  |  | 0
P12-KS-S06-M | P12-KS-S06-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 6 |  |  | 274 | [5 empty] | Not started |  |  | 0
P12-KS-S05-M | P12-KS-S05-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 5 |  |  | 275 | [5 empty] | Not started |  |  | 0
P12-KS-S04-M | P12-KS-S04-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 4 |  |  | 276 | [5 empty] | Not started |  |  | 0
P12-KS-S03-M | P12-KS-S03-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 3 |  |  | 277 | [5 empty] | Not started |  |  | 0
P12-KS-S02-M | P12-KS-S02-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 2 |  |  | 278 | [5 empty] | Not started |  |  | 0
P12-KS-S01-M | P12-KS-S01-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P11-P12 | KS | 1 |  |  | 279 | [5 empty] | Not started |  |  | 0
P12-BP-S01-M | P12-BP-S01-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 1 |  |  | 280 | [5 empty] | Not started |  |  | 0
P12-BP-S02-M | P12-BP-S02-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 2 |  |  | 281 | [5 empty] | Not started |  |  | 0
P12-BP-S03-M | P12-BP-S03-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 3 |  |  | 282 | [5 empty] | Not started |  |  | 0
P12-BP-S04-M | P12-BP-S04-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 4 |  |  | 283 | [5 empty] | Not started |  |  | 0
P12-BP-S05-M | P12-BP-S05-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 5 |  |  | 284 | [5 empty] | Not started |  |  | 0
P12-BP-S06-M | P12-BP-S06-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 6 |  |  | 285 | [5 empty] | Not started |  |  | 0
P12-BP-S07-M | P12-BP-S07-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 7 |  |  | 286 | [5 empty] | Not started |  |  | 0
P12-BP-S08-M | P12-BP-S08-M© | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 8 |  | Y | 287 | [5 empty] | Not started |  |  | 0
P12-BP-S09-M | P12-BP-S09-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 9 |  |  | 288 | [5 empty] | Not started |  |  | 0
P12-BP-S10-M | P12-BP-S10-M© | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 10 |  | Y | 289 | [5 empty] | Not started |  |  | 0
P12-BP-S11-M | P12-BP-S11-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 11 |  |  | 290 | [5 empty] | Not started |  |  | 0
P12-BP-S12-M | P12-BP-S12-M© | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 12 |  | Y | 291 | [5 empty] | Not started |  |  | 0
P12-BP-S13-M | P12-BP-S13-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 13 |  |  | 292 | [5 empty] | Not started |  |  | 0
P12-BP-S14-M | P12-BP-S14-M© | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 14 |  | Y | 293 | [5 empty] | Not started |  |  | 0
P12-BP-S15-M | P12-BP-S15-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 15 |  |  | 294 | [5 empty] | Not started |  |  | 0
P12-BP-S16-M | P12-BP-S16-M© | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 16 |  | Y | 295 | [5 empty] | Not started |  |  | 0
P12-BP-S17-M | P12-BP-S17-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 17 |  |  | 296 | [5 empty] | Not started |  |  | 0
P12-BP-S18-M | P12-BP-S18-M | Precast segment | P12 | P12 | Middle pylon |  | 2 | P12-P13 | BP | 18 |  |  | 297 | [5 empty] | Not started |  |  | 0
P13-KS-S34-O | P13-KS-S34-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 34 |  |  | 298 | [5 empty] | Not started |  |  | 0
P13-KS-S33-O | P13-KS-S33-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 33 |  | Y | 299 | [5 empty] | Not started |  |  | 0
P13-KS-S32-O | P13-KS-S32-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 32 |  |  | 300 | [5 empty] | Not started |  |  | 0
P13-KS-S31-O | P13-KS-S31-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 31 |  | Y | 301 | [5 empty] | Not started |  |  | 0
P13-KS-S30-O | P13-KS-S30-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 30 |  |  | 302 | [5 empty] | Not started |  |  | 0
P13-KS-S29-O | P13-KS-S29-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 29 |  | Y | 303 | [5 empty] | Not started |  |  | 0
P13-KS-S28-O | P13-KS-S28-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 28 |  |  | 304 | [5 empty] | Not started |  |  | 0
P13-KS-S27-O | P13-KS-S27-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 27 |  | Y | 305 | [5 empty] | Not started |  |  | 0
P13-KS-S26-O | P13-KS-S26-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 26 |  |  | 306 | [5 empty] | Not started |  |  | 0
P13-KS-S25-O | P13-KS-S25-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 25 |  | Y | 307 | [5 empty] | Not started |  |  | 0
P13-KS-S24-O | P13-KS-S24-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 24 |  |  | 308 | [5 empty] | Not started |  |  | 0
P13-KS-S23-O | P13-KS-S23-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 23 |  | Y | 309 | [5 empty] | Not started |  |  | 0
P13-KS-S22-O | P13-KS-S22-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 22 |  |  | 310 | [5 empty] | Not started |  |  | 0
P13-KS-S21-O | P13-KS-S21-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 21 |  | Y | 311 | [5 empty] | Not started |  |  | 0
P13-KS-S20-O | P13-KS-S20-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 20 |  |  | 312 | [5 empty] | Not started |  |  | 0
P13-KS-S19-O | P13-KS-S19-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 19 |  | Y | 313 | [5 empty] | Not started |  |  | 0
P13-KS-S18-O | P13-KS-S18-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 18 |  |  | 314 | [5 empty] | Not started |  |  | 0
P13-KS-S17-O | P13-KS-S17-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 17 |  | Y | 315 | [5 empty] | Not started |  |  | 0
P13-KS-S16-O | P13-KS-S16-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 16 |  |  | 316 | [5 empty] | Not started |  |  | 0
P13-KS-S15-O | P13-KS-S15-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 15 |  | Y | 317 | [5 empty] | Not started |  |  | 0
P13-KS-S14-O | P13-KS-S14-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 14 |  |  | 318 | [5 empty] | Not started |  |  | 0
P13-KS-S13-O | P13-KS-S13-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 13 |  | Y | 319 | [5 empty] | Not started |  |  | 0
P13-KS-S12-O | P13-KS-S12-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 12 |  |  | 320 | [5 empty] | Not started |  |  | 0
P13-KS-S11-O | P13-KS-S11-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 11 |  | Y | 321 | [5 empty] | Not started |  |  | 0
P13-KS-S10-O | P13-KS-S10-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 10 |  |  | 322 | [5 empty] | Not started |  |  | 0
P13-KS-S09-O | P13-KS-S09-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 9 |  | Y | 323 | [5 empty] | Not started |  |  | 0
P13-KS-S08-O | P13-KS-S08-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 8 |  |  | 324 | [5 empty] | Not started |  |  | 0
P13-KS-S07-O | P13-KS-S07-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 7 |  |  | 325 | [5 empty] | Not started |  |  | 0
P13-KS-S06-O | P13-KS-S06-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 6 |  |  | 326 | [5 empty] | Not started |  |  | 0
P13-KS-S05-O | P13-KS-S05-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 5 |  |  | 327 | [5 empty] | Not started |  |  | 0
P13-KS-S04-O | P13-KS-S04-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 4 |  |  | 328 | [5 empty] | Not started |  |  | 0
P13-KS-S03-O | P13-KS-S03-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 3 |  |  | 329 | [5 empty] | Not started |  |  | 0
P13-KS-S02-O | P13-KS-S02-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 2 |  |  | 330 | [5 empty] | Not started |  |  | 0
P13-KS-S01-O | P13-KS-S01-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P12-P13 | KS | 1 |  |  | 331 | [5 empty] | Not started |  |  | 0
P13-BP-S01a-O | P13-BP-S01a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 1 | Y |  | 332 | [5 empty] | Not started |  |  | 0
P13-BP-S02a-O | P13-BP-S02a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 2 | Y |  | 333 | [5 empty] | Not started |  |  | 0
P13-BP-S03a-O | P13-BP-S03a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 3 | Y |  | 334 | [5 empty] | Not started |  |  | 0
P13-BP-S04a-O | P13-BP-S04a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 4 | Y |  | 335 | [5 empty] | Not started |  |  | 0
P13-BP-S05a-O | P13-BP-S05a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 5 | Y |  | 336 | [5 empty] | Not started |  |  | 0
P13-BP-S06a-O | P13-BP-S06a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 6 | Y |  | 337 | [5 empty] | Not started |  |  | 0
P13-BP-S07a-O | P13-BP-S07a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 7 | Y |  | 338 | [5 empty] | Not started |  |  | 0
P13-BP-S08a-O | P13-BP-S08a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 8 | Y |  | 339 | [5 empty] | Not started |  |  | 0
P13-BP-S09a-O | P13-BP-S09a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 9 | Y | Y | 340 | [5 empty] | Not started |  |  | 0
P13-BP-S10a-O | P13-BP-S10a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 10 | Y |  | 341 | [5 empty] | Not started |  |  | 0
P13-BP-S11a-O | P13-BP-S11a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 11 | Y | Y | 342 | [5 empty] | Not started |  |  | 0
P13-BP-S12a-O | P13-BP-S12a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 12 | Y |  | 343 | [5 empty] | Not started |  |  | 0
P13-BP-S13a-O | P13-BP-S13a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 13 | Y | Y | 344 | [5 empty] | Not started |  |  | 0
P13-BP-S14a-O | P13-BP-S14a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 14 | Y |  | 345 | [5 empty] | Not started |  |  | 0
P13-BP-S15a-O | P13-BP-S15a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 15 | Y | Y | 346 | [5 empty] | Not started |  |  | 0
P13-BP-S16a-O | P13-BP-S16a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 16 | Y |  | 347 | [5 empty] | Not started |  |  | 0
P13-BP-S17a-O | P13-BP-S17a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 17 | Y | Y | 348 | [5 empty] | Not started |  |  | 0
P13-BP-S18a-O | P13-BP-S18a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 18 | Y |  | 349 | [5 empty] | Not started |  |  | 0
P13-BP-S19a-O | P13-BP-S19a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 19 | Y | Y | 350 | [5 empty] | Not started |  |  | 0
P13-BP-S20a-O | P13-BP-S20a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 20 | Y |  | 351 | [5 empty] | Not started |  |  | 0
P13-BP-S21a-O | P13-BP-S21a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 21 | Y | Y | 352 | [5 empty] | Not started |  |  | 0
P13-BP-S22a-O | P13-BP-S22a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 22 | Y |  | 353 | [5 empty] | Not started |  |  | 0
P13-BP-S23a-O | P13-BP-S23a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 23 | Y | Y | 354 | [5 empty] | Not started |  |  | 0
P13-BP-S24a-O | P13-BP-S24a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 24 | Y |  | 355 | [5 empty] | Not started |  |  | 0
P13-BP-S25a-O | P13-BP-S25a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 25 | Y | Y | 356 | [5 empty] | Not started |  |  | 0
P13-BP-S26a-O | P13-BP-S26a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 26 | Y |  | 357 | [5 empty] | Not started |  |  | 0
P13-BP-S27a-O | P13-BP-S27a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 27 | Y | Y | 358 | [5 empty] | Not started |  |  | 0
P13-BP-S28a-O | P13-BP-S28a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 28 | Y |  | 359 | [5 empty] | Not started |  |  | 0
P13-BP-S29a-O | P13-BP-S29a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 29 | Y | Y | 360 | [5 empty] | Not started |  |  | 0
P13-BP-S30a-O | P13-BP-S30a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 30 | Y |  | 361 | [5 empty] | Not started |  |  | 0
P13-BP-S31a-O | P13-BP-S31a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 31 | Y | Y | 362 | [5 empty] | Not started |  |  | 0
P13-BP-S32a-O | P13-BP-S32a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 32 | Y |  | 363 | [5 empty] | Not started |  |  | 0
P13-BP-S33a-O | P13-BP-S33a-O© | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 33 | Y | Y | 364 | [5 empty] | Not started |  |  | 0
P13-BP-S34a-O | P13-BP-S34a-O | Precast segment | P13 | P13 | Outer pylon |  | 2 | P13-P14 | BP | 34 | Y |  | 365 | [5 empty] | Not started |  |  | 0
P14-KS-S06-E | P14-KS-S06-E | Precast segment | P14 | P14 | EJ pier |  | 2 | P13-P14 | KS | 6 |  |  | 366 | [5 empty] | Not started |  |  | 0
P14-KS-S05-E | P14-KS-S05-E | Precast segment | P14 | P14 | EJ pier |  | 2 | P13-P14 | KS | 5 |  |  | 367 | [5 empty] | Not started |  |  | 0
P14-KS-S04-E | P14-KS-S04-E | Precast segment | P14 | P14 | EJ pier |  | 2 | P13-P14 | KS | 4 |  |  | 368 | [5 empty] | Not started |  |  | 0
P14-KS-S03-E | P14-KS-S03-E | Precast segment | P14 | P14 | EJ pier |  | 2 | P13-P14 | KS | 3 |  |  | 369 | [5 empty] | Not started |  |  | 0
P14-KS-S02-E | P14-KS-S02-E | Precast segment | P14 | P14 | EJ pier |  | 2 | P13-P14 | KS | 2 |  |  | 370 | [5 empty] | Not started |  |  | 0
P14-KS-S01-E | P14-KS-S01-E | Precast segment | P14 | P14 | EJ pier |  | 2 | P13-P14 | KS | 1 |  |  | 371 | [5 empty] | Not started |  |  | 0
P14-KS-S01a-E | P14-KS-S01a-E | Precast segment | P14 | P14 | EJ pier |  | 2 | P13-P14 | KS | 1 | Y |  | 372 | [5 empty] | Not started |  |  | 0
P14-BP-S01a-E | P14-BP-S01a-E | Precast segment | P14 | P14 | EJ pier |  | 3 | P14-P15 | BP | 1 | Y |  | 373 | [5 empty] | Not started |  |  | 0
P14-BP-S01-E | P14-BP-S01-E | Precast segment | P14 | P14 | EJ pier |  | 3 | P14-P15 | BP | 1 |  |  | 374 | [5 empty] | Not started |  |  | 0
P14-BP-S02-E | P14-BP-S02-E | Precast segment | P14 | P14 | EJ pier |  | 3 | P14-P15 | BP | 2 |  |  | 375 | [5 empty] | Not started |  |  | 0
P14-BP-S03-E | P14-BP-S03-E | Precast segment | P14 | P14 | EJ pier |  | 3 | P14-P15 | BP | 3 |  |  | 376 | [5 empty] | Not started |  |  | 0
P14-BP-S04-E | P14-BP-S04-E | Precast segment | P14 | P14 | EJ pier |  | 3 | P14-P15 | BP | 4 |  |  | 377 | [5 empty] | Not started |  |  | 0
P14-BP-S05-E | P14-BP-S05-E | Precast segment | P14 | P14 | EJ pier |  | 3 | P14-P15 | BP | 5 |  |  | 378 | [5 empty] | Not started |  |  | 0
P14-BP-S06-E | P14-BP-S06-E | Precast segment | P14 | P14 | EJ pier |  | 3 | P14-P15 | BP | 6 |  |  | 379 | [5 empty] | Not started |  |  | 0
P15-KS-S34a-O | P15-KS-S34a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 34 | Y |  | 380 | [5 empty] | Not started |  |  | 0
P15-KS-S33a-O | P15-KS-S33a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 33 | Y | Y | 381 | [5 empty] | Not started |  |  | 0
P15-KS-S32a-O | P15-KS-S32a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 32 | Y |  | 382 | [5 empty] | Not started |  |  | 0
P15-KS-S31a-O | P15-KS-S31a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 31 | Y | Y | 383 | [5 empty] | Not started |  |  | 0
P15-KS-S30a-O | P15-KS-S30a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 30 | Y |  | 384 | [5 empty] | Not started |  |  | 0
P15-KS-S29a-O | P15-KS-S29a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 29 | Y | Y | 385 | [5 empty] | Not started |  |  | 0
P15-KS-S28a-O | P15-KS-S28a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 28 | Y |  | 386 | [5 empty] | Not started |  |  | 0
P15-KS-S27a-O | P15-KS-S27a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 27 | Y | Y | 387 | [5 empty] | Not started |  |  | 0
P15-KS-S26a-O | P15-KS-S26a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 26 | Y |  | 388 | [5 empty] | Not started |  |  | 0
P15-KS-S25a-O | P15-KS-S25a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 25 | Y | Y | 389 | [5 empty] | Not started |  |  | 0
P15-KS-S24a-O | P15-KS-S24a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 24 | Y |  | 390 | [5 empty] | Not started |  |  | 0
P15-KS-S23a-O | P15-KS-S23a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 23 | Y | Y | 391 | [5 empty] | Not started |  |  | 0
P15-KS-S22a-O | P15-KS-S22a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 22 | Y |  | 392 | [5 empty] | Not started |  |  | 0
P15-KS-S21a-O | P15-KS-S21a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 21 | Y | Y | 393 | [5 empty] | Not started |  |  | 0
P15-KS-S20a-O | P15-KS-S20a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 20 | Y |  | 394 | [5 empty] | Not started |  |  | 0
P15-KS-S19a-O | P15-KS-S19a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 19 | Y | Y | 395 | [5 empty] | Not started |  |  | 0
P15-KS-S18a-O | P15-KS-S18a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 18 | Y |  | 396 | [5 empty] | Not started |  |  | 0
P15-KS-S17a-O | P15-KS-S17a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 17 | Y | Y | 397 | [5 empty] | Not started |  |  | 0
P15-KS-S16a-O | P15-KS-S16a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 16 | Y |  | 398 | [5 empty] | Not started |  |  | 0
P15-KS-S15a-O | P15-KS-S15a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 15 | Y | Y | 399 | [5 empty] | Not started |  |  | 0
P15-KS-S14a-O | P15-KS-S14a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 14 | Y |  | 400 | [5 empty] | Not started |  |  | 0
P15-KS-S13a-O | P15-KS-S13a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 13 | Y | Y | 401 | [5 empty] | Not started |  |  | 0
P15-KS-S12a-O | P15-KS-S12a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 12 | Y |  | 402 | [5 empty] | Not started |  |  | 0
P15-KS-S11a-O | P15-KS-S11a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 11 | Y | Y | 403 | [5 empty] | Not started |  |  | 0
P15-KS-S10a-O | P15-KS-S10a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 10 | Y |  | 404 | [5 empty] | Cast in yard | 2026-07-31 | IPC - 34 | 3 | MPSB/MB/2230 · MPSB/Sur/3819 · MPSB/MB/2246
P15-KS-S09a-O | P15-KS-S09a-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 9 | Y | Y | 405 | [5 empty] | Cast in yard | 2026-07-30 | IPC - 34 | 3 | MPSB/MB/2223 · MPSB/Sur/3807 · MPSB/MB/2231
P15-KS-S08a-O | P15-KS-S08a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 8 | Y |  | 406 | [5 empty] | Not started |  |  | 0
P15-KS-S07a-O | P15-KS-S07a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 7 | Y |  | 407 | [5 empty] | Not started |  |  | 0
P15-KS-S06a-O | P15-KS-S06a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 6 | Y |  | 408 | [5 empty] | Not started |  |  | 0
P15-KS-S05a-O | P15-KS-S05a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 5 | Y |  | 409 | [5 empty] | Not started |  |  | 0
P15-KS-S04a-O | P15-KS-S04a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 4 | Y |  | 410 | [5 empty] | Not started |  |  | 0
P15-KS-S03a-O | P15-KS-S03a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 3 | Y |  | 411 | [5 empty] | Not started |  |  | 0
P15-KS-S02a-O | P15-KS-S02a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 2 | Y |  | 412 | [5 empty] | Not started |  |  | 0
P15-KS-S01a-O | P15-KS-S01a-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P14-P15 | KS | 1 | Y |  | 413 | [5 empty] | Not started |  |  | 0
P15-BP-S01-O | P15-BP-S01-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 1 |  |  | 414 | [5 empty] | Not started |  |  | 0
P15-BP-S02-O | P15-BP-S02-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 2 |  |  | 415 | [5 empty] | Not started |  |  | 0
P15-BP-S03-O | P15-BP-S03-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 3 |  |  | 416 | [5 empty] | Not started |  |  | 0
P15-BP-S04-O | P15-BP-S04-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 4 |  |  | 417 | [5 empty] | Not started |  |  | 0
P15-BP-S05-O | P15-BP-S05-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 5 |  |  | 418 | [5 empty] | Not started |  |  | 0
P15-BP-S06-O | P15-BP-S06-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 6 |  |  | 419 | [5 empty] | Not started |  |  | 0
P15-BP-S07-O | P15-BP-S07-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 7 |  |  | 420 | [5 empty] | Not started |  |  | 0
P15-BP-S08-O | P15-BP-S08-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 8 |  |  | 421 | [5 empty] | Not started |  |  | 0
P15-BP-S09-O | P15-BP-S09-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 9 |  | Y | 422 | [5 empty] | Not started |  |  | 0
P15-BP-S10-O | P15-BP-S10-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 10 |  |  | 423 | [5 empty] | Cast in yard | 2026-07-08 | IPC - 34 | 3 | MPSB/MB/2086 · MPSB/Sur/3731 · MPSB/MB/2087
P15-BP-S11-O | P15-BP-S11-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 11 |  | Y | 424 | [5 empty] | Cast in yard | 2026-07-13 | IPC - 34 | 3 | MPSB/MB/2098 · MPSB/Sur/3758 · MPSB/MB/2116
P15-BP-S12-O | P15-BP-S12-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 12 |  |  | 425 | [5 empty] | Cast in yard | 2026-07-18 | IPC - 34 | 2 | MPSB/MB/2148 · MPSB/MB/2156
P15-BP-S13-O | P15-BP-S13-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 13 |  | Y | 426 | [5 empty] | Cast in yard | 2026-07-23 | IPC - 34 | 3 | MPSB/MB/2170 · MPSB/Sur/3789 · MPSB/MB/2192
P15-BP-S14-O | P15-BP-S14-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 14 |  |  | 427 | [5 empty] | Cast in yard | 2026-07-27 | IPC - 34 | 3 | MPSB/MB/2181 · MPSB/Sur/3797 · MPSB/MB/2211
P15-BP-S15-O | P15-BP-S15-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 15 |  | Y | 428 | [5 empty] | Cast in yard | 2026-07-30 | IPC - 34 | 3 | MPSB/MB/2224 · MPSB/Sur/3808 · MPSB/MB/2232
P15-BP-S16-O | P15-BP-S16-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 16 |  |  | 429 | [5 empty] | Not started |  |  | 0
P15-BP-S17-O | P15-BP-S17-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 17 |  | Y | 430 | [5 empty] | Not started |  |  | 0
P15-BP-S18-O | P15-BP-S18-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 18 |  |  | 431 | [5 empty] | Not started |  |  | 0
P15-BP-S19-O | P15-BP-S19-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 19 |  | Y | 432 | [5 empty] | Not started |  |  | 0
P15-BP-S20-O | P15-BP-S20-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 20 |  |  | 433 | [5 empty] | Not started |  |  | 0
P15-BP-S21-O | P15-BP-S21-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 21 |  | Y | 434 | [5 empty] | Not started |  |  | 0
P15-BP-S22-O | P15-BP-S22-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 22 |  |  | 435 | [5 empty] | Cast in yard | 2026-07-31 | IPC - 34 | 3 | MPSB/MB/2227 · MPSB/Sur/3816 · MPSB/MB/2243
P15-BP-S23-O | P15-BP-S23-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 23 |  | Y | 436 | [5 empty] | Not started |  |  | 0
P15-BP-S24-O | P15-BP-S24-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 24 |  |  | 437 | [5 empty] | Not started |  |  | 0
P15-BP-S25-O | P15-BP-S25-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 25 |  | Y | 438 | [5 empty] | Not started |  |  | 0
P15-BP-S26-O | P15-BP-S26-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 26 |  |  | 439 | [5 empty] | Not started |  |  | 0
P15-BP-S27-O | P15-BP-S27-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 27 |  | Y | 440 | [5 empty] | Not started |  |  | 0
P15-BP-S28-O | P15-BP-S28-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 28 |  |  | 441 | [5 empty] | Not started |  |  | 0
P15-BP-S29-O | P15-BP-S29-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 29 |  | Y | 442 | [5 empty] | Not started |  |  | 0
P15-BP-S30-O | P15-BP-S30-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 30 |  |  | 443 | [5 empty] | Not started |  |  | 0
P15-BP-S31-O | P15-BP-S31-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 31 |  | Y | 444 | [5 empty] | Not started |  |  | 0
P15-BP-S32-O | P15-BP-S32-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 32 |  |  | 445 | [5 empty] | Not started |  |  | 0
P15-BP-S33-O | P15-BP-S33-O© | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 33 |  | Y | 446 | [5 empty] | Not started |  |  | 0
P15-BP-S34-O | P15-BP-S34-O | Precast segment | P15 | P15 | Outer pylon |  | 3 | P15-P16 | BP | 34 |  |  | 447 | [5 empty] | Not started |  |  | 0
P16-KS-S18-M | P16-KS-S18-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 18 |  |  | 448 | [5 empty] | Not started |  |  | 0
P16-KS-S17-M | P16-KS-S17-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 17 |  |  | 449 | [5 empty] | Not started |  |  | 0
P16-KS-S16-M | P16-KS-S16-M© | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 16 |  | Y | 450 | [5 empty] | Not started |  |  | 0
P16-KS-S15-M | P16-KS-S15-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 15 |  |  | 451 | [5 empty] | Not started |  |  | 0
P16-KS-S14-M | P16-KS-S14-M© | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 14 |  | Y | 452 | [5 empty] | Cast in yard | 2026-07-31 | IPC - 34 | 3 | MPSB/MB/2228 · MPSB/Sur/3817 · MPSB/MB/2244
P16-KS-S13-M | P16-KS-S13-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 13 |  |  | 453 | [5 empty] | Cast in yard | 2026-07-27 | IPC - 34 | 3 | MPSB/MB/2180 · MPSB/Sur/3796 · MPSB/MB/2210
P16-KS-S12-M | P16-KS-S12-M© | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 12 |  | Y | 454 | [5 empty] | Cast in yard | 2026-07-23 | IPC - 34 | 3 | MPSB/MB/2168 · MPSB/Sur/3786 · MPSB/MB/2182
P16-KS-S11-M | P16-KS-S11-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 11 |  |  | 455 | [5 empty] | Cast in yard | 2026-07-20 | IPC - 34 | 3 | MPSB/MB/2163 · MPSB/Sur/3780 · MPSB/MB/2167
P16-KS-S10-M | P16-KS-S10-M© | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 10 |  | Y | 456 | [5 empty] | Cast in yard | 2026-07-15 | IPC - 34 | 3 | MPSB/MB/2132 · MPSB/Sur/3765 · MPSB/MB/2139
P16-KS-S09-M | P16-KS-S09-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 9 |  |  | 457 | [5 empty] | Cast in yard | 2026-07-09 | IPC - 34 | 3 | MPSB/MB/2085 · MPSB/Sur/3735 · MPSB/MB/2089
P16-KS-S08-M | P16-KS-S08-M© | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 8 |  | Y | 458 | [5 empty] | Cast in yard | 2026-06-29 | IPC - 33 | 3 | MPSB/MB/2034 · MPSB/Sur/3701 · MPSB/MB/2052
P16-KS-S07-M | P16-KS-S07-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 7 |  |  | 459 | [5 empty] | Not started |  |  | 0
P16-KS-S06-M | P16-KS-S06-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 6 |  |  | 460 | [5 empty] | Not started |  |  | 0
P16-KS-S05-M | P16-KS-S05-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 5 |  |  | 461 | [5 empty] | Not started |  |  | 0
P16-KS-S04-M | P16-KS-S04-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 4 |  |  | 462 | [5 empty] | Not started |  |  | 0
P16-KS-S03-M | P16-KS-S03-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 3 |  |  | 463 | [5 empty] | Not started |  |  | 0
P16-KS-S02-M | P16-KS-S02-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 2 |  |  | 464 | [5 empty] | Not started |  |  | 0
P16-KS-S01-M | P16-KS-S01-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P15-P16 | KS | 1 |  |  | 465 | [5 empty] | Not started |  |  | 0
P16-BP-S01-M | P16-BP-S01-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 1 |  |  | 466 | [5 empty] | Not started |  |  | 0
P16-BP-S02-M | P16-BP-S02-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 2 |  |  | 467 | [5 empty] | Not started |  |  | 0
P16-BP-S03-M | P16-BP-S03-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 3 |  |  | 468 | [5 empty] | Not started |  |  | 0
P16-BP-S04-M | P16-BP-S04-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 4 |  |  | 469 | [5 empty] | Not started |  |  | 0
P16-BP-S05-M | P16-BP-S05-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 5 |  |  | 470 | [5 empty] | Not started |  |  | 0
P16-BP-S06-M | P16-BP-S06-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 6 |  |  | 471 | [5 empty] | Not started |  |  | 0
P16-BP-S07-M | P16-BP-S07-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 7 |  |  | 472 | [5 empty] | Not started |  |  | 0
P16-BP-S08-M | P16-BP-S08-M© | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 8 |  | Y | 473 | [5 empty] | Cast in yard | 2026-05-04 | IPC - 31 | 2 | MPSB/MB/1685 · MPSB/MB/1690
P16-BP-S09-M | P16-BP-S09-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 9 |  |  | 474 | [5 empty] | Cast in yard | 2026-05-07 | IPC - 31 | 3 | MPSB/MB/1709 · MPSB/Sur/3424 · MPSB/MB/1711
P16-BP-S10-M | P16-BP-S10-M© | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 10 |  | Y | 475 | [5 empty] | Cast in yard | 2026-05-13 | IPC - 31 | 3 | MPSB/MB/1744 · MPSB/Sur/3472 · MPSB/MB/1751
P16-BP-S11-M | P16-BP-S11-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 11 |  |  | 476 | [5 empty] | Cast in yard | 2026-05-20 | IPC - 31 | 3 | MPSB/MB/1768 · MPSB/Sur/3517 · MPSB/MB/1805
P16-BP-S12-M | P16-BP-S12-M© | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 12 |  | Y | 477 | [5 empty] | Cast in yard | 2026-05-25 | IPC - 31 | 3 | MPSB/MB/1835 · MPSB/Sur/3548 · MPSB/MB/1844
P16-BP-S13-M | P16-BP-S13-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 13 |  |  | 478 | [5 empty] | Cast in yard | 2026-06-16 | IPC - 33 | 3 | MPSB/MB/1967 · MPSB/Sur/3657 · MPSB/MB/1978
P16-BP-S14-M | P16-BP-S14-M© | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 14 |  | Y | 479 | [5 empty] | Cast in yard | 2026-06-22 | IPC - 33 | 3 | MPSB/MB/1998 · MPSB/Sur/3677 · MPSB/MB/2003
P16-BP-S15-M | P16-BP-S15-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 15 |  |  | 480 | [5 empty] | Cast in yard | 2026-06-26 | IPC - 33 | 3 | MPSB/MB/2024 · MPSB/Sur/3695 · MPSB/MB/2033
P16-BP-S16-M | P16-BP-S16-M© | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 16 |  | Y | 481 | [5 empty] | Cast in yard | 2026-06-30 | IPC - 33 | 3 | MPSB/MB/2047 · MPSB/Sur/3705 · MPSB/MB/2054
P16-BP-S17-M | P16-BP-S17-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 17 |  |  | 482 | [5 empty] | Cast in yard | 2026-07-11 | IPC - 34 | 3 | MPSB/MB/2100 · MPSB/Sur/3748 · MPSB/MB/2109
P16-BP-S18-M | P16-BP-S18-M | Precast segment | P16 | P16 | Middle pylon |  | 3 | P16-P17 | BP | 18 |  |  | 483 | [5 empty] | Cast in yard | 2026-07-17 | IPC - 34 | 3 | MPSB/MB/2147 · MPSB/Sur/3773 · MPSB/MB/2149
P17-KS-S34-O | P17-KS-S34-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 34 |  |  | 484 | [5 empty] | Cast in yard | 2025-12-08 | IPC - 25 | 3 | MPSB/MB/453 · MPSB/Sur/2366 · MPSB/MB/464
P17-KS-S33-O | P17-KS-S33-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 33 |  | Y | 485 | [5 empty] | Cast in yard | 2025-12-04 | IPC - 25 | 3 | MPSB/MB/434 · MPSB/Sur/2336 · MPSB/MB/435
P17-KS-S32-O | P17-KS-S32-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 32 |  |  | 486 | [5 empty] | Cast in yard | 2025-11-25 | IPC - 23 | 3 | MPSB/MB/390 · MPSB/Sur/2272 · MPSB/MB/402
P17-KS-S31-O | P17-KS-S31-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 31 |  | Y | 487 | [5 empty] | Cast in yard | 2025-11-20 | IPC - 23 | 3 | MPSB/MB/369 · MPSB/Sur/2237 · MPSB/MB/381
P17-KS-S30-O | P17-KS-S30-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 30 |  |  | 488 | [5 empty] | Cast in yard | 2025-11-10 | IPC - 23 | 3 | MPSB/MB/329 · MPSB/Sur/2169 · MPSB/MB/344
P17-KS-S29-O | P17-KS-S29-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 29 |  | Y | 489 | [5 empty] | Cast in yard | 2025-11-03 | IPC - 23 | 3 | MPSB/MB/320 · MPSB/Sur/2119 · MPSB/MB/327
P17-KS-S28-O | P17-KS-S28-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 28 |  |  | 490 | [5 empty] | Cast in yard | 2025-10-30 | IPC - 22 | 3 | MPSB/MB/301 · MPSB/Sur/2073 · MPSB/MB/307
P17-KS-S27-O | P17-KS-S27-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 27 |  | Y | 491 | [5 empty] | Cast in yard | 2025-10-27 | IPC - 22 | 3 | MPSB/MB/286 · MPSB/Sur/2057 · MPSB/MB/296
P17-KS-S26-O | P17-KS-S26-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 26 |  |  | 492 | [5 empty] | Cast in yard | 2025-10-22 | IPC - 22 | 3 | MPSB/MB/273 · MPSB/Sur/2023 · MPSB/MB/278
P17-KS-S25-O | P17-KS-S25-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 25 |  | Y | 493 | [5 empty] | Cast in yard | 2025-10-17 | IPC - 22 | 3 | MPSB/MB/259 · MPSB/Sur/1998 · MPSB/MB/266
P17-KS-S24-O | P17-KS-S24-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 24 |  |  | 494 | [5 empty] | Cast in yard | 2025-10-14 | IPC - 22 | 3 | MPSB/MB/249 · MPSB/Sur/1978 · MPSB/MB/257
P17-KS-S23-O | P17-KS-S23-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 23 |  | Y | 495 | [5 empty] | Cast in yard | 2025-10-09 | IPC - 22 | 3 | MPSB/MB/227 · MPSB/Sur/1957 · MPSB/MB/241
P17-KS-S22-O | P17-KS-S22-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 22 |  |  | 496 | [5 empty] | Cast in yard | 2025-10-06 | IPC - 22 | 3 | MPSB/MB/195 · MPSB/Sur/1927 · MPSB/MB/230
P17-KS-S21-O | P17-KS-S21-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 21 |  | Y | 497 | [5 empty] | Cast in yard | 2025-09-30 | IPC - 20 | 3 | MPSB/Str/2346 · MPSB/Sur/1896 · MPSB/MB/212
P17-KS-S20-O | P17-KS-S20-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 20 |  |  | 498 | [5 empty] | Cast in yard | 2025-09-27 | IPC - 20 | 3 | MPSB/MB/196 · MPSB/Sur/1878 · MPSB/MB/206
P17-KS-S19-O | P17-KS-S19-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 19 |  | Y | 499 | [5 empty] | Cast in yard | 2025-09-22 | IPC - 20 | 3 | MPSB/MB/185 · MPSB/Sur/1859 · MPSB/MB/188
P17-KS-S18-O | P17-KS-S18-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 18 |  |  | 500 | [5 empty] | Cast in yard | 2025-09-18 | IPC - 20 | 3 | MPSB/MB/162 · MPSB/Sur/1834 · MPSB/MB/178
P17-KS-S17-O | P17-KS-S17-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 17 |  | Y | 501 | [5 empty] | Cast in yard | 2025-09-12 | IPC - 20 | 3 | MPSB/MB/152 · MPSB/Sur/1816 · MPSB/MB/154
P17-KS-S16-O | P17-KS-S16-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 16 |  |  | 502 | [5 empty] | Cast in yard | 2025-09-08 | IPC - 20 | 3 | MPSB/MB/137 · MPSB/Sur/1794 · MPSB/MB/142
P17-KS-S15-O | P17-KS-S15-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 15 |  | Y | 503 | [5 empty] | Cast in yard | 2025-09-04 | IPC - 20 | 3 | MPSB/MB/128 · MPSB/Sur/1769 · MPSB/MB/135
P17-KS-S14-O | P17-KS-S14-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 14 |  |  | 504 | [5 empty] | Cast in yard | 2025-08-30 | IPC - 19 | 3 | MPSB/MB/114 · MPSB/Sur/1753 · MPSB/MB/123
P17-KS-S13-O | P17-KS-S13-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 13 |  | Y | 505 | [5 empty] | Cast in yard | 2025-08-27 | IPC - 19 | 3 | MPSB/MB/108 · MPSB/Sur/1736 · MPSB/MB/112
P17-KS-S12-O | P17-KS-S12-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 12 |  |  | 506 | [5 empty] | Cast in yard | 2025-08-21 | IPC - 19 | 3 | MPSB/MB/95 · MPSB/Sur/1713 · MPSB/MB/103
P17-KS-S11-O | P17-KS-S11-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 11 |  | Y | 507 | [5 empty] | Cast in yard | 2025-08-16 | IPC - 19 | 3 | MPSB/MB/86 · MPSB/Sur/1696 · MPSB/MB/90
P17-KS-S10-O | P17-KS-S10-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 10 |  |  | 508 | [5 empty] | Cast in yard | 2025-08-11 | IPC - 19 | 3 | MPSB/MB/76 · MPSB/Sur/1681 · MPSB/MB/80
P17-KS-S09-O | P17-KS-S09-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 9 |  | Y | 509 | [5 empty] | Cast in yard | 2025-08-04 | IPC - 19 | 3 | MPSB/MB/58 · MPSB/Sur/1645 · MPSB/MB/68
P17-KS-S08-O | P17-KS-S08-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 8 |  |  | 510 | [5 empty] | Not started |  |  | 0
P17-KS-S07-O | P17-KS-S07-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 7 |  |  | 511 | [5 empty] | Not started |  |  | 0
P17-KS-S06-O | P17-KS-S06-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 6 |  |  | 512 | [5 empty] | Not started |  |  | 0
P17-KS-S05-O | P17-KS-S05-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 5 |  |  | 513 | [5 empty] | Not started |  |  | 0
P17-KS-S04-O | P17-KS-S04-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 4 |  |  | 514 | [5 empty] | Not started |  |  | 0
P17-KS-S03-O | P17-KS-S03-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 3 |  |  | 515 | [5 empty] | Not started |  |  | 0
P17-KS-S02-O | P17-KS-S02-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 2 |  |  | 516 | [5 empty] | Not started |  |  | 0
P17-KS-S01-O | P17-KS-S01-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P16-P17 | KS | 1 |  |  | 517 | [5 empty] | Not started |  |  | 0
P17-BP-S01a-O | P17-BP-S01a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 1 | Y |  | 518 | [5 empty] | Not started |  |  | 0
P17-BP-S02a-O | P17-BP-S02a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 2 | Y |  | 519 | [5 empty] | Not started |  |  | 0
P17-BP-S03a-O | P17-BP-S03a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 3 | Y |  | 520 | [5 empty] | Not started |  |  | 0
P17-BP-S04a-O | P17-BP-S04a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 4 | Y |  | 521 | [5 empty] | Not started |  |  | 0
P17-BP-S05a-O | P17-BP-S05a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 5 | Y |  | 522 | [5 empty] | Not started |  |  | 0
P17-BP-S06a-O | P17-BP-S06a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 6 | Y |  | 523 | [5 empty] | Not started |  |  | 0
P17-BP-S07a-O | P17-BP-S07a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 7 | Y |  | 524 | [5 empty] | Not started |  |  | 0
P17-BP-S08a-O | P17-BP-S08a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 8 | Y |  | 525 | [5 empty] | Not started |  |  | 0
P17-BP-S09a-O | P17-BP-S09a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 9 | Y | Y | 526 | [5 empty] | Cast in yard | 2025-06-16 | IPC - 18 | 3 | MPSB/MB/19 · MPSB/Sur/1429 · MPSB/MB/20
P17-BP-S10a-O | P17-BP-S10a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 10 | Y |  | 527 | [5 empty] | Cast in yard | 2025-06-25 | IPC - 18 | 2 | MPSB/MB/22 · MPSB/MB/25
P17-BP-S11a-O | P17-BP-S11a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 11 | Y | Y | 528 | [5 empty] | Cast in yard | 2025-07-02 | IPC - 18 | 2 | MPSB/Sur/1482 · MPSB/MB/0031
P17-BP-S12a-O | P17-BP-S12a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 12 | Y |  | 529 | [5 empty] | Cast in yard | 2025-07-09 | IPC - 18 | 3 | MPSB/MB/034 · MPSB/Sur/1506 · MPSB/MB/038
P17-BP-S13a-O | P17-BP-S13a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 13 | Y | Y | 530 | [5 empty] | Cast in yard | 2025-07-15 | IPC - 18 | 3 | MPSB/MB/040 · MPSB/Sur/1527 · MPSB/MB/042
P17-BP-S14a-O | P17-BP-S14a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 14 | Y |  | 531 | [5 empty] | Cast in yard | 2025-07-21 | IPC - 18 | 3 | MPSB/MB/046 · MPSB/Sur/1558 · MPSB/MB/049
P17-BP-S15a-O | P17-BP-S15a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 15 | Y | Y | 532 | [5 empty] | Cast in yard | 2025-07-28 | IPC - 18 | 3 | MPSB/MB/054 · MPSB/Sur/1589 · MPSB/MB/057
P17-BP-S16a-O | P17-BP-S16a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 16 | Y |  | 533 | [5 empty] | Cast in yard | 2025-08-01 | IPC - 19 | 3 | MPSB/MB/60 · MPSB/Sur/1636 · MPSB/MB/65
P17-BP-S17a-O | P17-BP-S17a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 17 | Y | Y | 534 | [5 empty] | Cast in yard | 2025-08-07 | IPC - 19 | 3 | MPSB/MB/69 · MPSB/Sur/1657 · MPSB/MB/74
P17-BP-S18a-O | P17-BP-S18a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 18 | Y |  | 535 | [5 empty] | Cast in yard | 2025-08-12 | IPC - 19 | 3 | MPSB/MB/75 · MPSB/Sur/1685 · MPSB/MB/83
P17-BP-S19a-O | P17-BP-S19a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 19 | Y | Y | 536 | [5 empty] | Cast in yard | 2025-08-18 | IPC - 19 | 3 | MPSB/MB/84 · MPSB/Sur/1698 · MPSB/MB/93
P17-BP-S20a-O | P17-BP-S20a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 20 | Y |  | 537 | [5 empty] | Cast in yard | 2025-08-24 | IPC - 19 | 2 | MPSB/Sur/1727 · MPSB/MB/107
P17-BP-S21a-O | P17-BP-S21a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 21 | Y | Y | 538 | [5 empty] | Cast in yard | 2025-08-30 | IPC - 19 | 3 | MPSB/MB/119 · MPSB/Sur/1752 · MPSB/MB/122
P17-BP-S22a-O | P17-BP-S22a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 22 | Y |  | 539 | [5 empty] | Cast in yard | 2025-08-21 | IPC - 19 | 3 | MPSB/MB/92 · MPSB/Sur/1714 · MPSB/MB/104
P17-BP-S23a-O | P17-BP-S23a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 23 | Y | Y | 540 | [5 empty] | Cast in yard | 2025-08-28 | IPC - 19 | 3 | MPSB/MB/110 · MPSB/Sur/1741 · MPSB/MB/116
P17-BP-S24a-O | P17-BP-S24a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 24 | Y |  | 541 | [5 empty] | Cast in yard | 2025-09-01 | IPC - 20 | 3 | MPSB/MB/121 · MPSB/Sur/1759 · MPSB/MB/127
P17-BP-S25a-O | P17-BP-S25a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 25 | Y | Y | 542 | [5 empty] | Cast in yard | 2025-09-06 | IPC - 20 | 3 | MPSB/MB/134 · MPSB/Sur/1778 · MPSB/MB/138
P17-BP-S26a-O | P17-BP-S26a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 26 | Y |  | 543 | [5 empty] | Cast in yard | 2025-09-09 | IPC - 20 | 3 | MPSB/MB/141 · MPSB/Sur/1800 · MPSB/MB/144
P17-BP-S27a-O | P17-BP-S27a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 27 | Y | Y | 544 | [5 empty] | Cast in yard | 2025-09-13 | IPC - 20 | 3 | MPSB/MB/151 · MPSB/Sur/1818 · MPSB/MB/157
P17-BP-S28a-O | P17-BP-S28a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 28 | Y |  | 545 | [5 empty] | Cast in yard | 2025-09-18 | IPC - 20 | 3 | MPSB/MB/166 · MPSB/Sur/1833 · MPSB/MB/177
P17-BP-S29a-O | P17-BP-S29a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 29 | Y | Y | 546 | [5 empty] | Cast in yard | 2025-09-23 | IPC - 20 | 3 | MPSB/MB/182 · MPSB/Sur/1861 · MPSB/MB/192
P17-BP-S30a-O | P17-BP-S30a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 30 | Y |  | 547 | [5 empty] | Cast in yard | 2025-09-27 | IPC - 20 | 3 | MPSB/MB/200 · MPSB/Sur/1882 · MPSB/MB/207
P17-BP-S31a-O | P17-BP-S31a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 31 | Y | Y | 548 | [5 empty] | Cast in yard | 2025-09-30 | IPC - 20 | 3 | MPSB/Str/2345 · MPSB/Sur/1897 · MPSB/MB/213
P17-BP-S32a-O | P17-BP-S32a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 32 | Y |  | 549 | [5 empty] | Cast in yard | 2025-10-10 | IPC - 34 | 3 | MPSB/MB/237 · MPSB/Sur/1963 · MPSB/MB/244
P17-BP-S33a-O | P17-BP-S33a-O© | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 33 | Y | Y | 550 | [5 empty] | Cast in yard | 2025-10-18 | IPC - 22 | 3 | MPSB/MB/264 · MPSB/Sur/2011 · MPSB/MB/271
P17-BP-S34a-O | P17-BP-S34a-O | Precast segment | P17 | P17 | Outer pylon |  | 3 | P17-P18 | BP | 34 | Y |  | 551 | [5 empty] | Cast in yard | 2025-10-25 | IPC - 22 | 3 | MPSB/MB/285 · MPSB/Sur/2043 · MPSB/MB/294
P18-KS-S06-E | P18-KS-S06-E | Precast segment | P18 | P18 | EJ pier |  | 3 | P17-P18 | KS | 6 |  |  | 552 | [5 empty] | Cast in yard | 2025-11-06 | IPC - 23 | 3 | MPSB/MB/323 · MPSB/Sur/2129 · MPSB/MB/332
P18-KS-S05-E | P18-KS-S05-E | Precast segment | P18 | P18 | EJ pier |  | 3 | P17-P18 | KS | 5 |  |  | 553 | [5 empty] | Cast in yard | 2025-10-31 | IPC - 22 | 3 | MPSB/MB/305 · MPSB/Sur/2087 · MPSB/MB/319
P18-KS-S04-E | P18-KS-S04-E | Precast segment | P18 | P18 | EJ pier |  | 3 | P17-P18 | KS | 4 |  |  | 554 | [5 empty] | Cast in yard | 2025-10-28 | IPC - 22 | 3 | MPSB/MB/297 · MPSB/Sur/2064 · MPSB/MB/302
P18-KS-S03-E | P18-KS-S03-E | Precast segment | P18 | P18 | EJ pier |  | 3 | P17-P18 | KS | 3 |  |  | 555 | [5 empty] | Cast in yard | 2025-10-22 | IPC - 22 | 3 | MPSB/MB/276 · MPSB/Sur/2024 · MPSB/MB/281
P18-KS-S02-E | P18-KS-S02-E | Precast segment | P18 | P18 | EJ pier |  | 3 | P17-P18 | KS | 2 |  |  | 556 | [5 empty] | Cast in yard | 2025-10-13 | IPC - 22 | 3 | MPSB/MB/245 · MPSB/Sur/1976 · MPSB/MB/256
P18-KS-S01-E | P18-KS-S01-E | Precast segment | P18 | P18 | EJ pier |  | 3 | P17-P18 | KS | 1 |  |  | 557 | [5 empty] | Cast in yard | 2025-10-07 | IPC - 22 | 3 | MPSB/MB/220 · MPSB/Sur/1934 · MPSB/MB/233
P18-KS-S01a-E | P18-KS-S01a-E | Precast segment | P18 | P18 | EJ pier |  | 3 | P17-P18 | KS | 1 | Y |  | 558 | [5 empty] | Cast in yard | 2025-09-30 | IPC - 22 | 3 | MPSB/MB/197 · MPSB/Sur/1898 · MPSB/MB/214
P18-BP-S01a-E | P18-BP-S01a-E | Precast segment | P18 | P18 | EJ pier |  | 4 | P18-P19 | BP | 1 | Y |  | 559 | [5 empty] | Not started |  |  | 0
P18-BP-S01-E | P18-BP-S01-E | Precast segment | P18 | P18 | EJ pier |  | 4 | P18-P19 | BP | 1 |  |  | 560 | [5 empty] | Not started |  |  | 0
P18-BP-S02-E | P18-BP-S02-E | Precast segment | P18 | P18 | EJ pier |  | 4 | P18-P19 | BP | 2 |  |  | 561 | [5 empty] | Not started |  |  | 0
P18-BP-S03-E | P18-BP-S03-E | Precast segment | P18 | P18 | EJ pier |  | 4 | P18-P19 | BP | 3 |  |  | 562 | [5 empty] | Not started |  |  | 0
P18-BP-S04-E | P18-BP-S04-E | Precast segment | P18 | P18 | EJ pier |  | 4 | P18-P19 | BP | 4 |  |  | 563 | [5 empty] | Not started |  |  | 0
P18-BP-S05-E | P18-BP-S05-E | Precast segment | P18 | P18 | EJ pier |  | 4 | P18-P19 | BP | 5 |  |  | 564 | [5 empty] | Not started |  |  | 0
P18-BP-S06-E | P18-BP-S06-E | Precast segment | P18 | P18 | EJ pier |  | 4 | P18-P19 | BP | 6 |  |  | 565 | [5 empty] | Not started |  |  | 0
P19-KS-S34a-O | P19-KS-S34a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 34 | Y |  | 566 | [5 empty] | Not started |  |  | 0
P19-KS-S33a-O | P19-KS-S33a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 33 | Y | Y | 567 | [5 empty] | Not started |  |  | 0
P19-KS-S32a-O | P19-KS-S32a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 32 | Y |  | 568 | [5 empty] | Not started |  |  | 0
P19-KS-S31a-O | P19-KS-S31a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 31 | Y | Y | 569 | [5 empty] | Not started |  |  | 0
P19-KS-S30a-O | P19-KS-S30a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 30 | Y |  | 570 | [5 empty] | Not started |  |  | 0
P19-KS-S29a-O | P19-KS-S29a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 29 | Y | Y | 571 | [5 empty] | Not started |  |  | 0
P19-KS-S28a-O | P19-KS-S28a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 28 | Y |  | 572 | [5 empty] | Not started |  |  | 0
P19-KS-S27a-O | P19-KS-S27a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 27 | Y | Y | 573 | [5 empty] | Not started |  |  | 0
P19-KS-S26a-O | P19-KS-S26a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 26 | Y |  | 574 | [5 empty] | Not started |  |  | 0
P19-KS-S25a-O | P19-KS-S25a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 25 | Y | Y | 575 | [5 empty] | Not started |  |  | 0
P19-KS-S24a-O | P19-KS-S24a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 24 | Y |  | 576 | [5 empty] | Not started |  |  | 0
P19-KS-S23a-O | P19-KS-S23a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 23 | Y | Y | 577 | [5 empty] | Not started |  |  | 0
P19-KS-S22a-O | P19-KS-S22a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 22 | Y |  | 578 | [5 empty] | Not started |  |  | 0
P19-KS-S21a-O | P19-KS-S21a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 21 | Y | Y | 579 | [5 empty] | Not started |  |  | 0
P19-KS-S20a-O | P19-KS-S20a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 20 | Y |  | 580 | [5 empty] | Not started |  |  | 0
P19-KS-S19a-O | P19-KS-S19a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 19 | Y | Y | 581 | [5 empty] | Not started |  |  | 0
P19-KS-S18a-O | P19-KS-S18a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 18 | Y |  | 582 | [5 empty] | Not started |  |  | 0
P19-KS-S17a-O | P19-KS-S17a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 17 | Y | Y | 583 | [5 empty] | Not started |  |  | 0
P19-KS-S16a-O | P19-KS-S16a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 16 | Y |  | 584 | [5 empty] | Not started |  |  | 0
P19-KS-S15a-O | P19-KS-S15a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 15 | Y | Y | 585 | [5 empty] | Not started |  |  | 0
P19-KS-S14a-O | P19-KS-S14a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 14 | Y |  | 586 | [5 empty] | Not started |  |  | 0
P19-KS-S13a-O | P19-KS-S13a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 13 | Y | Y | 587 | [5 empty] | Not started |  |  | 0
P19-KS-S12a-O | P19-KS-S12a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 12 | Y |  | 588 | [5 empty] | Not started |  |  | 0
P19-KS-S11a-O | P19-KS-S11a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 11 | Y | Y | 589 | [5 empty] | Not started |  |  | 0
P19-KS-S10a-O | P19-KS-S10a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 10 | Y |  | 590 | [5 empty] | Not started |  |  | 0
P19-KS-S09a-O | P19-KS-S09a-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 9 | Y | Y | 591 | [5 empty] | Cast in yard | 2026-07-31 | IPC - 34 | 3 | MPSB/MB/2234 · MPSB/Sur/3812 · MPSB/MB/2238
P19-KS-S08a-O | P19-KS-S08a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 8 | Y |  | 592 | [5 empty] | Not started |  |  | 0
P19-KS-S07a-O | P19-KS-S07a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 7 | Y |  | 593 | [5 empty] | Not started |  |  | 0
P19-KS-S06a-O | P19-KS-S06a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 6 | Y |  | 594 | [5 empty] | Not started |  |  | 0
P19-KS-S05a-O | P19-KS-S05a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 5 | Y |  | 595 | [5 empty] | Not started |  |  | 0
P19-KS-S04a-O | P19-KS-S04a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 4 | Y |  | 596 | [5 empty] | Not started |  |  | 0
P19-KS-S03a-O | P19-KS-S03a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 3 | Y |  | 597 | [5 empty] | Not started |  |  | 0
P19-KS-S02a-O | P19-KS-S02a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 2 | Y |  | 598 | [5 empty] | Not started |  |  | 0
P19-KS-S01a-O | P19-KS-S01a-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P18-P19 | KS | 1 | Y |  | 599 | [5 empty] | Not started |  |  | 0
P19-BP-S01-O | P19-BP-S01-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 1 |  |  | 600 | [5 empty] | Not started |  |  | 0
P19-BP-S02-O | P19-BP-S02-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 2 |  |  | 601 | [5 empty] | Not started |  |  | 0
P19-BP-S03-O | P19-BP-S03-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 3 |  |  | 602 | [5 empty] | Not started |  |  | 0
P19-BP-S04-O | P19-BP-S04-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 4 |  |  | 603 | [5 empty] | Not started |  |  | 0
P19-BP-S05-O | P19-BP-S05-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 5 |  |  | 604 | [5 empty] | Not started |  |  | 0
P19-BP-S06-O | P19-BP-S06-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 6 |  |  | 605 | [5 empty] | Not started |  |  | 0
P19-BP-S07-O | P19-BP-S07-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 7 |  |  | 606 | [5 empty] | Not started |  |  | 0
P19-BP-S08-O | P19-BP-S08-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 8 |  |  | 607 | [5 empty] | Not started |  |  | 0
P19-BP-S09-O | P19-BP-S09-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 9 |  | Y | 608 | [5 empty] | Not started |  |  | 0
P19-BP-S10-O | P19-BP-S10-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 10 |  |  | 609 | [5 empty] | Not started |  |  | 0
P19-BP-S11-O | P19-BP-S11-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 11 |  | Y | 610 | [5 empty] | Not started |  |  | 0
P19-BP-S12-O | P19-BP-S12-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 12 |  |  | 611 | [5 empty] | Not started |  |  | 0
P19-BP-S13-O | P19-BP-S13-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 13 |  | Y | 612 | [5 empty] | Not started |  |  | 0
P19-BP-S14-O | P19-BP-S14-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 14 |  |  | 613 | [5 empty] | Not started |  |  | 0
P19-BP-S15-O | P19-BP-S15-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 15 |  | Y | 614 | [5 empty] | Not started |  |  | 0
P19-BP-S16-O | P19-BP-S16-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 16 |  |  | 615 | [5 empty] | Not started |  |  | 0
P19-BP-S17-O | P19-BP-S17-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 17 |  | Y | 616 | [5 empty] | Not started |  |  | 0
P19-BP-S18-O | P19-BP-S18-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 18 |  |  | 617 | [5 empty] | Not started |  |  | 0
P19-BP-S19-O | P19-BP-S19-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 19 |  | Y | 618 | [5 empty] | Not started |  |  | 0
P19-BP-S20-O | P19-BP-S20-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 20 |  |  | 619 | [5 empty] | Not started |  |  | 0
P19-BP-S21-O | P19-BP-S21-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 21 |  | Y | 620 | [5 empty] | Not started |  |  | 0
P19-BP-S22-O | P19-BP-S22-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 22 |  |  | 621 | [5 empty] | Not started |  |  | 0
P19-BP-S23-O | P19-BP-S23-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 23 |  | Y | 622 | [5 empty] | Not started |  |  | 0
P19-BP-S24-O | P19-BP-S24-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 24 |  |  | 623 | [5 empty] | Not started |  |  | 0
P19-BP-S25-O | P19-BP-S25-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 25 |  | Y | 624 | [5 empty] | Not started |  |  | 0
P19-BP-S26-O | P19-BP-S26-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 26 |  |  | 625 | [5 empty] | Not started |  |  | 0
P19-BP-S27-O | P19-BP-S27-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 27 |  | Y | 626 | [5 empty] | Not started |  |  | 0
P19-BP-S28-O | P19-BP-S28-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 28 |  |  | 627 | [5 empty] | Not started |  |  | 0
P19-BP-S29-O | P19-BP-S29-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 29 |  | Y | 628 | [5 empty] | Not started |  |  | 0
P19-BP-S30-O | P19-BP-S30-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 30 |  |  | 629 | [5 empty] | Not started |  |  | 0
P19-BP-S31-O | P19-BP-S31-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 31 |  | Y | 630 | [5 empty] | Not started |  |  | 0
P19-BP-S32-O | P19-BP-S32-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 32 |  |  | 631 | [5 empty] | Not started |  |  | 0
P19-BP-S33-O | P19-BP-S33-O© | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 33 |  | Y | 632 | [5 empty] | Not started |  |  | 0
P19-BP-S34-O | P19-BP-S34-O | Precast segment | P19 | P19 | Outer pylon |  | 4 | P19-P20 | BP | 34 |  |  | 633 | [5 empty] | Not started |  |  | 0
P20-KS-S18-M | P20-KS-S18-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 18 |  |  | 634 | [5 empty] | Not started |  |  | 0
P20-KS-S17-M | P20-KS-S17-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 17 |  |  | 635 | [5 empty] | Not started |  |  | 0
P20-KS-S16-M | P20-KS-S16-M© | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 16 |  | Y | 636 | [5 empty] | Not started |  |  | 0
P20-KS-S15-M | P20-KS-S15-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 15 |  |  | 637 | [5 empty] | Not started |  |  | 0
P20-KS-S14-M | P20-KS-S14-M© | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 14 |  | Y | 638 | [5 empty] | Not started |  |  | 0
P20-KS-S13-M | P20-KS-S13-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 13 |  |  | 639 | [5 empty] | Not started |  |  | 0
P20-KS-S12-M | P20-KS-S12-M© | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 12 |  | Y | 640 | [5 empty] | Not started |  |  | 0
P20-KS-S11-M | P20-KS-S11-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 11 |  |  | 641 | [5 empty] | Not started |  |  | 0
P20-KS-S10-M | P20-KS-S10-M© | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 10 |  | Y | 642 | [5 empty] | Not started |  |  | 0
P20-KS-S09-M | P20-KS-S09-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 9 |  |  | 643 | [5 empty] | Not started |  |  | 0
P20-KS-S08-M | P20-KS-S08-M© | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 8 |  | Y | 644 | [5 empty] | Not started |  |  | 0
P20-KS-S07-M | P20-KS-S07-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 7 |  |  | 645 | [5 empty] | Not started |  |  | 0
P20-KS-S06-M | P20-KS-S06-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 6 |  |  | 646 | [5 empty] | Not started |  |  | 0
P20-KS-S05-M | P20-KS-S05-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 5 |  |  | 647 | [5 empty] | Not started |  |  | 0
P20-KS-S04-M | P20-KS-S04-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 4 |  |  | 648 | [5 empty] | Not started |  |  | 0
P20-KS-S03-M | P20-KS-S03-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 3 |  |  | 649 | [5 empty] | Not started |  |  | 0
P20-KS-S02-M | P20-KS-S02-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 2 |  |  | 650 | [5 empty] | Not started |  |  | 0
P20-KS-S01-M | P20-KS-S01-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P19-P20 | KS | 1 |  |  | 651 | [5 empty] | Not started |  |  | 0
P20-BP-S01-M | P20-BP-S01-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 1 |  |  | 652 | [5 empty] | Not started |  |  | 0
P20-BP-S02-M | P20-BP-S02-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 2 |  |  | 653 | [5 empty] | Not started |  |  | 0
P20-BP-S03-M | P20-BP-S03-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 3 |  |  | 654 | [5 empty] | Not started |  |  | 0
P20-BP-S04-M | P20-BP-S04-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 4 |  |  | 655 | [5 empty] | Not started |  |  | 0
P20-BP-S05-M | P20-BP-S05-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 5 |  |  | 656 | [5 empty] | Not started |  |  | 0
P20-BP-S06-M | P20-BP-S06-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 6 |  |  | 657 | [5 empty] | Not started |  |  | 0
P20-BP-S07-M | P20-BP-S07-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 7 |  |  | 658 | [5 empty] | Not started |  |  | 0
P20-BP-S08-M | P20-BP-S08-M© | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 8 |  | Y | 659 | [5 empty] | Not started |  |  | 0
P20-BP-S09-M | P20-BP-S09-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 9 |  |  | 660 | [5 empty] | Not started |  |  | 0
P20-BP-S10-M | P20-BP-S10-M© | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 10 |  | Y | 661 | [5 empty] | Not started |  |  | 0
P20-BP-S11-M | P20-BP-S11-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 11 |  |  | 662 | [5 empty] | Not started |  |  | 0
P20-BP-S12-M | P20-BP-S12-M© | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 12 |  | Y | 663 | [5 empty] | Not started |  |  | 0
P20-BP-S13-M | P20-BP-S13-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 13 |  |  | 664 | [5 empty] | Not started |  |  | 0
P20-BP-S14-M | P20-BP-S14-M© | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 14 |  | Y | 665 | [5 empty] | Not started |  |  | 0
P20-BP-S15-M | P20-BP-S15-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 15 |  |  | 666 | [5 empty] | Not started |  |  | 0
P20-BP-S16-M | P20-BP-S16-M© | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 16 |  | Y | 667 | [5 empty] | Not started |  |  | 0
P20-BP-S17-M | P20-BP-S17-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 17 |  |  | 668 | [5 empty] | Not started |  |  | 0
P20-BP-S18-M | P20-BP-S18-M | Precast segment | P20 | P20 | Middle pylon |  | 4 | P20-P21 | BP | 18 |  |  | 669 | [5 empty] | Not started |  |  | 0
P21-KS-S34-O | P21-KS-S34-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 34 |  |  | 670 | [5 empty] | Cast in yard | 2026-07-15 | IPC - 34 | 3 | MPSB/MB/2120 · MPSB/Sur/3764 · MPSB/MB/2138
P21-KS-S33-O | P21-KS-S33-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 33 |  | Y | 671 | [5 empty] | Cast in yard | 2026-07-10 | IPC - 34 | 3 | MPSB/MB/2095 · MPSB/Sur/3745 · MPSB/MB/2107
P21-KS-S32-O | P21-KS-S32-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 32 |  |  | 672 | [5 empty] | Cast in yard | 2026-06-30 | IPC - 33 | 3 | MPSB/MB/2063 · MPSB/Sur/3718 · MPSB/MB/2065
P21-KS-S31-O | P21-KS-S31-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 31 |  | Y | 673 | [5 empty] | Cast in yard | 2026-06-29 | IPC - 33 | 3 | MPSB/MB/2010 · MPSB/MB/2048 · MPSB/MB/2049
P21-KS-S30-O | P21-KS-S30-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 30 |  |  | 674 | [5 empty] | Cast in yard | 2026-06-24 | IPC - 33 | 3 | MPSB/MB/1988 · MPSB/Sur/3688 · MPSB/MB/2025
P21-KS-S29-O | P21-KS-S29-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 29 |  | Y | 675 | [5 empty] | Cast in yard | 2026-06-17 | IPC - 33 | 3 | MPSB/MB/1966 · MPSB/Sur/3659 · MPSB/MB/1983
P21-KS-S28-O | P21-KS-S28-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 28 |  |  | 676 | [5 empty] | Cast in yard | 2026-06-15 | IPC - 33 | 3 | MPSB/MB/1948 · MPSB/Sur/3656 · MPSB/MB/1972
P21-KS-S27-O | P21-KS-S27-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 27 |  | Y | 677 | [5 empty] | Cast in yard | 2026-06-10 | IPC - 33 | 3 | MPSB/MB/1933 · MPSB/Sur/3627 · MPSB/MB/1947
P21-KS-S26-O | P21-KS-S26-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 26 |  |  | 678 | [5 empty] | Cast in yard | 2026-06-06 | IPC - 33 | 3 | MPSB/MB/1919 · MPSB/Sur/3616 · MPSB/MB/1926
P21-KS-S25-O | P21-KS-S25-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 25 |  | Y | 679 | [5 empty] | Cast in yard | 2026-05-30 | IPC - 31 | 3 | MPSB/MB/1881 · MPSB/Sur/3581 · MPSB/MB/1883
P21-KS-S24-O | P21-KS-S24-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 24 |  |  | 680 | [5 empty] | Cast in yard | 2026-05-29 | IPC - 31 | 3 | MPSB/MB/1862 · MPSB/Sur/3569 · MPSB/MB/1868
P21-KS-S23-O | P21-KS-S23-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 23 |  | Y | 681 | [5 empty] | Cast in yard | 2026-05-26 | IPC - 31 | 3 | MPSB/MB/1856 · MPSB/Sur/3554 · MPSB/MB/1857
P21-KS-S22-O | P21-KS-S22-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 22 |  |  | 682 | [5 empty] | Cast in yard | 2026-05-22 | IPC - 31 | 3 | MPSB/MB/1880 · MPSB/Sur/3534 · MPSB/MB/1832 | Y
P21-KS-S21-O | P21-KS-S21-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 21 |  | Y | 683 | [5 empty] | Cast in yard | 2026-06-05 | IPC - 33 | 3 | MPSB/MB/1916 · MPSB/Sur/3611 · MPSB/MB/1917
P21-KS-S20-O | P21-KS-S20-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 20 |  |  | 684 | [5 empty] | Cast in yard | 2026-05-30 | IPC - 31 | 3 | MPSB/MB/1874 · MPSB/Sur/3579 · MPSB/MB/1880 | Y
P21-KS-S19-O | P21-KS-S19-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 19 |  | Y | 685 | [5 empty] | Cast in yard | 2026-05-27 | IPC - 31 | 3 | MPSB/MB/1827 · MPSB/Sur/3562 · MPSB/MB/1863
P21-KS-S18-O | P21-KS-S18-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 18 |  |  | 686 | [5 empty] | Cast in yard | 2026-05-19 | IPC - 31 | 3 | MPSB/MB/1787 · MPSB/Sur/3509 · MPSB/MB/1802
P21-KS-S17-O | P21-KS-S17-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 17 |  | Y | 687 | [5 empty] | Cast in yard | 2026-05-16 | IPC - 31 | 3 | MPSB/MB/1761 · MPSB/Sur/3488 · MPSB/MB/1777
P21-KS-S16-O | P21-KS-S16-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 16 |  |  | 688 | [5 empty] | Cast in yard | 2026-05-12 | IPC - 31 | 3 | MPSB/MB/1735 · MPSB/Sur/3427 · MPSB/MB/1747 | Y
P21-KS-S15-O | P21-KS-S15-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 15 |  | Y | 689 | [5 empty] | Cast in yard | 2026-05-07 | IPC - 31 | 3 | MPSB/MB/1706 · MPSB/Sur/3427 · MPSB/MB/1716 | Y
P21-KS-S14-O | P21-KS-S14-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 14 |  |  | 690 | [5 empty] | Cast in yard | 2026-04-13 | IPC - 30 | 3 | MPSB/MB/1491 · MPSB/Sur/3288 · MPSB/MB/1511
P21-KS-S13-O | P21-KS-S13-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 13 |  | Y | 691 | [5 empty] | Cast in yard | 2026-04-10 | IPC - 30 | 3 | MPSB/MB/1465 · MPSB/Sur/3268 · MPSB/MB/1487
P21-KS-S12-O | P21-KS-S12-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 12 |  |  | 692 | [5 empty] | Cast in yard | 2026-04-06 | IPC - 30 | 3 | MPSB/MB/1444 · MPSB/Sur/3248 · MPSB/MB/1445
P21-KS-S11-O | P21-KS-S11-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 11 |  | Y | 693 | [5 empty] | Cast in yard | 2026-03-31 | IPC - 29 | 3 | MPSB/MB/1413 · MPSB/Sur/3225 · MPSB/MB/1414
P21-KS-S10-O | P21-KS-S10-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 10 |  |  | 694 | [5 empty] | Cast in yard | 2026-03-31 | IPC - 29 | 3 | MPSB/MB/1382 · MPSB/Sur/3217 · MPSB/MB/1407
P21-KS-S09-O | P21-KS-S09-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 9 |  | Y | 695 | [5 empty] | Cast in yard | 2026-03-26 | IPC - 29 | 3 | MPSB/MB/1352 · MPSB/Sur/3179 · MPSB/MB/1363
P21-KS-S08-O | P21-KS-S08-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 8 |  |  | 696 | [5 empty] | Not started |  |  | 0
P21-KS-S07-O | P21-KS-S07-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 7 |  |  | 697 | [5 empty] | Not started |  |  | 0
P21-KS-S06-O | P21-KS-S06-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 6 |  |  | 698 | [5 empty] | Not started |  |  | 0
P21-KS-S05-O | P21-KS-S05-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 5 |  |  | 699 | [5 empty] | Not started |  |  | 0
P21-KS-S04-O | P21-KS-S04-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 4 |  |  | 700 | [5 empty] | Not started |  |  | 0
P21-KS-S03-O | P21-KS-S03-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 3 |  |  | 701 | [5 empty] | Not started |  |  | 0
P21-KS-S02-O | P21-KS-S02-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 2 |  |  | 702 | [5 empty] | Not started |  |  | 0
P21-KS-S01-O | P21-KS-S01-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P20-P21 | KS | 1 |  |  | 703 | [5 empty] | Not started |  |  | 0
P21-BP-S01a-O | P21-BP-S01a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 1 | Y |  | 704 | [5 empty] | Not started |  |  | 0
P21-BP-S02a-O | P21-BP-S02a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 2 | Y |  | 705 | [5 empty] | Not started |  |  | 0
P21-BP-S03a-O | P21-BP-S03a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 3 | Y |  | 706 | [5 empty] | Not started |  |  | 0
P21-BP-S04a-O | P21-BP-S04a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 4 | Y |  | 707 | [5 empty] | Not started |  |  | 0
P21-BP-S05a-O | P21-BP-S05a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 5 | Y |  | 708 | [5 empty] | Not started |  |  | 0
P21-BP-S06a-O | P21-BP-S06a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 6 | Y |  | 709 | [5 empty] | Not started |  |  | 0
P21-BP-S07a-O | P21-BP-S07a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 7 | Y |  | 710 | [5 empty] | Not started |  |  | 0
P21-BP-S08a-O | P21-BP-S08a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 8 | Y |  | 711 | [5 empty] | Not started |  |  | 0
P21-BP-S09a-O | P21-BP-S09a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 9 | Y | Y | 712 | [5 empty] | Cast in yard | 2026-04-28 | IPC - 30 | 3 | MPSB/MB/1641 · MPSB/Sur/3377 · MPSB/MB/1646
P21-BP-S10a-O | P21-BP-S10a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 10 | Y |  | 713 | [5 empty] | Cast in yard | 2026-04-30 | IPC - 30 | 3 | MPSB/MB/1673 · MPSB/Sur/3392 · MPSB/MB/1676
P21-BP-S11a-O | P21-BP-S11a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 11 | Y | Y | 714 | [5 empty] | Cast in yard | 2026-05-11 | IPC - 31 | 3 | MPSB/MB/1718 · MPSB/Sur/3457 · MPSB/MB/1737
P21-BP-S12a-O | P21-BP-S12a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 12 | Y |  | 715 | [5 empty] | Cast in yard | 2026-05-14 | IPC - 31 | 2 | MPSB/MB/1738 · MPSB/MB/1762
P21-BP-S13a-O | P21-BP-S13a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 13 | Y | Y | 716 | [5 empty] | Cast in yard | 2026-05-16 | IPC - 31 | 3 | MPSB/MB/1763 · MPSB/Sur/3489 · MPSB/MB/1778
P21-BP-S14a-O | P21-BP-S14a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 14 | Y |  | 717 | [5 empty] | Cast in yard | 2026-05-20 | IPC - 31 | 3 | MPSB/MB/1813 · MPSB/Sur/3522 · MPSB/MB/1814
P21-BP-S15a-O | P21-BP-S15a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 15 | Y | Y | 718 | [5 empty] | Cast in yard | 2026-05-22 | IPC - 31 | 3 | MPSB/MB/1821 · MPSB/Sur/3535 · MPSB/MB/1833
P21-BP-S16a-O | P21-BP-S16a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 16 | Y |  | 719 | [5 empty] | Cast in yard | 2026-05-26 | IPC - 31 | 3 | MPSB/MB/1845 · MPSB/Sur/3555 · MPSB/MB/1860
P21-BP-S17a-O | P21-BP-S17a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 17 | Y | Y | 720 | [5 empty] | Cast in yard | 2026-05-29 | IPC - 31 | 3 | MPSB/MB/1872 · MPSB/Sur/3571 · MPSB/MB/1873
P21-BP-S18a-O | P21-BP-S18a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 18 | Y |  | 721 | [5 empty] | Cast in yard | 2026-06-09 | IPC - 33 | 3 | MPSB/MB/1878 · MPSB/Sur/3578 · MPSB/MB/1941
P21-BP-S19a-O | P21-BP-S19a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 19 | Y | Y | 722 | [5 empty] | Cast in yard | 2026-06-18 | IPC - 33 | 3 | MPSB/MB/1982 · MPSB/Sur/3665 · MPSB/MB/1986
P21-BP-S20a-O | P21-BP-S20a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 20 | Y |  | 723 | [5 empty] | Cast in yard | 2026-06-30 | IPC - 33 | 3 | MPSB/MB/2051 · MPSB/Sur/3715 · MPSB/MB/2060
P21-BP-S21a-O | P21-BP-S21a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 21 | Y | Y | 724 | [5 empty] | Cast in yard | 2026-07-15 | IPC - 34 | 3 | MPSB/MB/2114 · MPSB/Sur/3763 · MPSB/MB/2137
P21-BP-S22a-O | P21-BP-S22a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 22 | Y |  | 725 | [5 empty] | Cast in yard | 2026-06-06 | IPC - 33 | 3 | MPSB/MB/1876 · MPSB/Sur/3615 · MPSB/MB/1925
P21-BP-S23a-O | P21-BP-S23a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 23 | Y | Y | 726 | [5 empty] | Cast in yard | 2026-06-13 | IPC - 33 | 3 | MPSB/MB/1952 · MPSB/Sur/3650 · MPSB/MB/1964
P21-BP-S24a-O | P21-BP-S24a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 24 | Y |  | 727 | [5 empty] | Cast in yard | 2026-06-22 | IPC - 33 | 3 | MPSB/MB/2001 · MPSB/Sur/3679 · MPSB/MB/2007
P21-BP-S25a-O | P21-BP-S25a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 25 | Y | Y | 728 | [5 empty] | Cast in yard | 2026-07-11 | IPC - 34 | 2 | MPSB/Sur/3749 · MPSB/MB/2113
P21-BP-S26a-O | P21-BP-S26a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 26 | Y |  | 729 | [5 empty] | Cast in yard | 2026-07-18 | IPC - 34 | 3 | MPSB/MB/2135 · MPSB/Sur/3777 · MPSB/MB/2159
P21-BP-S27a-O | P21-BP-S27a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 27 | Y | Y | 730 | [5 empty] | Cast in yard | 2026-07-22 | IPC - 34 | 3 | MPSB/MB/2165 · MPSB/Sur/3785 · MPSB/MB/2179
P21-BP-S28a-O | P21-BP-S28a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 28 | Y |  | 731 | [5 empty] | Cast in yard | 2026-07-25 | IPC - 34 | 3 | MPSB/MB/2189 · MPSB/Sur/3791 · MPSB/MB/2196
P21-BP-S29a-O | P21-BP-S29a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 29 | Y | Y | 732 | [5 empty] | Cast in yard | 2026-07-28 | IPC - 34 | 3 | MPSB/MB/2199 · MPSB/Sur/3799 · MPSB/MB/2214
P21-BP-S30a-O | P21-BP-S30a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 30 | Y |  | 733 | [5 empty] | Cast in yard | 2026-07-30 | IPC - 34 | 3 | MPSB/MB/2217 · MPSB/Sur/3809 · MPSB/MB/2235
P21-BP-S31a-O | P21-BP-S31a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 31 | Y | Y | 734 | [5 empty] | Cast in yard | 2026-07-31 | IPC - 34 | 3 | MPSB/MB/2236 · MPSB/Sur/3813 · MPSB/MB/2239
P21-BP-S32a-O | P21-BP-S32a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 32 | Y |  | 735 | [5 empty] | Not started |  |  | 0
P21-BP-S33a-O | P21-BP-S33a-O© | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 33 | Y | Y | 736 | [5 empty] | Not started |  |  | 0
P21-BP-S34a-O | P21-BP-S34a-O | Precast segment | P21 | P21 | Outer pylon |  | 4 | P21-P22 | BP | 34 | Y |  | 737 | [5 empty] | Not started |  |  | 0
P22-KS-S06-E | P22-KS-S06-E | Precast segment | P22 | P22 | EJ pier |  | 4 | P21-P22 | KS | 6 |  |  | 738 | [5 empty] | Not started |  |  | 0
P22-KS-S05-E | P22-KS-S05-E | Precast segment | P22 | P22 | EJ pier |  | 4 | P21-P22 | KS | 5 |  |  | 739 | [5 empty] | Not started |  |  | 0
P22-KS-S04-E | P22-KS-S04-E | Precast segment | P22 | P22 | EJ pier |  | 4 | P21-P22 | KS | 4 |  |  | 740 | [5 empty] | Not started |  |  | 0
P22-KS-S03-E | P22-KS-S03-E | Precast segment | P22 | P22 | EJ pier |  | 4 | P21-P22 | KS | 3 |  |  | 741 | [5 empty] | Not started |  |  | 0
P22-KS-S02-E | P22-KS-S02-E | Precast segment | P22 | P22 | EJ pier |  | 4 | P21-P22 | KS | 2 |  |  | 742 | [5 empty] | Not started |  |  | 0
P22-KS-S01-E | P22-KS-S01-E | Precast segment | P22 | P22 | EJ pier |  | 4 | P21-P22 | KS | 1 |  |  | 743 | [5 empty] | Not started |  |  | 0
P22-KS-S01a-E | P22-KS-S01a-E | Precast segment | P22 | P22 | EJ pier |  | 4 | P21-P22 | KS | 1 | Y |  | 744 | [5 empty] | Not started |  |  | 0
P22-BP-S01a-E | P22-BP-S01a-E | Precast segment | P22 | P22 | EJ pier |  | 5 | P22-P23 | BP | 1 | Y |  | 745 | [5 empty] | Cast in yard | 2026-06-19 | IPC - 33 | 3 | MPSB/MB/1993 · MPSB/Sur/3669 · MPSB/MB/1994
P22-BP-S01-E | P22-BP-S01-E | Precast segment | P22 | P22 | EJ pier |  | 5 | P22-P23 | BP | 1 |  |  | 746 | [5 empty] | Cast in yard | 2026-06-23 | IPC - 33 | 3 | MPSB/MB/2012 · MPSB/Sur/3683 · MPSB/MB/2013
P22-BP-S02-E | P22-BP-S02-E | Precast segment | P22 | P22 | EJ pier |  | 5 | P22-P23 | BP | 2 |  |  | 747 | [5 empty] | Cast in yard | 2026-06-26 | IPC - 33 | 3 | MPSB/MB/2026 · MPSB/Sur/3696 · MPSB/MB/2036
P22-BP-S03-E | P22-BP-S03-E | Precast segment | P22 | P22 | EJ pier |  | 5 | P22-P23 | BP | 3 |  |  | 748 | [5 empty] | Cast in yard | 2026-06-30 | IPC - 33 | 3 | MPSB/MB/2041 · MPSB/Sur/3716 · MPSB/MB/2061
P22-BP-S04-E | P22-BP-S04-E | Precast segment | P22 | P22 | EJ pier |  | 5 | P22-P23 | BP | 4 |  |  | 749 | [5 empty] | Cast in yard | 2026-07-13 | IPC - 34 | 3 | MPSB/MB/2081 · MPSB/Sur/3759 · MPSB/MB/2118
P22-BP-S05-E | P22-BP-S05-E | Precast segment | P22 | P22 | EJ pier |  | 5 | P22-P23 | BP | 5 |  |  | 750 | [5 empty] | Cast in yard | 2026-07-17 | IPC - 34 | 3 | MPSB/MB/2136 · MPSB/Sur/3775 · MPSB/MB/2154
P22-BP-S06-E | P22-BP-S06-E | Precast segment | P22 | P22 | EJ pier |  | 5 | P22-P23 | BP | 6 |  |  | 751 | [5 empty] | Cast in yard | 2026-07-22 | IPC - 34 | 3 | MPSB/MB/2153 · MPSB/Sur/3784 · MPSB/MB/2178
P23-KS-S34a-O | P23-KS-S34a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 34 | Y |  | 752 | [5 empty] | Cast in yard | 2026-03-16 | IPC - 29 | 3 | MPSB/MB/1322 · MPSB/Sur/3127 · MPSB/MB/1269
P23-KS-S33a-O | P23-KS-S33a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 33 | Y | Y | 753 | [5 empty] | Cast in yard | 2026-03-12 | IPC - 29 | 3 | MPSB/MB/1210 · MPSB/Sur/3104 · MPSB/MB/1241
P23-KS-S32a-O | P23-KS-S32a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 32 | Y |  | 754 | [5 empty] | Cast in yard | 2026-03-05 | IPC - 29 | 3 | MPSB/MB/1145 · MPSB/Sur/3061 · MPSB/MB/1147
P23-KS-S31a-O | P23-KS-S31a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 31 | Y | Y | 755 | [5 empty] | Cast in yard | 2026-02-28 | IPC - 27 | 3 | MPSB/MB/1099 · MPSB/Sur/3030 · MPSB/MB/1114
P23-KS-S30a-O | P23-KS-S30a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 30 | Y |  | 756 | [5 empty] | Cast in yard | 2026-02-27 | IPC - 27 | 3 | MPSB/MB/1066 · MPSB/Sur/3026 · MPSB/MB/1108
P23-KS-S29a-O | P23-KS-S29a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 29 | Y | Y | 757 | [5 empty] | Cast in yard | 2026-02-24 | IPC - 27 | 3 | MPSB/MB/1023 · MPSB/Sur/2985 · MPSB/MB/1064 | Y
P23-KS-S28a-O | P23-KS-S28a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 28 | Y |  | 758 | [5 empty] | Cast in yard | 2026-02-20 | IPC - 27 | 3 | MPSB/MB/1023 · MPSB/Sur/2968 · MPSB/MB/1037 | Y
P23-KS-S27a-O | P23-KS-S27a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 27 | Y | Y | 759 | [5 empty] | Cast in yard | 2026-02-17 | IPC - 27 | 3 | MPSB/MB/1013 · MPSB/Sur/2950 · MPSB/MB/1012
P23-KS-S26a-O | P23-KS-S26a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 26 | Y |  | 760 | [5 empty] | Cast in yard | 2026-02-14 | IPC - 27 | 3 | MPSB/MB/984 · MPSB/Sur/2933 · MPSB/MB/995
P23-KS-S25a-O | P23-KS-S25a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 25 | Y | Y | 761 | [5 empty] | Cast in yard | 2026-02-11 | IPC - 27 | 3 | MPSB/MB/956 · MPSB/Sur/2916 · MPSB/MB/962
P23-KS-S24a-O | P23-KS-S24a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 24 | Y |  | 762 | [5 empty] | Cast in yard | 2026-02-07 | IPC - 27 | 3 | MPSB/MB/928 · MPSB/Sur/2885 · MPSB/MB/936
P23-KS-S23a-O | P23-KS-S23a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 23 | Y | Y | 763 | [5 empty] | Cast in yard | 2026-01-31 | IPC - 26 | 3 | MPSB/MB/881 · MPSB/Sur/2838 · MPSB/MB/883
P23-KS-S22a-O | P23-KS-S22a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 22 | Y |  | 764 | [5 empty] | Cast in yard | 2026-01-28 | IPC - 26 | 3 | MPSB/MB/819 · MPSB/Sur/2786 · MPSB/MB/826
P23-KS-S21a-O | P23-KS-S21a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 21 | Y | Y | 765 | [5 empty] | Cast in yard | 2025-11-28 | IPC - 23 | 3 | MPSB/MB/414 · MPSB/Sur/2299 · MPSB/MB/417
P23-KS-S20a-O | P23-KS-S20a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 20 | Y |  | 766 | [5 empty] | Cast in yard | 2025-11-20 | IPC - 23 | 3 | MPSB/MB/374 · MPSB/Sur/2229 · MPSB/MB/377
P23-KS-S19a-O | P23-KS-S19a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 19 | Y | Y | 767 | [5 empty] | Cast in yard | 2025-11-15 | IPC - 23 | 3 | MPSB/MB/346 · MPSB/Sur/2194 · MPSB/MB/359
P23-KS-S18a-O | P23-KS-S18a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 18 | Y |  | 768 | [5 empty] | Cast in yard | 2025-11-07 | IPC - 23 | 3 | MPSB/MB/336 · MPSB/Sur/2141 · MPSB/MB/337
P23-KS-S17a-O | P23-KS-S17a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 17 | Y | Y | 769 | [5 empty] | Cast in yard | 2025-11-04 | IPC - 23 | 3 | MPSB/MB/312 · MPSB/Sur/2122 · MPSB/MB/331
P23-KS-S16a-O | P23-KS-S16a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 16 | Y |  | 770 | [5 empty] | Cast in yard | 2025-10-30 | IPC - 22 | 3 | MPSB/MB/303 · MPSB/Sur/2075 · MPSB/MB/311
P23-KS-S15a-O | P23-KS-S15a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 15 | Y | Y | 771 | [5 empty] | Cast in yard | 2025-10-27 | IPC - 22 | 3 | MPSB/MB/289 · MPSB/Sur/2055 · MPSB/MB/295
P23-KS-S14a-O | P23-KS-S14a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 14 | Y |  | 772 | [5 empty] | Cast in yard | 2025-10-22 | IPC - 22 | 3 | MPSB/MB/274 · MPSB/Sur/2018 · MPSB/MB/279
P23-KS-S13a-O | P23-KS-S13a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 13 | Y | Y | 773 | [5 empty] | Cast in yard | 2025-10-18 | IPC - 22 | 3 | MPSB/MB/269 · MPSB/Sur/2015 · MPSB/MB/272
P23-KS-S12a-O | P23-KS-S12a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 12 | Y |  | 774 | [5 empty] | Cast in yard | 2025-10-15 | IPC - 22 | 3 | MPSB/MB/252 · MPSB/Sur/1987 · MPSB/MB/260
P23-KS-S11a-O | P23-KS-S11a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 11 | Y | Y | 775 | [5 empty] | Cast in yard | 2025-10-11 | IPC - 22 | 3 | MPSB/MB/243 · MPSB/Sur/1970 · MPSB/MB/250
P23-KS-S10a-O | P23-KS-S10a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 10 | Y |  | 776 | [5 empty] | Cast in yard | 2025-10-08 | IPC - 22 | 3 | MPSB/MB/231 · MPSB/Sur/1948 · MPSB/MB/235
P23-KS-S09a-O | P23-KS-S09a-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 9 | Y | Y | 777 | [5 empty] | Cast in yard | 2025-10-03 | IPC - 22 | 3 | MPSB/MB/198 · MPSB/Sur/1915 · MPSB/MB/217
P23-KS-S08a-O | P23-KS-S08a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 8 | Y |  | 778 | [5 empty] | Cast in yard | 2026-04-07 | IPC - 30 | 3 | MPSB/MB/1443 · MPSB/Sur/3257 · MPSB/MB/1467
P23-KS-S07a-O | P23-KS-S07a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 7 | Y |  | 779 | [5 empty] | Cast in yard | 2026-03-31 | IPC - 29 | 3 | MPSB/MB/1409 · MPSB/Sur/3224 · MPSB/MB/1412
P23-KS-S06a-O | P23-KS-S06a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 6 | Y |  | 780 | [5 empty] | Cast in yard | 2026-03-31 | IPC - 29 | 3 | MPSB/MB/1402 · MPSB/Sur/3222 · MPSB/MB/1410
P23-KS-S05a-O | P23-KS-S05a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 5 | Y |  | 781 | [5 empty] | Cast in yard | 2026-03-28 | IPC - 29 | 3 | MPSB/MB/1372 · MPSB/Sur/3186 · MPSB/MB/1379
P23-KS-S04a-O | P23-KS-S04a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 4 | Y |  | 782 | [5 empty] | Cast in yard | 2026-03-24 | IPC - 29 | 3 | MPSB/MB/1338 · MPSB/Sur/3167 · MPSB/MB/1350
P23-KS-S03a-O | P23-KS-S03a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 3 | Y |  | 783 | [5 empty] | Cast in yard | 2026-03-21 | IPC - 29 | 3 | MPSB/MB/1299 · MPSB/Sur/3157 · MPSB/MB/1330
P23-KS-S02a-O | P23-KS-S02a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 2 | Y |  | 784 | [5 empty] | Cast in yard | 2026-03-16 | IPC - 29 | 3 | MPSB/MB/1262 · MPSB/Sur/3128 · MPSB/MB/1270
P23-KS-S01a-O | P23-KS-S01a-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P22-P23 | KS | 1 | Y |  | 785 | [5 empty] | Cast in yard | 2026-03-11 | IPC - 29 | 3 | MPSB/MB/1233 · MPSB/Sur/3101 · MPSB/MB/1235
P23-BP-S01-O | P23-BP-S01-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 1 |  |  | 786 | [5 empty] | Cast in yard | 2026-05-29 | IPC - 31 | 3 | MPSB/MB/1865 · MPSB/Sur/3570 · MPSB/MB/1871
P23-BP-S02-O | P23-BP-S02-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 2 |  |  | 787 | [5 empty] | Cast in yard | 2026-05-30 | IPC - 31 | 3 | MPSB/MB/1875 · MPSB/Sur/3577 · MPSB/MB/1877
P23-BP-S03-O | P23-BP-S03-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 3 |  |  | 788 | [5 empty] | Cast in yard | 2026-06-08 | IPC - 33 | 2 | MPSB/Sur/3617 · MPSB/MB/1930
P23-BP-S04-O | P23-BP-S04-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 4 |  |  | 789 | [5 empty] | Cast in yard | 2026-06-11 | IPC - 33 | 3 | MPSB/MB/1940 · MPSB/Sur/3636 · MPSB/MB/1951
P23-BP-S05-O | P23-BP-S05-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 5 |  |  | 790 | [5 empty] | Cast in yard | 2026-06-15 | IPC - 33 | 3 | MPSB/MB/1963 · MPSB/Sur/3655 · MPSB/MB/1971
P23-BP-S06-O | P23-BP-S06-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 6 |  |  | 791 | [5 empty] | Cast in yard | 2026-06-19 | IPC - 33 | 3 | MPSB/MB/1981 · MPSB/Sur/3670 · MPSB/MB/1996
P23-BP-S07-O | P23-BP-S07-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 7 |  |  | 792 | [5 empty] | Cast in yard | 2026-06-23 | IPC - 33 | 3 | MPSB/MB/2005 · MPSB/Sur/3684 · MPSB/MB/2015
P23-BP-S08-O | P23-BP-S08-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 8 |  |  | 793 | [5 empty] | Cast in yard | 2026-06-26 | IPC - 33 | 2 | MPSB/MB/2016 · MPSB/MB/2037
P23-BP-S09-O | P23-BP-S09-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 9 |  | Y | 794 | [5 empty] | Cast in yard | 2025-12-09 | IPC - 25 | 3 | MPSB/MB/461 · MPSB/Sur/2377 · MPSB/MB/472
P23-BP-S10-O | P23-BP-S10-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 10 |  |  | 795 | [5 empty] | Cast in yard | 2025-12-13 | IPC - 25 | 3 | MPSB/MB/490 · MPSB/Sur/2402 · MPSB/MB/491
P23-BP-S11-O | P23-BP-S11-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 11 |  | Y | 796 | [5 empty] | Cast in yard | 2025-12-18 | IPC - 25 | 3 | MPSB/MB/508 · MPSB/Sur/2445 · MPSB/MB/522
P23-BP-S12-O | P23-BP-S12-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 12 |  |  | 797 | [5 empty] | Cast in yard | 2025-12-21 | IPC - 25 | 3 | MPSB/MB/528 · MPSB/Sur/2458 · MPSB/MB/534
P23-BP-S13-O | P23-BP-S13-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 13 |  | Y | 798 | [5 empty] | Cast in yard | 2025-12-25 | IPC - 25 | 3 | MPSB/MB/540 · MPSB/Sur/2496 · MPSB/MB/566
P23-BP-S14-O | P23-BP-S14-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 14 |  |  | 799 | [5 empty] | Cast in yard | 2025-12-27 | IPC - 25 | 3 | MPSB/MB/569 · MPSB/Sur/2512 · MPSB/MB/575
P23-BP-S15-O | P23-BP-S15-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 15 |  | Y | 800 | [5 empty] | Cast in yard | 2026-01-08 | IPC - 26 | 3 | MPSB/MB/644 · MPSB/Sur/2626 · MPSB/MB/676
P23-BP-S16-O | P23-BP-S16-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 16 |  |  | 801 | [5 empty] | Cast in yard | 2026-01-12 | IPC - 26 | 3 | MPSB/MB/688 · MPSB/Sur/2661 · MPSB/MB/697
P23-BP-S17-O | P23-BP-S17-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 17 |  | Y | 802 | [5 empty] | Cast in yard | 2026-01-16 | IPC - 26 | 3 | MPSB/MB/728 · MPSB/Sur/2693 · MPSB/MB/742
P23-BP-S18-O | P23-BP-S18-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 18 |  |  | 803 | [5 empty] | Cast in yard | 2026-01-19 | IPC - 26 | 3 | MPSB/MB/748 · MPSB/Sur/2716 · MPSB/MB/753
P23-BP-S19-O | P23-BP-S19-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 19 |  | Y | 804 | [5 empty] | Cast in yard | 2026-01-24 | IPC - 26 | 3 | MPSB/MB/791 · MPSB/Sur/2764 · MPSB/MB/797
P23-BP-S20-O | P23-BP-S20-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 20 |  |  | 805 | [5 empty] | Cast in yard | 2026-01-31 | IPC - 26 | 3 | MPSB/MB/843 · MPSB/Sur/2820 · MPSB/MB/847
P23-BP-S21-O | P23-BP-S21-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 21 |  | Y | 806 | [5 empty] | Cast in yard | 2026-02-09 | IPC - 27 | 3 | MPSB/MB/927 · MPSB/Sur/2897 · MPSB/MB/948
P23-BP-S22-O | P23-BP-S22-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 22 |  |  | 807 | [5 empty] | Cast in yard | 2026-02-25 | IPC - 27 | 3 | MPSB/MB/1061 · MPSB/Sur/3002 · MPSB/MB/1075
P23-BP-S23-O | P23-BP-S23-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 23 |  | Y | 808 | [5 empty] | Cast in yard | 2026-02-27 | IPC - 27 | 3 | MPSB/MB/1040 · MPSB/Sur/3025 · MPSB/MB/1107
P23-BP-S24-O | P23-BP-S24-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 24 |  |  | 809 | [5 empty] | Cast in yard | 2026-02-28 | IPC - 27 | 3 | MPSB/MB/1113 · MPSB/Sur/3029 · MPSB/MB/1112
P23-BP-S25-O | P23-BP-S25-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 25 |  | Y | 810 | [5 empty] | Cast in yard | 2026-03-07 | IPC - 29 | 3 | MPSB/MB/1171 · MPSB/Sur/3073 · MPSB/MB/1183
P23-BP-S26-O | P23-BP-S26-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 26 |  |  | 811 | [5 empty] | Cast in yard | 2026-03-10 | IPC - 29 | 3 | MPSB/MB/1209 · MPSB/Sur/3088 · MPSB/MB/1211
P23-BP-S27-O | P23-BP-S27-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 27 |  | Y | 812 | [5 empty] | Cast in yard | 2026-03-14 | IPC - 29 | 3 | MPSB/MB/1240 · MPSB/Sur/3121 · MPSB/MB/1267
P23-BP-S28-O | P23-BP-S28-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 28 |  |  | 813 | [5 empty] | Cast in yard | 2026-03-17 | IPC - 29 | 3 | MPSB/MB/1268 · MPSB/Sur/3137 · MPSB/MB/1283
P23-BP-S29-O | P23-BP-S29-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 29 |  | Y | 814 | [5 empty] | Cast in yard | 2026-03-23 | IPC - 29 | 3 | MPSB/MB/1329 · MPSB/Sur/3161 · MPSB/MB/1340
P23-BP-S30-O | P23-BP-S30-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 30 |  |  | 815 | [5 empty] | Cast in yard | 2026-03-25 | IPC - 29 | 3 | MPSB/MB/1334 · MPSB/Sur/3174 · MPSB/MB/1357
P23-BP-S31-O | P23-BP-S31-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 31 |  | Y | 816 | [5 empty] | Cast in yard | 2026-03-30 | IPC - 29 | 3 | MPSB/MB/1374 · MPSB/Sur/3205 · MPSB/MB/1394
P23-BP-S32-O | P23-BP-S32-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 32 |  |  | 817 | [5 empty] | Cast in yard | 2026-03-31 | IPC - 29 | 3 | MPSB/MB/1404 · MPSB/Sur/3223 · MPSB/MB/1411
P23-BP-S33-O | P23-BP-S33-O© | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 33 |  | Y | 818 | [5 empty] | Cast in yard | 2026-04-08 | IPC - 30 | 2 | MPSB/Sur/3258 · MPSB/MB/1472
P23-BP-S34-O | P23-BP-S34-O | Precast segment | P23 | P23 | Outer pylon |  | 5 | P23-P24 | BP | 34 |  |  | 819 | [5 empty] | Cast in yard | 2026-04-11 | IPC - 30 | 3 | MPSB/MB/1488 · MPSB/Sur/3277 · MPSB/MB/1500
P24-KS-S18-M | P24-KS-S18-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 18 |  |  | 820 | [5 empty] | Cast in yard | 2025-12-25 | IPC - 25 | 3 | MPSB/MB/564 · MPSB/Sur/2497 · MPSB/MB/567
P24-KS-S17-M | P24-KS-S17-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 17 |  |  | 821 | [5 empty] | Cast in yard | 2025-12-20 | IPC - 25 | 3 | MPSB/MB/527 · MPSB/Sur/2451 · MPSB/MB/529
P24-KS-S16-M | P24-KS-S16-M© | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 16 |  | Y | 822 | [5 empty] | Cast in yard | 2025-12-16 | IPC - 25 | 3 | MPSB/MB/505 · MPSB/Sur/2420 · MPSB/MB/507
P24-KS-S15-M | P24-KS-S15-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 15 |  |  | 823 | [5 empty] | Cast in yard | 2025-12-12 | IPC - 25 | 3 | MPSB/MB/485 · MPSB/Sur/2398 · MPSB/MB/487
P24-KS-S14-M | P24-KS-S14-M© | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 14 |  | Y | 824 | [5 empty] | Cast in yard | 2025-12-09 | IPC - 25 | 3 | MPSB/MB/462 · MPSB/Sur/2376 · MPSB/MB/471
P24-KS-S13-M | P24-KS-S13-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 13 |  |  | 825 | [5 empty] | Cast in yard | 2025-12-05 | IPC - 25 | 3 | MPSB/MB/387 · MPSB/Sur/2347 · MPSB/MB/452
P24-KS-S12-M | P24-KS-S12-M© | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 12 |  | Y | 826 | [5 empty] | Cast in yard | 2025-11-29 | IPC - 23 | 3 | MPSB/MB/425 · MPSB/Sur/2305 · MPSB/MB/426
P24-KS-S11-M | P24-KS-S11-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 11 |  |  | 827 | [5 empty] | Cast in yard | 2025-11-26 | IPC - 23 | 3 | MPSB/MB/400 · MPSB/Sur/2281 · MPSB/MB/406
P24-KS-S10-M | P24-KS-S10-M© | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 10 |  | Y | 828 | [5 empty] | Cast in yard | 2025-11-22 | IPC - 23 | 3 | MPSB/MB/386 · MPSB/Sur/2248 · MPSB/MB/389
P24-KS-S09-M | P24-KS-S09-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 9 |  |  | 829 | [5 empty] | Cast in yard | 2025-11-18 | IPC - 23 | 3 | MPSB/MB/366 · MPSB/Sur/2220 · MPSB/MB/373
P24-KS-S08-M | P24-KS-S08-M© | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 8 |  | Y | 830 | [5 empty] | Cast in yard | 2025-11-13 | IPC - 23 | 3 | MPSB/MB/343 · MPSB/Sur/2182 · MPSB/MB/353
P24-KS-S07-M | P24-KS-S07-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 7 |  |  | 831 | [5 empty] | Not started |  |  | 0
P24-KS-S06-M | P24-KS-S06-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 6 |  |  | 832 | [5 empty] | Not started |  |  | 0
P24-KS-S05-M | P24-KS-S05-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 5 |  |  | 833 | [5 empty] | Not started |  |  | 0
P24-KS-S04-M | P24-KS-S04-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 4 |  |  | 834 | [5 empty] | Cast in yard | 2026-07-31 | IPC - 34 | 3 | MPSB/MB/2237 · MPSB/Sur/3815 · MPSB/MB/2241
P24-KS-S03-M | P24-KS-S03-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 3 |  |  | 835 | [5 empty] | Cast in yard | 2026-07-29 | IPC - 34 | 3 | MPSB/MB/2216 · MPSB/Sur/3802 · MPSB/MB/2225
P24-KS-S02-M | P24-KS-S02-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 2 |  |  | 836 | [5 empty] | Cast in yard | 2026-07-24 | IPC - 34 | 3 | MPSB/MB/2164 · MPSB/Sur/3790 · MPSB/MB/2195
P24-KS-S01-M | P24-KS-S01-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P23-P24 | KS | 1 |  |  | 837 | [5 empty] | Cast in yard | 2026-07-16 | IPC - 34 | 3 | MPSB/MB/2127 · MPSB/Sur/3771 · MPSB/MB/2144
P24-BP-S01-M | P24-BP-S01-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 1 |  |  | 838 | [5 empty] | Not started |  |  | 0
P24-BP-S02-M | P24-BP-S02-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 2 |  |  | 839 | [5 empty] | Not started |  |  | 0
P24-BP-S03-M | P24-BP-S03-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 3 |  |  | 840 | [5 empty] | Not started |  |  | 0
P24-BP-S04-M | P24-BP-S04-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 4 |  |  | 841 | [5 empty] | Not started |  |  | 0
P24-BP-S05-M | P24-BP-S05-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 5 |  |  | 842 | [5 empty] | Not started |  |  | 0
P24-BP-S06-M | P24-BP-S06-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 6 |  |  | 843 | [5 empty] | Not started |  |  | 0
P24-BP-S07-M | P24-BP-S07-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 7 |  |  | 844 | [5 empty] | Not started |  |  | 0
P24-BP-S08-M | P24-BP-S08-M© | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 8 |  | Y | 845 | [5 empty] | Cast in yard | 2026-03-31 | IPC - 29 | 3 | MPSB/MB/1381 · MPSB/Sur/3218 · MPSB/MB/1408
P24-BP-S09-M | P24-BP-S09-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 9 |  |  | 846 | [5 empty] | Cast in yard | 2026-04-06 | IPC - 30 | 3 | MPSB/MB/1416 · MPSB/Sur/3249 · MPSB/MB/1446
P24-BP-S10-M | P24-BP-S10-M© | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 10 |  | Y | 847 | [5 empty] | Cast in yard | 2026-04-10 | IPC - 30 | 3 | MPSB/MB/1485 · MPSB/Sur/3267 · MPSB/MB/1486
P24-BP-S11-M | P24-BP-S11-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 11 |  |  | 848 | [5 empty] | Cast in yard | 2026-04-13 | IPC - 30 | 3 | MPSB/MB/1498 · MPSB/Sur/3289 · MPSB/MB/1513
P24-BP-S12-M | P24-BP-S12-M© | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 12 |  | Y | 849 | [5 empty] | Cast in yard | 2026-04-17 | IPC - 30 | 3 | MPSB/MB/1536 · MPSB/Sur/3314 · MPSB/MB/1561
P24-BP-S13-M | P24-BP-S13-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 13 |  |  | 850 | [5 empty] | Cast in yard | 2026-04-20 | IPC - 30 | 3 | MPSB/MB/1560 · MPSB/Sur/3332 · MPSB/MB/1594
P24-BP-S14-M | P24-BP-S14-M© | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 14 |  | Y | 851 | [5 empty] | Cast in yard | 2026-04-24 | IPC - 30 | 3 | MPSB/MB/1593 · MPSB/Sur/3346 · MPSB/MB/1630
P24-BP-S15-M | P24-BP-S15-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 15 |  |  | 852 | [5 empty] | Cast in yard | 2026-04-27 | IPC - 30 | 3 | MPSB/MB/1631 · MPSB/Sur/3364 · MPSB/MB/1645
P24-BP-S16-M | P24-BP-S16-M© | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 16 |  | Y | 853 | [5 empty] | Cast in yard | 2026-04-30 | IPC - 30 | 3 | MPSB/MB/1664 · MPSB/Sur/3390 · MPSB/MB/1674
P24-BP-S17-M | P24-BP-S17-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 17 |  |  | 854 | [5 empty] | Cast in yard | 2026-04-30 | IPC - 30 | 3 | MPSB/MB/1672 · MPSB/Sur/3391 · MPSB/MB/1675
P24-BP-S18-M | P24-BP-S18-M | Precast segment | P24 | P24 | Middle pylon |  | 5 | P24-P25 | BP | 18 |  |  | 855 | [5 empty] | Cast in yard | 2026-05-09 | IPC - 31 | 3 | MPSB/MB/1727 · MPSB/Sur/3446 · MPSB/MB/1734
P25-KS-S34-O | P25-KS-S34-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 34 |  |  | 856 | [5 empty] | Cast in yard | 2026-02-13 | IPC - 27 | 3 | MPSB/MB/970 · MPSB/Sur/2925 · MPSB/MB/987
P25-KS-S33-O | P25-KS-S33-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 33 |  | Y | 857 | [5 empty] | Cast in yard | 2026-02-09 | IPC - 27 | 3 | MPSB/MB/940 · MPSB/Sur/2898 · MPSB/MB/949
P25-KS-S32-O | P25-KS-S32-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 32 |  |  | 858 | [5 empty] | Cast in yard | 2026-01-31 | IPC - 26 | 3 | MPSB/MB/842 · MPSB/Sur/2821 · MPSB/MB/848
P25-KS-S31-O | P25-KS-S31-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 31 |  | Y | 859 | [5 empty] | Cast in yard | 2026-01-23 | IPC - 26 | 3 | MPSB/MB/781 · MPSB/Sur/2749 · MPSB/MB/792
P25-KS-S30-O | P25-KS-S30-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 30 |  |  | 860 | [5 empty] | Cast in yard | 2026-01-18 | IPC - 26 | 3 | MPSB/MB/747 · MPSB/Sur/2706 · MPSB/MB/751
P25-KS-S29-O | P25-KS-S29-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 29 |  | Y | 861 | [5 empty] | Cast in yard | 2026-01-14 | IPC - 26 | 3 | MPSB/MB/696 · MPSB/Sur/2680 · MPSB/MB/729
P25-KS-S28-O | P25-KS-S28-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 28 |  |  | 862 | [5 empty] | Cast in yard | 2026-01-09 | IPC - 26 | 2 | MPSB/Sur/2644 · MPSB/MB/685
P25-KS-S27-O | P25-KS-S27-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 27 |  | Y | 863 | [5 empty] | Cast in yard | 2026-01-06 | IPC - 26 | 3 | MPSB/MB/642 · MPSB/Sur/2614 · MPSB/MB/645
P25-KS-S26-O | P25-KS-S26-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 26 |  |  | 864 | [5 empty] | Cast in yard | 2026-01-03 | IPC - 26 | 3 | MPSB/MB/610 · MPSB/Sur/2594 · MPSB/MB/618
P25-KS-S25-O | P25-KS-S25-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 25 |  | Y | 865 | [5 empty] | Cast in yard | 2025-12-30 | IPC - 25 | 3 | MPSB/MB/593 · MPSB/Sur/2551 · MPSB/MB/596
P25-KS-S24-O | P25-KS-S24-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 24 |  |  | 866 | [5 empty] | Cast in yard | 2025-12-27 | IPC - 25 | 3 | MPSB/MB/568 · MPSB/Sur/2511 · MPSB/MB/574
P25-KS-S23-O | P25-KS-S23-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 23 |  | Y | 867 | [5 empty] | Cast in yard | 2025-12-23 | IPC - 25 | 3 | MPSB/MB/539 · MPSB/Sur/2472 · MPSB/MB/541
P25-KS-S22-O | P25-KS-S22-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 22 |  |  | 868 | [5 empty] | Cast in yard | 2025-12-17 | IPC - 25 | 3 | MPSB/MB/506 · MPSB/Sur/2433 · MPSB/MB/520
P25-KS-S21-O | P25-KS-S21-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 21 |  | Y | 869 | [5 empty] | Cast in yard | 2025-09-26 | IPC - 20 | 3 | MPSB/MB/202 · MPSB/Sur/1876 · MPSB/MB/204
P25-KS-S20-O | P25-KS-S20-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 20 |  |  | 870 | [5 empty] | Cast in yard | 2025-09-19 | IPC - 20 | 3 | MPSB/MB/169 · MPSB/Sur/1838 · MPSB/MB/180
P25-KS-S19-O | P25-KS-S19-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 19 |  | Y | 871 | [5 empty] | Cast in yard | 2025-09-13 | IPC - 20 | 3 | MPSB/MB/148 · MPSB/Sur/1820 · MPSB/MB/159
P25-KS-S18-O | P25-KS-S18-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 18 |  |  | 872 | [5 empty] | Cast in yard | 2025-09-08 | IPC - 20 | 3 | MPSB/MB/133 · MPSB/Sur/1793 · MPSB/MB/140
P25-KS-S17-O | P25-KS-S17-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 17 |  | Y | 873 | [5 empty] | Cast in yard | 2025-09-01 | IPC - 20 | 3 | MPSB/MB/111 · MPSB/Sur/1758 · MPSB/MB/126
P25-KS-S16-O | P25-KS-S16-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 16 |  |  | 874 | [5 empty] | Cast in yard | 2025-08-25 | IPC - 19 | 3 | MPSB/MB/100 · MPSB/Sur/1730 · MPSB/MB/109
P25-KS-S15-O | P25-KS-S15-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 15 |  | Y | 875 | [5 empty] | Cast in yard | 2025-08-21 | IPC - 19 | 3 | MPSB/MB/96 · MPSB/Sur/1712 · MPSB/MB/101
P25-KS-S14-O | P25-KS-S14-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 14 |  |  | 876 | [5 empty] | Cast in yard | 2025-08-16 | IPC - 19 | 3 | MPSB/MB/85 · MPSB/Sur/1695 · MPSB/MB/89
P25-KS-S13-O | P25-KS-S13-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 13 |  | Y | 877 | [5 empty] | Cast in yard | 2025-08-09 | IPC - 19 | 3 | MPSB/MB/72 · MPSB/Sur/1667 · MPSB/MB/78
P25-KS-S12-O | P25-KS-S12-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 12 |  |  | 878 | [5 empty] | Cast in yard | 2025-08-04 | IPC - 19 | 3 | MPSB/MB/63 · MPSB/Sur/1644 · MPSB/MB/67
P25-KS-S11-O | P25-KS-S11-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 11 |  | Y | 879 | [5 empty] | Cast in yard | 2025-07-29 | IPC - 18 | 3 | MPSB/MB/037 · MPSB/Sur/1603 · MPSB/MB/059
P25-KS-S10-O | P25-KS-S10-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 10 |  |  | 880 | [5 empty] | Cast in yard | 2025-07-19 | IPC - 18 | 3 | MPSB/MB/044 · MPSB/Sur/1546 · MPSB/MB/047
P25-KS-S09-O | P25-KS-S09-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 9 |  | Y | 881 | [5 empty] | Cast in yard | 2025-07-10 | IPC - 18 | 3 | MPSB/MB/033 · MPSB/Sur/1508 · MPSB/MB/039
P25-KS-S08-O | P25-KS-S08-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 8 |  |  | 882 | [5 empty] | Not started |  |  | 0
P25-KS-S07-O | P25-KS-S07-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 7 |  |  | 883 | [5 empty] | Cast in yard | 2026-02-28 | IPC - 27 | 3 | MPSB/MB/1100 · MPSB/Sur/3031 · MPSB/MB/1115
P25-KS-S06-O | P25-KS-S06-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 6 |  |  | 884 | [5 empty] | Cast in yard | 2026-02-23 | IPC - 27 | 3 | MPSB/MB/1045 · MPSB/Sur/2979 · MPSB/MB/1058
P25-KS-S05-O | P25-KS-S05-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 5 |  |  | 885 | [5 empty] | Cast in yard | 2026-02-18 | IPC - 27 | 3 | MPSB/MB/1014 · MPSB/Sur/2953 · MPSB/MB/1021
P25-KS-S04-O | P25-KS-S04-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 4 |  |  | 886 | [5 empty] | Cast in yard | 2026-02-14 | IPC - 27 | 3 | MPSB/MB/983 · MPSB/Sur/2932 · MPSB/MB/994
P25-KS-S03-O | P25-KS-S03-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 3 |  |  | 887 | [5 empty] | Cast in yard | 2026-02-10 | IPC - 27 | 3 | MPSB/MB/939 · MPSB/Sur/2903 · MPSB/MB/958
P25-KS-S02-O | P25-KS-S02-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 2 |  |  | 888 | [5 empty] | Cast in yard | 2026-02-03 | IPC - 27 | 3 | MPSB/MB/888 · MPSB/Sur/2849 · MPSB/MB/891
P25-KS-S01-O | P25-KS-S01-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P24-P25 | KS | 1 |  |  | 889 | [5 empty] | Cast in yard | 2026-01-27 | IPC - 26 | 3 | MPSB/MB/790 · MPSB/Sur/2781 · MPSB/MB/818
P25-BP-S01a-O | P25-BP-S01a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 1 | Y |  | 890 | [5 empty] | Cast in yard | 2026-04-17 | IPC - 30 | 3 | MPSB/MB/1497 · MPSB/Sur/3315 · MPSB/MB/1566
P25-BP-S02a-O | P25-BP-S02a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 2 | Y |  | 891 | [5 empty] | Cast in yard | 2026-04-29 | IPC - 30 | 3 | MPSB/MB/1596 · MPSB/Sur/3384 · MPSB/MB/1663
P25-BP-S03a-O | P25-BP-S03a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 3 | Y |  | 892 | [5 empty] | Cast in yard | 2026-04-30 | IPC - 30 | 3 | MPSB/MB/1666 · MPSB/Sur/3389 · MPSB/MB/1671
P25-BP-S04a-O | P25-BP-S04a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 4 | Y |  | 893 | [5 empty] | Not started |  |  | 0
P25-BP-S05a-O | P25-BP-S05a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 5 | Y |  | 894 | [5 empty] | Cast in yard | 2026-05-11 | IPC - 31 | 3 | MPSB/MB/1728 · MPSB/Sur/3458 · MPSB/MB/1740
P25-BP-S06a-O | P25-BP-S06a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 6 | Y |  | 895 | [5 empty] | Cast in yard | 2026-05-15 | IPC - 31 | 3 | MPSB/MB/1756 · MPSB/Sur/3482 · MPSB/MB/1773
P25-BP-S07a-O | P25-BP-S07a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 7 | Y |  | 896 | [5 empty] | Cast in yard | 2026-05-19 | IPC - 31 | 3 | MPSB/MB/1782 · MPSB/Sur/3508 · MPSB/MB/1801
P25-BP-S08a-O | P25-BP-S08a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 8 | Y |  | 897 | [5 empty] | Cast in yard | 2026-05-22 | IPC - 31 | 3 | MPSB/MB/1822 · MPSB/Sur/3533 · MPSB/MB/1831
P25-BP-S09a-O | P25-BP-S09a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 9 | Y | Y | 898 | [5 empty] | Cast in yard | 2025-09-13 | IPC - 20 | 3 | MPSB/MB/125 · MPSB/Sur/1819 · MPSB/MB/158
P25-BP-S10a-O | P25-BP-S10a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 10 | Y |  | 899 | [5 empty] | Cast in yard | 2025-09-22 | IPC - 20 | 3 | MPSB/MB/170 · MPSB/Sur/1860 · MPSB/MB/191
P25-BP-S11a-O | P25-BP-S11a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 11 | Y | Y | 900 | [5 empty] | Cast in yard | 2025-09-27 | IPC - 20 | 3 | MPSB/MB/201 · MPSB/Sur/1883 · MPSB/MB/209
P25-BP-S12a-O | P25-BP-S12a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 12 | Y |  | 901 | [5 empty] | Cast in yard | 2025-09-30 | IPC - 20 | 3 | MPSB/MB/210 · MPSB/Sur/1895 · MPSB/MB/211
P25-BP-S13a-O | P25-BP-S13a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 13 | Y | Y | 902 | [5 empty] | Cast in yard | 2025-10-09 | IPC - 22 | 3 | MPSB/MB/232 · MPSB/Sur/1949 · MPSB/MB/239
P25-BP-S14a-O | P25-BP-S14a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 14 | Y |  | 903 | [5 empty] | Cast in yard | 2025-10-13 | IPC - 22 | 3 | MPSB/MB/248 · MPSB/Sur/1972 · MPSB/MB/253
P25-BP-S15a-O | P25-BP-S15a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 15 | Y | Y | 904 | [5 empty] | Cast in yard | 2025-10-17 | IPC - 22 | 3 | MPSB/MB/262 · MPSB/Sur/2002 · MPSB/MB/270
P25-BP-S16a-O | P25-BP-S16a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 16 | Y |  | 905 | [5 empty] | Cast in yard | 2025-10-24 | IPC - 22 | 3 | MPSB/MB/280 · MPSB/Sur/2036 · MPSB/MB/288
P25-BP-S17a-O | P25-BP-S17a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 17 | Y | Y | 906 | [5 empty] | Cast in yard | 2025-10-30 | IPC - 22 | 3 | MPSB/MB/304 · MPSB/Sur/2074 · MPSB/MB/310
P25-BP-S18a-O | P25-BP-S18a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 18 | Y |  | 907 | [5 empty] | Cast in yard | 2025-11-15 | IPC - 23 | 3 | MPSB/MB/347 · MPSB/Sur/2195 · MPSB/MB/360
P25-BP-S19a-O | P25-BP-S19a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 19 | Y | Y | 908 | [5 empty] | Cast in yard | 2025-11-21 | IPC - 23 | 3 | MPSB/MB/375 · MPSB/Sur/2244 · MPSB/MB/388
P25-BP-S20a-O | P25-BP-S20a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 20 | Y |  | 909 | [5 empty] | Cast in yard | 2025-11-30 | IPC - 23 | 2 | MPSB/MB/418 · MPSB/MB/427
P25-BP-S21a-O | P25-BP-S21a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 21 | Y | Y | 910 | [5 empty] | Cast in yard | 2025-12-31 | IPC - 25 | 3 | MPSB/MB/595 · MPSB/Sur/2578 · MPSB/MB/611
P25-BP-S22a-O | P25-BP-S22a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 22 | Y |  | 911 | [5 empty] | Cast in yard | 2026-01-22 | IPC - 26 | 3 | MPSB/MB/767 · MPSB/Sur/2741 · MPSB/MB/777
P25-BP-S23a-O | P25-BP-S23a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 23 | Y | Y | 912 | [5 empty] | Cast in yard | 2026-01-28 | IPC - 26 | 3 | MPSB/MB/820 · MPSB/Sur/2787 · MPSB/MB/827
P25-BP-S24a-O | P25-BP-S24a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 24 | Y |  | 913 | [5 empty] | Cast in yard | 2026-01-31 | IPC - 26 | 3 | MPSB/MB/882 · MPSB/Sur/2839 · MPSB/MB/884
P25-BP-S25a-O | P25-BP-S25a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 25 | Y | Y | 914 | [5 empty] | Cast in yard | 2026-02-11 | IPC - 27 | 3 | MPSB/MB/957 · MPSB/Sur/2915 · MPSB/MB/961
P25-BP-S26a-O | P25-BP-S26a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 26 | Y |  | 915 | [5 empty] | Cast in yard | 2026-02-15 | IPC - 27 | 3 | MPSB/MB/982 · MPSB/Sur/2937 · MPSB/MB/998
P25-BP-S27a-O | P25-BP-S27a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 27 | Y | Y | 916 | [5 empty] | Cast in yard | 2026-02-18 | IPC - 27 | 3 | MPSB/MB/1015 · MPSB/Sur/2954 · MPSB/MB/1022
P25-BP-S28a-O | P25-BP-S28a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 28 | Y |  | 917 | [5 empty] | Cast in yard | 2026-02-20 | IPC - 27 | 3 | MPSB/MB/1024 · MPSB/Sur/2969 · MPSB/MB/1038
P25-BP-S29a-O | P25-BP-S29a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 29 | Y | Y | 918 | [5 empty] | Cast in yard | 2026-02-23 | IPC - 27 | 3 | MPSB/MB/1039 · MPSB/Sur/2980 · MPSB/MB/1059
P25-BP-S30a-O | P25-BP-S30a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 30 | Y |  | 919 | [5 empty] | Cast in yard | 2026-02-26 | IPC - 27 | 3 | MPSB/MB/1065 · MPSB/Sur/3014 · MPSB/MB/1097
P25-BP-S31a-O | P25-BP-S31a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 31 | Y | Y | 920 | [5 empty] | Cast in yard | 2026-02-28 | IPC - 27 | 3 | MPSB/MB/1119 · MPSB/Sur/3033 · MPSB/MB/1120
P25-BP-S32a-O | P25-BP-S32a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 32 | Y |  | 921 | [5 empty] | Cast in yard | 2026-03-05 | IPC - 29 | 3 | MPSB/MB/1146 · MPSB/Sur/3062 · MPSB/MB/1148 | Y
P25-BP-S33a-O | P25-BP-S33a-O© | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 33 | Y | Y | 922 | [5 empty] | Cast in yard | 2026-03-08 | IPC - 29 | 3 | MPSB/MB/1182 · MPSB/Sur/3078 · MPSB/MB/1195
P25-BP-S34a-O | P25-BP-S34a-O | Precast segment | P25 | P25 | Outer pylon |  | 5 | P25-P26 | BP | 34 | Y |  | 923 | [5 empty] | Cast in yard | 2026-03-12 | IPC - 29 | 3 | MPSB/MB/1234 · MPSB/Sur/3103 · MPSB/MB/1239
P26-KS-S06-E | P26-KS-S06-E | Precast segment | P26 | P26 | EJ pier |  | 5 | P25-P26 | KS | 6 |  |  | 924 | [5 empty] | Cast in yard | 2026-03-21 | IPC - 29 | 3 | MPSB/MB/1300 · MPSB/Sur/3158 · MPSB/MB/1331
P26-KS-S05-E | P26-KS-S05-E | Precast segment | P26 | P26 | EJ pier |  | 5 | P25-P26 | KS | 5 |  |  | 925 | [5 empty] | Cast in yard | 2026-03-17 | IPC - 29 | 2 | MPSB/Sur/3138 · MPSB/MB/1284
P26-KS-S04-E | P26-KS-S04-E | Precast segment | P26 | P26 | EJ pier |  | 5 | P25-P26 | KS | 4 |  |  | 926 | [5 empty] | Cast in yard | 2026-03-13 | IPC - 29 | 3 | MPSB/MB/1258 · MPSB/Sur/3113 · MPSB/MB/1259
P26-KS-S03-E | P26-KS-S03-E | Precast segment | P26 | P26 | EJ pier |  | 5 | P25-P26 | KS | 3 |  |  | 927 | [5 empty] | Cast in yard | 2026-03-08 | IPC - 29 | 3 | MPSB/MB/1181 · MPSB/Sur/3079 · MPSB/MB/1196
P26-KS-S02-E | P26-KS-S02-E | Precast segment | P26 | P26 | EJ pier |  | 5 | P25-P26 | KS | 2 |  |  | 928 | [5 empty] | Cast in yard | 2026-02-28 | IPC - 27 | 3 | MPSB/MB/1121 · MPSB/Sur/3034 · MPSB/MB/1122
P26-KS-S01-E | P26-KS-S01-E | Precast segment | P26 | P26 | EJ pier |  | 5 | P25-P26 | KS | 1 |  |  | 929 | [5 empty] | Cast in yard | 2026-02-28 | IPC - 27 | 3 | MPSB/MB/1109 · MPSB/Sur/3032 · MPSB/MB/1116
P26-KS-S01a-E | P26-KS-S01a-E | Precast segment | P26 | P26 | EJ pier |  | 5 | P25-P26 | KS | 1 | Y |  | 930 | [5 empty] | Cast in yard | 2026-02-25 | IPC - 27 | 3 | MPSB/MB/1060 · MPSB/Sur/3003 · MPSB/MB/1076
P26-BP-S01a-E | P26-BP-S01a-E | Precast segment | P26 | P26 | EJ pier |  | 6 | P26-P27 | BP | 1 | Y |  | 931 | [5 empty] | Not started |  |  | 0
P26-BP-S01-E | P26-BP-S01-E | Precast segment | P26 | P26 | EJ pier |  | 6 | P26-P27 | BP | 1 |  |  | 932 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGr6 | 1752527
P26-BP-S02-E | P26-BP-S02-E | Precast segment | P26 | P26 | EJ pier |  | 6 | P26-P27 | BP | 2 |  |  | 933 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGrZ | 1752554
P26-BP-S03-E | P26-BP-S03-E | Precast segment | P26 | P26 | EJ pier |  | 6 | P26-P27 | BP | 3 |  |  | 934 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGwC | 1752581
P26-BP-S04-E | P26-BP-S04-E | Precast segment | P26 | P26 | EJ pier |  | 6 | P26-P27 | BP | 4 |  |  | 935 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGwf | 1752608
P26-BP-S05-E | P26-BP-S05-E | Precast segment | P26 | P26 | EJ pier |  | 6 | P26-P27 | BP | 5 |  |  | 936 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGwo | 1752635
P26-BP-S06-E | P26-BP-S06-E | Precast segment | P26 | P26 | EJ pier |  | 6 | P26-P27 | BP | 6 |  |  | 937 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGxV | 1752662
P27-KS-S34a-O | P27-KS-S34a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 34 | Y |  | 938 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGxu | 1752689
P27-KS-S33a-O | P27-KS-S33a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 33 | Y | Y | 939 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGu5 | 1752716
P27-KS-S32a-O | P27-KS-S32a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 32 | Y |  | 940 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGuk | 1752743
P27-KS-S31a-O | P27-KS-S31a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 31 | Y | Y | 941 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGvB | 1752770
P27-KS-S30a-O | P27-KS-S30a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 30 | Y |  | 942 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGvK | 1752797
P27-KS-S29a-O | P27-KS-S29a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 29 | Y | Y | 943 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGvn | 1752824
P27-KS-S28a-O | P27-KS-S28a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 28 | Y |  | 944 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFG_Q | 1752851
P27-KS-S27a-O | P27-KS-S27a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 27 | Y | Y | 945 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFG_d | 1752878
P27-KS-S26a-O | P27-KS-S26a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 26 | Y |  | 946 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFG$0 | 1752905
P27-KS-S25a-O | P27-KS-S25a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 25 | Y | Y | 947 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFG$j | 1752932
P27-KS-S24a-O | P27-KS-S24a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 24 | Y |  | 948 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFG$s | 1752959
P27-KS-S23a-O | P27-KS-S23a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 23 | Y | Y | 949 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGyJ | 1752986
P27-KS-S22a-O | P27-KS-S22a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 22 | Y |  | 950 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGyy | 1753013
P27-KS-S21a-O | P27-KS-S21a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 21 | Y | Y | 951 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGzP | 1753040
P27-KS-S20a-O | P27-KS-S20a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 20 | Y |  | 952 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFGzY | 1753067
P27-KS-S19a-O | P27-KS-S19a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 19 | Y | Y | 953 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN2F | 1753094
P27-KS-S18a-O | P27-KS-S18a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 18 | Y |  | 954 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN2e | 1753121
P27-KS-S17a-O | P27-KS-S17a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 17 | Y | Y | 955 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN2r | 1753148
P27-KS-S16a-O | P27-KS-S16a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 16 | Y |  | 956 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN3U | 1753175
P27-KS-S15a-O | P27-KS-S15a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 15 | Y | Y | 957 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN3x | 1753202
P27-KS-S14a-O | P27-KS-S14a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 14 | Y |  | 958 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN04 | 1753229
P27-KS-S13a-O | P27-KS-S13a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 13 | Y | Y | 959 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN0X | 1753256
P27-KS-S12a-O | P27-KS-S12a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 12 | Y |  | 960 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN1A | 1753283
P27-KS-S11a-O | P27-KS-S11a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 11 | Y | Y | 961 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN1N | 1753310
P27-KS-S10a-O | P27-KS-S10a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 10 | Y |  | 962 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN1m | 1753337
P27-KS-S09a-O | P27-KS-S09a-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 9 | Y | Y | 963 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN6T | 1753364
P27-KS-S08a-O | P27-KS-S08a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 8 | Y |  | 964 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN6v | 1753392
P27-KS-S07a-O | P27-KS-S07a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 7 | Y |  | 965 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN72 | 1753419
P27-KS-S06a-O | P27-KS-S06a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 6 | Y |  | 966 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN7l | 1753446
P27-KS-S05a-O | P27-KS-S05a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 5 | Y |  | 967 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN48 | 1753473
P27-KS-S04a-O | P27-KS-S04a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 4 | Y |  | 968 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN4L | 1753500
P27-KS-S03a-O | P27-KS-S03a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 3 | Y |  | 969 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN4_ | 1753527
P27-KS-S02a-O | P27-KS-S02a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 2 | Y |  | 970 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN5R | 1753554
P27-KS-S01a-O | P27-KS-S01a-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P26-P27 | KS | 1 | Y |  | 971 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN5a | 1753581
P27-BP-S01-O | P27-BP-S01-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 1 |  |  | 972 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNA0 | 1753609
P27-BP-S02-O | P27-BP-S02-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 2 |  |  | 973 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNAj | 1753636
P27-BP-S03-O | P27-BP-S03-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 3 |  |  | 974 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNAs | 1753663
P27-BP-S04-O | P27-BP-S04-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 4 |  |  | 975 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNBJ | 1753690
P27-BP-S05-O | P27-BP-S05-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 5 |  |  | 976 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNBy | 1753717
P27-BP-S06-O | P27-BP-S06-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 6 |  |  | 977 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN8P | 1753744
P27-BP-S07-O | P27-BP-S07-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 7 |  |  | 978 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN8Y | 1753771
P27-BP-S08-O | P27-BP-S08-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 8 |  |  | 979 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN9F | 1753798
P27-BP-S09-O | P27-BP-S09-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 9 |  | Y | 980 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN9e | 1753825
P27-BP-S10-O | P27-BP-S10-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 10 |  |  | 981 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN9r | 1753852
P27-BP-S11-O | P27-BP-S11-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 11 |  | Y | 982 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNEU | 1753879
P27-BP-S12-O | P27-BP-S12-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 12 |  |  | 983 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNEx | 1753906
P27-BP-S13-O | P27-BP-S13-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 13 |  | Y | 984 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNF4 | 1753933
P27-BP-S14-O | P27-BP-S14-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 14 |  |  | 985 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNFX | 1753960
P27-BP-S15-O | P27-BP-S15-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 15 |  | Y | 986 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNCA | 1753987
P27-BP-S16-O | P27-BP-S16-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 16 |  |  | 987 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNCN | 1754014
P27-BP-S17-O | P27-BP-S17-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 17 |  | Y | 988 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNCm | 1754041
P27-BP-S18-O | P27-BP-S18-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 18 |  |  | 989 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNDT | 1754068
P27-BP-S19-O | P27-BP-S19-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 19 |  | Y | 990 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNDc | 1754095
P27-BP-S20-O | P27-BP-S20-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 20 |  |  | 991 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNI3 | 1754122
P27-BP-S21-O | P27-BP-S21-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 21 |  | Y | 992 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNIi | 1754149
P27-BP-S22-O | P27-BP-S22-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 22 |  |  | 993 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNJ9 | 1754176
P27-BP-S23-O | P27-BP-S23-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 23 |  | Y | 994 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNJK | 1754205
P27-BP-S24-O | P27-BP-S24-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 24 |  |  | 995 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNJn | 1754232
P27-BP-S25-O | P27-BP-S25-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 25 |  | Y | 996 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNGQ | 1754259
P27-BP-S26-O | P27-BP-S26-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 26 |  |  | 997 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNGd | 1754286
P27-BP-S27-O | P27-BP-S27-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 27 |  | Y | 998 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNH0 | 1754313
P27-BP-S28-O | P27-BP-S28-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 28 |  |  | 999 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNHj | 1754340
P27-BP-S29-O | P27-BP-S29-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 29 |  | Y | 1000 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNHs | 1754367
P27-BP-S30-O | P27-BP-S30-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 30 |  |  | 1001 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNMJ | 1754394
P27-BP-S31-O | P27-BP-S31-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 31 |  | Y | 1002 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNMy | 1754421
P27-BP-S32-O | P27-BP-S32-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 32 |  |  | 1003 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNNP | 1754448
P27-BP-S33-O | P27-BP-S33-O© | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 33 |  | Y | 1004 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNNY | 1754475
P27-BP-S34-O | P27-BP-S34-O | Precast segment | P27 | P27 | Outer pylon |  | 6 | P27-P28 | BP | 34 |  |  | 1005 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNKF | 1754502
P28-KS-S18-M | P28-KS-S18-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 18 |  |  | 1006 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNKg | 1754531
P28-KS-S17-M | P28-KS-S17-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 17 |  |  | 1007 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNKt | 1754558
P28-KS-S16-M | P28-KS-S16-M© | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 16 |  | Y | 1008 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNLG | 1754585
P28-KS-S15-M | P28-KS-S15-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 15 |  |  | 1009 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNLz | 1754612
P28-KS-S14-M | P28-KS-S14-M© | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 14 |  | Y | 1010 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNQ6 | 1754639
P28-KS-S13-M | P28-KS-S13-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 13 |  |  | 1011 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNQZ | 1754666
P28-KS-S12-M | P28-KS-S12-M© | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 12 |  | Y | 1012 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNRC | 1754693
P28-KS-S11-M | P28-KS-S11-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 11 |  |  | 1013 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNRf | 1754720
P28-KS-S10-M | P28-KS-S10-M© | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 10 |  | Y | 1014 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNRo | 1754747
P28-KS-S09-M | P28-KS-S09-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 9 |  |  | 1015 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNOV | 1754774
P28-KS-S08-M | P28-KS-S08-M© | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 8 |  | Y | 1016 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNOu | 1754801
P28-KS-S07-M | P28-KS-S07-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 7 |  |  | 1017 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNP7 | 1754830
P28-KS-S06-M | P28-KS-S06-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 6 |  |  | 1018 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNPW | 1754857
P28-KS-S05-M | P28-KS-S05-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 5 |  |  | 1019 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNUD | 1754884
P28-KS-S04-M | P28-KS-S04-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 4 |  |  | 1020 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNUM | 1754911
P28-KS-S03-M | P28-KS-S03-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 3 |  |  | 1021 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNUp | 1754938
P28-KS-S02-M | P28-KS-S02-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 2 |  |  | 1022 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNVS | 1754965
P28-KS-S01-M | P28-KS-S01-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P27-P28 | KS | 1 |  |  | 1023 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNVv | 1754992
P28-BP-S01-M | P28-BP-S01-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 1 |  |  | 1024 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNS7 | 1755022
P28-BP-S02-M | P28-BP-S02-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 2 |  |  | 1025 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNSW | 1755049
P28-BP-S03-M | P28-BP-S03-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 3 |  |  | 1026 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNTD | 1755076
P28-BP-S04-M | P28-BP-S04-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 4 |  |  | 1027 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNTM | 1755103
P28-BP-S05-M | P28-BP-S05-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 5 |  |  | 1028 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNTp | 1755130
P28-BP-S06-M | P28-BP-S06-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 6 |  |  | 1029 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNYS | 1755157
P28-BP-S07-M | P28-BP-S07-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 7 |  |  | 1030 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNYv | 1755184
P28-BP-S08-M | P28-BP-S08-M© | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 8 |  | Y | 1031 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNZ4 | 1755213
P28-BP-S09-M | P28-BP-S09-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 9 |  |  | 1032 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNZX | 1755240
P28-BP-S10-M | P28-BP-S10-M© | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 10 |  | Y | 1033 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNWA | 1755267
P28-BP-S11-M | P28-BP-S11-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 11 |  |  | 1034 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNWN | 1755294
P28-BP-S12-M | P28-BP-S12-M© | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 12 |  | Y | 1035 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNWm | 1755321
P28-BP-S13-M | P28-BP-S13-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 13 |  |  | 1036 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNXT | 1755348
P28-BP-S14-M | P28-BP-S14-M© | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 14 |  | Y | 1037 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNXc | 1755375
P28-BP-S15-M | P28-BP-S15-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 15 |  |  | 1038 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNc3 | 1755402
P28-BP-S16-M | P28-BP-S16-M© | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 16 |  | Y | 1039 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNci | 1755429
P28-BP-S17-M | P28-BP-S17-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 17 |  |  | 1040 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNd9 | 1755456
P28-BP-S18-M | P28-BP-S18-M | Precast segment | P28 | P28 | Middle pylon |  | 6 | P28-P29 | BP | 18 |  |  | 1041 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNdI | 1755483
P29-KS-S34-O | P29-KS-S34-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 34 |  |  | 1042 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNdn | 1755512
P29-KS-S33-O | P29-KS-S33-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 33 |  | Y | 1043 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNaT | 1755540
P29-KS-S32-O | P29-KS-S32-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 32 |  |  | 1044 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNac | 1755567
P29-KS-S31-O | P29-KS-S31-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 31 |  | Y | 1045 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNb3 | 1755594
P29-KS-S30-O | P29-KS-S30-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 30 |  |  | 1046 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNbi | 1755621
P29-KS-S29-O | P29-KS-S29-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 29 |  | Y | 1047 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNg9 | 1755648
P29-KS-S28-O | P29-KS-S28-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 28 |  |  | 1048 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNgI | 1755675
P29-KS-S27-O | P29-KS-S27-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 27 |  | Y | 1049 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNg$ | 1755702
P29-KS-S26-O | P29-KS-S26-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 26 |  |  | 1050 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNhO | 1755729
P29-KS-S25-O | P29-KS-S25-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 25 |  | Y | 1051 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNhb | 1755756
P29-KS-S24-O | P29-KS-S24-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 24 |  |  | 1052 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNeE | 1755783
P29-KS-S23-O | P29-KS-S23-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 23 |  | Y | 1053 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNeh | 1755810
P29-KS-S22-O | P29-KS-S22-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 22 |  |  | 1054 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNeq | 1755837
P29-KS-S21-O | P29-KS-S21-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 21 |  | Y | 1055 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNfH | 1755864
P29-KS-S20-O | P29-KS-S20-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 20 |  |  | 1056 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNfw | 1755891
P29-KS-S19-O | P29-KS-S19-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 19 |  | Y | 1057 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNk7 | 1755918
P29-KS-S18-O | P29-KS-S18-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 18 |  |  | 1058 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNkW | 1755945
P29-KS-S17-O | P29-KS-S17-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 17 |  | Y | 1059 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNlD | 1755972
P29-KS-S16-O | P29-KS-S16-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 16 |  |  | 1060 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNlM | 1755999
P29-KS-S15-O | P29-KS-S15-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 15 |  | Y | 1061 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNlp | 1756026
P29-KS-S14-O | P29-KS-S14-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 14 |  |  | 1062 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNiS | 1756053
P29-KS-S13-O | P29-KS-S13-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 13 |  | Y | 1063 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNiv | 1756080
P29-KS-S12-O | P29-KS-S12-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 12 |  |  | 1064 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNj2 | 1756107
P29-KS-S11-O | P29-KS-S11-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 11 |  | Y | 1065 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNjl | 1756134
P29-KS-S10-O | P29-KS-S10-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 10 |  |  | 1066 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNo8 | 1756161
P29-KS-S09-O | P29-KS-S09-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 9 |  | Y | 1067 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNoL | 1756188
P29-KS-S08-O | P29-KS-S08-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 8 |  |  | 1068 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNom | 1756217
P29-KS-S07-O | P29-KS-S07-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 7 |  |  | 1069 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNpT | 1756244
P29-KS-S06-O | P29-KS-S06-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 6 |  |  | 1070 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNpc | 1756271
P29-KS-S05-O | P29-KS-S05-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 5 |  |  | 1071 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNm3 | 1756298
P29-KS-S04-O | P29-KS-S04-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 4 |  |  | 1072 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNmi | 1756325
P29-KS-S03-O | P29-KS-S03-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 3 |  |  | 1073 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNn9 | 1756352
P29-KS-S02-O | P29-KS-S02-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 2 |  |  | 1074 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNnI | 1756379
P29-KS-S01-O | P29-KS-S01-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P28-P29 | KS | 1 |  |  | 1075 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNn$ | 1756406
P29-BP-S01a-O | P29-BP-S01a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 1 | Y |  | 1076 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNsM | 1756447
P29-BP-S02a-O | P29-BP-S02a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 2 | Y |  | 1077 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNsp | 1756474
P29-BP-S03a-O | P29-BP-S03a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 3 | Y |  | 1078 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNtS | 1756501
P29-BP-S04a-O | P29-BP-S04a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 4 | Y |  | 1079 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNtv | 1756528
P29-BP-S05a-O | P29-BP-S05a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 5 | Y |  | 1080 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNq2 | 1756555
P29-BP-S06a-O | P29-BP-S06a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 6 | Y |  | 1081 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNql | 1756582
P29-BP-S07a-O | P29-BP-S07a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 7 | Y |  | 1082 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNr8 | 1756609
P29-BP-S08a-O | P29-BP-S08a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 8 | Y |  | 1083 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNrL | 1756636
P29-BP-S09a-O | P29-BP-S09a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 9 | Y | Y | 1084 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNrm | 1756665
P29-BP-S10a-O | P29-BP-S10a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 10 | Y |  | 1085 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNwT | 1756692
P29-BP-S11a-O | P29-BP-S11a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 11 | Y | Y | 1086 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNwc | 1756719
P29-BP-S12a-O | P29-BP-S12a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 12 | Y |  | 1087 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNx3 | 1756746
P29-BP-S13a-O | P29-BP-S13a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 13 | Y | Y | 1088 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNxi | 1756773
P29-BP-S14a-O | P29-BP-S14a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 14 | Y |  | 1089 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNu9 | 1756800
P29-BP-S15a-O | P29-BP-S15a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 15 | Y | Y | 1090 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNuI | 1756827
P29-BP-S16a-O | P29-BP-S16a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 16 | Y |  | 1091 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNu$ | 1756854
P29-BP-S17a-O | P29-BP-S17a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 17 | Y | Y | 1092 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNvO | 1756881
P29-BP-S18a-O | P29-BP-S18a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 18 | Y |  | 1093 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNvb | 1756908
P29-BP-S19a-O | P29-BP-S19a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 19 | Y | Y | 1094 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN_E | 1756935
P29-BP-S20a-O | P29-BP-S20a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 20 | Y |  | 1095 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN_h | 1756962
P29-BP-S21a-O | P29-BP-S21a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 21 | Y | Y | 1096 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN_q | 1756989
P29-BP-S22a-O | P29-BP-S22a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 22 | Y |  | 1097 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN$H | 1757016
P29-BP-S23a-O | P29-BP-S23a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 23 | Y | Y | 1098 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFN$w | 1757043
P29-BP-S24a-O | P29-BP-S24a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 24 | Y |  | 1099 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNy7 | 1757070
P29-BP-S25a-O | P29-BP-S25a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 25 | Y | Y | 1100 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNyW | 1757097
P29-BP-S26a-O | P29-BP-S26a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 26 | Y |  | 1101 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNzD | 1757124
P29-BP-S27a-O | P29-BP-S27a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 27 | Y | Y | 1102 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNzM | 1757151
P29-BP-S28a-O | P29-BP-S28a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 28 | Y |  | 1103 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFNzp | 1757178
P29-BP-S29a-O | P29-BP-S29a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 29 | Y | Y | 1104 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM2S | 1757205
P29-BP-S30a-O | P29-BP-S30a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 30 | Y |  | 1105 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM2v | 1757232
P29-BP-S31a-O | P29-BP-S31a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 31 | Y | Y | 1106 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM32 | 1757259
P29-BP-S32a-O | P29-BP-S32a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 32 | Y |  | 1107 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM3l | 1757286
P29-BP-S33a-O | P29-BP-S33a-O© | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 33 | Y | Y | 1108 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM08 | 1757313
P29-BP-S34a-O | P29-BP-S34a-O | Precast segment | P29 | P29 | Outer pylon |  | 6 | P29-P30 | BP | 34 | Y |  | 1109 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM0L | 1757340
P30-KS-S06-E | P30-KS-S06-E | Precast segment | P30 | P30 | EJ pier |  | 6 | P29-P30 | KS | 6 |  |  | 1110 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM0m | 1757369
P30-KS-S05-E | P30-KS-S05-E | Precast segment | P30 | P30 | EJ pier |  | 6 | P29-P30 | KS | 5 |  |  | 1111 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM1T | 1757396
P30-KS-S04-E | P30-KS-S04-E | Precast segment | P30 | P30 | EJ pier |  | 6 | P29-P30 | KS | 4 |  |  | 1112 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM1c | 1757423
P30-KS-S03-E | P30-KS-S03-E | Precast segment | P30 | P30 | EJ pier |  | 6 | P29-P30 | KS | 3 |  |  | 1113 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM63 | 1757450
P30-KS-S02-E | P30-KS-S02-E | Precast segment | P30 | P30 | EJ pier |  | 6 | P29-P30 | KS | 2 |  |  | 1114 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM6i | 1757477
P30-KS-S01-E | P30-KS-S01-E | Precast segment | P30 | P30 | EJ pier |  | 6 | P29-P30 | KS | 1 |  |  | 1115 | [5 empty] | Not started |  |  | 0 |  |  | 2EjqfCRAz07gd2_buxFM79 | 1757504
P30-KS-S01a-E | P30-KS-S01a-E | Precast segment | P30 | P30 | EJ pier |  | 6 | P29-P30 | KS | 1 | Y |  | 1116 | [5 empty] | Not started |  |  | 0
Rows: 1810. Only the yellow columns are inputs; every other column is regenerated from the IPC file.

## RFI_Log
Element_Key | Site_Text | BOQ_Item | RFI_No | RFI_Series | Chain_Pos | Chain_Len | RFI_Date | IPC | Qty | Bank | Source_Row | Also_Used_By
| Circular - 8 Nos. Double D - 6 Nos. | 401.a | MPSB/MB/1 | Mb | 1 | 1 | 2024-09-30 | IPC - 05 | 14 | Palashbari | 9
| Double D - 1 No. | 401.a | MPSB/MB/2 | Mb | 1 | 1 | 2024-09-30 | IPC - 05 | 1 | Sualkuchi | 10
| Double D - 1 No. | 401.a | MPSB/MB/3 | Mb | 1 | 1 | 2024-10-28 | IPC - 07 | 1 | Sualkuchi | 11
| Circular - 5 Nos. Double D - 4 Nos. | 401.a | MPSB/MB/4 | Mb | 1 | 1 | 2024-10-31 | IPC - 07 | 9 | Palashbari | 12
P14(N)-WELL-CE | P14(N) | 401.a | MPSB/MB/457 | Mb | 1 | 1 | 2025-12-06 | IPC - 26 | 1 | Palashbari | 14
P12(A)-WELL-CE | P12(A) | 401.a | MPSB/MB/0660 | Mb | 1 | 1 | 2026-01-07 | IPC - 33 | 1 | Palashbari | 15
P12-WELL-CE | P12 | 401.a | MPSB/MB/1794 | Mb | 1 | 1 | 2026-05-18 | IPC - 33 | 1 | Palashbari | 16
P26-WELL-CE | P26 | 401.b | MPSB/Sur/56 | Sur | 1 | 1 | 2024-10-24 | IPC - 07 | 1 | Sualkuchi | 22
P24-WELL-CE | P24 | 401.b | MPSB/Sur/57 | Sur | 1 | 1 | 2024-10-26 | IPC - 07 | 1 | Sualkuchi | 23
P22-WELL-CE | P22 | 401.b | MPSB/Sur/60 | Sur | 1 | 1 | 2024-10-28 | IPC - 07 | 1 | Sualkuchi | 24
P25-WELL-CE | P25 | 401.b | MPSB/Sur/76 | Sur | 1 | 1 | 2024-10-31 | IPC - 07 | 1 | Sualkuchi | 25
P23-WELL-CE | P23 | 401.b | MPSB/Sur/77 | Sur | 1 | 1 | 2024-10-31 | IPC - 07 | 1 | Sualkuchi | 26
P20-WELL-CE | P20 | 401.b | MPSB/Sur/103 | Sur | 1 | 1 | 2024-11-16 | IPC - 08 | 1 | Sualkuchi | 27
P6-WELL-CE | P6 | 401.b | MPSB/Sur/80 | Sur | 1 | 1 | 2024-11-04 | IPC - 08 | 1 | Palashbari | 28
P7-WELL-CE | P7 | 401.b | MPSB/Sur/120 | Sur | 1 | 1 | 2024-11-22 | IPC - 08 | 1 | Palashbari | 29
P21-WELL-CE | P21 | 401.b | MPSB/Sur/153 | Sur | 1 | 1 | 2024-11-30 | IPC - 08 | 1 | Sualkuchi | 30
P28-WELL-CE | P28 | 401.b | MPSB/Sur/168 | Sur | 1 | 1 | 2024-12-03 | IPC - 08 | 1 | Sualkuchi | 31
P19-WELL-CE | P19 | 401.b | MPSB/Sur/176 | Sur | 1 | 1 | 2024-12-05 | IPC - 08 | 1 | Sualkuchi | 32
P18-WELL-CE | P18 | 401.b | MPSB/Sur/167 | Sur | 1 | 1 | 2024-12-03 | IPC - 09 | 1 | Sualkuchi | 33
P16-WELL-CE | P16 | 401.b | MPSB/Sur/185 | Sur | 1 | 1 | 2024-12-09 | IPC - 09 | 1 | Palashbari | 34
P8-WELL-CE | P8 | 401.b | MPSB/Sur/189 | Sur | 1 | 1 | 2024-12-11 | IPC - 09 | 1 | Palashbari | 35
P17-WELL-CE | P17 | 401.b | MPSB/Sur/202 | Sur | 1 | 1 | 2024-12-17 | IPC - 09 | 1 | Palashbari | 36
P9-WELL-CE | P9 | 401.b | MPSB/Sur/216 | Sur | 1 | 1 | 2024-12-25 | IPC - 09 | 1 | Palashbari | 37
P29-WELL-CE | P29 | 401.b | MPSB/Sur/241 | Sur | 1 | 1 | 2024-12-30 | IPC - 09 | 1 | Sualkuchi | 38
P15-WELL-CE | P15 | 401.b | MPSB/Sur/333 | Sur | 1 | 1 | 2025-01-20 | IPC - 10 | 1 | Palashbari | 39
P10-WELL-CE | P10 | 401.b | MPSB/Sur/357 | Sur | 1 | 1 | 2025-01-24 | IPC - 10 | 1 | Palashbari | 40
P14-WELL-CE | P14 | 401.b | MPSB/Sur/441 | Sur | 1 | 1 | 2025-02-08 | IPC - 11 | 1 | Palashbari | 41
P12-WELL-CE | P12 | 401.b | MPSB/Sur/477 | Sur | 1 | 1 | 2025-02-16 | IPC - 11 | 1 | Palashbari | 42
P27-WELL-CE | P27 | 401.b | MPSB/Sur/495 | Sur | 1 | 1 | 2025-02-18 | IPC - 11 | 1 | Sualkuchi | 43
P30-WELL-CE | P30 | 401.b | MPSB/Sur/2068 | Sur | 1 | 1 | 2025-10-29 | IPC - 22 | 1 | Sualkuchi | 44
P11-WELL-CE | P11 | 401.b | MPSB/Sur/2561 | Sur | 1 | 1 | 2025-12-30 | IPC - 26 | 1 | Palashbari | 45
P13-WELL-CE | P13 | 401.b | MPSB/Sur/2645 | Sur | 1 | 1 | 2026-01-10 | IPC - 26 | 1 | Palashbari | 46
P14(N)-WELL-CE | P14(N) | 401.b | MPSB/Sur/2435 | Sur | 1 | 1 | 2025-12-17 | IPC - 26 | 1 | Palashbari | 48
P12(A)-WELL-CE | P12(A) | 401.b | MPSB/Sur/2755 | Sur | 1 | 1 | 2026-01-24 | IPC - 33 | 1 | Palashbari | 49
P26-WELL-CE | P26 | 401.c | MPSB/Sur/87 | Sur | 1 | 1 | 2024-11-09 | IPC - 08 | 1 | Sualkuchi | 55
P22-WELL-CE | P22 | 401.c | MPSB/Sur/92 | Sur | 1 | 1 | 2024-11-13 | IPC - 08 | 1 | Sualkuchi | 56
P24-WELL-CE | P24 | 401.c | MPSB/Sur/102 | Sur | 1 | 1 | 2024-11-16 | IPC - 08 | 1 | Sualkuchi | 57
P6-WELL-CE | P6 | 401.c | MPSB/Sur/115 | Sur | 1 | 1 | 2024-11-21 | IPC - 08 | 1 | Palashbari | 58
P20-WELL-CE | P20 | 401.c | MPSB/Sur/127 | Sur | 1 | 1 | 2024-11-25 | IPC - 08 | 1 | Sualkuchi | 59
P28-WELL-CE | P28 | 401.c | MPSB/Sur/190 | Sur | 1 | 1 | 2024-12-11 | IPC - 08 | 1 | Palashbari | 60
P25-WELL-CE | P25 | 401.c | MPSB/Sur/196 | Sur | 1 | 1 | 2024-12-11 | IPC - 09 | 1 | Sualkuchi | 61
P18-WELL-CE | P18 | 401.c | MPSB/Sur/191 | Sur | 1 | 1 | 2024-12-14 | IPC - 09 | 1 | Sualkuchi | 62
P16-WELL-CE | P16 | 401.c | MPSB/Sur/205 | Sur | 1 | 1 | 2024-12-14 | IPC - 09 | 1 | Palashbari | 63
P7-WELL-CE | P7 | 401.c | MPSB/Sur/204 | Sur | 1 | 1 | 2024-12-19 | IPC - 09 | 1 | Sualkuchi | 64
P8-WELL-CE | P8 | 401.c | MPSB/Sur/207 | Sur | 1 | 1 | 2024-12-20 | IPC - 09 | 1 | Palashbari | 65
P19-WELL-CE | P19 | 401.c | MPSB/Sur/228 | Sur | 1 | 1 | 2025-12-28 | IPC - 10 | 1 | Sualkuchi | 66
P17-WELL-CE | P17 | 401.c | MPSB/Sur/294 | Sur | 1 | 1 | 2025-01-13 | IPC - 10 | 1 | Palashbari | 67
P21-WELL-CE | P21 | 401.c | MPSB/Sur/314 | Sur | 1 | 1 | 2025-01-17 | IPC - 10 | 1 | Sualkuchi | 68
P29-WELL-CE | P29 | 401.c | MPSB/Sur/343 | Sur | 1 | 1 | 2025-01-22 | IPC - 10 | 1 | Sualkuchi | 69
P15-WELL-CE | P15 | 401.c | MPSB/Sur/367 | Sur | 1 | 1 | 2025-01-27 | IPC - 10 | 1 | Palashbari | 70
P10-WELL-CE | P10 | 401.c | MPSB/Sur/368 | Sur | 1 | 1 | 2025-01-27 | IPC - 10 | 1 | Palashbari | 71
P9-WELL-CE | P9 | 401.c | MPSB/Sur/289 | Sur | 1 | 1 | 2025-01-11 | IPC - 11 | 1 | Palashbari | 72
P14-WELL-CE | P14 | 401.c | MPSB/Sur/460 | Sur | 1 | 1 | 2025-02-12 | IPC - 11 | 1 | Palashbari | 73
P23-WELL-CE | P23 | 401.c | MPSB/Sur/461 | Sur | 1 | 1 | 2025-02-12 | IPC - 11 | 1 | Sualkuchi | 74
P12-WELL-CE | P12 | 401.c | MPSB/Sur/501 | Sur | 1 | 1 | 2025-02-19 | IPC - 11 | 1 | Palashbari | 75
P27-WELL-CE | P27 | 401.c | MPSB/Sur/512 | Sur | 1 | 1 | 2025-02-20 | IPC - 11 | 1 | Sualkuchi | 76
P30-WELL-CE | P30 | 401.c | MPSB/Sur/2110 | Sur | 1 | 1 | 2025-11-01 | IPC - 23 | 1 | Sualkuchi | 77
P11-WELL-CE | P11 | 401.c | MPSB/Sur/2637 | Sur | 1 | 1 | 2026-01-09 | IPC - 26 | 1 | Palashbari | 78
P13-WELL-CE | P13 | 401.c | MPSB/Sur/2686 | Sur | 1 | 1 | 2026-01-16 | IPC - 26 | 1 | Palashbari | 79
P14(N)-WELL-CE | P14(N) | 401.c | MPSB/Sur/2466 | Sur | 1 | 1 | 2025-12-22 | IPC - 26 | 1 | Palashbari | 81
P12(A)-WELL-CE | P12(A) | 401.c | MPSB/Sur/2783 | Sur | 1 | 1 | 2026-01-28 | IPC - 33 | 1 | Palashbari | 82
P22-WELL-L00 | P22 - Well Curb | 402.a | MPSB/Str/135 | Str | 1 | 5 | 2024-11-26 | IPC - 08 | 4.32 | Sualkuchi | 89
P22-WELL-L00 | P22 - Well Curb | 402.a | MPSB/Sur/137 | Sur | 2 | 5 | 2024-11-28 | IPC - 08 | 4.32 | Sualkuchi | 89
P22-WELL-L00 | P22 - Well Curb | 402.a | MPSB/Str/153 | Str | 3 | 5 | 2024-11-29 | IPC - 08 | 4.32 | Sualkuchi | 89
P22-WELL-L00 | P22 - Well Curb | 402.a | MPSB/Sur/175 | Sur | 4 | 5 | 2024-12-04 | IPC - 08 | 4.32 | Sualkuchi | 89
P22-WELL-L00 | P22 - Well Curb | 402.a | MPSB/Str/182 | Str | 5 | 5 | 2024-12-04 | IPC - 08 | 4.32 | Sualkuchi | 89
P6-WELL-L00 | P6 - Well Curb | 402.a | MPSB/Str/148 | Str | 1 | 5 | 2024-11-28 | IPC - 08 | 4.32 | Palashbari | 90
P6-WELL-L00 | P6 - Well Curb | 402.a | MPSB/Sur/157 | Sur | 2 | 5 | 2024-11-30 | IPC - 08 | 4.32 | Palashbari | 90
P6-WELL-L00 | P6 - Well Curb | 402.a | MPSB/Str/164 | Str | 3 | 5 | 2024-11-30 | IPC - 08 | 4.32 | Palashbari | 90
P6-WELL-L00 | P6 - Well Curb | 402.a | MPSB/Sur/179 | Sur | 4 | 5 | 2024-12-06 | IPC - 08 | 4.32 | Palashbari | 90
P6-WELL-L00 | P6 - Well Curb | 402.a | MPSB/Str/184 | Str | 5 | 5 | 2024-12-06 | IPC - 08 | 4.32 | Palashbari | 90
P26-WELL-L00 | P26 - Well Curb | 402.a | MPSB/Str/99 | Str | 1 | 5 | 2024-11-16 | IPC - 09 | 4.32 | Sualkuchi | 91
P26-WELL-L00 | P26 - Well Curb | 402.a | MPSB/Sur/184 | Sur | 2 | 5 | 2024-12-08 | IPC - 09 | 4.32 | Sualkuchi | 91
P26-WELL-L00 | P26 - Well Curb | 402.a | MPSB/Str/190 | Str | 3 | 5 | 2024-12-08 | IPC - 09 | 4.32 | Sualkuchi | 91
P26-WELL-L00 | P26 - Well Curb | 402.a | MPSB/Sur/194 | Sur | 4 | 5 | 2024-12-13 | IPC - 09 | 4.32 | Sualkuchi | 91
P26-WELL-L00 | P26 - Well Curb | 402.a | MPSB/Str/202 | Str | 5 | 5 | 2024-12-13 | IPC - 09 | 4.32 | Sualkuchi | 91
P20-WELL-L00 | P20 - Well Curb | 402.a | MPSB/Str/209 | Str | 1 | 4 | 2024-12-15 | IPC - 09 | 4.32 | Sualkuchi | 92
P20-WELL-L00 | P20 - Well Curb | 402.a | MPSB/Str/210 | Str | 2 | 4 | 2024-12-16 | IPC - 09 | 4.32 | Sualkuchi | 92
P20-WELL-L00 | P20 - Well Curb | 402.a | MPSB/Sur/210 | Sur | 3 | 4 | 2024-12-22 | IPC - 09 | 4.32 | Sualkuchi | 92
P20-WELL-L00 | P20 - Well Curb | 402.a | MPSB/Str/231 | Str | 4 | 4 | 2024-12-22 | IPC - 09 | 4.32 | Sualkuchi | 92
P24-WELL-L00 | P24 - Well Curb | 402.a | MPSB/Str/215 | Str | 1 | 4 | 2024-12-17 | IPC - 09 | 4.32 | Sualkuchi | 93
P24-WELL-L00 | P24 - Well Curb | 402.a | MPSB/Str/223 | Str | 2 | 4 | 2024-12-19 | IPC - 09 | 4.32 | Sualkuchi | 93
P24-WELL-L00 | P24 - Well Curb | 402.a | MPSB/Str/253 | Str | 3 | 4 | 2024-12-25 | IPC - 09 | 4.32 | Sualkuchi | 93
P24-WELL-L00 | P24 - Well Curb | 402.a | MPSB/Str/254 | Str | 4 | 4 | 2024-12-25 | IPC - 09 | 4.32 | Sualkuchi | 93
P16-WELL-L00 | P16 - Well Curb | 402.a | MPSB/Str/235 | Str | 1 | 4 | 2024-12-22 | IPC - 09 | 4.32 | Palashbari | 94
P16-WELL-L00 | P16 - Well Curb | 402.a | MPSB/Str/236 | Str | 2 | 4 | 2024-12-23 | IPC - 09 | 4.32 | Palashbari | 94
P16-WELL-L00 | P16 - Well Curb | 402.a | MPSB/Str/276 | Str | 3 | 4 | 2024-12-29 | IPC - 09 | 4.32 | Palashbari | 94
P16-WELL-L00 | P16 - Well Curb | 402.a | MPSB/Str/277 | Str | 4 | 4 | 2024-12-29 | IPC - 09 | 4.32 | Palashbari | 94
P28-WELL-L00 | P28 - Well Curb | 402.a | MPSB/Str/238 | Str | 1 | 4 | 2024-12-23 | IPC - 09 | 4.32 | Sualkuchi | 95
P28-WELL-L00 | P28 - Well Curb | 402.a | MPSB/Str/242 | Str | 2 | 4 | 2024-12-23 | IPC - 09 | 4.32 | Sualkuchi | 95
P28-WELL-L00 | P28 - Well Curb | 402.a | MPSB/Str/268 | Str | 3 | 4 | 2024-12-28 | IPC - 09 | 4.32 | Sualkuchi | 95
P28-WELL-L00 | P28 - Well Curb | 402.a | MPSB/Str/269 | Str | 4 | 4 | 2024-12-28 | IPC - 09 | 4.32 | Sualkuchi | 95
P18-WELL-L00 | P18 - Well Curb | 402.a | MPSB/Str/250 | Str | 1 | 4 | 2024-12-25 | IPC - 09 | 4.32 | Sualkuchi | 96
P18-WELL-L00 | P18 - Well Curb | 402.a | MPSB/Str/264 | Str | 2 | 4 | 2024-12-28 | IPC - 09 | 4.32 | Sualkuchi | 96
P18-WELL-L00 | P18 - Well Curb | 402.a | MPSB/Str/301 | Str | 3 | 4 | 2024-12-31 | IPC - 09 | 4.32 | Sualkuchi | 96
P18-WELL-L00 | P18 - Well Curb | 402.a | MPSB/Str/302 | Str | 4 | 4 | 2024-12-31 | IPC - 09 | 4.32 | Sualkuchi | 96
P8-WELL-L00 | P8 - Well Curb | 402.a | MPSB/Str/261 | Str | 1 | 4 | 2024-12-27 | IPC - 09 | 4.32 | Palashbari | 97
P8-WELL-L00 | P8 - Well Curb | 402.a | MPSB/Str/271 | Str | 2 | 4 | 2024-12-29 | IPC - 09 | 4.32 | Palashbari | 97
P8-WELL-L00 | P8 - Well Curb | 402.a | MPSB/Sur/245 | Sur | 3 | 4 | 2024-12-31 | IPC - 09 | 4.32 | Palashbari | 97
P8-WELL-L00 | P8 - Well Curb | 402.a | MPSB/Sur/246 | Sur | 4 | 4 | 2024-12-31 | IPC - 09 | 4.32 | Palashbari | 97
P25-WELL-L00 | P25 - Well Curb | 402.a | MPSB/Str/267 | Str | 1 | 2 | 2024-12-28 | IPC - 09 | 6.04 | Sualkuchi | 98
P25-WELL-L00 | P25 - Well Curb | 402.a | MPSB/Str/289 | Str | 2 | 2 | 2024-12-30 | IPC - 09 | 6.04 | Sualkuchi | 98
P7-WELL-L00 | P7 - Well Curb | 402.a | MPSB/Str/299 | Str | 1 | 4 | 2024-12-31 | IPC - 10 | 6.04 | Palashbari | 99
P7-WELL-L00 | P7 - Well Curb | 402.a | MPSB/Str/334 | Str | 2 | 4 | 2025-01-08 | IPC - 10 | 6.04 | Palashbari | 99
P7-WELL-L00 | P7 - Well Curb | 402.a | MPSB/Sur/316 | Sur | 3 | 4 | 2025-01-17 | IPC - 10 | 6.04 | Palashbari | 99
P7-WELL-L00 | P7 - Well Curb | 402.a | MPSB/Sur/317 | Sur | 4 | 4 | 2025-01-17 | IPC - 10 | 6.04 | Palashbari | 99
P9-WELL-L00 | P9 - Well Curb | 402.a | MPSB/Str/408 | Str | 1 | 4 | 2025-01-22 | IPC - 10 | 6.04 | Palashbari | 100
P9-WELL-L00 | P9 - Well Curb | 402.a | MPSB/Str/424 | Str | 2 | 4 | 2025-01-24 | IPC - 10 | 6.04 | Palashbari | 100
P9-WELL-L00 | P9 - Well Curb | 402.a | MPSB/Sur/396 | Sur | 3 | 4 | 2025-01-31 | IPC - 10 | 6.04 | Palashbari | 100
P9-WELL-L00 | P9 - Well Curb | 402.a | MPSB/Sur/397 | Sur | 4 | 4 | 2025-01-31 | IPC - 10 | 6.04 | Palashbari | 100
P17-WELL-L00 | P17 - Well Curb | 402.a | MPSB/Str/439 | Str | 1 | 2 | 2025-01-27 | IPC - 10 | 6.04 | Palashbari | 101
P17-WELL-L00 | P17 - Well Curb | 402.a | MPSB/Str/455 | Str | 2 | 2 | 2025-01-30 | IPC - 10 | 6.04 | Palashbari | 101
P19-WELL-L00 | P19 - Well Curb | 402.a | MPSB/Str/359 | Str | 1 | 3 | 2025-01-13 | IPC - 10 | 6.04 | Sualkuchi | 102
P19-WELL-L00 | P19 - Well Curb | 402.a | MPSB/Str/381 | Str | 2 | 3 | 2025-01-18 | IPC - 10 | 6.04 | Sualkuchi | 102
P19-WELL-L00 | P19 - Well Curb | 402.a | MPSB/Sur/380 | Sur | 3 | 3 | 2025-01-28 | IPC - 10 | 6.04 | Sualkuchi | 102
P10-WELL-L00 | P10 - Well Curb | 402.a | MPSB/Str/489 | Str | 1 | 5 | 2025-02-05 | IPC - 11 | 4.32 | Palashbari | 103
P10-WELL-L00 | P10 - Well Curb | 402.a | MPSB/Sur/426 | Sur | 2 | 5 | 2025-02-06 | IPC - 11 | 4.32 | Palashbari | 103
P10-WELL-L00 | P10 - Well Curb | 402.a | MPSB/Str/494 | Str | 3 | 5 | 2025-02-06 | IPC - 11 | 4.32 | Palashbari | 103
P10-WELL-L00 | P10 - Well Curb | 402.a | MPSB/Sur/453 | Sur | 4 | 5 | 2025-02-11 | IPC - 11 | 4.32 | Palashbari | 103
P10-WELL-L00 | P10 - Well Curb | 402.a | MPSB/Sur/454 | Sur | 5 | 5 | 2025-02-11 | IPC - 11 | 4.32 | Palashbari | 103
P12-WELL-L00 | P12 - Well Curb | 402.a | MPSB/Str/628 | Str | 1 | 3 | 2025-02-25 | IPC - 11 | 4.48 | Palashbari | 104
P12-WELL-L00 | P12 - Well Curb | 402.a | MPSB/Sur/581 | Sur | 2 | 3 | 2025-02-27 | IPC - 11 | 4.48 | Palashbari | 104
P12-WELL-L00 | P12 - Well Curb | 402.a | MPSB/Str/661 | Str | 3 | 3 | 2025-02-27 | IPC - 11 | 4.48 | Palashbari | 104
P14-WELL-L00 | P14 - Well Curb | 402.a | MPSB/Str/566 | Str | 1 | 5 | 2025-02-18 | IPC - 11 | 4.32 | Palashbari | 105
P14-WELL-L00 | P14 - Well Curb | 402.a | MPSB/Sur/500 | Sur | 2 | 5 | 2025-02-19 | IPC - 11 | 4.32 | Palashbari | 105
P14-WELL-L00 | P14 - Well Curb | 402.a | MPSB/Str/592 | Str | 3 | 5 | 2025-02-21 | IPC - 11 | 4.32 | Palashbari | 105
P14-WELL-L00 | P14 - Well Curb | 402.a | MPSB/Sur/551 | Sur | 4 | 5 | 2025-02-25 | IPC - 11 | 4.32 | Palashbari | 105
P14-WELL-L00 | P14 - Well Curb | 402.a | MPSB/Sur/552 | Sur | 5 | 5 | 2025-02-25 | IPC - 11 | 4.32 | Palashbari | 105
P15-WELL-L00 | P15 - Well Curb | 402.a | MPSB/Str/508 | Str | 1 | 5 | 2025-02-09 | IPC - 11 | 6.2 | Palashbari | 106
P15-WELL-L00 | P15 - Well Curb | 402.a | MPSB/Sur/457 | Sur | 2 | 5 | 2025-02-12 | IPC - 11 | 6.2 | Palashbari | 106
P15-WELL-L00 | P15 - Well Curb | 402.a | MPSB/Str/526 | Str | 3 | 5 | 2025-02-12 | IPC - 11 | 6.2 | Palashbari | 106
P15-WELL-L00 | P15 - Well Curb | 402.a | MPSB/Sur/515 | Sur | 4 | 5 | 2025-02-20 | IPC - 11 | 6.2 | Palashbari | 106
P15-WELL-L00 | P15 - Well Curb | 402.a | MPSB/Sur/536 | Sur | 5 | 5 | 2025-02-23 | IPC - 11 | 6.2 | Palashbari | 106
P21-WELL-L00 | P21 - Well Curb | 402.a | MPSB/Str/513 | Str | 1 | 4 | 2025-02-10 | IPC - 11 | 6.2 | Sualkuchi | 107
P21-WELL-L00 | P21 - Well Curb | 402.a | MPSB/Str/615 | Str | 2 | 4 | 2025-02-24 | IPC - 11 | 6.2 | Sualkuchi | 107
P21-WELL-L00 | P21 - Well Curb | 402.a | MPSB/Sur/600 | Sur | 3 | 4 | 2025-02-28 | IPC - 11 | 6.2 | Sualkuchi | 107
P21-WELL-L00 | P21 - Well Curb | 402.a | MPSB/Sur/601 | Sur | 4 | 4 | 2025-02-28 | IPC - 11 | 6.2 | Sualkuchi | 107
P23-WELL-L00 | P23 - Well Curb | 402.a | MPSB/Str/633 | Str | 1 | 2 | 2025-02-25 | IPC - 11 | 6.2 | Sualkuchi | 108
P23-WELL-L00 | P23 - Well Curb | 402.a | MPSB/Str/686 | Str | 2 | 2 | 2025-02-28 | IPC - 11 | 6.2 | Sualkuchi | 108
P29-WELL-L00 | P29 - Well Curb | 402.a | MPSB/Str/500 | Str | 1 | 4 | 2025-02-07 | IPC - 11 | 6.2 | Sualkuchi | 109
P29-WELL-L00 | P29 - Well Curb | 402.a | MPSB/Str/523 | Str | 2 | 4 | 2025-02-10 | IPC - 11 | 6.2 | Sualkuchi | 109
P29-WELL-L00 | P29 - Well Curb | 402.a | MPSB/Sur/487 | Sur | 3 | 4 | 2025-02-17 | IPC - 11 | 6.2 | Sualkuchi | 109
P29-WELL-L00 | P29 - Well Curb | 402.a | MPSB/Sur/493 | Sur | 4 | 4 | 2025-02-18 | IPC - 11 | 6.2 | Sualkuchi | 109
P27-WELL-L00 | P27 - Well Curb | 402.a | MPSB/Str/748 | Str | 1 | 4 | 2025-03-07 | IPC - 13 | 6.2 | Sualkuchi | 110
P27-WELL-L00 | P27 - Well Curb | 402.a | MPSB/Str/832 | Str | 2 | 4 | 2025-03-19 | IPC - 13 | 6.2 | Sualkuchi | 110
P27-WELL-L00 | P27 - Well Curb | 402.a | MPSB/Sur/819 | Sur | 3 | 4 | 2025-03-28 | IPC - 13 | 6.2 | Sualkuchi | 110
P27-WELL-L00 | P27 - Well Curb | 402.a | MPSB/Sur/821 | Sur | 4 | 4 | 2025-03-28 | IPC - 13 | 6.2 | Sualkuchi | 110
P30-WELL-L00 | P30 - Well Curb | 402.a | MPSB/Str/2757 | Str | 1 | 4 | 2025-11-10 | IPC - 23 | 4.48 | Sualkuchi | 111
P30-WELL-L00 | P30 - Well Curb | 402.a | MPSB/Sur/2164 | Sur | 2 | 4 | 2025-11-10 | IPC - 23 | 4.48 | Sualkuchi | 111
P30-WELL-L00 | P30 - Well Curb | 402.a | MPSB/Str/2758 | Str | 3 | 4 | 2025-11-10 | IPC - 23 | 4.48 | Sualkuchi | 111
P30-WELL-L00 | P30 - Well Curb | 402.a | MPSB/Sur/2225 | Sur | 4 | 4 | 2025-11-19 | IPC - 23 | 4.48 | Sualkuchi | 111
P11-WELL-L00 | P11 - Well Curb | 402.a | MPSB/Str/3534 | Str | 1 | 5 | 2026-01-16 | IPC - 26 | 6.2 | Palashbari | 112
P11-WELL-L00 | P11 - Well Curb | 402.a | MPSB/Sur/2710 | Sur | 2 | 5 | 2026-01-19 | IPC - 26 | 6.2 | Palashbari | 112
P11-WELL-L00 | P11 - Well Curb | 402.a | MPSB/Str/3567 | Str | 3 | 5 | 2026-01-19 | IPC - 26 | 6.2 | Palashbari | 112
P11-WELL-L00 | P11 - Well Curb | 402.a | MPSB/Sur/2782 | Sur | 4 | 5 | 2026-01-28 | IPC - 26 | 6.2 | Palashbari | 112
P11-WELL-L00 | P11 - Well Curb | 402.a | MPSB/Sur/2793 | Sur | 5 | 5 | 2026-01-29 | IPC - 26 | 6.2 | Palashbari | 112
P13-WELL-L00 | P13 - Well Curb | 402.a | MPSB/Str/3607 | Str | 1 | 4 | 2026-01-22 | IPC - 26 | 6.2 | Palashbari | 113
P13-WELL-L00 | P13 - Well Curb | 402.a | MPSB/Sur/2756 | Sur | 2 | 4 | 2026-01-24 | IPC - 26 | 6.2 | Palashbari | 113
P13-WELL-L00 | P13 - Well Curb | 402.a | MPSB/Str/3637 | Str | 3 | 4 | 2026-01-24 | IPC - 26 | 6.2 | Palashbari | 113
P13-WELL-L00 | P13 - Well Curb | 402.a | MPSB/Sur/2819 | Sur | 4 | 4 | 2026-01-31 | IPC - 26 | 6.2 | Palashbari | 113
P14(N)-WELL-L00 | P14(N) - Well Curb | 402.a | MPSB/Str/3229 | Str | 1 | 5 | 2025-12-22 | IPC - 26 | 4.48 | Palashbari | 116
P14(N)-WELL-L00 | P14(N) - Well Curb | 402.a | MPSB/Sur/2510 | Sur | 2 | 5 | 2025-12-27 | IPC - 26 | 4.48 | Palashbari | 116
P14(N)-WELL-L00 | P14(N) - Well Curb | 402.a | MPSB/Str/3292 | Str | 3 | 5 | 2025-12-27 | IPC - 26 | 4.48 | Palashbari | 116
P14(N)-WELL-L00 | P14(N) - Well Curb | 402.a | MPSB/Sur/2582 | Sur | 4 | 5 | 2026-01-01 | IPC - 26 | 4.48 | Palashbari | 116
P14(N)-WELL-L00 | P14(N) - Well Curb | 402.a | MPSB/Sur/2592 | Sur | 5 | 5 | 2026-01-03 | IPC - 26 | 4.48 | Palashbari | 116
P12(A)-WELL-L00 | P12(A) - Well Curb | 402.a | MPSB/Str/3668 | Str | 1 | 5 | 2026-01-29 | IPC - 33 | 4.48 | Palashbari | 117
P12(A)-WELL-L00 | P12(A) - Well Curb | 402.a | MPSB/Sur/2802 | Sur | 2 | 5 | 2026-01-30 | IPC - 33 | 4.48 | Palashbari | 117
P12(A)-WELL-L00 | P12(A) - Well Curb | 402.a | MPSB/Str/3685 | Str | 3 | 5 | 2026-01-30 | IPC - 33 | 4.48 | Palashbari | 117
P12(A)-WELL-L00 | P12(A) - Well Curb | 402.a | MPSB/Sur/2848 | Sur | 4 | 5 | 2026-02-03 | IPC - 33 | 4.48 | Palashbari | 117
P12(A)-WELL-L00 | P12(A) - Well Curb | 402.a | MPSB/Sur/2853 | Sur | 5 | 5 | 2026-02-04 | IPC - 33 | 4.48 | Palashbari | 117
P22-WELL-L01 | P22 - 1st Lift | 402.a | MPSB/Sur/180 | Sur | 1 | 4 | 2024-12-06 | IPC - 09 | 2.65 | Sualkuchi | 119
P22-WELL-L01 | P22 - 1st Lift | 402.a | MPSB/Str/192 | Str | 2 | 4 | 2024-12-09 | IPC - 09 | 2.65 | Sualkuchi | 119
P22-WELL-L01 | P22 - 1st Lift | 402.a | MPSB/Str/193 | Str | 3 | 4 | 2024-12-09 | IPC - 09 | 2.65 | Sualkuchi | 119
P22-WELL-L01 | P22 - 1st Lift | 402.a | MPSB/Str/199 | Str | 4 | 4 | 2024-12-12 | IPC - 09 | 2.65 | Sualkuchi | 119
P6-WELL-L01 | P6 - 1st Lift | 402.a | MPSB/Str/207 | Str | 1 | 3 | 2024-12-14 | IPC - 09 | 2.65 | Palashbari | 120
P6-WELL-L01 | P6 - 1st Lift | 402.a | MPSB/Str/208 | Str | 2 | 3 | 2024-12-14 | IPC - 09 | 2.65 | Palashbari | 120
P6-WELL-L01 | P6 - 1st Lift | 402.a | MPSB/Str/221 | Str | 3 | 3 | 2024-12-18 | IPC - 09 | 2.65 | Palashbari | 120
P26-WELL-L01 | P26 - 1st Lift | 402.a | MPSB/Sur/206 | Sur | 1 | 4 | 2024-12-19 | IPC - 09 | 2.65 | Sualkuchi | 121
P26-WELL-L01 | P26 - 1st Lift | 402.a | MPSB/Str/224 | Str | 2 | 4 | 2024-12-19 | IPC - 09 | 2.65 | Sualkuchi | 121
P26-WELL-L01 | P26 - 1st Lift | 402.a | MPSB/Str/225 | Str | 3 | 4 | 2024-12-19 | IPC - 09 | 2.65 | Sualkuchi | 121
P26-WELL-L01 | P26 - 1st Lift | 402.a | MPSB/Str/232 | Str | 4 | 4 | 2024-12-22 | IPC - 09 | 2.65 | Sualkuchi | 121
P20-WELL-L01 | P20 - 1st Lift | 402.a | MPSB/Sur/219 | Sur | 1 | 4 | 2024-12-25 | IPC - 09 | 2.65 | Sualkuchi | 122
P20-WELL-L01 | P20 - 1st Lift | 402.a | MPSB/Str/251 | Str | 2 | 4 | 2024-12-25 | IPC - 09 | 2.65 | Sualkuchi | 122
P20-WELL-L01 | P20 - 1st Lift | 402.a | MPSB/Str/252 | Str | 3 | 4 | 2024-12-25 | IPC - 09 | 2.65 | Sualkuchi | 122
P20-WELL-L01 | P20 - 1st Lift | 402.a | MPSB/Str/280 | Str | 4 | 4 | 2024-12-29 | IPC - 09 | 2.65 | Sualkuchi | 122
P24-WELL-L01 | P24 - 1st Lift | 402.a | MPSB/Sur/227 | Sur | 1 | 4 | 2024-12-28 | IPC - 09 | 2.65 | Sualkuchi | 123
P24-WELL-L01 | P24 - 1st Lift | 402.a | MPSB/Str/265 | Str | 2 | 4 | 2024-12-28 | IPC - 09 | 2.65 | Sualkuchi | 123
P24-WELL-L01 | P24 - 1st Lift | 402.a | MPSB/Str/266 | Str | 3 | 4 | 2024-12-28 | IPC - 09 | 2.65 | Sualkuchi | 123
P24-WELL-L01 | P24 - 1st Lift | 402.a | MPSB/Str/294 | Str | 4 | 4 | 2024-12-30 | IPC - 09 | 2.65 | Sualkuchi | 123
P7-WELL-L01 | P7 - 1st Lift | 402.a | MPSB/Str/450 | Str | 1 | 3 | 2025-01-28 | IPC - 10 | 3.31 | Palashbari | 124
P7-WELL-L01 | P7 - 1st Lift | 402.a | MPSB/Str/467 | Str | 2 | 3 | 2025-01-30 | IPC - 10 | 3.31 | Palashbari | 124
P7-WELL-L01 | P7 - 1st Lift | 402.a | MPSB/Sur/390 | Sur | 3 | 3 | 2025-01-30 | IPC - 10 | 3.31 | Palashbari | 124
P8-WELL-L01 | P8 - 1st Lift | 402.a | MPSB/Str/335 | Str | 1 | 4 | 2025-01-08 | IPC - 10 | 2.65 | Palashbari | 125
P8-WELL-L01 | P8 - 1st Lift | 402.a | MPSB/Str/352 | Str | 2 | 4 | 2025-01-11 | IPC - 10 | 2.65 | Palashbari | 125
P8-WELL-L01 | P8 - 1st Lift | 402.a | MPSB/Sur/288 | Sur | 3 | 4 | 2025-01-11 | IPC - 10 | 2.65 | Palashbari | 125
P8-WELL-L01 | P8 - 1st Lift | 402.a | MPSB/Sur/300 | Sur | 4 | 4 | 2025-01-14 | IPC - 10 | 2.65 | Palashbari | 125
P16-WELL-L01 | P16 - 1st Lift | 402.a | MPSB/Str/331 | Str | 1 | 4 | 2025-01-08 | IPC - 10 | 2.65 | Palashbari | 126
P16-WELL-L01 | P16 - 1st Lift | 402.a | MPSB/Sur/270 | Sur | 2 | 4 | 2025-01-08 | IPC - 10 | 2.65 | Palashbari | 126
P16-WELL-L01 | P16 - 1st Lift | 402.a | MPSB/Str/349 | Str | 3 | 4 | 2025-01-11 | IPC - 10 | 2.65 | Palashbari | 126
P16-WELL-L01 | P16 - 1st Lift | 402.a | MPSB/Sur/309 | Sur | 4 | 4 | 2025-01-17 | IPC - 10 | 2.65 | Palashbari | 126
P18-WELL-L01 | P18 - 1st Lift | 402.a | MPSB/Str/346 | Str | 1 | 4 | 2025-01-10 | IPC - 10 | 2.65 | Sualkuchi | 127
P18-WELL-L01 | P18 - 1st Lift | 402.a | MPSB/Sur/284 | Sur | 2 | 4 | 2025-01-10 | IPC - 10 | 2.65 | Sualkuchi | 127
P18-WELL-L01 | P18 - 1st Lift | 402.a | MPSB/Str/353 | Str | 3 | 4 | 2025-01-12 | IPC - 10 | 2.65 | Sualkuchi | 127
P18-WELL-L01 | P18 - 1st Lift | 402.a | MPSB/Sur/306 | Sur | 4 | 4 | 2025-01-16 | IPC - 10 | 2.65 | Sualkuchi | 127
P25-WELL-L01 | P25 - 1st Lift | 402.a | MPSB/Str/388 | Str | 1 | 4 | 2025-01-20 | IPC - 10 | 3.31 | Sualkuchi | 128
P25-WELL-L01 | P25 - 1st Lift | 402.a | MPSB/Sur/328 | Sur | 2 | 4 | 2025-01-20 | IPC - 10 | 3.31 | Sualkuchi | 128
P25-WELL-L01 | P25 - 1st Lift | 402.a | MPSB/Str/389 | Str | 3 | 4 | 2025-01-20 | IPC - 10 | 3.31 | Sualkuchi | 128
P25-WELL-L01 | P25 - 1st Lift | 402.a | MPSB/Sur/354 | Sur | 4 | 4 | 2025-01-24 | IPC - 10 | 3.31 | Sualkuchi | 128
P28-WELL-L01 | P28 - 1st Lift | 402.a | MPSB/Str/336 | Str | 1 | 4 | 2025-01-08 | IPC - 10 | 2.65 | Sualkuchi | 129
P28-WELL-L01 | P28 - 1st Lift | 402.a | MPSB/Sur/271 | Sur | 2 | 4 | 2025-01-08 | IPC - 10 | 2.65 | Sualkuchi | 129
P28-WELL-L01 | P28 - 1st Lift | 402.a | MPSB/Str/337 | Str | 3 | 4 | 2025-01-08 | IPC - 10 | 2.65 | Sualkuchi | 129
P28-WELL-L01 | P28 - 1st Lift | 402.a | MPSB/Sur/291 | Sur | 4 | 4 | 2025-01-12 | IPC - 10 | 2.65 | Sualkuchi | 129
P9-WELL-L01 | P9 - 1st Lift | 402.a | MPSB/Str/538 | Str | 1 | 4 | 2025-02-14 | IPC - 11 | 2 | Palashbari | 130
P9-WELL-L01 | P9 - 1st Lift | 402.a | MPSB/Sur/471 | Sur | 2 | 4 | 2025-02-15 | IPC - 11 | 2 | Palashbari | 130
P9-WELL-L01 | P9 - 1st Lift | 402.a | MPSB/Str/549 | Str | 3 | 4 | 2025-02-15 | IPC - 11 | 2 | Palashbari | 130
P9-WELL-L01 | P9 - 1st Lift | 402.a | MPSB/Sur/534 | Sur | 4 | 4 | 2025-02-23 | IPC - 11 | 2 | Palashbari | 130
P10-WELL-L01 | P10 - 1st Lift | 402.a | MPSB/Str/577 | Str | 1 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Palashbari | 131
P10-WELL-L01 | P10 - 1st Lift | 402.a | MPSB/Sur/508 | Sur | 2 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Palashbari | 131
P10-WELL-L01 | P10 - 1st Lift | 402.a | MPSB/Str/578 | Str | 3 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Palashbari | 131
P10-WELL-L01 | P10 - 1st Lift | 402.a | MPSB/Sur/545 | Sur | 4 | 4 | 2025-02-24 | IPC - 11 | 2.5 | Palashbari | 131
P14-WELL-L01 | P14 - 1st Lift | 402.a | MPSB/Str/668 | Str | 1 | 3 | 2025-02-28 | IPC - 11 | 2.65 | Palashbari | 132
P14-WELL-L01 | P14 - 1st Lift | 402.a | MPSB/Sur/591 | Sur | 2 | 3 | 2025-02-28 | IPC - 11 | 2.65 | Palashbari | 132
P14-WELL-L01 | P14 - 1st Lift | 402.a | MPSB/Str/669 | Str | 3 | 3 | 2025-02-28 | IPC - 11 | 2.65 | Palashbari | 132
P15-WELL-L01 | P15 - 1st Lift | 402.a | MPSB/Str/670 | Str | 1 | 3 | 2025-02-28 | IPC - 11 | 2.66 | Palashbari | 133
P15-WELL-L01 | P15 - 1st Lift | 402.a | MPSB/Sur/592 | Sur | 2 | 3 | 2025-02-28 | IPC - 11 | 2.66 | Palashbari | 133
P15-WELL-L01 | P15 - 1st Lift | 402.a | MPSB/Str/671 | Str | 3 | 3 | 2025-02-28 | IPC - 11 | 2.66 | Palashbari | 133
P17-WELL-L01 | P17 - 1st Lift | 402.a | MPSB/Str/602 | Str | 1 | 4 | 2025-02-22 | IPC - 11 | 2.16 | Sualkuchi | 134
P17-WELL-L01 | P17 - 1st Lift | 402.a | MPSB/Sur/529 | Sur | 2 | 4 | 2025-02-22 | IPC - 11 | 2.16 | Sualkuchi | 134
P17-WELL-L01 | P17 - 1st Lift | 402.a | MPSB/Str/603 | Str | 3 | 4 | 2025-02-22 | IPC - 11 | 2.16 | Sualkuchi | 134
P17-WELL-L01 | P17 - 1st Lift | 402.a | MPSB/Sur/583 | Sur | 4 | 4 | 2025-02-27 | IPC - 11 | 2.16 | Sualkuchi | 134
P19-WELL-L01 | P19 - 1st Lift | 402.a | MPSB/Str/546 | Str | 1 | 4 | 2025-02-15 | IPC - 11 | 2.65 | Sualkuchi | 135
P19-WELL-L01 | P19 - 1st Lift | 402.a | MPSB/Sur/480 | Sur | 2 | 4 | 2025-02-17 | IPC - 11 | 2.65 | Sualkuchi | 135
P19-WELL-L01 | P19 - 1st Lift | 402.a | MPSB/Str/562 | Str | 3 | 4 | 2025-02-17 | IPC - 11 | 2.65 | Sualkuchi | 135
P19-WELL-L01 | P19 - 1st Lift | 402.a | MPSB/Sur/511 | Sur | 4 | 4 | 2025-02-20 | IPC - 11 | 2.65 | Sualkuchi | 135
P29-WELL-L01 | P29 - 1st Lift | 402.a | MPSB/Str/657 | Str | 1 | 3 | 2025-02-27 | IPC - 11 | 2 | Sualkuchi | 136
P29-WELL-L01 | P29 - 1st Lift | 402.a | MPSB/Sur/579 | Sur | 2 | 3 | 2025-02-27 | IPC - 11 | 2 | Sualkuchi | 136
P29-WELL-L01 | P29 - 1st Lift | 402.a | MPSB/Str/658 | Str | 3 | 3 | 2025-02-27 | IPC - 11 | 2 | Sualkuchi | 136
P12-WELL-L01 | P12 - 1st Lift | 402.a | MPSB/Sur/682 | Sur | 1 | 4 | 2025-03-10 | IPC - 13 | 2.475 | Palashbari | 137
P12-WELL-L01 | P12 - 1st Lift | 402.a | MPSB/Str/771 | Str | 2 | 4 | 2025-03-10 | IPC - 13 | 2.475 | Palashbari | 137
P12-WELL-L01 | P12 - 1st Lift | 402.a | MPSB/Str/772 | Str | 3 | 4 | 2025-03-10 | IPC - 13 | 2.475 | Palashbari | 137
P12-WELL-L01 | P12 - 1st Lift | 402.a | MPSB/Sur/718 | Sur | 4 | 4 | 2025-03-15 | IPC - 13 | 2.475 | Palashbari | 137
P21-WELL-L01 | P21 - 1st Lift | 402.a | MPSB/Str/802 | Str | 1 | 4 | 2025-03-15 | IPC - 13 | 2 | Sualkuchi | 138
P21-WELL-L01 | P21 - 1st Lift | 402.a | MPSB/Sur/712 | Sur | 2 | 4 | 2025-03-15 | IPC - 13 | 2 | Sualkuchi | 138
P21-WELL-L01 | P21 - 1st Lift | 402.a | MPSB/Str/816 | Str | 3 | 4 | 2025-03-17 | IPC - 13 | 2 | Sualkuchi | 138
P21-WELL-L01 | P21 - 1st Lift | 402.a | MPSB/Sur/760 | Sur | 4 | 4 | 2025-03-22 | IPC - 13 | 2 | Sualkuchi | 138
P23-WELL-L01 | P23 - 1st Lift | 402.a | MPSB/Str/956 | Str | 1 | 4 | 2025-03-29 | IPC - 13 | 2 | Sualkuchi | 139
P23-WELL-L01 | P23 - 1st Lift | 402.a | MPSB/Sur/833 | Sur | 2 | 4 | 2025-03-29 | IPC - 13 | 2 | Sualkuchi | 139
P23-WELL-L01 | P23 - 1st Lift | 402.a | MPSB/Str/957 | Str | 3 | 4 | 2025-03-29 | IPC - 13 | 2 | Sualkuchi | 139
P23-WELL-L01 | P23 - 1st Lift | 402.a | MPSB/Sur/884 | Sur | 4 | 4 | 2025-03-31 | IPC - 13 | 2 | Sualkuchi | 139
P27-WELL-L01 | P27 - 1st Lift | 402.a | MPSB/Str/962 | Str | 1 | 3 | 2025-03-29 | IPC - 13 | 2.5 | Sualkuchi | 140
P27-WELL-L01 | P27 - 1st Lift | 402.a | MPSB/Sur/836 | Sur | 2 | 3 | 2025-03-29 | IPC - 13 | 2.5 | Sualkuchi | 140
P27-WELL-L01 | P27 - 1st Lift | 402.a | MPSB/Str/963 | Str | 3 | 3 | 2025-03-29 | IPC - 13 | 2.5 | Sualkuchi | 140
P30-WELL-L01 | P30 - 1st Lift | 402.a | MPSB/Str/2901 | Str | 1 | 4 | 2025-11-23 | IPC - 23 | 2.5 | Sualkuchi | 141
P30-WELL-L01 | P30 - 1st Lift | 402.a | MPSB/Sur/2251 | Sur | 2 | 4 | 2025-11-23 | IPC - 23 | 2.5 | Sualkuchi | 141
P30-WELL-L01 | P30 - 1st Lift | 402.a | MPSB/Str/2902 | Str | 3 | 4 | 2025-11-23 | IPC - 23 | 2.5 | Sualkuchi | 141
P30-WELL-L01 | P30 - 1st Lift | 402.a | MPSB/Sur/2275 | Sur | 4 | 4 | 2025-11-26 | IPC - 23 | 2.5 | Sualkuchi | 141
P11-WELL-L01 | P11 - 1st Lift | 402.a | MPSB/Str/3715 | Str | 1 | 3 | 2026-01-31 | IPC - 26 | 2.5 | Palashbari | 142
P11-WELL-L01 | P11 - 1st Lift | 402.a | MPSB/Sur/2818 | Sur | 2 | 3 | 2026-01-31 | IPC - 26 | 2.5 | Palashbari | 142
P11-WELL-L01 | P11 - 1st Lift | 402.a | MPSB/Str/3716 | Str | 3 | 3 | 2026-01-31 | IPC - 26 | 2.5 | Palashbari | 142
P14(N)-WELL-L01 | P14(N) - 1st Lift | 402.a | MPSB/Str/3422 | Str | 1 | 4 | 2026-01-05 | IPC - 26 | 2.5 | Palashbari | 145
P14(N)-WELL-L01 | P14(N) - 1st Lift | 402.a | MPSB/Sur/2603 | Sur | 2 | 4 | 2026-01-05 | IPC - 26 | 2.5 | Palashbari | 145
P14(N)-WELL-L01 | P14(N) - 1st Lift | 402.a | MPSB/Str/3423 | Str | 3 | 4 | 2026-01-05 | IPC - 26 | 2.5 | Palashbari | 145
P14(N)-WELL-L01 | P14(N) - 1st Lift | 402.a | MPSB/Sur/2636 | Sur | 4 | 4 | 2026-01-09 | IPC - 26 | 2.5 | Palashbari | 145
P13-WELL-L01 | P13 - 1st Lift | 402.a | MPSB/Str/3771 | Str | 1 | 4 | 2026-02-06 | IPC - 27 | 2.5 | Palashbari | 146
P13-WELL-L01 | P13 - 1st Lift | 402.a | MPSB/Sur/2866 | Sur | 2 | 4 | 2026-02-06 | IPC - 27 | 2.5 | Palashbari | 146
P13-WELL-L01 | P13 - 1st Lift | 402.a | MPSB/Str/3772 | Str | 3 | 4 | 2026-02-06 | IPC - 27 | 2.5 | Palashbari | 146
P13-WELL-L01 | P13 - 1st Lift | 402.a | MPSB/Sur/2908 | Sur | 4 | 4 | 2026-02-11 | IPC - 27 | 2.5 | Palashbari | 146
P12(A)-WELL-L01 | P12(A) - 1st Lift | 402.a | MPSB/Str/3784 | Str | 1 | 4 | 2026-02-07 | IPC - 33 | 2.8 | Palashbari | 147
P12(A)-WELL-L01 | P12(A) - 1st Lift | 402.a | MPSB/Sur/2881 | Sur | 2 | 4 | 2026-02-07 | IPC - 33 | 2.8 | Palashbari | 147
P12(A)-WELL-L01 | P12(A) - 1st Lift | 402.a | MPSB/Str/3785 | Str | 3 | 4 | 2026-02-07 | IPC - 33 | 2.8 | Palashbari | 147
P12(A)-WELL-L01 | P12(A) - 1st Lift | 402.a | MPSB/Sur/2905 | Sur | 4 | 4 | 2026-02-11 | IPC - 33 | 2.8 | Palashbari | 147
P22-WELL-L02 | P22 - 2nd Lift | 402.a | MPSB/Sur/195 | Sur | 1 | 4 | 2024-12-13 | IPC - 09 | 2.5 | Sualkuchi | 149
P22-WELL-L02 | P22 - 2nd Lift | 402.a | MPSB/Str/203 | Str | 2 | 4 | 2024-12-13 | IPC - 09 | 2.5 | Sualkuchi | 149
P22-WELL-L02 | P22 - 2nd Lift | 402.a | MPSB/Str/204 | Str | 3 | 4 | 2024-12-13 | IPC - 09 | 2.5 | Sualkuchi | 149
P22-WELL-L02 | P22 - 2nd Lift | 402.a | MPSB/Str/214 | Str | 4 | 4 | 2024-12-16 | IPC - 09 | 2.5 | Sualkuchi | 149
P6-WELL-L02 | P6 - 2nd Lift | 402.a | MPSB/Sur/211 | Sur | 1 | 4 | 2024-12-22 | IPC - 09 | 2.5 | Palashbari | 150
P6-WELL-L02 | P6 - 2nd Lift | 402.a | MPSB/Str/233 | Str | 2 | 4 | 2024-12-22 | IPC - 09 | 2.5 | Palashbari | 150
P6-WELL-L02 | P6 - 2nd Lift | 402.a | MPSB/Str/234 | Str | 3 | 4 | 2024-12-22 | IPC - 09 | 2.5 | Palashbari | 150
P6-WELL-L02 | P6 - 2nd Lift | 402.a | MPSB/Str/247 | Str | 4 | 4 | 2024-12-25 | IPC - 09 | 2.5 | Palashbari | 150
P26-WELL-L02 | P26 - 2nd Lift | 402.a | MPSB/Sur/220 | Sur | 1 | 4 | 2024-12-25 | IPC - 09 | 2.5 | Sualkuchi | 151
P26-WELL-L02 | P26 - 2nd Lift | 402.a | MPSB/Str/255 | Str | 2 | 4 | 2024-12-25 | IPC - 09 | 2.5 | Sualkuchi | 151
P26-WELL-L02 | P26 - 2nd Lift | 402.a | MPSB/Str/256 | Str | 3 | 4 | 2024-12-25 | IPC - 09 | 2.5 | Sualkuchi | 151
P26-WELL-L02 | P26 - 2nd Lift | 402.a | MPSB/Str/282 | Str | 4 | 4 | 2024-12-29 | IPC - 09 | 2.5 | Sualkuchi | 151
P20-WELL-L02 | P20 - 2nd Lift | 402.a | MPSB/Sur/237 | Sur | 1 | 3 | 2024-12-30 | IPC - 09 | 2.5 | Sualkuchi | 152
P20-WELL-L02 | P20 - 2nd Lift | 402.a | MPSB/Str/287 | Str | 2 | 3 | 2024-12-30 | IPC - 09 | 2.5 | Sualkuchi | 152
P20-WELL-L02 | P20 - 2nd Lift | 402.a | MPSB/Str/288 | Str | 3 | 3 | 2024-12-30 | IPC - 09 | 2.5 | Sualkuchi | 152
P16-WELL-L02 | P16 - 2nd Lift | 402.a | MPSB/Str/394 | Str | 1 | 3 | 2025-01-21 | IPC - 10 | 2.5 | Palashbari | 153
P16-WELL-L02 | P16 - 2nd Lift | 402.a | MPSB/Sur/334 | Sur | 2 | 3 | 2025-01-21 | IPC - 10 | 2.5 | Palashbari | 153
P16-WELL-L02 | P16 - 2nd Lift | 402.a | MPSB/Str/395 | Str | 3 | 3 | 2025-01-21 | IPC - 10 | 2.5 | Palashbari | 153
P18-WELL-L02 | P18 - 2nd Lift | 402.a | MPSB/Str/385 | Str | 1 | 4 | 2025-01-20 | IPC - 10 | 2.5 | Sualkuchi | 154
P18-WELL-L02 | P18 - 2nd Lift | 402.a | MPSB/Sur/325 | Sur | 2 | 4 | 2025-01-20 | IPC - 10 | 2.5 | Sualkuchi | 154
P18-WELL-L02 | P18 - 2nd Lift | 402.a | MPSB/Str/386 | Str | 3 | 4 | 2025-01-20 | IPC - 10 | 2.5 | Sualkuchi | 154
P18-WELL-L02 | P18 - 2nd Lift | 402.a | MPSB/Sur/361 | Sur | 4 | 4 | 2025-01-25 | IPC - 10 | 2.5 | Sualkuchi | 154
P24-WELL-L02 | P24 - 2nd Lift | 402.a | MPSB/Str/305 | Str | 1 | 4 | 2024-12-31 | IPC - 10 | 2.5 | Sualkuchi | 155
P24-WELL-L02 | P24 - 2nd Lift | 402.a | MPSB/Sur/250 | Sur | 2 | 4 | 2024-12-31 | IPC - 10 | 2.5 | Sualkuchi | 155
P24-WELL-L02 | P24 - 2nd Lift | 402.a | MPSB/Str/306 | Str | 3 | 4 | 2024-12-31 | IPC - 10 | 2.5 | Sualkuchi | 155
P24-WELL-L02 | P24 - 2nd Lift | 402.a | MPSB/Sur/283 | Sur | 4 | 4 | 2025-01-10 | IPC - 10 | 2.5 | Sualkuchi | 155
P28-WELL-L02 | P28 - 2nd Lift | 402.a | MPSB/Str/374 | Str | 1 | 4 | 2025-01-17 | IPC - 10 | 2.5 | Sualkuchi | 156
P28-WELL-L02 | P28 - 2nd Lift | 402.a | MPSB/Sur/313 | Sur | 2 | 4 | 2025-01-17 | IPC - 10 | 2.5 | Sualkuchi | 156
P28-WELL-L02 | P28 - 2nd Lift | 402.a | MPSB/Str/375 | Str | 3 | 4 | 2025-01-17 | IPC - 10 | 2.5 | Sualkuchi | 156
P28-WELL-L02 | P28 - 2nd Lift | 402.a | MPSB/Sur/326 | Sur | 4 | 4 | 2025-01-20 | IPC - 10 | 2.5 | Sualkuchi | 156
P8-WELL-L02 | P8 - 2nd Lift | 402.a | MPSB/Str/392 | Str | 1 | 4 | 2025-01-20 | IPC - 10 | 2.5 | Palashbari | 157
P8-WELL-L02 | P8 - 2nd Lift | 402.a | MPSB/Sur/345 | Sur | 2 | 4 | 2025-01-22 | IPC - 10 | 2.5 | Palashbari | 157
P8-WELL-L02 | P8 - 2nd Lift | 402.a | MPSB/Str/409 | Str | 3 | 4 | 2025-01-22 | IPC - 10 | 2.5 | Palashbari | 157
P8-WELL-L02 | P8 - 2nd Lift | 402.a | MPSB/Sur/394 | Sur | 4 | 4 | 2025-01-31 | IPC - 10 | 2.5 | Palashbari | 157
P25-WELL-L02 | P25 - 2nd Lift | 402.a | MPSB/Str/447 | Str | 1 | 3 | 2025-01-28 | IPC - 10 | 2.5 | Sualkuchi | 158
P25-WELL-L02 | P25 - 2nd Lift | 402.a | MPSB/Sur/378 | Sur | 2 | 3 | 2025-01-28 | IPC - 10 | 2.5 | Sualkuchi | 158
P25-WELL-L02 | P25 - 2nd Lift | 402.a | MPSB/Str/469 | Str | 3 | 3 | 2025-01-30 | IPC - 10 | 2.5 | Sualkuchi | 158
P7-WELL-L02 | P7 - 2nd Lift | 402.a | MPSB/Str/585 | Str | 1 | 3 | 2025-02-21 | IPC - 11 | 2.5 | Palashbari | 159
P7-WELL-L02 | P7 - 2nd Lift | 402.a | MPSB/Sur/518 | Sur | 2 | 3 | 2025-02-21 | IPC - 11 | 2.5 | Palashbari | 159
P7-WELL-L02 | P7 - 2nd Lift | 402.a | MPSB/Str/586 | Str | 3 | 3 | 2025-02-21 | IPC - 11 | 2.5 | Palashbari | 159
P9-WELL-L02 | P9 - 2nd Lift | 402.a | MPSB/Str/563 | Str | 1 | 4 | 2025-02-17 | IPC - 11 | 1.05 | Palashbari | 160
P9-WELL-L02 | P9 - 2nd Lift | 402.a | MPSB/Sur/488 | Sur | 2 | 4 | 2025-02-17 | IPC - 11 | 1.05 | Palashbari | 160
P9-WELL-L02 | P9 - 2nd Lift | 402.a | MPSB/Str/564 | Str | 3 | 4 | 2025-02-17 | IPC - 11 | 1.05 | Palashbari | 160
P9-WELL-L02 | P9 - 2nd Lift | 402.a | MPSB/Sur/535 | Sur | 4 | 4 | 2025-02-23 | IPC - 11 | 1.05 | Palashbari | 160
P10-WELL-L02 | P10 - 2nd Lift | 402.a | MPSB/Str/659 | Str | 1 | 3 | 2025-02-27 | IPC - 11 | 2.5 | Palashbari | 161
P10-WELL-L02 | P10 - 2nd Lift | 402.a | MPSB/Sur/580 | Sur | 2 | 3 | 2025-02-27 | IPC - 11 | 2.5 | Palashbari | 161
P10-WELL-L02 | P10 - 2nd Lift | 402.a | MPSB/Str/660 | Str | 3 | 3 | 2025-02-27 | IPC - 11 | 2.5 | Palashbari | 161
P17-WELL-L02 | P17 - 2nd Lift | 402.a | MPSB/Str/604 | Str | 1 | 4 | 2025-02-22 | IPC - 11 | 1.15 | Sualkuchi | 162
P17-WELL-L02 | P17 - 2nd Lift | 402.a | MPSB/Sur/530 | Sur | 2 | 4 | 2025-02-22 | IPC - 11 | 1.15 | Sualkuchi | 162
P17-WELL-L02 | P17 - 2nd Lift | 402.a | MPSB/Str/605 | Str | 3 | 4 | 2025-02-22 | IPC - 11 | 1.15 | Sualkuchi | 162
P17-WELL-L02 | P17 - 2nd Lift | 402.a | MPSB/Sur/585 | Sur | 4 | 4 | 2025-02-27 | IPC - 11 | 1.15 | Sualkuchi | 162
P19-WELL-L02 | P19 - 2nd Lift | 402.a | MPSB/Str/629 | Str | 1 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 163
P19-WELL-L02 | P19 - 2nd Lift | 402.a | MPSB/Sur/557 | Sur | 2 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 163
P19-WELL-L02 | P19 - 2nd Lift | 402.a | MPSB/Str/630 | Str | 3 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 163
P19-WELL-L02 | P19 - 2nd Lift | 402.a | MPSB/Sur/572 | Sur | 4 | 4 | 2025-02-27 | IPC - 11 | 2.5 | Sualkuchi | 163
P29-WELL-L02 | P29 - 2nd Lift | 402.a | MPSB/Str/695 | Str | 1 | 3 | 2025-02-28 | IPC - 11 | 1.15 | Sualkuchi | 164
P29-WELL-L02 | P29 - 2nd Lift | 402.a | MPSB/Sur/606 | Sur | 2 | 3 | 2025-02-28 | IPC - 11 | 1.15 | Sualkuchi | 164
P29-WELL-L02 | P29 - 2nd Lift | 402.a | MPSB/Str/696 | Str | 3 | 3 | 2025-02-28 | IPC - 11 | 1.15 | Sualkuchi | 164
P12-WELL-L02 | P12 - 2nd Lift | 402.a | MPSB/Str/839 | Str | 1 | 4 | 2025-03-20 | IPC - 13 | 2.5 | Palashbari | 165
P12-WELL-L02 | P12 - 2nd Lift | 402.a | MPSB/Str/840 | Str | 2 | 4 | 2025-03-20 | IPC - 13 | 2.5 | Palashbari | 165
P12-WELL-L02 | P12 - 2nd Lift | 402.a | MPSB/Sur/746 | Sur | 3 | 4 | 2025-03-20 | IPC - 13 | 2.5 | Palashbari | 165
P12-WELL-L02 | P12 - 2nd Lift | 402.a | MPSB/Sur/845 | Sur | 4 | 4 | 2025-03-28 | IPC - 13 | 2.5 | Palashbari | 165 | P12-WELL-L03
P14-WELL-L02 | P14 - 2nd Lift | 402.a | MPSB/Str/799 | Str | 1 | 3 | 2025-03-13 | IPC - 13 | 2.485 | Palashbari | 166
P14-WELL-L02 | P14 - 2nd Lift | 402.a | MPSB/Str/800 | Str | 2 | 3 | 2025-03-13 | IPC - 13 | 2.485 | Palashbari | 166
P14-WELL-L02 | P14 - 2nd Lift | 402.a | MPSB/Sur/707 | Sur | 3 | 3 | 2025-03-13 | IPC - 13 | 2.485 | Palashbari | 166
P15-WELL-L02 | P15 - 2nd Lift | 402.a | MPSB/Str/797 | Str | 1 | 4 | 2025-03-13 | IPC - 13 | 2.49 | Palashbari | 167
P15-WELL-L02 | P15 - 2nd Lift | 402.a | MPSB/Str/798 | Str | 2 | 4 | 2025-03-13 | IPC - 13 | 2.49 | Palashbari | 167
P15-WELL-L02 | P15 - 2nd Lift | 402.a | MPSB/Sur/706 | Sur | 3 | 4 | 2025-03-13 | IPC - 13 | 2.49 | Palashbari | 167
P15-WELL-L02 | P15 - 2nd Lift | 402.a | MPSB/Sur/734 | Sur | 4 | 4 | 2025-03-18 | IPC - 13 | 2.49 | Palashbari | 167
P21-WELL-L02 | P21 - 2nd Lift | 402.a | MPSB/Str/804 | Str | 1 | 4 | 2025-03-15 | IPC - 13 | 1.15 | Sualkuchi | 168
P21-WELL-L02 | P21 - 2nd Lift | 402.a | MPSB/Sur/713 | Sur | 2 | 4 | 2025-03-15 | IPC - 13 | 1.15 | Sualkuchi | 168
P21-WELL-L02 | P21 - 2nd Lift | 402.a | MPSB/Str/820 | Str | 3 | 4 | 2025-03-18 | IPC - 13 | 1.15 | Sualkuchi | 168
P21-WELL-L02 | P21 - 2nd Lift | 402.a | MPSB/Sur/762 | Sur | 4 | 4 | 2025-03-22 | IPC - 13 | 1.15 | Sualkuchi | 168
P23-WELL-L02 | P23 - 2nd Lift | 402.a | MPSB/Str/958 | Str | 1 | 4 | 2025-03-29 | IPC - 13 | 1.15 | Sualkuchi | 169
P23-WELL-L02 | P23 - 2nd Lift | 402.a | MPSB/Sur/834 | Sur | 2 | 4 | 2025-03-29 | IPC - 13 | 1.15 | Sualkuchi | 169
P23-WELL-L02 | P23 - 2nd Lift | 402.a | MPSB/Str/959 | Str | 3 | 4 | 2025-03-29 | IPC - 13 | 1.15 | Sualkuchi | 169
P23-WELL-L02 | P23 - 2nd Lift | 402.a | MPSB/Sur/886 | Sur | 4 | 4 | 2025-03-31 | IPC - 13 | 1.15 | Sualkuchi | 169
P27-WELL-L02 | P27 - 2nd Lift | 402.a | MPSB/Str/1172 | Str | 1 | 4 | 2025-04-17 | IPC - 14 | 2.5 | Sualkuchi | 170
P27-WELL-L02 | P27 - 2nd Lift | 402.a | MPSB/Sur/1015 | Sur | 2 | 4 | 2025-04-17 | IPC - 14 | 2.5 | Sualkuchi | 170
P27-WELL-L02 | P27 - 2nd Lift | 402.a | MPSB/Str/1198 | Str | 3 | 4 | 2025-04-20 | IPC - 14 | 2.5 | Sualkuchi | 170
P27-WELL-L02 | P27 - 2nd Lift | 402.a | MPSB/Sur/1072 | Sur | 4 | 4 | 2025-04-23 | IPC - 14 | 2.5 | Sualkuchi | 170
P30-WELL-L02 | P30 - 2nd Lift | 402.a | MPSB/Str/2970 | Str | 1 | 3 | 2025-11-28 | IPC - 23 | 2.5 | Sualkuchi | 171
P30-WELL-L02 | P30 - 2nd Lift | 402.a | MPSB/Sur/2295 | Sur | 2 | 3 | 2025-11-28 | IPC - 23 | 2.5 | Sualkuchi | 171
P30-WELL-L02 | P30 - 2nd Lift | 402.a | MPSB/Str/2971 | Str | 3 | 3 | 2025-11-28 | IPC - 23 | 2.5 | Sualkuchi | 171
P14(N)-WELL-L02 | P14(N) - 2nd Lift | 402.a | MPSB/Str/3477 | Str | 1 | 4 | 2026-01-10 | IPC - 26 | 2.5 | Palashbari | 174
P14(N)-WELL-L02 | P14(N) - 2nd Lift | 402.a | MPSB/Sur/2646 | Sur | 2 | 4 | 2026-01-10 | IPC - 26 | 2.5 | Palashbari | 174
P14(N)-WELL-L02 | P14(N) - 2nd Lift | 402.a | MPSB/Str/3478 | Str | 3 | 4 | 2026-01-10 | IPC - 26 | 2.5 | Palashbari | 174
P14(N)-WELL-L02 | P14(N) - 2nd Lift | 402.a | MPSB/Sur/2704 | Sur | 4 | 4 | 2026-01-17 | IPC - 26 | 2.5 | Palashbari | 174 | P14(N)-WELL-L03
P11-WELL-L02 | P11 - 2nd Lift | 402.a | MPSB/Str/3809 | Str | 1 | 4 | 2026-02-09 | IPC - 27 | 2.5 | Palashbari | 175
P11-WELL-L02 | P11 - 2nd Lift | 402.a | MPSB/Sur/2894 | Sur | 2 | 4 | 2026-02-09 | IPC - 27 | 2.5 | Palashbari | 175
P11-WELL-L02 | P11 - 2nd Lift | 402.a | MPSB/Str/3810 | Str | 3 | 4 | 2026-02-09 | IPC - 27 | 2.5 | Palashbari | 175
P11-WELL-L02 | P11 - 2nd Lift | 402.a | MPSB/Sur/2924 | Sur | 4 | 4 | 2026-02-13 | IPC - 27 | 2.5 | Palashbari | 175
P13-WELL-L02 | P13 - 2nd Lift | 402.a | MPSB/Str/3848 | Str | 1 | 4 | 2026-02-13 | IPC - 27 | 2.5 | Palashbari | 176
P13-WELL-L02 | P13 - 2nd Lift | 402.a | MPSB/Sur/2922 | Sur | 2 | 4 | 2026-02-13 | IPC - 27 | 2.5 | Palashbari | 176
P13-WELL-L02 | P13 - 2nd Lift | 402.a | MPSB/Str/3849 | Str | 3 | 4 | 2026-02-13 | IPC - 27 | 2.5 | Palashbari | 176
P13-WELL-L02 | P13 - 2nd Lift | 402.a | MPSB/Sur/2948 | Sur | 4 | 4 | 2026-02-17 | IPC - 27 | 2.5 | Palashbari | 176
P12(A)-WELL-L02 | P12(A) - 2nd Lift | 402.a | MPSB/Str/3827 | Str | 1 | 4 | 2026-02-11 | IPC - 33 | 2.8 | Palashbari | 177
P12(A)-WELL-L02 | P12(A) - 2nd Lift | 402.a | MPSB/Sur/2906 | Sur | 2 | 4 | 2026-02-11 | IPC - 33 | 2.8 | Palashbari | 177
P12(A)-WELL-L02 | P12(A) - 2nd Lift | 402.a | MPSB/Str/3828 | Str | 3 | 4 | 2026-02-11 | IPC - 33 | 2.8 | Palashbari | 177
P12(A)-WELL-L02 | P12(A) - 2nd Lift | 402.a | MPSB/Sur/2928 | Sur | 4 | 4 | 2026-02-14 | IPC - 33 | 2.8 | Palashbari | 177
P22-WELL-L03 | P22 - 3rd Lift | 402.a | MPSB/Sur/209 | Sur | 1 | 4 | 2024-12-21 | IPC - 09 | 2.5 | Sualkuchi | 179
P22-WELL-L03 | P22 - 3rd Lift | 402.a | MPSB/Str/229 | Str | 2 | 4 | 2024-12-21 | IPC - 09 | 2.5 | Sualkuchi | 179
P22-WELL-L03 | P22 - 3rd Lift | 402.a | MPSB/Str/230 | Str | 3 | 4 | 2024-12-22 | IPC - 09 | 2.5 | Sualkuchi | 179
P22-WELL-L03 | P22 - 3rd Lift | 402.a | MPSB/Str/270 | Str | 4 | 4 | 2024-12-28 | IPC - 09 | 2.5 | Sualkuchi | 179
P6-WELL-L03 | P6 - 3rd Lift | 402.a | MPSB/Sur/295 | Sur | 1 | 3 | 2024-12-30 | IPC - 09 | 2.5 | Palashbari | 180 | P24-WELL-L03
P6-WELL-L03 | P6 - 3rd Lift | 402.a | MPSB/Str/295 | Str | 2 | 3 | 2024-12-30 | IPC - 09 | 2.5 | Palashbari | 180
P6-WELL-L03 | P6 - 3rd Lift | 402.a | MPSB/Sur/243 | Sur | 3 | 3 | 2024-12-31 | IPC - 09 | 2.5 | Palashbari | 180
P20-WELL-L03 | P20 - 3rd Lift | 402.a | MPSB/Str/338 | Str | 1 | 4 | 2025-01-08 | IPC - 10 | 2.5 | Sualkuchi | 181
P20-WELL-L03 | P20 - 3rd Lift | 402.a | MPSB/Sur/272 | Sur | 2 | 4 | 2025-01-08 | IPC - 10 | 2.5 | Sualkuchi | 181
P20-WELL-L03 | P20 - 3rd Lift | 402.a | MPSB/Str/339 | Str | 3 | 4 | 2025-01-08 | IPC - 10 | 2.5 | Sualkuchi | 181
P20-WELL-L03 | P20 - 3rd Lift | 402.a | MPSB/Sur/312 | Sur | 4 | 4 | 2025-01-17 | IPC - 10 | 2.5 | Sualkuchi | 181
P24-WELL-L03 | P24 - 3rd Lift | 402.a | MPSB/Str/357 | Str | 1 | 4 | 2025-01-13 | IPC - 10 | 2.5 | Sualkuchi | 182
P24-WELL-L03 | P24 - 3rd Lift | 402.a | MPSB/Sur/295 | Sur | 2 | 4 | 2025-01-13 | IPC - 10 | 2.5 | Sualkuchi | 182 | P6-WELL-L03
P24-WELL-L03 | P24 - 3rd Lift | 402.a | MPSB/Str/367 | Str | 3 | 4 | 2025-01-15 | IPC - 10 | 2.5 | Sualkuchi | 182
P24-WELL-L03 | P24 - 3rd Lift | 402.a | MPSB/Sur/370 | Sur | 4 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 182
P26-WELL-L03 | P26 - 3rd Lift | 402.a | MPSB/Str/292 | Str | 1 | 4 | 2024-12-30 | IPC - 10 | 2.5 | Sualkuchi | 183
P26-WELL-L03 | P26 - 3rd Lift | 402.a | MPSB/Sur/240 | Sur | 2 | 4 | 2024-12-30 | IPC - 10 | 2.5 | Sualkuchi | 183
P26-WELL-L03 | P26 - 3rd Lift | 402.a | MPSB/Str/293 | Str | 3 | 4 | 2024-12-30 | IPC - 10 | 2.5 | Sualkuchi | 183
P26-WELL-L03 | P26 - 3rd Lift | 402.a | MPSB/Sur/276 | Sur | 4 | 4 | 2025-01-09 | IPC - 10 | 2.5 | Sualkuchi | 183
P16-WELL-L03 | P16 - 3rd Lift | 402.a | MPSB/Str/431 | Str | 1 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Palashbari | 184
P16-WELL-L03 | P16 - 3rd Lift | 402.a | MPSB/Sur/366 | Sur | 2 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Palashbari | 184
P16-WELL-L03 | P16 - 3rd Lift | 402.a | MPSB/Str/441 | Str | 3 | 4 | 2025-01-28 | IPC - 10 | 2.5 | Palashbari | 184
P16-WELL-L03 | P16 - 3rd Lift | 402.a | MPSB/Sur/389 | Sur | 4 | 4 | 2025-01-30 | IPC - 10 | 2.5 | Palashbari | 184
P18-WELL-L03 | P18 - 3rd Lift | 402.a | MPSB/Str/435 | Str | 1 | 3 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 185
P18-WELL-L03 | P18 - 3rd Lift | 402.a | MPSB/Sur/372 | Sur | 2 | 3 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 185
P18-WELL-L03 | P18 - 3rd Lift | 402.a | MPSB/Str/436 | Str | 3 | 3 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 185
P28-WELL-L03 | P28 - 3rd Lift | 402.a | MPSB/Str/433 | Str | 1 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 186
P28-WELL-L03 | P28 - 3rd Lift | 402.a | MPSB/Sur/369 | Sur | 2 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 186
P28-WELL-L03 | P28 - 3rd Lift | 402.a | MPSB/Str/434 | Str | 3 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 186
P28-WELL-L03 | P28 - 3rd Lift | 402.a | MPSB/Sur/401 | Sur | 4 | 4 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 186
P8-WELL-L03 | P8 - 3rd Lift | 402.a | MPSB/Str/432 | Str | 1 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Palashbari | 187
P8-WELL-L03 | P8 - 3rd Lift | 402.a | MPSB/Sur/379 | Sur | 2 | 4 | 2025-01-28 | IPC - 10 | 2.5 | Palashbari | 187
P8-WELL-L03 | P8 - 3rd Lift | 402.a | MPSB/Str/449 | Str | 3 | 4 | 2025-01-28 | IPC - 10 | 2.5 | Palashbari | 187
P8-WELL-L03 | P8 - 3rd Lift | 402.a | MPSB/Sur/395 | Sur | 4 | 4 | 2025-01-31 | IPC - 10 | 2.5 | Palashbari | 187
P9-WELL-L03 | P9 - 3rd Lift | 402.a | MPSB/Str/704 | Str | 1 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 188
P9-WELL-L03 | P9 - 3rd Lift | 402.a | MPSB/Sur/613 | Sur | 2 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 188
P9-WELL-L03 | P9 - 3rd Lift | 402.a | MPSB/Str/705 | Str | 3 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 188
P10-WELL-L03 | P10 - 3rd Lift | 402.a | MPSB/Str/666 | Str | 1 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 189
P10-WELL-L03 | P10 - 3rd Lift | 402.a | MPSB/Sur/590 | Sur | 2 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 189
P10-WELL-L03 | P10 - 3rd Lift | 402.a | MPSB/Str/667 | Str | 3 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 189
P17-WELL-L03 | P17 - 3rd Lift | 402.a | MPSB/Str/674 | Str | 1 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 190
P17-WELL-L03 | P17 - 3rd Lift | 402.a | MPSB/Sur/594 | Sur | 2 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 190
P17-WELL-L03 | P17 - 3rd Lift | 402.a | MPSB/Str/675 | Str | 3 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 190
P25-WELL-L03 | P25 - 3rd Lift | 402.a | MPSB/Str/544 | Str | 1 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Sualkuchi | 191
P25-WELL-L03 | P25 - 3rd Lift | 402.a | MPSB/Sur/469 | Sur | 2 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Sualkuchi | 191
P25-WELL-L03 | P25 - 3rd Lift | 402.a | MPSB/Str/545 | Str | 3 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Sualkuchi | 191
P25-WELL-L03 | P25 - 3rd Lift | 402.a | MPSB/Sur/503 | Sur | 4 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Sualkuchi | 191
P7-WELL-L03 | P7 - 3rd Lift | 402.a | MPSB/Str/791 | Str | 1 | 4 | 2025-03-12 | IPC - 13 | 2.4 | Palashbari | 192
P7-WELL-L03 | P7 - 3rd Lift | 402.a | MPSB/Str/792 | Str | 2 | 4 | 2025-03-12 | IPC - 13 | 2.4 | Palashbari | 192
P7-WELL-L03 | P7 - 3rd Lift | 402.a | MPSB/Sur/703 | Sur | 3 | 4 | 2025-03-12 | IPC - 13 | 2.4 | Palashbari | 192
P7-WELL-L03 | P7 - 3rd Lift | 402.a | MPSB/Sur/727 | Sur | 4 | 4 | 2025-03-17 | IPC - 13 | 2.4 | Palashbari | 192
P12-WELL-L03 | P12 - 3rd Lift | 402.a | MPSB/Str/893 | Str | 1 | 4 | 2025-03-25 | IPC - 13 | 2.32 | Palashbari | 193
P12-WELL-L03 | P12 - 3rd Lift | 402.a | MPSB/Str/894 | Str | 2 | 4 | 2025-03-25 | IPC - 13 | 2.32 | Palashbari | 193
P12-WELL-L03 | P12 - 3rd Lift | 402.a | MPSB/Sur/784 | Sur | 3 | 4 | 2025-03-25 | IPC - 13 | 2.32 | Palashbari | 193
P12-WELL-L03 | P12 - 3rd Lift | 402.a | MPSB/Sur/845 | Sur | 4 | 4 | 2025-03-29 | IPC - 13 | 2.32 | Palashbari | 193 | P12-WELL-L02
P14-WELL-L03 | P14 - 3rd Lift | 402.a | MPSB/Str/858 | Str | 1 | 3 | 2025-03-22 | IPC - 13 | 2.5 | Palashbari | 194
P14-WELL-L03 | P14 - 3rd Lift | 402.a | MPSB/Str/859 | Str | 2 | 3 | 2025-03-22 | IPC - 13 | 2.5 | Palashbari | 194
P14-WELL-L03 | P14 - 3rd Lift | 402.a | MPSB/Sur/765 | Sur | 3 | 3 | 2025-03-22 | IPC - 13 | 2.5 | Palashbari | 194
P15-WELL-L03 | P15 - 3rd Lift | 402.a | MPSB/Str/886 | Str | 1 | 3 | 2025-03-24 | IPC - 13 | 2.5 | Palashbari | 195
P15-WELL-L03 | P15 - 3rd Lift | 402.a | MPSB/Str/887 | Str | 2 | 3 | 2025-03-24 | IPC - 13 | 2.5 | Palashbari | 195
P15-WELL-L03 | P15 - 3rd Lift | 402.a | MPSB/Sur/777 | Sur | 3 | 3 | 2025-03-24 | IPC - 13 | 2.5 | Palashbari | 195
P19-WELL-L03 | P19 - 3rd Lift | 402.a | MPSB/Str/758 | Str | 1 | 4 | 2025-03-09 | IPC - 13 | 2.51 | Sualkuchi | 196
P19-WELL-L03 | P19 - 3rd Lift | 402.a | MPSB/Sur/673 | Sur | 2 | 4 | 2025-03-09 | IPC - 13 | 2.51 | Sualkuchi | 196 | P19-WELL-L04
P19-WELL-L03 | P19 - 3rd Lift | 402.a | MPSB/Str/759 | Str | 3 | 4 | 2025-03-09 | IPC - 13 | 2.51 | Sualkuchi | 196
P19-WELL-L03 | P19 - 3rd Lift | 402.a | MPSB/Sur/701 | Sur | 4 | 4 | 2025-03-12 | IPC - 13 | 2.51 | Sualkuchi | 196
P21-WELL-L03 | P21 - 3rd Lift | 402.a | MPSB/Str/888 | Str | 1 | 4 | 2025-03-25 | IPC - 13 | 2.5 | Sualkuchi | 197
P21-WELL-L03 | P21 - 3rd Lift | 402.a | MPSB/Sur/780 | Sur | 2 | 4 | 2025-03-25 | IPC - 13 | 2.5 | Sualkuchi | 197
P21-WELL-L03 | P21 - 3rd Lift | 402.a | MPSB/Str/889 | Str | 3 | 4 | 2025-03-25 | IPC - 13 | 2.5 | Sualkuchi | 197
P21-WELL-L03 | P21 - 3rd Lift | 402.a | MPSB/Sur/880 | Sur | 4 | 4 | 2025-03-31 | IPC - 13 | 2.5 | Sualkuchi | 197
P29-WELL-L03 | P29 - 3rd Lift | 402.a | MPSB/Str/784 | Str | 1 | 4 | 2025-03-12 | IPC - 13 | 2.5 | Sualkuchi | 198
P29-WELL-L03 | P29 - 3rd Lift | 402.a | MPSB/Sur/702 | Sur | 2 | 4 | 2025-03-12 | IPC - 13 | 2.5 | Sualkuchi | 198
P29-WELL-L03 | P29 - 3rd Lift | 402.a | MPSB/Str/785 | Str | 3 | 4 | 2025-03-12 | IPC - 13 | 2.5 | Sualkuchi | 198
P29-WELL-L03 | P29 - 3rd Lift | 402.a | MPSB/Sur/724 | Sur | 4 | 4 | 2025-03-16 | IPC - 13 | 2.5 | Sualkuchi | 198
P23-WELL-L03 | P23 - 3rd Lift | 402.a | MPSB/Str/1136 | Str | 1 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Sualkuchi | 199
P23-WELL-L03 | P23 - 3rd Lift | 402.a | MPSB/Sur/997 | Sur | 2 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Sualkuchi | 199
P23-WELL-L03 | P23 - 3rd Lift | 402.a | MPSB/Str/1137 | Str | 3 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Sualkuchi | 199
P23-WELL-L03 | P23 - 3rd Lift | 402.a | MPSB/Sur/1042 | Sur | 4 | 4 | 2025-04-20 | IPC - 14 | 2.5 | Sualkuchi | 199
P27-WELL-L03 | P27 - 3rd Lift | 402.a | MPSB/Str/1289 | Str | 1 | 4 | 2025-04-26 | IPC - 14 | 2.5 | Sualkuchi | 200
P27-WELL-L03 | P27 - 3rd Lift | 402.a | MPSB/Sur/1114 | Sur | 2 | 4 | 2025-04-26 | IPC - 14 | 2.5 | Sualkuchi | 200
P27-WELL-L03 | P27 - 3rd Lift | 402.a | MPSB/Str/1290 | Str | 3 | 4 | 2025-04-26 | IPC - 14 | 2.5 | Sualkuchi | 200
P27-WELL-L03 | P27 - 3rd Lift | 402.a | MPSB/Sur/1143 | Sur | 4 | 4 | 2025-04-29 | IPC - 14 | 2.5 | Sualkuchi | 200
P30-WELL-L03 | P30 - 3rd Lift | 402.a | MPSB/Str/2997 | Str | 1 | 3 | 2025-11-30 | IPC - 23 | 2.5 | Sualkuchi | 201
P30-WELL-L03 | P30 - 3rd Lift | 402.a | MPSB/Sur/2313 | Sur | 2 | 3 | 2025-11-30 | IPC - 23 | 2.5 | Sualkuchi | 201
P30-WELL-L03 | P30 - 3rd Lift | 402.a | MPSB/Str/2998 | Str | 3 | 3 | 2025-11-30 | IPC - 23 | 2.5 | Sualkuchi | 201
P14(N)-WELL-L03 | P14(N) - 3rd Lift | 402.a | MPSB/Str/3519 | Str | 1 | 4 | 2026-01-14 | IPC - 26 | 2.5 | Palashbari | 204
P14(N)-WELL-L03 | P14(N) - 3rd Lift | 402.a | MPSB/Sur/2676 | Sur | 2 | 4 | 2026-01-14 | IPC - 26 | 2.5 | Palashbari | 204
P14(N)-WELL-L03 | P14(N) - 3rd Lift | 402.a | MPSB/Str/3520 | Str | 3 | 4 | 2026-01-14 | IPC - 26 | 2.5 | Palashbari | 204
P14(N)-WELL-L03 | P14(N) - 3rd Lift | 402.a | MPSB/Sur/2704 | Sur | 4 | 4 | 2026-01-17 | IPC - 26 | 2.5 | Palashbari | 204 | P14(N)-WELL-L02
P11-WELL-L03 | P11 - 3rd Lift | 402.a | MPSB/Str/3859 | Str | 1 | 4 | 2026-02-15 | IPC - 27 | 2.5 | Palashbari | 205
P11-WELL-L03 | P11 - 3rd Lift | 402.a | MPSB/Sur/2934 | Sur | 2 | 4 | 2026-02-15 | IPC - 27 | 2.5 | Palashbari | 205
P11-WELL-L03 | P11 - 3rd Lift | 402.a | MPSB/Str/3860 | Str | 3 | 4 | 2026-02-15 | IPC - 27 | 2.5 | Palashbari | 205
P11-WELL-L03 | P11 - 3rd Lift | 402.a | MPSB/Sur/2957 | Sur | 4 | 4 | 2026-02-19 | IPC - 27 | 2.5 | Palashbari | 205
P13-WELL-L03 | P13 - 3rd Lift | 402.a | MPSB/Str/3894 | Str | 1 | 4 | 2026-02-19 | IPC - 27 | 2.5 | Palashbari | 206
P13-WELL-L03 | P13 - 3rd Lift | 402.a | MPSB/Sur/2955 | Sur | 2 | 4 | 2026-02-19 | IPC - 27 | 2.5 | Palashbari | 206
P13-WELL-L03 | P13 - 3rd Lift | 402.a | MPSB/Str/3895 | Str | 3 | 4 | 2026-02-19 | IPC - 27 | 2.5 | Palashbari | 206
P13-WELL-L03 | P13 - 3rd Lift | 402.a | MPSB/Sur/2978 | Sur | 4 | 4 | 2026-02-23 | IPC - 27 | 2.5 | Palashbari | 206
P12(A)-WELL-L03 | P12(A) - 3rd Lift | 402.a | MPSB/Str/3864 | Str | 1 | 4 | 2026-02-16 | IPC - 33 | 2.8 | Palashbari | 207
P12(A)-WELL-L03 | P12(A) - 3rd Lift | 402.a | MPSB/Sur/2939 | Sur | 2 | 4 | 2026-02-16 | IPC - 33 | 2.8 | Palashbari | 207
P12(A)-WELL-L03 | P12(A) - 3rd Lift | 402.a | MPSB/Str/3865 | Str | 3 | 4 | 2026-02-16 | IPC - 33 | 2.8 | Palashbari | 207
P12(A)-WELL-L03 | P12(A) - 3rd Lift | 402.a | MPSB/Sur/2962 | Sur | 4 | 4 | 2026-02-20 | IPC - 33 | 2.8 | Palashbari | 207
P22-WELL-L04 | P22 - 4th Lift | 402.a | MPSB/Sur/223 | Sur | 1 | 4 | 2024-12-26 | IPC - 09 | 2.5 | Sualkuchi | 209
P22-WELL-L04 | P22 - 4th Lift | 402.a | MPSB/Str/259 | Str | 2 | 4 | 2024-12-26 | IPC - 09 | 2.5 | Sualkuchi | 209
P22-WELL-L04 | P22 - 4th Lift | 402.a | MPSB/Str/260 | Str | 3 | 4 | 2024-12-26 | IPC - 09 | 2.5 | Sualkuchi | 209
P22-WELL-L04 | P22 - 4th Lift | 402.a | MPSB/Str/281 | Str | 4 | 4 | 2024-12-29 | IPC - 09 | 2.5 | Sualkuchi | 209
P26-WELL-L04 | P26 - 4th Lift | 402.a | MPSB/Str/355 | Str | 1 | 4 | 2025-01-13 | IPC - 10 | 2.5 | Sualkuchi | 210
P26-WELL-L04 | P26 - 4th Lift | 402.a | MPSB/Sur/292 | Sur | 2 | 4 | 2025-01-13 | IPC - 10 | 2.5 | Sualkuchi | 210
P26-WELL-L04 | P26 - 4th Lift | 402.a | MPSB/Str/366 | Str | 3 | 4 | 2025-01-15 | IPC - 10 | 2.5 | Sualkuchi | 210
P26-WELL-L04 | P26 - 4th Lift | 402.a | MPSB/Sur/322 | Sur | 4 | 4 | 2025-01-18 | IPC - 10 | 2.5 | Sualkuchi | 210
P28-WELL-L04 | P28 - 4th Lift | 402.a | MPSB/Str/472 | Str | 1 | 3 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 211
P28-WELL-L04 | P28 - 4th Lift | 402.a | MPSB/Sur/403 | Sur | 2 | 3 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 211
P28-WELL-L04 | P28 - 4th Lift | 402.a | MPSB/Str/473 | Str | 3 | 3 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 211
P6-WELL-L04 | P6 - 4th Lift | 402.a | MPSB/Str/297 | Str | 1 | 4 | 2024-12-31 | IPC - 10 | 2.5 | Palashbari | 212
P6-WELL-L04 | P6 - 4th Lift | 402.a | MPSB/Str/333 | Str | 2 | 4 | 2025-01-07 | IPC - 10 | 2.5 | Palashbari | 212
P6-WELL-L04 | P6 - 4th Lift | 402.a | MPSB/Sur/274 | Sur | 3 | 4 | 2025-01-07 | IPC - 10 | 2.5 | Palashbari | 212
P6-WELL-L04 | P6 - 4th Lift | 402.a | MPSB/Sur/290 | Sur | 4 | 4 | 2025-01-11 | IPC - 10 | 2.5 | Palashbari | 212
P20-WELL-L04 | P20 - 4th Lift | 402.a | MPSB/Str/420 | Str | 1 | 4 | 2025-01-24 | IPC - 10 | 2.5 | Sualkuchi | 213
P20-WELL-L04 | P20 - 4th Lift | 402.a | MPSB/Sur/352 | Sur | 2 | 4 | 2025-01-24 | IPC - 10 | 2.5 | Sualkuchi | 213
P20-WELL-L04 | P20 - 4th Lift | 402.a | MPSB/Str/421 | Str | 3 | 4 | 2025-01-24 | IPC - 10 | 2.5 | Sualkuchi | 213
P20-WELL-L04 | P20 - 4th Lift | 402.a | MPSB/Sur/392 | Sur | 4 | 4 | 2025-01-29 | IPC - 10 | 2.5 | Sualkuchi | 213
P24-WELL-L04 | P24 - 4th Lift | 402.a | MPSB/Str/396 | Str | 1 | 4 | 2025-01-21 | IPC - 10 | 2.5 | Sualkuchi | 214
P24-WELL-L04 | P24 - 4th Lift | 402.a | MPSB/Sur/335 | Sur | 2 | 4 | 2025-01-21 | IPC - 10 | 2.5 | Sualkuchi | 214
P24-WELL-L04 | P24 - 4th Lift | 402.a | MPSB/Str/397 | Str | 3 | 4 | 2025-01-21 | IPC - 10 | 2.5 | Sualkuchi | 214
P24-WELL-L04 | P24 - 4th Lift | 402.a | MPSB/Sur/371 | Sur | 4 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 214
P18-WELL-L04 | P18 - 4th Lift | 402.a | MPSB/Str/474 | Str | 1 | 3 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 215
P18-WELL-L04 | P18 - 4th Lift | 402.a | MPSB/Sur/404 | Sur | 2 | 3 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 215
P18-WELL-L04 | P18 - 4th Lift | 402.a | MPSB/Str/475 | Str | 3 | 3 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 215
P8-WELL-L04 | P8 - 4th Lift | 402.a | MPSB/Str/509 | Str | 1 | 4 | 2025-02-09 | IPC - 11 | 2.5 | Palashbari | 216
P8-WELL-L04 | P8 - 4th Lift | 402.a | MPSB/Sur/455 | Sur | 2 | 4 | 2025-02-11 | IPC - 11 | 2.5 | Palashbari | 216
P8-WELL-L04 | P8 - 4th Lift | 402.a | MPSB/Str/525 | Str | 3 | 4 | 2025-02-11 | IPC - 11 | 2.5 | Palashbari | 216
P8-WELL-L04 | P8 - 4th Lift | 402.a | MPSB/Sur/537 | Sur | 4 | 4 | 2025-02-23 | IPC - 11 | 2.5 | Palashbari | 216
P16-WELL-L04 | P16 - 4th Lift | 402.a | MPSB/Str/492 | Str | 1 | 4 | 2025-02-06 | IPC - 11 | 2.5 | Palashbari | 217
P16-WELL-L04 | P16 - 4th Lift | 402.a | MPSB/Sur/437 | Sur | 2 | 4 | 2025-02-07 | IPC - 11 | 2.5 | Palashbari | 217
P16-WELL-L04 | P16 - 4th Lift | 402.a | MPSB/Str/503 | Str | 3 | 4 | 2025-02-07 | IPC - 11 | 2.5 | Palashbari | 217
P16-WELL-L04 | P16 - 4th Lift | 402.a | MPSB/Sur/489 | Sur | 4 | 4 | 2025-02-18 | IPC - 11 | 2.5 | Palashbari | 217 | P16-WELL-L05
P25-WELL-L04 | P25 - 4th Lift | 402.a | MPSB/Str/600 | Str | 1 | 4 | 2025-02-22 | IPC - 11 | 2.5 | Sualkuchi | 218
P25-WELL-L04 | P25 - 4th Lift | 402.a | MPSB/Sur/528 | Sur | 2 | 4 | 2025-02-22 | IPC - 11 | 2.5 | Sualkuchi | 218
P25-WELL-L04 | P25 - 4th Lift | 402.a | MPSB/Str/601 | Str | 3 | 4 | 2025-02-22 | IPC - 11 | 2.5 | Sualkuchi | 218
P25-WELL-L04 | P25 - 4th Lift | 402.a | MPSB/Sur/561 | Sur | 4 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 218
P7-WELL-L04 | P7 - 4th Lift | 402.a | MPSB/Str/932 | Str | 1 | 3 | 2025-03-27 | IPC - 13 | 2.5 | Palashbari | 219
P7-WELL-L04 | P7 - 4th Lift | 402.a | MPSB/Str/933 | Str | 2 | 3 | 2025-03-27 | IPC - 13 | 2.5 | Palashbari | 219
P7-WELL-L04 | P7 - 4th Lift | 402.a | MPSB/Sur/809 | Sur | 3 | 3 | 2025-03-27 | IPC - 13 | 2.5 | Palashbari | 219
P9-WELL-L04 | P9 - 4th Lift | 402.a | MPSB/Str/827 | Str | 1 | 4 | 2025-03-18 | IPC - 13 | 2.61 | Palashbari | 220
P9-WELL-L04 | P9 - 4th Lift | 402.a | MPSB/Str/828 | Str | 2 | 4 | 2025-03-18 | IPC - 13 | 2.61 | Palashbari | 220
P9-WELL-L04 | P9 - 4th Lift | 402.a | MPSB/Sur/738 | Sur | 3 | 4 | 2025-03-18 | IPC - 13 | 2.61 | Palashbari | 220
P9-WELL-L04 | P9 - 4th Lift | 402.a | MPSB/Sur/855 | Sur | 4 | 4 | 2025-03-30 | IPC - 13 | 2.61 | Palashbari | 220
P10-WELL-L04 | P10 - 4th Lift | 402.a | MPSB/Str/837 | Str | 1 | 3 | 2025-03-20 | IPC - 13 | 2.615 | Palashbari | 221
P10-WELL-L04 | P10 - 4th Lift | 402.a | MPSB/Str/838 | Str | 2 | 3 | 2025-03-20 | IPC - 13 | 2.615 | Palashbari | 221
P10-WELL-L04 | P10 - 4th Lift | 402.a | MPSB/Sur/745 | Sur | 3 | 3 | 2025-03-20 | IPC - 13 | 2.615 | Palashbari | 221
P12-WELL-L04 | P12 - 4th Lift | 402.a | MPSB/Str/999 | Str | 1 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 222
P12-WELL-L04 | P12 - 4th Lift | 402.a | MPSB/Str/1000 | Str | 2 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 222
P12-WELL-L04 | P12 - 4th Lift | 402.a | MPSB/Sur/863 | Sur | 3 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 222
P14-WELL-L04 | P14 - 4th Lift | 402.a | MPSB/Str/926 | Str | 1 | 3 | 2025-03-27 | IPC - 13 | 2.5 | Palashbari | 223
P14-WELL-L04 | P14 - 4th Lift | 402.a | MPSB/Str/927 | Str | 2 | 3 | 2025-03-27 | IPC - 13 | 2.5 | Palashbari | 223
P14-WELL-L04 | P14 - 4th Lift | 402.a | MPSB/Sur/841 | Sur | 3 | 3 | 2025-03-29 | IPC - 13 | 2.5 | Palashbari | 223
P15-WELL-L04 | P15 - 4th Lift | 402.a | MPSB/Str/997 | Str | 1 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 224
P15-WELL-L04 | P15 - 4th Lift | 402.a | MPSB/Str/998 | Str | 2 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 224
P15-WELL-L04 | P15 - 4th Lift | 402.a | MPSB/Sur/862 | Sur | 3 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 224
P17-WELL-L04 | P17 - 4th Lift | 402.a | MPSB/Str/769 | Str | 1 | 4 | 2025-03-10 | IPC - 13 | 2.5 | Palashbari | 225
P17-WELL-L04 | P17 - 4th Lift | 402.a | MPSB/Str/770 | Str | 2 | 4 | 2025-03-10 | IPC - 13 | 2.5 | Palashbari | 225
P17-WELL-L04 | P17 - 4th Lift | 402.a | MPSB/Sur/680 | Sur | 3 | 4 | 2025-03-10 | IPC - 13 | 2.5 | Palashbari | 225
P17-WELL-L04 | P17 - 4th Lift | 402.a | MPSB/Sur/720 | Sur | 4 | 4 | 2025-03-15 | IPC - 13 | 2.5 | Palashbari | 225
P19-WELL-L04 | P19 - 4th Lift | 402.a | MPSB/Str/853 | Str | 1 | 4 | 2025-03-22 | IPC - 13 | 2.5 | Sualkuchi | 226
P19-WELL-L04 | P19 - 4th Lift | 402.a | MPSB/Sur/673 | Sur | 2 | 4 | 2025-03-22 | IPC - 13 | 2.5 | Sualkuchi | 226 | P19-WELL-L03
P19-WELL-L04 | P19 - 4th Lift | 402.a | MPSB/Str/854 | Str | 3 | 4 | 2025-03-22 | IPC - 13 | 2.5 | Sualkuchi | 226
P19-WELL-L04 | P19 - 4th Lift | 402.a | MPSB/Sur/788 | Sur | 4 | 4 | 2025-03-26 | IPC - 13 | 2.5 | Sualkuchi | 226
P29-WELL-L04 | P29 - 4th Lift | 402.a | MPSB/Str/848 | Str | 1 | 4 | 2025-03-21 | IPC - 13 | 2.5 | Sualkuchi | 227
P29-WELL-L04 | P29 - 4th Lift | 402.a | MPSB/Sur/754 | Sur | 2 | 4 | 2025-03-21 | IPC - 13 | 2.5 | Sualkuchi | 227
P29-WELL-L04 | P29 - 4th Lift | 402.a | MPSB/Str/849 | Str | 3 | 4 | 2025-03-21 | IPC - 13 | 2.5 | Sualkuchi | 227
P29-WELL-L04 | P29 - 4th Lift | 402.a | MPSB/Sur/779 | Sur | 4 | 4 | 2025-03-25 | IPC - 13 | 2.5 | Sualkuchi | 227
P21-WELL-L04 | P21 - 4th Lift | 402.a | MPSB/Str/1111 | Str | 1 | 4 | 2025-04-12 | IPC - 14 | 2.5 | Sualkuchi | 228
P21-WELL-L04 | P21 - 4th Lift | 402.a | MPSB/Sur/973 | Sur | 2 | 4 | 2025-04-12 | IPC - 14 | 2.5 | Sualkuchi | 228
P21-WELL-L04 | P21 - 4th Lift | 402.a | MPSB/Str/1112 | Str | 3 | 4 | 2025-04-12 | IPC - 14 | 2.5 | Sualkuchi | 228
P21-WELL-L04 | P21 - 4th Lift | 402.a | MPSB/Sur/995 | Sur | 4 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Sualkuchi | 228
P23-WELL-L04 | P23 - 4th Lift | 402.a | MPSB/Str/1269 | Str | 1 | 3 | 2025-04-25 | IPC - 14 | 2.5 | Sualkuchi | 229
P23-WELL-L04 | P23 - 4th Lift | 402.a | MPSB/Sur/1128 | Sur | 2 | 3 | 2025-04-27 | IPC - 14 | 2.5 | Sualkuchi | 229
P23-WELL-L04 | P23 - 4th Lift | 402.a | MPSB/Str/1301 | Str | 3 | 3 | 2025-04-27 | IPC - 14 | 2.5 | Sualkuchi | 229
P27-WELL-L04 | P27 - 4th Lift | 402.a | MPSB/Str/1361 | Str | 1 | 3 | 2025-04-30 | IPC - 14 | 2.5 | Sualkuchi | 230
P27-WELL-L04 | P27 - 4th Lift | 402.a | MPSB/Sur/1162 | Sur | 2 | 3 | 2025-04-30 | IPC - 14 | 2.5 | Sualkuchi | 230
P27-WELL-L04 | P27 - 4th Lift | 402.a | MPSB/Str/1362 | Str | 3 | 3 | 2025-04-30 | IPC - 14 | 2.5 | Sualkuchi | 230
P30-WELL-L04 | P30 - 4th Lift | 402.a | MPSB/Str/3069 | Str | 1 | 4 | 2025-12-06 | IPC - 25 | 2.5 | Sualkuchi | 231
P30-WELL-L04 | P30 - 4th Lift | 402.a | MPSB/Sur/2353 | Sur | 2 | 4 | 2025-12-06 | IPC - 25 | 2.5 | Sualkuchi | 231
P30-WELL-L04 | P30 - 4th Lift | 402.a | MPSB/Str/3070 | Str | 3 | 4 | 2025-12-06 | IPC - 25 | 2.5 | Sualkuchi | 231
P30-WELL-L04 | P30 - 4th Lift | 402.a | MPSB/Sur/2373 | Sur | 4 | 4 | 2025-12-09 | IPC - 25 | 2.5 | Sualkuchi | 231
P14(N)-WELL-L04 | P14(N) - 4th Lift | 402.a | MPSB/Str/3597 | Str | 1 | 3 | 2026-01-21 | IPC - 26 | 2.5 | Palashbari | 234
P14(N)-WELL-L04 | P14(N) - 4th Lift | 402.a | MPSB/Sur/2732 | Sur | 2 | 3 | 2026-01-21 | IPC - 26 | 2.5 | Palashbari | 234
P14(N)-WELL-L04 | P14(N) - 4th Lift | 402.a | MPSB/Str/3598 | Str | 3 | 3 | 2026-01-21 | IPC - 26 | 2.5 | Palashbari | 234
P11-WELL-L04 | P11 - 4th Lift | 402.a | MPSB/Str/3919 | Str | 1 | 4 | 2026-02-21 | IPC - 27 | 2.5 | Palashbari | 235
P11-WELL-L04 | P11 - 4th Lift | 402.a | MPSB/Sur/2973 | Sur | 2 | 4 | 2026-02-21 | IPC - 27 | 2.5 | Palashbari | 235
P11-WELL-L04 | P11 - 4th Lift | 402.a | MPSB/Str/3920 | Str | 3 | 4 | 2026-02-21 | IPC - 27 | 2.5 | Palashbari | 235
P11-WELL-L04 | P11 - 4th Lift | 402.a | MPSB/Sur/3041 | Sur | 4 | 4 | 2026-02-28 | IPC - 27 | 2.5 | Palashbari | 235 | P11-WELL-L05
P13-WELL-L04 | P13 - 4th Lift | 402.a | MPSB/Str/3979 | Str | 1 | 3 | 2026-02-27 | IPC - 27 | 2.5 | Palashbari | 236
P13-WELL-L04 | P13 - 4th Lift | 402.a | MPSB/Sur/3019 | Sur | 2 | 3 | 2026-02-27 | IPC - 27 | 2.5 | Palashbari | 236
P13-WELL-L04 | P13 - 4th Lift | 402.a | MPSB/Str/3980 | Str | 3 | 3 | 2026-02-27 | IPC - 27 | 2.5 | Palashbari | 236
P12(A)-WELL-L04 | P12(A) - 4th Lift | 402.a | MPSB/Str/3929 | Str | 1 | 4 | 2026-02-23 | IPC - 33 | 2.8 | Palashbari | 237
P12(A)-WELL-L04 | P12(A) - 4th Lift | 402.a | MPSB/Sur/2976 | Sur | 2 | 4 | 2026-02-23 | IPC - 33 | 2.8 | Palashbari | 237
P12(A)-WELL-L04 | P12(A) - 4th Lift | 402.a | MPSB/Str/3930 | Str | 3 | 4 | 2026-02-23 | IPC - 33 | 2.8 | Palashbari | 237
P12(A)-WELL-L04 | P12(A) - 4th Lift | 402.a | MPSB/Sur/3083 | Sur | 4 | 4 | 2026-03-10 | IPC - 33 | 2.8 | Palashbari | 237 | P12(A)-WELL-L05
P22-WELL-L05 | P22 - 5th Lift | 402.a | MPSB/Sur/239 | Sur | 1 | 3 | 2024-12-30 | IPC - 09 | 2.5 | Sualkuchi | 239
P22-WELL-L05 | P22 - 5th Lift | 402.a | MPSB/Str/290 | Str | 2 | 3 | 2024-12-30 | IPC - 09 | 2.5 | Sualkuchi | 239
P22-WELL-L05 | P22 - 5th Lift | 402.a | MPSB/Str/291 | Str | 3 | 3 | 2024-12-30 | IPC - 09 | 2.5 | Sualkuchi | 239
P26-WELL-L05 | P26 - 5th Lift | 402.a | MPSB/Str/406 | Str | 1 | 4 | 2025-01-22 | IPC - 10 | 2.5 | Sualkuchi | 240
P26-WELL-L05 | P26 - 5th Lift | 402.a | MPSB/Sur/344 | Sur | 2 | 4 | 2025-01-22 | IPC - 10 | 2.5 | Sualkuchi | 240
P26-WELL-L05 | P26 - 5th Lift | 402.a | MPSB/Str/407 | Str | 3 | 4 | 2025-01-22 | IPC - 10 | 2.5 | Sualkuchi | 240
P26-WELL-L05 | P26 - 5th Lift | 402.a | MPSB/Sur/373 | Sur | 4 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 240
P6-WELL-L05 | P6 - 5th Lift | 402.a | MPSB/Str/376 | Str | 1 | 3 | 2025-01-17 | IPC - 10 | 2.5 | Palashbari | 241
P6-WELL-L05 | P6 - 5th Lift | 402.a | MPSB/Str/377 | Str | 2 | 3 | 2025-01-17 | IPC - 10 | 2.5 | Palashbari | 241
P6-WELL-L05 | P6 - 5th Lift | 402.a | MPSB/Sur/362 | Sur | 3 | 3 | 2025-01-26 | IPC - 10 | 2.5 | Palashbari | 241
P20-WELL-L05 | P20 - 5th Lift | 402.a | MPSB/Str/456 | Str | 1 | 3 | 2025-01-30 | IPC - 10 | 2.5 | Sualkuchi | 242
P20-WELL-L05 | P20 - 5th Lift | 402.a | MPSB/Sur/385 | Sur | 2 | 3 | 2025-01-30 | IPC - 10 | 2.5 | Sualkuchi | 242
P20-WELL-L05 | P20 - 5th Lift | 402.a | MPSB/Str/457 | Str | 3 | 3 | 2025-01-30 | IPC - 10 | 2.5 | Sualkuchi | 242
P24-WELL-L05 | P24 - 5th Lift | 402.a | MPSB/Str/458 | Str | 1 | 3 | 2025-01-30 | IPC - 10 | 2.5 | Sualkuchi | 243
P24-WELL-L05 | P24 - 5th Lift | 402.a | MPSB/Sur/386 | Sur | 2 | 3 | 2025-01-30 | IPC - 10 | 2.5 | Sualkuchi | 243
P24-WELL-L05 | P24 - 5th Lift | 402.a | MPSB/Str/459 | Str | 3 | 3 | 2025-01-30 | IPC - 10 | 2.5 | Sualkuchi | 243
P8-WELL-L05 | P8 - 5th Lift | 402.a | MPSB/Str/575 | Str | 1 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Palashbari | 244
P8-WELL-L05 | P8 - 5th Lift | 402.a | MPSB/Sur/506 | Sur | 2 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Palashbari | 244
P8-WELL-L05 | P8 - 5th Lift | 402.a | MPSB/Str/576 | Str | 3 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Palashbari | 244
P8-WELL-L05 | P8 - 5th Lift | 402.a | MPSB/Sur/554 | Sur | 4 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Palashbari | 244
P16-WELL-L05 | P16 - 5th Lift | 402.a | MPSB/Str/540 | Str | 1 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Palashbari | 245
P16-WELL-L05 | P16 - 5th Lift | 402.a | MPSB/Sur/466 | Sur | 2 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Palashbari | 245
P16-WELL-L05 | P16 - 5th Lift | 402.a | MPSB/Str/539 | Str | 3 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Palashbari | 245
P16-WELL-L05 | P16 - 5th Lift | 402.a | MPSB/Sur/489 | Sur | 4 | 4 | 2025-02-18 | IPC - 11 | 2.5 | Palashbari | 245 | P16-WELL-L04
P18-WELL-L05 | P18 - 5th Lift | 402.a | MPSB/Str/530 | Str | 1 | 3 | 2025-02-12 | IPC - 11 | 2.5 | Sualkuchi | 246
P18-WELL-L05 | P18 - 5th Lift | 402.a | MPSB/Str/537 | Str | 2 | 3 | 2025-02-14 | IPC - 11 | 2.5 | Sualkuchi | 246
P18-WELL-L05 | P18 - 5th Lift | 402.a | MPSB/Sur/482 | Sur | 3 | 3 | 2025-02-17 | IPC - 11 | 2.5 | Sualkuchi | 246
P25-WELL-L05 | P25 - 5th Lift | 402.a | MPSB/Str/652 | Str | 1 | 3 | 2025-02-26 | IPC - 11 | 2.5 | Sualkuchi | 247
P25-WELL-L05 | P25 - 5th Lift | 402.a | MPSB/Str/653 | Str | 2 | 3 | 2025-02-26 | IPC - 11 | 2.5 | Sualkuchi | 247
P25-WELL-L05 | P25 - 5th Lift | 402.a | MPSB/Sur/569 | Sur | 3 | 3 | 2025-02-26 | IPC - 11 | 2.5 | Sualkuchi | 247
P28-WELL-L05 | P28 - 5th Lift | 402.a | MPSB/Str/542 | Str | 1 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Sualkuchi | 248
P28-WELL-L05 | P28 - 5th Lift | 402.a | MPSB/Sur/468 | Sur | 2 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Sualkuchi | 248
P28-WELL-L05 | P28 - 5th Lift | 402.a | MPSB/Str/561 | Str | 3 | 4 | 2025-02-17 | IPC - 11 | 2.5 | Sualkuchi | 248
P28-WELL-L05 | P28 - 5th Lift | 402.a | MPSB/Sur/533 | Sur | 4 | 4 | 2025-02-23 | IPC - 11 | 2.5 | Sualkuchi | 248
P10-WELL-L05 | P10 - 5th Lift | 402.a | MPSB/Str/914 | Str | 1 | 3 | 2025-03-26 | IPC - 13 | 2.32 | Palashbari | 249
P10-WELL-L05 | P10 - 5th Lift | 402.a | MPSB/Str/915 | Str | 2 | 3 | 2025-03-26 | IPC - 13 | 2.32 | Palashbari | 249
P10-WELL-L05 | P10 - 5th Lift | 402.a | MPSB/Sur/798 | Sur | 3 | 3 | 2025-03-26 | IPC - 13 | 2.32 | Palashbari | 249
P14-WELL-L05 | P14 - 5th Lift | 402.a | MPSB/Sur/861 | Sur | 1 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 250
P14-WELL-L05 | P14 - 5th Lift | 402.a | MPSB/Str/995 | Str | 2 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 250
P14-WELL-L05 | P14 - 5th Lift | 402.a | MPSB/Str/996 | Str | 3 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 250
P17-WELL-L05 | P17 - 5th Lift | 402.a | MPSB/Str/810 | Str | 1 | 4 | 2025-03-17 | IPC - 13 | 2.5 | Palashbari | 251
P17-WELL-L05 | P17 - 5th Lift | 402.a | MPSB/Str/811 | Str | 2 | 4 | 2025-03-17 | IPC - 13 | 2.5 | Palashbari | 251
P17-WELL-L05 | P17 - 5th Lift | 402.a | MPSB/Sur/722 | Sur | 3 | 4 | 2025-03-17 | IPC - 13 | 2.5 | Palashbari | 251
P17-WELL-L05 | P17 - 5th Lift | 402.a | MPSB/Sur/756 | Sur | 4 | 4 | 2025-03-21 | IPC - 13 | 2.5 | Palashbari | 251
P19-WELL-L05 | P19 - 5th Lift | 402.a | MPSB/Str/954 | Str | 1 | 4 | 2025-03-29 | IPC - 13 | 2.5 | Sualkuchi | 252
P19-WELL-L05 | P19 - 5th Lift | 402.a | MPSB/Sur/832 | Sur | 2 | 4 | 2025-03-29 | IPC - 13 | 2.5 | Sualkuchi | 252
P19-WELL-L05 | P19 - 5th Lift | 402.a | MPSB/Str/955 | Str | 3 | 4 | 2025-03-29 | IPC - 13 | 2.5 | Sualkuchi | 252
P19-WELL-L05 | P19 - 5th Lift | 402.a | MPSB/Sur/876 | Sur | 4 | 4 | 2025-03-31 | IPC - 13 | 2.5 | Sualkuchi | 252
P29-WELL-L05 | P29 - 5th Lift | 402.a | MPSB/Str/964 | Str | 1 | 4 | 2025-03-29 | IPC - 13 | 2.5 | Sualkuchi | 253
P29-WELL-L05 | P29 - 5th Lift | 402.a | MPSB/Sur/837 | Sur | 2 | 4 | 2025-03-29 | IPC - 13 | 2.5 | Sualkuchi | 253
P29-WELL-L05 | P29 - 5th Lift | 402.a | MPSB/Str/965 | Str | 3 | 4 | 2025-03-29 | IPC - 13 | 2.5 | Sualkuchi | 253
P29-WELL-L05 | P29 - 5th Lift | 402.a | MPSB/Sur/894 | Sur | 4 | 4 | 2025-03-31 | IPC - 13 | 2.5 | Sualkuchi | 253
P7-WELL-L05 | P7 - 5th Lift | 402.a | MPSB/Str/1117 | Str | 1 | 3 | 2025-04-12 | IPC - 14 | 2.6 | Palashbari | 254
P7-WELL-L05 | P7 - 5th Lift | 402.a | MPSB/Sur/979 | Sur | 2 | 3 | 2025-04-12 | IPC - 14 | 2.6 | Palashbari | 254
P7-WELL-L05 | P7 - 5th Lift | 402.a | MPSB/Str/1118 | Str | 3 | 3 | 2025-04-12 | IPC - 14 | 2.6 | Palashbari | 254
P9-WELL-L05 | P9 - 5th Lift | 402.a | MPSB/Str/1048 | Str | 1 | 4 | 2025-04-05 | IPC - 14 | 2.5 | Palashbari | 255
P9-WELL-L05 | P9 - 5th Lift | 402.a | MPSB/Sur/919 | Sur | 2 | 4 | 2025-04-05 | IPC - 14 | 2.5 | Palashbari | 255
P9-WELL-L05 | P9 - 5th Lift | 402.a | MPSB/Str/1049 | Str | 3 | 4 | 2025-04-05 | IPC - 14 | 2.5 | Palashbari | 255
P9-WELL-L05 | P9 - 5th Lift | 402.a | MPSB/Sur/969 | Sur | 4 | 4 | 2025-04-11 | IPC - 14 | 2.5 | Palashbari | 255
P12-WELL-L05 | P12 - 5th Lift | 402.a | MPSB/Str/1109 | Str | 1 | 4 | 2025-04-12 | IPC - 14 | 2.4 | Palashbari | 256
P12-WELL-L05 | P12 - 5th Lift | 402.a | MPSB/Sur/985 | Sur | 2 | 4 | 2025-04-12 | IPC - 14 | 2.4 | Palashbari | 256
P12-WELL-L05 | P12 - 5th Lift | 402.a | MPSB/Str/1110 | Str | 3 | 4 | 2025-04-12 | IPC - 14 | 2.4 | Palashbari | 256
P12-WELL-L05 | P12 - 5th Lift | 402.a | MPSB/Sur/1022 | Sur | 4 | 4 | 2025-04-17 | IPC - 14 | 2.4 | Palashbari | 256
P15-WELL-L05 | P15 - 5th Lift | 402.a | MPSB/Str/1107 | Str | 1 | 3 | 2025-04-12 | IPC - 14 | 2.5 | Palashbari | 257
P15-WELL-L05 | P15 - 5th Lift | 402.a | MPSB/Sur/971 | Sur | 2 | 3 | 2025-04-12 | IPC - 14 | 2.5 | Palashbari | 257
P15-WELL-L05 | P15 - 5th Lift | 402.a | MPSB/Str/1108 | Str | 3 | 3 | 2025-04-12 | IPC - 14 | 2.5 | Palashbari | 257
P21-WELL-L05 | P21 - 5th Lift | 402.a | MPSB/Str/1205 | Str | 1 | 4 | 2025-04-21 | IPC - 14 | 2.5 | Sualkuchi | 258
P21-WELL-L05 | P21 - 5th Lift | 402.a | MPSB/Sur/1048 | Sur | 2 | 4 | 2025-04-21 | IPC - 14 | 2.5 | Sualkuchi | 258
P21-WELL-L05 | P21 - 5th Lift | 402.a | MPSB/Str/1206 | Str | 3 | 4 | 2025-04-21 | IPC - 14 | 2.5 | Sualkuchi | 258
P21-WELL-L05 | P21 - 5th Lift | 402.a | MPSB/Sur/1100 | Sur | 4 | 4 | 2025-04-25 | IPC - 14 | 2.5 | Sualkuchi | 258
P23-WELL-L05 | P23 - 5th Lift | 402.a | MPSB/Str/1440 | Str | 1 | 4 | 2025-05-07 | IPC - 15 | 2.5 | Sualkuchi | 259
P23-WELL-L05 | P23 - 5th Lift | 402.a | MPSB/Sur/1232 | Sur | 2 | 4 | 2025-05-07 | IPC - 15 | 2.5 | Sualkuchi | 259
P23-WELL-L05 | P23 - 5th Lift | 402.a | MPSB/Str/1441 | Str | 3 | 4 | 2025-05-07 | IPC - 15 | 2.5 | Sualkuchi | 259
P23-WELL-L05 | P23 - 5th Lift | 402.a | MPSB/Sur/1258 | Sur | 4 | 4 | 2025-05-12 | IPC - 15 | 2.5 | Sualkuchi | 259
P27-WELL-L05 | P27 - 5th Lift | 402.a | MPSB/Str/1444 | Str | 1 | 4 | 2025-05-08 | IPC - 15 | 2.5 | Sualkuchi | 260
P27-WELL-L05 | P27 - 5th Lift | 402.a | MPSB/Sur/1235 | Sur | 2 | 4 | 2025-05-08 | IPC - 15 | 2.5 | Sualkuchi | 260
P27-WELL-L05 | P27 - 5th Lift | 402.a | MPSB/Str/1445 | Str | 3 | 4 | 2025-05-08 | IPC - 15 | 2.5 | Sualkuchi | 260
P27-WELL-L05 | P27 - 5th Lift | 402.a | MPSB/Sur/1273 | Sur | 4 | 4 | 2025-05-13 | IPC - 15 | 2.5 | Sualkuchi | 260
P30-WELL-L05 | P30 - 5th Lift | 402.a | MPSB/Str/3099 | Str | 1 | 3 | 2025-12-10 | IPC - 25 | 2.5 | Sualkuchi | 261
P30-WELL-L05 | P30 - 5th Lift | 402.a | MPSB/Sur/2382 | Sur | 2 | 3 | 2025-12-10 | IPC - 25 | 2.5 | Sualkuchi | 261
P30-WELL-L05 | P30 - 5th Lift | 402.a | MPSB/Str/3100 | Str | 3 | 3 | 2025-12-10 | IPC - 25 | 2.5 | Sualkuchi | 261
P14(N)-WELL-L05 | P14(N) - 5th Lift | 402.a | MPSB/Str/3657 | Str | 1 | 3 | 2026-01-27 | IPC - 26 | 2.5 | Palashbari | 264
P14(N)-WELL-L05 | P14(N) - 5th Lift | 402.a | MPSB/Sur/2780 | Sur | 2 | 3 | 2026-01-27 | IPC - 26 | 2.5 | Palashbari | 264
P14(N)-WELL-L05 | P14(N) - 5th Lift | 402.a | MPSB/Str/3658 | Str | 3 | 3 | 2026-01-27 | IPC - 26 | 2.5 | Palashbari | 264
P11-WELL-L05 | P11 - 5th Lift | 402.a | MPSB/Str/3960 | Str | 1 | 4 | 2026-02-26 | IPC - 27 | 2.5 | Palashbari | 265
P11-WELL-L05 | P11 - 5th Lift | 402.a | MPSB/Sur/3009 | Sur | 2 | 4 | 2026-02-26 | IPC - 27 | 2.5 | Palashbari | 265
P11-WELL-L05 | P11 - 5th Lift | 402.a | MPSB/Str/3961 | Str | 3 | 4 | 2026-02-26 | IPC - 27 | 2.5 | Palashbari | 265
P11-WELL-L05 | P11 - 5th Lift | 402.a | MPSB/Sur/3041 | Sur | 4 | 4 | 2026-02-28 | IPC - 27 | 2.5 | Palashbari | 265 | P11-WELL-L04
P13-WELL-L05 | P13 - 5th Lift | 402.a | MPSB/Str/4056 | Str | 1 | 3 | 2026-03-07 | IPC - 29 | 2.5 | Palashbari | 266
P13-WELL-L05 | P13 - 5th Lift | 402.a | MPSB/Sur/3069 | Sur | 2 | 3 | 2026-03-07 | IPC - 29 | 2.5 | Palashbari | 266
P13-WELL-L05 | P13 - 5th Lift | 402.a | MPSB/Str/4057 | Str | 3 | 3 | 2026-03-07 | IPC - 29 | 2.5 | Palashbari | 266
P12(A)-WELL-L05 | P12(A) - 5th Lift | 402.a | MPSB/Str/3962 | Str | 1 | 4 | 2026-02-26 | IPC - 33 | 2.8 | Palashbari | 267
P12(A)-WELL-L05 | P12(A) - 5th Lift | 402.a | MPSB/Sur/3010 | Sur | 2 | 4 | 2026-02-26 | IPC - 33 | 2.8 | Palashbari | 267
P12(A)-WELL-L05 | P12(A) - 5th Lift | 402.a | MPSB/Str/3963 | Str | 3 | 4 | 2026-02-26 | IPC - 33 | 2.8 | Palashbari | 267
P12(A)-WELL-L05 | P12(A) - 5th Lift | 402.a | MPSB/Sur/3083 | Sur | 4 | 4 | 2026-03-10 | IPC - 33 | 2.8 | Palashbari | 267 | P12(A)-WELL-L04
P26-WELL-L06 | P26 - 6th Lift | 402.a | MPSB/Str/470 | Str | 1 | 3 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 269
P26-WELL-L06 | P26 - 6th Lift | 402.a | MPSB/Sur/402 | Sur | 2 | 3 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 269
P26-WELL-L06 | P26 - 6th Lift | 402.a | MPSB/Str/471 | Str | 3 | 3 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 269
P6-WELL-L06 | P6 - 6th Lift | 402.a | MPSB/Str/410 | Str | 1 | 4 | 2025-01-22 | IPC - 10 | 2.5 | Palashbari | 270
P6-WELL-L06 | P6 - 6th Lift | 402.a | MPSB/Sur/350 | Sur | 2 | 4 | 2025-01-23 | IPC - 10 | 2.5 | Palashbari | 270
P6-WELL-L06 | P6 - 6th Lift | 402.a | MPSB/Str/416 | Str | 3 | 4 | 2025-01-23 | IPC - 10 | 2.5 | Palashbari | 270
P6-WELL-L06 | P6 - 6th Lift | 402.a | MPSB/Sur/393 | Sur | 4 | 4 | 2025-01-31 | IPC - 10 | 2.5 | Palashbari | 270
P22-WELL-L06 | P22 - 6th Lift | 402.a | MPSB/Str/340 | Str | 1 | 4 | 2025-01-09 | IPC - 10 | 2.5 | Sualkuchi | 271
P22-WELL-L06 | P22 - 6th Lift | 402.a | MPSB/Sur/277 | Sur | 2 | 4 | 2025-01-09 | IPC - 10 | 2.5 | Sualkuchi | 271
P22-WELL-L06 | P22 - 6th Lift | 402.a | MPSB/Str/341 | Str | 3 | 4 | 2025-01-09 | IPC - 10 | 2.5 | Sualkuchi | 271
P22-WELL-L06 | P22 - 6th Lift | 402.a | MPSB/Sur/299 | Sur | 4 | 4 | 2025-01-14 | IPC - 10 | 2.5 | Sualkuchi | 271
P8-WELL-L06 | P8 - 6th Lift | 402.a | MPSB/Str/702 | Str | 1 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 272
P8-WELL-L06 | P8 - 6th Lift | 402.a | MPSB/Sur/610 | Sur | 2 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 272
P8-WELL-L06 | P8 - 6th Lift | 402.a | MPSB/Str/703 | Str | 3 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 272
P16-WELL-L06 | P16 - 6th Lift | 402.a | MPSB/Str/616 | Str | 1 | 3 | 2025-02-24 | IPC - 11 | 2.5 | Palashbari | 273
P16-WELL-L06 | P16 - 6th Lift | 402.a | MPSB/Sur/549 | Sur | 2 | 3 | 2025-02-25 | IPC - 11 | 2.5 | Palashbari | 273
P16-WELL-L06 | P16 - 6th Lift | 402.a | MPSB/Str/624 | Str | 3 | 3 | 2025-02-25 | IPC - 11 | 2.5 | Palashbari | 273
P18-WELL-L06 | P18 - 6th Lift | 402.a | MPSB/Str/598 | Str | 1 | 4 | 2025-02-22 | IPC - 11 | 2.5 | Sualkuchi | 274
P18-WELL-L06 | P18 - 6th Lift | 402.a | MPSB/Sur/527 | Sur | 2 | 4 | 2025-02-22 | IPC - 11 | 2.5 | Sualkuchi | 274
P18-WELL-L06 | P18 - 6th Lift | 402.a | MPSB/Str/599 | Str | 3 | 4 | 2025-02-22 | IPC - 11 | 2.5 | Sualkuchi | 274
P18-WELL-L06 | P18 - 6th Lift | 402.a | MPSB/Sur/556 | Sur | 4 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 274
P20-WELL-L06 | P20 - 6th Lift | 402.a | MPSB/Str/506 | Str | 1 | 4 | 2025-02-08 | IPC - 11 | 2.5 | Sualkuchi | 275
P20-WELL-L06 | P20 - 6th Lift | 402.a | MPSB/Sur/440 | Sur | 2 | 4 | 2025-02-08 | IPC - 11 | 2.5 | Sualkuchi | 275
P20-WELL-L06 | P20 - 6th Lift | 402.a | MPSB/Str/550 | Str | 3 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Sualkuchi | 275
P20-WELL-L06 | P20 - 6th Lift | 402.a | MPSB/Sur/484 | Sur | 4 | 4 | 2025-02-17 | IPC - 11 | 2.5 | Sualkuchi | 275
P24-WELL-L06 | P24 - 6th Lift | 402.a | MPSB/Str/514 | Str | 1 | 4 | 2025-02-10 | IPC - 11 | 2.5 | Sualkuchi | 276
P24-WELL-L06 | P24 - 6th Lift | 402.a | MPSB/Sur/465 | Sur | 2 | 4 | 2025-02-13 | IPC - 11 | 2.5 | Sualkuchi | 276
P24-WELL-L06 | P24 - 6th Lift | 402.a | MPSB/Str/535 | Str | 3 | 4 | 2025-02-13 | IPC - 11 | 2.5 | Sualkuchi | 276
P24-WELL-L06 | P24 - 6th Lift | 402.a | MPSB/Sur/476 | Sur | 4 | 4 | 2025-02-16 | IPC - 11 | 2.5 | Sualkuchi | 276
P28-WELL-L06 | P28 - 6th Lift | 402.a | MPSB/Str/641 | Str | 1 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 277
P28-WELL-L06 | P28 - 6th Lift | 402.a | MPSB/Sur/563 | Sur | 2 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 277
P28-WELL-L06 | P28 - 6th Lift | 402.a | MPSB/Str/642 | Str | 3 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 277
P28-WELL-L06 | P28 - 6th Lift | 402.a | MPSB/Sur/578 | Sur | 4 | 4 | 2025-02-27 | IPC - 11 | 2.5 | Sualkuchi | 277
P10-WELL-L06 | P10 - 6th Lift | 402.a | MPSB/Str/991 | Str | 1 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 278
P10-WELL-L06 | P10 - 6th Lift | 402.a | MPSB/Str/992 | Str | 2 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 278
P10-WELL-L06 | P10 - 6th Lift | 402.a | MPSB/Sur/859 | Sur | 3 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 278
P17-WELL-L06 | P17 - 6th Lift | 402.a | MPSB/Str/993 | Str | 1 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 279
P17-WELL-L06 | P17 - 6th Lift | 402.a | MPSB/Str/994 | Str | 2 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 279
P17-WELL-L06 | P17 - 6th Lift | 402.a | MPSB/Sur/860 | Sur | 3 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Palashbari | 279
P25-WELL-L06 | P25 - 6th Lift | 402.a | MPSB/Str/806 | Str | 1 | 4 | 2025-03-15 | IPC - 13 | 2.5 | Sualkuchi | 280
P25-WELL-L06 | P25 - 6th Lift | 402.a | MPSB/Sur/714 | Sur | 2 | 4 | 2025-03-15 | IPC - 13 | 2.5 | Sualkuchi | 280
P25-WELL-L06 | P25 - 6th Lift | 402.a | MPSB/Str/807 | Str | 3 | 4 | 2025-03-15 | IPC - 13 | 2.5 | Sualkuchi | 280
P25-WELL-L06 | P25 - 6th Lift | 402.a | MPSB/Sur/732 | Sur | 4 | 4 | 2025-03-18 | IPC - 13 | 2.5 | Sualkuchi | 280
P7-WELL-L06 | P7 - 6th Lift | 402.a | MPSB/Str/1201 | Str | 1 | 3 | 2025-04-21 | IPC - 14 | 2.5 | Palashbari | 281
P7-WELL-L06 | P7 - 6th Lift | 402.a | MPSB/Sur/1044 | Sur | 2 | 3 | 2025-04-21 | IPC - 14 | 2.5 | Palashbari | 281
P7-WELL-L06 | P7 - 6th Lift | 402.a | MPSB/Str/1202 | Str | 3 | 3 | 2025-04-21 | IPC - 14 | 2.5 | Palashbari | 281
P9-WELL-L06 | P9 - 6th Lift | 402.a | MPSB/Str/1155 | Str | 1 | 3 | 2025-04-16 | IPC - 14 | 2.5 | Palashbari | 282
P9-WELL-L06 | P9 - 6th Lift | 402.a | MPSB/Sur/1004 | Sur | 2 | 3 | 2025-04-16 | IPC - 14 | 2.5 | Palashbari | 282
P9-WELL-L06 | P9 - 6th Lift | 402.a | MPSB/Str/1156 | Str | 3 | 3 | 2025-04-16 | IPC - 14 | 2.5 | Palashbari | 282
P12-WELL-L06 | P12 - 6th Lift | 402.a | MPSB/Str/1199 | Str | 1 | 4 | 2025-04-20 | IPC - 14 | 2.6 | Palashbari | 283
P12-WELL-L06 | P12 - 6th Lift | 402.a | MPSB/Sur/1043 | Sur | 2 | 4 | 2025-04-20 | IPC - 14 | 2.6 | Palashbari | 283
P12-WELL-L06 | P12 - 6th Lift | 402.a | MPSB/Str/1200 | Str | 3 | 4 | 2025-04-20 | IPC - 14 | 2.6 | Palashbari | 283
P12-WELL-L06 | P12 - 6th Lift | 402.a | MPSB/Sur/1079 | Sur | 4 | 4 | 2025-04-24 | IPC - 14 | 2.6 | Palashbari | 283
P14-WELL-L06 | P14 - 6th Lift | 402.a | MPSB/Str/1142 | Str | 1 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Palashbari | 284
P14-WELL-L06 | P14 - 6th Lift | 402.a | MPSB/Sur/1001 | Sur | 2 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Palashbari | 284
P14-WELL-L06 | P14 - 6th Lift | 402.a | MPSB/Str/1143 | Str | 3 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Palashbari | 284
P14-WELL-L06 | P14 - 6th Lift | 402.a | MPSB/Sur/1120 | Sur | 4 | 4 | 2025-04-26 | IPC - 14 | 2.5 | Palashbari | 284 | P14-WELL-L07
P15-WELL-L06 | P15 - 6th Lift | 402.a | MPSB/Str/1176 | Str | 1 | 3 | 2025-04-17 | IPC - 14 | 2.5 | Palashbari | 285
P15-WELL-L06 | P15 - 6th Lift | 402.a | MPSB/Sur/1023 | Sur | 2 | 3 | 2025-04-17 | IPC - 14 | 2.5 | Palashbari | 285
P15-WELL-L06 | P15 - 6th Lift | 402.a | MPSB/Str/1177 | Str | 3 | 3 | 2025-04-17 | IPC - 14 | 2.5 | Palashbari | 285
P19-WELL-L06 | P19 - 6th Lift | 402.a | MPSB/Str/1069 | Str | 1 | 4 | 2025-04-08 | IPC - 14 | 2.5 | Sualkuchi | 286
P19-WELL-L06 | P19 - 6th Lift | 402.a | MPSB/Sur/940 | Sur | 2 | 4 | 2025-04-08 | IPC - 14 | 2.5 | Sualkuchi | 286
P19-WELL-L06 | P19 - 6th Lift | 402.a | MPSB/Str/1070 | Str | 3 | 4 | 2025-04-08 | IPC - 14 | 2.5 | Sualkuchi | 286
P19-WELL-L06 | P19 - 6th Lift | 402.a | MPSB/Sur/977 | Sur | 4 | 4 | 2025-04-12 | IPC - 14 | 2.5 | Sualkuchi | 286
P21-WELL-L06 | P21 - 6th Lift | 402.a | MPSB/Str/1312 | Str | 1 | 3 | 2025-04-28 | IPC - 14 | 2.5 | Sualkuchi | 287
P21-WELL-L06 | P21 - 6th Lift | 402.a | MPSB/Sur/1135 | Sur | 2 | 3 | 2025-04-28 | IPC - 14 | 2.5 | Sualkuchi | 287
P21-WELL-L06 | P21 - 6th Lift | 402.a | MPSB/Str/1313 | Str | 3 | 3 | 2025-04-28 | IPC - 14 | 2.5 | Sualkuchi | 287
P29-WELL-L06 | P29 - 6th Lift | 402.a | MPSB/Str/1121 | Str | 1 | 4 | 2025-04-13 | IPC - 14 | 2.5 | Sualkuchi | 288
P29-WELL-L06 | P29 - 6th Lift | 402.a | MPSB/Sur/981 | Sur | 2 | 4 | 2025-04-13 | IPC - 14 | 2.5 | Sualkuchi | 288
P29-WELL-L06 | P29 - 6th Lift | 402.a | MPSB/Str/1122 | Str | 3 | 4 | 2025-04-13 | IPC - 14 | 2.5 | Sualkuchi | 288
P29-WELL-L06 | P29 - 6th Lift | 402.a | MPSB/Sur/1018 | Sur | 4 | 4 | 2025-04-17 | IPC - 14 | 2.5 | Sualkuchi | 288
P23-WELL-L06 | P23 - 6th Lift | 402.a | MPSB/Str/1552 | Str | 1 | 4 | 2025-05-22 | IPC - 15 | 2.5 | Sualkuchi | 289
P23-WELL-L06 | P23 - 6th Lift | 402.a | MPSB/Sur/1333 | Sur | 2 | 4 | 2025-05-22 | IPC - 15 | 2.5 | Sualkuchi | 289
P23-WELL-L06 | P23 - 6th Lift | 402.a | MPSB/Str/1553 | Str | 3 | 4 | 2025-05-22 | IPC - 15 | 2.5 | Sualkuchi | 289
P23-WELL-L06 | P23 - 6th Lift | 402.a | MPSB/Sur/1357 | Sur | 4 | 4 | 2025-05-26 | IPC - 15 | 2.5 | Sualkuchi | 289
P27-WELL-L06 | P27 - 6th Lift | 402.a | MPSB/Str/1532 | Str | 1 | 4 | 2025-05-19 | IPC - 15 | 2.5 | Sualkuchi | 290
P27-WELL-L06 | P27 - 6th Lift | 402.a | MPSB/Sur/1314 | Sur | 2 | 4 | 2025-05-19 | IPC - 15 | 2.5 | Sualkuchi | 290
P27-WELL-L06 | P27 - 6th Lift | 402.a | MPSB/Str/1533 | Str | 3 | 4 | 2025-05-19 | IPC - 15 | 2.5 | Sualkuchi | 290
P27-WELL-L06 | P27 - 6th Lift | 402.a | MPSB/Sur/1336 | Sur | 4 | 4 | 2025-05-23 | IPC - 15 | 2.5 | Sualkuchi | 290
P30-WELL-L06 | P30 - 6th Lift | 402.a | MPSB/Str/3152 | Str | 1 | 4 | 2025-12-15 | IPC - 25 | 2.5 | Sualkuchi | 291
P30-WELL-L06 | P30 - 6th Lift | 402.a | MPSB/Sur/2418 | Sur | 2 | 4 | 2025-12-15 | IPC - 25 | 2.5 | Sualkuchi | 291
P30-WELL-L06 | P30 - 6th Lift | 402.a | MPSB/Str/3153 | Str | 3 | 4 | 2025-12-15 | IPC - 25 | 2.5 | Sualkuchi | 291
P30-WELL-L06 | P30 - 6th Lift | 402.a | MPSB/Sur/2439 | Sur | 4 | 4 | 2025-12-18 | IPC - 25 | 2.5 | Sualkuchi | 291
P14(N)-WELL-L06 | P14(N) - 6th Lift | 402.a | MPSB/Str/3713 | Str | 1 | 3 | 2026-01-31 | IPC - 26 | 2.5 | Palashbari | 294
P14(N)-WELL-L06 | P14(N) - 6th Lift | 402.a | MPSB/Sur/2817 | Sur | 2 | 3 | 2026-01-31 | IPC - 26 | 2.5 | Palashbari | 294
P14(N)-WELL-L06 | P14(N) - 6th Lift | 402.a | MPSB/Str/3714 | Str | 3 | 3 | 2026-01-31 | IPC - 26 | 2.5 | Palashbari | 294
P11-WELL-L06 | P11 - 6th Lift | 402.a | MPSB/Str/4077 | Str | 1 | 3 | 2026-03-10 | IPC - 29 | 2.5 | Palashbari | 295
P11-WELL-L06 | P11 - 6th Lift | 402.a | MPSB/Sur/3084 | Sur | 2 | 3 | 2026-03-10 | IPC - 29 | 2.5 | Palashbari | 295
P11-WELL-L06 | P11 - 6th Lift | 402.a | MPSB/Str/4078 | Str | 3 | 3 | 2026-03-10 | IPC - 29 | 2.5 | Palashbari | 295
P13-WELL-L06 | P13 - 6th Lift | 402.a | MPSB/Str/4143 | Str | 1 | 3 | 2026-03-18 | IPC - 29 | 2.5 | Palashbari | 296
P13-WELL-L06 | P13 - 6th Lift | 402.a | MPSB/Sur/3142 | Sur | 2 | 3 | 2026-03-18 | IPC - 29 | 2.5 | Palashbari | 296
P13-WELL-L06 | P13 - 6th Lift | 402.a | MPSB/Str/4144 | Str | 3 | 3 | 2026-03-18 | IPC - 29 | 2.5 | Palashbari | 296
P12(A)-WELL-L06 | P12(A) - 6th Lift | 402.a | MPSB/Str/4086 | Str | 1 | 4 | 2026-03-11 | IPC - 33 | 2.8 | Palashbari | 297
P12(A)-WELL-L06 | P12(A) - 6th Lift | 402.a | MPSB/Sur/3091 | Sur | 2 | 4 | 2026-03-11 | IPC - 33 | 2.8 | Palashbari | 297
P12(A)-WELL-L06 | P12(A) - 6th Lift | 402.a | MPSB/Str/4087 | Str | 3 | 4 | 2026-03-11 | IPC - 33 | 2.8 | Palashbari | 297
P12(A)-WELL-L06 | P12(A) - 6th Lift | 402.a | MPSB/Sur/3118 | Sur | 4 | 4 | 2026-03-14 | IPC - 33 | 2.8 | Palashbari | 297
P10-WELL-L07 | P10 - 7th Lift | 402.a | MPSB/Str/1102 | Str | 1 | 4 | 2025-04-11 | IPC - 14 | 2.5 | Palashbari | 299
P10-WELL-L07 | P10 - 7th Lift | 402.a | MPSB/Sur/964 | Sur | 2 | 4 | 2025-04-11 | IPC - 14 | 2.5 | Palashbari | 299
P10-WELL-L07 | P10 - 7th Lift | 402.a | MPSB/Str/1103 | Str | 3 | 4 | 2025-04-11 | IPC - 14 | 2.5 | Palashbari | 299
P10-WELL-L07 | P10 - 7th Lift | 402.a | MPSB/Sur/1000 | Sur | 4 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Palashbari | 299
P11-WELL-L07 | P11 - 7th Lift | 402.a | MPSB/Str/4120 | Str | 1 | 3 | 2026-03-15 | IPC - 29 | 2.5 | Palashbari | 300
P11-WELL-L07 | P11 - 7th Lift | 402.a | MPSB/Sur/3123 | Sur | 2 | 3 | 2026-03-15 | IPC - 29 | 2.5 | Palashbari | 300
P11-WELL-L07 | P11 - 7th Lift | 402.a | MPSB/Str/4119 | Str | 3 | 3 | 2026-03-15 | IPC - 29 | 2.5 | Palashbari | 300
P12-WELL-L07 | P12 - 7th Lift | 402.a | MPSB/Str/1272 | Str | 1 | 3 | 2025-04-25 | IPC - 14 | 2.5 | Palashbari | 301
P12-WELL-L07 | P12 - 7th Lift | 402.a | MPSB/Sur/1102 | Sur | 2 | 3 | 2025-04-25 | IPC - 14 | 2.5 | Palashbari | 301
P12-WELL-L07 | P12 - 7th Lift | 402.a | MPSB/Str/1273 | Str | 3 | 3 | 2025-04-25 | IPC - 14 | 2.5 | Palashbari | 301
P12(A)-WELL-L07 | P12(A) - 7th Lift | 402.a | MPSB/Str/4153 | Str | 1 | 4 | 2026-03-19 | IPC - 33 | 2.8 | Palashbari | 303
P12(A)-WELL-L07 | P12(A) - 7th Lift | 402.a | MPSB/Sur/3145 | Sur | 2 | 4 | 2026-03-19 | IPC - 33 | 2.8 | Palashbari | 303
P12(A)-WELL-L07 | P12(A) - 7th Lift | 402.a | MPSB/Str/4154 | Str | 3 | 4 | 2026-03-19 | IPC - 33 | 2.8 | Palashbari | 303
P12(A)-WELL-L07 | P12(A) - 7th Lift | 402.a | MPSB/Sur/3237 | Sur | 4 | 4 | 2026-04-03 | IPC - 33 | 2.8 | Palashbari | 303 | P12(A)-WELL-L08
P13-WELL-L07 | P13 - 7th Lift | 402.a | MPSB/Str/4191 | Str | 1 | 3 | 2026-03-24 | IPC - 29 | 2.5 | Palashbari | 304
P13-WELL-L07 | P13 - 7th Lift | 402.a | MPSB/Sur/3164 | Sur | 2 | 3 | 2026-03-24 | IPC - 29 | 2.5 | Palashbari | 304
P13-WELL-L07 | P13 - 7th Lift | 402.a | MPSB/Str/4192 | Str | 3 | 3 | 2026-03-24 | IPC - 29 | 2.5 | Palashbari | 304
P14-WELL-L07 | P14 - 7th Lift | 402.a | MPSB/Str/1214 | Str | 1 | 4 | 2025-04-21 | IPC - 14 | 2.5 | Palashbari | 305
P14-WELL-L07 | P14 - 7th Lift | 402.a | MPSB/Sur/1056 | Sur | 2 | 4 | 2025-04-21 | IPC - 14 | 2.5 | Palashbari | 305
P14-WELL-L07 | P14 - 7th Lift | 402.a | MPSB/Str/1215 | Str | 3 | 4 | 2025-04-21 | IPC - 14 | 2.5 | Palashbari | 305
P14-WELL-L07 | P14 - 7th Lift | 402.a | MPSB/Sur/1120 | Sur | 4 | 4 | 2025-04-26 | IPC - 14 | 2.5 | Palashbari | 305 | P14-WELL-L06
P14(N)-WELL-L07 | P14(N) - 7th Lift | 402.a | MPSB/Str/3758 | Str | 1 | 4 | 2026-02-04 | IPC - 27 | 2.5 | Palashbari | 307
P14(N)-WELL-L07 | P14(N) - 7th Lift | 402.a | MPSB/Sur/2852 | Sur | 2 | 4 | 2026-02-04 | IPC - 27 | 2.5 | Palashbari | 307
P14(N)-WELL-L07 | P14(N) - 7th Lift | 402.a | MPSB/Str/3759 | Str | 3 | 4 | 2026-02-04 | IPC - 27 | 2.5 | Palashbari | 307
P14(N)-WELL-L07 | P14(N) - 7th Lift | 402.a | MPSB/Sur/2910 | Sur | 4 | 4 | 2026-02-11 | IPC - 27 | 2.5 | Palashbari | 307
P15-WELL-L07 | P15 - 7th Lift | 402.a | MPSB/Str/1234 | Str | 1 | 3 | 2025-04-23 | IPC - 14 | 2.5 | Palashbari | 308
P15-WELL-L07 | P15 - 7th Lift | 402.a | MPSB/Sur/1067 | Sur | 2 | 3 | 2025-04-23 | IPC - 14 | 2.5 | Palashbari | 308
P15-WELL-L07 | P15 - 7th Lift | 402.a | MPSB/Str/1235 | Str | 3 | 3 | 2025-04-23 | IPC - 14 | 2.5 | Palashbari | 308
P16-WELL-L07 | P16 - 7th Lift | 402.a | MPSB/Sur/679 | Sur | 1 | 4 | 2025-03-09 | IPC - 13 | 2.51 | Palashbari | 309
P16-WELL-L07 | P16 - 7th Lift | 402.a | MPSB/Str/767 | Str | 2 | 4 | 2025-03-09 | IPC - 13 | 2.51 | Palashbari | 309
P16-WELL-L07 | P16 - 7th Lift | 402.a | MPSB/Str/768 | Str | 3 | 4 | 2025-03-09 | IPC - 13 | 2.51 | Palashbari | 309
P16-WELL-L07 | P16 - 7th Lift | 402.a | MPSB/Sur/699 | Sur | 4 | 4 | 2025-03-11 | IPC - 13 | 2.51 | Palashbari | 309
P17-WELL-L07 | P17 - 7th Lift | 402.a | MPSB/Str/1088 | Str | 1 | 4 | 2025-04-09 | IPC - 14 | 2.5 | Palashbari | 310
P17-WELL-L07 | P17 - 7th Lift | 402.a | MPSB/Sur/952 | Sur | 2 | 4 | 2025-04-09 | IPC - 14 | 2.5 | Palashbari | 310
P17-WELL-L07 | P17 - 7th Lift | 402.a | MPSB/Str/1089 | Str | 3 | 4 | 2025-04-09 | IPC - 14 | 2.5 | Palashbari | 310
P17-WELL-L07 | P17 - 7th Lift | 402.a | MPSB/Sur/1069 | Sur | 4 | 4 | 2025-04-23 | IPC - 14 | 2.5 | Palashbari | 310
P18-WELL-L07 | P18 - 7th Lift | 402.a | MPSB/Str/746 | Str | 1 | 4 | 2025-03-07 | IPC - 13 | 2.51 | Sualkuchi | 311
P18-WELL-L07 | P18 - 7th Lift | 402.a | MPSB/Sur/664 | Sur | 2 | 4 | 2025-03-07 | IPC - 13 | 2.51 | Sualkuchi | 311
P18-WELL-L07 | P18 - 7th Lift | 402.a | MPSB/Str/747 | Str | 3 | 4 | 2025-03-07 | IPC - 13 | 2.51 | Sualkuchi | 311
P18-WELL-L07 | P18 - 7th Lift | 402.a | MPSB/Sur/686 | Sur | 4 | 4 | 2025-03-11 | IPC - 13 | 2.51 | Sualkuchi | 311
P19-WELL-L07 | P19 - 7th Lift | 402.a | MPSB/Str/1134 | Str | 1 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Sualkuchi | 312
P19-WELL-L07 | P19 - 7th Lift | 402.a | MPSB/Sur/996 | Sur | 2 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Sualkuchi | 312
P19-WELL-L07 | P19 - 7th Lift | 402.a | MPSB/Str/1135 | Str | 3 | 4 | 2025-04-15 | IPC - 14 | 2.5 | Sualkuchi | 312
P19-WELL-L07 | P19 - 7th Lift | 402.a | MPSB/Sur/1050 | Sur | 4 | 4 | 2025-04-21 | IPC - 14 | 2.5 | Sualkuchi | 312
P20-WELL-L07 | P20 - 7th Lift | 402.a | MPSB/Str/587 | Str | 1 | 4 | 2025-02-21 | IPC - 11 | 2.5 | Sualkuchi | 313
P20-WELL-L07 | P20 - 7th Lift | 402.a | MPSB/Sur/521 | Sur | 2 | 4 | 2025-02-21 | IPC - 11 | 2.5 | Sualkuchi | 313
P20-WELL-L07 | P20 - 7th Lift | 402.a | MPSB/Str/588 | Str | 3 | 4 | 2025-02-21 | IPC - 11 | 2.5 | Sualkuchi | 313
P20-WELL-L07 | P20 - 7th Lift | 402.a | MPSB/Sur/544 | Sur | 4 | 4 | 2025-02-24 | IPC - 11 | 2.5 | Sualkuchi | 313
P21-WELL-L07 | P21 - 7th Lift | 402.a | MPSB/Str/1470 | Str | 1 | 4 | 2025-05-11 | IPC - 15 | 2.5 | Sualkuchi | 314
P21-WELL-L07 | P21 - 7th Lift | 402.a | MPSB/Sur/1252 | Sur | 2 | 4 | 2025-05-11 | IPC - 15 | 2.5 | Sualkuchi | 314
P21-WELL-L07 | P21 - 7th Lift | 402.a | MPSB/Str/1471 | Str | 3 | 4 | 2025-05-11 | IPC - 15 | 2.5 | Sualkuchi | 314
P21-WELL-L07 | P21 - 7th Lift | 402.a | MPSB/Sur/1285 | Sur | 4 | 4 | 2025-05-16 | IPC - 15 | 2.5 | Sualkuchi | 314
P22-WELL-L07 | P22 - 7th Lift | 402.a | MPSB/Str/437 | Str | 1 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 315
P22-WELL-L07 | P22 - 7th Lift | 402.a | MPSB/Sur/374 | Sur | 2 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 315
P22-WELL-L07 | P22 - 7th Lift | 402.a | MPSB/Str/438 | Str | 3 | 4 | 2025-01-27 | IPC - 10 | 2.5 | Sualkuchi | 315
P22-WELL-L07 | P22 - 7th Lift | 402.a | MPSB/Sur/400 | Sur | 4 | 4 | 2025-01-31 | IPC - 10 | 2.5 | Sualkuchi | 315
P23-WELL-L07 | P23 - 7th Lift | 402.a | MPSB/Str/1877 | Str | 1 | 4 | 2025-07-24 | IPC - 18 | 2.5 | Sualkuchi | 316
P23-WELL-L07 | P23 - 7th Lift | 402.a | MPSB/Sur/1571 | Sur | 2 | 4 | 2025-07-24 | IPC - 18 | 2.5 | Sualkuchi | 316
P23-WELL-L07 | P23 - 7th Lift | 402.a | MPSB/Str/1878 | Str | 3 | 4 | 2025-07-24 | IPC - 18 | 2.5 | Sualkuchi | 316
P23-WELL-L07 | P23 - 7th Lift | 402.a | MPSB/Sur/1609 | Sur | 4 | 4 | 2025-07-30 | IPC - 18 | 2.5 | Sualkuchi | 316
P24-WELL-L07 | P24 - 7th Lift | 402.a | MPSB/Str/573 | Str | 1 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Sualkuchi | 317
P24-WELL-L07 | P24 - 7th Lift | 402.a | MPSB/Sur/504 | Sur | 2 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Sualkuchi | 317
P24-WELL-L07 | P24 - 7th Lift | 402.a | MPSB/Str/574 | Str | 3 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Sualkuchi | 317
P24-WELL-L07 | P24 - 7th Lift | 402.a | MPSB/Sur/542 | Sur | 4 | 4 | 2025-02-24 | IPC - 11 | 2.5 | Sualkuchi | 317
P25-WELL-L07 | P25 - 7th Lift | 402.a | MPSB/Str/863 | Str | 1 | 4 | 2025-03-23 | IPC - 13 | 2.5 | Sualkuchi | 318
P25-WELL-L07 | P25 - 7th Lift | 402.a | MPSB/Sur/771 | Sur | 2 | 4 | 2025-03-24 | IPC - 13 | 2.5 | Sualkuchi | 318
P25-WELL-L07 | P25 - 7th Lift | 402.a | MPSB/Str/864 | Str | 3 | 4 | 2025-03-23 | IPC - 13 | 2.5 | Sualkuchi | 318
P25-WELL-L07 | P25 - 7th Lift | 402.a | MPSB/Sur/806 | Sur | 4 | 4 | 2025-03-27 | IPC - 13 | 2.5 | Sualkuchi | 318
P26-WELL-L07 | P26 - 7th Lift | 402.a | MPSB/Str/516 | Str | 1 | 4 | 2025-02-10 | IPC - 11 | 2.5 | Sualkuchi | 319
P26-WELL-L07 | P26 - 7th Lift | 402.a | MPSB/Sur/467 | Sur | 2 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Sualkuchi | 319
P26-WELL-L07 | P26 - 7th Lift | 402.a | MPSB/Str/541 | Str | 3 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Sualkuchi | 319
P26-WELL-L07 | P26 - 7th Lift | 402.a | MPSB/Sur/492 | Sur | 4 | 4 | 2025-02-18 | IPC - 11 | 2.5 | Sualkuchi | 319
P27-WELL-L07 | P27 - 7th Lift | 402.a | MPSB/Str/1590 | Str | 1 | 3 | 2025-05-28 | IPC - 15 | 2.5 | Sualkuchi | 320
P27-WELL-L07 | P27 - 7th Lift | 402.a | MPSB/Sur/1372 | Sur | 2 | 3 | 2025-05-28 | IPC - 15 | 2.5 | Sualkuchi | 320
P27-WELL-L07 | P27 - 7th Lift | 402.a | MPSB/Str/1591 | Str | 3 | 3 | 2025-05-28 | IPC - 15 | 2.5 | Sualkuchi | 320
P28-WELL-L07 | P28 - 7th Lift | 402.a | MPSB/Str/762 | Str | 1 | 4 | 2025-03-10 | IPC - 13 | 2.51 | Sualkuchi | 321
P28-WELL-L07 | P28 - 7th Lift | 402.a | MPSB/Sur/675 | Sur | 2 | 4 | 2025-03-10 | IPC - 13 | 2.51 | Sualkuchi | 321
P28-WELL-L07 | P28 - 7th Lift | 402.a | MPSB/Str/763 | Str | 3 | 4 | 2025-03-10 | IPC - 13 | 2.51 | Sualkuchi | 321
P28-WELL-L07 | P28 - 7th Lift | 402.a | MPSB/Sur/709 | Sur | 4 | 4 | 2025-03-13 | IPC - 13 | 2.51 | Sualkuchi | 321
P29-WELL-L07 | P29 - 7th Lift | 402.a | MPSB/Str/1207 | Str | 1 | 3 | 2025-04-21 | IPC - 14 | 2.5 | Sualkuchi | 322
P29-WELL-L07 | P29 - 7th Lift | 402.a | MPSB/Sur/1051 | Sur | 2 | 3 | 2025-04-21 | IPC - 14 | 2.5 | Sualkuchi | 322
P29-WELL-L07 | P29 - 7th Lift | 402.a | MPSB/Str/1208 | Str | 3 | 3 | 2025-04-21 | IPC - 14 | 2.5 | Sualkuchi | 322
P30-WELL-L07 | P30 - 7th Lift | 402.a | MPSB/Str/3201 | Str | 1 | 4 | 2025-12-19 | IPC - 25 | 2.5 | Sualkuchi | 323
P30-WELL-L07 | P30 - 7th Lift | 402.a | MPSB/Sur/2448 | Sur | 2 | 4 | 2025-12-19 | IPC - 25 | 2.5 | Sualkuchi | 323
P30-WELL-L07 | P30 - 7th Lift | 402.a | MPSB/Str/3202 | Str | 3 | 4 | 2025-12-19 | IPC - 25 | 2.5 | Sualkuchi | 323
P30-WELL-L07 | P30 - 7th Lift | 402.a | MPSB/Sur/2469 | Sur | 4 | 4 | 2025-12-22 | IPC - 25 | 2.5 | Sualkuchi | 323
P6-WELL-L07 | P6 - 7th Lift | 402.a | MPSB/Str/547 | Str | 1 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Palashbari | 324
P6-WELL-L07 | P6 - 7th Lift | 402.a | MPSB/Sur/459 | Sur | 2 | 4 | 2025-02-12 | IPC - 11 | 2.5 | Palashbari | 324
P6-WELL-L07 | P6 - 7th Lift | 402.a | MPSB/Str/548 | Str | 3 | 4 | 2025-02-15 | IPC - 11 | 2.5 | Palashbari | 324
P6-WELL-L07 | P6 - 7th Lift | 402.a | MPSB/Sur/507 | Sur | 4 | 4 | 2025-02-19 | IPC - 11 | 2.5 | Palashbari | 324
P7-WELL-L07 | P7 - 7th Lift | 402.a | MPSB/Str/1504 | Str | 1 | 4 | 2025-05-16 | IPC - 15 | 2.5 | Palashbari | 325
P7-WELL-L07 | P7 - 7th Lift | 402.a | MPSB/Sur/1294 | Sur | 2 | 4 | 2025-05-16 | IPC - 15 | 2.5 | Palashbari | 325
P7-WELL-L07 | P7 - 7th Lift | 402.a | MPSB/Str/1505 | Str | 3 | 4 | 2025-05-16 | IPC - 15 | 2.5 | Palashbari | 325
P7-WELL-L07 | P7 - 7th Lift | 402.a | MPSB/Sur/1384 | Sur | 4 | 4 | 2025-05-29 | IPC - 15 | 2.5 | Palashbari | 325
P8-WELL-L07 | P8 - 7th Lift | 402.a | MPSB/Str/825 | Str | 1 | 3 | 2025-03-18 | IPC - 13 | 2.51 | Palashbari | 326
P8-WELL-L07 | P8 - 7th Lift | 402.a | MPSB/Str/826 | Str | 2 | 3 | 2025-03-18 | IPC - 13 | 2.51 | Palashbari | 326
P8-WELL-L07 | P8 - 7th Lift | 402.a | MPSB/Sur/737 | Sur | 3 | 3 | 2025-03-18 | IPC - 13 | 2.51 | Palashbari | 326
P9-WELL-L07 | P9 - 7th Lift | 402.a | MPSB/Str/1274 | Str | 1 | 3 | 2025-04-26 | IPC - 14 | 2.6 | Palashbari | 327
P9-WELL-L07 | P9 - 7th Lift | 402.a | MPSB/Sur/1103 | Sur | 2 | 3 | 2025-04-26 | IPC - 14 | 2.6 | Palashbari | 327
P9-WELL-L07 | P9 - 7th Lift | 402.a | MPSB/Str/1275 | Str | 3 | 3 | 2025-04-26 | IPC - 14 | 2.6 | Palashbari | 327
P6-WELL-L08 | P6 - 8th Lift | 402.a | MPSB/Str/654 | Str | 1 | 3 | 2025-02-27 | IPC - 11 | 0.5 | Palashbari | 329
P6-WELL-L08 | P6 - 8th Lift | 402.a | MPSB/Sur/570 | Sur | 2 | 3 | 2025-02-27 | IPC - 11 | 0.5 | Palashbari | 329
P6-WELL-L08 | P6 - 8th Lift | 402.a | MPSB/Str/655 | Str | 3 | 3 | 2025-02-27 | IPC - 11 | 0.5 | Palashbari | 329
P20-WELL-L08 | P20 - 8th Lift | 402.a | MPSB/Str/631 | Str | 1 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 330
P20-WELL-L08 | P20 - 8th Lift | 402.a | MPSB/Sur/558 | Sur | 2 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 330
P20-WELL-L08 | P20 - 8th Lift | 402.a | MPSB/Str/632 | Str | 3 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 330
P20-WELL-L08 | P20 - 8th Lift | 402.a | MPSB/Sur/574 | Sur | 4 | 4 | 2025-02-27 | IPC - 11 | 2.5 | Sualkuchi | 330
P24-WELL-L08 | P24 - 8th Lift | 402.a | MPSB/Str/635 | Str | 1 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 331
P24-WELL-L08 | P24 - 8th Lift | 402.a | MPSB/Sur/559 | Sur | 2 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 331
P24-WELL-L08 | P24 - 8th Lift | 402.a | MPSB/Str/636 | Str | 3 | 4 | 2025-02-25 | IPC - 11 | 2.5 | Sualkuchi | 331
P24-WELL-L08 | P24 - 8th Lift | 402.a | MPSB/Sur/576 | Sur | 4 | 4 | 2025-02-27 | IPC - 11 | 2.5 | Sualkuchi | 331
P8-WELL-L08 | P8 - 8th Lift | 402.a | MPSB/Str/987 | Str | 1 | 3 | 2025-03-30 | IPC - 13 | 2.5 | Palashbari | 332
P8-WELL-L08 | P8 - 8th Lift | 402.a | MPSB/Str/988 | Str | 2 | 3 | 2025-03-30 | IPC - 13 | 2.5 | Palashbari | 332
P8-WELL-L08 | P8 - 8th Lift | 402.a | MPSB/Sur/856 | Sur | 3 | 3 | 2025-03-30 | IPC - 13 | 2.5 | Palashbari | 332
P16-WELL-L08 | P16 - 8th Lift | 402.a | MPSB/Str/912 | Str | 1 | 3 | 2025-03-26 | IPC - 13 | 2.8 | Palashbari | 333
P16-WELL-L08 | P16 - 8th Lift | 402.a | MPSB/Str/913 | Str | 2 | 3 | 2025-03-26 | IPC - 13 | 2.8 | Palashbari | 333
P16-WELL-L08 | P16 - 8th Lift | 402.a | MPSB/Sur/797 | Sur | 3 | 3 | 2025-03-26 | IPC - 13 | 2.8 | Palashbari | 333
P18-WELL-L08 | P18 - 8th Lift | 402.a | MPSB/Str/928 | Str | 1 | 3 | 2025-03-27 | IPC - 13 | 0.5 | Sualkuchi | 334
P18-WELL-L08 | P18 - 8th Lift | 402.a | MPSB/Sur/807 | Sur | 2 | 3 | 2025-03-27 | IPC - 13 | 0.5 | Sualkuchi | 334
P18-WELL-L08 | P18 - 8th Lift | 402.a | MPSB/Str/929 | Str | 3 | 3 | 2025-03-27 | IPC - 13 | 0.5 | Sualkuchi | 334
P22-WELL-L08 | P22 - 8th Lift | 402.a | MPSB/Str/760 | Str | 1 | 4 | 2025-03-10 | IPC - 13 | 1.31 | Sualkuchi | 335
P22-WELL-L08 | P22 - 8th Lift | 402.a | MPSB/Sur/674 | Sur | 2 | 4 | 2025-03-10 | IPC - 13 | 1.31 | Sualkuchi | 335
P22-WELL-L08 | P22 - 8th Lift | 402.a | MPSB/Str/761 | Str | 3 | 4 | 2025-03-10 | IPC - 13 | 1.31 | Sualkuchi | 335
P22-WELL-L08 | P22 - 8th Lift | 402.a | MPSB/Sur/711 | Sur | 4 | 4 | 2025-03-13 | IPC - 13 | 1.31 | Sualkuchi | 335
P26-WELL-L08 | P26 - 8th Lift | 402.a | MPSB/Str/855 | Str | 1 | 4 | 2025-03-22 | IPC - 13 | 0.51 | Sualkuchi | 336
P26-WELL-L08 | P26 - 8th Lift | 402.a | MPSB/Sur/763 | Sur | 2 | 4 | 2025-03-22 | IPC - 13 | 0.51 | Sualkuchi | 336
P26-WELL-L08 | P26 - 8th Lift | 402.a | MPSB/Str/862 | Str | 3 | 4 | 2025-03-23 | IPC - 13 | 0.51 | Sualkuchi | 336
P26-WELL-L08 | P26 - 8th Lift | 402.a | MPSB/Sur/888 | Sur | 4 | 4 | 2025-03-31 | IPC - 13 | 0.51 | Sualkuchi | 336
P28-WELL-L08 | P28 - 8th Lift | 402.a | MPSB/Str/830 | Str | 1 | 4 | 2025-03-19 | IPC - 13 | 2.5 | Sualkuchi | 337
P28-WELL-L08 | P28 - 8th Lift | 402.a | MPSB/Sur/743 | Sur | 2 | 4 | 2025-03-19 | IPC - 13 | 2.5 | Sualkuchi | 337
P28-WELL-L08 | P28 - 8th Lift | 402.a | MPSB/Str/831 | Str | 3 | 4 | 2025-03-19 | IPC - 13 | 2.5 | Sualkuchi | 337
P28-WELL-L08 | P28 - 8th Lift | 402.a | MPSB/Sur/767 | Sur | 4 | 4 | 2025-03-23 | IPC - 13 | 2.5 | Sualkuchi | 337
P9-WELL-L08 | P9 - 8th Lift | 402.a | MPSB/Str/1386 | Str | 1 | 3 | 2025-04-30 | IPC - 14 | 2.5 | Palashbari | 338
P9-WELL-L08 | P9 - 8th Lift | 402.a | MPSB/Sur/1179 | Sur | 2 | 3 | 2025-04-30 | IPC - 14 | 2.5 | Palashbari | 338
P9-WELL-L08 | P9 - 8th Lift | 402.a | MPSB/Str/1387 | Str | 3 | 3 | 2025-04-30 | IPC - 14 | 2.5 | Palashbari | 338
P10-WELL-L08 | P10 - 8th Lift | 402.a | MPSB/Str/1216 | Str | 1 | 3 | 2025-04-21 | IPC - 14 | 0.545 | Palashbari | 339
P10-WELL-L08 | P10 - 8th Lift | 402.a | MPSB/Sur/1057 | Sur | 2 | 3 | 2025-04-21 | IPC - 14 | 0.545 | Palashbari | 339
P10-WELL-L08 | P10 - 8th Lift | 402.a | MPSB/Str/1217 | Str | 3 | 3 | 2025-04-21 | IPC - 14 | 0.545 | Palashbari | 339
P17-WELL-L08 | P17 - 8th Lift | 402.a | MPSB/Str/1189 | Str | 1 | 3 | 2025-04-19 | IPC - 14 | 2.5 | Palashbari | 340
P17-WELL-L08 | P17 - 8th Lift | 402.a | MPSB/Sur/1032 | Sur | 2 | 3 | 2025-04-19 | IPC - 14 | 2.5 | Palashbari | 340
P17-WELL-L08 | P17 - 8th Lift | 402.a | MPSB/Str/1190 | Str | 3 | 3 | 2025-04-19 | IPC - 14 | 2.5 | Palashbari | 340
P19-WELL-L08 | P19 - 8th Lift | 402.a | MPSB/Str/1351 | Str | 1 | 3 | 2025-04-30 | IPC - 14 | 2 | Sualkuchi | 341
P19-WELL-L08 | P19 - 8th Lift | 402.a | MPSB/Sur/1157 | Sur | 2 | 3 | 2025-04-30 | IPC - 14 | 2 | Sualkuchi | 341
P19-WELL-L08 | P19 - 8th Lift | 402.a | MPSB/Str/1352 | Str | 3 | 3 | 2025-04-30 | IPC - 14 | 2 | Sualkuchi | 341
P25-WELL-L08 | P25 - 8th Lift | 402.a | MPSB/Str/1132 | Str | 1 | 4 | 2025-04-14 | IPC - 14 | 1.3 | Sualkuchi | 342
P25-WELL-L08 | P25 - 8th Lift | 402.a | MPSB/Sur/993 | Sur | 2 | 4 | 2025-04-14 | IPC - 14 | 1.3 | Sualkuchi | 342
P25-WELL-L08 | P25 - 8th Lift | 402.a | MPSB/Str/1133 | Str | 3 | 4 | 2025-04-14 | IPC - 14 | 1.3 | Sualkuchi | 342
P25-WELL-L08 | P25 - 8th Lift | 402.a | MPSB/Sur/1036 | Sur | 4 | 4 | 2025-04-19 | IPC - 14 | 1.3 | Sualkuchi | 342
P15-WELL-L08 | P15 - 8th Lift | 402.a | MPSB/Str/1474 | Str | 1 | 4 | 2025-05-12 | IPC - 15 | 2.5 | Palashbari | 343
P15-WELL-L08 | P15 - 8th Lift | 402.a | MPSB/Sur/1254 | Sur | 2 | 4 | 2025-05-12 | IPC - 15 | 2.5 | Palashbari | 343
P15-WELL-L08 | P15 - 8th Lift | 402.a | MPSB/Str/1475 | Str | 3 | 4 | 2025-05-12 | IPC - 15 | 2.5 | Palashbari | 343
P15-WELL-L08 | P15 - 8th Lift | 402.a | MPSB/Sur/1289 | Sur | 4 | 4 | 2025-05-16 | IPC - 15 | 2.5 | Palashbari | 343
P29-WELL-L08 | P29 - 8th Lift | 402.a | MPSB/Str/1418 | Str | 1 | 4 | 2025-05-05 | IPC - 15 | 2.5 | Sualkuchi | 344
P29-WELL-L08 | P29 - 8th Lift | 402.a | MPSB/Sur/1218 | Sur | 2 | 4 | 2025-05-05 | IPC - 15 | 2.5 | Sualkuchi | 344
P29-WELL-L08 | P29 - 8th Lift | 402.a | MPSB/Str/1419 | Str | 3 | 4 | 2025-05-05 | IPC - 15 | 2.5 | Sualkuchi | 344
P29-WELL-L08 | P29 - 8th Lift | 402.a | MPSB/Sur/1303 | Sur | 4 | 4 | 2025-05-18 | IPC - 15 | 2.5 | Sualkuchi | 344
P7-WELL-L08 | P7 - 8th Lift | 402.a | MPSB/Str/1644 | Str | 1 | 4 | 2025-06-09 | IPC - 16 | 2.5 | Palashbari | 345
P7-WELL-L08 | P7 - 8th Lift | 402.a | MPSB/Sur/1409 | Sur | 2 | 4 | 2025-06-09 | IPC - 16 | 2.5 | Palashbari | 345
P7-WELL-L08 | P7 - 8th Lift | 402.a | MPSB/Str/1645 | Str | 3 | 4 | 2025-06-09 | IPC - 16 | 2.5 | Palashbari | 345
P7-WELL-L08 | P7 - 8th Lift | 402.a | MPSB/Sur/1434 | Sur | 4 | 4 | 2025-06-17 | IPC - 16 | 2.5 | Palashbari | 345
P27-WELL-L08 | P27 - 8th Lift | 402.a | MPSB/Str/1699 | Str | 1 | 4 | 2025-06-24 | IPC - 16 | 2 | Sualkuchi | 346
P27-WELL-L08 | P27 - 8th Lift | 402.a | MPSB/Sur/1457 | Sur | 2 | 4 | 2025-06-24 | IPC - 16 | 2 | Sualkuchi | 346
P27-WELL-L08 | P27 - 8th Lift | 402.a | MPSB/Str/1700 | Str | 3 | 4 | 2025-06-24 | IPC - 16 | 2 | Sualkuchi | 346
P27-WELL-L08 | P27 - 8th Lift | 402.a | MPSB/Sur/1470 | Sur | 4 | 4 | 2025-06-28 | IPC - 16 | 2 | Sualkuchi | 346
P21-WELL-L08 | P21 - 8th Lift | 402.a | MPSB/Str/2065 | Str | 1 | 4 | 2025-08-21 | IPC - 19 | 2.5 | Sualkuchi | 347
P21-WELL-L08 | P21 - 8th Lift | 402.a | MPSB/Sur/1715 | Sur | 2 | 4 | 2025-08-21 | IPC - 19 | 2.5 | Sualkuchi | 347
P21-WELL-L08 | P21 - 8th Lift | 402.a | MPSB/Str/2066 | Str | 3 | 4 | 2025-08-21 | IPC - 19 | 2.5 | Sualkuchi | 347
P21-WELL-L08 | P21 - 8th Lift | 402.a | MPSB/Sur/1750 | Sur | 4 | 4 | 2025-08-30 | IPC - 19 | 2.5 | Sualkuchi | 347
P23-WELL-L08 | P23 - 8th Lift | 402.a | MPSB/Str/2058 | Str | 1 | 4 | 2025-08-21 | IPC - 20 | 2.5 | Sualkuchi | 348
P23-WELL-L08 | P23 - 8th Lift | 402.a | MPSB/Sur/1726 | Sur | 2 | 4 | 2025-08-23 | IPC - 20 | 2.5 | Sualkuchi | 348
P23-WELL-L08 | P23 - 8th Lift | 402.a | MPSB/Str/2075 | Str | 3 | 4 | 2025-08-23 | IPC - 20 | 2.5 | Sualkuchi | 348
P23-WELL-L08 | P23 - 8th Lift | 402.a | MPSB/Sur/1761 | Sur | 4 | 4 | 2025-09-03 | IPC - 20 | 2.5 | Sualkuchi | 348
P30-WELL-L08 | P30 - 8th Lift | 402.a | MPSB/Str/3307 | Str | 1 | 3 | 2025-12-28 | IPC - 25 | 0.5 | Sualkuchi | 349
P30-WELL-L08 | P30 - 8th Lift | 402.a | MPSB/Sur/2526 | Sur | 2 | 3 | 2025-12-28 | IPC - 25 | 0.5 | Sualkuchi | 349
P30-WELL-L08 | P30 - 8th Lift | 402.a | MPSB/Str/3308 | Str | 3 | 3 | 2025-12-28 | IPC - 25 | 0.5 | Sualkuchi | 349
P14(N)-WELL-L08 | P14(N) - 8th Lift | 402.a | MPSB/Str/3977 | Str | 1 | 3 | 2026-02-27 | IPC - 27 | 3.32 | Palashbari | 350
P14(N)-WELL-L08 | P14(N) - 8th Lift | 402.a | MPSB/Sur/3018 | Sur | 2 | 3 | 2026-02-27 | IPC - 27 | 3.32 | Palashbari | 350
P14(N)-WELL-L08 | P14(N) - 8th Lift | 402.a | MPSB/Str/3978 | Str | 3 | 3 | 2026-02-27 | IPC - 27 | 3.32 | Palashbari | 350
P11-WELL-L08 | P11 - 8th Lift | 402.a | MPSB/Str/4215 | Str | 1 | 3 | 2026-03-27 | IPC - 29 | 2.5 | Palashbari | 351
P11-WELL-L08 | P11 - 8th Lift | 402.a | MPSB/Sur/3180 | Sur | 2 | 3 | 2026-03-27 | IPC - 29 | 2.5 | Palashbari | 351
P11-WELL-L08 | P11 - 8th Lift | 402.a | MPSB/Str/4216 | Str | 3 | 3 | 2026-03-27 | IPC - 29 | 2.5 | Palashbari | 351
P13-WELL-L08 | P13 - 8th Lift | 402.a | MPSB/Str/4272 | Str | 1 | 3 | 2026-03-31 | IPC - 29 | 2.5 | Palashbari | 352
P13-WELL-L08 | P13 - 8th Lift | 402.a | MPSB/Sur/3209 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 2.5 | Palashbari | 352
P13-WELL-L08 | P13 - 8th Lift | 402.a | MPSB/Str/4273 | Str | 3 | 3 | 2026-03-31 | IPC - 29 | 2.5 | Palashbari | 352
P12(A)-WELL-L08 | P12(A) - 8th Lift | 402.a | MPSB/Str/4257 | Str | 1 | 4 | 2026-03-30 | IPC - 33 | 3.45 | Palashbari | 353
P12(A)-WELL-L08 | P12(A) - 8th Lift | 402.a | MPSB/Sur/3202 | Sur | 2 | 4 | 2026-03-30 | IPC - 33 | 3.45 | Palashbari | 353
P12(A)-WELL-L08 | P12(A) - 8th Lift | 402.a | MPSB/Str/4258 | Str | 3 | 4 | 2026-03-30 | IPC - 33 | 3.45 | Palashbari | 353
P12(A)-WELL-L08 | P12(A) - 8th Lift | 402.a | MPSB/Sur/3237 | Sur | 4 | 4 | 2026-04-03 | IPC - 33 | 3.45 | Palashbari | 353 | P12(A)-WELL-L07
P6-WELL-L09 | P6 - 9th Lift | 402.a | MPSB/Str/712 | Str | 1 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 355
P6-WELL-L09 | P6 - 9th Lift | 402.a | MPSB/Sur/627 | Sur | 2 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 355
P6-WELL-L09 | P6 - 9th Lift | 402.a | MPSB/Str/713 | Str | 3 | 3 | 2025-02-28 | IPC - 11 | 2.5 | Palashbari | 355
P16-WELL-L09 | P16 - 9th Lift | 402.a | MPSB/Str/989 | Str | 1 | 3 | 2025-03-31 | IPC - 13 | 2.8 | Palashbari | 356
P16-WELL-L09 | P16 - 9th Lift | 402.a | MPSB/Str/990 | Str | 2 | 3 | 2025-03-31 | IPC - 13 | 2.8 | Palashbari | 356
P16-WELL-L09 | P16 - 9th Lift | 402.a | MPSB/Sur/858 | Sur | 3 | 3 | 2025-03-31 | IPC - 13 | 2.8 | Palashbari | 356
P18-WELL-L09 | P18 - 9th Lift | 402.a | MPSB/Str/939 | Str | 1 | 3 | 2025-03-28 | IPC - 13 | 2.8 | Sualkuchi | 357
P18-WELL-L09 | P18 - 9th Lift | 402.a | MPSB/Str/940 | Str | 2 | 3 | 2025-03-28 | IPC - 13 | 2.8 | Sualkuchi | 357
P18-WELL-L09 | P18 - 9th Lift | 402.a | MPSB/Sur/818 | Sur | 3 | 3 | 2025-03-28 | IPC - 13 | 2.8 | Sualkuchi | 357
P20-WELL-L09 | P20 - 9th Lift | 402.a | MPSB/Str/812 | Str | 1 | 4 | 2025-03-17 | IPC - 13 | 2.51 | Sualkuchi | 358
P20-WELL-L09 | P20 - 9th Lift | 402.a | MPSB/Sur/725 | Sur | 2 | 4 | 2025-03-17 | IPC - 13 | 2.51 | Sualkuchi | 358
P20-WELL-L09 | P20 - 9th Lift | 402.a | MPSB/Str/813 | Str | 3 | 4 | 2025-03-17 | IPC - 13 | 2.51 | Sualkuchi | 358
P20-WELL-L09 | P20 - 9th Lift | 402.a | MPSB/Sur/750 | Sur | 4 | 4 | 2025-03-20 | IPC - 13 | 2.51 | Sualkuchi | 358
P24-WELL-L09 | P24 - 9th Lift | 402.a | MPSB/Str/773 | Str | 1 | 4 | 2025-03-11 | IPC - 13 | 2.51 | Sualkuchi | 359
P24-WELL-L09 | P24 - 9th Lift | 402.a | MPSB/Sur/687 | Sur | 2 | 4 | 2025-03-11 | IPC - 13 | 2.51 | Sualkuchi | 359
P24-WELL-L09 | P24 - 9th Lift | 402.a | MPSB/Str/774 | Str | 3 | 4 | 2025-03-11 | IPC - 13 | 2.51 | Sualkuchi | 359
P24-WELL-L09 | P24 - 9th Lift | 402.a | MPSB/Sur/716 | Sur | 4 | 4 | 2025-03-15 | IPC - 13 | 2.51 | Sualkuchi | 359
P26-WELL-L09 | P26 - 9th Lift | 402.a | MPSB/Str/930 | Str | 1 | 4 | 2025-03-27 | IPC - 13 | 2.8 | Sualkuchi | 360
P26-WELL-L09 | P26 - 9th Lift | 402.a | MPSB/Sur/808 | Sur | 2 | 4 | 2025-03-27 | IPC - 13 | 2.8 | Sualkuchi | 360
P26-WELL-L09 | P26 - 9th Lift | 402.a | MPSB/Str/931 | Str | 3 | 4 | 2025-03-27 | IPC - 13 | 2.8 | Sualkuchi | 360
P26-WELL-L09 | P26 - 9th Lift | 402.a | MPSB/Sur/890 | Sur | 4 | 4 | 2025-03-31 | IPC - 13 | 2.8 | Sualkuchi | 360
P28-WELL-L09 | P28 - 9th Lift | 402.a | MPSB/Str/902 | Str | 1 | 4 | 2025-03-26 | IPC - 13 | 2.5 | Sualkuchi | 361
P28-WELL-L09 | P28 - 9th Lift | 402.a | MPSB/Sur/789 | Sur | 2 | 4 | 2025-03-26 | IPC - 13 | 2.5 | Sualkuchi | 361
P28-WELL-L09 | P28 - 9th Lift | 402.a | MPSB/Str/903 | Str | 3 | 4 | 2025-03-26 | IPC - 13 | 2.5 | Sualkuchi | 361
P28-WELL-L09 | P28 - 9th Lift | 402.a | MPSB/Sur/854 | Sur | 4 | 4 | 2025-03-30 | IPC - 13 | 2.5 | Sualkuchi | 361
P8-WELL-L09 | P8 - 9th Lift | 402.a | MPSB/Str/1276 | Str | 1 | 3 | 2025-04-26 | IPC - 14 | 2.5 | Palashbari | 362
P8-WELL-L09 | P8 - 9th Lift | 402.a | MPSB/Sur/1104 | Sur | 2 | 3 | 2025-04-26 | IPC - 14 | 2.5 | Palashbari | 362
P8-WELL-L09 | P8 - 9th Lift | 402.a | MPSB/Str/1277 | Str | 3 | 3 | 2025-04-26 | IPC - 14 | 2.5 | Palashbari | 362
P10-WELL-L09 | P10 - 9th Lift | 402.a | MPSB/Str/1248 | Str | 1 | 3 | 2025-04-24 | IPC - 14 | 2.81 | Palashbari | 363
P10-WELL-L09 | P10 - 9th Lift | 402.a | MPSB/Sur/1077 | Sur | 2 | 3 | 2025-04-24 | IPC - 14 | 2.81 | Palashbari | 363
P10-WELL-L09 | P10 - 9th Lift | 402.a | MPSB/Str/1249 | Str | 3 | 3 | 2025-04-24 | IPC - 14 | 2.81 | Palashbari | 363
P22-WELL-L09 | P22 - 9th Lift | 402.a | MPSB/Str/1203 | Str | 1 | 3 | 2025-04-21 | IPC - 14 | 0.5 | Palashbari | 364
P22-WELL-L09 | P22 - 9th Lift | 402.a | MPSB/Sur/1047 | Sur | 2 | 3 | 2025-04-21 | IPC - 14 | 0.5 | Palashbari | 364
P22-WELL-L09 | P22 - 9th Lift | 402.a | MPSB/Str/1204 | Str | 3 | 3 | 2025-04-21 | IPC - 14 | 0.5 | Palashbari | 364
P25-WELL-L09 | P25 - 9th Lift | 402.a | MPSB/Str/1244 | Str | 1 | 3 | 2025-04-24 | IPC - 14 | 2.7 | Sualkuchi | 365
P25-WELL-L09 | P25 - 9th Lift | 402.a | MPSB/Sur/1076 | Sur | 2 | 3 | 2025-04-24 | IPC - 14 | 2.7 | Sualkuchi | 365
P25-WELL-L09 | P25 - 9th Lift | 402.a | MPSB/Str/1245 | Str | 3 | 3 | 2025-04-24 | IPC - 14 | 2.7 | Sualkuchi | 365
P15-WELL-L09 | P15 - 9th Lift | 402.a | MPSB/Str/1538 | Str | 1 | 4 | 2025-05-21 | IPC - 15 | 2.5 | Palashbari | 366
P15-WELL-L09 | P15 - 9th Lift | 402.a | MPSB/Sur/1325 | Sur | 2 | 4 | 2025-05-21 | IPC - 15 | 2.5 | Palashbari | 366
P15-WELL-L09 | P15 - 9th Lift | 402.a | MPSB/Str/1539 | Str | 3 | 4 | 2025-05-21 | IPC - 15 | 2.5 | Palashbari | 366
P15-WELL-L09 | P15 - 9th Lift | 402.a | MPSB/Sur/1347 | Sur | 4 | 4 | 2025-05-26 | IPC - 15 | 2.5 | Palashbari | 366
P17-WELL-L09 | P17 - 9th Lift | 402.a | MPSB/Str/1462 | Str | 1 | 3 | 2025-05-10 | IPC - 15 | 1.05 | Palashbari | 367
P17-WELL-L09 | P17 - 9th Lift | 402.a | MPSB/Sur/1249 | Sur | 2 | 3 | 2025-05-10 | IPC - 15 | 1.05 | Palashbari | 367
P17-WELL-L09 | P17 - 9th Lift | 402.a | MPSB/Str/1463 | Str | 3 | 3 | 2025-05-10 | IPC - 15 | 1.05 | Palashbari | 367
P19-WELL-L09 | P19 - 9th Lift | 402.a | MPSB/Str/1506 | Str | 1 | 4 | 2025-05-17 | IPC - 15 | 2.7 | Sualkuchi | 368
P19-WELL-L09 | P19 - 9th Lift | 402.a | MPSB/Sur/1295 | Sur | 2 | 4 | 2025-05-17 | IPC - 15 | 2.7 | Sualkuchi | 368
P19-WELL-L09 | P19 - 9th Lift | 402.a | MPSB/Str/1507 | Str | 3 | 4 | 2025-05-17 | IPC - 15 | 2.7 | Sualkuchi | 368
P19-WELL-L09 | P19 - 9th Lift | 402.a | MPSB/Sur/1355 | Sur | 4 | 4 | 2025-05-26 | IPC - 15 | 2.7 | Sualkuchi | 368
P29-WELL-L09 | P29 - 9th Lift | 402.a | MPSB/Str/1489 | Str | 1 | 4 | 2025-05-14 | IPC - 15 | 2.2 | Sualkuchi | 369
P29-WELL-L09 | P29 - 9th Lift | 402.a | MPSB/Sur/1275 | Sur | 2 | 4 | 2025-05-14 | IPC - 15 | 2.2 | Sualkuchi | 369
P29-WELL-L09 | P29 - 9th Lift | 402.a | MPSB/Str/1490 | Str | 3 | 4 | 2025-05-14 | IPC - 15 | 2.2 | Sualkuchi | 369
P29-WELL-L09 | P29 - 9th Lift | 402.a | MPSB/Sur/1324 | Sur | 4 | 4 | 2025-05-20 | IPC - 15 | 2.2 | Sualkuchi | 369
P9-WELL-L09 | P9 - 9th Lift | 402.a | MPSB/Str/1667 | Str | 1 | 3 | 2025-06-16 | IPC - 16 | 2.5 | Palashbari | 370
P9-WELL-L09 | P9 - 9th Lift | 402.a | MPSB/Sur/1426 | Sur | 2 | 3 | 2025-06-16 | IPC - 16 | 2.5 | Palashbari | 370
P9-WELL-L09 | P9 - 9th Lift | 402.a | MPSB/Str/1668 | Str | 3 | 3 | 2025-06-16 | IPC - 16 | 2.5 | Palashbari | 370
P7-WELL-L09 | P7 - 9th Lift | 402.a | MPSB/Str/1803 | Str | 1 | 3 | 2025-07-12 | IPC - 18 | 2.7 | Sualkuchi | 371
P7-WELL-L09 | P7 - 9th Lift | 402.a | MPSB/Sur/1517 | Sur | 2 | 3 | 2025-07-12 | IPC - 18 | 2.7 | Sualkuchi | 371
P7-WELL-L09 | P7 - 9th Lift | 402.a | MPSB/Str/1804 | Str | 3 | 3 | 2025-07-12 | IPC - 18 | 2.7 | Sualkuchi | 371
P27-WELL-L09 | P27 - 9th Lift | 402.a | MPSB/Str/1924 | Str | 1 | 3 | 2025-07-30 | IPC - 18 | 2.7 | Sualkuchi | 372
P27-WELL-L09 | P27 - 9th Lift | 402.a | MPSB/Sur/1610 | Sur | 2 | 3 | 2025-07-30 | IPC - 18 | 2.7 | Sualkuchi | 372
P27-WELL-L09 | P27 - 9th Lift | 402.a | MPSB/Str/1925 | Str | 3 | 3 | 2025-07-30 | IPC - 18 | 2.7 | Sualkuchi | 372
P21-WELL-L09 | P21 - 9th Lift | 402.a | MPSB/Str/2374 | Str | 1 | 3 | 2025-09-30 | IPC - 20 | 1.3 | Sualkuchi | 373
P21-WELL-L09 | P21 - 9th Lift | 402.a | MPSB/Sur/1903 | Sur | 2 | 3 | 2025-09-30 | IPC - 20 | 1.3 | Sualkuchi | 373
P21-WELL-L09 | P21 - 9th Lift | 402.a | MPSB/Str/2375 | Str | 3 | 3 | 2025-09-30 | IPC - 20 | 1.3 | Sualkuchi | 373
P23-WELL-L09 | P23 - 9th Lift | 402.a | MPSB/Str/2243 | Str | 1 | 4 | 2025-09-16 | IPC - 20 | 1.3 | Sualkuchi | 374
P23-WELL-L09 | P23 - 9th Lift | 402.a | MPSB/Sur/1828 | Sur | 2 | 4 | 2025-09-16 | IPC - 20 | 1.3 | Sualkuchi | 374
P23-WELL-L09 | P23 - 9th Lift | 402.a | MPSB/Str/2244 | Str | 3 | 4 | 2025-09-16 | IPC - 20 | 1.3 | Sualkuchi | 374
P23-WELL-L09 | P23 - 9th Lift | 402.a | MPSB/Sur/1905 | Sur | 4 | 4 | 2025-09-30 | IPC - 20 | 1.3 | Sualkuchi | 374
P30-WELL-L09 | P30 - 9th Lift | 402.a | MPSB/Str/3354 | Str | 1 | 3 | 2025-12-30 | IPC - 25 | 2.8 | Sualkuchi | 375
P30-WELL-L09 | P30 - 9th Lift | 402.a | MPSB/Sur/2555 | Sur | 2 | 3 | 2025-12-30 | IPC - 25 | 2.8 | Sualkuchi | 375
P30-WELL-L09 | P30 - 9th Lift | 402.a | MPSB/Str/3355 | Str | 3 | 3 | 2025-12-30 | IPC - 25 | 2.8 | Sualkuchi | 375
P14(N)-WELL-L09 | P14(N) - 9th Lift | 402.a | MPSB/Str/4097 | Str | 1 | 3 | 2026-03-13 | IPC - 29 | 2.5 | Palashbari | 376
P14(N)-WELL-L09 | P14(N) - 9th Lift | 402.a | MPSB/Sur/3109 | Sur | 2 | 3 | 2026-03-13 | IPC - 29 | 2.5 | Palashbari | 376
P14(N)-WELL-L09 | P14(N) - 9th Lift | 402.a | MPSB/Str/4096 | Str | 3 | 3 | 2026-03-13 | IPC - 29 | 2.5 | Palashbari | 376
P11-WELL-L09 | P11 - 9th Lift | 402.a | MPSB/Str/4345 | Str | 1 | 3 | 2026-04-07 | IPC - 30 | 2.7 | Palashbari | 377
P11-WELL-L09 | P11 - 9th Lift | 402.a | MPSB/Sur/3255 | Sur | 2 | 3 | 2026-04-07 | IPC - 30 | 2.7 | Palashbari | 377 | P11-WELL-L10
P11-WELL-L09 | P11 - 9th Lift | 402.a | MPSB/Str/4346 | Str | 3 | 3 | 2026-04-07 | IPC - 30 | 2.7 | Palashbari | 377
P13-WELL-L09 | P13 - 9th Lift | 402.a | MPSB/Str/4359 | Str | 1 | 3 | 2026-04-10 | IPC - 30 | 2.5 | Palashbari | 378
P13-WELL-L09 | P13 - 9th Lift | 402.a | MPSB/Sur/3264 | Sur | 2 | 3 | 2026-04-10 | IPC - 30 | 2.5 | Palashbari | 378
P13-WELL-L09 | P13 - 9th Lift | 402.a | MPSB/Str/4360 | Str | 3 | 3 | 2026-04-10 | IPC - 30 | 2.5 | Palashbari | 378
P12(A)-WELL-L09 | P12(A) - 9th Lift | 402.a | MPSB/Str/4362 | Str | 1 | 4 | 2026-04-10 | IPC - 33 | 2.8 | Palashbari | 379
P12(A)-WELL-L09 | P12(A) - 9th Lift | 402.a | MPSB/Sur/3269 | Sur | 2 | 4 | 2026-04-10 | IPC - 33 | 2.8 | Palashbari | 379
P12(A)-WELL-L09 | P12(A) - 9th Lift | 402.a | MPSB/Str/4363 | Str | 3 | 4 | 2026-04-10 | IPC - 33 | 2.8 | Palashbari | 379
P12(A)-WELL-L09 | P12(A) - 9th Lift | 402.a | MPSB/Sur/3321 | Sur | 4 | 4 | 2026-04-17 | IPC - 33 | 2.8 | Palashbari | 379 | P12(A)-WELL-L10
P6-WELL-L10 | P6 - 10th Lift | 402.a | MPSB/Str/1016 | Str | 1 | 3 | 2025-03-31 | IPC - 13 | 2.66 | Palashbari | 381
P6-WELL-L10 | P6 - 10th Lift | 402.a | MPSB/Sur/843 | Sur | 2 | 3 | 2025-03-31 | IPC - 13 | 2.66 | Palashbari | 381
P6-WELL-L10 | P6 - 10th Lift | 402.a | MPSB/Str/1017 | Str | 3 | 3 | 2025-03-31 | IPC - 13 | 2.66 | Palashbari | 381
P20-WELL-L10 | P20 - 10th Lift | 402.a | MPSB/Str/865 | Str | 1 | 4 | 2025-03-24 | IPC - 13 | 2.5 | Sualkuchi | 382
P20-WELL-L10 | P20 - 10th Lift | 402.a | MPSB/Sur/769 | Sur | 2 | 4 | 2025-03-24 | IPC - 13 | 2.5 | Sualkuchi | 382
P20-WELL-L10 | P20 - 10th Lift | 402.a | MPSB/Str/866 | Str | 3 | 4 | 2025-03-24 | IPC - 13 | 2.5 | Sualkuchi | 382
P20-WELL-L10 | P20 - 10th Lift | 402.a | MPSB/Sur/817 | Sur | 4 | 4 | 2025-03-28 | IPC - 13 | 2.5 | Sualkuchi | 382
P24-WELL-L10 | P24 - 10th Lift | 402.a | MPSB/Str/904 | Str | 1 | 3 | 2025-03-26 | IPC - 13 | 2.5 | Sualkuchi | 383
P24-WELL-L10 | P24 - 10th Lift | 402.a | MPSB/Sur/790 | Sur | 2 | 3 | 2025-03-26 | IPC - 13 | 2.5 | Sualkuchi | 383
P24-WELL-L10 | P24 - 10th Lift | 402.a | MPSB/Str/905 | Str | 3 | 3 | 2025-03-26 | IPC - 13 | 2.5 | Sualkuchi | 383
P8-WELL-L10 | P8 - 10th Lift | 402.a | MPSB/Str/1380 | Str | 1 | 3 | 2025-04-30 | IPC - 14 | 2.25 | Palashbari | 384
P8-WELL-L10 | P8 - 10th Lift | 402.a | MPSB/Sur/1176 | Sur | 2 | 3 | 2025-04-30 | IPC - 14 | 2.25 | Palashbari | 384
P8-WELL-L10 | P8 - 10th Lift | 402.a | MPSB/Str/1381 | Str | 3 | 3 | 2025-04-30 | IPC - 14 | 2.25 | Palashbari | 384
P18-WELL-L10 | P18 - 10th Lift | 402.a | MPSB/Str/1191 | Str | 1 | 3 | 2025-04-19 | IPC - 14 | 2.5 | Sualkuchi | 385
P18-WELL-L10 | P18 - 10th Lift | 402.a | MPSB/Sur/1037 | Sur | 2 | 3 | 2025-04-19 | IPC - 14 | 2.5 | Sualkuchi | 385
P18-WELL-L10 | P18 - 10th Lift | 402.a | MPSB/Str/1220 | Str | 3 | 3 | 2025-04-21 | IPC - 14 | 2.5 | Sualkuchi | 385
P22-WELL-L10 | P22 - 10th Lift | 402.a | MPSB/Str/1267 | Str | 1 | 3 | 2025-04-25 | IPC - 14 | 2.8 | Sualkuchi | 386
P22-WELL-L10 | P22 - 10th Lift | 402.a | MPSB/Sur/1127 | Sur | 2 | 3 | 2025-04-27 | IPC - 14 | 2.8 | Sualkuchi | 386
P22-WELL-L10 | P22 - 10th Lift | 402.a | MPSB/Str/1300 | Str | 3 | 3 | 2025-04-27 | IPC - 14 | 2.8 | Sualkuchi | 386
P25-WELL-L10 | P25 - 10th Lift | 402.a | MPSB/Str/1357 | Str | 1 | 3 | 2025-04-30 | IPC - 14 | 2.8 | Sualkuchi | 387
P25-WELL-L10 | P25 - 10th Lift | 402.a | MPSB/Sur/1160 | Sur | 2 | 3 | 2025-04-30 | IPC - 14 | 2.8 | Sualkuchi | 387
P25-WELL-L10 | P25 - 10th Lift | 402.a | MPSB/Str/1358 | Str | 3 | 3 | 2025-04-30 | IPC - 14 | 2.8 | Sualkuchi | 387
P26-WELL-L10 | P26 - 10th Lift | 402.a | MPSB/Str/1153 | Str | 1 | 4 | 2025-04-16 | IPC - 14 | 2.5 | Sualkuchi | 388
P26-WELL-L10 | P26 - 10th Lift | 402.a | MPSB/Sur/1003 | Sur | 2 | 4 | 2025-04-16 | IPC - 14 | 2.5 | Sualkuchi | 388
P26-WELL-L10 | P26 - 10th Lift | 402.a | MPSB/Str/1154 | Str | 3 | 4 | 2025-04-16 | IPC - 14 | 2.5 | Sualkuchi | 388
P26-WELL-L10 | P26 - 10th Lift | 402.a | MPSB/Sur/1066 | Sur | 4 | 4 | 2025-04-22 | IPC - 14 | 2.5 | Sualkuchi | 388
P28-WELL-L10 | P28 - 10th Lift | 402.a | MPSB/Str/1123 | Str | 1 | 4 | 2025-04-13 | IPC - 14 | 2.5 | Sualkuchi | 389
P28-WELL-L10 | P28 - 10th Lift | 402.a | MPSB/Sur/982 | Sur | 2 | 4 | 2025-04-13 | IPC - 14 | 2.5 | Sualkuchi | 389
P28-WELL-L10 | P28 - 10th Lift | 402.a | MPSB/Str/1124 | Str | 3 | 4 | 2025-04-13 | IPC - 14 | 2.5 | Sualkuchi | 389
P28-WELL-L10 | P28 - 10th Lift | 402.a | MPSB/Sur/1034 | Sur | 4 | 4 | 2025-04-19 | IPC - 14 | 2.5 | Sualkuchi | 389
P10-WELL-L10 | P10 - 10th Lift | 402.a | MPSB/Str/1472 | Str | 1 | 4 | 2025-05-11 | IPC - 15 | 2.5 | Palashbari | 390
P10-WELL-L10 | P10 - 10th Lift | 402.a | MPSB/Sur/1253 | Sur | 2 | 4 | 2025-05-11 | IPC - 15 | 2.5 | Palashbari | 390
P10-WELL-L10 | P10 - 10th Lift | 402.a | MPSB/Str/1473 | Str | 3 | 4 | 2025-05-11 | IPC - 15 | 2.5 | Palashbari | 390
P10-WELL-L10 | P10 - 10th Lift | 402.a | MPSB/Sur/1291 | Sur | 4 | 4 | 2025-05-16 | IPC - 15 | 2.5 | Palashbari | 390
P15-WELL-L10 | P15 - 10th Lift | 402.a | MPSB/Str/1604 | Str | 1 | 3 | 2025-05-30 | IPC - 15 | 2.5 | Palashbari | 391
P15-WELL-L10 | P15 - 10th Lift | 402.a | MPSB/Sur/1388 | Sur | 2 | 3 | 2025-05-30 | IPC - 15 | 2.5 | Palashbari | 391
P15-WELL-L10 | P15 - 10th Lift | 402.a | MPSB/Str/1605 | Str | 3 | 3 | 2025-05-30 | IPC - 15 | 2.5 | Palashbari | 391
P16-WELL-L10 | P16 - 10th Lift | 402.a | MPSB/Str/1436 | Str | 1 | 3 | 2025-05-07 | IPC - 15 | 2.5 | Palashbari | 392
P16-WELL-L10 | P16 - 10th Lift | 402.a | MPSB/Sur/1230 | Sur | 2 | 3 | 2025-05-07 | IPC - 15 | 2.5 | Palashbari | 392
P16-WELL-L10 | P16 - 10th Lift | 402.a | MPSB/Str/1437 | Str | 3 | 3 | 2025-05-07 | IPC - 15 | 2.5 | Palashbari | 392
P17-WELL-L10 | P17 - 10th Lift | 402.a | MPSB/Str/1588 | Str | 1 | 3 | 2025-05-28 | IPC - 15 | 1.88 | Palashbari | 393
P17-WELL-L10 | P17 - 10th Lift | 402.a | MPSB/Sur/1371 | Sur | 2 | 3 | 2025-05-28 | IPC - 15 | 1.88 | Palashbari | 393
P17-WELL-L10 | P17 - 10th Lift | 402.a | MPSB/Str/1589 | Str | 3 | 3 | 2025-05-28 | IPC - 15 | 1.88 | Palashbari | 393
P19-WELL-L10 | P19 - 10th Lift | 402.a | MPSB/Str/1548 | Str | 1 | 3 | 2025-05-22 | IPC - 15 | 2.8 | Sualkuchi | 394
P19-WELL-L10 | P19 - 10th Lift | 402.a | MPSB/Sur/1331 | Sur | 2 | 3 | 2025-05-22 | IPC - 15 | 2.8 | Sualkuchi | 394
P19-WELL-L10 | P19 - 10th Lift | 402.a | MPSB/Str/1549 | Str | 3 | 3 | 2025-05-22 | IPC - 15 | 2.8 | Sualkuchi | 394
P29-WELL-L10 | P29 - 10th Lift | 402.a | MPSB/Str/1563 | Str | 1 | 4 | 2025-05-24 | IPC - 15 | 2.8 | Sualkuchi | 395
P29-WELL-L10 | P29 - 10th Lift | 402.a | MPSB/Sur/1343 | Sur | 2 | 4 | 2025-05-24 | IPC - 15 | 2.8 | Sualkuchi | 395
P29-WELL-L10 | P29 - 10th Lift | 402.a | MPSB/Str/1564 | Str | 3 | 4 | 2025-05-24 | IPC - 15 | 2.8 | Sualkuchi | 395
P29-WELL-L10 | P29 - 10th Lift | 402.a | MPSB/Sur/1362 | Sur | 4 | 4 | 2025-05-27 | IPC - 15 | 2.8 | Sualkuchi | 395
P7-WELL-L10 | P7 - 10th Lift | 402.a | MPSB/Str/1853 | Str | 1 | 3 | 2025-07-21 | IPC - 18 | 2.95 | Sualkuchi | 396
P7-WELL-L10 | P7 - 10th Lift | 402.a | MPSB/Sur/1556 | Sur | 2 | 3 | 2025-07-21 | IPC - 18 | 2.95 | Sualkuchi | 396
P7-WELL-L10 | P7 - 10th Lift | 402.a | MPSB/Str/1854 | Str | 3 | 3 | 2025-07-21 | IPC - 18 | 2.95 | Sualkuchi | 396
P9-WELL-L10 | P9 - 10th Lift | 402.a | MPSB/Str/1976 | Str | 1 | 4 | 2025-08-05 | IPC - 19 | 2.7 | Palashbari | 397
P9-WELL-L10 | P9 - 10th Lift | 402.a | MPSB/Sur/1648 | Sur | 2 | 4 | 2025-08-05 | IPC - 19 | 2.7 | Palashbari | 397
P9-WELL-L10 | P9 - 10th Lift | 402.a | MPSB/Str/1977 | Str | 3 | 4 | 2025-08-05 | IPC - 19 | 2.7 | Palashbari | 397
P9-WELL-L10 | P9 - 10th Lift | 402.a | MPSB/Sur/1706 | Sur | 4 | 4 | 2025-08-20 | IPC - 19 | 2.7 | Palashbari | 397
P27-WELL-L10 | P27 - 10th Lift | 402.a | MPSB/Str/1994 | Str | 1 | 4 | 2025-08-07 | IPC - 19 | 2.8 | Sualkuchi | 398
P27-WELL-L10 | P27 - 10th Lift | 402.a | MPSB/Sur/1656 | Sur | 2 | 4 | 2025-08-07 | IPC - 19 | 2.8 | Sualkuchi | 398
P27-WELL-L10 | P27 - 10th Lift | 402.a | MPSB/Str/1995 | Str | 3 | 4 | 2025-08-07 | IPC - 19 | 2.8 | Sualkuchi | 398
P27-WELL-L10 | P27 - 10th Lift | 402.a | MPSB/Sur/1689 | Sur | 4 | 4 | 2025-08-14 | IPC - 19 | 2.8 | Sualkuchi | 398
P23-WELL-L10 | P23 - 10th Lift | 402.a | MPSB/Str/2552 | Str | 1 | 3 | 2025-10-23 | IPC - 22 | 2.8 | Sualkuchi | 399
P23-WELL-L10 | P23 - 10th Lift | 402.a | MPSB/Sur/2025 | Sur | 2 | 3 | 2025-10-23 | IPC - 22 | 2.8 | Sualkuchi | 399
P23-WELL-L10 | P23 - 10th Lift | 402.a | MPSB/Str/2553 | Str | 3 | 3 | 2025-10-23 | IPC - 22 | 2.8 | Sualkuchi | 399
P21-WELL-L10 | P21 - 10th Lift | 402.a | MPSB/Str/2934 | Str | 1 | 3 | 2025-11-26 | IPC - 23 | 2.7 | Sualkuchi | 400
P21-WELL-L10 | P21 - 10th Lift | 402.a | MPSB/Sur/2276 | Sur | 2 | 3 | 2025-11-26 | IPC - 23 | 2.7 | Sualkuchi | 400
P21-WELL-L10 | P21 - 10th Lift | 402.a | MPSB/Str/2935 | Str | 3 | 3 | 2025-11-26 | IPC - 23 | 2.7 | Sualkuchi | 400
P30-WELL-L10 | P30 - 10th Lift | 402.a | MPSB/Str/3510 | Str | 1 | 4 | 2026-01-13 | IPC - 26 | 2.5 | Sualkuchi | 401
P30-WELL-L10 | P30 - 10th Lift | 402.a | MPSB/Sur/2669 | Sur | 2 | 4 | 2026-01-13 | IPC - 26 | 2.5 | Sualkuchi | 401
P30-WELL-L10 | P30 - 10th Lift | 402.a | MPSB/Str/3511 | Str | 3 | 4 | 2026-01-13 | IPC - 26 | 2.5 | Sualkuchi | 401
P30-WELL-L10 | P30 - 10th Lift | 402.a | MPSB/Sur/2700 | Sur | 4 | 4 | 2026-01-17 | IPC - 26 | 2.5 | Sualkuchi | 401
P14(N)-WELL-L10 | P14(N) - 10th Lift | 402.a | MPSB/Str/4162 | Str | 1 | 3 | 2026-03-20 | IPC - 29 | 2.5 | Palashbari | 402
P14(N)-WELL-L10 | P14(N) - 10th Lift | 402.a | MPSB/Sur/3151 | Sur | 2 | 3 | 2026-03-20 | IPC - 29 | 2.5 | Palashbari | 402
P14(N)-WELL-L10 | P14(N) - 10th Lift | 402.a | MPSB/Str/4163 | Str | 3 | 3 | 2026-03-20 | IPC - 29 | 2.5 | Palashbari | 402
P11-WELL-L10 | P11 - 10th Lift | 402.a | MPSB/Str/4367 | Str | 1 | 3 | 2026-04-11 | IPC - 30 | 2.8 | Palashbari | 403
P11-WELL-L10 | P11 - 10th Lift | 402.a | MPSB/Sur/3255 | Sur | 2 | 3 | 2026-04-07 | IPC - 30 | 2.8 | Palashbari | 403 | P11-WELL-L09
P11-WELL-L10 | P11 - 10th Lift | 402.a | MPSB/Str/4368 | Str | 3 | 3 | 2026-04-11 | IPC - 30 | 2.8 | Palashbari | 403
P13-WELL-L10 | P13 - 10th Lift | 402.a | MPSB/Str/4416 | Str | 1 | 3 | 2026-04-16 | IPC - 30 | 2.5 | Palashbari | 404
P13-WELL-L10 | P13 - 10th Lift | 402.a | MPSB/Sur/3307 | Sur | 2 | 3 | 2026-04-16 | IPC - 30 | 2.5 | Palashbari | 404
P13-WELL-L10 | P13 - 10th Lift | 402.a | MPSB/Str/4417 | Str | 3 | 3 | 2026-04-16 | IPC - 30 | 2.5 | Palashbari | 404
P12(A)-WELL-L10 | P12(A) - 10th Lift | 402.a | MPSB/Str/4396 | Str | 1 | 4 | 2026-04-14 | IPC - 33 | 2.8 | Palashbari | 405
P12(A)-WELL-L10 | P12(A) - 10th Lift | 402.a | MPSB/Sur/3296 | Sur | 2 | 4 | 2026-04-14 | IPC - 33 | 2.8 | Palashbari | 405
P12(A)-WELL-L10 | P12(A) - 10th Lift | 402.a | MPSB/Str/4397 | Str | 3 | 4 | 2026-04-14 | IPC - 33 | 2.8 | Palashbari | 405
P12(A)-WELL-L10 | P12(A) - 10th Lift | 402.a | MPSB/Sur/3321 | Sur | 4 | 4 | 2026-04-17 | IPC - 33 | 2.8 | Palashbari | 405 | P12(A)-WELL-L09
P20-WELL-L11 | P20 - 11th Lift | 402.a | MPSB/Str/1008 | Str | 1 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Sualkuchi | 407
P20-WELL-L11 | P20 - 11th Lift | 402.a | MPSB/Sur/870 | Sur | 2 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Sualkuchi | 407
P20-WELL-L11 | P20 - 11th Lift | 402.a | MPSB/Str/1009 | Str | 3 | 3 | 2025-03-31 | IPC - 13 | 2.5 | Sualkuchi | 407
P6-WELL-L11 | P6 - 11th Lift | 402.a | MPSB/Str/1115 | Str | 1 | 3 | 2025-04-12 | IPC - 14 | 2.5 | Palashbari | 408
P6-WELL-L11 | P6 - 11th Lift | 402.a | MPSB/Sur/978 | Sur | 2 | 3 | 2025-04-12 | IPC - 14 | 2.5 | Palashbari | 408
P6-WELL-L11 | P6 - 11th Lift | 402.a | MPSB/Str/1116 | Str | 3 | 3 | 2025-04-12 | IPC - 14 | 2.5 | Palashbari | 408
P18-WELL-L11 | P18 - 11th Lift | 402.a | MPSB/Str/1240 | Str | 1 | 3 | 2025-04-24 | IPC - 14 | 2.5 | Sualkuchi | 409
P18-WELL-L11 | P18 - 11th Lift | 402.a | MPSB/Sur/1074 | Sur | 2 | 3 | 2025-04-24 | IPC - 14 | 2.5 | Sualkuchi | 409
P18-WELL-L11 | P18 - 11th Lift | 402.a | MPSB/Str/1241 | Str | 3 | 3 | 2025-04-24 | IPC - 14 | 2.5 | Sualkuchi | 409
P26-WELL-L11 | P26 - 11th Lift | 402.a | MPSB/Str/1242 | Str | 1 | 4 | 2025-04-24 | IPC - 14 | 2.5 | Sualkuchi | 410
P26-WELL-L11 | P26 - 11th Lift | 402.a | MPSB/Sur/1075 | Sur | 2 | 4 | 2025-04-24 | IPC - 14 | 2.5 | Sualkuchi | 410
P26-WELL-L11 | P26 - 11th Lift | 402.a | MPSB/Str/1243 | Str | 3 | 4 | 2025-04-24 | IPC - 14 | 2.5 | Sualkuchi | 410
P26-WELL-L11 | P26 - 11th Lift | 402.a | MPSB/Sur/1126 | Sur | 4 | 4 | 2025-04-27 | IPC - 14 | 2.5 | Sualkuchi | 410
P28-WELL-L11 | P28 - 11th Lift | 402.a | MPSB/Str/1327 | Str | 1 | 3 | 2025-04-29 | IPC - 14 | 2.5 | Sualkuchi | 411
P28-WELL-L11 | P28 - 11th Lift | 402.a | MPSB/Sur/1144 | Sur | 2 | 3 | 2025-04-29 | IPC - 14 | 2.5 | Sualkuchi | 411
P28-WELL-L11 | P28 - 11th Lift | 402.a | MPSB/Str/1328 | Str | 3 | 3 | 2025-04-29 | IPC - 14 | 2.5 | Sualkuchi | 411
P8-WELL-L11 | P8 - 11th Lift | 402.a | MPSB/Str/1554 | Str | 1 | 4 | 2025-05-23 | IPC - 15 | 2.75 | Palashbari | 412
P8-WELL-L11 | P8 - 11th Lift | 402.a | MPSB/Sur/1334 | Sur | 2 | 4 | 2025-05-23 | IPC - 15 | 2.75 | Palashbari | 412
P8-WELL-L11 | P8 - 11th Lift | 402.a | MPSB/Str/1555 | Str | 3 | 4 | 2025-05-23 | IPC - 15 | 2.75 | Palashbari | 412
P8-WELL-L11 | P8 - 11th Lift | 402.a | MPSB/Sur/1383 | Sur | 4 | 4 | 2025-05-29 | IPC - 15 | 2.75 | Palashbari | 412
P10-WELL-L11 | P10 - 11th Lift | 402.a | MPSB/Str/1561 | Str | 1 | 3 | 2025-05-24 | IPC - 15 | 2.5 | Palashbari | 413
P10-WELL-L11 | P10 - 11th Lift | 402.a | MPSB/Sur/1342 | Sur | 2 | 3 | 2025-05-24 | IPC - 15 | 2.5 | Palashbari | 413
P10-WELL-L11 | P10 - 11th Lift | 402.a | MPSB/Str/1562 | Str | 3 | 3 | 2025-05-24 | IPC - 15 | 2.5 | Palashbari | 413
P16-WELL-L11 | P16 - 11th Lift | 402.a | MPSB/Str/1491 | Str | 1 | 4 | 2025-05-15 | IPC - 15 | 2.5 | Palashbari | 414
P16-WELL-L11 | P16 - 11th Lift | 402.a | MPSB/Sur/1278 | Sur | 2 | 4 | 2025-05-15 | IPC - 15 | 2.5 | Palashbari | 414
P16-WELL-L11 | P16 - 11th Lift | 402.a | MPSB/Str/1492 | Str | 3 | 4 | 2025-05-15 | IPC - 15 | 2.5 | Palashbari | 414
P16-WELL-L11 | P16 - 11th Lift | 402.a | MPSB/Sur/1319 | Sur | 4 | 4 | 2025-05-20 | IPC - 15 | 2.5 | Palashbari | 414
P22-WELL-L11 | P22 - 11th Lift | 402.a | MPSB/Str/1464 | Str | 1 | 4 | 2025-05-10 | IPC - 15 | 2.5 | Sualkuchi | 415
P22-WELL-L11 | P22 - 11th Lift | 402.a | MPSB/Sur/1250 | Sur | 2 | 4 | 2025-05-10 | IPC - 15 | 2.5 | Sualkuchi | 415
P22-WELL-L11 | P22 - 11th Lift | 402.a | MPSB/Str/1465 | Str | 3 | 4 | 2025-05-10 | IPC - 15 | 2.5 | Sualkuchi | 415
P22-WELL-L11 | P22 - 11th Lift | 402.a | MPSB/Sur/1256 | Sur | 4 | 4 | 2025-05-12 | IPC - 15 | 2.5 | Sualkuchi | 415
P24-WELL-L11 | P24 - 11th Lift | 402.a | MPSB/Str/1458 | Str | 1 | 4 | 2025-05-09 | IPC - 15 | 2.5 | Sualkuchi | 416
P24-WELL-L11 | P24 - 11th Lift | 402.a | MPSB/Sur/1247 | Sur | 2 | 4 | 2025-05-09 | IPC - 15 | 2.5 | Sualkuchi | 416
P24-WELL-L11 | P24 - 11th Lift | 402.a | MPSB/Str/1459 | Str | 3 | 4 | 2025-05-09 | IPC - 15 | 2.5 | Sualkuchi | 416
P24-WELL-L11 | P24 - 11th Lift | 402.a | MPSB/Sur/1282 | Sur | 4 | 4 | 2025-05-15 | IPC - 15 | 2.5 | Sualkuchi | 416
P25-WELL-L11 | P25 - 11th Lift | 402.a | MPSB/Str/1513 | Str | 1 | 4 | 2025-05-18 | IPC - 15 | 2.5 | Sualkuchi | 417
P25-WELL-L11 | P25 - 11th Lift | 402.a | MPSB/Sur/1302 | Sur | 2 | 4 | 2025-05-18 | IPC - 15 | 2.5 | Sualkuchi | 417
P25-WELL-L11 | P25 - 11th Lift | 402.a | MPSB/Str/1514 | Str | 3 | 4 | 2025-05-18 | IPC - 15 | 2.5 | Sualkuchi | 417
P25-WELL-L11 | P25 - 11th Lift | 402.a | MPSB/Sur/1323 | Sur | 4 | 4 | 2025-05-20 | IPC - 15 | 2.5 | Sualkuchi | 417
P17-WELL-L11 | P17 - 11th Lift | 402.a | MPSB/Str/1676 | Str | 1 | 3 | 2025-06-18 | IPC - 16 | 3.63 | Palashbari | 418
P17-WELL-L11 | P17 - 11th Lift | 402.a | MPSB/Sur/1435 | Sur | 2 | 3 | 2025-06-18 | IPC - 16 | 3.63 | Palashbari | 418
P17-WELL-L11 | P17 - 11th Lift | 402.a | MPSB/Str/1677 | Str | 3 | 3 | 2025-06-18 | IPC - 16 | 3.63 | Palashbari | 418
P29-WELL-L11 | P29 - 11th Lift | 402.a | MPSB/Str/1708 | Str | 1 | 3 | 2025-06-27 | IPC - 16 | 2.7 | Sualkuchi | 419
P29-WELL-L11 | P29 - 11th Lift | 402.a | MPSB/Sur/1460 | Sur | 2 | 3 | 2025-06-27 | IPC - 16 | 2.7 | Sualkuchi | 419
P29-WELL-L11 | P29 - 11th Lift | 402.a | MPSB/Str/1709 | Str | 3 | 3 | 2025-06-27 | IPC - 16 | 2.7 | Sualkuchi | 419
P7-WELL-L11 | P7 - 11th Lift | 402.a | MPSB/Str/2073 | Str | 1 | 3 | 2025-08-23 | IPC - 19 | 2.5 | Palashbari | 420
P7-WELL-L11 | P7 - 11th Lift | 402.a | MPSB/Sur/1721 | Sur | 2 | 3 | 2025-08-23 | IPC - 19 | 2.5 | Palashbari | 420
P7-WELL-L11 | P7 - 11th Lift | 402.a | MPSB/Str/2074 | Str | 3 | 3 | 2025-08-23 | IPC - 19 | 2.5 | Palashbari | 420
P9-WELL-L11 | P9 - 11th Lift | 402.a | MPSB/Str/2012 | Str | 1 | 4 | 2025-08-09 | IPC - 19 | 2.8 | Palashbari | 421
P9-WELL-L11 | P9 - 11th Lift | 402.a | MPSB/Sur/1669 | Sur | 2 | 4 | 2025-08-09 | IPC - 19 | 2.8 | Palashbari | 421
P9-WELL-L11 | P9 - 11th Lift | 402.a | MPSB/Str/2013 | Str | 3 | 4 | 2025-08-09 | IPC - 19 | 2.8 | Palashbari | 421
P9-WELL-L11 | P9 - 11th Lift | 402.a | MPSB/Sur/1717 | Sur | 4 | 4 | 2025-08-22 | IPC - 19 | 2.8 | Palashbari | 421
P27-WELL-L11 | P27 - 11th Lift | 402.a | MPSB/Str/2200 | Str | 1 | 4 | 2025-09-10 | IPC - 20 | 2.5 | Sualkuchi | 422
P27-WELL-L11 | P27 - 11th Lift | 402.a | MPSB/Sur/1803 | Sur | 2 | 4 | 2025-09-10 | IPC - 20 | 2.5 | Sualkuchi | 422
P27-WELL-L11 | P27 - 11th Lift | 402.a | MPSB/Str/2201 | Str | 3 | 4 | 2025-09-10 | IPC - 20 | 2.5 | Sualkuchi | 422
P27-WELL-L11 | P27 - 11th Lift | 402.a | MPSB/Sur/1848 | Sur | 4 | 4 | 2025-09-20 | IPC - 20 | 2.5 | Sualkuchi | 422
P15-WELL-L11 | P15 - 11th Lift | 402.a | MPSB/Str/2591 | Str | 1 | 3 | 2025-10-27 | IPC - 22 | 2.34 | Palashbari | 423
P15-WELL-L11 | P15 - 11th Lift | 402.a | MPSB/Sur/2054 | Sur | 2 | 3 | 2025-10-27 | IPC - 22 | 2.34 | Palashbari | 423
P15-WELL-L11 | P15 - 11th Lift | 402.a | MPSB/Str/2592 | Str | 3 | 3 | 2025-10-27 | IPC - 22 | 2.34 | Palashbari | 423
P23-WELL-L11 | P23 - 11th Lift | 402.a | MPSB/Str/2602 | Str | 1 | 3 | 2025-10-27 | IPC - 22 | 2.7 | Sualkuchi | 424
P23-WELL-L11 | P23 - 11th Lift | 402.a | MPSB/Sur/2061 | Sur | 2 | 3 | 2025-10-27 | IPC - 22 | 2.7 | Sualkuchi | 424
P23-WELL-L11 | P23 - 11th Lift | 402.a | MPSB/Str/2603 | Str | 3 | 3 | 2025-10-27 | IPC - 22 | 2.7 | Sualkuchi | 424
P19-WELL-L11 | P19 - 11th Lift | 402.a | MPSB/Str/2839 | Str | 1 | 4 | 2025-11-18 | IPC - 23 | 2.5 | Sualkuchi | 425
P19-WELL-L11 | P19 - 11th Lift | 402.a | MPSB/Sur/2213 | Sur | 2 | 4 | 2025-11-18 | IPC - 23 | 2.5 | Sualkuchi | 425
P19-WELL-L11 | P19 - 11th Lift | 402.a | MPSB/Str/2840 | Str | 3 | 4 | 2025-11-18 | IPC - 23 | 2.5 | Sualkuchi | 425
P19-WELL-L11 | P19 - 11th Lift | 402.a | MPSB/Sur/2255 | Sur | 4 | 4 | 2025-11-23 | IPC - 23 | 2.5 | Sualkuchi | 425
P21-WELL-L11 | P21 - 11th Lift | 402.a | MPSB/Str/2995 | Str | 1 | 3 | 2025-11-30 | IPC - 23 | 2.8 | Sualkuchi | 426
P21-WELL-L11 | P21 - 11th Lift | 402.a | MPSB/Sur/2312 | Sur | 2 | 3 | 2025-11-30 | IPC - 23 | 2.8 | Sualkuchi | 426
P21-WELL-L11 | P21 - 11th Lift | 402.a | MPSB/Str/2996 | Str | 3 | 3 | 2025-11-30 | IPC - 23 | 2.8 | Sualkuchi | 426
P30-WELL-L11 | P30 - 11th Lift | 402.a | MPSB/Str/3589 | Str | 1 | 4 | 2026-01-20 | IPC - 26 | 2.5 | Sualkuchi | 427
P30-WELL-L11 | P30 - 11th Lift | 402.a | MPSB/Sur/2726 | Sur | 2 | 4 | 2026-01-20 | IPC - 26 | 2.5 | Sualkuchi | 427
P30-WELL-L11 | P30 - 11th Lift | 402.a | MPSB/Str/3590 | Str | 3 | 4 | 2026-01-20 | IPC - 26 | 2.5 | Sualkuchi | 427
P30-WELL-L11 | P30 - 11th Lift | 402.a | MPSB/Sur/2744 | Sur | 4 | 4 | 2026-01-22 | IPC - 26 | 2.5 | Sualkuchi | 427
P14(N)-WELL-L11 | P14(N) - 11th Lift | 402.a | MPSB/Str/4259 | Str | 1 | 3 | 2026-03-30 | IPC - 29 | 2.5 | Palashbari | 428
P14(N)-WELL-L11 | P14(N) - 11th Lift | 402.a | MPSB/Sur/3203 | Sur | 2 | 3 | 2026-03-30 | IPC - 29 | 2.5 | Palashbari | 428
P14(N)-WELL-L11 | P14(N) - 11th Lift | 402.a | MPSB/Str/4260 | Str | 3 | 3 | 2026-03-30 | IPC - 29 | 2.5 | Palashbari | 428
P11-WELL-L11 | P11 - 11th Lift | 402.a | MPSB/Str/4473 | Str | 1 | 3 | 2026-04-24 | IPC - 30 | 2.5 | Palashbari | 429
P11-WELL-L11 | P11 - 11th Lift | 402.a | MPSB/Sur/3344 | Sur | 2 | 3 | 2026-04-24 | IPC - 30 | 2.5 | Palashbari | 429
P11-WELL-L11 | P11 - 11th Lift | 402.a | MPSB/Str/4474 | Str | 3 | 3 | 2026-04-24 | IPC - 30 | 2.5 | Palashbari | 429
P13-WELL-L11 | P13 - 11th Lift | 402.a | MPSB/Str/4527 | Str | 1 | 3 | 2026-04-29 | IPC - 30 | 2.7 | Palashbari | 430
P13-WELL-L11 | P13 - 11th Lift | 402.a | MPSB/Sur/3382 | Sur | 2 | 3 | 2026-04-29 | IPC - 30 | 2.7 | Palashbari | 430
P13-WELL-L11 | P13 - 11th Lift | 402.a | MPSB/Str/4528 | Str | 3 | 3 | 2026-04-29 | IPC - 30 | 2.7 | Palashbari | 430
P12(A)-WELL-L11 | P12(A) - 11th Lift | 402.a | MPSB/Str/4525 | Str | 1 | 4 | 2026-04-29 | IPC - 33 | 2.8 | Palashbari | 431
P12(A)-WELL-L11 | P12(A) - 11th Lift | 402.a | MPSB/Sur/3381 | Sur | 2 | 4 | 2026-04-29 | IPC - 33 | 2.8 | Palashbari | 431
P12(A)-WELL-L11 | P12(A) - 11th Lift | 402.a | MPSB/Str/4526 | Str | 3 | 4 | 2026-04-29 | IPC - 33 | 2.8 | Palashbari | 431
P12(A)-WELL-L11 | P12(A) - 11th Lift | 402.a | MPSB/Sur/3435 | Sur | 4 | 4 | 2026-05-08 | IPC - 33 | 2.8 | Palashbari | 431 | P12(A)-WELL-L12
P6-WELL-L12 | P6 - 12th Lift | 402.a | MPSB/Str/1196 | Str | 1 | 4 | 2025-04-19 | IPC - 14 | 2.5 | Palashbari | 433
P6-WELL-L12 | P6 - 12th Lift | 402.a | MPSB/Sur/1040 | Sur | 2 | 4 | 2025-04-19 | IPC - 14 | 2.5 | Palashbari | 433
P6-WELL-L12 | P6 - 12th Lift | 402.a | MPSB/Str/1197 | Str | 3 | 4 | 2025-04-19 | IPC - 14 | 2.5 | Palashbari | 433
P6-WELL-L12 | P6 - 12th Lift | 402.a | MPSB/Sur/1091 | Sur | 4 | 4 | 2025-04-24 | IPC - 14 | 2.5 | Palashbari | 433
P26-WELL-L12 | P26 - 12th Lift | 402.a | MPSB/Str/1314 | Str | 1 | 3 | 2025-04-28 | IPC - 14 | 2.5 | Sualkuchi | 434
P26-WELL-L12 | P26 - 12th Lift | 402.a | MPSB/Sur/1136 | Sur | 2 | 3 | 2025-04-28 | IPC - 14 | 2.5 | Sualkuchi | 434
P26-WELL-L12 | P26 - 12th Lift | 402.a | MPSB/Str/1315 | Str | 3 | 3 | 2025-04-28 | IPC - 14 | 2.5 | Sualkuchi | 434
P10-WELL-L12 | P10 - 12th Lift | 402.a | MPSB/Str/1600 | Str | 1 | 3 | 2025-05-29 | IPC - 15 | 2.2 | Palashbari | 435
P10-WELL-L12 | P10 - 12th Lift | 402.a | MPSB/Sur/1385 | Sur | 2 | 3 | 2025-05-29 | IPC - 15 | 2.2 | Palashbari | 435
P10-WELL-L12 | P10 - 12th Lift | 402.a | MPSB/Str/1601 | Str | 3 | 3 | 2025-05-29 | IPC - 15 | 2.2 | Palashbari | 435
P20-WELL-L12 | P20 - 12th Lift | 402.a | MPSB/Str/1476 | Str | 1 | 4 | 2025-05-12 | IPC - 15 | 2.5 | Sualkuchi | 436
P20-WELL-L12 | P20 - 12th Lift | 402.a | MPSB/Sur/1259 | Sur | 2 | 4 | 2025-05-12 | IPC - 15 | 2.5 | Sualkuchi | 436
P20-WELL-L12 | P20 - 12th Lift | 402.a | MPSB/Str/1477 | Str | 3 | 4 | 2025-05-12 | IPC - 15 | 2.5 | Sualkuchi | 436
P20-WELL-L12 | P20 - 12th Lift | 402.a | MPSB/Sur/1297 | Sur | 4 | 4 | 2025-05-17 | IPC - 15 | 2.5 | Sualkuchi | 436
P22-WELL-L12 | P22 - 12th Lift | 402.a | MPSB/Str/1528 | Str | 1 | 4 | 2025-05-19 | IPC - 15 | 2.5 | Sualkuchi | 437
P22-WELL-L12 | P22 - 12th Lift | 402.a | MPSB/Sur/1312 | Sur | 2 | 4 | 2025-05-19 | IPC - 15 | 2.5 | Sualkuchi | 437
P22-WELL-L12 | P22 - 12th Lift | 402.a | MPSB/Str/1529 | Str | 3 | 4 | 2025-05-19 | IPC - 15 | 2.5 | Sualkuchi | 437
P22-WELL-L12 | P22 - 12th Lift | 402.a | MPSB/Sur/1328 | Sur | 4 | 4 | 2025-05-21 | IPC - 15 | 2.5 | Sualkuchi | 437
P25-WELL-L12 | P25 - 12th Lift | 402.a | MPSB/Str/1575 | Str | 1 | 3 | 2025-05-26 | IPC - 15 | 2.5 | Sualkuchi | 438
P25-WELL-L12 | P25 - 12th Lift | 402.a | MPSB/Sur/1351 | Sur | 2 | 3 | 2025-05-26 | IPC - 15 | 2.5 | Sualkuchi | 438
P25-WELL-L12 | P25 - 12th Lift | 402.a | MPSB/Str/1576 | Str | 3 | 3 | 2025-05-26 | IPC - 15 | 2.5 | Sualkuchi | 438
P28-WELL-L12 | P28 - 12th Lift | 402.a | MPSB/Str/1535 | Str | 1 | 4 | 2025-05-20 | IPC - 15 | 2.5 | Sualkuchi | 439
P28-WELL-L12 | P28 - 12th Lift | 402.a | MPSB/Sur/1321 | Sur | 2 | 4 | 2025-05-20 | IPC - 15 | 2.5 | Sualkuchi | 439
P28-WELL-L12 | P28 - 12th Lift | 402.a | MPSB/Str/1536 | Str | 3 | 4 | 2025-05-20 | IPC - 15 | 2.5 | Sualkuchi | 439
P28-WELL-L12 | P28 - 12th Lift | 402.a | MPSB/Sur/1341 | Sur | 4 | 4 | 2025-05-24 | IPC - 15 | 2.5 | Sualkuchi | 439
P8-WELL-L12 | P8 - 12th Lift | 402.a | MPSB/Str/1669 | Str | 1 | 3 | 2025-06-16 | IPC - 16 | 2.5 | Palashbari | 440
P8-WELL-L12 | P8 - 12th Lift | 402.a | MPSB/Sur/1427 | Sur | 2 | 3 | 2025-06-16 | IPC - 16 | 2.5 | Palashbari | 440
P8-WELL-L12 | P8 - 12th Lift | 402.a | MPSB/Str/1670 | Str | 3 | 3 | 2025-06-16 | IPC - 16 | 2.5 | Palashbari | 440
P18-WELL-L12 | P18 - 12th Lift | 402.a | MPSB/Str/1751 | Str | 1 | 4 | 2025-07-02 | IPC - 18 | 2.5 | Palashbari | 441
P18-WELL-L12 | P18 - 12th Lift | 402.a | MPSB/Sur/1483 | Sur | 2 | 4 | 2025-07-02 | IPC - 18 | 2.5 | Palashbari | 441
P18-WELL-L12 | P18 - 12th Lift | 402.a | MPSB/Str/1752 | Str | 3 | 4 | 2025-07-02 | IPC - 18 | 2.5 | Palashbari | 441
P18-WELL-L12 | P18 - 12th Lift | 402.a | MPSB/Sur/1574 | Sur | 4 | 4 | 2025-07-24 | IPC - 18 | 2.5 | Palashbari | 441 | P18-WELL-L13
P16-WELL-L12 | P16 - 12th Lift | 402.a | MPSB/Str/1753 | Str | 1 | 3 | 2025-07-03 | IPC - 18 | 2.5 | Palashbari | 442
P16-WELL-L12 | P16 - 12th Lift | 402.a | MPSB/Sur/1484 | Sur | 2 | 3 | 2025-07-03 | IPC - 18 | 2.5 | Palashbari | 442
P16-WELL-L12 | P16 - 12th Lift | 402.a | MPSB/Str/1754 | Str | 3 | 3 | 2025-07-03 | IPC - 18 | 2.5 | Palashbari | 442
P29-WELL-L12 | P29 - 12th Lift | 402.a | MPSB/Str/1760 | Str | 1 | 4 | 2025-07-04 | IPC - 18 | 2.8 | Sualkuchi | 443
P29-WELL-L12 | P29 - 12th Lift | 402.a | MPSB/Sur/1490 | Sur | 2 | 4 | 2025-07-04 | IPC - 18 | 2.8 | Sualkuchi | 443
P29-WELL-L12 | P29 - 12th Lift | 402.a | MPSB/Str/1761 | Str | 3 | 4 | 2025-07-04 | IPC - 18 | 2.8 | Sualkuchi | 443
P29-WELL-L12 | P29 - 12th Lift | 402.a | MPSB/Sur/1582 | Sur | 4 | 4 | 2025-07-25 | IPC - 18 | 2.8 | Sualkuchi | 443
P17-WELL-L12 | P17 - 12th Lift | 402.a | MPSB/Str/2101 | Str | 1 | 3 | 2025-08-28 | IPC - 19 | 2.65 | Palashbari | 444
P17-WELL-L12 | P17 - 12th Lift | 402.a | MPSB/Sur/1737 | Sur | 2 | 3 | 2025-08-28 | IPC - 19 | 2.65 | Palashbari | 444
P17-WELL-L12 | P17 - 12th Lift | 402.a | MPSB/Str/2102 | Str | 3 | 3 | 2025-08-28 | IPC - 19 | 2.65 | Palashbari | 444
P24-WELL-L12 | P24 - 12th Lift | 402.a | MPSB/Str/2024 | Str | 1 | 3 | 2025-08-12 | IPC - 19 | 2.5 | Sualkuchi | 445
P24-WELL-L12 | P24 - 12th Lift | 402.a | MPSB/Sur/1687 | Sur | 2 | 3 | 2025-08-12 | IPC - 19 | 2.5 | Sualkuchi | 445
P24-WELL-L12 | P24 - 12th Lift | 402.a | MPSB/Str/2025 | Str | 3 | 3 | 2025-08-12 | IPC - 19 | 2.5 | Sualkuchi | 445
P7-WELL-L12 | P7 - 12th Lift | 402.a | MPSB/Str/2126 | Str | 1 | 3 | 2025-08-31 | IPC - 20 | 2.5 | Palashbari | 446
P7-WELL-L12 | P7 - 12th Lift | 402.a | MPSB/Sur/1757 | Sur | 2 | 3 | 2025-08-31 | IPC - 20 | 2.5 | Palashbari | 446
P7-WELL-L12 | P7 - 12th Lift | 402.a | MPSB/Str/2127 | Str | 3 | 3 | 2025-08-31 | IPC - 20 | 2.5 | Palashbari | 446
P9-WELL-L12 | P9 - 12th Lift | 402.a | MPSB/Str/2166 | Str | 1 | 3 | 2025-09-06 | IPC - 20 | 2.5 | Palashbari | 447
P9-WELL-L12 | P9 - 12th Lift | 402.a | MPSB/Sur/1782 | Sur | 2 | 3 | 2025-09-06 | IPC - 20 | 2.5 | Palashbari | 447
P9-WELL-L12 | P9 - 12th Lift | 402.a | MPSB/Str/2167 | Str | 3 | 3 | 2025-09-06 | IPC - 20 | 2.5 | Palashbari | 447
P27-WELL-L12 | P27 - 12th Lift | 402.a | MPSB/Str/2348 | Str | 1 | 3 | 2025-09-28 | IPC - 20 | 2.5 | Sualkuchi | 448
P27-WELL-L12 | P27 - 12th Lift | 402.a | MPSB/Sur/1886 | Sur | 2 | 3 | 2025-09-28 | IPC - 20 | 2.5 | Sualkuchi | 448
P27-WELL-L12 | P27 - 12th Lift | 402.a | MPSB/Str/2349 | Str | 3 | 3 | 2025-09-28 | IPC - 20 | 2.5 | Sualkuchi | 448
P15-WELL-L12 | P15 - 12th Lift | 402.a | MPSB/Str/2654 | Str | 1 | 3 | 2025-10-31 | IPC - 23 | 3.17 | Palashbari | 449
P15-WELL-L12 | P15 - 12th Lift | 402.a | MPSB/Sur/2088 | Sur | 2 | 3 | 2025-10-31 | IPC - 23 | 3.17 | Palashbari | 449
P15-WELL-L12 | P15 - 12th Lift | 402.a | MPSB/Str/2655 | Str | 3 | 3 | 2025-10-31 | IPC - 23 | 3.17 | Palashbari | 449
P19-WELL-L12 | P19 - 12th Lift | 402.a | MPSB/Str/2986 | Str | 1 | 3 | 2025-11-29 | IPC - 23 | 2.5 | Palashbari | 450
P19-WELL-L12 | P19 - 12th Lift | 402.a | MPSB/Sur/2302 | Sur | 2 | 3 | 2025-11-29 | IPC - 23 | 2.5 | Palashbari | 450
P19-WELL-L12 | P19 - 12th Lift | 402.a | MPSB/Str/2987 | Str | 3 | 3 | 2025-11-29 | IPC - 23 | 2.5 | Palashbari | 450
P23-WELL-L12 | P23 - 12th Lift | 402.a | MPSB/Str/2793 | Str | 1 | 4 | 2025-11-13 | IPC - 23 | 2.5 | Sualkuchi | 451
P23-WELL-L12 | P23 - 12th Lift | 402.a | MPSB/Sur/2183 | Sur | 2 | 4 | 2025-11-13 | IPC - 23 | 2.5 | Sualkuchi | 451
P23-WELL-L12 | P23 - 12th Lift | 402.a | MPSB/Str/2794 | Str | 3 | 4 | 2025-11-13 | IPC - 23 | 2.5 | Sualkuchi | 451
P23-WELL-L12 | P23 - 12th Lift | 402.a | MPSB/Sur/2223 | Sur | 4 | 4 | 2025-11-19 | IPC - 23 | 2.5 | Sualkuchi | 451
P21-WELL-L12 | P21 - 12th Lift | 402.a | MPSB/Str/3227 | Str | 1 | 4 | 2025-12-22 | IPC - 25 | 2.5 | Sualkuchi | 452
P21-WELL-L12 | P21 - 12th Lift | 402.a | MPSB/Sur/2467 | Sur | 2 | 4 | 2025-12-22 | IPC - 25 | 2.5 | Sualkuchi | 452
P21-WELL-L12 | P21 - 12th Lift | 402.a | MPSB/Str/3228 | Str | 3 | 4 | 2025-12-22 | IPC - 25 | 2.5 | Sualkuchi | 452
P21-WELL-L12 | P21 - 12th Lift | 402.a | MPSB/Sur/2487 | Sur | 4 | 4 | 2025-12-24 | IPC - 25 | 2.5 | Sualkuchi | 452
P30-WELL-L12 | P30 - 12th Lift | 402.a | MPSB/Str/3640 | Str | 1 | 4 | 2026-01-24 | IPC - 26 | 2.5 | Sualkuchi | 453
P30-WELL-L12 | P30 - 12th Lift | 402.a | MPSB/Sur/2757 | Sur | 2 | 4 | 2026-01-24 | IPC - 26 | 2.5 | Sualkuchi | 453
P30-WELL-L12 | P30 - 12th Lift | 402.a | MPSB/Str/3641 | Str | 3 | 4 | 2026-01-24 | IPC - 26 | 2.5 | Sualkuchi | 453
P30-WELL-L12 | P30 - 12th Lift | 402.a | MPSB/Sur/2774 | Sur | 4 | 4 | 2026-01-25 | IPC - 26 | 2.5 | Sualkuchi | 453
P13-WELL-L12 | P13 - 12th Lift | 402.a | MPSB/Str/4543 | Str | 1 | 3 | 2026-04-30 | IPC - 30 | 2.5 | Palashbari | 454 | P12(A)-WELL-L12
P13-WELL-L12 | P13 - 12th Lift | 402.a | MPSB/Sur/3394 | Sur | 2 | 3 | 2026-04-30 | IPC - 30 | 2.5 | Palashbari | 454 | P12(A)-WELL-L12
P13-WELL-L12 | P13 - 12th Lift | 402.a | MPSB/Str/4544 | Str | 3 | 3 | 2026-04-30 | IPC - 30 | 2.5 | Palashbari | 454 | P12(A)-WELL-L12
P14(N)-WELL-L12 | P14(N) - 12th Lift | 402.a | MPSB/Str/4322 | Str | 1 | 3 | 2026-04-04 | IPC - 30 | 2.8 | Palashbari | 455
P14(N)-WELL-L12 | P14(N) - 12th Lift | 402.a | MPSB/Sur/3240 | Sur | 2 | 3 | 2026-04-04 | IPC - 30 | 2.8 | Palashbari | 455
P14(N)-WELL-L12 | P14(N) - 12th Lift | 402.a | MPSB/Str/4323 | Str | 3 | 3 | 2026-04-04 | IPC - 30 | 2.8 | Palashbari | 455
P11-WELL-L12 | P11 - 12th Lift | 402.a | MPSB/Str/4602 | Str | 1 | 3 | 2026-05-08 | IPC - 31 | 2.5 | Palashbari | 456
P11-WELL-L12 | P11 - 12th Lift | 402.a | MPSB/Sur/3433 | Sur | 2 | 3 | 2026-05-08 | IPC - 31 | 2.5 | Palashbari | 456
P11-WELL-L12 | P11 - 12th Lift | 402.a | MPSB/Str/4603 | Str | 3 | 3 | 2026-05-08 | IPC - 31 | 2.5 | Palashbari | 456
P12(A)-WELL-L12 | P12(A) - 12th Lift | 402.a | MPSB/Str/4543 | Str | 1 | 4 | 2026-04-30 | IPC - 33 | 2.8 | Palashbari | 457 | P13-WELL-L12
P12(A)-WELL-L12 | P12(A) - 12th Lift | 402.a | MPSB/Sur/3394 | Sur | 2 | 4 | 2026-04-30 | IPC - 33 | 2.8 | Palashbari | 457 | P13-WELL-L12
P12(A)-WELL-L12 | P12(A) - 12th Lift | 402.a | MPSB/Str/4544 | Str | 3 | 4 | 2026-04-30 | IPC - 33 | 2.8 | Palashbari | 457 | P13-WELL-L12
P12(A)-WELL-L12 | P12(A) - 12th Lift | 402.a | MPSB/Sur/3435 | Sur | 4 | 4 | 2026-05-08 | IPC - 33 | 2.8 | Palashbari | 457 | P12(A)-WELL-L11
P26-WELL-L13 | P26 - 13th Lift | 402.a | MPSB/Str/1359 | Str | 1 | 3 | 2025-04-30 | IPC - 14 | 2.5 | Sualkuchi | 459
P26-WELL-L13 | P26 - 13th Lift | 402.a | MPSB/Sur/1161 | Sur | 2 | 3 | 2025-04-30 | IPC - 14 | 2.5 | Sualkuchi | 459
P26-WELL-L13 | P26 - 13th Lift | 402.a | MPSB/Str/1360 | Str | 3 | 3 | 2025-04-30 | IPC - 14 | 2.5 | Sualkuchi | 459
P6-WELL-L13 | P6 - 13th Lift | 402.a | MPSB/Str/1521 | Str | 1 | 3 | 2025-05-19 | IPC - 15 | 2.5 | Palashbari | 460
P6-WELL-L13 | P6 - 13th Lift | 402.a | MPSB/Sur/1307 | Sur | 2 | 3 | 2025-05-19 | IPC - 15 | 2.5 | Palashbari | 460
P6-WELL-L13 | P6 - 13th Lift | 402.a | MPSB/Str/1522 | Str | 3 | 3 | 2025-05-19 | IPC - 15 | 2.5 | Palashbari | 460
P10-WELL-L13 | P10 - 13th Lift | 402.a | MPSB/Str/1674 | Str | 1 | 3 | 2025-06-17 | IPC - 16 | 2.8 | Palashbari | 461
P10-WELL-L13 | P10 - 13th Lift | 402.a | MPSB/Str/1675 | Str | 2 | 3 | 2025-06-17 | IPC - 16 | 2.8 | Palashbari | 461
P10-WELL-L13 | P10 - 13th Lift | 402.a | MPSB/Sur/1462 | Sur | 3 | 3 | 2025-06-27 | IPC - 16 | 2.8 | Palashbari | 461 | P10-WELL-L14
P20-WELL-L13 | P20 - 13th Lift | 402.a | MPSB/Str/1690 | Str | 1 | 3 | 2025-06-21 | IPC - 16 | 3.3 | Sualkuchi | 462
P20-WELL-L13 | P20 - 13th Lift | 402.a | MPSB/Sur/1448 | Sur | 2 | 3 | 2025-06-21 | IPC - 16 | 3.3 | Sualkuchi | 462
P20-WELL-L13 | P20 - 13th Lift | 402.a | MPSB/Str/1691 | Str | 3 | 3 | 2025-06-21 | IPC - 16 | 3.3 | Sualkuchi | 462
P22-WELL-L13 | P22 - 13th Lift | 402.a | MPSB/Sur/1360 | Sur | 1 | 3 | 2025-05-27 | IPC - 16 | 2.5 | Sualkuchi | 463
P22-WELL-L13 | P22 - 13th Lift | 402.a | MPSB/Str/1662 | Str | 2 | 3 | 2025-06-14 | IPC - 16 | 2.5 | Sualkuchi | 463
P22-WELL-L13 | P22 - 13th Lift | 402.a | MPSB/Str/1663 | Str | 3 | 3 | 2025-06-14 | IPC - 16 | 2.5 | Sualkuchi | 463
P8-WELL-L13 | P8 - 13th Lift | 402.a | MPSB/Str/1765 | Str | 1 | 4 | 2025-07-05 | IPC - 18 | 3.15 | Palashbari | 464
P8-WELL-L13 | P8 - 13th Lift | 402.a | MPSB/Sur/1494 | Sur | 2 | 4 | 2025-07-05 | IPC - 18 | 3.15 | Palashbari | 464
P8-WELL-L13 | P8 - 13th Lift | 402.a | MPSB/Str/1766 | Str | 3 | 4 | 2025-07-05 | IPC - 18 | 3.15 | Palashbari | 464
P8-WELL-L13 | P8 - 13th Lift | 402.a | MPSB/Sur/1562 | Sur | 4 | 4 | 2025-07-22 | IPC - 18 | 3.15 | Palashbari | 464 | P8-WELL-L14
P18-WELL-L13 | P18 - 13th Lift | 402.a | MPSB/Str/1784 | Str | 1 | 4 | 2025-07-09 | IPC - 18 | 2.5 | Palashbari | 465
P18-WELL-L13 | P18 - 13th Lift | 402.a | MPSB/Sur/1505 | Sur | 2 | 4 | 2025-07-09 | IPC - 18 | 2.5 | Palashbari | 465
P18-WELL-L13 | P18 - 13th Lift | 402.a | MPSB/Str/1785 | Str | 3 | 4 | 2025-07-09 | IPC - 18 | 2.5 | Palashbari | 465
P18-WELL-L13 | P18 - 13th Lift | 402.a | MPSB/Sur/1574 | Sur | 4 | 4 | 2025-07-24 | IPC - 18 | 2.5 | Palashbari | 465 | P18-WELL-L12
P16-WELL-L13 | P16 - 13th Lift | 402.a | MPSB/Str/1883 | Str | 1 | 3 | 2025-07-25 | IPC - 18 | 3.15 | Palashbari | 466
P16-WELL-L13 | P16 - 13th Lift | 402.a | MPSB/Sur/1577 | Sur | 2 | 3 | 2025-07-25 | IPC - 18 | 3.15 | Palashbari | 466
P16-WELL-L13 | P16 - 13th Lift | 402.a | MPSB/Str/1884 | Str | 3 | 3 | 2025-07-25 | IPC - 18 | 3.15 | Palashbari | 466
P28-WELL-L13 | P28 - 13th Lift | 402.a | MPSB/Str/2008 | Str | 1 | 4 | 2025-08-09 | IPC - 19 | 0.5 | Sualkuchi | 467
P28-WELL-L13 | P28 - 13th Lift | 402.a | MPSB/Sur/1666 | Sur | 2 | 4 | 2025-08-09 | IPC - 19 | 0.5 | Sualkuchi | 467
P28-WELL-L13 | P28 - 13th Lift | 402.a | MPSB/Str/2009 | Str | 3 | 4 | 2025-08-09 | IPC - 19 | 0.5 | Sualkuchi | 467
P28-WELL-L13 | P28 - 13th Lift | 402.a | MPSB/Sur/1723 | Sur | 4 | 4 | 2025-08-23 | IPC - 19 | 0.5 | Sualkuchi | 467 | P28-WELL-L14
P29-WELL-L13 | P29 - 13th Lift | 402.a | MPSB/Str/2114 | Str | 1 | 3 | 2025-08-30 | IPC - 19 | 2.5 | Sualkuchi | 468
P29-WELL-L13 | P29 - 13th Lift | 402.a | MPSB/Sur/1748 | Sur | 2 | 3 | 2025-08-30 | IPC - 19 | 2.5 | Sualkuchi | 468
P29-WELL-L13 | P29 - 13th Lift | 402.a | MPSB/Str/2115 | Str | 3 | 3 | 2025-08-30 | IPC - 19 | 2.5 | Sualkuchi | 468
P7-WELL-L13 | P7 - 13th Lift | 402.a | MPSB/Str/2229 | Str | 1 | 4 | 2025-09-13 | IPC - 20 | 2.5 | Palashbari | 469
P7-WELL-L13 | P7 - 13th Lift | 402.a | MPSB/Sur/1822 | Sur | 2 | 4 | 2025-09-13 | IPC - 20 | 2.5 | Palashbari | 469
P7-WELL-L13 | P7 - 13th Lift | 402.a | MPSB/Str/2230 | Str | 3 | 4 | 2025-09-13 | IPC - 20 | 2.5 | Palashbari | 469
P7-WELL-L13 | P7 - 13th Lift | 402.a | MPSB/Sur/1869 | Sur | 4 | 4 | 2025-09-24 | IPC - 20 | 2.5 | Palashbari | 469
P9-WELL-L13 | P9 - 13th Lift | 402.a | MPSB/Str/2288 | Str | 1 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Palashbari | 470
P9-WELL-L13 | P9 - 13th Lift | 402.a | MPSB/Sur/1854 | Sur | 2 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Palashbari | 470
P9-WELL-L13 | P9 - 13th Lift | 402.a | MPSB/Str/2289 | Str | 3 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Palashbari | 470
P17-WELL-L13 | P17 - 13th Lift | 402.a | MPSB/Str/2220 | Str | 1 | 4 | 2025-09-12 | IPC - 20 | 2.5 | Palashbari | 471
P17-WELL-L13 | P17 - 13th Lift | 402.a | MPSB/Sur/1813 | Sur | 2 | 4 | 2025-09-12 | IPC - 20 | 2.5 | Palashbari | 471
P17-WELL-L13 | P17 - 13th Lift | 402.a | MPSB/Str/2221 | Str | 3 | 4 | 2025-09-12 | IPC - 20 | 2.5 | Palashbari | 471
P17-WELL-L13 | P17 - 13th Lift | 402.a | MPSB/Sur/1837 | Sur | 4 | 4 | 2025-09-19 | IPC - 20 | 2.5 | Palashbari | 471
P25-WELL-L13 | P25 - 13th Lift | 402.a | MPSB/Str/2193 | Str | 1 | 4 | 2025-09-09 | IPC - 20 | 2.5 | Sualkuchi | 472
P25-WELL-L13 | P25 - 13th Lift | 402.a | MPSB/Sur/1797 | Sur | 2 | 4 | 2025-09-09 | IPC - 20 | 2.5 | Sualkuchi | 472
P25-WELL-L13 | P25 - 13th Lift | 402.a | MPSB/Str/2194 | Str | 3 | 4 | 2025-09-09 | IPC - 20 | 2.5 | Sualkuchi | 472
P25-WELL-L13 | P25 - 13th Lift | 402.a | MPSB/Sur/1824 | Sur | 4 | 4 | 2025-09-15 | IPC - 20 | 2.5 | Sualkuchi | 472
P24-WELL-L13 | P24 - 13th Lift | 402.a | MPSB/Str/2483 | Str | 1 | 4 | 2025-10-15 | IPC - 22 | 0.5 | Sualkuchi | 473
P24-WELL-L13 | P24 - 13th Lift | 402.a | MPSB/Sur/1989 | Sur | 2 | 4 | 2025-10-15 | IPC - 22 | 0.5 | Sualkuchi | 473
P24-WELL-L13 | P24 - 13th Lift | 402.a | MPSB/Str/2484 | Str | 3 | 4 | 2025-10-15 | IPC - 22 | 0.5 | Sualkuchi | 473
P24-WELL-L13 | P24 - 13th Lift | 402.a | MPSB/Sur/2051 | Sur | 4 | 4 | 2025-10-26 | IPC - 22 | 0.5 | Sualkuchi | 473 | P24-WELL-L14
P27-WELL-L13 | P27 - 13th Lift | 402.a | MPSB/Str/2481 | Str | 1 | 4 | 2025-10-15 | IPC - 22 | 2.5 | Sualkuchi | 474
P27-WELL-L13 | P27 - 13th Lift | 402.a | MPSB/Sur/1988 | Sur | 2 | 4 | 2025-10-15 | IPC - 22 | 2.5 | Sualkuchi | 474
P27-WELL-L13 | P27 - 13th Lift | 402.a | MPSB/Str/2482 | Str | 3 | 4 | 2025-10-15 | IPC - 22 | 2.5 | Sualkuchi | 474
P27-WELL-L13 | P27 - 13th Lift | 402.a | MPSB/Sur/2042 | Sur | 4 | 4 | 2025-10-25 | IPC - 22 | 2.5 | Sualkuchi | 474
P23-WELL-L13 | P23 - 13th Lift | 402.a | MPSB/Str/2921 | Str | 1 | 3 | 2025-11-25 | IPC - 23 | 2.5 | Sualkuchi | 475
P23-WELL-L13 | P23 - 13th Lift | 402.a | MPSB/Sur/2264 | Sur | 2 | 3 | 2025-11-25 | IPC - 23 | 2.5 | Sualkuchi | 475
P23-WELL-L13 | P23 - 13th Lift | 402.a | MPSB/Str/2922 | Str | 3 | 3 | 2025-11-25 | IPC - 23 | 2.5 | Sualkuchi | 475
P15-WELL-L13 | P15 - 13th Lift | 402.a | MPSB/Str/3094 | Str | 1 | 3 | 2025-12-10 | IPC - 25 | 2.5 | Palashbari | 476
P15-WELL-L13 | P15 - 13th Lift | 402.a | MPSB/Sur/2378 | Sur | 2 | 3 | 2025-12-10 | IPC - 25 | 2.5 | Palashbari | 476
P15-WELL-L13 | P15 - 13th Lift | 402.a | MPSB/Str/3095 | Str | 3 | 3 | 2025-12-10 | IPC - 25 | 2.5 | Palashbari | 476
P19-WELL-L13 | P19 - 13th Lift | 402.a | MPSB/Str/3148 | Str | 1 | 4 | 2025-12-15 | IPC - 25 | 2.5 | Sualkuchi | 477
P19-WELL-L13 | P19 - 13th Lift | 402.a | MPSB/Sur/2417 | Sur | 2 | 4 | 2025-12-15 | IPC - 25 | 2.5 | Sualkuchi | 477
P19-WELL-L13 | P19 - 13th Lift | 402.a | MPSB/Str/3149 | Str | 3 | 4 | 2025-12-15 | IPC - 25 | 2.5 | Sualkuchi | 477
P19-WELL-L13 | P19 - 13th Lift | 402.a | MPSB/Sur/2454 | Sur | 4 | 4 | 2025-12-20 | IPC - 25 | 2.5 | Sualkuchi | 477
P21-WELL-L13 | P21 - 13th Lift | 402.a | MPSB/Str/3323 | Str | 1 | 3 | 2025-12-29 | IPC - 25 | 2.5 | Sualkuchi | 478
P21-WELL-L13 | P21 - 13th Lift | 402.a | MPSB/Sur/2533 | Sur | 2 | 3 | 2025-12-29 | IPC - 25 | 2.5 | Sualkuchi | 478
P21-WELL-L13 | P21 - 13th Lift | 402.a | MPSB/Str/3324 | Str | 3 | 3 | 2025-12-29 | IPC - 25 | 2.5 | Sualkuchi | 478
P30-WELL-L13 | P30 - 13th Lift | 402.a | MPSB/Str/3653 | Str | 1 | 4 | 2026-01-27 | IPC - 26 | 2.5 | Sualkuchi | 479
P30-WELL-L13 | P30 - 13th Lift | 402.a | MPSB/Sur/2778 | Sur | 2 | 4 | 2026-01-27 | IPC - 26 | 2.5 | Sualkuchi | 479
P30-WELL-L13 | P30 - 13th Lift | 402.a | MPSB/Str/3654 | Str | 3 | 4 | 2026-01-27 | IPC - 26 | 2.5 | Sualkuchi | 479
P30-WELL-L13 | P30 - 13th Lift | 402.a | MPSB/Sur/2801 | Sur | 4 | 4 | 2026-01-30 | IPC - 26 | 2.5 | Sualkuchi | 479
P14(N)-WELL-L13 | P14(N) - 13th Lift | 402.a | MPSB/Str/4395 | Str | 1 | 3 | 2026-04-13 | IPC - 30 | 2.2 | Palashbari | 480
P14(N)-WELL-L13 | P14(N) - 13th Lift | 402.a | MPSB/Sur/3295 | Sur | 2 | 3 | 2026-04-13 | IPC - 30 | 2.2 | Palashbari | 480
P14(N)-WELL-L13 | P14(N) - 13th Lift | 402.a | MPSB/Str/4394 | Str | 3 | 3 | 2026-04-13 | IPC - 30 | 2.2 | Palashbari | 480
P11-WELL-L13 | P11 - 13th Lift | 402.a | MPSB/Str/4684 | Str | 1 | 3 | 2026-05-15 | IPC - 31 | 2.5 | Palashbari | 481
P11-WELL-L13 | P11 - 13th Lift | 402.a | MPSB/Sur/3480 | Sur | 2 | 3 | 2026-05-15 | IPC - 31 | 2.5 | Palashbari | 481
P11-WELL-L13 | P11 - 13th Lift | 402.a | MPSB/Str/4685 | Str | 3 | 3 | 2026-05-15 | IPC - 31 | 2.5 | Palashbari | 481
P13-WELL-L13 | P13 - 13th Lift | 402.a | MPSB/Str/4764 | Str | 1 | 3 | 2026-05-23 | IPC - 31 | 2.5 | Palashbari | 482
P13-WELL-L13 | P13 - 13th Lift | 402.a | MPSB/Sur/3536 | Sur | 2 | 3 | 2026-05-23 | IPC - 31 | 2.5 | Palashbari | 482
P13-WELL-L13 | P13 - 13th Lift | 402.a | MPSB/Str/4765 | Str | 3 | 3 | 2026-05-23 | IPC - 31 | 2.5 | Palashbari | 482
P12(A)-WELL-L13 | P12(A) - 13th Lift | 402.a | MPSB/Str/4716 | Str | 1 | 3 | 2026-05-18 | IPC - 33 | 2.8 | Palashbari | 483
P12(A)-WELL-L13 | P12(A) - 13th Lift | 402.a | MPSB/Sur/3501 | Sur | 2 | 3 | 2026-05-18 | IPC - 33 | 2.8 | Palashbari | 483
P12(A)-WELL-L13 | P12(A) - 13th Lift | 402.a | MPSB/Str/4717 | Str | 3 | 3 | 2026-05-18 | IPC - 33 | 2.8 | Palashbari | 483
P6-WELL-L14 | P6 - 14th Lift | 402.a | MPSB/Str/1582 | Str | 1 | 3 | 2025-05-27 | IPC - 15 | 2.57 | Palashbari | 485
P6-WELL-L14 | P6 - 14th Lift | 402.a | MPSB/Sur/1364 | Sur | 2 | 3 | 2025-05-27 | IPC - 15 | 2.57 | Palashbari | 485
P6-WELL-L14 | P6 - 14th Lift | 402.a | MPSB/Str/1583 | Str | 3 | 3 | 2025-05-27 | IPC - 15 | 2.57 | Palashbari | 485
P26-WELL-L14 | P26 - 14th Lift | 402.a | MPSB/Str/1495 | Str | 1 | 4 | 2025-05-15 | IPC - 15 | 2.5 | Sualkuchi | 486
P26-WELL-L14 | P26 - 14th Lift | 402.a | MPSB/Sur/1280 | Sur | 2 | 4 | 2025-05-15 | IPC - 15 | 2.5 | Sualkuchi | 486
P26-WELL-L14 | P26 - 14th Lift | 402.a | MPSB/Str/1496 | Str | 3 | 4 | 2025-05-15 | IPC - 15 | 2.5 | Sualkuchi | 486
P26-WELL-L14 | P26 - 14th Lift | 402.a | MPSB/Sur/1316 | Sur | 4 | 4 | 2025-05-19 | IPC - 15 | 2.5 | Sualkuchi | 486
P10-WELL-L14 | P10 - 14th Lift | 402.a | MPSB/Str/1694 | Str | 1 | 4 | 2025-06-23 | IPC - 16 | 2.7 | Palashbari | 487
P10-WELL-L14 | P10 - 14th Lift | 402.a | MPSB/Sur/1451 | Sur | 2 | 4 | 2025-06-23 | IPC - 16 | 2.7 | Palashbari | 487
P10-WELL-L14 | P10 - 14th Lift | 402.a | MPSB/Str/1695 | Str | 3 | 4 | 2025-06-23 | IPC - 16 | 2.7 | Palashbari | 487
P10-WELL-L14 | P10 - 14th Lift | 402.a | MPSB/Sur/1462 | Sur | 4 | 4 | 2025-06-27 | IPC - 16 | 2.7 | Palashbari | 487 | P10-WELL-L13
P8-WELL-L14 | P8 - 14th Lift | 402.a | MPSB/Str/1805 | Str | 1 | 4 | 2025-07-12 | IPC - 18 | 2.5 | Palashbari | 488
P8-WELL-L14 | P8 - 14th Lift | 402.a | MPSB/Sur/1518 | Sur | 2 | 4 | 2025-07-12 | IPC - 18 | 2.5 | Palashbari | 488
P8-WELL-L14 | P8 - 14th Lift | 402.a | MPSB/Str/1806 | Str | 3 | 4 | 2025-07-12 | IPC - 18 | 2.5 | Palashbari | 488
P8-WELL-L14 | P8 - 14th Lift | 402.a | MPSB/Sur/1562 | Sur | 4 | 4 | 2025-07-22 | IPC - 18 | 2.5 | Palashbari | 488 | P8-WELL-L13
P18-WELL-L14 | P18 - 14th Lift | 402.a | MPSB/Str/1815 | Str | 1 | 3 | 2025-07-15 | IPC - 18 | 2.5 | Palashbari | 489
P18-WELL-L14 | P18 - 14th Lift | 402.a | MPSB/Sur/1529 | Sur | 2 | 3 | 2025-07-15 | IPC - 18 | 2.5 | Palashbari | 489
P18-WELL-L14 | P18 - 14th Lift | 402.a | MPSB/Str/1816 | Str | 3 | 3 | 2025-07-15 | IPC - 18 | 2.5 | Palashbari | 489
P22-WELL-L14 | P22 - 14th Lift | 402.a | MPSB/Str/1889 | Str | 1 | 3 | 2025-07-25 | IPC - 18 | 2.5 | Sualkuchi | 490
P22-WELL-L14 | P22 - 14th Lift | 402.a | MPSB/Sur/1583 | Sur | 2 | 3 | 2025-07-25 | IPC - 18 | 2.5 | Sualkuchi | 490
P22-WELL-L14 | P22 - 14th Lift | 402.a | MPSB/Str/1915 | Str | 3 | 3 | 2025-07-28 | IPC - 18 | 2.5 | Sualkuchi | 490
P16-WELL-L14 | P16 - 14th Lift | 402.a | MPSB/Str/1970 | Str | 1 | 4 | 2025-08-04 | IPC - 19 | 2.5 | Palashbari | 491
P16-WELL-L14 | P16 - 14th Lift | 402.a | MPSB/Sur/1643 | Sur | 2 | 4 | 2025-08-04 | IPC - 19 | 2.5 | Palashbari | 491
P16-WELL-L14 | P16 - 14th Lift | 402.a | MPSB/Str/1971 | Str | 3 | 4 | 2025-08-04 | IPC - 19 | 2.5 | Palashbari | 491
P16-WELL-L14 | P16 - 14th Lift | 402.a | MPSB/Sur/1732 | Sur | 4 | 4 | 2025-08-26 | IPC - 19 | 2.5 | Palashbari | 491
P28-WELL-L14 | P28 - 14th Lift | 402.a | MPSB/Str/2038 | Str | 1 | 4 | 2025-08-18 | IPC - 19 | 2.8 | Sualkuchi | 492
P28-WELL-L14 | P28 - 14th Lift | 402.a | MPSB/Sur/1697 | Sur | 2 | 4 | 2025-08-18 | IPC - 19 | 2.8 | Sualkuchi | 492
P28-WELL-L14 | P28 - 14th Lift | 402.a | MPSB/Str/2039 | Str | 3 | 4 | 2025-08-18 | IPC - 19 | 2.8 | Sualkuchi | 492
P28-WELL-L14 | P28 - 14th Lift | 402.a | MPSB/Sur/1723 | Sur | 4 | 4 | 2025-08-23 | IPC - 19 | 2.8 | Sualkuchi | 492 | P28-WELL-L13
P9-WELL-L14 | P9 - 14th Lift | 402.a | MPSB/Str/2378 | Str | 1 | 3 | 2025-09-30 | IPC - 20 | 2.5 | Palashbari | 493
P9-WELL-L14 | P9 - 14th Lift | 402.a | MPSB/Sur/1907 | Sur | 2 | 3 | 2025-09-30 | IPC - 20 | 2.5 | Palashbari | 493
P9-WELL-L14 | P9 - 14th Lift | 402.a | MPSB/Str/2379 | Str | 3 | 3 | 2025-09-30 | IPC - 20 | 2.5 | Palashbari | 493
P17-WELL-L14 | P17 - 14th Lift | 402.a | MPSB/Str/2365 | Str | 1 | 3 | 2025-09-30 | IPC - 20 | 2.5 | Palashbari | 494
P17-WELL-L14 | P17 - 14th Lift | 402.a | MPSB/Sur/1894 | Sur | 2 | 3 | 2025-09-30 | IPC - 20 | 2.5 | Palashbari | 494
P17-WELL-L14 | P17 - 14th Lift | 402.a | MPSB/Str/2366 | Str | 3 | 3 | 2025-09-30 | IPC - 20 | 2.5 | Palashbari | 494
P25-WELL-L14 | P25 - 14th Lift | 402.a | MPSB/Str/2350 | Str | 1 | 3 | 2025-09-29 | IPC - 20 | 2.5 | Sualkuchi | 495
P25-WELL-L14 | P25 - 14th Lift | 402.a | MPSB/Sur/1887 | Sur | 2 | 3 | 2025-09-29 | IPC - 20 | 2.5 | Sualkuchi | 495
P25-WELL-L14 | P25 - 14th Lift | 402.a | MPSB/Str/2351 | Str | 3 | 3 | 2025-09-29 | IPC - 20 | 2.5 | Sualkuchi | 495
P29-WELL-L14 | P29 - 14th Lift | 402.a | MPSB/Str/2280 | Str | 1 | 3 | 2025-09-20 | IPC - 20 | 2.5 | Sualkuchi | 496
P29-WELL-L14 | P29 - 14th Lift | 402.a | MPSB/Sur/1846 | Sur | 2 | 3 | 2025-09-20 | IPC - 20 | 2.5 | Sualkuchi | 496
P29-WELL-L14 | P29 - 14th Lift | 402.a | MPSB/Str/2281 | Str | 3 | 3 | 2025-09-20 | IPC - 20 | 2.5 | Sualkuchi | 496
P7-WELL-L14 | P7 - 14th Lift | 402.a | MPSB/Str/2461 | Str | 1 | 3 | 2025-10-13 | IPC - 22 | 2.5 | Palashbari | 497
P7-WELL-L14 | P7 - 14th Lift | 402.a | MPSB/Sur/1975 | Sur | 2 | 3 | 2025-10-13 | IPC - 22 | 2.5 | Palashbari | 497
P7-WELL-L14 | P7 - 14th Lift | 402.a | MPSB/Str/2462 | Str | 3 | 3 | 2025-10-13 | IPC - 22 | 2.5 | Palashbari | 497
P20-WELL-L14 | P20 - 14th Lift | 402.a | MPSB/Str/2402 | Str | 1 | 4 | 2025-10-06 | IPC - 22 | 2.5 | Sualkuchi | 498
P20-WELL-L14 | P20 - 14th Lift | 402.a | MPSB/Sur/1923 | Sur | 2 | 4 | 2025-10-06 | IPC - 22 | 2.5 | Sualkuchi | 498
P20-WELL-L14 | P20 - 14th Lift | 402.a | MPSB/Str/2403 | Str | 3 | 4 | 2025-10-06 | IPC - 22 | 2.5 | Sualkuchi | 498
P20-WELL-L14 | P20 - 14th Lift | 402.a | MPSB/Sur/1962 | Sur | 4 | 4 | 2025-10-10 | IPC - 22 | 2.5 | Sualkuchi | 498
P24-WELL-L14 | P24 - 14th Lift | 402.a | MPSB/Str/2537 | Str | 1 | 4 | 2025-10-20 | IPC - 22 | 2.8 | Sualkuchi | 499
P24-WELL-L14 | P24 - 14th Lift | 402.a | MPSB/Sur/2017 | Sur | 2 | 4 | 2025-10-20 | IPC - 22 | 2.8 | Sualkuchi | 499
P24-WELL-L14 | P24 - 14th Lift | 402.a | MPSB/Str/2538 | Str | 3 | 4 | 2025-10-20 | IPC - 22 | 2.8 | Sualkuchi | 499
P24-WELL-L14 | P24 - 14th Lift | 402.a | MPSB/Sur/2051 | Sur | 4 | 4 | 2025-10-26 | IPC - 22 | 2.8 | Sualkuchi | 499 | P24-WELL-L13
P27-WELL-L14 | P27 - 14th Lift | 402.a | MPSB/Str/2706 | Str | 1 | 4 | 2025-11-05 | IPC - 23 | 2.5 | Sualkuchi | 500
P27-WELL-L14 | P27 - 14th Lift | 402.a | MPSB/Sur/2128 | Sur | 2 | 4 | 2025-11-05 | IPC - 23 | 2.5 | Sualkuchi | 500
P27-WELL-L14 | P27 - 14th Lift | 402.a | MPSB/Str/2707 | Str | 3 | 4 | 2025-11-05 | IPC - 23 | 2.5 | Sualkuchi | 500
P27-WELL-L14 | P27 - 14th Lift | 402.a | MPSB/Sur/2185 | Sur | 4 | 4 | 2025-11-13 | IPC - 23 | 2.5 | Sualkuchi | 500
P15-WELL-L14 | P15 - 14th Lift | 402.a | MPSB/Str/3194 | Str | 1 | 3 | 2025-12-19 | IPC - 25 | 2.5 | Palashbari | 501
P15-WELL-L14 | P15 - 14th Lift | 402.a | MPSB/Sur/2446 | Sur | 2 | 3 | 2025-12-19 | IPC - 25 | 2.5 | Palashbari | 501
P15-WELL-L14 | P15 - 14th Lift | 402.a | MPSB/Str/3195 | Str | 3 | 3 | 2025-12-19 | IPC - 25 | 2.5 | Palashbari | 501
P19-WELL-L14 | P19 - 14th Lift | 402.a | MPSB/Str/3261 | Str | 1 | 4 | 2025-12-24 | IPC - 25 | 2.5 | Sualkuchi | 502
P19-WELL-L14 | P19 - 14th Lift | 402.a | MPSB/Sur/2488 | Sur | 2 | 4 | 2025-12-24 | IPC - 25 | 2.5 | Sualkuchi | 502
P19-WELL-L14 | P19 - 14th Lift | 402.a | MPSB/Str/3262 | Str | 3 | 4 | 2025-12-24 | IPC - 25 | 2.5 | Sualkuchi | 502
P19-WELL-L14 | P19 - 14th Lift | 402.a | MPSB/Sur/2504 | Sur | 4 | 4 | 2025-12-26 | IPC - 25 | 2.5 | Sualkuchi | 502
P23-WELL-L14 | P23 - 14th Lift | 402.a | MPSB/Str/3087 | Str | 1 | 4 | 2025-12-08 | IPC - 25 | 2.5 | Sualkuchi | 503
P23-WELL-L14 | P23 - 14th Lift | 402.a | MPSB/Sur/2369 | Sur | 2 | 4 | 2025-12-08 | IPC - 25 | 2.5 | Sualkuchi | 503
P23-WELL-L14 | P23 - 14th Lift | 402.a | MPSB/Str/3088 | Str | 3 | 4 | 2025-12-08 | IPC - 25 | 2.5 | Sualkuchi | 503
P23-WELL-L14 | P23 - 14th Lift | 402.a | MPSB/Sur/2401 | Sur | 4 | 4 | 2025-12-12 | IPC - 25 | 2.5 | Sualkuchi | 503
P21-WELL-L14 | P21 - 14th Lift | 402.a | MPSB/Str/3438 | Str | 1 | 4 | 2026-01-06 | IPC - 26 | 2.5 | Sualkuchi | 504
P21-WELL-L14 | P21 - 14th Lift | 402.a | MPSB/Sur/2618 | Sur | 2 | 4 | 2026-01-06 | IPC - 26 | 2.5 | Sualkuchi | 504
P21-WELL-L14 | P21 - 14th Lift | 402.a | MPSB/Str/3439 | Str | 3 | 4 | 2026-01-06 | IPC - 26 | 2.5 | Sualkuchi | 504
P21-WELL-L14 | P21 - 14th Lift | 402.a | MPSB/Sur/2650 | Sur | 4 | 4 | 2026-01-11 | IPC - 26 | 2.5 | Sualkuchi | 504
P30-WELL-L14 | P30 - 14th Lift | 402.a | MPSB/Str/3732 | Str | 1 | 3 | 2026-01-31 | IPC - 26 | 2.5 | Sualkuchi | 505
P30-WELL-L14 | P30 - 14th Lift | 402.a | MPSB/Sur/2826 | Sur | 2 | 3 | 2026-01-31 | IPC - 26 | 2.5 | Sualkuchi | 505
P30-WELL-L14 | P30 - 14th Lift | 402.a | MPSB/Str/3733 | Str | 3 | 3 | 2026-01-31 | IPC - 26 | 2.5 | Sualkuchi | 505
P14(N)-WELL-L14 | P14(N) - 14th Lift | 402.a | MPSB/Str/4455 | Str | 1 | 3 | 2026-04-21 | IPC - 30 | 2.8 | Palashbari | 506
P14(N)-WELL-L14 | P14(N) - 14th Lift | 402.a | MPSB/Sur/3333 | Sur | 2 | 3 | 2026-04-21 | IPC - 30 | 2.8 | Palashbari | 506
P14(N)-WELL-L14 | P14(N) - 14th Lift | 402.a | MPSB/Str/4456 | Str | 3 | 3 | 2026-04-21 | IPC - 30 | 2.8 | Palashbari | 506
P12(A)-WELL-L14 | P12(A) - 14th Lift | 402.a | MPSB/Str/4874 | Str | 1 | 3 | 2026-06-06 | IPC - 33 | 2.8 | Palashbari | 507
P12(A)-WELL-L14 | P12(A) - 14th Lift | 402.a | MPSB/Sur/3614 | Sur | 2 | 3 | 2026-06-06 | IPC - 33 | 2.8 | Palashbari | 507
P12(A)-WELL-L14 | P12(A) - 14th Lift | 402.a | MPSB/Str/4875 | Str | 3 | 3 | 2026-06-06 | IPC - 33 | 2.8 | Palashbari | 507
P11-WELL-L14 | P11 - 14th Lift | 402.a | MPSB/Str/4896 | Str | 1 | 3 | 2026-06-12 | IPC - 33 | 2.5 | Palashbari | 508
P11-WELL-L14 | P11 - 14th Lift | 402.a | MPSB/Sur/3640 | Sur | 2 | 3 | 2026-06-12 | IPC - 33 | 2.5 | Palashbari | 508
P11-WELL-L14 | P11 - 14th Lift | 402.a | MPSB/Str/4897 | Str | 3 | 3 | 2026-06-12 | IPC - 33 | 2.5 | Palashbari | 508
P13-WELL-L14 | P13 - 14th Lift | 402.a | MPSB/Str/4943 | Str | 1 | 3 | 2026-06-18 | IPC - 33 | 2.5 | Palashbari | 509
P13-WELL-L14 | P13 - 14th Lift | 402.a | MPSB/Sur/3664 | Sur | 2 | 3 | 2026-06-18 | IPC - 33 | 2.5 | Palashbari | 509
P13-WELL-L14 | P13 - 14th Lift | 402.a | MPSB/Str/4944 | Str | 3 | 3 | 2026-06-18 | IPC - 33 | 2.5 | Palashbari | 509
P26-WELL-L15 | P26 - 15th Lift | 402.a | MPSB/Str/1550 | Str | 1 | 4 | 2025-05-22 | IPC - 15 | 2.5 | Sualkuchi | 511
P26-WELL-L15 | P26 - 15th Lift | 402.a | MPSB/Sur/1332 | Sur | 2 | 4 | 2025-05-22 | IPC - 15 | 2.5 | Sualkuchi | 511
P26-WELL-L15 | P26 - 15th Lift | 402.a | MPSB/Str/1551 | Str | 3 | 4 | 2025-05-22 | IPC - 15 | 2.5 | Sualkuchi | 511
P26-WELL-L15 | P26 - 15th Lift | 402.a | MPSB/Sur/1359 | Sur | 4 | 4 | 2025-05-26 | IPC - 15 | 2.5 | Sualkuchi | 511
P6-WELL-L15 | P6 - 15th Lift | 402.a | MPSB/Str/1705 | Str | 1 | 3 | 2025-06-26 | IPC - 16 | 2.5 | Palashbari | 512
P6-WELL-L15 | P6 - 15th Lift | 402.a | MPSB/Sur/1458 | Sur | 2 | 3 | 2025-06-26 | IPC - 16 | 2.5 | Palashbari | 512
P6-WELL-L15 | P6 - 15th Lift | 402.a | MPSB/Str/1706 | Str | 3 | 3 | 2025-06-26 | IPC - 16 | 2.5 | Palashbari | 512
P10-WELL-L15 | P10 - 15th Lift | 402.a | MPSB/Str/1720 | Str | 1 | 3 | 2025-06-28 | IPC - 16 | 2.5 | Palashbari | 513
P10-WELL-L15 | P10 - 15th Lift | 402.a | MPSB/Sur/1466 | Sur | 2 | 3 | 2025-06-28 | IPC - 16 | 2.5 | Palashbari | 513
P10-WELL-L15 | P10 - 15th Lift | 402.a | MPSB/Str/1721 | Str | 3 | 3 | 2025-06-28 | IPC - 16 | 2.5 | Palashbari | 513
P8-WELL-L15 | P8 - 15th Lift | 402.a | MPSB/Str/1968 | Str | 1 | 4 | 2025-08-03 | IPC - 19 | 2.5 | Palashbari | 514
P8-WELL-L15 | P8 - 15th Lift | 402.a | MPSB/Sur/1642 | Sur | 2 | 4 | 2025-08-03 | IPC - 19 | 2.5 | Palashbari | 514
P8-WELL-L15 | P8 - 15th Lift | 402.a | MPSB/Str/1969 | Str | 3 | 4 | 2025-08-03 | IPC - 19 | 2.5 | Palashbari | 514
P8-WELL-L15 | P8 - 15th Lift | 402.a | MPSB/Sur/1710 | Sur | 4 | 4 | 2025-08-21 | IPC - 19 | 2.5 | Palashbari | 514 | P8-WELL-L16
P16-WELL-L15 | P16 - 15th Lift | 402.a | MPSB/Str/2094 | Str | 1 | 3 | 2025-08-27 | IPC - 19 | 2.5 | Palashbari | 515
P16-WELL-L15 | P16 - 15th Lift | 402.a | MPSB/Sur/1735 | Sur | 2 | 3 | 2025-08-27 | IPC - 19 | 2.5 | Palashbari | 515
P16-WELL-L15 | P16 - 15th Lift | 402.a | MPSB/Str/2095 | Str | 3 | 3 | 2025-08-27 | IPC - 19 | 2.5 | Palashbari | 515
P18-WELL-L15 | P18 - 15th Lift | 402.a | MPSB/Str/1928 | Str | 1 | 4 | 2025-07-31 | IPC - 19 | 2.3 | Palashbari | 516
P18-WELL-L15 | P18 - 15th Lift | 402.a | MPSB/Sur/1614 | Sur | 2 | 4 | 2025-07-31 | IPC - 19 | 2.3 | Palashbari | 516
P18-WELL-L15 | P18 - 15th Lift | 402.a | MPSB/Str/1929 | Str | 3 | 4 | 2025-07-31 | IPC - 19 | 2.3 | Palashbari | 516
P18-WELL-L15 | P18 - 15th Lift | 402.a | MPSB/Sur/1677 | Sur | 4 | 4 | 2025-08-11 | IPC - 19 | 2.3 | Palashbari | 516 | P18-WELL-L16
P22-WELL-L15 | P22 - 15th Lift | 402.a | MPSB/Str/2103 | Str | 1 | 3 | 2025-08-28 | IPC - 19 | 2.5 | Sualkuchi | 517
P22-WELL-L15 | P22 - 15th Lift | 402.a | MPSB/Sur/1738 | Sur | 2 | 3 | 2025-08-28 | IPC - 19 | 2.5 | Sualkuchi | 517
P22-WELL-L15 | P22 - 15th Lift | 402.a | MPSB/Str/2104 | Str | 3 | 3 | 2025-08-28 | IPC - 19 | 2.5 | Sualkuchi | 517
P28-WELL-L15 | P28 - 15th Lift | 402.a | MPSB/Str/2175 | Str | 1 | 4 | 2025-09-07 | IPC - 20 | 2.5 | Sualkuchi | 518
P28-WELL-L15 | P28 - 15th Lift | 402.a | MPSB/Sur/1785 | Sur | 2 | 4 | 2025-09-07 | IPC - 20 | 2.5 | Sualkuchi | 518
P28-WELL-L15 | P28 - 15th Lift | 402.a | MPSB/Str/2176 | Str | 3 | 4 | 2025-09-07 | IPC - 20 | 2.5 | Sualkuchi | 518
P28-WELL-L15 | P28 - 15th Lift | 402.a | MPSB/Sur/1810 | Sur | 4 | 4 | 2025-09-11 | IPC - 20 | 2.5 | Sualkuchi | 518
P7-WELL-L15 | P7 - 15th Lift | 402.a | MPSB/Str/2569 | Str | 1 | 3 | 2025-10-24 | IPC - 22 | 2.5 | Palashbari | 519
P7-WELL-L15 | P7 - 15th Lift | 402.a | MPSB/Sur/2037 | Sur | 2 | 3 | 2025-10-24 | IPC - 22 | 2.5 | Palashbari | 519
P7-WELL-L15 | P7 - 15th Lift | 402.a | MPSB/Str/2570 | Str | 3 | 3 | 2025-10-24 | IPC - 22 | 2.5 | Palashbari | 519
P9-WELL-L15 | P9 - 15th Lift | 402.a | MPSB/Str/2664 | Str | 1 | 3 | 2025-10-31 | IPC - 22 | 2.5 | Palashbari | 520
P9-WELL-L15 | P9 - 15th Lift | 402.a | MPSB/Sur/2096 | Sur | 2 | 3 | 2025-10-31 | IPC - 22 | 2.5 | Palashbari | 520
P9-WELL-L15 | P9 - 15th Lift | 402.a | MPSB/Str/2665 | Str | 3 | 3 | 2025-10-31 | IPC - 22 | 2.5 | Palashbari | 520
P17-WELL-L15 | P17 - 15th Lift | 402.a | MPSB/Str/2512 | Str | 1 | 3 | 2025-10-18 | IPC - 22 | 2.5 | Palashbari | 521
P17-WELL-L15 | P17 - 15th Lift | 402.a | MPSB/Sur/2005 | Sur | 2 | 3 | 2025-10-18 | IPC - 22 | 2.5 | Palashbari | 521
P17-WELL-L15 | P17 - 15th Lift | 402.a | MPSB/Str/2513 | Str | 3 | 3 | 2025-10-18 | IPC - 22 | 2.5 | Palashbari | 521
P20-WELL-L15 | P20 - 15th Lift | 402.a | MPSB/Str/2518 | Str | 1 | 4 | 2025-10-18 | IPC - 22 | 2.5 | Sualkuchi | 522
P20-WELL-L15 | P20 - 15th Lift | 402.a | MPSB/Sur/2008 | Sur | 2 | 4 | 2025-10-18 | IPC - 22 | 2.5 | Sualkuchi | 522
P20-WELL-L15 | P20 - 15th Lift | 402.a | MPSB/Str/2519 | Str | 3 | 4 | 2025-10-18 | IPC - 22 | 2.5 | Sualkuchi | 522
P20-WELL-L15 | P20 - 15th Lift | 402.a | MPSB/Sur/2031 | Sur | 4 | 4 | 2025-10-23 | IPC - 22 | 2.5 | Sualkuchi | 522
P25-WELL-L15 | P25 - 15th Lift | 402.a | MPSB/Str/2488 | Str | 1 | 4 | 2025-10-16 | IPC - 22 | 2.5 | Sualkuchi | 523
P25-WELL-L15 | P25 - 15th Lift | 402.a | MPSB/Sur/1991 | Sur | 2 | 4 | 2025-10-16 | IPC - 22 | 2.5 | Sualkuchi | 523
P25-WELL-L15 | P25 - 15th Lift | 402.a | MPSB/Str/2489 | Str | 3 | 4 | 2025-10-16 | IPC - 22 | 2.5 | Sualkuchi | 523
P25-WELL-L15 | P25 - 15th Lift | 402.a | MPSB/Sur/2029 | Sur | 4 | 4 | 2025-10-23 | IPC - 22 | 2.5 | Sualkuchi | 523
P29-WELL-L15 | P29 - 15th Lift | 402.a | MPSB/Str/2413 | Str | 1 | 4 | 2025-10-07 | IPC - 22 | 2.5 | Sualkuchi | 524
P29-WELL-L15 | P29 - 15th Lift | 402.a | MPSB/Sur/1935 | Sur | 2 | 4 | 2025-10-07 | IPC - 22 | 2.5 | Sualkuchi | 524
P29-WELL-L15 | P29 - 15th Lift | 402.a | MPSB/Str/2414 | Str | 3 | 4 | 2025-10-07 | IPC - 22 | 2.5 | Sualkuchi | 524
P29-WELL-L15 | P29 - 15th Lift | 402.a | MPSB/Sur/1974 | Sur | 4 | 4 | 2025-10-13 | IPC - 22 | 2.5 | Sualkuchi | 524
P24-WELL-L15 | P24 - 15th Lift | 402.a | MPSB/Str/2709 | Str | 1 | 3 | 2025-11-06 | IPC - 23 | 2.5 | Sualkuchi | 525
P24-WELL-L15 | P24 - 15th Lift | 402.a | MPSB/Sur/2134 | Sur | 2 | 3 | 2025-11-06 | IPC - 23 | 2.5 | Sualkuchi | 525
P24-WELL-L15 | P24 - 15th Lift | 402.a | MPSB/Str/2710 | Str | 3 | 3 | 2025-11-06 | IPC - 23 | 2.5 | Sualkuchi | 525
P27-WELL-L15 | P27 - 15th Lift | 402.a | MPSB/Str/2871 | Str | 1 | 4 | 2025-11-20 | IPC - 23 | 2.5 | Sualkuchi | 526
P27-WELL-L15 | P27 - 15th Lift | 402.a | MPSB/Sur/2239 | Sur | 2 | 4 | 2025-11-20 | IPC - 23 | 2.5 | Sualkuchi | 526
P27-WELL-L15 | P27 - 15th Lift | 402.a | MPSB/Str/2872 | Str | 3 | 4 | 2025-11-20 | IPC - 23 | 2.5 | Sualkuchi | 526
P27-WELL-L15 | P27 - 15th Lift | 402.a | MPSB/Sur/2260 | Sur | 4 | 4 | 2025-11-24 | IPC - 23 | 2.5 | Sualkuchi | 526
P15-WELL-L15 | P15 - 15th Lift | 402.a | MPSB/Str/3317 | Str | 1 | 3 | 2025-12-29 | IPC - 25 | 2.5 | Palashbari | 527
P15-WELL-L15 | P15 - 15th Lift | 402.a | MPSB/Sur/2529 | Sur | 2 | 3 | 2025-12-29 | IPC - 25 | 2.5 | Palashbari | 527
P15-WELL-L15 | P15 - 15th Lift | 402.a | MPSB/Str/3318 | Str | 3 | 3 | 2025-12-29 | IPC - 25 | 2.5 | Palashbari | 527
P19-WELL-L15 | P19 - 15th Lift | 402.a | MPSB/Str/3352 | Str | 1 | 3 | 2025-12-30 | IPC - 25 | 2.5 | Sualkuchi | 528
P19-WELL-L15 | P19 - 15th Lift | 402.a | MPSB/Sur/2554 | Sur | 2 | 3 | 2025-12-30 | IPC - 25 | 2.5 | Sualkuchi | 528
P19-WELL-L15 | P19 - 15th Lift | 402.a | MPSB/Str/3353 | Str | 3 | 3 | 2025-12-30 | IPC - 25 | 2.5 | Sualkuchi | 528
P23-WELL-L15 | P23 - 15th Lift | 402.a | MPSB/Str/3177 | Str | 1 | 4 | 2025-12-17 | IPC - 25 | 2.5 | Sualkuchi | 529
P23-WELL-L15 | P23 - 15th Lift | 402.a | MPSB/Sur/2431 | Sur | 2 | 4 | 2025-12-17 | IPC - 25 | 2.5 | Sualkuchi | 529
P23-WELL-L15 | P23 - 15th Lift | 402.a | MPSB/Str/3203 | Str | 3 | 4 | 2025-12-19 | IPC - 25 | 2.5 | Sualkuchi | 529
P23-WELL-L15 | P23 - 15th Lift | 402.a | MPSB/Sur/2474 | Sur | 4 | 4 | 2025-12-23 | IPC - 25 | 2.5 | Sualkuchi | 529
P21-WELL-L15 | P21 - 15th Lift | 402.a | MPSB/Str/3521 | Str | 1 | 4 | 2026-01-14 | IPC - 26 | 2.5 | Sualkuchi | 530
P21-WELL-L15 | P21 - 15th Lift | 402.a | MPSB/Sur/2677 | Sur | 2 | 4 | 2026-01-14 | IPC - 26 | 2.5 | Sualkuchi | 530
P21-WELL-L15 | P21 - 15th Lift | 402.a | MPSB/Str/3522 | Str | 3 | 4 | 2026-01-14 | IPC - 26 | 2.5 | Sualkuchi | 530
P21-WELL-L15 | P21 - 15th Lift | 402.a | MPSB/Sur/2713 | Sur | 4 | 4 | 2026-01-19 | IPC - 26 | 2.5 | Sualkuchi | 530
P30-WELL-L15 | P30 - 15th Lift | 402.a | MPSB/Str/3834 | Str | 1 | 4 | 2026-02-11 | IPC - 27 | 2.5 | Palashbari | 531
P30-WELL-L15 | P30 - 15th Lift | 402.a | MPSB/Sur/2914 | Sur | 2 | 4 | 2026-02-11 | IPC - 27 | 2.5 | Palashbari | 531
P30-WELL-L15 | P30 - 15th Lift | 402.a | MPSB/Str/3835 | Str | 3 | 4 | 2026-02-11 | IPC - 27 | 2.5 | Palashbari | 531
P30-WELL-L15 | P30 - 15th Lift | 402.a | MPSB/Sur/2936 | Sur | 4 | 4 | 2026-02-15 | IPC - 27 | 2.5 | Palashbari | 531
P14(N)-WELL-L15 | P14(N) - 15th Lift | 402.a | MPSB/Str/4666 | Str | 1 | 3 | 2026-05-13 | IPC - 31 | 2.5 | Palashbari | 532
P14(N)-WELL-L15 | P14(N) - 15th Lift | 402.a | MPSB/Sur/3474 | Sur | 2 | 3 | 2026-05-13 | IPC - 31 | 2.5 | Palashbari | 532
P14(N)-WELL-L15 | P14(N) - 15th Lift | 402.a | MPSB/Str/4667 | Str | 3 | 3 | 2026-05-13 | IPC - 31 | 2.5 | Palashbari | 532
P12(A)-WELL-L15 | P12(A) - 15th Lift | 402.a | MPSB/Str/4978 | Str | 1 | 3 | 2026-06-22 | IPC - 33 | 2.8 | Palashbari | 533
P12(A)-WELL-L15 | P12(A) - 15th Lift | 402.a | MPSB/Sur/3676 | Sur | 2 | 3 | 2026-06-22 | IPC - 33 | 2.8 | Palashbari | 533
P12(A)-WELL-L15 | P12(A) - 15th Lift | 402.a | MPSB/Str/4979 | Str | 3 | 3 | 2026-06-22 | IPC - 33 | 2.8 | Palashbari | 533
P11-WELL-L15 | P11 - 15th Lift | 402.a | MPSB/Str/5002 | Str | 1 | 3 | 2026-06-25 | IPC - 33 | 2.5 | Palashbari | 534
P11-WELL-L15 | P11 - 15th Lift | 402.a | MPSB/Sur/3690 | Sur | 2 | 3 | 2026-06-25 | IPC - 33 | 2.5 | Palashbari | 534
P11-WELL-L15 | P11 - 15th Lift | 402.a | MPSB/Str/5003 | Str | 3 | 3 | 2026-06-25 | IPC - 33 | 2.5 | Palashbari | 534
P6-WELL-L16 | P6 - 16th Lift | 402.a | MPSB/Str/1732 | Str | 1 | 3 | 2025-06-29 | IPC - 16 | 2.5 | Palashbari | 536
P6-WELL-L16 | P6 - 16th Lift | 402.a | MPSB/Sur/1473 | Sur | 2 | 3 | 2025-06-29 | IPC - 16 | 2.5 | Palashbari | 536
P6-WELL-L16 | P6 - 16th Lift | 402.a | MPSB/Str/1733 | Str | 3 | 3 | 2025-06-29 | IPC - 16 | 2.5 | Palashbari | 536
P26-WELL-L16 | P26 - 16th Lift | 402.a | MPSB/Str/1728 | Str | 1 | 3 | 2025-06-29 | IPC - 16 | 2.5 | Sualkuchi | 537
P26-WELL-L16 | P26 - 16th Lift | 402.a | MPSB/Sur/1472 | Sur | 2 | 3 | 2025-06-29 | IPC - 16 | 2.5 | Sualkuchi | 537
P26-WELL-L16 | P26 - 16th Lift | 402.a | MPSB/Str/1729 | Str | 3 | 3 | 2025-06-29 | IPC - 16 | 2.5 | Sualkuchi | 537
P10-WELL-L16 | P10 - 16th Lift | 402.a | MPSB/Str/1807 | Str | 1 | 4 | 2025-07-14 | IPC - 18 | 2.5 | Palashbari | 538
P10-WELL-L16 | P10 - 16th Lift | 402.a | MPSB/Sur/1519 | Sur | 2 | 4 | 2025-07-14 | IPC - 18 | 2.5 | Palashbari | 538
P10-WELL-L16 | P10 - 16th Lift | 402.a | MPSB/Str/1808 | Str | 3 | 4 | 2025-07-14 | IPC - 18 | 2.5 | Palashbari | 538
P10-WELL-L16 | P10 - 16th Lift | 402.a | MPSB/Sur/1550 | Sur | 4 | 4 | 2025-07-19 | IPC - 18 | 2.5 | Palashbari | 538
P8-WELL-L16 | P8 - 16th Lift | 402.a | MPSB/Str/2047 | Str | 1 | 4 | 2025-08-18 | IPC - 19 | 2.5 | Palashbari | 539
P8-WELL-L16 | P8 - 16th Lift | 402.a | MPSB/Sur/1700 | Sur | 2 | 4 | 2025-08-18 | IPC - 19 | 2.5 | Palashbari | 539
P8-WELL-L16 | P8 - 16th Lift | 402.a | MPSB/Str/2048 | Str | 3 | 4 | 2025-08-18 | IPC - 19 | 2.5 | Palashbari | 539
P8-WELL-L16 | P8 - 16th Lift | 402.a | MPSB/Sur/1710 | Sur | 4 | 4 | 2025-08-21 | IPC - 19 | 2.5 | Palashbari | 539 | P8-WELL-L15
P18-WELL-L16 | P18 - 16th Lift | 402.a | MPSB/Str/1996 | Str | 1 | 4 | 2025-08-07 | IPC - 19 | 2.6 | Palashbari | 540
P18-WELL-L16 | P18 - 16th Lift | 402.a | MPSB/Sur/1658 | Sur | 2 | 4 | 2025-08-07 | IPC - 19 | 2.6 | Palashbari | 540
P18-WELL-L16 | P18 - 16th Lift | 402.a | MPSB/Str/1997 | Str | 3 | 4 | 2025-08-07 | IPC - 19 | 2.6 | Palashbari | 540
P18-WELL-L16 | P18 - 16th Lift | 402.a | MPSB/Sur/1677 | Sur | 4 | 4 | 2025-08-11 | IPC - 19 | 2.6 | Palashbari | 540 | P18-WELL-L15
P16-WELL-L16 | P16 - 16th Lift | 402.a | MPSB/Str/2147 | Str | 1 | 4 | 2025-09-04 | IPC - 20 | 2.5 | Palashbari | 541
P16-WELL-L16 | P16 - 16th Lift | 402.a | MPSB/Sur/1766 | Sur | 2 | 4 | 2025-09-04 | IPC - 20 | 2.5 | Palashbari | 541
P16-WELL-L16 | P16 - 16th Lift | 402.a | MPSB/Str/2148 | Str | 3 | 4 | 2025-09-04 | IPC - 20 | 2.5 | Palashbari | 541
P16-WELL-L16 | P16 - 16th Lift | 402.a | MPSB/Sur/1788 | Sur | 4 | 4 | 2025-09-08 | IPC - 20 | 2.5 | Palashbari | 541
P22-WELL-L16 | P22 - 16th Lift | 402.a | MPSB/Str/2356 | Str | 1 | 3 | 2025-09-29 | IPC - 20 | 2.57 | Sualkuchi | 542
P22-WELL-L16 | P22 - 16th Lift | 402.a | MPSB/Sur/1890 | Sur | 2 | 3 | 2025-09-29 | IPC - 20 | 2.57 | Sualkuchi | 542
P22-WELL-L16 | P22 - 16th Lift | 402.a | MPSB/Str/2357 | Str | 3 | 3 | 2025-09-29 | IPC - 20 | 2.57 | Sualkuchi | 542
P28-WELL-L16 | P28 - 16th Lift | 402.a | MPSB/Str/2292 | Str | 1 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Sualkuchi | 543
P28-WELL-L16 | P28 - 16th Lift | 402.a | MPSB/Sur/1856 | Sur | 2 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Sualkuchi | 543
P28-WELL-L16 | P28 - 16th Lift | 402.a | MPSB/Str/2315 | Str | 3 | 3 | 2025-09-25 | IPC - 20 | 2.5 | Sualkuchi | 543
P17-WELL-L16 | P17 - 16th Lift | 402.a | MPSB/Str/2611 | Str | 1 | 3 | 2025-10-28 | IPC - 22 | 2.5 | Palashbari | 544
P17-WELL-L16 | P17 - 16th Lift | 402.a | MPSB/Sur/2062 | Sur | 2 | 3 | 2025-10-28 | IPC - 22 | 2.5 | Palashbari | 544
P17-WELL-L16 | P17 - 16th Lift | 402.a | MPSB/Str/2612 | Str | 3 | 3 | 2025-10-28 | IPC - 22 | 2.5 | Palashbari | 544
P20-WELL-L16 | P20 - 16th Lift | 402.a | MPSB/Str/2628 | Str | 1 | 3 | 2025-10-30 | IPC - 22 | 2.5 | Sualkuchi | 545
P20-WELL-L16 | P20 - 16th Lift | 402.a | MPSB/Sur/2069 | Sur | 2 | 3 | 2025-10-30 | IPC - 22 | 2.5 | Sualkuchi | 545
P20-WELL-L16 | P20 - 16th Lift | 402.a | MPSB/Str/2629 | Str | 3 | 3 | 2025-10-30 | IPC - 22 | 2.5 | Sualkuchi | 545
P25-WELL-L16 | P25 - 16th Lift | 402.a | MPSB/Str/2619 | Str | 1 | 3 | 2025-10-29 | IPC - 22 | 2.5 | Sualkuchi | 546
P25-WELL-L16 | P25 - 16th Lift | 402.a | MPSB/Sur/2066 | Sur | 2 | 3 | 2025-10-29 | IPC - 22 | 2.5 | Sualkuchi | 546
P25-WELL-L16 | P25 - 16th Lift | 402.a | MPSB/Str/2620 | Str | 3 | 3 | 2025-10-29 | IPC - 22 | 2.5 | Sualkuchi | 546
P29-WELL-L16 | P29 - 16th Lift | 402.a | MPSB/Str/2586 | Str | 1 | 3 | 2025-10-25 | IPC - 22 | 2.5 | Sualkuchi | 547
P29-WELL-L16 | P29 - 16th Lift | 402.a | MPSB/Sur/2049 | Sur | 2 | 3 | 2025-10-25 | IPC - 22 | 2.5 | Sualkuchi | 547
P29-WELL-L16 | P29 - 16th Lift | 402.a | MPSB/Str/2587 | Str | 3 | 3 | 2025-10-25 | IPC - 22 | 2.5 | Sualkuchi | 547
P7-WELL-L16 | P7 - 16th Lift | 402.a | MPSB/Str/2867 | Str | 1 | 3 | 2025-11-20 | IPC - 23 | 2.5 | Palashbari | 548
P7-WELL-L16 | P7 - 16th Lift | 402.a | MPSB/Sur/2232 | Sur | 2 | 3 | 2025-11-20 | IPC - 23 | 2.5 | Palashbari | 548
P7-WELL-L16 | P7 - 16th Lift | 402.a | MPSB/Str/2868 | Str | 3 | 3 | 2025-11-20 | IPC - 23 | 2.5 | Palashbari | 548
P9-WELL-L16 | P9 - 16th Lift | 402.a | MPSB/Str/2777 | Str | 1 | 3 | 2025-11-12 | IPC - 23 | 2.5 | Palashbari | 549
P9-WELL-L16 | P9 - 16th Lift | 402.a | MPSB/Sur/2176 | Sur | 2 | 3 | 2025-11-12 | IPC - 23 | 2.5 | Palashbari | 549
P9-WELL-L16 | P9 - 16th Lift | 402.a | MPSB/Str/2778 | Str | 3 | 3 | 2025-11-12 | IPC - 23 | 2.5 | Palashbari | 549
P24-WELL-L16 | P24 - 16th Lift | 402.a | MPSB/Str/2923 | Str | 1 | 3 | 2025-11-25 | IPC - 23 | 2.5 | Sualkuchi | 550
P24-WELL-L16 | P24 - 16th Lift | 402.a | MPSB/Sur/2265 | Sur | 2 | 3 | 2025-11-25 | IPC - 23 | 2.5 | Sualkuchi | 550
P24-WELL-L16 | P24 - 16th Lift | 402.a | MPSB/Str/2924 | Str | 3 | 3 | 2025-11-25 | IPC - 23 | 2.5 | Sualkuchi | 550
P27-WELL-L16 | P27 - 16th Lift | 402.a | MPSB/Str/3003 | Str | 1 | 3 | 2025-11-30 | IPC - 23 | 2.5 | Sualkuchi | 551
P27-WELL-L16 | P27 - 16th Lift | 402.a | MPSB/Sur/2316 | Sur | 2 | 3 | 2025-11-30 | IPC - 23 | 2.5 | Sualkuchi | 551
P27-WELL-L16 | P27 - 16th Lift | 402.a | MPSB/Str/3004 | Str | 3 | 3 | 2025-11-30 | IPC - 23 | 2.5 | Sualkuchi | 551
P23-WELL-L16 | P23 - 16th Lift | 402.a | MPSB/Str/3284 | Str | 1 | 3 | 2025-12-26 | IPC - 25 | 2.5 | Sualkuchi | 552
P23-WELL-L16 | P23 - 16th Lift | 402.a | MPSB/Sur/2506 | Sur | 2 | 3 | 2025-12-26 | IPC - 25 | 2.5 | Sualkuchi | 552
P23-WELL-L16 | P23 - 16th Lift | 402.a | MPSB/Str/3285 | Str | 3 | 3 | 2025-12-26 | IPC - 25 | 2.5 | Sualkuchi | 552
P15-WELL-L16 | P15 - 16th Lift | 402.a | MPSB/Str/3444 | Str | 1 | 3 | 2026-01-07 | IPC - 26 | 2.5 | Palashbari | 553
P15-WELL-L16 | P15 - 16th Lift | 402.a | MPSB/Sur/2620 | Sur | 2 | 3 | 2026-01-07 | IPC - 26 | 2.5 | Palashbari | 553
P15-WELL-L16 | P15 - 16th Lift | 402.a | MPSB/Str/3445 | Str | 3 | 3 | 2026-01-07 | IPC - 26 | 2.5 | Palashbari | 553
P19-WELL-L16 | P19 - 16th Lift | 402.a | MPSB/Str/3475 | Str | 1 | 4 | 2026-01-09 | IPC - 26 | 2.5 | Palashbari | 554
P19-WELL-L16 | P19 - 16th Lift | 402.a | MPSB/Sur/2641 | Sur | 2 | 4 | 2026-01-09 | IPC - 26 | 2.5 | Palashbari | 554
P19-WELL-L16 | P19 - 16th Lift | 402.a | MPSB/Str/3476 | Str | 3 | 4 | 2026-01-09 | IPC - 26 | 2.5 | Palashbari | 554
P19-WELL-L16 | P19 - 16th Lift | 402.a | MPSB/Sur/2668 | Sur | 4 | 4 | 2026-01-13 | IPC - 26 | 2.5 | Palashbari | 554
P21-WELL-L16 | P21 - 16th Lift | 402.a | MPSB/Str/3617 | Str | 1 | 4 | 2026-01-23 | IPC - 26 | 2.5 | Sualkuchi | 555
P21-WELL-L16 | P21 - 16th Lift | 402.a | MPSB/Sur/2746 | Sur | 2 | 4 | 2026-01-23 | IPC - 26 | 2.5 | Sualkuchi | 555
P21-WELL-L16 | P21 - 16th Lift | 402.a | MPSB/Str/3618 | Str | 3 | 4 | 2026-01-23 | IPC - 26 | 2.5 | Sualkuchi | 555
P21-WELL-L16 | P21 - 16th Lift | 402.a | MPSB/Sur/2772 | Sur | 4 | 4 | 2026-01-25 | IPC - 26 | 2.5 | Sualkuchi | 555
P30-WELL-L16 | P30 - 16th Lift | 402.a | MPSB/Str/3955 | Str | 1 | 3 | 2026-02-26 | IPC - 27 | 2.5 | Palashbari | 556
P30-WELL-L16 | P30 - 16th Lift | 402.a | MPSB/Sur/3008 | Sur | 2 | 3 | 2026-02-26 | IPC - 27 | 2.5 | Palashbari | 556
P30-WELL-L16 | P30 - 16th Lift | 402.a | MPSB/Str/3956 | Str | 3 | 3 | 2026-02-26 | IPC - 27 | 2.5 | Palashbari | 556
P14(N)-WELL-L16 | P14(N) - 16th Lift | 402.a | MPSB/Str/4779 | Str | 1 | 3 | 2026-05-25 | IPC - 31 | 2.5 | Palashbari | 557
P14(N)-WELL-L16 | P14(N) - 16th Lift | 402.a | MPSB/Sur/3545 | Sur | 2 | 3 | 2026-05-25 | IPC - 31 | 2.5 | Palashbari | 557
P14(N)-WELL-L16 | P14(N) - 16th Lift | 402.a | MPSB/Str/4780 | Str | 3 | 3 | 2026-05-25 | IPC - 31 | 2.5 | Palashbari | 557
P26-WELL-L17 | P26 - 17th Lift | 402.a | MPSB/Str/1857 | Str | 1 | 4 | 2025-07-21 | IPC - 18 | 2.5 | Sualkuchi | 559
P26-WELL-L17 | P26 - 17th Lift | 402.a | MPSB/Sur/1557 | Sur | 2 | 4 | 2025-07-21 | IPC - 18 | 2.5 | Sualkuchi | 559
P26-WELL-L17 | P26 - 17th Lift | 402.a | MPSB/Str/1858 | Str | 3 | 4 | 2025-07-21 | IPC - 18 | 2.5 | Sualkuchi | 559
P26-WELL-L17 | P26 - 17th Lift | 402.a | MPSB/Sur/1628 | Sur | 4 | 4 | 2025-07-31 | IPC - 18 | 2.5 | Sualkuchi | 559
P6-WELL-L17 | P6 - 17th Lift | 402.a | MPSB/Str/1902 | Str | 1 | 3 | 2025-07-27 | IPC - 18 | 2.5 | Palashbari | 560
P6-WELL-L17 | P6 - 17th Lift | 402.a | MPSB/Sur/1594 | Sur | 2 | 3 | 2025-07-27 | IPC - 18 | 2.5 | Palashbari | 560
P6-WELL-L17 | P6 - 17th Lift | 402.a | MPSB/Str/1903 | Str | 3 | 3 | 2025-07-27 | IPC - 18 | 2.5 | Palashbari | 560
P10-WELL-L17 | P10 - 17th Lift | 402.a | MPSB/Str/1930 | Str | 1 | 3 | 2025-07-31 | IPC - 18 | 2.5 | Palashbari | 561
P10-WELL-L17 | P10 - 17th Lift | 402.a | MPSB/Sur/1615 | Sur | 2 | 3 | 2025-07-31 | IPC - 18 | 2.5 | Palashbari | 561
P10-WELL-L17 | P10 - 17th Lift | 402.a | MPSB/Str/1931 | Str | 3 | 3 | 2025-07-31 | IPC - 18 | 2.5 | Palashbari | 561
P18-WELL-L17 | P18 - 17th Lift | 402.a | MPSB/Str/2107 | Str | 1 | 3 | 2025-08-29 | IPC - 19 | 2.5 | Palashbari | 562
P18-WELL-L17 | P18 - 17th Lift | 402.a | MPSB/Sur/1745 | Sur | 2 | 3 | 2025-08-29 | IPC - 19 | 2.5 | Palashbari | 562
P18-WELL-L17 | P18 - 17th Lift | 402.a | MPSB/Str/2108 | Str | 3 | 3 | 2025-08-29 | IPC - 19 | 2.5 | Palashbari | 562
P8-WELL-L17 | P8 - 17th Lift | 402.a | MPSB/Str/2190 | Str | 1 | 3 | 2025-09-09 | IPC - 20 | 2.5 | Palashbari | 563
P8-WELL-L17 | P8 - 17th Lift | 402.a | MPSB/Sur/1796 | Sur | 2 | 3 | 2025-09-09 | IPC - 20 | 2.5 | Palashbari | 563
P8-WELL-L17 | P8 - 17th Lift | 402.a | MPSB/Str/2191 | Str | 3 | 3 | 2025-09-09 | IPC - 20 | 2.5 | Palashbari | 563
P16-WELL-L17 | P16 - 17th Lift | 402.a | MPSB/Str/2290 | Str | 1 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Palashbari | 564
P16-WELL-L17 | P16 - 17th Lift | 402.a | MPSB/Sur/1855 | Sur | 2 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Palashbari | 564
P16-WELL-L17 | P16 - 17th Lift | 402.a | MPSB/Str/2291 | Str | 3 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Palashbari | 564
P22-WELL-L17 | P22 - 17th Lift | 402.a | MPSB/Str/2475 | Str | 1 | 4 | 2025-10-14 | IPC - 22 | 2.5 | Sualkuchi | 565
P22-WELL-L17 | P22 - 17th Lift | 402.a | MPSB/Sur/1984 | Sur | 2 | 4 | 2025-10-14 | IPC - 22 | 2.5 | Sualkuchi | 565
P22-WELL-L17 | P22 - 17th Lift | 402.a | MPSB/Str/2476 | Str | 3 | 4 | 2025-10-14 | IPC - 22 | 2.5 | Sualkuchi | 565
P22-WELL-L17 | P22 - 17th Lift | 402.a | MPSB/Sur/2010 | Sur | 4 | 4 | 2025-10-18 | IPC - 22 | 2.5 | Sualkuchi | 565
P28-WELL-L17 | P28 - 17th Lift | 402.a | MPSB/Str/2442 | Str | 1 | 4 | 2025-10-10 | IPC - 22 | 2.5 | Sualkuchi | 566
P28-WELL-L17 | P28 - 17th Lift | 402.a | MPSB/Sur/1960 | Sur | 2 | 4 | 2025-10-10 | IPC - 22 | 2.5 | Sualkuchi | 566
P28-WELL-L17 | P28 - 17th Lift | 402.a | MPSB/Str/2460 | Str | 3 | 4 | 2025-10-13 | IPC - 22 | 2.5 | Sualkuchi | 566
P28-WELL-L17 | P28 - 17th Lift | 402.a | MPSB/Sur/2001 | Sur | 4 | 4 | 2025-10-17 | IPC - 22 | 2.5 | Sualkuchi | 566
P29-WELL-L17 | P29 - 17th Lift | 402.a | MPSB/Str/2652 | Str | 1 | 3 | 2025-10-31 | IPC - 22 | 2.5 | Sualkuchi | 567
P29-WELL-L17 | P29 - 17th Lift | 402.a | MPSB/Sur/2082 | Sur | 2 | 3 | 2025-10-31 | IPC - 22 | 2.5 | Sualkuchi | 567
P29-WELL-L17 | P29 - 17th Lift | 402.a | MPSB/Str/2653 | Str | 3 | 3 | 2025-10-31 | IPC - 22 | 2.5 | Sualkuchi | 567
P7-WELL-L17 | P7 - 17th Lift | 402.a | MPSB/Str/2938 | Str | 1 | 3 | 2025-11-26 | IPC - 23 | 2.5 | Palashbari | 568
P7-WELL-L17 | P7 - 17th Lift | 402.a | MPSB/Sur/2278 | Sur | 2 | 3 | 2025-11-26 | IPC - 23 | 2.5 | Palashbari | 568
P7-WELL-L17 | P7 - 17th Lift | 402.a | MPSB/Str/2939 | Str | 3 | 3 | 2025-11-26 | IPC - 23 | 2.5 | Palashbari | 568
P20-WELL-L17 | P20 - 17th Lift | 402.a | MPSB/Str/2811 | Str | 1 | 4 | 2025-11-14 | IPC - 23 | 2.5 | Sualkuchi | 569
P20-WELL-L17 | P20 - 17th Lift | 402.a | MPSB/Sur/2193 | Sur | 2 | 4 | 2025-11-14 | IPC - 23 | 2.5 | Sualkuchi | 569
P20-WELL-L17 | P20 - 17th Lift | 402.a | MPSB/Str/2812 | Str | 3 | 4 | 2025-11-14 | IPC - 23 | 2.5 | Sualkuchi | 569
P20-WELL-L17 | P20 - 17th Lift | 402.a | MPSB/Sur/2215 | Sur | 4 | 4 | 2025-11-18 | IPC - 23 | 2.5 | Sualkuchi | 569
P25-WELL-L17 | P25 - 17th Lift | 402.a | MPSB/Str/2749 | Str | 1 | 4 | 2025-11-09 | IPC - 23 | 2.5 | Sualkuchi | 570
P25-WELL-L17 | P25 - 17th Lift | 402.a | MPSB/Sur/2161 | Sur | 2 | 4 | 2025-11-09 | IPC - 23 | 2.5 | Sualkuchi | 570
P25-WELL-L17 | P25 - 17th Lift | 402.a | MPSB/Str/2750 | Str | 3 | 4 | 2025-11-09 | IPC - 23 | 2.5 | Sualkuchi | 570
P25-WELL-L17 | P25 - 17th Lift | 402.a | MPSB/Sur/2199 | Sur | 4 | 4 | 2025-11-15 | IPC - 23 | 2.5 | Sualkuchi | 570
P9-WELL-L17 | P9 - 17th Lift | 402.a | MPSB/Str/3165 | Str | 1 | 3 | 2025-12-16 | IPC - 25 | 2.3 | Palashbari | 571
P9-WELL-L17 | P9 - 17th Lift | 402.a | MPSB/Sur/2424 | Sur | 2 | 3 | 2025-12-16 | IPC - 25 | 2.3 | Palashbari | 571
P9-WELL-L17 | P9 - 17th Lift | 402.a | MPSB/Str/3166 | Str | 3 | 3 | 2025-12-16 | IPC - 25 | 2.3 | Palashbari | 571
P23-WELL-L17 | P23 - 17th Lift | 402.a | MPSB/Str/3387 | Str | 1 | 3 | 2025-12-31 | IPC - 25 | 2.5 | Sualkuchi | 572
P23-WELL-L17 | P23 - 17th Lift | 402.a | MPSB/Sur/2575 | Sur | 2 | 3 | 2025-12-31 | IPC - 25 | 2.5 | Sualkuchi | 572
P23-WELL-L17 | P23 - 17th Lift | 402.a | MPSB/Str/3388 | Str | 3 | 3 | 2025-12-31 | IPC - 25 | 2.5 | Sualkuchi | 572
P24-WELL-L17 | P24 - 17th Lift | 402.a | MPSB/Str/3085 | Str | 1 | 4 | 2025-12-08 | IPC - 25 | 2.5 | Sualkuchi | 573
P24-WELL-L17 | P24 - 17th Lift | 402.a | MPSB/Sur/2368 | Sur | 2 | 4 | 2025-12-08 | IPC - 25 | 2.5 | Sualkuchi | 573
P24-WELL-L17 | P24 - 17th Lift | 402.a | MPSB/Str/3086 | Str | 3 | 4 | 2025-12-08 | IPC - 25 | 2.5 | Sualkuchi | 573
P24-WELL-L17 | P24 - 17th Lift | 402.a | MPSB/Sur/2388 | Sur | 4 | 4 | 2025-12-11 | IPC - 25 | 2.5 | Sualkuchi | 573
P27-WELL-L17 | P27 - 17th Lift | 402.a | MPSB/Str/3281 | Str | 1 | 3 | 2025-12-26 | IPC - 25 | 2.5 | Sualkuchi | 574
P27-WELL-L17 | P27 - 17th Lift | 402.a | MPSB/Sur/2505 | Sur | 2 | 3 | 2025-12-26 | IPC - 25 | 2.5 | Sualkuchi | 574
P27-WELL-L17 | P27 - 17th Lift | 402.a | MPSB/Str/3325 | Str | 3 | 3 | 2025-12-29 | IPC - 25 | 2.5 | Sualkuchi | 574
P17-WELL-L17 | P17 - 17th Lift | 402.a | MPSB/Str/3569 | Str | 1 | 4 | 2026-01-19 | IPC - 26 | 2.5 | Palashbari | 575
P17-WELL-L17 | P17 - 17th Lift | 402.a | MPSB/Sur/2711 | Sur | 2 | 4 | 2026-01-19 | IPC - 26 | 2.5 | Palashbari | 575
P17-WELL-L17 | P17 - 17th Lift | 402.a | MPSB/Str/3570 | Str | 3 | 4 | 2026-01-19 | IPC - 26 | 2.5 | Palashbari | 575
P17-WELL-L17 | P17 - 17th Lift | 402.a | MPSB/Sur/2767 | Sur | 4 | 4 | 2026-01-24 | IPC - 26 | 2.5 | Palashbari | 575
P19-WELL-L17 | P19 - 17th Lift | 402.a | MPSB/Str/3545 | Str | 1 | 4 | 2026-01-16 | IPC - 26 | 2.5 | Sualkuchi | 576
P19-WELL-L17 | P19 - 17th Lift | 402.a | MPSB/Sur/2697 | Sur | 2 | 4 | 2026-01-16 | IPC - 26 | 2.5 | Sualkuchi | 576
P19-WELL-L17 | P19 - 17th Lift | 402.a | MPSB/Str/3546 | Str | 3 | 4 | 2026-01-16 | IPC - 26 | 2.5 | Sualkuchi | 576
P19-WELL-L17 | P19 - 17th Lift | 402.a | MPSB/Sur/2725 | Sur | 4 | 4 | 2026-01-20 | IPC - 26 | 2.5 | Sualkuchi | 576
P21-WELL-L17 | P21 - 17th Lift | 402.a | MPSB/Str/3693 | Str | 1 | 3 | 2026-01-30 | IPC - 26 | 2.5 | Sualkuchi | 577
P21-WELL-L17 | P21 - 17th Lift | 402.a | MPSB/Sur/2805 | Sur | 2 | 3 | 2026-01-30 | IPC - 26 | 2.5 | Sualkuchi | 577
P21-WELL-L17 | P21 - 17th Lift | 402.a | MPSB/Str/3694 | Str | 3 | 3 | 2026-01-30 | IPC - 26 | 2.5 | Sualkuchi | 577
P15-WELL-L17 | P15 - 17th Lift | 402.a | MPSB/Str/3886 | Str | 1 | 4 | 2026-02-17 | IPC - 27 | 2.5 | Palashbari | 578
P15-WELL-L17 | P15 - 17th Lift | 402.a | MPSB/Sur/2951 | Sur | 2 | 4 | 2026-02-17 | IPC - 27 | 2.5 | Palashbari | 578
P15-WELL-L17 | P15 - 17th Lift | 402.a | MPSB/Str/3887 | Str | 3 | 4 | 2026-02-17 | IPC - 27 | 2.5 | Palashbari | 578
P15-WELL-L17 | P15 - 17th Lift | 402.a | MPSB/Sur/2990 | Sur | 4 | 4 | 2026-02-25 | IPC - 27 | 2.5 | Palashbari | 578
P30-WELL-L17 | P30 - 17th Lift | 402.a | MPSB/Str/4567 | Str | 1 | 3 | 2026-04-30 | IPC - 30 | 2.5 | Palashbari | 579
P30-WELL-L17 | P30 - 17th Lift | 402.a | MPSB/Sur/3406 | Sur | 2 | 3 | 2026-04-30 | IPC - 30 | 2.5 | Palashbari | 579
P30-WELL-L17 | P30 - 17th Lift | 402.a | MPSB/Str/4568 | Str | 3 | 3 | 2026-04-30 | IPC - 30 | 2.5 | Palashbari | 579
P14(N)-WELL-L17 | P14(N) - 17th Lift | 402.a | MPSB/Str/4894 | Str | 1 | 3 | 2026-06-12 | IPC - 33 | 2.5 | Palashbari | 580
P14(N)-WELL-L17 | P14(N) - 17th Lift | 402.a | MPSB/Sur/3639 | Sur | 2 | 3 | 2026-06-12 | IPC - 33 | 2.5 | Palashbari | 580
P14(N)-WELL-L17 | P14(N) - 17th Lift | 402.a | MPSB/Str/4895 | Str | 3 | 3 | 2026-06-12 | IPC - 33 | 2.5 | Palashbari | 580
P6-WELL-L18 | P6 - 18th Lift | 402.a | MPSB/Str/2010 | Str | 1 | 4 | 2025-08-09 | IPC - 19 | 2.4 | Palashbari | 582
P6-WELL-L18 | P6 - 18th Lift | 402.a | MPSB/Sur/1668 | Sur | 2 | 4 | 2025-08-09 | IPC - 19 | 2.4 | Palashbari | 582
P6-WELL-L18 | P6 - 18th Lift | 402.a | MPSB/Str/2011 | Str | 3 | 4 | 2025-08-09 | IPC - 19 | 2.4 | Palashbari | 582
P6-WELL-L18 | P6 - 18th Lift | 402.a | MPSB/Sur/1704 | Sur | 4 | 4 | 2025-08-20 | IPC - 19 | 2.4 | Palashbari | 582
P26-WELL-L18 | P26 - 18th Lift | 402.a | MPSB/Str/1985 | Str | 1 | 3 | 2025-08-05 | IPC - 19 | 1.85 | Sualkuchi | 583
P26-WELL-L18 | P26 - 18th Lift | 402.a | MPSB/Sur/1654 | Sur | 2 | 3 | 2025-08-05 | IPC - 19 | 1.85 | Sualkuchi | 583
P26-WELL-L18 | P26 - 18th Lift | 402.a | MPSB/Str/1986 | Str | 3 | 3 | 2025-08-05 | IPC - 19 | 1.85 | Sualkuchi | 583
P16-WELL-L18 | P16 - 18th Lift | 402.a | MPSB/Str/2337 | Str | 1 | 3 | 2025-09-29 | IPC - 20 | 2.5 | Palashbari | 584
P16-WELL-L18 | P16 - 18th Lift | 402.a | MPSB/Sur/1884 | Sur | 2 | 3 | 2025-09-29 | IPC - 20 | 2.5 | Palashbari | 584
P16-WELL-L18 | P16 - 18th Lift | 402.a | MPSB/Str/2338 | Str | 3 | 3 | 2025-09-29 | IPC - 20 | 2.5 | Palashbari | 584
P8-WELL-L18 | P8 - 18th Lift | 402.a | MPSB/Str/2286 | Str | 1 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Palashbari | 585
P8-WELL-L18 | P8 - 18th Lift | 402.a | MPSB/Sur/1853 | Sur | 2 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Palashbari | 585
P8-WELL-L18 | P8 - 18th Lift | 402.a | MPSB/Str/2287 | Str | 3 | 3 | 2025-09-22 | IPC - 20 | 2.5 | Palashbari | 585
P18-WELL-L18 | P18 - 18th Lift | 402.a | MPSB/Str/2159 | Str | 1 | 3 | 2025-09-06 | IPC - 20 | 2.6 | Palashbari | 586
P18-WELL-L18 | P18 - 18th Lift | 402.a | MPSB/Sur/1777 | Sur | 2 | 3 | 2025-09-06 | IPC - 20 | 2.6 | Palashbari | 586
P18-WELL-L18 | P18 - 18th Lift | 402.a | MPSB/Str/2160 | Str | 3 | 3 | 2025-09-06 | IPC - 20 | 2.6 | Palashbari | 586
P22-WELL-L18 | P22 - 18th Lift | 402.a | MPSB/Str/2593 | Str | 1 | 4 | 2025-10-27 | IPC - 22 | 2 | Sualkuchi | 587
P22-WELL-L18 | P22 - 18th Lift | 402.a | MPSB/Sur/2056 | Sur | 2 | 4 | 2025-10-27 | IPC - 22 | 2 | Sualkuchi | 587
P22-WELL-L18 | P22 - 18th Lift | 402.a | MPSB/Str/2594 | Str | 3 | 4 | 2025-10-27 | IPC - 22 | 2 | Sualkuchi | 587
P22-WELL-L18 | P22 - 18th Lift | 402.a | MPSB/Sur/2072 | Sur | 4 | 4 | 2025-10-30 | IPC - 22 | 2 | Sualkuchi | 587
P28-WELL-L18 | P28 - 18th Lift | 402.a | MPSB/Str/2632 | Str | 1 | 3 | 2025-10-30 | IPC - 22 | 2.5 | Sualkuchi | 588
P28-WELL-L18 | P28 - 18th Lift | 402.a | MPSB/Sur/2070 | Sur | 2 | 3 | 2025-10-30 | IPC - 22 | 2.5 | Sualkuchi | 588
P28-WELL-L18 | P28 - 18th Lift | 402.a | MPSB/Str/2633 | Str | 3 | 3 | 2025-10-30 | IPC - 22 | 2.5 | Sualkuchi | 588
P10-WELL-L18 | P10 - 18th Lift | 402.a | MPSB/Str/2775 | Str | 1 | 3 | 2025-11-12 | IPC - 23 | 2.66 | Sualkuchi | 589
P10-WELL-L18 | P10 - 18th Lift | 402.a | MPSB/Sur/2175 | Sur | 2 | 3 | 2025-11-12 | IPC - 23 | 2.66 | Sualkuchi | 589
P10-WELL-L18 | P10 - 18th Lift | 402.a | MPSB/Str/2776 | Str | 3 | 3 | 2025-11-12 | IPC - 23 | 2.66 | Sualkuchi | 589
P20-WELL-L18 | P20 - 18th Lift | 402.a | MPSB/Str/2962 | Str | 1 | 3 | 2025-11-27 | IPC - 23 | 2.7 | Sualkuchi | 590
P20-WELL-L18 | P20 - 18th Lift | 402.a | MPSB/Sur/2289 | Sur | 2 | 3 | 2025-11-27 | IPC - 23 | 2.7 | Sualkuchi | 590
P20-WELL-L18 | P20 - 18th Lift | 402.a | MPSB/Str/2963 | Str | 3 | 3 | 2025-11-27 | IPC - 23 | 2.7 | Sualkuchi | 590
P25-WELL-L18 | P25 - 18th Lift | 402.a | MPSB/Str/2895 | Str | 1 | 4 | 2025-11-22 | IPC - 23 | 2.5 | Sualkuchi | 591
P25-WELL-L18 | P25 - 18th Lift | 402.a | MPSB/Sur/2250 | Sur | 2 | 4 | 2025-11-22 | IPC - 23 | 2.5 | Sualkuchi | 591
P25-WELL-L18 | P25 - 18th Lift | 402.a | MPSB/Str/2896 | Str | 3 | 4 | 2025-11-22 | IPC - 23 | 2.5 | Sualkuchi | 591
P25-WELL-L18 | P25 - 18th Lift | 402.a | MPSB/Sur/2297 | Sur | 4 | 4 | 2025-11-28 | IPC - 23 | 2.5 | Sualkuchi | 591
P29-WELL-L18 | P29 - 18th Lift | 402.a | MPSB/Str/2972 | Str | 1 | 3 | 2025-11-28 | IPC - 23 | 2.55 | Sualkuchi | 592
P29-WELL-L18 | P29 - 18th Lift | 402.a | MPSB/Sur/2296 | Sur | 2 | 3 | 2025-11-28 | IPC - 23 | 2.55 | Sualkuchi | 592
P29-WELL-L18 | P29 - 18th Lift | 402.a | MPSB/Str/2973 | Str | 3 | 3 | 2025-11-28 | IPC - 23 | 2.55 | Sualkuchi | 592
P7-WELL-L18 | P7 - 18th Lift | 402.a | MPSB/Str/3054 | Str | 1 | 4 | 2025-12-05 | IPC - 25 | 2.5 | Palashbari | 593
P7-WELL-L18 | P7 - 18th Lift | 402.a | MPSB/Sur/2346 | Sur | 2 | 4 | 2025-12-05 | IPC - 25 | 2.5 | Palashbari | 593
P7-WELL-L18 | P7 - 18th Lift | 402.a | MPSB/Str/3055 | Str | 3 | 4 | 2025-12-05 | IPC - 25 | 2.5 | Palashbari | 593
P7-WELL-L18 | P7 - 18th Lift | 402.a | MPSB/Sur/2522 | Sur | 4 | 4 | 2025-12-28 | IPC - 25 | 2.5 | Palashbari | 593
P9-WELL-L18 | P9 - 18th Lift | 402.a | MPSB/Str/3246 | Str | 1 | 3 | 2025-12-24 | IPC - 25 | 2.7 | Palashbari | 594
P9-WELL-L18 | P9 - 18th Lift | 402.a | MPSB/Sur/2481 | Sur | 2 | 3 | 2025-12-24 | IPC - 25 | 2.7 | Palashbari | 594
P9-WELL-L18 | P9 - 18th Lift | 402.a | MPSB/Str/3247 | Str | 3 | 3 | 2025-12-24 | IPC - 25 | 2.7 | Palashbari | 594
P24-WELL-L18 | P24 - 18th Lift | 402.a | MPSB/Str/3300 | Str | 1 | 4 | 2025-12-27 | IPC - 25 | 2.5 | Sualkuchi | 595
P24-WELL-L18 | P24 - 18th Lift | 402.a | MPSB/Sur/2518 | Sur | 2 | 4 | 2025-12-27 | IPC - 25 | 2.5 | Sualkuchi | 595
P24-WELL-L18 | P24 - 18th Lift | 402.a | MPSB/Str/3301 | Str | 3 | 4 | 2025-12-27 | IPC - 25 | 2.5 | Sualkuchi | 595
P24-WELL-L18 | P24 - 18th Lift | 402.a | MPSB/Sur/2577 | Sur | 4 | 4 | 2025-12-31 | IPC - 25 | 2.5 | Sualkuchi | 595
P19-WELL-L18 | P19 - 18th Lift | 402.a | MPSB/Str/3642 | Str | 1 | 4 | 2026-01-24 | IPC - 26 | 2.5 | Sualkuchi | 596
P19-WELL-L18 | P19 - 18th Lift | 402.a | MPSB/Sur/2758 | Sur | 2 | 4 | 2026-01-24 | IPC - 26 | 2.5 | Sualkuchi | 596
P19-WELL-L18 | P19 - 18th Lift | 402.a | MPSB/Str/3643 | Str | 3 | 4 | 2026-01-24 | IPC - 26 | 2.5 | Sualkuchi | 596
P19-WELL-L18 | P19 - 18th Lift | 402.a | MPSB/Sur/2789 | Sur | 4 | 4 | 2026-01-28 | IPC - 26 | 2.5 | Sualkuchi | 596
P23-WELL-L18 | P23 - 18th Lift | 402.a | MPSB/Str/3508 | Str | 1 | 4 | 2026-01-13 | IPC - 26 | 2.5 | Sualkuchi | 597
P23-WELL-L18 | P23 - 18th Lift | 402.a | MPSB/Sur/2666 | Sur | 2 | 4 | 2026-01-13 | IPC - 26 | 2.5 | Sualkuchi | 597
P23-WELL-L18 | P23 - 18th Lift | 402.a | MPSB/Str/3509 | Str | 3 | 4 | 2026-01-13 | IPC - 26 | 2.5 | Sualkuchi | 597
P23-WELL-L18 | P23 - 18th Lift | 402.a | MPSB/Sur/2695 | Sur | 4 | 4 | 2026-01-16 | IPC - 26 | 2.5 | Sualkuchi | 597
P27-WELL-L18 | P27 - 18th Lift | 402.a | MPSB/Str/3695 | Str | 1 | 3 | 2026-01-30 | IPC - 26 | 2.5 | Sualkuchi | 598
P27-WELL-L18 | P27 - 18th Lift | 402.a | MPSB/Sur/2806 | Sur | 2 | 3 | 2026-01-30 | IPC - 26 | 2.5 | Sualkuchi | 598
P27-WELL-L18 | P27 - 18th Lift | 402.a | MPSB/Str/3696 | Str | 3 | 3 | 2026-01-30 | IPC - 26 | 2.5 | Sualkuchi | 598
P17-WELL-L18 | P17 - 18th Lift | 402.a | MPSB/Str/3797 | Str | 1 | 4 | 2026-02-07 | IPC - 27 | 2.5 | Palashbari | 599
P17-WELL-L18 | P17 - 18th Lift | 402.a | MPSB/Sur/2887 | Sur | 2 | 4 | 2026-02-07 | IPC - 27 | 2.5 | Palashbari | 599
P17-WELL-L18 | P17 - 18th Lift | 402.a | MPSB/Str/3798 | Str | 3 | 4 | 2026-02-07 | IPC - 27 | 2.5 | Palashbari | 599
P17-WELL-L18 | P17 - 18th Lift | 402.a | MPSB/Sur/3053 | Sur | 4 | 4 | 2026-02-28 | IPC - 27 | 2.5 | Palashbari | 599 | P17-WELL-L19
P21-WELL-L18 | P21 - 18th Lift | 402.a | MPSB/Str/3855 | Str | 1 | 4 | 2026-02-14 | IPC - 27 | 2.5 | Sualkuchi | 600
P21-WELL-L18 | P21 - 18th Lift | 402.a | MPSB/Sur/2931 | Sur | 2 | 4 | 2026-02-14 | IPC - 27 | 2.5 | Sualkuchi | 600
P21-WELL-L18 | P21 - 18th Lift | 402.a | MPSB/Str/3856 | Str | 3 | 4 | 2026-02-14 | IPC - 27 | 2.5 | Sualkuchi | 600
P21-WELL-L18 | P21 - 18th Lift | 402.a | MPSB/Sur/2999 | Sur | 4 | 4 | 2026-02-25 | IPC - 27 | 2.5 | Sualkuchi | 600
P15-WELL-L18 | P15 - 18th Lift | 402.a | MPSB/Str/4091 | Str | 1 | 3 | 2026-03-12 | IPC - 29 | 2 | Palashbari | 601
P15-WELL-L18 | P15 - 18th Lift | 402.a | MPSB/Sur/3105 | Sur | 2 | 3 | 2026-03-12 | IPC - 29 | 2 | Palashbari | 601
P15-WELL-L18 | P15 - 18th Lift | 402.a | MPSB/Str/4092 | Str | 3 | 3 | 2026-03-12 | IPC - 29 | 2 | Palashbari | 601
P6-WELL-L19 | P6 - 19th Lift | 402.a | MPSB/Str/2321 | Str | 1 | 3 | 2025-09-25 | IPC - 20 | 2.95 | Palashbari | 603
P6-WELL-L19 | P6 - 19th Lift | 402.a | MPSB/Sur/1871 | Sur | 2 | 3 | 2025-09-25 | IPC - 20 | 2.95 | Palashbari | 603
P6-WELL-L19 | P6 - 19th Lift | 402.a | MPSB/Str/2322 | Str | 3 | 3 | 2025-09-25 | IPC - 20 | 2.95 | Palashbari | 603
P8-WELL-L19 | P8 - 19th Lift | 402.a | MPSB/Str/2360 | Str | 1 | 3 | 2025-09-30 | IPC - 20 | 2.5 | Palashbari | 604
P8-WELL-L19 | P8 - 19th Lift | 402.a | MPSB/Sur/1891 | Sur | 2 | 3 | 2025-09-30 | IPC - 20 | 2.5 | Palashbari | 604
P8-WELL-L19 | P8 - 19th Lift | 402.a | MPSB/Str/2361 | Str | 3 | 3 | 2025-09-30 | IPC - 20 | 2.5 | Palashbari | 604
P18-WELL-L19 | P18 - 19th Lift | 402.a | MPSB/Str/2339 | Str | 1 | 3 | 2025-09-29 | IPC - 20 | 2.77 | Palashbari | 605
P18-WELL-L19 | P18 - 19th Lift | 402.a | MPSB/Sur/1885 | Sur | 2 | 3 | 2025-09-29 | IPC - 20 | 2.77 | Palashbari | 605
P18-WELL-L19 | P18 - 19th Lift | 402.a | MPSB/Str/2340 | Str | 3 | 3 | 2025-09-29 | IPC - 20 | 2.77 | Palashbari | 605
P26-WELL-L19 | P26 - 19th Lift | 402.a | MPSB/Str/2154 | Str | 1 | 4 | 2025-09-05 | IPC - 20 | 2.5 | Sualkuchi | 606
P26-WELL-L19 | P26 - 19th Lift | 402.a | MPSB/Sur/1773 | Sur | 2 | 4 | 2025-09-05 | IPC - 20 | 2.5 | Sualkuchi | 606
P26-WELL-L19 | P26 - 19th Lift | 402.a | MPSB/Str/2155 | Str | 3 | 4 | 2025-09-05 | IPC - 20 | 2.5 | Sualkuchi | 606
P26-WELL-L19 | P26 - 19th Lift | 402.a | MPSB/Sur/1815 | Sur | 4 | 4 | 2025-09-12 | IPC - 20 | 2.5 | Sualkuchi | 606
P16-WELL-L19 | P16 - 19th Lift | 402.a | MPSB/Str/2458 | Str | 1 | 3 | 2025-10-13 | IPC - 22 | 2.5 | Palashbari | 607
P16-WELL-L19 | P16 - 19th Lift | 402.a | MPSB/Sur/1971 | Sur | 2 | 3 | 2025-10-13 | IPC - 22 | 2.5 | Palashbari | 607
P16-WELL-L19 | P16 - 19th Lift | 402.a | MPSB/Str/2459 | Str | 3 | 3 | 2025-10-13 | IPC - 22 | 2.5 | Palashbari | 607
P10-WELL-L19 | P10 - 19th Lift | 402.a | MPSB/Str/2979 | Str | 1 | 3 | 2025-11-29 | IPC - 23 | 2.58 | Sualkuchi | 608
P10-WELL-L19 | P10 - 19th Lift | 402.a | MPSB/Sur/2301 | Sur | 2 | 3 | 2025-11-29 | IPC - 23 | 2.58 | Sualkuchi | 608
P10-WELL-L19 | P10 - 19th Lift | 402.a | MPSB/Str/2980 | Str | 3 | 3 | 2025-11-29 | IPC - 23 | 2.58 | Sualkuchi | 608
P22-WELL-L19 | P22 - 19th Lift | 402.a | MPSB/Str/2873 | Str | 1 | 4 | 2025-11-20 | IPC - 23 | 2.5 | Sualkuchi | 609
P22-WELL-L19 | P22 - 19th Lift | 402.a | MPSB/Sur/2240 | Sur | 2 | 4 | 2025-11-20 | IPC - 23 | 2.5 | Sualkuchi | 609
P22-WELL-L19 | P22 - 19th Lift | 402.a | MPSB/Str/2874 | Str | 3 | 4 | 2025-11-20 | IPC - 23 | 2.5 | Sualkuchi | 609
P22-WELL-L19 | P22 - 19th Lift | 402.a | MPSB/Sur/2267 | Sur | 4 | 4 | 2025-11-25 | IPC - 23 | 2.5 | Sualkuchi | 609
P25-WELL-L19 | P25 - 19th Lift | 402.a | MPSB/Str/3001 | Str | 1 | 3 | 2025-11-30 | IPC - 23 | 1.9 | Sualkuchi | 610
P25-WELL-L19 | P25 - 19th Lift | 402.a | MPSB/Sur/2315 | Sur | 2 | 3 | 2025-11-30 | IPC - 23 | 1.9 | Sualkuchi | 610
P25-WELL-L19 | P25 - 19th Lift | 402.a | MPSB/Str/3002 | Str | 3 | 3 | 2025-11-30 | IPC - 23 | 1.9 | Sualkuchi | 610
P28-WELL-L19 | P28 - 19th Lift | 402.a | MPSB/Str/2936 | Str | 1 | 3 | 2025-11-26 | IPC - 23 | 2.5 | Sualkuchi | 611
P28-WELL-L19 | P28 - 19th Lift | 402.a | MPSB/Sur/2277 | Sur | 2 | 3 | 2025-11-26 | IPC - 23 | 2.5 | Sualkuchi | 611
P28-WELL-L19 | P28 - 19th Lift | 402.a | MPSB/Str/2937 | Str | 3 | 3 | 2025-11-26 | IPC - 23 | 2.5 | Sualkuchi | 611
P9-WELL-L19 | P9 - 19th Lift | 402.a | MPSB/Str/3379 | Str | 1 | 3 | 2025-12-31 | IPC - 25 | 2.5 | Palashbari | 612
P9-WELL-L19 | P9 - 19th Lift | 402.a | MPSB/Sur/2571 | Sur | 2 | 3 | 2025-12-31 | IPC - 25 | 2.5 | Palashbari | 612
P9-WELL-L19 | P9 - 19th Lift | 402.a | MPSB/Str/3380 | Str | 3 | 3 | 2025-12-31 | IPC - 25 | 2.5 | Palashbari | 612
P20-WELL-L19 | P20 - 19th Lift | 402.a | MPSB/Str/3175 | Str | 1 | 4 | 2025-12-17 | IPC - 25 | 2.5 | Sualkuchi | 613
P20-WELL-L19 | P20 - 19th Lift | 402.a | MPSB/Sur/2430 | Sur | 2 | 4 | 2025-12-17 | IPC - 25 | 2.5 | Sualkuchi | 613
P20-WELL-L19 | P20 - 19th Lift | 402.a | MPSB/Str/3176 | Str | 3 | 4 | 2025-12-17 | IPC - 25 | 2.5 | Sualkuchi | 613
P20-WELL-L19 | P20 - 19th Lift | 402.a | MPSB/Sur/2485 | Sur | 4 | 4 | 2025-12-24 | IPC - 25 | 2.5 | Sualkuchi | 613
P29-WELL-L19 | P29 - 19th Lift | 402.a | MPSB/Str/3092 | Str | 1 | 3 | 2025-12-09 | IPC - 25 | 3.15 | Sualkuchi | 614
P29-WELL-L19 | P29 - 19th Lift | 402.a | MPSB/Sur/2371 | Sur | 2 | 3 | 2025-12-09 | IPC - 25 | 3.15 | Sualkuchi | 614
P29-WELL-L19 | P29 - 19th Lift | 402.a | MPSB/Str/3123 | Str | 3 | 3 | 2025-12-12 | IPC - 25 | 3.15 | Sualkuchi | 614
P23-WELL-L19 | P23 - 19th Lift | 402.a | MPSB/Str/3591 | Str | 1 | 4 | 2026-01-20 | IPC - 26 | 2.5 | Sualkuchi | 615
P23-WELL-L19 | P23 - 19th Lift | 402.a | MPSB/Sur/2727 | Sur | 2 | 4 | 2026-01-20 | IPC - 26 | 2.5 | Sualkuchi | 615
P23-WELL-L19 | P23 - 19th Lift | 402.a | MPSB/Str/3592 | Str | 3 | 4 | 2026-01-20 | IPC - 26 | 2.5 | Sualkuchi | 615
P23-WELL-L19 | P23 - 19th Lift | 402.a | MPSB/Sur/2770 | Sur | 4 | 4 | 2026-01-25 | IPC - 26 | 2.5 | Sualkuchi | 615
P24-WELL-L19 | P24 - 19th Lift | 402.a | MPSB/Str/3459 | Str | 1 | 4 | 2026-01-08 | IPC - 26 | 2.5 | Sualkuchi | 616
P24-WELL-L19 | P24 - 19th Lift | 402.a | MPSB/Sur/2627 | Sur | 2 | 4 | 2026-01-08 | IPC - 26 | 2.5 | Sualkuchi | 616
P24-WELL-L19 | P24 - 19th Lift | 402.a | MPSB/Str/3460 | Str | 3 | 4 | 2026-01-08 | IPC - 26 | 2.5 | Sualkuchi | 616
P24-WELL-L19 | P24 - 19th Lift | 402.a | MPSB/Sur/2660 | Sur | 4 | 4 | 2026-01-12 | IPC - 26 | 2.5 | Sualkuchi | 616
P7-WELL-L19 | P7 - 19th Lift | 402.a | MPSB/Str/3820 | Str | 1 | 3 | 2026-02-10 | IPC - 27 | 1.55 | Palashbari | 617
P7-WELL-L19 | P7 - 19th Lift | 402.a | MPSB/Sur/2902 | Sur | 2 | 3 | 2026-02-10 | IPC - 27 | 1.55 | Palashbari | 617
P7-WELL-L19 | P7 - 19th Lift | 402.a | MPSB/Str/3821 | Str | 3 | 3 | 2026-02-10 | IPC - 27 | 1.55 | Palashbari | 617
P17-WELL-L19 | P17 - 19th Lift | 402.a | MPSB/Str/3922 | Str | 1 | 4 | 2026-02-21 | IPC - 27 | 2.5 | Palashbari | 618
P17-WELL-L19 | P17 - 19th Lift | 402.a | MPSB/Sur/2974 | Sur | 2 | 4 | 2026-02-21 | IPC - 27 | 2.5 | Palashbari | 618
P17-WELL-L19 | P17 - 19th Lift | 402.a | MPSB/Str/3923 | Str | 3 | 4 | 2026-02-21 | IPC - 27 | 2.5 | Palashbari | 618
P17-WELL-L19 | P17 - 19th Lift | 402.a | MPSB/Sur/3053 | Sur | 4 | 4 | 2026-02-28 | IPC - 27 | 2.5 | Palashbari | 618 | P17-WELL-L18
P19-WELL-L19 | P19 - 19th Lift | 402.a | MPSB/Str/3795 | Str | 1 | 4 | 2026-02-07 | IPC - 27 | 1.85 | Sualkuchi | 619
P19-WELL-L19 | P19 - 19th Lift | 402.a | MPSB/Sur/2886 | Sur | 2 | 4 | 2026-02-07 | IPC - 27 | 1.85 | Sualkuchi | 619
P19-WELL-L19 | P19 - 19th Lift | 402.a | MPSB/Str/3796 | Str | 3 | 4 | 2026-02-07 | IPC - 27 | 1.85 | Sualkuchi | 619
P19-WELL-L19 | P19 - 19th Lift | 402.a | MPSB/Sur/2994 | Sur | 4 | 4 | 2026-02-25 | IPC - 27 | 1.85 | Sualkuchi | 619 | P19-WELL-L20
P21-WELL-L19 | P21 - 19th Lift | 402.a | MPSB/Str/3975 | Str | 1 | 3 | 2026-02-27 | IPC - 27 | 2.5 | Sualkuchi | 620
P21-WELL-L19 | P21 - 19th Lift | 402.a | MPSB/Sur/3017 | Sur | 2 | 3 | 2026-02-27 | IPC - 27 | 2.5 | Sualkuchi | 620
P21-WELL-L19 | P21 - 19th Lift | 402.a | MPSB/Str/3976 | Str | 3 | 3 | 2026-02-27 | IPC - 27 | 2.5 | Sualkuchi | 620
P27-WELL-L19 | P27 - 19th Lift | 402.a | MPSB/Str/3934 | Str | 1 | 3 | 2026-02-24 | IPC - 27 | 1.55 | Sualkuchi | 621
P27-WELL-L19 | P27 - 19th Lift | 402.a | MPSB/Sur/2981 | Sur | 2 | 3 | 2026-02-24 | IPC - 27 | 1.55 | Sualkuchi | 621
P27-WELL-L19 | P27 - 19th Lift | 402.a | MPSB/Str/3935 | Str | 3 | 3 | 2026-02-24 | IPC - 27 | 1.55 | Sualkuchi | 621
P15-WELL-L19 | P15 - 19th Lift | 402.a | MPSB/Str/4442 | Str | 1 | 3 | 2026-04-20 | IPC - 30 | 1.6 | Palashbari | 622
P15-WELL-L19 | P15 - 19th Lift | 402.a | MPSB/Sur/3329 | Sur | 2 | 3 | 2026-04-20 | IPC - 30 | 1.6 | Palashbari | 622
P15-WELL-L19 | P15 - 19th Lift | 402.a | MPSB/Str/4443 | Str | 3 | 3 | 2026-04-20 | IPC - 30 | 1.6 | Palashbari | 622
P8-WELL-L20 | P8 - 20th Lift | 402.a | MPSB/Str/2578 | Str | 1 | 3 | 2025-10-25 | IPC - 22 | 1.42 | Palashbari | 624
P8-WELL-L20 | P8 - 20th Lift | 402.a | MPSB/Sur/2046 | Sur | 2 | 3 | 2025-10-25 | IPC - 22 | 1.42 | Palashbari | 624
P8-WELL-L20 | P8 - 20th Lift | 402.a | MPSB/Str/2579 | Str | 3 | 3 | 2025-10-25 | IPC - 22 | 1.42 | Palashbari | 624
P16-WELL-L20 | P16 - 20th Lift | 402.a | MPSB/Str/2530 | Str | 1 | 3 | 2025-10-20 | IPC - 22 | 0.82 | Palashbari | 625
P16-WELL-L20 | P16 - 20th Lift | 402.a | MPSB/Sur/2016 | Sur | 2 | 3 | 2025-10-20 | IPC - 22 | 0.82 | Palashbari | 625
P16-WELL-L20 | P16 - 20th Lift | 402.a | MPSB/Str/2531 | Str | 3 | 3 | 2025-10-20 | IPC - 22 | 0.82 | Palashbari | 625
P26-WELL-L20 | P26 - 20th Lift | 402.a | MPSB/Str/2435 | Str | 1 | 3 | 2025-10-09 | IPC - 22 | 0.92 | Palashbari | 626
P26-WELL-L20 | P26 - 20th Lift | 402.a | MPSB/Sur/1956 | Sur | 2 | 3 | 2025-10-09 | IPC - 22 | 0.92 | Palashbari | 626
P26-WELL-L20 | P26 - 20th Lift | 402.a | MPSB/Str/2436 | Str | 3 | 3 | 2025-10-09 | IPC - 22 | 0.92 | Palashbari | 626
P22-WELL-L20 | P22 - 20th Lift | 402.a | MPSB/Str/3136 | Str | 1 | 4 | 2025-12-14 | IPC - 25 | 2 | Sualkuchi | 627
P22-WELL-L20 | P22 - 20th Lift | 402.a | MPSB/Sur/2409 | Sur | 2 | 4 | 2025-12-14 | IPC - 25 | 2 | Sualkuchi | 627
P22-WELL-L20 | P22 - 20th Lift | 402.a | MPSB/Str/3137 | Str | 3 | 4 | 2025-12-14 | IPC - 25 | 2 | Sualkuchi | 627
P22-WELL-L20 | P22 - 20th Lift | 402.a | MPSB/Sur/2437 | Sur | 4 | 4 | 2025-12-18 | IPC - 25 | 2 | Sualkuchi | 627
P25-WELL-L20 | P25 - 20th Lift | 402.a | MPSB/Str/3356 | Str | 1 | 3 | 2025-12-30 | IPC - 25 | 1 | Sualkuchi | 628
P25-WELL-L20 | P25 - 20th Lift | 402.a | MPSB/Sur/2556 | Sur | 2 | 3 | 2025-12-30 | IPC - 25 | 1 | Sualkuchi | 628
P25-WELL-L20 | P25 - 20th Lift | 402.a | MPSB/Str/3357 | Str | 3 | 3 | 2025-12-30 | IPC - 25 | 1 | Sualkuchi | 628
P28-WELL-L20 | P28 - 20th Lift | 402.a | MPSB/Str/3179 | Str | 1 | 4 | 2025-12-17 | IPC - 25 | 2.5 | Sualkuchi | 629
P28-WELL-L20 | P28 - 20th Lift | 402.a | MPSB/Sur/2432 | Sur | 2 | 4 | 2025-12-17 | IPC - 25 | 2.5 | Sualkuchi | 629
P28-WELL-L20 | P28 - 20th Lift | 402.a | MPSB/Str/3180 | Str | 3 | 4 | 2025-12-17 | IPC - 25 | 2.5 | Sualkuchi | 629
P28-WELL-L20 | P28 - 20th Lift | 402.a | MPSB/Sur/2476 | Sur | 4 | 4 | 2025-12-23 | IPC - 25 | 2.5 | Sualkuchi | 629
P9-WELL-L20 | P9 - 20th Lift | 402.a | MPSB/Str/3624 | Str | 1 | 3 | 2026-01-23 | IPC - 26 | 1.8 | Palashbari | 630
P9-WELL-L20 | P9 - 20th Lift | 402.a | MPSB/Sur/2750 | Sur | 2 | 3 | 2026-01-23 | IPC - 26 | 1.8 | Palashbari | 630
P9-WELL-L20 | P9 - 20th Lift | 402.a | MPSB/Str/3625 | Str | 3 | 3 | 2026-01-23 | IPC - 26 | 1.8 | Palashbari | 630
P20-WELL-L20 | P20 - 20th Lift | 402.a | MPSB/Str/3613 | Str | 1 | 3 | 2026-01-22 | IPC - 26 | 1.07 | Palashbari | 631
P20-WELL-L20 | P20 - 20th Lift | 402.a | MPSB/Sur/2742 | Sur | 2 | 3 | 2026-01-22 | IPC - 26 | 1.07 | Palashbari | 631
P20-WELL-L20 | P20 - 20th Lift | 402.a | MPSB/Str/3614 | Str | 3 | 3 | 2026-01-22 | IPC - 26 | 1.07 | Palashbari | 631
P23-WELL-L20 | P23 - 20th Lift | 402.a | MPSB/Str/3672 | Str | 1 | 3 | 2026-01-29 | IPC - 26 | 0.35 | Sualkuchi | 632
P23-WELL-L20 | P23 - 20th Lift | 402.a | MPSB/Sur/2795 | Sur | 2 | 3 | 2026-01-29 | IPC - 26 | 0.35 | Sualkuchi | 632
P23-WELL-L20 | P23 - 20th Lift | 402.a | MPSB/Str/3673 | Str | 3 | 3 | 2026-01-29 | IPC - 26 | 0.35 | Sualkuchi | 632
P24-WELL-L20 | P24 - 20th Lift | 402.a | MPSB/Str/3572 | Str | 1 | 4 | 2026-01-19 | IPC - 26 | 2.5 | Sualkuchi | 633
P24-WELL-L20 | P24 - 20th Lift | 402.a | MPSB/Sur/2715 | Sur | 2 | 4 | 2026-01-19 | IPC - 26 | 2.5 | Sualkuchi | 633
P24-WELL-L20 | P24 - 20th Lift | 402.a | MPSB/Str/3573 | Str | 3 | 4 | 2026-01-19 | IPC - 26 | 2.5 | Sualkuchi | 633
P24-WELL-L20 | P24 - 20th Lift | 402.a | MPSB/Sur/2761 | Sur | 4 | 4 | 2026-01-24 | IPC - 26 | 2.5 | Sualkuchi | 633
P19-WELL-L20 | P19 - 20th Lift | 402.a | MPSB/Str/3880 | Str | 1 | 4 | 2026-02-17 | IPC - 27 | 1 | Sualkuchi | 635
P19-WELL-L20 | P19 - 20th Lift | 402.a | MPSB/Sur/2949 | Sur | 2 | 4 | 2026-02-17 | IPC - 27 | 1 | Sualkuchi | 635
P19-WELL-L20 | P19 - 20th Lift | 402.a | MPSB/Str/3881 | Str | 3 | 4 | 2026-02-17 | IPC - 27 | 1 | Sualkuchi | 635
P19-WELL-L20 | P19 - 20th Lift | 402.a | MPSB/Sur/2994 | Sur | 4 | 4 | 2026-02-25 | IPC - 27 | 1 | Sualkuchi | 635 | P19-WELL-L19
P29-WELL-L20 | P29 - 20th Lift | 402.a | MPSB/Str/3746 | Str | 1 | 3 | 2026-02-02 | IPC - 27 | 1 | Sualkuchi | 636
P29-WELL-L20 | P29 - 20th Lift | 402.a | MPSB/Sur/2844 | Sur | 2 | 3 | 2026-02-02 | IPC - 27 | 1 | Sualkuchi | 636
P29-WELL-L20 | P29 - 20th Lift | 402.a | MPSB/Str/3747 | Str | 3 | 3 | 2026-02-02 | IPC - 27 | 1 | Sualkuchi | 636
P21-WELL-L20 | P21 - 20th Lift | 402.a | MPSB/Str/4128 | Str | 1 | 3 | 2026-03-16 | IPC - 29 | 1.85 | Sualkuchi | 637
P21-WELL-L20 | P21 - 20th Lift | 402.a | MPSB/Sur/3131 | Sur | 2 | 3 | 2026-03-16 | IPC - 29 | 1.85 | Sualkuchi | 637
P21-WELL-L20 | P21 - 20th Lift | 402.a | MPSB/Str/4129 | Str | 3 | 3 | 2026-03-16 | IPC - 29 | 1.85 | Sualkuchi | 637
P27-WELL-L20 | P27 - 20th Lift | 402.a | MPSB/Str/4073 | Str | 1 | 3 | 2026-03-09 | IPC - 29 | 1.3 | Sualkuchi | 638
P27-WELL-L20 | P27 - 20th Lift | 402.a | MPSB/Sur/3081 | Sur | 2 | 3 | 2026-03-09 | IPC - 29 | 1.3 | Sualkuchi | 638
P27-WELL-L20 | P27 - 20th Lift | 402.a | MPSB/Str/4074 | Str | 3 | 3 | 2026-03-09 | IPC - 29 | 1.3 | Sualkuchi | 638
P17-WELL-L20 | P17 - 20th Lift | 402.a | MPSB/Str/4475 | Str | 1 | 3 | 2026-04-24 | IPC - 30 | 1.85 | Palashbari | 639
P17-WELL-L20 | P17 - 20th Lift | 402.a | MPSB/Sur/3347 | Sur | 2 | 3 | 2026-04-24 | IPC - 30 | 1.85 | Palashbari | 639
P17-WELL-L20 | P17 - 20th Lift | 402.a | MPSB/Str/4476 | Str | 3 | 3 | 2026-04-24 | IPC - 30 | 1.85 | Palashbari | 639
P15-WELL-L20 | P15 - 20th Lift | 402.a | MPSB/Str/4637 | Str | 1 | 3 | 2026-05-11 | IPC - 31 | 1.09 | Palashbari | 640
P15-WELL-L20 | P15 - 20th Lift | 402.a | MPSB/Sur/3455 | Sur | 2 | 3 | 2026-05-11 | IPC - 31 | 1.09 | Palashbari | 640
P15-WELL-L20 | P15 - 20th Lift | 402.a | MPSB/Str/4638 | Str | 3 | 3 | 2026-05-11 | IPC - 31 | 1.09 | Palashbari | 640
P22-WELL-L21 | P22 - 21st Lift | 402.a | MPSB/Str/3263 | Str | 1 | 3 | 2025-12-24 | IPC - 25 | 0.9 | Sualkuchi | 642
P22-WELL-L21 | P22 - 21st Lift | 402.a | MPSB/Sur/2489 | Sur | 2 | 3 | 2025-12-24 | IPC - 25 | 0.9 | Sualkuchi | 642
P22-WELL-L21 | P22 - 21st Lift | 402.a | MPSB/Str/3283 | Str | 3 | 3 | 2025-12-26 | IPC - 25 | 0.9 | Sualkuchi | 642
P24-WELL-L21 | P24 - 21st Lift | 402.a | MPSB/Str/3709 | Str | 1 | 3 | 2026-01-30 | IPC - 26 | 1.27 | Sualkuchi | 643
P24-WELL-L21 | P24 - 21st Lift | 402.a | MPSB/Sur/2816 | Sur | 2 | 3 | 2026-01-30 | IPC - 26 | 1.27 | Sualkuchi | 643
P24-WELL-L21 | P24 - 21st Lift | 402.a | MPSB/Str/3710 | Str | 3 | 3 | 2026-01-30 | IPC - 26 | 1.27 | Sualkuchi | 643
P28-WELL-L21 | P28 - 21st Lift | 402.a | MPSB/Str/3486 | Str | 1 | 3 | 2026-01-11 | IPC - 26 | 1.27 | Sualkuchi | 644
P28-WELL-L21 | P28 - 21st Lift | 402.a | MPSB/Sur/2648 | Sur | 2 | 3 | 2026-01-11 | IPC - 26 | 1.27 | Sualkuchi | 644
P28-WELL-L21 | P28 - 21st Lift | 402.a | MPSB/Str/3487 | Str | 3 | 3 | 2026-01-11 | IPC - 26 | 1.27 | Sualkuchi | 644
P23-WELL-L21 | P23 - 21st Lift | 402.a | MPSB/Str/3767 | Str | 1 | 4 | 2026-02-05 | IPC - 27 | 1.55 | Sualkuchi | 645
P23-WELL-L21 | P23 - 21st Lift | 402.a | MPSB/Sur/2863 | Sur | 2 | 4 | 2026-02-05 | IPC - 27 | 1.55 | Sualkuchi | 645
P23-WELL-L21 | P23 - 21st Lift | 402.a | MPSB/Str/3768 | Str | 3 | 4 | 2026-02-05 | IPC - 27 | 1.55 | Sualkuchi | 645
P23-WELL-L21 | P23 - 21st Lift | 402.a | MPSB/Sur/3001 | Sur | 4 | 4 | 2026-02-25 | IPC - 27 | 1.55 | Sualkuchi | 645 | P23-WELL-L22
P21-WELL-L21 | P21 - 21st Lift | 402.a | MPSB/Str/4376 | Str | 1 | 3 | 2026-04-11 | IPC - 30 | 1.05 | Palashbari | 646
P21-WELL-L21 | P21 - 21st Lift | 402.a | MPSB/Sur/3279 | Sur | 2 | 3 | 2026-04-11 | IPC - 30 | 1.05 | Palashbari | 646
P21-WELL-L21 | P21 - 21st Lift | 402.a | MPSB/Str/4377 | Str | 3 | 3 | 2026-04-11 | IPC - 30 | 1.05 | Palashbari | 646
P23-WELL-L22 | P23 - 22nd Lift | 402.a | MPSB/Str/3904 | Str | 1 | 4 | 2026-02-20 | IPC - 27 | 1 | Sualkuchi | 648
P23-WELL-L22 | P23 - 22nd Lift | 402.a | MPSB/Sur/2963 | Sur | 2 | 4 | 2026-02-20 | IPC - 27 | 1 | Sualkuchi | 648
P23-WELL-L22 | P23 - 22nd Lift | 402.a | MPSB/Str/3905 | Str | 3 | 4 | 2026-02-20 | IPC - 27 | 1 | Sualkuchi | 648
P23-WELL-L22 | P23 - 22nd Lift | 402.a | MPSB/Sur/3001 | Sur | 4 | 4 | 2026-02-25 | IPC - 27 | 1 | Sualkuchi | 648 | P23-WELL-L21
P26-WELL-PLUG | P26 - Bottom Plugging | 402.b | MPSB/Str/3754 | Str | 1 | 1 | 2026-02-03 | IPC - 27 | 1 | Sualkuchi | 654
P8-WELL-PLUG | P8 - Bottom Plugging | 402.b | MPSB/Str/3781 | Str | 1 | 1 | 2026-02-06 | IPC - 27 | 1 | Palashbari | 655
P22-WELL-PLUG | P22 - Bottom Plugging | 402.b | MPSB/Str/3952 | Str | 1 | 1 | 2026-02-25 | IPC - 27 | 1 | Sualkuchi | 656
P20-WELL-PLUG | P20 - Bottom Plugging | 402.b | MPSB/Str/4164 | Str | 1 | 1 | 2026-03-20 | IPC - 29 | 1 | Sualkuchi | 657
P19-WELL-PLUG | P19 - Bottom Plugging | 402.b | MPSB/Str/4231 | Str | 1 | 1 | 2026-03-28 | IPC - 29 | 1 | Sualkuchi | 658
P25-WELL-PLUG | P25 - Bottom Plugging | 402.b | MPSB/Str/4435 | Str | 1 | 1 | 2026-04-18 | IPC - 30 | 1 | Sualkuchi | 659
P7-WELL-PLUG | P7 - Bottom Plugging | 402.b | MPSB/Str/4565 | Str | 1 | 1 | 2026-04-30 | IPC - 30 | 1 | Palashbari | 660
P29-WELL-PLUG | P29 - Bottom Plugging | 402.b | MPSB/Str/4803 | Str | 1 | 1 | 2026-05-28 | IPC - 31 | 1 | Sualkuchi | 661
P24-WELL-PLUG | P24 - Bottom Plugging | 402.b | MPSB/Str/4975 | Str | 1 | 1 | 2026-06-21 | IPC - 33 | 1 | Sualkuchi | 662
P23-WELL-PLUG | P23 - Bottom Plugging | 402.b | MPSB/Str/5073 | Str | 1 | 1 | 2026-06-30 | IPC - 33 | 1 | Sualkuchi | 663
P26-WELL-CAP | P26 - Well Cap | 402.c | MPSB/Str/3951 | Str | 1 | 1 | 2026-02-25 | IPC - 27 | 1 | Sualkuchi | 669
P8-WELL-CAP | P8 - Well Cap | 402.c | MPSB/Str/4033 | Str | 1 | 2 | 2026-02-28 | IPC - 27 | 1 | Palashbari | 670
P8-WELL-CAP | P8 - Well Cap | 402.c | MPSB/Str/4034 | Str | 2 | 2 | 2026-02-28 | IPC - 27 | 1 | Palashbari | 670
P22-WELL-CAP | P22 - Well Cap | 402.c | MPSB/Sur/3119 | Sur | 1 | 2 | 2026-03-14 | IPC - 29 | 1 | Sualkuchi | 671
P22-WELL-CAP | P22 - Well Cap | 402.c | MPSB/Str/4108 | Str | 2 | 2 | 2026-03-14 | IPC - 29 | 1 | Sualkuchi | 671
P20-WELL-CAP | P20 - Well Cap | 402.c | MPSB/Sur/3195 | Sur | 1 | 2 | 2026-03-29 | IPC - 29 | 1 | Sualkuchi | 672
P20-WELL-CAP | P20 - Well Cap | 402.c | MPSB/Str/4237 | Str | 2 | 2 | 2026-03-29 | IPC - 29 | 1 | Sualkuchi | 672
P19-WELL-CAP | P19 - Well Cap | 402.c | MPSB/Sur/3342 | Sur | 1 | 2 | 2026-04-23 | IPC - 30 | 1 | Sualkuchi | 673
P19-WELL-CAP | P19 - Well Cap | 402.c | MPSB/Str/4470 | Str | 2 | 2 | 2026-04-23 | IPC - 30 | 1 | Sualkuchi | 673
P25-WELL-CAP | P25 - Well Cap | 402.c | MPSB/Sur/3497 | Sur | 1 | 2 | 2026-05-18 | IPC - 31 | 1 | Sualkuchi | 674
P25-WELL-CAP | P25 - Well Cap | 402.c | MPSB/Str/4709 | Str | 2 | 2 | 2026-05-18 | IPC - 31 | 1 | Sualkuchi | 674
P7-WELL-CAP | P7 - Well Cap | 402.c | MPSB/Sur/3584 | Sur | 1 | 2 | 2026-05-31 | IPC - 31 | 1 | Palashbari | 675
P7-WELL-CAP | P7 - Well Cap | 402.c | MPSB/Str/4837 | Str | 2 | 2 | 2026-05-31 | IPC - 31 | 1 | Palashbari | 675
P29-WELL-CAP | P29 - Well Cap | 402.c | MPSB/Sur/3700 | Sur | 1 | 2 | 2026-06-29 | IPC - 33 | 1 | Sualkuchi | 676
P29-WELL-CAP | P29 - Well Cap | 402.c | MPSB/Str/5029 | Str | 2 | 2 | 2026-06-29 | IPC - 33 | 1 | Sualkuchi | 676
P24-WELL-CAP | P24 - Well Cap | 402.c | MPSB/Sur/3801 | Sur | 1 | 2 | 2026-07-29 | IPC - 34 | 1 | Sualkuchi | 677
P24-WELL-CAP | P24 - Well Cap | 402.c | MPSB/Str/5219 | Str | 2 | 2 | 2026-07-29 | IPC - 34 | 1 | Sualkuchi | 677
P19-LPYL-L01 | P19 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4725 | Str | 1 | 3 | 2026-05-19 | IPC - 31 | 4 | Sualkuchi | 683
P19-LPYL-L01 | P19 - Lower Pylon - 1st Lift | 403.a | MPSB/Sur/3510 | Sur | 2 | 3 | 2026-05-19 | IPC - 31 | 4 | Sualkuchi | 683
P19-LPYL-L01 | P19 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4726 | Str | 3 | 3 | 2026-05-19 | IPC - 31 | 4 | Sualkuchi | 683
P19-LPYL-L00 | P19 - Lower Pylon - Starter | 403.a | MPSB/Str/4588 | Str | 1 | 3 | 2026-05-06 | IPC - 31 | 0.63 | Sualkuchi | 684
P19-LPYL-L00 | P19 - Lower Pylon - Starter | 403.a | MPSB/Sur/3421 | Sur | 2 | 3 | 2026-05-06 | IPC - 31 | 0.63 | Sualkuchi | 684
P19-LPYL-L00 | P19 - Lower Pylon - Starter | 403.a | MPSB/Str/4589 | Str | 3 | 3 | 2026-05-06 | IPC - 31 | 0.63 | Sualkuchi | 684
P20-LPYL-L01 | P20 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4754 | Str | 1 | 3 | 2026-05-22 | IPC - 31 | 4 | Sualkuchi | 685
P20-LPYL-L01 | P20 - Lower Pylon - 1st Lift | 403.a | MPSB/Sur/3530 | Sur | 2 | 3 | 2026-05-22 | IPC - 31 | 4 | Sualkuchi | 685
P20-LPYL-L01 | P20 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4755 | Str | 3 | 3 | 2026-05-22 | IPC - 31 | 4 | Sualkuchi | 685
P20-LPYL-L02 | P20 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/4993 | Str | 1 | 3 | 2026-06-23 | IPC - 33 | 2 | Sualkuchi | 686
P20-LPYL-L02 | P20 - Lower Pylon - 2nd Lift | 403.a | MPSB/Sur/3685 | Sur | 2 | 3 | 2026-06-23 | IPC - 33 | 2 | Sualkuchi | 686
P20-LPYL-L02 | P20 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/4994 | Str | 3 | 3 | 2026-06-23 | IPC - 33 | 2 | Sualkuchi | 686
P20-LPYL-L00 | P20 - Lower Pylon - Starter | 403.a | MPSB/Str/4660 | Str | 1 | 3 | 2026-05-12 | IPC - 31 | 0.515 | Sualkuchi | 687
P20-LPYL-L00 | P20 - Lower Pylon - Starter | 403.a | MPSB/Sur/3470 | Sur | 2 | 3 | 2026-05-12 | IPC - 31 | 0.515 | Sualkuchi | 687
P20-LPYL-L00 | P20 - Lower Pylon - Starter | 403.a | MPSB/Str/4661 | Str | 3 | 3 | 2026-05-12 | IPC - 31 | 0.515 | Sualkuchi | 687
P22-LPYL-L01 | P22 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4428 | Str | 1 | 3 | 2026-04-17 | IPC - 30 | 4 | Sualkuchi | 688
P22-LPYL-L01 | P22 - Lower Pylon - 1st Lift | 403.a | MPSB/Sur/3318 | Sur | 2 | 3 | 2026-04-17 | IPC - 30 | 4 | Sualkuchi | 688
P22-LPYL-L01 | P22 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4429 | Str | 3 | 3 | 2026-04-17 | IPC - 30 | 4 | Sualkuchi | 688
P22-LPYL-L02 | P22 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/4678 | Str | 1 | 3 | 2026-05-14 | IPC - 31 | 4 | Sualkuchi | 689
P22-LPYL-L02 | P22 - Lower Pylon - 2nd Lift | 403.a | MPSB/Sur/3479 | Sur | 2 | 3 | 2026-05-14 | IPC - 31 | 4 | Sualkuchi | 689
P22-LPYL-L02 | P22 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/4679 | Str | 3 | 3 | 2026-05-14 | IPC - 31 | 4 | Sualkuchi | 689
P22-LPYL-L03 | P22 - Lower Pylon - 3rd Lift | 403.a | MPSB/Str/5007 | Str | 1 | 3 | 2026-06-25 | IPC - 33 | 2 | Sualkuchi | 690
P22-LPYL-L03 | P22 - Lower Pylon - 3rd Lift | 403.a | MPSB/Sur/3692 | Sur | 2 | 3 | 2026-06-25 | IPC - 33 | 2 | Sualkuchi | 690
P22-LPYL-L03 | P22 - Lower Pylon - 3rd Lift | 403.a | MPSB/Str/5008 | Str | 3 | 3 | 2026-06-25 | IPC - 33 | 2 | Sualkuchi | 690
P22-LPYL-L00 | P22 - Lower Pylon - Starter | 403.a | MPSB/Str/4332 | Str | 1 | 3 | 2026-04-06 | IPC - 30 | 0.63 | Sualkuchi | 691
P22-LPYL-L00 | P22 - Lower Pylon - Starter | 403.a | MPSB/Sur/3247 | Sur | 2 | 3 | 2026-04-06 | IPC - 30 | 0.63 | Sualkuchi | 691
P22-LPYL-L00 | P22 - Lower Pylon - Starter | 403.a | MPSB/Str/4333 | Str | 3 | 3 | 2026-04-06 | IPC - 30 | 0.63 | Sualkuchi | 691
P25-LPYL-L01 | P25 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/5017 | Str | 1 | 3 | 2026-06-26 | IPC - 33 | 2.115 | Sualkuchi | 692
P25-LPYL-L01 | P25 - Lower Pylon - 1st Lift | 403.a | MPSB/Sur/3693 | Sur | 2 | 3 | 2026-06-26 | IPC - 33 | 2.115 | Sualkuchi | 692
P25-LPYL-L01 | P25 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/5018 | Str | 3 | 3 | 2026-06-26 | IPC - 33 | 2.115 | Sualkuchi | 692
P25-LPYL-L02 | P25 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/5100 | Str | 1 | 3 | 2026-07-09 | IPC - 34 | -3.14 | Sualkuchi | 693
P25-LPYL-L02 | P25 - Lower Pylon - 2nd Lift | 403.a | MPSB/Sur/3733 | Sur | 2 | 3 | 2026-07-09 | IPC - 34 | -3.14 | Sualkuchi | 693
P25-LPYL-L02 | P25 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/5101 | Str | 3 | 3 | 2026-07-09 | IPC - 34 | -3.14 | Sualkuchi | 693
P25-LPYL-L00 | P25 - Lower Pylon - Starter | 403.a | MPSB/Str/4902 | Str | 1 | 3 | 2026-06-14 | IPC - 33 | 0.63 | Sualkuchi | 694
P25-LPYL-L00 | P25 - Lower Pylon - Starter | 403.a | MPSB/Sur/3651 | Sur | 2 | 3 | 2026-06-14 | IPC - 33 | 0.63 | Sualkuchi | 694
P25-LPYL-L00 | P25 - Lower Pylon - Starter | 403.a | MPSB/Str/4903 | Str | 3 | 3 | 2026-06-14 | IPC - 33 | 0.63 | Sualkuchi | 694
P26-LPYL-L01 | P26 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4523 | Str | 1 | 3 | 2026-04-28 | IPC - 30 | 4 | Sualkuchi | 695
P26-LPYL-L01 | P26 - Lower Pylon - 1st Lift | 403.a | MPSB/Sur/3378 | Sur | 2 | 3 | 2026-04-28 | IPC - 30 | 4 | Sualkuchi | 695
P26-LPYL-L01 | P26 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4524 | Str | 3 | 3 | 2026-04-28 | IPC - 30 | 4 | Sualkuchi | 695
P26-LPYL-L02 | P26 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/4741 | Str | 1 | 3 | 2026-05-21 | IPC - 31 | 4 | Sualkuchi | 696
P26-LPYL-L02 | P26 - Lower Pylon - 2nd Lift | 403.a | MPSB/Sur/3526 | Sur | 2 | 3 | 2026-05-21 | IPC - 31 | 4 | Sualkuchi | 696
P26-LPYL-L02 | P26 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/4742 | Str | 3 | 3 | 2026-05-21 | IPC - 31 | 4 | Sualkuchi | 696
P26-LPYL-L03 | P26 - Lower Pylon - 3rd Lift | 403.a | MPSB/Str/4904 | Str | 1 | 3 | 2026-06-15 | IPC - 33 | 2.115 | Sualkuchi | 697
P26-LPYL-L03 | P26 - Lower Pylon - 3rd Lift | 403.a | MPSB/Sur/3652 | Sur | 2 | 3 | 2026-06-15 | IPC - 33 | 2.115 | Sualkuchi | 697
P26-LPYL-L03 | P26 - Lower Pylon - 3rd Lift | 403.a | MPSB/Str/4905 | Str | 3 | 3 | 2026-06-15 | IPC - 33 | 2.115 | Sualkuchi | 697
P26-LPYL-L04 | P26 - Lower Pylon - 4th Lift | 403.a | MPSB/Str/5234 | Str | 1 | 3 | 2026-07-30 | IPC - 34 | 5.38 | Sualkuchi | 698
P26-LPYL-L04 | P26 - Lower Pylon - 4th Lift | 403.a | MPSB/Sur/3806 | Sur | 2 | 3 | 2026-07-30 | IPC - 34 | 5.38 | Sualkuchi | 698
P26-LPYL-L04 | P26 - Lower Pylon - 4th Lift | 403.a | MPSB/Str/5235 | Str | 3 | 3 | 2026-07-30 | IPC - 34 | 5.38 | Sualkuchi | 698
P26-LPYL-L00 | P26 - Lower Pylon - Starter | 403.a | MPSB/Str/4318 | Str | 1 | 3 | 2026-04-04 | IPC - 30 | 0.515 | Sualkuchi | 699
P26-LPYL-L00 | P26 - Lower Pylon - Starter | 403.a | MPSB/Sur/3238 | Sur | 2 | 3 | 2026-04-04 | IPC - 30 | 0.515 | Sualkuchi | 699
P26-LPYL-L00 | P26 - Lower Pylon - Starter | 403.a | MPSB/Str/4319 | Str | 3 | 3 | 2026-04-04 | IPC - 30 | 0.515 | Sualkuchi | 699
P29-LPYL-L01 | P29 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/5175 | Str | 1 | 3 | 2026-07-21 | IPC - 34 | 2.115 | Sualkuchi | 700
P29-LPYL-L01 | P29 - Lower Pylon - 1st Lift | 403.a | MPSB/Sur/3781 | Sur | 2 | 3 | 2026-07-21 | IPC - 34 | 2.115 | Sualkuchi | 700
P29-LPYL-L01 | P29 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/5176 | Str | 3 | 3 | 2026-07-21 | IPC - 34 | 2.115 | Sualkuchi | 700
P29-LPYL-L02 | P29 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/5230 | Str | 1 | 3 | 2026-07-30 | IPC - 34 | 4 | Sualkuchi | 701
P29-LPYL-L02 | P29 - Lower Pylon - 2nd Lift | 403.a | MPSB/Sur/3804 | Sur | 2 | 3 | 2026-07-30 | IPC - 34 | 4 | Sualkuchi | 701
P29-LPYL-L02 | P29 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/5231 | Str | 3 | 3 | 2026-07-30 | IPC - 34 | 4 | Sualkuchi | 701
P29-LPYL-L00 | P29 - Lower Pylon - Starter | 403.a | MPSB/Str/5127 | Str | 1 | 3 | 2026-07-13 | IPC - 34 | 0.63 | Sualkuchi | 702
P29-LPYL-L00 | P29 - Lower Pylon - Starter | 403.a | MPSB/Sur/3752 | Sur | 2 | 3 | 2026-07-12 | IPC - 34 | 0.63 | Sualkuchi | 702
P29-LPYL-L00 | P29 - Lower Pylon - Starter | 403.a | MPSB/Str/5128 | Str | 3 | 3 | 2026-07-13 | IPC - 34 | 0.63 | Sualkuchi | 702
P7-LPYL-L01 | P7 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4927 | Str | 1 | 3 | 2026-06-17 | IPC - 33 | 4 | Palashbari | 703
P7-LPYL-L01 | P7 - Lower Pylon - 1st Lift | 403.a | MPSB/Sur/3675 | Sur | 2 | 3 | 2026-06-21 | IPC - 33 | 4 | Palashbari | 703
P7-LPYL-L01 | P7 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4976 | Str | 3 | 3 | 2026-06-21 | IPC - 33 | 4 | Palashbari | 703
P7-LPYL-L02 | P7 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/5107 | Str | 1 | 3 | 2026-07-09 | IPC - 34 | 2 | Palashbari | 704
P7-LPYL-L02 | P7 - Lower Pylon - 2nd Lift | 403.a | MPSB/Sur/3738 | Sur | 2 | 3 | 2026-07-09 | IPC - 34 | 2 | Palashbari | 704
P7-LPYL-L02 | P7 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/5108 | Str | 3 | 3 | 2026-07-09 | IPC - 34 | 2 | Palashbari | 704
P7-LPYL-L00 | P7 - Lower Pylon - Starter | 403.a | MPSB/Str/4886 | Str | 1 | 3 | 2026-06-10 | IPC - 33 | 0.525 | Palashbari | 705
P7-LPYL-L00 | P7 - Lower Pylon - Starter | 403.a | MPSB/Sur/3625 | Sur | 2 | 3 | 2026-06-10 | IPC - 33 | 0.525 | Palashbari | 705
P7-LPYL-L00 | P7 - Lower Pylon - Starter | 403.a | MPSB/Str/4887 | Str | 3 | 3 | 2026-06-10 | IPC - 33 | 0.525 | Palashbari | 705
P8-LPYL-L01 | P8 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4337 | Str | 1 | 3 | 2026-04-05 | IPC - 30 | 4 | Palashbari | 706
P8-LPYL-L01 | P8 - Lower Pylon - 1st Lift | 403.a | MPSB/Sur/3243 | Sur | 2 | 3 | 2026-04-05 | IPC - 30 | 4 | Palashbari | 706
P8-LPYL-L01 | P8 - Lower Pylon - 1st Lift | 403.a | MPSB/Str/4328 | Str | 3 | 3 | 2026-04-05 | IPC - 30 | 4 | Palashbari | 706
P8-LPYL-L02 | P8 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/4407 | Str | 1 | 3 | 2026-04-15 | IPC - 30 | 2 | Palashbari | 707
P8-LPYL-L02 | P8 - Lower Pylon - 2nd Lift | 403.a | MPSB/Sur/3303 | Sur | 2 | 3 | 2026-04-15 | IPC - 30 | 2 | Palashbari | 707
P8-LPYL-L02 | P8 - Lower Pylon - 2nd Lift | 403.a | MPSB/Str/4408 | Str | 3 | 3 | 2026-04-15 | IPC - 30 | 2 | Palashbari | 707
P8-LPYL-L03 | P8 - Lower Pylon - 3rd Lift | 403.a | MPSB/Str/4514 | Str | 1 | 3 | 2026-04-28 | IPC - 30 | 2 | Palashbari | 708
P8-LPYL-L03 | P8 - Lower Pylon - 3rd Lift | 403.a | MPSB/Sur/3370 | Sur | 2 | 3 | 2026-04-28 | IPC - 30 | 2 | Palashbari | 708
P8-LPYL-L03 | P8 - Lower Pylon - 3rd Lift | 403.a | MPSB/Str/4515 | Str | 3 | 3 | 2026-04-28 | IPC - 30 | 2 | Palashbari | 708
P8-LPYL-L04 | P8 - Lower Pylon - 4th Lift | 403.a | MPSB/Str/4690 | Str | 1 | 3 | 2026-05-15 | IPC - 31 | 3.65 | Palashbari | 709
P8-LPYL-L04 | P8 - Lower Pylon - 4th Lift | 403.a | MPSB/Sur/3484 | Sur | 2 | 3 | 2026-05-15 | IPC - 31 | 3.65 | Palashbari | 709
P8-LPYL-L04 | P8 - Lower Pylon - 4th Lift | 403.a | MPSB/Str/4691 | Str | 3 | 3 | 2026-05-15 | IPC - 31 | 3.65 | Palashbari | 709
P8-LPYL-L05 | P8 - Lower Pylon - 5th Lift | 403.a | MPSB/Str/4793 | Str | 1 | 3 | 2026-05-27 | IPC - 31 | 0.67 | Palashbari | 710
P8-LPYL-L05 | P8 - Lower Pylon - 5th Lift | 403.a | MPSB/Sur/3556 | Sur | 2 | 3 | 2026-05-27 | IPC - 31 | 0.67 | Palashbari | 710
P8-LPYL-L05 | P8 - Lower Pylon - 5th Lift | 403.a | MPSB/Str/4794 | Str | 3 | 3 | 2026-05-27 | IPC - 31 | 0.67 | Palashbari | 710
P8-LPYL-L06 | P8 - Lower Pylon - 6th Lift | 403.a | MPSB/Str/4997 | Str | 1 | 3 | 2026-06-24 | IPC - 33 | 4.45 | Palashbari | 711
P8-LPYL-L06 | P8 - Lower Pylon - 6th Lift | 403.a | MPSB/Sur/3689 | Sur | 2 | 3 | 2026-06-24 | IPC - 33 | 4.45 | Palashbari | 711
P8-LPYL-L06 | P8 - Lower Pylon - 6th Lift | 403.a | MPSB/Str/4998 | Str | 3 | 3 | 2026-06-24 | IPC - 33 | 4.45 | Palashbari | 711
P8-LPYL-L07 | P8 - Lower Pylon - 7th Lift | 403.a | MPSB/Str/5150 | Str | 1 | 3 | 2026-07-15 | IPC - 34 | 4.329 | Palashbari | 712
P8-LPYL-L07 | P8 - Lower Pylon - 7th Lift | 403.a | MPSB/Sur/3767 | Sur | 2 | 3 | 2026-07-15 | IPC - 34 | 4.329 | Palashbari | 712
P8-LPYL-L07 | P8 - Lower Pylon - 7th Lift | 403.a | MPSB/Str/5151 | Str | 3 | 3 | 2026-07-15 | IPC - 34 | 4.329 | Palashbari | 712
P8-LPYL-L00 | P8 - Lower Pylon - Starter | 403.a | MPSB/Str/4310 | Str | 1 | 3 | 2026-04-01 | IPC - 30 | 0.525 | Palashbari | 713
P8-LPYL-L00 | P8 - Lower Pylon - Starter | 403.a | MPSB/Sur/3233 | Sur | 2 | 3 | 2026-04-01 | IPC - 30 | 0.525 | Palashbari | 713
P8-LPYL-L00 | P8 - Lower Pylon - Starter | 403.a | MPSB/Str/4311 | Str | 3 | 3 | 2026-04-01 | IPC - 30 | 0.525 | Palashbari | 713
P17-BP-S09a-O | P17-BP-S09a-O© | 406.a/407.c/408.c | MPSB/MB/19 | Mb | 1 | 3 | 2025-06-16 | IPC - 18 | 1 | Palashbari | 721
P17-BP-S09a-O | P17-BP-S09a-O© | 406.a/407.c/408.c | MPSB/Sur/1429 | Sur | 2 | 3 | 2025-06-16 | IPC - 18 | 1 | Palashbari | 721
P17-BP-S09a-O | P17-BP-S09a-O© | 406.a/407.c/408.c | MPSB/MB/20 | Mb | 3 | 3 | 2025-06-16 | IPC - 18 | 1 | Palashbari | 721
P17-BP-S10a-O | P17-BP-S10a-O | 406.a/407.c | MPSB/MB/22 | Mb | 1 | 2 | 2025-06-21 | IPC - 18 | 1 | Palashbari | 722
P17-BP-S10a-O | P17-BP-S10a-O | 406.a/407.c | MPSB/MB/25 | Mb | 2 | 2 | 2025-06-25 | IPC - 18 | 1 | Palashbari | 722
P17-BP-S11a-O | P17-BP-S11a-O© | 406.a/407.c/408.c | MPSB/Sur/1482 | Sur | 1 | 2 | 2025-07-02 | IPC - 18 | 1 | Palashbari | 723
P17-BP-S11a-O | P17-BP-S11a-O© | 406.a/407.c/408.c | MPSB/MB/0031 | Mb | 2 | 2 | 2025-07-02 | IPC - 18 | 1 | Palashbari | 723
P17-BP-S12a-O | P17-BP-S12a-O | 406.a/407.c | MPSB/MB/034 | Mb | 1 | 3 | 2025-07-07 | IPC - 18 | 1 | Palashbari | 724
P17-BP-S12a-O | P17-BP-S12a-O | 406.a/407.c | MPSB/Sur/1506 | Sur | 2 | 3 | 2025-07-09 | IPC - 18 | 1 | Palashbari | 724
P17-BP-S12a-O | P17-BP-S12a-O | 406.a/407.c | MPSB/MB/038 | Mb | 3 | 3 | 2025-07-09 | IPC - 18 | 1 | Palashbari | 724
P17-BP-S13a-O | P17-BP-S13a-O© | 406.a/407.c/408.c | MPSB/MB/040 | Mb | 1 | 3 | 2025-07-11 | IPC - 18 | 1 | Palashbari | 725
P17-BP-S13a-O | P17-BP-S13a-O© | 406.a/407.c/408.c | MPSB/Sur/1527 | Sur | 2 | 3 | 2025-07-15 | IPC - 18 | 1 | Palashbari | 725
P17-BP-S13a-O | P17-BP-S13a-O© | 406.a/407.c/408.c | MPSB/MB/042 | Mb | 3 | 3 | 2025-07-15 | IPC - 18 | 1 | Palashbari | 725
P17-BP-S14a-O | P17-BP-S14a-O | 406.a/407.c | MPSB/MB/046 | Mb | 1 | 3 | 2025-07-17 | IPC - 18 | 1 | Palashbari | 726
P17-BP-S14a-O | P17-BP-S14a-O | 406.a/407.c | MPSB/Sur/1558 | Sur | 2 | 3 | 2025-07-21 | IPC - 18 | 1 | Palashbari | 726
P17-BP-S14a-O | P17-BP-S14a-O | 406.a/407.c | MPSB/MB/049 | Mb | 3 | 3 | 2025-07-21 | IPC - 18 | 1 | Palashbari | 726
P17-BP-S15a-O | P17-BP-S15a-O© | 406.a/407.c/408.c | MPSB/MB/054 | Mb | 1 | 3 | 2025-07-25 | IPC - 18 | 1 | Palashbari | 727
P17-BP-S15a-O | P17-BP-S15a-O© | 406.a/407.c/408.c | MPSB/Sur/1589 | Sur | 2 | 3 | 2025-07-26 | IPC - 18 | 1 | Palashbari | 727
P17-BP-S15a-O | P17-BP-S15a-O© | 406.a/407.c/408.c | MPSB/MB/057 | Mb | 3 | 3 | 2025-07-28 | IPC - 18 | 1 | Palashbari | 727
P25-KS-S09-O | P25-KS-S09-O© | 406.a/407.c/408.c | MPSB/MB/033 | Mb | 1 | 3 | 2025-07-03 | IPC - 18 | 1 | Sualkuchi | 728
P25-KS-S09-O | P25-KS-S09-O© | 406.a/407.c/408.c | MPSB/Sur/1508 | Sur | 2 | 3 | 2025-07-10 | IPC - 18 | 1 | Sualkuchi | 728
P25-KS-S09-O | P25-KS-S09-O© | 406.a/407.c/408.c | MPSB/MB/039 | Mb | 3 | 3 | 2025-07-10 | IPC - 18 | 1 | Sualkuchi | 728
P25-KS-S10-O | P25-KS-S10-O | 406.a/407.c | MPSB/MB/044 | Mb | 1 | 3 | 2025-07-16 | IPC - 18 | 1 | Sualkuchi | 729
P25-KS-S10-O | P25-KS-S10-O | 406.a/407.c | MPSB/Sur/1546 | Sur | 2 | 3 | 2025-07-19 | IPC - 18 | 1 | Sualkuchi | 729
P25-KS-S10-O | P25-KS-S10-O | 406.a/407.c | MPSB/MB/047 | Mb | 3 | 3 | 2025-07-19 | IPC - 18 | 1 | Sualkuchi | 729
P25-KS-S11-O | P25-KS-S11-O© | 406.a/407.c/408.c | MPSB/MB/037 | Mb | 1 | 3 | 2025-07-08 | IPC - 18 | 1 | Sualkuchi | 730
P25-KS-S11-O | P25-KS-S11-O© | 406.a/407.c/408.c | MPSB/Sur/1603 | Sur | 2 | 3 | 2025-07-29 | IPC - 18 | 1 | Sualkuchi | 730
P25-KS-S11-O | P25-KS-S11-O© | 406.a/407.c/408.c | MPSB/MB/059 | Mb | 3 | 3 | 2025-07-29 | IPC - 18 | 1 | Sualkuchi | 730
P17-BP-S16a-O | P17-BP-S16a-O | 406.a/407.c | MPSB/MB/60 | Mb | 1 | 3 | 2025-07-30 | IPC - 19 | 1 | Palashbari | 731
P17-BP-S16a-O | P17-BP-S16a-O | 406.a/407.c | MPSB/Sur/1636 | Sur | 2 | 3 | 2025-08-01 | IPC - 19 | 1 | Palashbari | 731
P17-BP-S16a-O | P17-BP-S16a-O | 406.a/407.c | MPSB/MB/65 | Mb | 3 | 3 | 2025-08-01 | IPC - 19 | 1 | Palashbari | 731
P17-BP-S17a-O | P17-BP-S17a-O© | 406.a/407.c/408.c | MPSB/MB/69 | Mb | 1 | 3 | 2025-08-04 | IPC - 19 | 1 | Palashbari | 732
P17-BP-S17a-O | P17-BP-S17a-O© | 406.a/407.c/408.c | MPSB/Sur/1657 | Sur | 2 | 3 | 2025-08-07 | IPC - 19 | 1 | Palashbari | 732
P17-BP-S17a-O | P17-BP-S17a-O© | 406.a/407.c/408.c | MPSB/MB/74 | Mb | 3 | 3 | 2025-08-07 | IPC - 19 | 1 | Palashbari | 732
P17-BP-S18a-O | P17-BP-S18a-O | 406.a/407.c | MPSB/MB/75 | Mb | 1 | 3 | 2025-08-07 | IPC - 19 | 1 | Palashbari | 733
P17-BP-S18a-O | P17-BP-S18a-O | 406.a/407.c | MPSB/Sur/1685 | Sur | 2 | 3 | 2025-08-12 | IPC - 19 | 1 | Palashbari | 733
P17-BP-S18a-O | P17-BP-S18a-O | 406.a/407.c | MPSB/MB/83 | Mb | 3 | 3 | 2025-08-12 | IPC - 19 | 1 | Palashbari | 733
P17-BP-S19a-O | P17-BP-S19a-O© | 406.a/407.c/408.c | MPSB/MB/84 | Mb | 1 | 3 | 2025-08-12 | IPC - 19 | 1 | Palashbari | 734
P17-BP-S19a-O | P17-BP-S19a-O© | 406.a/407.c/408.c | MPSB/Sur/1698 | Sur | 2 | 3 | 2025-08-18 | IPC - 19 | 1 | Palashbari | 734
P17-BP-S19a-O | P17-BP-S19a-O© | 406.a/407.c/408.c | MPSB/MB/93 | Mb | 3 | 3 | 2025-08-18 | IPC - 19 | 1 | Palashbari | 734
P17-BP-S20a-O | P17-BP-S20a-O | 406.a/407.c | MPSB/Sur/1727 | Sur | 1 | 2 | 2025-08-24 | IPC - 19 | 1 | Palashbari | 735
P17-BP-S20a-O | P17-BP-S20a-O | 406.a/407.c | MPSB/MB/107 | Mb | 2 | 2 | 2025-08-24 | IPC - 19 | 1 | Palashbari | 735
P17-BP-S21a-O | P17-BP-S21a-O© | 406.a/407.c/408.c | MPSB/MB/119 | Mb | 1 | 3 | 2025-08-29 | IPC - 19 | 1 | Palashbari | 736
P17-BP-S21a-O | P17-BP-S21a-O© | 406.a/407.c/408.c | MPSB/Sur/1752 | Sur | 2 | 3 | 2025-08-30 | IPC - 19 | 1 | Palashbari | 736
P17-BP-S21a-O | P17-BP-S21a-O© | 406.a/407.c/408.c | MPSB/MB/122 | Mb | 3 | 3 | 2025-08-30 | IPC - 19 | 1 | Palashbari | 736
P17-BP-S22a-O | P17-BP-S22a-O | 406.a/407.c | MPSB/MB/92 | Mb | 1 | 3 | 2025-08-18 | IPC - 19 | 1 | Palashbari | 737
P17-BP-S22a-O | P17-BP-S22a-O | 406.a/407.c | MPSB/Sur/1714 | Sur | 2 | 3 | 2025-08-21 | IPC - 19 | 1 | Palashbari | 737
P17-BP-S22a-O | P17-BP-S22a-O | 406.a/407.c | MPSB/MB/104 | Mb | 3 | 3 | 2025-08-21 | IPC - 19 | 1 | Palashbari | 737
P17-BP-S23a-O | P17-BP-S23a-O© | 406.a/407.c/408.c | MPSB/MB/110 | Mb | 1 | 3 | 2025-08-26 | IPC - 19 | 1 | Palashbari | 738
P17-BP-S23a-O | P17-BP-S23a-O© | 406.a/407.c/408.c | MPSB/Sur/1741 | Sur | 2 | 3 | 2025-08-28 | IPC - 19 | 1 | Palashbari | 738
P17-BP-S23a-O | P17-BP-S23a-O© | 406.a/407.c/408.c | MPSB/MB/116 | Mb | 3 | 3 | 2025-08-28 | IPC - 19 | 1 | Palashbari | 738
P17-KS-S09-O | P17-KS-S09-O© | 406.a/407.c/408.c | MPSB/MB/58 | Mb | 1 | 3 | 2025-07-29 | IPC - 19 | 1 | Palashbari | 739
P17-KS-S09-O | P17-KS-S09-O© | 406.a/407.c/408.c | MPSB/Sur/1645 | Sur | 2 | 3 | 2025-08-04 | IPC - 19 | 1 | Palashbari | 739
P17-KS-S09-O | P17-KS-S09-O© | 406.a/407.c/408.c | MPSB/MB/68 | Mb | 3 | 3 | 2025-08-04 | IPC - 19 | 1 | Palashbari | 739
P17-KS-S10-O | P17-KS-S10-O | 406.a/407.c | MPSB/MB/76 | Mb | 1 | 3 | 2025-08-07 | IPC - 19 | 1 | Palashbari | 740
P17-KS-S10-O | P17-KS-S10-O | 406.a/407.c | MPSB/Sur/1681 | Sur | 2 | 3 | 2025-08-11 | IPC - 19 | 1 | Palashbari | 740
P17-KS-S10-O | P17-KS-S10-O | 406.a/407.c | MPSB/MB/80 | Mb | 3 | 3 | 2025-08-11 | IPC - 19 | 1 | Palashbari | 740
P17-KS-S11-O | P17-KS-S11-O© | 406.a/407.c/408.c | MPSB/MB/86 | Mb | 1 | 3 | 2025-08-12 | IPC - 19 | 1 | Palashbari | 741
P17-KS-S11-O | P17-KS-S11-O© | 406.a/407.c/408.c | MPSB/Sur/1696 | Sur | 2 | 3 | 2025-08-16 | IPC - 19 | 1 | Palashbari | 741
P17-KS-S11-O | P17-KS-S11-O© | 406.a/407.c/408.c | MPSB/MB/90 | Mb | 3 | 3 | 2025-08-16 | IPC - 19 | 1 | Palashbari | 741
P17-KS-S12-O | P17-KS-S12-O | 406.a/407.c | MPSB/MB/95 | Mb | 1 | 3 | 2025-08-18 | IPC - 19 | 1 | Palashbari | 742
P17-KS-S12-O | P17-KS-S12-O | 406.a/407.c | MPSB/Sur/1713 | Sur | 2 | 3 | 2025-08-21 | IPC - 19 | 1 | Palashbari | 742
P17-KS-S12-O | P17-KS-S12-O | 406.a/407.c | MPSB/MB/103 | Mb | 3 | 3 | 2025-08-21 | IPC - 19 | 1 | Palashbari | 742
P17-KS-S13-O | P17-KS-S13-O© | 406.a/407.c/408.c | MPSB/MB/108 | Mb | 1 | 3 | 2025-08-24 | IPC - 19 | 1 | Palashbari | 743
P17-KS-S13-O | P17-KS-S13-O© | 406.a/407.c/408.c | MPSB/Sur/1736 | Sur | 2 | 3 | 2025-08-27 | IPC - 19 | 1 | Palashbari | 743
P17-KS-S13-O | P17-KS-S13-O© | 406.a/407.c/408.c | MPSB/MB/112 | Mb | 3 | 3 | 2025-08-27 | IPC - 19 | 1 | Palashbari | 743
P17-KS-S14-O | P17-KS-S14-O | 406.a/407.c | MPSB/MB/114 | Mb | 1 | 3 | 2025-08-27 | IPC - 19 | 1 | Palashbari | 744
P17-KS-S14-O | P17-KS-S14-O | 406.a/407.c | MPSB/Sur/1753 | Sur | 2 | 3 | 2025-08-30 | IPC - 19 | 1 | Palashbari | 744
P17-KS-S14-O | P17-KS-S14-O | 406.a/407.c | MPSB/MB/123 | Mb | 3 | 3 | 2025-08-30 | IPC - 19 | 1 | Palashbari | 744
P25-KS-S12-O | P25-KS-S12-O | 406.a/407.c | MPSB/MB/63 | Mb | 1 | 3 | 2025-08-01 | IPC - 19 | 1 | Sualkuchi | 745
P25-KS-S12-O | P25-KS-S12-O | 406.a/407.c | MPSB/Sur/1644 | Sur | 2 | 3 | 2025-08-04 | IPC - 19 | 1 | Sualkuchi | 745
P25-KS-S12-O | P25-KS-S12-O | 406.a/407.c | MPSB/MB/67 | Mb | 3 | 3 | 2025-08-04 | IPC - 19 | 1 | Sualkuchi | 745
P25-KS-S13-O | P25-KS-S13-O© | 406.a/407.c/408.c | MPSB/MB/72 | Mb | 1 | 3 | 2025-08-07 | IPC - 19 | 1 | Sualkuchi | 746
P25-KS-S13-O | P25-KS-S13-O© | 406.a/407.c/408.c | MPSB/Sur/1667 | Sur | 2 | 3 | 2025-08-09 | IPC - 19 | 1 | Sualkuchi | 746
P25-KS-S13-O | P25-KS-S13-O© | 406.a/407.c/408.c | MPSB/MB/78 | Mb | 3 | 3 | 2025-08-09 | IPC - 19 | 1 | Sualkuchi | 746
P25-KS-S14-O | P25-KS-S14-O | 406.a/407.c | MPSB/MB/85 | Mb | 1 | 3 | 2025-08-12 | IPC - 19 | 1 | Sualkuchi | 747
P25-KS-S14-O | P25-KS-S14-O | 406.a/407.c | MPSB/Sur/1695 | Sur | 2 | 3 | 2025-08-16 | IPC - 19 | 1 | Sualkuchi | 747
P25-KS-S14-O | P25-KS-S14-O | 406.a/407.c | MPSB/MB/89 | Mb | 3 | 3 | 2025-08-16 | IPC - 19 | 1 | Sualkuchi | 747
P25-KS-S15-O | P25-KS-S15-O© | 406.a/407.c/408.c | MPSB/MB/96 | Mb | 1 | 3 | 2025-08-18 | IPC - 19 | 1 | Sualkuchi | 748
P25-KS-S15-O | P25-KS-S15-O© | 406.a/407.c/408.c | MPSB/Sur/1712 | Sur | 2 | 3 | 2025-08-21 | IPC - 19 | 1 | Sualkuchi | 748
P25-KS-S15-O | P25-KS-S15-O© | 406.a/407.c/408.c | MPSB/MB/101 | Mb | 3 | 3 | 2025-08-21 | IPC - 19 | 1 | Sualkuchi | 748
P25-KS-S16-O | P25-KS-S16-O | 406.a/407.c | MPSB/MB/100 | Mb | 1 | 3 | 2025-08-21 | IPC - 19 | 1 | Sualkuchi | 749
P25-KS-S16-O | P25-KS-S16-O | 406.a/407.c | MPSB/Sur/1730 | Sur | 2 | 3 | 2025-08-25 | IPC - 19 | 1 | Sualkuchi | 749
P25-KS-S16-O | P25-KS-S16-O | 406.a/407.c | MPSB/MB/109 | Mb | 3 | 3 | 2025-08-25 | IPC - 19 | 1 | Sualkuchi | 749
P17-BP-S24a-O | P17-BP-S24a-O | 406.a/407.c | MPSB/MB/121 | Mb | 1 | 3 | 2025-08-30 | IPC - 20 | 1 | Palashbari | 750
P17-BP-S24a-O | P17-BP-S24a-O | 406.a/407.c | MPSB/Sur/1759 | Sur | 2 | 3 | 2025-09-01 | IPC - 20 | 1 | Palashbari | 750
P17-BP-S24a-O | P17-BP-S24a-O | 406.a/407.c | MPSB/MB/127 | Mb | 3 | 3 | 2025-09-01 | IPC - 20 | 1 | Palashbari | 750
P17-BP-S25a-O | P17-BP-S25a-O© | 406.a/407.c/408.c | MPSB/MB/134 | Mb | 1 | 3 | 2025-09-04 | IPC - 20 | 1 | Palashbari | 751
P17-BP-S25a-O | P17-BP-S25a-O© | 406.a/407.c/408.c | MPSB/Sur/1778 | Sur | 2 | 3 | 2025-09-06 | IPC - 20 | 1 | Palashbari | 751
P17-BP-S25a-O | P17-BP-S25a-O© | 406.a/407.c/408.c | MPSB/MB/138 | Mb | 3 | 3 | 2025-09-06 | IPC - 20 | 1 | Palashbari | 751
P17-BP-S26a-O | P17-BP-S26a-O | 406.a/407.c | MPSB/MB/141 | Mb | 1 | 3 | 2025-09-08 | IPC - 20 | 1 | Palashbari | 752
P17-BP-S26a-O | P17-BP-S26a-O | 406.a/407.c | MPSB/Sur/1800 | Sur | 2 | 3 | 2025-09-09 | IPC - 20 | 1 | Palashbari | 752
P17-BP-S26a-O | P17-BP-S26a-O | 406.a/407.c | MPSB/MB/144 | Mb | 3 | 3 | 2025-09-09 | IPC - 20 | 1 | Palashbari | 752
P17-BP-S27a-O | P17-BP-S27a-O© | 406.a/407.c/408.c | MPSB/MB/151 | Mb | 1 | 3 | 2025-09-11 | IPC - 20 | 1 | Palashbari | 753
P17-BP-S27a-O | P17-BP-S27a-O© | 406.a/407.c/408.c | MPSB/Sur/1818 | Sur | 2 | 3 | 2025-09-13 | IPC - 20 | 1 | Palashbari | 753
P17-BP-S27a-O | P17-BP-S27a-O© | 406.a/407.c/408.c | MPSB/MB/157 | Mb | 3 | 3 | 2025-09-13 | IPC - 20 | 1 | Palashbari | 753
P17-BP-S28a-O | P17-BP-S28a-O | 406.a/407.c | MPSB/MB/166 | Mb | 1 | 3 | 2025-09-15 | IPC - 20 | 1 | Palashbari | 754
P17-BP-S28a-O | P17-BP-S28a-O | 406.a/407.c | MPSB/Sur/1833 | Sur | 2 | 3 | 2025-09-18 | IPC - 20 | 1 | Palashbari | 754
P17-BP-S28a-O | P17-BP-S28a-O | 406.a/407.c | MPSB/MB/177 | Mb | 3 | 3 | 2025-09-18 | IPC - 20 | 1 | Palashbari | 754
P17-BP-S29a-O | P17-BP-S29a-O© | 406.a/407.c/408.c | MPSB/MB/182 | Mb | 1 | 3 | 2025-09-19 | IPC - 20 | 1 | Palashbari | 755
P17-BP-S29a-O | P17-BP-S29a-O© | 406.a/407.c/408.c | MPSB/Sur/1861 | Sur | 2 | 3 | 2025-09-23 | IPC - 20 | 1 | Palashbari | 755
P17-BP-S29a-O | P17-BP-S29a-O© | 406.a/407.c/408.c | MPSB/MB/192 | Mb | 3 | 3 | 2025-09-23 | IPC - 20 | 1 | Palashbari | 755
P17-BP-S30a-O | P17-BP-S30a-O | 406.a/407.c | MPSB/MB/200 | Mb | 1 | 3 | 2025-09-25 | IPC - 20 | 1 | Palashbari | 756
P17-BP-S30a-O | P17-BP-S30a-O | 406.a/407.c | MPSB/Sur/1882 | Sur | 2 | 3 | 2025-09-27 | IPC - 20 | 1 | Palashbari | 756
P17-BP-S30a-O | P17-BP-S30a-O | 406.a/407.c | MPSB/MB/207 | Mb | 3 | 3 | 2025-09-27 | IPC - 20 | 1 | Palashbari | 756
P17-BP-S31a-O | P17-BP-S31a-O© | 406.a/407.c/408.c | MPSB/Str/2345 | Str | 1 | 3 | 2025-09-29 | IPC - 20 | 1 | Palashbari | 757
P17-BP-S31a-O | P17-BP-S31a-O© | 406.a/407.c/408.c | MPSB/Sur/1897 | Sur | 2 | 3 | 2025-09-30 | IPC - 20 | 1 | Palashbari | 757
P17-BP-S31a-O | P17-BP-S31a-O© | 406.a/407.c/408.c | MPSB/MB/213 | Mb | 3 | 3 | 2025-09-30 | IPC - 20 | 1 | Palashbari | 757
P17-KS-S15-O | P17-KS-S15-O© | 406.a/407.c/408.c | MPSB/MB/128 | Mb | 1 | 3 | 2025-09-01 | IPC - 20 | 1 | Palashbari | 758
P17-KS-S15-O | P17-KS-S15-O© | 406.a/407.c/408.c | MPSB/Sur/1769 | Sur | 2 | 3 | 2025-09-04 | IPC - 20 | 1 | Palashbari | 758
P17-KS-S15-O | P17-KS-S15-O© | 406.a/407.c/408.c | MPSB/MB/135 | Mb | 3 | 3 | 2025-09-04 | IPC - 20 | 1 | Palashbari | 758
P17-KS-S16-O | P17-KS-S16-O | 406.a/407.c | MPSB/MB/137 | Mb | 1 | 3 | 2025-09-06 | IPC - 20 | 1 | Palashbari | 759
P17-KS-S16-O | P17-KS-S16-O | 406.a/407.c | MPSB/Sur/1794 | Sur | 2 | 3 | 2025-09-08 | IPC - 20 | 1 | Palashbari | 759
P17-KS-S16-O | P17-KS-S16-O | 406.a/407.c | MPSB/MB/142 | Mb | 3 | 3 | 2025-09-08 | IPC - 20 | 1 | Palashbari | 759
P17-KS-S17-O | P17-KS-S17-O© | 406.a/407.c/408.c | MPSB/MB/152 | Mb | 1 | 3 | 2025-09-11 | IPC - 20 | 1 | Palashbari | 760
P17-KS-S17-O | P17-KS-S17-O© | 406.a/407.c/408.c | MPSB/Sur/1816 | Sur | 2 | 3 | 2025-09-12 | IPC - 20 | 1 | Palashbari | 760
P17-KS-S17-O | P17-KS-S17-O© | 406.a/407.c/408.c | MPSB/MB/154 | Mb | 3 | 3 | 2025-09-12 | IPC - 20 | 1 | Palashbari | 760
P17-KS-S18-O | P17-KS-S18-O | 406.a/407.c | MPSB/MB/162 | Mb | 1 | 3 | 2025-09-13 | IPC - 20 | 1 | Palashbari | 761
P17-KS-S18-O | P17-KS-S18-O | 406.a/407.c | MPSB/Sur/1834 | Sur | 2 | 3 | 2025-09-18 | IPC - 20 | 1 | Palashbari | 761
P17-KS-S18-O | P17-KS-S18-O | 406.a/407.c | MPSB/MB/178 | Mb | 3 | 3 | 2025-09-18 | IPC - 20 | 1 | Palashbari | 761
P17-KS-S19-O | P17-KS-S19-O© | 406.a/407.c/408.c | MPSB/MB/185 | Mb | 1 | 3 | 2025-09-20 | IPC - 20 | 1 | Palashbari | 762
P17-KS-S19-O | P17-KS-S19-O© | 406.a/407.c/408.c | MPSB/Sur/1859 | Sur | 2 | 3 | 2025-09-22 | IPC - 20 | 1 | Palashbari | 762
P17-KS-S19-O | P17-KS-S19-O© | 406.a/407.c/408.c | MPSB/MB/188 | Mb | 3 | 3 | 2025-09-22 | IPC - 20 | 1 | Palashbari | 762
P17-KS-S20-O | P17-KS-S20-O | 406.a/407.c | MPSB/MB/196 | Mb | 1 | 3 | 2025-09-24 | IPC - 20 | 1 | Palashbari | 763
P17-KS-S20-O | P17-KS-S20-O | 406.a/407.c | MPSB/Sur/1878 | Sur | 2 | 3 | 2025-09-27 | IPC - 20 | 1 | Palashbari | 763
P17-KS-S20-O | P17-KS-S20-O | 406.a/407.c | MPSB/MB/206 | Mb | 3 | 3 | 2025-09-27 | IPC - 20 | 1 | Palashbari | 763
P17-KS-S21-O | P17-KS-S21-O© | 406.a/407.c/408.c | MPSB/Str/2346 | Str | 1 | 3 | 2025-09-29 | IPC - 20 | 1 | Palashbari | 764
P17-KS-S21-O | P17-KS-S21-O© | 406.a/407.c/408.c | MPSB/Sur/1896 | Sur | 2 | 3 | 2025-09-30 | IPC - 20 | 1 | Palashbari | 764
P17-KS-S21-O | P17-KS-S21-O© | 406.a/407.c/408.c | MPSB/MB/212 | Mb | 3 | 3 | 2025-09-30 | IPC - 20 | 1 | Palashbari | 764
P25-KS-S17-O | P25-KS-S17-O© | 406.a/407.c/408.c | MPSB/MB/111 | Mb | 1 | 3 | 2025-08-27 | IPC - 20 | 1 | Sualkuchi | 765
P25-KS-S17-O | P25-KS-S17-O© | 406.a/407.c/408.c | MPSB/Sur/1758 | Sur | 2 | 3 | 2025-09-01 | IPC - 20 | 1 | Sualkuchi | 765
P25-KS-S17-O | P25-KS-S17-O© | 406.a/407.c/408.c | MPSB/MB/126 | Mb | 3 | 3 | 2025-09-01 | IPC - 20 | 1 | Sualkuchi | 765
P25-KS-S18-O | P25-KS-S18-O | 406.a/407.c | MPSB/MB/133 | Mb | 1 | 3 | 2025-09-04 | IPC - 20 | 1 | Sualkuchi | 766
P25-KS-S18-O | P25-KS-S18-O | 406.a/407.c | MPSB/Sur/1793 | Sur | 2 | 3 | 2025-09-08 | IPC - 20 | 1 | Sualkuchi | 766
P25-KS-S18-O | P25-KS-S18-O | 406.a/407.c | MPSB/MB/140 | Mb | 3 | 3 | 2025-09-08 | IPC - 20 | 1 | Sualkuchi | 766
P25-KS-S19-O | P25-KS-S19-O© | 406.a/407.c/408.c | MPSB/MB/148 | Mb | 1 | 3 | 2025-09-10 | IPC - 20 | 1 | Sualkuchi | 767
P25-KS-S19-O | P25-KS-S19-O© | 406.a/407.c/408.c | MPSB/Sur/1820 | Sur | 2 | 3 | 2025-09-13 | IPC - 20 | 1 | Sualkuchi | 767
P25-KS-S19-O | P25-KS-S19-O© | 406.a/407.c/408.c | MPSB/MB/159 | Mb | 3 | 3 | 2025-09-13 | IPC - 20 | 1 | Sualkuchi | 767
P25-KS-S20-O | P25-KS-S20-O | 406.a/407.c | MPSB/MB/169 | Mb | 1 | 3 | 2025-09-16 | IPC - 20 | 1 | Sualkuchi | 768
P25-KS-S20-O | P25-KS-S20-O | 406.a/407.c | MPSB/Sur/1838 | Sur | 2 | 3 | 2025-09-19 | IPC - 20 | 1 | Sualkuchi | 768
P25-KS-S20-O | P25-KS-S20-O | 406.a/407.c | MPSB/MB/180 | Mb | 3 | 3 | 2025-09-19 | IPC - 20 | 1 | Sualkuchi | 768
P25-KS-S21-O | P25-KS-S21-O© | 406.a/407.c/408.c | MPSB/MB/202 | Mb | 1 | 3 | 2025-09-25 | IPC - 20 | 1 | Sualkuchi | 769
P25-KS-S21-O | P25-KS-S21-O© | 406.a/407.c/408.c | MPSB/Sur/1876 | Sur | 2 | 3 | 2025-09-26 | IPC - 20 | 1 | Sualkuchi | 769
P25-KS-S21-O | P25-KS-S21-O© | 406.a/407.c/408.c | MPSB/MB/204 | Mb | 3 | 3 | 2025-09-26 | IPC - 20 | 1 | Sualkuchi | 769
P25-BP-S09a-O | P25-BP-S09a-O© | 406.a/407.c/408.c | MPSB/MB/125 | Mb | 1 | 3 | 2025-09-01 | IPC - 20 | 1 | Sualkuchi | 770
P25-BP-S09a-O | P25-BP-S09a-O© | 406.a/407.c/408.c | MPSB/Sur/1819 | Sur | 2 | 3 | 2025-09-13 | IPC - 20 | 1 | Sualkuchi | 770
P25-BP-S09a-O | P25-BP-S09a-O© | 406.a/407.c/408.c | MPSB/MB/158 | Mb | 3 | 3 | 2025-09-13 | IPC - 20 | 1 | Sualkuchi | 770
P25-BP-S10a-O | P25-BP-S10a-O | 406.a/407.c | MPSB/MB/170 | Mb | 1 | 3 | 2025-09-16 | IPC - 20 | 1 | Sualkuchi | 771
P25-BP-S10a-O | P25-BP-S10a-O | 406.a/407.c | MPSB/Sur/1860 | Sur | 2 | 3 | 2025-09-22 | IPC - 20 | 1 | Sualkuchi | 771
P25-BP-S10a-O | P25-BP-S10a-O | 406.a/407.c | MPSB/MB/191 | Mb | 3 | 3 | 2025-09-22 | IPC - 20 | 1 | Sualkuchi | 771
P25-BP-S11a-O | P25-BP-S11a-O© | 406.a/407.c/408.c | MPSB/MB/201 | Mb | 1 | 3 | 2025-09-25 | IPC - 20 | 1 | Sualkuchi | 772
P25-BP-S11a-O | P25-BP-S11a-O© | 406.a/407.c/408.c | MPSB/Sur/1883 | Sur | 2 | 3 | 2025-09-27 | IPC - 20 | 1 | Sualkuchi | 772
P25-BP-S11a-O | P25-BP-S11a-O© | 406.a/407.c/408.c | MPSB/MB/209 | Mb | 3 | 3 | 2025-09-27 | IPC - 20 | 1 | Sualkuchi | 772
P25-BP-S12a-O | P25-BP-S12a-O | 406.a/407.c | MPSB/MB/210 | Mb | 1 | 3 | 2025-09-30 | IPC - 20 | 1 | Sualkuchi | 773
P25-BP-S12a-O | P25-BP-S12a-O | 406.a/407.c | MPSB/Sur/1895 | Sur | 2 | 3 | 2025-09-30 | IPC - 20 | 1 | Sualkuchi | 773
P25-BP-S12a-O | P25-BP-S12a-O | 406.a/407.c | MPSB/MB/211 | Mb | 3 | 3 | 2025-09-30 | IPC - 20 | 1 | Sualkuchi | 773
P17-BP-S33a-O | P17-BP-S33a-O© | 406.a/407.c/408.c | MPSB/MB/264 | Mb | 1 | 3 | 2025-10-16 | IPC - 22 | 1 | Palashbari | 774
P17-BP-S33a-O | P17-BP-S33a-O© | 406.a/407.c/408.c | MPSB/Sur/2011 | Sur | 2 | 3 | 2025-10-18 | IPC - 22 | 1 | Palashbari | 774
P17-BP-S33a-O | P17-BP-S33a-O© | 406.a/407.c/408.c | MPSB/MB/271 | Mb | 3 | 3 | 2025-10-18 | IPC - 22 | 1 | Palashbari | 774
P17-BP-S34a-O | P17-BP-S34a-O | 406.a/407.c | MPSB/MB/285 | Mb | 1 | 3 | 2025-10-23 | IPC - 22 | 1 | Palashbari | 775
P17-BP-S34a-O | P17-BP-S34a-O | 406.a/407.c | MPSB/Sur/2043 | Sur | 2 | 3 | 2025-10-25 | IPC - 22 | 1 | Palashbari | 775
P17-BP-S34a-O | P17-BP-S34a-O | 406.a/407.c | MPSB/MB/294 | Mb | 3 | 3 | 2025-10-25 | IPC - 22 | 1 | Palashbari | 775
P18-KS-S01a-E | P18-KS-S01a-E | 406.a/407.c | MPSB/MB/197 | Mb | 1 | 3 | 2025-09-24 | IPC - 22 | 1 | Palashbari | 776
P18-KS-S01a-E | P18-KS-S01a-E | 406.a/407.c | MPSB/Sur/1898 | Sur | 2 | 3 | 2025-09-30 | IPC - 22 | 1 | Palashbari | 776
P18-KS-S01a-E | P18-KS-S01a-E | 406.a/407.c | MPSB/MB/214 | Mb | 3 | 3 | 2025-09-30 | IPC - 22 | 1 | Palashbari | 776
P18-KS-S01-E | P18-KS-S01-E | 406.a/407.c | MPSB/MB/220 | Mb | 1 | 3 | 2025-10-03 | IPC - 22 | 1 | Palashbari | 777
P18-KS-S01-E | P18-KS-S01-E | 406.a/407.c | MPSB/Sur/1934 | Sur | 2 | 3 | 2025-10-07 | IPC - 22 | 1 | Palashbari | 777
P18-KS-S01-E | P18-KS-S01-E | 406.a/407.c | MPSB/MB/233 | Mb | 3 | 3 | 2025-10-07 | IPC - 22 | 1 | Palashbari | 777
P18-KS-S02-E | P18-KS-S02-E | 406.a/407.c | MPSB/MB/245 | Mb | 1 | 3 | 2025-10-10 | IPC - 22 | 1 | Palashbari | 778
P18-KS-S02-E | P18-KS-S02-E | 406.a/407.c | MPSB/Sur/1976 | Sur | 2 | 3 | 2025-10-13 | IPC - 22 | 1 | Palashbari | 778
P18-KS-S02-E | P18-KS-S02-E | 406.a/407.c | MPSB/MB/256 | Mb | 3 | 3 | 2025-10-13 | IPC - 22 | 1 | Palashbari | 778
P18-KS-S03-E | P18-KS-S03-E | 406.a/407.c | MPSB/MB/276 | Mb | 1 | 3 | 2025-10-20 | IPC - 22 | 1 | Palashbari | 779
P18-KS-S03-E | P18-KS-S03-E | 406.a/407.c | MPSB/Sur/2024 | Sur | 2 | 3 | 2025-10-22 | IPC - 22 | 1 | Palashbari | 779
P18-KS-S03-E | P18-KS-S03-E | 406.a/407.c | MPSB/MB/281 | Mb | 3 | 3 | 2025-10-22 | IPC - 22 | 1 | Palashbari | 779
P18-KS-S04-E | P18-KS-S04-E | 406.a/407.c | MPSB/MB/297 | Mb | 1 | 3 | 2025-10-27 | IPC - 22 | 1 | Palashbari | 780
P18-KS-S04-E | P18-KS-S04-E | 406.a/407.c | MPSB/Sur/2064 | Sur | 2 | 3 | 2025-10-28 | IPC - 22 | 1 | Palashbari | 780
P18-KS-S04-E | P18-KS-S04-E | 406.a/407.c | MPSB/MB/302 | Mb | 3 | 3 | 2025-10-28 | IPC - 22 | 1 | Palashbari | 780
P18-KS-S05-E | P18-KS-S05-E | 406.a/407.c | MPSB/MB/305 | Mb | 1 | 3 | 2025-10-30 | IPC - 22 | 1 | Palashbari | 781
P18-KS-S05-E | P18-KS-S05-E | 406.a/407.c | MPSB/Sur/2087 | Sur | 2 | 3 | 2025-10-31 | IPC - 22 | 1 | Palashbari | 781
P18-KS-S05-E | P18-KS-S05-E | 406.a/407.c | MPSB/MB/319 | Mb | 3 | 3 | 2025-10-31 | IPC - 22 | 1 | Palashbari | 781
P17-KS-S22-O | P17-KS-S22-O | 406.a/407.c | MPSB/MB/195 | Mb | 1 | 3 | 2025-09-24 | IPC - 22 | 1 | Palashbari | 782
P17-KS-S22-O | P17-KS-S22-O | 406.a/407.c | MPSB/Sur/1927 | Sur | 2 | 3 | 2025-10-06 | IPC - 22 | 1 | Palashbari | 782
P17-KS-S22-O | P17-KS-S22-O | 406.a/407.c | MPSB/MB/230 | Mb | 3 | 3 | 2025-10-06 | IPC - 22 | 1 | Palashbari | 782
P17-KS-S23-O | P17-KS-S23-O© | 406.a/407.c/408.c | MPSB/MB/227 | Mb | 1 | 3 | 2025-10-06 | IPC - 22 | 1 | Palashbari | 783
P17-KS-S23-O | P17-KS-S23-O© | 406.a/407.c/408.c | MPSB/Sur/1957 | Sur | 2 | 3 | 2025-10-09 | IPC - 22 | 1 | Palashbari | 783
P17-KS-S23-O | P17-KS-S23-O© | 406.a/407.c/408.c | MPSB/MB/241 | Mb | 3 | 3 | 2025-10-09 | IPC - 22 | 1 | Palashbari | 783
P17-KS-S24-O | P17-KS-S24-O | 406.a/407.c | MPSB/MB/249 | Mb | 1 | 3 | 2025-10-11 | IPC - 22 | 1 | Palashbari | 784
P17-KS-S24-O | P17-KS-S24-O | 406.a/407.c | MPSB/Sur/1978 | Sur | 2 | 3 | 2025-10-14 | IPC - 22 | 1 | Palashbari | 784
P17-KS-S24-O | P17-KS-S24-O | 406.a/407.c | MPSB/MB/257 | Mb | 3 | 3 | 2025-10-14 | IPC - 22 | 1 | Palashbari | 784
P17-KS-S25-O | P17-KS-S25-O© | 406.a/407.c/408.c | MPSB/MB/259 | Mb | 1 | 3 | 2025-10-14 | IPC - 22 | 1 | Palashbari | 785
P17-KS-S25-O | P17-KS-S25-O© | 406.a/407.c/408.c | MPSB/Sur/1998 | Sur | 2 | 3 | 2025-10-17 | IPC - 22 | 1 | Palashbari | 785
P17-KS-S25-O | P17-KS-S25-O© | 406.a/407.c/408.c | MPSB/MB/266 | Mb | 3 | 3 | 2025-10-17 | IPC - 22 | 1 | Palashbari | 785
P17-KS-S26-O | P17-KS-S26-O | 406.a/407.c | MPSB/MB/273 | Mb | 1 | 3 | 2025-10-19 | IPC - 22 | 1 | Palashbari | 786
P17-KS-S26-O | P17-KS-S26-O | 406.a/407.c | MPSB/Sur/2023 | Sur | 2 | 3 | 2025-10-22 | IPC - 22 | 1 | Palashbari | 786
P17-KS-S26-O | P17-KS-S26-O | 406.a/407.c | MPSB/MB/278 | Mb | 3 | 3 | 2025-10-22 | IPC - 22 | 1 | Palashbari | 786
P17-KS-S27-O | P17-KS-S27-O© | 406.a/407.c/408.c | MPSB/MB/286 | Mb | 1 | 3 | 2025-10-23 | IPC - 22 | 1 | Palashbari | 787
P17-KS-S27-O | P17-KS-S27-O© | 406.a/407.c/408.c | MPSB/Sur/2057 | Sur | 2 | 3 | 2025-10-27 | IPC - 22 | 1 | Palashbari | 787
P17-KS-S27-O | P17-KS-S27-O© | 406.a/407.c/408.c | MPSB/MB/296 | Mb | 3 | 3 | 2025-10-27 | IPC - 22 | 1 | Palashbari | 787
P17-KS-S28-O | P17-KS-S28-O | 406.a/407.c | MPSB/MB/301 | Mb | 1 | 3 | 2025-10-28 | IPC - 22 | 1 | Palashbari | 788
P17-KS-S28-O | P17-KS-S28-O | 406.a/407.c | MPSB/Sur/2073 | Sur | 2 | 3 | 2025-10-30 | IPC - 22 | 1 | Palashbari | 788
P17-KS-S28-O | P17-KS-S28-O | 406.a/407.c | MPSB/MB/307 | Mb | 3 | 3 | 2025-10-30 | IPC - 22 | 1 | Palashbari | 788
P25-BP-S13a-O | P25-BP-S13a-O© | 406.a/407.c/408.c | MPSB/MB/232 | Mb | 1 | 3 | 2025-10-06 | IPC - 22 | 1 | Sualkuchi | 789
P25-BP-S13a-O | P25-BP-S13a-O© | 406.a/407.c/408.c | MPSB/Sur/1949 | Sur | 2 | 3 | 2025-10-09 | IPC - 22 | 1 | Sualkuchi | 789
P25-BP-S13a-O | P25-BP-S13a-O© | 406.a/407.c/408.c | MPSB/MB/239 | Mb | 3 | 3 | 2025-10-09 | IPC - 22 | 1 | Sualkuchi | 789
P25-BP-S14a-O | P25-BP-S14a-O | 406.a/407.c | MPSB/MB/248 | Mb | 1 | 3 | 2025-10-11 | IPC - 22 | 1 | Sualkuchi | 790
P25-BP-S14a-O | P25-BP-S14a-O | 406.a/407.c | MPSB/Sur/1972 | Sur | 2 | 3 | 2025-10-13 | IPC - 22 | 1 | Sualkuchi | 790
P25-BP-S14a-O | P25-BP-S14a-O | 406.a/407.c | MPSB/MB/253 | Mb | 3 | 3 | 2025-10-13 | IPC - 22 | 1 | Sualkuchi | 790
P25-BP-S15a-O | P25-BP-S15a-O© | 406.a/407.c/408.c | MPSB/MB/262 | Mb | 1 | 3 | 2025-10-15 | IPC - 22 | 1 | Sualkuchi | 791
P25-BP-S15a-O | P25-BP-S15a-O© | 406.a/407.c/408.c | MPSB/Sur/2002 | Sur | 2 | 3 | 2025-10-17 | IPC - 22 | 1 | Sualkuchi | 791
P25-BP-S15a-O | P25-BP-S15a-O© | 406.a/407.c/408.c | MPSB/MB/270 | Mb | 3 | 3 | 2025-10-17 | IPC - 22 | 1 | Sualkuchi | 791
P25-BP-S16a-O | P25-BP-S16a-O | 406.a/407.c | MPSB/MB/280 | Mb | 1 | 3 | 2025-10-22 | IPC - 22 | 1 | Sualkuchi | 792
P25-BP-S16a-O | P25-BP-S16a-O | 406.a/407.c | MPSB/Sur/2036 | Sur | 2 | 3 | 2025-10-24 | IPC - 22 | 1 | Sualkuchi | 792
P25-BP-S16a-O | P25-BP-S16a-O | 406.a/407.c | MPSB/MB/288 | Mb | 3 | 3 | 2025-10-24 | IPC - 22 | 1 | Sualkuchi | 792
P25-BP-S17a-O | P25-BP-S17a-O© | 406.a/407.c/408.c | MPSB/MB/304 | Mb | 1 | 3 | 2025-10-28 | IPC - 22 | 1 | Sualkuchi | 793
P25-BP-S17a-O | P25-BP-S17a-O© | 406.a/407.c/408.c | MPSB/Sur/2074 | Sur | 2 | 3 | 2025-10-30 | IPC - 22 | 1 | Sualkuchi | 793
P25-BP-S17a-O | P25-BP-S17a-O© | 406.a/407.c/408.c | MPSB/MB/310 | Mb | 3 | 3 | 2025-10-30 | IPC - 22 | 1 | Sualkuchi | 793
P23-KS-S09a-O | P23-KS-S09a-O© | 406.a/407.c/408.c | MPSB/MB/198 | Mb | 1 | 3 | 2025-09-24 | IPC - 22 | 1 | Sualkuchi | 794
P23-KS-S09a-O | P23-KS-S09a-O© | 406.a/407.c/408.c | MPSB/Sur/1915 | Sur | 2 | 3 | 2025-10-03 | IPC - 22 | 1 | Sualkuchi | 794
P23-KS-S09a-O | P23-KS-S09a-O© | 406.a/407.c/408.c | MPSB/MB/217 | Mb | 3 | 3 | 2025-10-03 | IPC - 22 | 1 | Sualkuchi | 794
P23-KS-S10a-O | P23-KS-S10a-O | 406.a/407.c | MPSB/MB/231 | Mb | 1 | 3 | 2025-10-06 | IPC - 22 | 1 | Sualkuchi | 795
P23-KS-S10a-O | P23-KS-S10a-O | 406.a/407.c | MPSB/Sur/1948 | Sur | 2 | 3 | 2025-10-08 | IPC - 22 | 1 | Sualkuchi | 795
P23-KS-S10a-O | P23-KS-S10a-O | 406.a/407.c | MPSB/MB/235 | Mb | 3 | 3 | 2025-10-08 | IPC - 22 | 1 | Sualkuchi | 795
P23-KS-S11a-O | P23-KS-S11a-O© | 406.a/407.c/408.c | MPSB/MB/243 | Mb | 1 | 3 | 2025-10-10 | IPC - 22 | 1 | Sualkuchi | 796
P23-KS-S11a-O | P23-KS-S11a-O© | 406.a/407.c/408.c | MPSB/Sur/1970 | Sur | 2 | 3 | 2025-10-11 | IPC - 22 | 1 | Sualkuchi | 796
P23-KS-S11a-O | P23-KS-S11a-O© | 406.a/407.c/408.c | MPSB/MB/250 | Mb | 3 | 3 | 2025-10-11 | IPC - 22 | 1 | Sualkuchi | 796
P23-KS-S12a-O | P23-KS-S12a-O | 406.a/407.c | MPSB/MB/252 | Mb | 1 | 3 | 2025-10-13 | IPC - 22 | 1 | Sualkuchi | 797
P23-KS-S12a-O | P23-KS-S12a-O | 406.a/407.c | MPSB/Sur/1987 | Sur | 2 | 3 | 2025-10-15 | IPC - 22 | 1 | Sualkuchi | 797
P23-KS-S12a-O | P23-KS-S12a-O | 406.a/407.c | MPSB/MB/260 | Mb | 3 | 3 | 2025-10-15 | IPC - 22 | 1 | Sualkuchi | 797
P23-KS-S13a-O | P23-KS-S13a-O© | 406.a/407.c/408.c | MPSB/MB/269 | Mb | 1 | 3 | 2025-10-17 | IPC - 22 | 1 | Sualkuchi | 798
P23-KS-S13a-O | P23-KS-S13a-O© | 406.a/407.c/408.c | MPSB/Sur/2015 | Sur | 2 | 3 | 2025-10-18 | IPC - 22 | 1 | Sualkuchi | 798
P23-KS-S13a-O | P23-KS-S13a-O© | 406.a/407.c/408.c | MPSB/MB/272 | Mb | 3 | 3 | 2025-10-18 | IPC - 22 | 1 | Sualkuchi | 798
P23-KS-S14a-O | P23-KS-S14a-O | 406.a/407.c | MPSB/MB/274 | Mb | 1 | 3 | 2025-10-19 | IPC - 22 | 1 | Sualkuchi | 799
P23-KS-S14a-O | P23-KS-S14a-O | 406.a/407.c | MPSB/Sur/2018 | Sur | 2 | 3 | 2025-10-22 | IPC - 22 | 1 | Sualkuchi | 799
P23-KS-S14a-O | P23-KS-S14a-O | 406.a/407.c | MPSB/MB/279 | Mb | 3 | 3 | 2025-10-22 | IPC - 22 | 1 | Sualkuchi | 799
P23-KS-S15a-O | P23-KS-S15a-O© | 406.a/407.c/408.c | MPSB/MB/289 | Mb | 1 | 3 | 2025-10-24 | IPC - 22 | 1 | Sualkuchi | 800
P23-KS-S15a-O | P23-KS-S15a-O© | 406.a/407.c/408.c | MPSB/Sur/2055 | Sur | 2 | 3 | 2025-10-27 | IPC - 22 | 1 | Sualkuchi | 800
P23-KS-S15a-O | P23-KS-S15a-O© | 406.a/407.c/408.c | MPSB/MB/295 | Mb | 3 | 3 | 2025-10-27 | IPC - 22 | 1 | Sualkuchi | 800
P23-KS-S16a-O | P23-KS-S16a-O | 406.a/407.c | MPSB/MB/303 | Mb | 1 | 3 | 2025-10-28 | IPC - 22 | 1 | Sualkuchi | 801
P23-KS-S16a-O | P23-KS-S16a-O | 406.a/407.c | MPSB/Sur/2075 | Sur | 2 | 3 | 2025-10-30 | IPC - 22 | 1 | Sualkuchi | 801
P23-KS-S16a-O | P23-KS-S16a-O | 406.a/407.c | MPSB/MB/311 | Mb | 3 | 3 | 2025-10-30 | IPC - 22 | 1 | Sualkuchi | 801
P17-KS-S29-O | P17-KS-S29-O© | 406.a/407.c/408.c | MPSB/MB/320 | Mb | 1 | 3 | 2025-11-01 | IPC - 23 | 1 | Palashbari | 802
P17-KS-S29-O | P17-KS-S29-O© | 406.a/407.c/408.c | MPSB/Sur/2119 | Sur | 2 | 3 | 2025-11-03 | IPC - 23 | 1 | Palashbari | 802
P17-KS-S29-O | P17-KS-S29-O© | 406.a/407.c/408.c | MPSB/MB/327 | Mb | 3 | 3 | 2025-11-03 | IPC - 23 | 1 | Palashbari | 802
P17-KS-S30-O | P17-KS-S30-O | 406.a/407.c | MPSB/MB/329 | Mb | 1 | 3 | 2025-11-04 | IPC - 23 | 1 | Palashbari | 803
P17-KS-S30-O | P17-KS-S30-O | 406.a/407.c | MPSB/Sur/2169 | Sur | 2 | 3 | 2025-11-10 | IPC - 23 | 1 | Palashbari | 803
P17-KS-S30-O | P17-KS-S30-O | 406.a/407.c | MPSB/MB/344 | Mb | 3 | 3 | 2025-11-10 | IPC - 23 | 1 | Palashbari | 803
P17-KS-S31-O | P17-KS-S31-O© | 406.a/407.c/408.c | MPSB/MB/369 | Mb | 1 | 3 | 2025-11-17 | IPC - 23 | 1 | Palashbari | 804
P17-KS-S31-O | P17-KS-S31-O© | 406.a/407.c/408.c | MPSB/Sur/2237 | Sur | 2 | 3 | 2025-11-20 | IPC - 23 | 1 | Palashbari | 804
P17-KS-S31-O | P17-KS-S31-O© | 406.a/407.c/408.c | MPSB/MB/381 | Mb | 3 | 3 | 2025-11-20 | IPC - 23 | 1 | Palashbari | 804
P17-KS-S32-O | P17-KS-S32-O | 406.a/407.c | MPSB/MB/390 | Mb | 1 | 3 | 2025-11-22 | IPC - 23 | 1 | Palashbari | 805
P17-KS-S32-O | P17-KS-S32-O | 406.a/407.c | MPSB/Sur/2272 | Sur | 2 | 3 | 2025-11-25 | IPC - 23 | 1 | Palashbari | 805
P17-KS-S32-O | P17-KS-S32-O | 406.a/407.c | MPSB/MB/402 | Mb | 3 | 3 | 2025-11-25 | IPC - 23 | 1 | Palashbari | 805
P18-KS-S06-E | P18-KS-S06-E | 406.a/407.c | MPSB/MB/323 | Mb | 1 | 3 | 2025-11-03 | IPC - 23 | 1 | Palashbari | 806
P18-KS-S06-E | P18-KS-S06-E | 406.a/407.c | MPSB/Sur/2129 | Sur | 2 | 3 | 2025-11-06 | IPC - 23 | 1 | Palashbari | 806
P18-KS-S06-E | P18-KS-S06-E | 406.a/407.c | MPSB/MB/332 | Mb | 3 | 3 | 2025-11-06 | IPC - 23 | 1 | Palashbari | 806
P23-KS-S17a-O | P23-KS-S17a-O© | 406.a/407.c/408.c | MPSB/MB/312 | Mb | 1 | 3 | 2025-10-31 | IPC - 23 | 1 | Sualkuchi | 807
P23-KS-S17a-O | P23-KS-S17a-O© | 406.a/407.c/408.c | MPSB/Sur/2122 | Sur | 2 | 3 | 2025-11-04 | IPC - 23 | 1 | Sualkuchi | 807
P23-KS-S17a-O | P23-KS-S17a-O© | 406.a/407.c/408.c | MPSB/MB/331 | Mb | 3 | 3 | 2025-11-04 | IPC - 23 | 1 | Sualkuchi | 807
P23-KS-S18a-O | P23-KS-S18a-O | 406.a/407.c | MPSB/MB/336 | Mb | 1 | 3 | 2025-11-07 | IPC - 23 | 1 | Sualkuchi | 808
P23-KS-S18a-O | P23-KS-S18a-O | 406.a/407.c | MPSB/Sur/2141 | Sur | 2 | 3 | 2025-11-07 | IPC - 23 | 1 | Sualkuchi | 808
P23-KS-S18a-O | P23-KS-S18a-O | 406.a/407.c | MPSB/MB/337 | Mb | 3 | 3 | 2025-11-07 | IPC - 23 | 1 | Sualkuchi | 808
P23-KS-S19a-O | P23-KS-S19a-O© | 406.a/407.c/408.c | MPSB/MB/346 | Mb | 1 | 3 | 2025-11-11 | IPC - 23 | 1 | Sualkuchi | 809
P23-KS-S19a-O | P23-KS-S19a-O© | 406.a/407.c/408.c | MPSB/Sur/2194 | Sur | 2 | 3 | 2025-11-15 | IPC - 23 | 1 | Sualkuchi | 809
P23-KS-S19a-O | P23-KS-S19a-O© | 406.a/407.c/408.c | MPSB/MB/359 | Mb | 3 | 3 | 2025-11-15 | IPC - 23 | 1 | Sualkuchi | 809
P23-KS-S20a-O | P23-KS-S20a-O | 406.a/407.c | MPSB/MB/374 | Mb | 1 | 3 | 2025-11-19 | IPC - 23 | 1 | Sualkuchi | 810
P23-KS-S20a-O | P23-KS-S20a-O | 406.a/407.c | MPSB/Sur/2229 | Sur | 2 | 3 | 2025-11-20 | IPC - 23 | 1 | Sualkuchi | 810
P23-KS-S20a-O | P23-KS-S20a-O | 406.a/407.c | MPSB/MB/377 | Mb | 3 | 3 | 2025-11-20 | IPC - 23 | 1 | Sualkuchi | 810
P23-KS-S21a-O | P23-KS-S21a-O© | 406.a/407.c/408.c | MPSB/MB/414 | Mb | 1 | 3 | 2025-11-27 | IPC - 23 | 1 | Sualkuchi | 811
P23-KS-S21a-O | P23-KS-S21a-O© | 406.a/407.c/408.c | MPSB/Sur/2299 | Sur | 2 | 3 | 2025-11-28 | IPC - 23 | 1 | Sualkuchi | 811
P23-KS-S21a-O | P23-KS-S21a-O© | 406.a/407.c/408.c | MPSB/MB/417 | Mb | 3 | 3 | 2025-11-28 | IPC - 23 | 1 | Sualkuchi | 811
P24-KS-S08-M | P24-KS-S08-M© | 406.a/407.c/408.c | MPSB/MB/343 | Mb | 1 | 3 | 2025-11-09 | IPC - 23 | 1 | Sualkuchi | 812
P24-KS-S08-M | P24-KS-S08-M© | 406.a/407.c/408.c | MPSB/Sur/2182 | Sur | 2 | 3 | 2025-11-13 | IPC - 23 | 1 | Sualkuchi | 812
P24-KS-S08-M | P24-KS-S08-M© | 406.a/407.c/408.c | MPSB/MB/353 | Mb | 3 | 3 | 2025-11-13 | IPC - 23 | 1 | Sualkuchi | 812
P24-KS-S09-M | P24-KS-S09-M | 406.a/407.c | MPSB/MB/366 | Mb | 1 | 3 | 2025-11-17 | IPC - 23 | 1 | Sualkuchi | 813
P24-KS-S09-M | P24-KS-S09-M | 406.a/407.c | MPSB/Sur/2220 | Sur | 2 | 3 | 2025-11-18 | IPC - 23 | 1 | Sualkuchi | 813
P24-KS-S09-M | P24-KS-S09-M | 406.a/407.c | MPSB/MB/373 | Mb | 3 | 3 | 2025-11-18 | IPC - 23 | 1 | Sualkuchi | 813
P24-KS-S10-M | P24-KS-S10-M© | 406.a/407.c/408.c | MPSB/MB/386 | Mb | 1 | 3 | 2025-11-21 | IPC - 23 | 1 | Sualkuchi | 814
P24-KS-S10-M | P24-KS-S10-M© | 406.a/407.c/408.c | MPSB/Sur/2248 | Sur | 2 | 3 | 2025-11-22 | IPC - 23 | 1 | Sualkuchi | 814
P24-KS-S10-M | P24-KS-S10-M© | 406.a/407.c/408.c | MPSB/MB/389 | Mb | 3 | 3 | 2025-11-22 | IPC - 23 | 1 | Sualkuchi | 814
P24-KS-S11-M | P24-KS-S11-M | 406.a/407.c | MPSB/MB/400 | Mb | 1 | 3 | 2025-11-25 | IPC - 23 | 1 | Sualkuchi | 815
P24-KS-S11-M | P24-KS-S11-M | 406.a/407.c | MPSB/Sur/2281 | Sur | 2 | 3 | 2025-11-26 | IPC - 23 | 1 | Sualkuchi | 815
P24-KS-S11-M | P24-KS-S11-M | 406.a/407.c | MPSB/MB/406 | Mb | 3 | 3 | 2025-11-26 | IPC - 23 | 1 | Sualkuchi | 815
P24-KS-S12-M | P24-KS-S12-M© | 406.a/407.c/408.c | MPSB/MB/425 | Mb | 1 | 3 | 2025-11-29 | IPC - 23 | 1 | Sualkuchi | 816
P24-KS-S12-M | P24-KS-S12-M© | 406.a/407.c/408.c | MPSB/Sur/2305 | Sur | 2 | 3 | 2025-11-29 | IPC - 23 | 1 | Sualkuchi | 816
P24-KS-S12-M | P24-KS-S12-M© | 406.a/407.c/408.c | MPSB/MB/426 | Mb | 3 | 3 | 2025-11-29 | IPC - 23 | 1 | Sualkuchi | 816
P25-BP-S18a-O | P25-BP-S18a-O | 406.a/407.c | MPSB/MB/347 | Mb | 1 | 3 | 2025-11-11 | IPC - 23 | 1 | Sualkuchi | 817
P25-BP-S18a-O | P25-BP-S18a-O | 406.a/407.c | MPSB/Sur/2195 | Sur | 2 | 3 | 2025-11-15 | IPC - 23 | 1 | Sualkuchi | 817
P25-BP-S18a-O | P25-BP-S18a-O | 406.a/407.c | MPSB/MB/360 | Mb | 3 | 3 | 2025-11-15 | IPC - 23 | 1 | Sualkuchi | 817
P25-BP-S19a-O | P25-BP-S19a-O© | 406.a/407.c/408.c | MPSB/MB/375 | Mb | 1 | 3 | 2025-11-19 | IPC - 23 | 1 | Sualkuchi | 818
P25-BP-S19a-O | P25-BP-S19a-O© | 406.a/407.c/408.c | MPSB/Sur/2244 | Sur | 2 | 3 | 2025-11-21 | IPC - 23 | 1 | Sualkuchi | 818
P25-BP-S19a-O | P25-BP-S19a-O© | 406.a/407.c/408.c | MPSB/MB/388 | Mb | 3 | 3 | 2025-11-21 | IPC - 23 | 1 | Sualkuchi | 818
P25-BP-S20a-O | P25-BP-S20a-O | 406.a/407.c | MPSB/MB/418 | Mb | 1 | 2 | 2025-11-28 | IPC - 23 | 1 | Sualkuchi | 819
P25-BP-S20a-O | P25-BP-S20a-O | 406.a/407.c | MPSB/MB/427 | Mb | 2 | 2 | 2025-11-30 | IPC - 23 | 1 | Sualkuchi | 819
P7-BP-S01-O | P7-BP-S01-O | 406.a/407.c | MPSB/MB/351 | Mb | 1 | 3 | 2025-11-11 | IPC - 23 | 1 | Palashbari | 820
P7-BP-S01-O | P7-BP-S01-O | 406.a/407.c | MPSB/Sur/2207 | Sur | 2 | 3 | 2025-11-17 | IPC - 23 | 1 | Palashbari | 820
P7-BP-S01-O | P7-BP-S01-O | 406.a/407.c | MPSB/MB/363 | Mb | 3 | 3 | 2025-11-17 | IPC - 23 | 1 | Palashbari | 820
P7-BP-S02-O | P7-BP-S02-O | 406.a/407.c | MPSB/MB/383 | Mb | 1 | 3 | 2025-11-21 | IPC - 23 | 1 | Palashbari | 821
P7-BP-S02-O | P7-BP-S02-O | 406.a/407.c | MPSB/Sur/2258 | Sur | 2 | 3 | 2025-11-24 | IPC - 23 | 1 | Palashbari | 821
P7-BP-S02-O | P7-BP-S02-O | 406.a/407.c | MPSB/MB/397 | Mb | 3 | 3 | 2025-11-24 | IPC - 23 | 1 | Palashbari | 821
P7-BP-S03-O | P7-BP-S03-O | 406.a/407.c | MPSB/MB/412 | Mb | 1 | 3 | 2025-11-27 | IPC - 23 | 1 | Palashbari | 822
P7-BP-S03-O | P7-BP-S03-O | 406.a/407.c | MPSB/Sur/2303 | Sur | 2 | 3 | 2025-11-29 | IPC - 23 | 1 | Palashbari | 822
P7-BP-S03-O | P7-BP-S03-O | 406.a/407.c | MPSB/MB/422 | Mb | 3 | 3 | 2025-11-29 | IPC - 23 | 1 | Palashbari | 822
P7-BP-S09-O | P7-BP-S09-O© | 406.a/407.c/408.c | MPSB/MB/338 | Mb | 1 | 3 | 2025-11-08 | IPC - 23 | 1 | Palashbari | 823
P7-BP-S09-O | P7-BP-S09-O© | 406.a/407.c/408.c | MPSB/Sur/2177 | Sur | 2 | 3 | 2025-11-12 | IPC - 23 | 1 | Palashbari | 823
P7-BP-S09-O | P7-BP-S09-O© | 406.a/407.c/408.c | MPSB/MB/352 | Mb | 3 | 3 | 2025-11-12 | IPC - 23 | 1 | Palashbari | 823
P7-BP-S10-O | P7-BP-S10-O | 406.a/407.c | MPSB/MB/358 | Mb | 1 | 3 | 2025-11-14 | IPC - 23 | 1 | Palashbari | 824
P7-BP-S10-O | P7-BP-S10-O | 406.a/407.c | MPSB/Sur/2206 | Sur | 2 | 3 | 2025-11-17 | IPC - 23 | 1 | Palashbari | 824
P7-BP-S10-O | P7-BP-S10-O | 406.a/407.c | MPSB/MB/362 | Mb | 3 | 3 | 2025-11-17 | IPC - 23 | 1 | Palashbari | 824
P7-BP-S11-O | P7-BP-S11-O© | 406.a/407.c/408.c | MPSB/MB/367 | Mb | 1 | 3 | 2025-11-18 | IPC - 23 | 1 | Palashbari | 825
P7-BP-S11-O | P7-BP-S11-O© | 406.a/407.c/408.c | MPSB/Sur/2238 | Sur | 2 | 3 | 2025-11-20 | IPC - 23 | 1 | Palashbari | 825
P7-BP-S11-O | P7-BP-S11-O© | 406.a/407.c/408.c | MPSB/MB/382 | Mb | 3 | 3 | 2025-11-20 | IPC - 23 | 1 | Palashbari | 825
P7-BP-S12-O | P7-BP-S12-O | 406.a/407.c | MPSB/MB/368 | Mb | 1 | 3 | 2025-11-18 | IPC - 23 | 1 | Palashbari | 826
P7-BP-S12-O | P7-BP-S12-O | 406.a/407.c | MPSB/Sur/2257 | Sur | 2 | 3 | 2025-11-24 | IPC - 23 | 1 | Palashbari | 826
P7-BP-S12-O | P7-BP-S12-O | 406.a/407.c | MPSB/MB/396 | Mb | 3 | 3 | 2025-11-24 | IPC - 23 | 1 | Palashbari | 826
P7-BP-S13-O | P7-BP-S13-O© | 406.a/407.c/408.c | MPSB/MB/403 | Mb | 1 | 3 | 2025-11-26 | IPC - 23 | 1 | Palashbari | 827
P7-BP-S13-O | P7-BP-S13-O© | 406.a/407.c/408.c | MPSB/Sur/2291 | Sur | 2 | 3 | 2025-11-27 | IPC - 23 | 1 | Palashbari | 827
P7-BP-S13-O | P7-BP-S13-O© | 406.a/407.c/408.c | MPSB/MB/415 | Mb | 3 | 3 | 2025-11-27 | IPC - 23 | 1 | Palashbari | 827
P7-BP-S14-O | P7-BP-S14-O | 406.a/407.c | MPSB/MB/398 | Mb | 1 | 2 | 2025-11-24 | IPC - 23 | 1 | Palashbari | 828
P7-BP-S14-O | P7-BP-S14-O | 406.a/407.c | MPSB/MB/419 | Mb | 2 | 2 | 2025-11-28 | IPC - 23 | 1 | Palashbari | 828
P7-KS-S09a-O | P7-KS-S09a-O© | 406.a/407.c/408.c | MPSB/MB/354 | Mb | 1 | 3 | 2025-11-13 | IPC - 23 | 1 | Palashbari | 829
P7-KS-S09a-O | P7-KS-S09a-O© | 406.a/407.c/408.c | MPSB/Sur/2205 | Sur | 2 | 3 | 2025-11-17 | IPC - 23 | 1 | Palashbari | 829
P7-KS-S09a-O | P7-KS-S09a-O© | 406.a/407.c/408.c | MPSB/MB/361 | Mb | 3 | 3 | 2025-11-17 | IPC - 23 | 1 | Palashbari | 829
P7-KS-S10a-O | P7-KS-S10a-O | 406.a/407.c | MPSB/MB/384 | Mb | 1 | 3 | 2025-11-21 | IPC - 23 | 1 | Palashbari | 830
P7-KS-S10a-O | P7-KS-S10a-O | 406.a/407.c | MPSB/Sur/2249 | Sur | 2 | 3 | 2025-11-22 | IPC - 23 | 1 | Palashbari | 830
P7-KS-S10a-O | P7-KS-S10a-O | 406.a/407.c | MPSB/MB/391 | Mb | 3 | 3 | 2025-11-22 | IPC - 23 | 1 | Palashbari | 830
P7-KS-S11a-O | P7-KS-S11a-O© | 406.a/407.c/408.c | MPSB/MB/404 | Mb | 1 | 3 | 2025-11-26 | IPC - 23 | 1 | Palashbari | 831
P7-KS-S11a-O | P7-KS-S11a-O© | 406.a/407.c/408.c | MPSB/Sur/2285 | Sur | 2 | 3 | 2025-11-27 | IPC - 23 | 1 | Palashbari | 831
P7-KS-S11a-O | P7-KS-S11a-O© | 406.a/407.c/408.c | MPSB/MB/411 | Mb | 3 | 3 | 2025-11-27 | IPC - 23 | 1 | Palashbari | 831
P7-KS-S12a-O | P7-KS-S12a-O | 406.a/407.c | MPSB/MB/420 | Mb | 1 | 3 | 2025-11-28 | IPC - 23 | 1 | Palashbari | 832
P7-KS-S12a-O | P7-KS-S12a-O | 406.a/407.c | MPSB/Sur/2304 | Sur | 2 | 3 | 2025-11-29 | IPC - 23 | 1 | Palashbari | 832
P7-KS-S12a-O | P7-KS-S12a-O | 406.a/407.c | MPSB/MB/423 | Mb | 3 | 3 | 2025-11-29 | IPC - 23 | 1 | Palashbari | 832
P17-KS-S33-O | P17-KS-S33-O© | 406.a/407.c/408.c | MPSB/MB/434 | Mb | 1 | 3 | 2025-12-02 | IPC - 25 | 1 | Palashbari | 833
P17-KS-S33-O | P17-KS-S33-O© | 406.a/407.c/408.c | MPSB/Sur/2336 | Sur | 2 | 3 | 2025-12-04 | IPC - 25 | 1 | Palashbari | 833
P17-KS-S33-O | P17-KS-S33-O© | 406.a/407.c/408.c | MPSB/MB/435 | Mb | 3 | 3 | 2025-12-02 | IPC - 25 | 1 | Palashbari | 833
P17-KS-S34-O | P17-KS-S34-O | 406.a/407.c | MPSB/MB/453 | Mb | 1 | 3 | 2025-12-06 | IPC - 25 | 1 | Palashbari | 834
P17-KS-S34-O | P17-KS-S34-O | 406.a/407.c | MPSB/Sur/2366 | Sur | 2 | 3 | 2025-12-08 | IPC - 25 | 1 | Palashbari | 834
P17-KS-S34-O | P17-KS-S34-O | 406.a/407.c | MPSB/MB/464 | Mb | 3 | 3 | 2025-12-08 | IPC - 25 | 1 | Palashbari | 834
P23-BP-S09-O | P23-BP-S09-O© | 406.a/407.c/408.c | MPSB/MB/461 | Mb | 1 | 3 | 2025-12-07 | IPC - 25 | 1 | Sualkuchi | 835
P23-BP-S09-O | P23-BP-S09-O© | 406.a/407.c/408.c | MPSB/Sur/2377 | Sur | 2 | 3 | 2025-12-09 | IPC - 25 | 1 | Sualkuchi | 835
P23-BP-S09-O | P23-BP-S09-O© | 406.a/407.c/408.c | MPSB/MB/472 | Mb | 3 | 3 | 2025-12-09 | IPC - 25 | 1 | Sualkuchi | 835
P23-BP-S10-O | P23-BP-S10-O | 406.a/407.c | MPSB/MB/490 | Mb | 1 | 3 | 2025-12-13 | IPC - 25 | 1 | Sualkuchi | 836
P23-BP-S10-O | P23-BP-S10-O | 406.a/407.c | MPSB/Sur/2402 | Sur | 2 | 3 | 2025-12-13 | IPC - 25 | 1 | Sualkuchi | 836
P23-BP-S10-O | P23-BP-S10-O | 406.a/407.c | MPSB/MB/491 | Mb | 3 | 3 | 2025-12-13 | IPC - 25 | 1 | Sualkuchi | 836
P23-BP-S11-O | P23-BP-S11-O© | 406.a/407.c/408.c | MPSB/MB/508 | Mb | 1 | 3 | 2025-12-16 | IPC - 25 | 1 | Sualkuchi | 837
P23-BP-S11-O | P23-BP-S11-O© | 406.a/407.c/408.c | MPSB/Sur/2445 | Sur | 2 | 3 | 2025-12-18 | IPC - 25 | 1 | Sualkuchi | 837
P23-BP-S11-O | P23-BP-S11-O© | 406.a/407.c/408.c | MPSB/MB/522 | Mb | 3 | 3 | 2025-12-18 | IPC - 25 | 1 | Sualkuchi | 837
P23-BP-S12-O | P23-BP-S12-O | 406.a/407.c | MPSB/MB/528 | Mb | 1 | 3 | 2025-12-20 | IPC - 25 | 1 | Sualkuchi | 838
P23-BP-S12-O | P23-BP-S12-O | 406.a/407.c | MPSB/Sur/2458 | Sur | 2 | 3 | 2025-12-21 | IPC - 25 | 1 | Sualkuchi | 838
P23-BP-S12-O | P23-BP-S12-O | 406.a/407.c | MPSB/MB/534 | Mb | 3 | 3 | 2025-12-21 | IPC - 25 | 1 | Sualkuchi | 838
P23-BP-S13-O | P23-BP-S13-O© | 406.a/407.c/408.c | MPSB/MB/540 | Mb | 1 | 3 | 2025-12-23 | IPC - 25 | 1 | Sualkuchi | 839
P23-BP-S13-O | P23-BP-S13-O© | 406.a/407.c/408.c | MPSB/Sur/2496 | Sur | 2 | 3 | 2025-12-25 | IPC - 25 | 1 | Sualkuchi | 839
P23-BP-S13-O | P23-BP-S13-O© | 406.a/407.c/408.c | MPSB/MB/566 | Mb | 3 | 3 | 2025-12-25 | IPC - 25 | 1 | Sualkuchi | 839
P23-BP-S14-O | P23-BP-S14-O | 406.a/407.c | MPSB/MB/569 | Mb | 1 | 3 | 2025-12-26 | IPC - 25 | 1 | Sualkuchi | 840
P23-BP-S14-O | P23-BP-S14-O | 406.a/407.c | MPSB/Sur/2512 | Sur | 2 | 3 | 2025-12-27 | IPC - 25 | 1 | Sualkuchi | 840
P23-BP-S14-O | P23-BP-S14-O | 406.a/407.c | MPSB/MB/575 | Mb | 3 | 3 | 2025-12-27 | IPC - 25 | 1 | Sualkuchi | 840
P24-KS-S13-M | P24-KS-S13-M | 406.a/407.c | MPSB/MB/387 | Mb | 1 | 3 | 2025-11-21 | IPC - 25 | 1 | Sualkuchi | 841
P24-KS-S13-M | P24-KS-S13-M | 406.a/407.c | MPSB/Sur/2347 | Sur | 2 | 3 | 2025-12-05 | IPC - 25 | 1 | Sualkuchi | 841
P24-KS-S13-M | P24-KS-S13-M | 406.a/407.c | MPSB/MB/452 | Mb | 3 | 3 | 2025-12-05 | IPC - 25 | 1 | Sualkuchi | 841
P24-KS-S14-M | P24-KS-S14-M© | 406.a/407.c/408.c | MPSB/MB/462 | Mb | 1 | 3 | 2025-12-08 | IPC - 25 | 1 | Sualkuchi | 842
P24-KS-S14-M | P24-KS-S14-M© | 406.a/407.c/408.c | MPSB/Sur/2376 | Sur | 2 | 3 | 2025-12-09 | IPC - 25 | 1 | Sualkuchi | 842
P24-KS-S14-M | P24-KS-S14-M© | 406.a/407.c/408.c | MPSB/MB/471 | Mb | 3 | 3 | 2025-12-09 | IPC - 25 | 1 | Sualkuchi | 842
P24-KS-S15-M | P24-KS-S15-M | 406.a/407.c | MPSB/MB/485 | Mb | 1 | 3 | 2025-12-12 | IPC - 25 | 1 | Sualkuchi | 843
P24-KS-S15-M | P24-KS-S15-M | 406.a/407.c | MPSB/Sur/2398 | Sur | 2 | 3 | 2025-12-12 | IPC - 25 | 1 | Sualkuchi | 843
P24-KS-S15-M | P24-KS-S15-M | 406.a/407.c | MPSB/MB/487 | Mb | 3 | 3 | 2025-12-12 | IPC - 25 | 1 | Sualkuchi | 843
P24-KS-S16-M | P24-KS-S16-M© | 406.a/407.c/408.c | MPSB/MB/505 | Mb | 1 | 3 | 2025-12-15 | IPC - 25 | 1 | Sualkuchi | 844
P24-KS-S16-M | P24-KS-S16-M© | 406.a/407.c/408.c | MPSB/Sur/2420 | Sur | 2 | 3 | 2025-12-16 | IPC - 25 | 1 | Sualkuchi | 844
P24-KS-S16-M | P24-KS-S16-M© | 406.a/407.c/408.c | MPSB/MB/507 | Mb | 3 | 3 | 2025-12-16 | IPC - 25 | 1 | Sualkuchi | 844
P24-KS-S17-M | P24-KS-S17-M | 406.a/407.c | MPSB/MB/527 | Mb | 1 | 3 | 2025-12-20 | IPC - 25 | 1 | Sualkuchi | 845
P24-KS-S17-M | P24-KS-S17-M | 406.a/407.c | MPSB/Sur/2451 | Sur | 2 | 3 | 2025-12-20 | IPC - 25 | 1 | Sualkuchi | 845
P24-KS-S17-M | P24-KS-S17-M | 406.a/407.c | MPSB/MB/529 | Mb | 3 | 3 | 2025-12-20 | IPC - 25 | 1 | Sualkuchi | 845
P24-KS-S18-M | P24-KS-S18-M | 406.a/407.c | MPSB/MB/564 | Mb | 1 | 3 | 2025-12-25 | IPC - 25 | 1 | Sualkuchi | 846
P24-KS-S18-M | P24-KS-S18-M | 406.a/407.c | MPSB/Sur/2497 | Sur | 2 | 3 | 2025-12-25 | IPC - 25 | 1 | Sualkuchi | 846
P24-KS-S18-M | P24-KS-S18-M | 406.a/407.c | MPSB/MB/567 | Mb | 3 | 3 | 2025-12-25 | IPC - 25 | 1 | Sualkuchi | 846
P25-BP-S21a-O | P25-BP-S21a-O© | 406.a/407.c/408.c | MPSB/MB/595 | Mb | 1 | 3 | 2025-12-30 | IPC - 25 | 1 | Sualkuchi | 847
P25-BP-S21a-O | P25-BP-S21a-O© | 406.a/407.c/408.c | MPSB/Sur/2578 | Sur | 2 | 3 | 2025-12-31 | IPC - 25 | 1 | Sualkuchi | 847
P25-BP-S21a-O | P25-BP-S21a-O© | 406.a/407.c/408.c | MPSB/MB/611 | Mb | 3 | 3 | 2025-12-31 | IPC - 25 | 1 | Sualkuchi | 847
P25-KS-S22-O | P25-KS-S22-O | 406.a/407.c | MPSB/MB/506 | Mb | 1 | 3 | 2025-12-15 | IPC - 25 | 1 | Sualkuchi | 848
P25-KS-S22-O | P25-KS-S22-O | 406.a/407.c | MPSB/Sur/2433 | Sur | 2 | 3 | 2025-12-17 | IPC - 25 | 1 | Sualkuchi | 848
P25-KS-S22-O | P25-KS-S22-O | 406.a/407.c | MPSB/MB/520 | Mb | 3 | 3 | 2025-12-17 | IPC - 25 | 1 | Sualkuchi | 848
P25-KS-S23-O | P25-KS-S23-O© | 406.a/407.c/408.c | MPSB/MB/539 | Mb | 1 | 3 | 2025-12-23 | IPC - 25 | 1 | Sualkuchi | 849
P25-KS-S23-O | P25-KS-S23-O© | 406.a/407.c/408.c | MPSB/Sur/2472 | Sur | 2 | 3 | 2025-12-23 | IPC - 25 | 1 | Sualkuchi | 849
P25-KS-S23-O | P25-KS-S23-O© | 406.a/407.c/408.c | MPSB/MB/541 | Mb | 3 | 3 | 2025-12-23 | IPC - 25 | 1 | Sualkuchi | 849
P25-KS-S24-O | P25-KS-S24-O | 406.a/407.c | MPSB/MB/568 | Mb | 1 | 3 | 2025-12-26 | IPC - 25 | 1 | Sualkuchi | 850
P25-KS-S24-O | P25-KS-S24-O | 406.a/407.c | MPSB/Sur/2511 | Sur | 2 | 3 | 2025-12-27 | IPC - 25 | 1 | Sualkuchi | 850
P25-KS-S24-O | P25-KS-S24-O | 406.a/407.c | MPSB/MB/574 | Mb | 3 | 3 | 2025-12-27 | IPC - 25 | 1 | Sualkuchi | 850
P25-KS-S25-O | P25-KS-S25-O© | 406.a/407.c/408.c | MPSB/MB/593 | Mb | 1 | 3 | 2025-12-29 | IPC - 25 | 1 | Sualkuchi | 851
P25-KS-S25-O | P25-KS-S25-O© | 406.a/407.c/408.c | MPSB/Sur/2551 | Sur | 2 | 3 | 2025-12-30 | IPC - 25 | 1 | Sualkuchi | 851
P25-KS-S25-O | P25-KS-S25-O© | 406.a/407.c/408.c | MPSB/MB/596 | Mb | 3 | 3 | 2025-12-30 | IPC - 25 | 1 | Sualkuchi | 851
P7-BP-S04-O | P7-BP-S04-O | 406.a/407.c | MPSB/MB/445 | Mb | 1 | 3 | 2025-12-04 | IPC - 25 | 1 | Palashbari | 852
P7-BP-S04-O | P7-BP-S04-O | 406.a/407.c | MPSB/Sur/2352 | Sur | 2 | 3 | 2025-12-06 | IPC - 25 | 1 | Palashbari | 852
P7-BP-S04-O | P7-BP-S04-O | 406.a/407.c | MPSB/MB/454 | Mb | 3 | 3 | 2025-12-06 | IPC - 25 | 1 | Palashbari | 852
P7-BP-S05-O | P7-BP-S05-O | 406.a/407.c | MPSB/MB/467 | Mb | 1 | 3 | 2025-12-08 | IPC - 25 | 1 | Palashbari | 853
P7-BP-S05-O | P7-BP-S05-O | 406.a/407.c | MPSB/Sur/2380 | Sur | 2 | 3 | 2025-12-10 | IPC - 25 | 1 | Palashbari | 853
P7-BP-S05-O | P7-BP-S05-O | 406.a/407.c | MPSB/MB/474 | Mb | 3 | 3 | 2025-12-10 | IPC - 25 | 1 | Palashbari | 853
P7-BP-S06-O | P7-BP-S06-O | 406.a/407.c | MPSB/MB/496 | Mb | 1 | 3 | 2025-12-14 | IPC - 25 | 1 | Palashbari | 854
P7-BP-S06-O | P7-BP-S06-O | 406.a/407.c | MPSB/Sur/2427 | Sur | 2 | 3 | 2025-12-17 | IPC - 25 | 1 | Palashbari | 854
P7-BP-S06-O | P7-BP-S06-O | 406.a/407.c | MPSB/MB/513 | Mb | 3 | 3 | 2025-12-17 | IPC - 25 | 1 | Palashbari | 854
P7-BP-S07-O | P7-BP-S07-O | 406.a/407.c | MPSB/MB/512 | Mb | 1 | 3 | 2025-12-17 | IPC - 25 | 1 | Palashbari | 855
P7-BP-S07-O | P7-BP-S07-O | 406.a/407.c | MPSB/Sur/2463 | Sur | 2 | 3 | 2025-12-22 | IPC - 25 | 1 | Palashbari | 855
P7-BP-S07-O | P7-BP-S07-O | 406.a/407.c | MPSB/MB/537 | Mb | 3 | 3 | 2025-12-22 | IPC - 25 | 1 | Palashbari | 855
P7-BP-S08-O | P7-BP-S08-O | 406.a/407.c | MPSB/MB/545 | Mb | 1 | 3 | 2025-12-23 | IPC - 25 | 1 | Palashbari | 856
P7-BP-S08-O | P7-BP-S08-O | 406.a/407.c | MPSB/Sur/2515 | Sur | 2 | 3 | 2025-12-27 | IPC - 25 | 1 | Palashbari | 856
P7-BP-S08-O | P7-BP-S08-O | 406.a/407.c | MPSB/MB/576 | Mb | 3 | 3 | 2025-12-27 | IPC - 25 | 1 | Palashbari | 856
P7-BP-S15-O | P7-BP-S15-O© | 406.a/407.c/408.c | MPSB/MB/440 | Mb | 1 | 3 | 2025-12-03 | IPC - 25 | 1 | Palashbari | 857
P7-BP-S15-O | P7-BP-S15-O© | 406.a/407.c/408.c | MPSB/Sur/2337 | Sur | 2 | 3 | 2025-12-04 | IPC - 25 | 1 | Palashbari | 857
P7-BP-S15-O | P7-BP-S15-O© | 406.a/407.c/408.c | MPSB/MB/448 | Mb | 3 | 3 | 2025-12-04 | IPC - 25 | 1 | Palashbari | 857
P7-BP-S16-O | P7-BP-S16-O | 406.a/407.c | MPSB/MB/458 | Mb | 1 | 3 | 2025-12-06 | IPC - 25 | 1 | Palashbari | 858
P7-BP-S16-O | P7-BP-S16-O | 406.a/407.c | MPSB/Sur/2381 | Sur | 2 | 3 | 2025-12-10 | IPC - 25 | 1 | Palashbari | 858
P7-BP-S16-O | P7-BP-S16-O | 406.a/407.c | MPSB/MB/468 | Mb | 3 | 3 | 2025-12-09 | IPC - 25 | 1 | Palashbari | 858
P7-BP-S17-O | P7-BP-S17-O© | 406.a/407.c/408.c | MPSB/MB/476 | Mb | 1 | 3 | 2025-12-10 | IPC - 25 | 1 | Palashbari | 859
P7-BP-S17-O | P7-BP-S17-O© | 406.a/407.c/408.c | MPSB/Sur/2415 | Sur | 2 | 3 | 2025-12-15 | IPC - 25 | 1 | Palashbari | 859
P7-BP-S17-O | P7-BP-S17-O© | 406.a/407.c/408.c | MPSB/MB/504 | Mb | 3 | 3 | 2025-12-15 | IPC - 25 | 1 | Palashbari | 859
P7-BP-S18-O | P7-BP-S18-O | 406.a/407.c | MPSB/MB/511 | Mb | 1 | 3 | 2025-12-17 | IPC - 25 | 1 | Palashbari | 860
P7-BP-S18-O | P7-BP-S18-O | 406.a/407.c | MPSB/Sur/2429 | Sur | 2 | 3 | 2025-12-17 | IPC - 25 | 1 | Palashbari | 860
P7-BP-S18-O | P7-BP-S18-O | 406.a/407.c | MPSB/MB/515 | Mb | 3 | 3 | 2025-12-17 | IPC - 25 | 1 | Palashbari | 860
P7-BP-S19-O | P7-BP-S19-O© | 406.a/407.c/408.c | MPSB/MB/531 | Mb | 1 | 3 | 2025-12-20 | IPC - 25 | 1 | Palashbari | 861
P7-BP-S19-O | P7-BP-S19-O© | 406.a/407.c/408.c | MPSB/Sur/2464 | Sur | 2 | 3 | 2025-12-22 | IPC - 25 | 1 | Palashbari | 861
P7-BP-S19-O | P7-BP-S19-O© | 406.a/407.c/408.c | MPSB/MB/538 | Mb | 3 | 3 | 2025-12-22 | IPC - 25 | 1 | Palashbari | 861
P7-BP-S20-O | P7-BP-S20-O | 406.a/407.c | MPSB/MB/552 | Mb | 1 | 3 | 2025-12-24 | IPC - 25 | 1 | Palashbari | 862
P7-BP-S20-O | P7-BP-S20-O | 406.a/407.c | MPSB/Sur/2495 | Sur | 2 | 3 | 2025-12-25 | IPC - 25 | 1 | Palashbari | 862
P7-BP-S20-O | P7-BP-S20-O | 406.a/407.c | MPSB/MB/559 | Mb | 3 | 3 | 2025-12-25 | IPC - 25 | 1 | Palashbari | 862
P7-BP-S21-O | P7-BP-S21-O© | 406.a/407.c/408.c | MPSB/Sur/2531 | Sur | 1 | 2 | 2025-12-29 | IPC - 25 | 1 | Palashbari | 863
P7-BP-S21-O | P7-BP-S21-O© | 406.a/407.c/408.c | MPSB/MB/584 | Mb | 2 | 2 | 2025-12-30 | IPC - 25 | 1 | Palashbari | 863
P7-BP-S22-O | P7-BP-S22-O | 406.a/407.c | MPSB/MB/459 | Mb | 1 | 3 | 2025-12-06 | IPC - 25 | 1 | Palashbari | 864
P7-BP-S22-O | P7-BP-S22-O | 406.a/407.c | MPSB/Sur/2367 | Sur | 2 | 3 | 2025-12-08 | IPC - 25 | 1 | Palashbari | 864
P7-BP-S22-O | P7-BP-S22-O | 406.a/407.c | MPSB/MB/465 | Mb | 3 | 3 | 2025-12-08 | IPC - 25 | 1 | Palashbari | 864
P7-BP-S23-O | P7-BP-S23-O© | 406.a/407.c/408.c | MPSB/MB/477 | Mb | 1 | 3 | 2025-12-10 | IPC - 25 | 1 | Palashbari | 865
P7-BP-S23-O | P7-BP-S23-O© | 406.a/407.c/408.c | MPSB/Sur/2399 | Sur | 2 | 3 | 2025-12-12 | IPC - 25 | 1 | Palashbari | 865
P7-BP-S23-O | P7-BP-S23-O© | 406.a/407.c/408.c | MPSB/MB/489 | Mb | 3 | 3 | 2025-12-12 | IPC - 25 | 1 | Palashbari | 865
P7-BP-S24-O | P7-BP-S24-O | 406.a/407.c | MPSB/MB/502 | Mb | 1 | 3 | 2025-12-15 | IPC - 25 | 1 | Palashbari | 866
P7-BP-S24-O | P7-BP-S24-O | 406.a/407.c | MPSB/Sur/2421 | Sur | 2 | 3 | 2025-12-16 | IPC - 25 | 1 | Palashbari | 866
P7-BP-S24-O | P7-BP-S24-O | 406.a/407.c | MPSB/MB/510 | Mb | 3 | 3 | 2025-12-16 | IPC - 25 | 1 | Palashbari | 866
P7-BP-S25-O | P7-BP-S25-O© | 406.a/407.c/408.c | MPSB/MB/521 | Mb | 1 | 3 | 2025-12-18 | IPC - 25 | 1 | Palashbari | 867
P7-BP-S25-O | P7-BP-S25-O© | 406.a/407.c/408.c | MPSB/Sur/2449 | Sur | 2 | 3 | 2025-12-19 | IPC - 25 | 1 | Palashbari | 867
P7-BP-S25-O | P7-BP-S25-O© | 406.a/407.c/408.c | MPSB/MB/525 | Mb | 3 | 3 | 2025-12-19 | IPC - 25 | 1 | Palashbari | 867
P7-BP-S26-O | P7-BP-S26-O | 406.a/407.c | MPSB/MB/543 | Mb | 1 | 3 | 2025-12-23 | IPC - 25 | 1 | Palashbari | 868
P7-BP-S26-O | P7-BP-S26-O | 406.a/407.c | MPSB/Sur/2490 | Sur | 2 | 3 | 2025-12-24 | IPC - 25 | 1 | Palashbari | 868
P7-BP-S26-O | P7-BP-S26-O | 406.a/407.c | MPSB/MB/553 | Mb | 3 | 3 | 2025-12-24 | IPC - 25 | 1 | Palashbari | 868
P7-BP-S27-O | P7-BP-S27-O© | 406.a/407.c/408.c | MPSB/MB/578 | Mb | 1 | 3 | 2025-12-27 | IPC - 25 | 1 | Palashbari | 869
P7-BP-S27-O | P7-BP-S27-O© | 406.a/407.c/408.c | MPSB/Sur/2530 | Sur | 2 | 3 | 2025-12-29 | IPC - 25 | 1 | Palashbari | 869
P7-BP-S27-O | P7-BP-S27-O© | 406.a/407.c/408.c | MPSB/MB/583 | Mb | 3 | 3 | 2025-12-29 | IPC - 25 | 1 | Palashbari | 869
P7-KS-S13a-O | P7-KS-S13a-O© | 406.a/407.c/408.c | MPSB/MB/444 | Mb | 1 | 3 | 2025-12-04 | IPC - 25 | 1 | Palashbari | 870
P7-KS-S13a-O | P7-KS-S13a-O© | 406.a/407.c/408.c | MPSB/Sur/2344 | Sur | 2 | 3 | 2025-12-05 | IPC - 25 | 1 | Palashbari | 870
P7-KS-S13a-O | P7-KS-S13a-O© | 406.a/407.c/408.c | MPSB/MB/451 | Mb | 3 | 3 | 2025-12-05 | IPC - 25 | 1 | Palashbari | 870
P7-KS-S14a-O | P7-KS-S14a-O | 406.a/407.c | MPSB/MB/466 | Mb | 1 | 3 | 2025-12-08 | IPC - 25 | 1 | Palashbari | 871
P7-KS-S14a-O | P7-KS-S14a-O | 406.a/407.c | MPSB/Sur/2379 | Sur | 2 | 3 | 2025-12-10 | IPC - 25 | 1 | Palashbari | 871
P7-KS-S14a-O | P7-KS-S14a-O | 406.a/407.c | MPSB/MB/473 | Mb | 3 | 3 | 2025-12-10 | IPC - 25 | 1 | Palashbari | 871
P7-KS-S15a-O | P7-KS-S15a-O© | 406.a/407.c/408.c | MPSB/MB/484 | Mb | 1 | 3 | 2025-12-11 | IPC - 25 | 1 | Palashbari | 872
P7-KS-S15a-O | P7-KS-S15a-O© | 406.a/407.c/408.c | MPSB/Sur/2405 | Sur | 2 | 3 | 2025-12-13 | IPC - 25 | 1 | Palashbari | 872
P7-KS-S15a-O | P7-KS-S15a-O© | 406.a/407.c/408.c | MPSB/MB/493 | Mb | 3 | 3 | 2025-12-13 | IPC - 25 | 1 | Palashbari | 872
P7-KS-S16a-O | P7-KS-S16a-O | 406.a/407.c | MPSB/MB/501 | Mb | 1 | 3 | 2025-12-15 | IPC - 25 | 1 | Palashbari | 873
P7-KS-S16a-O | P7-KS-S16a-O | 406.a/407.c | MPSB/Sur/2428 | Sur | 2 | 3 | 2025-12-17 | IPC - 25 | 1 | Palashbari | 873
P7-KS-S16a-O | P7-KS-S16a-O | 406.a/407.c | MPSB/MB/514 | Mb | 3 | 3 | 2025-12-17 | IPC - 25 | 1 | Palashbari | 873
P7-KS-S17a-O | P7-KS-S17a-O© | 406.a/407.c/408.c | MPSB/MB/535 | Mb | 1 | 3 | 2025-12-22 | IPC - 25 | 1 | Palashbari | 874
P7-KS-S17a-O | P7-KS-S17a-O© | 406.a/407.c/408.c | MPSB/Sur/2491 | Sur | 2 | 3 | 2025-12-24 | IPC - 25 | 1 | Palashbari | 874
P7-KS-S17a-O | P7-KS-S17a-O© | 406.a/407.c/408.c | MPSB/MB/554 | Mb | 3 | 3 | 2025-12-24 | IPC - 25 | 1 | Palashbari | 874
P7-KS-S18a-O | P7-KS-S18a-O | 406.a/407.c | MPSB/MB/601 | Mb | 1 | 3 | 2025-12-30 | IPC - 25 | 1 | Palashbari | 875
P7-KS-S18a-O | P7-KS-S18a-O | 406.a/407.c | MPSB/Sur/2552 | Sur | 2 | 3 | 2025-12-30 | IPC - 25 | 1 | Palashbari | 875
P7-KS-S18a-O | P7-KS-S18a-O | 406.a/407.c | MPSB/MB/604 | Mb | 3 | 3 | 2025-12-30 | IPC - 25 | 1 | Palashbari | 875
P8-KS-S08-M | P8-KS-S08-M© | 406.a/407.c/408.c | MPSB/MB/530 | Mb | 1 | 3 | 2025-12-20 | IPC - 25 | 1 | Palashbari | 876
P8-KS-S08-M | P8-KS-S08-M© | 406.a/407.c/408.c | MPSB/Sur/2477 | Sur | 2 | 3 | 2025-12-23 | IPC - 25 | 1 | Palashbari | 876
P8-KS-S08-M | P8-KS-S08-M© | 406.a/407.c/408.c | MPSB/MB/542 | Mb | 3 | 3 | 2025-12-23 | IPC - 25 | 1 | Palashbari | 876
P8-KS-S09-M | P8-KS-S09-M | 406.a/407.c | MPSB/Sur/2516 | Sur | 1 | 2 | 2025-12-27 | IPC - 25 | 1 | Palashbari | 877
P8-KS-S09-M | P8-KS-S09-M | 406.a/407.c | MPSB/MB/577 | Mb | 2 | 2 | 2025-12-27 | IPC - 25 | 1 | Palashbari | 877
P23-KS-S22a-O | P23-KS-S22a-O | 406.a/407.c | MPSB/MB/819 | Mb | 1 | 3 | 2026-01-27 | IPC - 26 | 1 | Sualkuchi | 878
P23-KS-S22a-O | P23-KS-S22a-O | 406.a/407.c | MPSB/Sur/2786 | Sur | 2 | 3 | 2026-01-28 | IPC - 26 | 1 | Sualkuchi | 878
P23-KS-S22a-O | P23-KS-S22a-O | 406.a/407.c | MPSB/MB/826 | Mb | 3 | 3 | 2026-01-28 | IPC - 26 | 1 | Sualkuchi | 878
P23-KS-S23a-O | P23-KS-S23a-O© | 406.a/407.c/408.c | MPSB/MB/881 | Mb | 1 | 3 | 2026-01-31 | IPC - 26 | 1 | Sualkuchi | 879
P23-KS-S23a-O | P23-KS-S23a-O© | 406.a/407.c/408.c | MPSB/Sur/2838 | Sur | 2 | 3 | 2026-01-31 | IPC - 26 | 1 | Sualkuchi | 879
P23-KS-S23a-O | P23-KS-S23a-O© | 406.a/407.c/408.c | MPSB/MB/883 | Mb | 3 | 3 | 2026-01-31 | IPC - 26 | 1 | Sualkuchi | 879
P23-BP-S15-O | P23-BP-S15-O© | 406.a/407.c/408.c | MPSB/MB/644 | Mb | 1 | 3 | 2026-01-06 | IPC - 26 | 1 | Sualkuchi | 880
P23-BP-S15-O | P23-BP-S15-O© | 406.a/407.c/408.c | MPSB/Sur/2626 | Sur | 2 | 3 | 2026-01-08 | IPC - 26 | 1 | Sualkuchi | 880
P23-BP-S15-O | P23-BP-S15-O© | 406.a/407.c/408.c | MPSB/MB/676 | Mb | 3 | 3 | 2026-01-08 | IPC - 26 | 1 | Sualkuchi | 880
P23-BP-S16-O | P23-BP-S16-O | 406.a/407.c | MPSB/MB/688 | Mb | 1 | 3 | 2026-01-10 | IPC - 26 | 1 | Sualkuchi | 881
P23-BP-S16-O | P23-BP-S16-O | 406.a/407.c | MPSB/Sur/2661 | Sur | 2 | 3 | 2026-01-12 | IPC - 26 | 1 | Sualkuchi | 881
P23-BP-S16-O | P23-BP-S16-O | 406.a/407.c | MPSB/MB/697 | Mb | 3 | 3 | 2026-01-12 | IPC - 26 | 1 | Sualkuchi | 881
P23-BP-S17-O | P23-BP-S17-O© | 406.a/407.c/408.c | MPSB/MB/728 | Mb | 1 | 3 | 2026-01-14 | IPC - 26 | 1 | Sualkuchi | 882
P23-BP-S17-O | P23-BP-S17-O© | 406.a/407.c/408.c | MPSB/Sur/2693 | Sur | 2 | 3 | 2026-01-16 | IPC - 26 | 1 | Sualkuchi | 882
P23-BP-S17-O | P23-BP-S17-O© | 406.a/407.c/408.c | MPSB/MB/742 | Mb | 3 | 3 | 2026-01-16 | IPC - 26 | 1 | Sualkuchi | 882
P23-BP-S18-O | P23-BP-S18-O | 406.a/407.c | MPSB/MB/748 | Mb | 1 | 3 | 2026-01-17 | IPC - 26 | 1 | Sualkuchi | 883
P23-BP-S18-O | P23-BP-S18-O | 406.a/407.c | MPSB/Sur/2716 | Sur | 2 | 3 | 2026-01-19 | IPC - 26 | 1 | Sualkuchi | 883
P23-BP-S18-O | P23-BP-S18-O | 406.a/407.c | MPSB/MB/753 | Mb | 3 | 3 | 2026-01-19 | IPC - 26 | 1 | Sualkuchi | 883
P23-BP-S19-O | P23-BP-S19-O© | 406.a/407.c/408.c | MPSB/MB/791 | Mb | 1 | 3 | 2026-01-23 | IPC - 26 | 1 | Sualkuchi | 884
P23-BP-S19-O | P23-BP-S19-O© | 406.a/407.c/408.c | MPSB/Sur/2764 | Sur | 2 | 3 | 2026-01-24 | IPC - 26 | 1 | Sualkuchi | 884
P23-BP-S19-O | P23-BP-S19-O© | 406.a/407.c/408.c | MPSB/MB/797 | Mb | 3 | 3 | 2026-01-24 | IPC - 26 | 1 | Sualkuchi | 884
P23-BP-S20-O | P23-BP-S20-O | 406.a/407.c | MPSB/MB/843 | Mb | 1 | 3 | 2026-01-30 | IPC - 26 | 1 | Sualkuchi | 885
P23-BP-S20-O | P23-BP-S20-O | 406.a/407.c | MPSB/Sur/2820 | Sur | 2 | 3 | 2026-01-31 | IPC - 26 | 1 | Sualkuchi | 885
P23-BP-S20-O | P23-BP-S20-O | 406.a/407.c | MPSB/MB/847 | Mb | 3 | 3 | 2026-01-31 | IPC - 26 | 1 | Sualkuchi | 885
P25-KS-S26-O | P25-KS-S26-O | 406.a/407.c | MPSB/MB/610 | Mb | 1 | 3 | 2025-12-31 | IPC - 26 | 1 | Sualkuchi | 886
P25-KS-S26-O | P25-KS-S26-O | 406.a/407.c | MPSB/Sur/2594 | Sur | 2 | 3 | 2026-01-03 | IPC - 26 | 1 | Sualkuchi | 886
P25-KS-S26-O | P25-KS-S26-O | 406.a/407.c | MPSB/MB/618 | Mb | 3 | 3 | 2026-01-03 | IPC - 26 | 1 | Sualkuchi | 886
P25-KS-S27-O | P25-KS-S27-O© | 406.a/407.c/408.c | MPSB/MB/642 | Mb | 1 | 3 | 2026-01-05 | IPC - 26 | 1 | Sualkuchi | 887
P25-KS-S27-O | P25-KS-S27-O© | 406.a/407.c/408.c | MPSB/Sur/2614 | Sur | 2 | 3 | 2026-01-06 | IPC - 26 | 1 | Sualkuchi | 887
P25-KS-S27-O | P25-KS-S27-O© | 406.a/407.c/408.c | MPSB/MB/645 | Mb | 3 | 3 | 2026-01-06 | IPC - 26 | 1 | Sualkuchi | 887
P25-KS-S28-O | P25-KS-S28-O | 406.a/407.c | MPSB/Sur/2644 | Sur | 1 | 2 | 2026-01-09 | IPC - 26 | 1 | Sualkuchi | 888
P25-KS-S28-O | P25-KS-S28-O | 406.a/407.c | MPSB/MB/685 | Mb | 2 | 2 | 2026-01-09 | IPC - 26 | 1 | Sualkuchi | 888
P25-KS-S29-O | P25-KS-S29-O© | 406.a/407.c/408.c | MPSB/MB/696 | Mb | 1 | 3 | 2026-01-12 | IPC - 26 | 1 | Sualkuchi | 889
P25-KS-S29-O | P25-KS-S29-O© | 406.a/407.c/408.c | MPSB/Sur/2680 | Sur | 2 | 3 | 2026-01-14 | IPC - 26 | 1 | Sualkuchi | 889
P25-KS-S29-O | P25-KS-S29-O© | 406.a/407.c/408.c | MPSB/MB/729 | Mb | 3 | 3 | 2026-01-14 | IPC - 26 | 1 | Sualkuchi | 889
P25-KS-S30-O | P25-KS-S30-O | 406.a/407.c | MPSB/MB/747 | Mb | 1 | 3 | 2026-01-17 | IPC - 26 | 1 | Sualkuchi | 890
P25-KS-S30-O | P25-KS-S30-O | 406.a/407.c | MPSB/Sur/2706 | Sur | 2 | 3 | 2026-01-18 | IPC - 26 | 1 | Sualkuchi | 890
P25-KS-S30-O | P25-KS-S30-O | 406.a/407.c | MPSB/MB/751 | Mb | 3 | 3 | 2026-01-18 | IPC - 26 | 1 | Sualkuchi | 890
P25-KS-S31-O | P25-KS-S31-O© | 406.a/407.c/408.c | MPSB/MB/781 | Mb | 1 | 3 | 2026-01-22 | IPC - 26 | 1 | Sualkuchi | 891
P25-KS-S31-O | P25-KS-S31-O© | 406.a/407.c/408.c | MPSB/Sur/2749 | Sur | 2 | 3 | 2026-01-23 | IPC - 26 | 1 | Sualkuchi | 891
P25-KS-S31-O | P25-KS-S31-O© | 406.a/407.c/408.c | MPSB/MB/792 | Mb | 3 | 3 | 2026-01-23 | IPC - 26 | 1 | Sualkuchi | 891
P25-KS-S32-O | P25-KS-S32-O | 406.a/407.c | MPSB/MB/842 | Mb | 1 | 3 | 2026-01-30 | IPC - 26 | 1 | Sualkuchi | 892
P25-KS-S32-O | P25-KS-S32-O | 406.a/407.c | MPSB/Sur/2821 | Sur | 2 | 3 | 2026-01-31 | IPC - 26 | 1 | Sualkuchi | 892
P25-KS-S32-O | P25-KS-S32-O | 406.a/407.c | MPSB/MB/848 | Mb | 3 | 3 | 2026-01-31 | IPC - 26 | 1 | Sualkuchi | 892
P25-KS-S01-O | P25-KS-S01-O | 406.a/407.c | MPSB/MB/790 | Mb | 1 | 3 | 2026-01-23 | IPC - 26 | 1 | Sualkuchi | 893
P25-KS-S01-O | P25-KS-S01-O | 406.a/407.c | MPSB/Sur/2781 | Sur | 2 | 3 | 2026-01-27 | IPC - 26 | 1 | Sualkuchi | 893
P25-KS-S01-O | P25-KS-S01-O | 406.a/407.c | MPSB/MB/818 | Mb | 3 | 3 | 2026-01-27 | IPC - 26 | 1 | Sualkuchi | 893
P25-BP-S22a-O | P25-BP-S22a-O | 406.a/407.c | MPSB/MB/767 | Mb | 1 | 3 | 2026-01-20 | IPC - 26 | 1 | Sualkuchi | 894
P25-BP-S22a-O | P25-BP-S22a-O | 406.a/407.c | MPSB/Sur/2741 | Sur | 2 | 3 | 2026-01-22 | IPC - 26 | 1 | Sualkuchi | 894
P25-BP-S22a-O | P25-BP-S22a-O | 406.a/407.c | MPSB/MB/777 | Mb | 3 | 3 | 2026-01-22 | IPC - 26 | 1 | Sualkuchi | 894
P25-BP-S23a-O | P25-BP-S23a-O© | 406.a/407.c/408.c | MPSB/MB/820 | Mb | 1 | 3 | 2026-01-27 | IPC - 26 | 1 | Sualkuchi | 895
P25-BP-S23a-O | P25-BP-S23a-O© | 406.a/407.c/408.c | MPSB/Sur/2787 | Sur | 2 | 3 | 2026-01-28 | IPC - 26 | 1 | Sualkuchi | 895
P25-BP-S23a-O | P25-BP-S23a-O© | 406.a/407.c/408.c | MPSB/MB/827 | Mb | 3 | 3 | 2026-01-28 | IPC - 26 | 1 | Sualkuchi | 895
P25-BP-S24a-O | P25-BP-S24a-O | 406.a/407.c | MPSB/MB/882 | Mb | 1 | 3 | 2026-01-31 | IPC - 26 | 1 | Sualkuchi | 896
P25-BP-S24a-O | P25-BP-S24a-O | 406.a/407.c | MPSB/Sur/2839 | Sur | 2 | 3 | 2026-01-31 | IPC - 26 | 1 | Sualkuchi | 896
P25-BP-S24a-O | P25-BP-S24a-O | 406.a/407.c | MPSB/MB/884 | Mb | 3 | 3 | 2026-01-31 | IPC - 26 | 1 | Sualkuchi | 896
P6-BP-S01a-E | P6-BP-S01a-E | 406.a/407.c | MPSB/Sur/2672 | Sur | 1 | 2 | 2026-01-13 | IPC - 26 | 1 | Palashbari | 897
P6-BP-S01a-E | P6-BP-S01a-E | 406.a/407.c | MPSB/MB/712 | Mb | 2 | 2 | 2026-01-13 | IPC - 26 | 1 | Palashbari | 897
P6-BP-S01-E | P6-BP-S01-E | 406.a/407.c | MPSB/MB/735 | Mb | 1 | 3 | 2026-01-15 | IPC - 26 | 1 | Palashbari | 898
P6-BP-S01-E | P6-BP-S01-E | 406.a/407.c | MPSB/Sur/2690 | Sur | 2 | 3 | 2026-01-16 | IPC - 26 | 1 | Palashbari | 898
P6-BP-S01-E | P6-BP-S01-E | 406.a/407.c | MPSB/MB/737 | Mb | 3 | 3 | 2026-01-16 | IPC - 26 | 1 | Palashbari | 898
P6-BP-S02-E | P6-BP-S02-E | 406.a/407.c | MPSB/MB/756 | Mb | 1 | 3 | 2026-01-19 | IPC - 26 | 1 | Palashbari | 899
P6-BP-S02-E | P6-BP-S02-E | 406.a/407.c | MPSB/Sur/2721 | Sur | 2 | 3 | 2026-01-20 | IPC - 26 | 1 | Palashbari | 899
P6-BP-S02-E | P6-BP-S02-E | 406.a/407.c | MPSB/MB/763 | Mb | 3 | 3 | 2026-01-20 | IPC - 26 | 1 | Palashbari | 899
P6-BP-S03-E | P6-BP-S03-E | 406.a/407.c | MPSB/MB/789 | Mb | 1 | 3 | 2026-01-23 | IPC - 26 | 1 | Palashbari | 900
P6-BP-S03-E | P6-BP-S03-E | 406.a/407.c | MPSB/Sur/2776 | Sur | 2 | 3 | 2026-01-27 | IPC - 26 | 1 | Palashbari | 900
P6-BP-S03-E | P6-BP-S03-E | 406.a/407.c | MPSB/MB/810 | Mb | 3 | 3 | 2026-01-27 | IPC - 26 | 1 | Palashbari | 900
P6-BP-S04-E | P6-BP-S04-E | 406.a/407.c | MPSB/Sur/2815 | Sur | 1 | 2 | 2026-01-30 | IPC - 26 | 1 | Palashbari | 901
P6-BP-S04-E | P6-BP-S04-E | 406.a/407.c | MPSB/MB/841 | Mb | 2 | 2 | 2026-01-30 | IPC - 26 | 1 | Palashbari | 901
P7-KS-S23a-O | P7-KS-S23a-O© | 406.a/407.c/408.c | MPSB/MB/833 | Mb | 1 | 3 | 2026-01-29 | IPC - 26 | 1 | Palashbari | 902
P7-KS-S23a-O | P7-KS-S23a-O© | 406.a/407.c/408.c | MPSB/Sur/2813 | Sur | 2 | 3 | 2026-01-30 | IPC - 26 | 1 | Palashbari | 902
P7-KS-S23a-O | P7-KS-S23a-O© | 406.a/407.c/408.c | MPSB/MB/838 | Mb | 3 | 3 | 2026-01-30 | IPC - 26 | 1 | Palashbari | 902
P7-KS-S22a-O | P7-KS-S22a-O | 406.a/407.c | MPSB/MB/806 | Mb | 1 | 3 | 2026-01-25 | IPC - 26 | 1 | Palashbari | 903
P7-KS-S22a-O | P7-KS-S22a-O | 406.a/407.c | MPSB/Sur/2777 | Sur | 2 | 3 | 2026-01-27 | IPC - 26 | 1 | Palashbari | 903
P7-KS-S22a-O | P7-KS-S22a-O | 406.a/407.c | MPSB/MB/811 | Mb | 3 | 3 | 2026-01-27 | IPC - 26 | 1 | Palashbari | 903
P7-KS-S21a-O | P7-KS-S21a-O© | 406.a/407.c/408.c | MPSB/MB/726 | Mb | 1 | 3 | 2026-01-14 | IPC - 26 | 1 | Palashbari | 904
P7-KS-S21a-O | P7-KS-S21a-O© | 406.a/407.c/408.c | MPSB/Sur/2692 | Sur | 2 | 3 | 2026-01-16 | IPC - 26 | 1 | Palashbari | 904
P7-KS-S21a-O | P7-KS-S21a-O© | 406.a/407.c/408.c | MPSB/MB/739 | Mb | 3 | 3 | 2026-01-16 | IPC - 26 | 1 | Palashbari | 904
P7-KS-S20a-O | P7-KS-S20a-O | 406.a/407.c | MPSB/MB/686 | Mb | 1 | 3 | 2026-01-10 | IPC - 26 | 1 | Palashbari | 905
P7-KS-S20a-O | P7-KS-S20a-O | 406.a/407.c | MPSB/Sur/2662 | Sur | 2 | 3 | 2026-01-12 | IPC - 26 | 1 | Palashbari | 905
P7-KS-S20a-O | P7-KS-S20a-O | 406.a/407.c | MPSB/MB/700 | Mb | 3 | 3 | 2026-01-12 | IPC - 26 | 1 | Palashbari | 905
P7-KS-S19a-O | P7-KS-S19a-O© | 406.a/407.c/408.c | MPSB/MB/630 | Mb | 1 | 3 | 2026-01-05 | IPC - 26 | 1 | Palashbari | 906
P7-KS-S19a-O | P7-KS-S19a-O© | 406.a/407.c/408.c | MPSB/Sur/2615 | Sur | 2 | 3 | 2026-01-06 | IPC - 26 | 1 | Palashbari | 906
P7-KS-S19a-O | P7-KS-S19a-O© | 406.a/407.c/408.c | MPSB/MB/654 | Mb | 3 | 3 | 2026-01-06 | IPC - 26 | 1 | Palashbari | 906
P7-KS-S08a-O | P7-KS-S08a-O | 406.a/407.c | MPSB/MB/831 | Mb | 1 | 3 | 2026-01-29 | IPC - 26 | 1 | Palashbari | 907
P7-KS-S08a-O | P7-KS-S08a-O | 406.a/407.c | MPSB/Sur/2814 | Sur | 2 | 3 | 2026-01-30 | IPC - 26 | 1 | Palashbari | 907
P7-KS-S08a-O | P7-KS-S08a-O | 406.a/407.c | MPSB/MB/839 | Mb | 3 | 3 | 2026-01-30 | IPC - 26 | 1 | Palashbari | 907
P7-KS-S07a-O | P7-KS-S07a-O | 406.a/407.c | MPSB/MB/787 | Mb | 1 | 3 | 2026-01-23 | IPC - 26 | 1 | Palashbari | 908
P7-KS-S07a-O | P7-KS-S07a-O | 406.a/407.c | MPSB/Sur/2762 | Sur | 2 | 3 | 2026-01-24 | IPC - 26 | 1 | Palashbari | 908
P7-KS-S07a-O | P7-KS-S07a-O | 406.a/407.c | MPSB/MB/793 | Mb | 3 | 3 | 2026-01-24 | IPC - 26 | 1 | Palashbari | 908
P7-KS-S06a-O | P7-KS-S06a-O | 406.a/407.c | MPSB/MB/755 | Mb | 1 | 3 | 2026-01-19 | IPC - 26 | 1 | Palashbari | 909
P7-KS-S06a-O | P7-KS-S06a-O | 406.a/407.c | MPSB/Sur/2722 | Sur | 2 | 3 | 2026-01-20 | IPC - 26 | 1 | Palashbari | 909
P7-KS-S06a-O | P7-KS-S06a-O | 406.a/407.c | MPSB/MB/764 | Mb | 3 | 3 | 2026-01-20 | IPC - 26 | 1 | Palashbari | 909
P7-KS-S05a-O | P7-KS-S05a-O | 406.a/407.c | MPSB/MB/734 | Mb | 1 | 3 | 2026-01-15 | IPC - 26 | 1 | Palashbari | 910
P7-KS-S05a-O | P7-KS-S05a-O | 406.a/407.c | MPSB/Sur/2691 | Sur | 2 | 3 | 2026-01-16 | IPC - 26 | 1 | Palashbari | 910
P7-KS-S05a-O | P7-KS-S05a-O | 406.a/407.c | MPSB/MB/738 | Mb | 3 | 3 | 2026-01-16 | IPC - 26 | 1 | Palashbari | 910
P7-KS-S04a-O | P7-KS-S04a-O | 406.a/407.c | MPSB/MB/710 | Mb | 1 | 3 | 2026-01-13 | IPC - 26 | 1 | Palashbari | 911
P7-KS-S04a-O | P7-KS-S04a-O | 406.a/407.c | MPSB/Sur/2671 | Sur | 2 | 3 | 2026-01-13 | IPC - 26 | 1 | Palashbari | 911
P7-KS-S04a-O | P7-KS-S04a-O | 406.a/407.c | MPSB/MB/711 | Mb | 3 | 3 | 2026-01-13 | IPC - 26 | 1 | Palashbari | 911
P7-KS-S03a-O | P7-KS-S03a-O | 406.a/407.c | MPSB/MB/665 | Mb | 1 | 3 | 2026-01-08 | IPC - 26 | 1 | Palashbari | 912
P7-KS-S03a-O | P7-KS-S03a-O | 406.a/407.c | MPSB/Sur/2665 | Sur | 2 | 3 | 2026-01-11 | IPC - 26 | 1 | Palashbari | 912
P7-KS-S03a-O | P7-KS-S03a-O | 406.a/407.c | MPSB/MB/695 | Mb | 3 | 3 | 2026-01-11 | IPC - 26 | 1 | Palashbari | 912
P7-KS-S02a-O | P7-KS-S02a-O | 406.a/407.c | MPSB/MB/628 | Mb | 1 | 3 | 2026-01-04 | IPC - 26 | 1 | Palashbari | 913
P7-KS-S02a-O | P7-KS-S02a-O | 406.a/407.c | MPSB/Sur/2611 | Sur | 2 | 3 | 2026-01-05 | IPC - 26 | 1 | Palashbari | 913
P7-KS-S02a-O | P7-KS-S02a-O | 406.a/407.c | MPSB/MB/636 | Mb | 3 | 3 | 2026-01-05 | IPC - 26 | 1 | Palashbari | 913
P7-KS-S01a-O | P7-KS-S01a-O | 406.a/407.c | MPSB/MB/603 | Mb | 1 | 3 | 2026-12-30 | IPC - 26 | 1 | Palashbari | 914
P7-KS-S01a-O | P7-KS-S01a-O | 406.a/407.c | MPSB/Sur/2587 | Sur | 2 | 3 | 2026-01-02 | IPC - 26 | 1 | Palashbari | 914
P7-KS-S01a-O | P7-KS-S01a-O | 406.a/407.c | MPSB/MB/615 | Mb | 3 | 3 | 2026-01-02 | IPC - 26 | 1 | Palashbari | 914
P7-BP-S28-O | P7-BP-S28-O | 406.a/407.c | MPSB/MB/602 | Mb | 1 | 3 | 2026-12-30 | IPC - 26 | 1 | Palashbari | 915
P7-BP-S28-O | P7-BP-S28-O | 406.a/407.c | MPSB/Sur/2586 | Sur | 2 | 3 | 2026-01-02 | IPC - 26 | 1 | Palashbari | 915
P7-BP-S28-O | P7-BP-S28-O | 406.a/407.c | MPSB/MB/614 | Mb | 3 | 3 | 2026-01-02 | IPC - 26 | 1 | Palashbari | 915
P7-BP-S29-O | P7-BP-S29-O© | 406.a/407.c/408.c | MPSB/MB/629 | Mb | 1 | 3 | 2026-01-05 | IPC - 26 | 1 | Palashbari | 916
P7-BP-S29-O | P7-BP-S29-O© | 406.a/407.c/408.c | MPSB/Sur/2616 | Sur | 2 | 3 | 2026-01-06 | IPC - 26 | 1 | Palashbari | 916
P7-BP-S29-O | P7-BP-S29-O© | 406.a/407.c/408.c | MPSB/MB/655 | Mb | 3 | 3 | 2026-01-06 | IPC - 26 | 1 | Palashbari | 916
P7-BP-S30-O | P7-BP-S30-O | 406.a/407.c | MPSB/MB/657 | Mb | 1 | 3 | 2026-01-07 | IPC - 26 | 1 | Palashbari | 917
P7-BP-S30-O | P7-BP-S30-O | 406.a/407.c | MPSB/Sur/2639 | Sur | 2 | 3 | 2026-01-09 | IPC - 26 | 1 | Palashbari | 917
P7-BP-S30-O | P7-BP-S30-O | 406.a/407.c | MPSB/MB/678 | Mb | 3 | 3 | 2026-01-09 | IPC - 26 | 1 | Palashbari | 917
P7-BP-S31-O | P7-BP-S31-O© | 406.a/407.c/408.c | MPSB/MB/689 | Mb | 1 | 3 | 2026-01-11 | IPC - 26 | 1 | Palashbari | 918
P7-BP-S31-O | P7-BP-S31-O© | 406.a/407.c/408.c | MPSB/Sur/2679 | Sur | 2 | 3 | 2026-01-14 | IPC - 26 | 1 | Palashbari | 918
P7-BP-S31-O | P7-BP-S31-O© | 406.a/407.c/408.c | MPSB/MB/727 | Mb | 3 | 3 | 2026-01-14 | IPC - 26 | 1 | Palashbari | 918
P7-BP-S32-O | P7-BP-S32-O | 406.a/407.c | MPSB/MB/741 | Mb | 1 | 3 | 2026-01-16 | IPC - 26 | 1 | Palashbari | 919
P7-BP-S32-O | P7-BP-S32-O | 406.a/407.c | MPSB/Sur/2719 | Sur | 2 | 3 | 2026-01-19 | IPC - 26 | 1 | Palashbari | 919
P7-BP-S32-O | P7-BP-S32-O | 406.a/407.c | MPSB/MB/757 | Mb | 3 | 3 | 2026-01-19 | IPC - 26 | 1 | Palashbari | 919
P7-BP-S33-O | P7-BP-S33-O© | 406.a/407.c/408.c | MPSB/MB/770 | Mb | 1 | 3 | 2026-01-21 | IPC - 26 | 1 | Palashbari | 920
P7-BP-S33-O | P7-BP-S33-O© | 406.a/407.c/408.c | MPSB/Sur/2739 | Sur | 2 | 3 | 2026-01-22 | IPC - 26 | 1 | Palashbari | 920
P7-BP-S33-O | P7-BP-S33-O© | 406.a/407.c/408.c | MPSB/MB/774 | Mb | 3 | 3 | 2026-01-22 | IPC - 26 | 1 | Palashbari | 920
P7-BP-S34-O | P7-BP-S34-O | 406.a/407.c | MPSB/MB/808 | Mb | 1 | 3 | 2026-01-25 | IPC - 26 | 1 | Palashbari | 921
P7-BP-S34-O | P7-BP-S34-O | 406.a/407.c | MPSB/Sur/2797 | Sur | 2 | 3 | 2026-01-29 | IPC - 26 | 1 | Palashbari | 921
P7-BP-S34-O | P7-BP-S34-O | 406.a/407.c | MPSB/MB/829 | Mb | 3 | 3 | 2026-01-29 | IPC - 26 | 1 | Palashbari | 921
P8-KS-S16-M | P8-KS-S16-M© | 406.a/407.c | MPSB/MB/854 | Mb | 1 | 3 | 2026-01-31 | IPC - 26 | 1 | Palashbari | 922
P8-KS-S16-M | P8-KS-S16-M© | 406.a/407.c | MPSB/Sur/2831 | Sur | 2 | 3 | 2026-01-31 | IPC - 26 | 1 | Palashbari | 922
P8-KS-S16-M | P8-KS-S16-M© | 406.a/407.c | MPSB/MB/874 | Mb | 3 | 3 | 2026-01-31 | IPC - 26 | 1 | Palashbari | 922
P8-KS-S15-M | P8-KS-S15-M | 406.a/407.c | MPSB/MB/807 | Mb | 1 | 3 | 2026-01-25 | IPC - 26 | 1 | Palashbari | 923
P8-KS-S15-M | P8-KS-S15-M | 406.a/407.c | MPSB/Sur/2798 | Sur | 2 | 3 | 2026-01-29 | IPC - 26 | 1 | Palashbari | 923
P8-KS-S15-M | P8-KS-S15-M | 406.a/407.c | MPSB/MB/830 | Mb | 3 | 3 | 2026-01-29 | IPC - 26 | 1 | Palashbari | 923
P8-KS-S14-M | P8-KS-S14-M© | 406.a/407.c/408.c | MPSB/MB/769 | Mb | 1 | 3 | 2026-01-21 | IPC - 26 | 1 | Palashbari | 924
P8-KS-S14-M | P8-KS-S14-M© | 406.a/407.c/408.c | MPSB/Sur/2740 | Sur | 2 | 3 | 2026-01-22 | IPC - 26 | 1 | Palashbari | 924
P8-KS-S14-M | P8-KS-S14-M© | 406.a/407.c/408.c | MPSB/MB/775 | Mb | 3 | 3 | 2026-01-22 | IPC - 26 | 1 | Palashbari | 924
P8-KS-S13-M | P8-KS-S13-M | 406.a/407.c | MPSB/MB/745 | Mb | 1 | 3 | 2026-01-17 | IPC - 26 | 1 | Palashbari | 925
P8-KS-S13-M | P8-KS-S13-M | 406.a/407.c | MPSB/Sur/2720 | Sur | 2 | 3 | 2026-01-19 | IPC - 26 | 1 | Palashbari | 925
P8-KS-S13-M | P8-KS-S13-M | 406.a/407.c | MPSB/MB/758 | Mb | 3 | 3 | 2026-01-19 | IPC - 26 | 1 | Palashbari | 925
P8-KS-S12-M | P8-KS-S12-M© | 406.a/407.c/408.c | MPSB/MB/705 | Mb | 1 | 3 | 2026-01-12 | IPC - 26 | 1 | Palashbari | 926
P8-KS-S12-M | P8-KS-S12-M© | 406.a/407.c/408.c | MPSB/Sur/2678 | Sur | 2 | 3 | 2026-01-14 | IPC - 26 | 1 | Palashbari | 926
P8-KS-S12-M | P8-KS-S12-M© | 406.a/407.c/408.c | MPSB/MB/721 | Mb | 3 | 3 | 2026-01-14 | IPC - 26 | 1 | Palashbari | 926
P8-KS-S11-M | P8-KS-S11-M | 406.a/407.c | MPSB/MB/656 | Mb | 1 | 3 | 2026-01-07 | IPC - 26 | 1 | Palashbari | 927
P8-KS-S11-M | P8-KS-S11-M | 406.a/407.c | MPSB/Sur/2625 | Sur | 2 | 3 | 2026-01-08 | IPC - 26 | 1 | Palashbari | 927
P8-KS-S11-M | P8-KS-S11-M | 406.a/407.c | MPSB/MB/666 | Mb | 3 | 3 | 2026-01-08 | IPC - 26 | 1 | Palashbari | 927
P8-KS-S10-M | P8-KS-S10-M© | 406.a/407.c/408.c | MPSB/MB/619 | Mb | 1 | 3 | 2026-01-03 | IPC - 26 | 1 | Palashbari | 928
P8-KS-S10-M | P8-KS-S10-M© | 406.a/407.c/408.c | MPSB/Sur/2610 | Sur | 2 | 3 | 2026-01-05 | IPC - 26 | 1 | Palashbari | 928
P8-KS-S10-M | P8-KS-S10-M© | 406.a/407.c/408.c | MPSB/MB/631 | Mb | 3 | 3 | 2026-01-05 | IPC - 26 | 1 | Palashbari | 928
P6-BP-S05-E | P6-BP-S05-E | 406.a/407.c | MPSB/MB/853 | Mb | 1 | 3 | 2026-01-31 | IPC - 27 | 1 | Palashbari | 929
P6-BP-S05-E | P6-BP-S05-E | 406.a/407.c | MPSB/Sur/2850 | Sur | 2 | 3 | 2026-02-03 | IPC - 27 | 1 | Palashbari | 929
P6-BP-S05-E | P6-BP-S05-E | 406.a/407.c | MPSB/MB/892 | Mb | 3 | 3 | 2026-02-03 | IPC - 27 | 1 | Palashbari | 929
P6-BP-S06-E | P6-BP-S06-E | 406.a/407.c | MPSB/MB/910 | Mb | 1 | 3 | 2026-02-05 | IPC - 27 | 1 | Palashbari | 930
P6-BP-S06-E | P6-BP-S06-E | 406.a/407.c | MPSB/Sur/2888 | Sur | 2 | 3 | 2026-02-08 | IPC - 27 | 1 | Palashbari | 930
P6-BP-S06-E | P6-BP-S06-E | 406.a/407.c | MPSB/MB/937 | Mb | 3 | 3 | 2026-02-08 | IPC - 27 | 1 | Palashbari | 930
P7-KS-S24a-O | P7-KS-S24a-O | 406.a/407.c | MPSB/MB/867 | Mb | 1 | 3 | 2026-01-31 | IPC - 27 | 1 | Palashbari | 931
P7-KS-S24a-O | P7-KS-S24a-O | 406.a/407.c | MPSB/Sur/2832 | Sur | 2 | 3 | 2026-01-31 | IPC - 27 | 1 | Palashbari | 931
P7-KS-S24a-O | P7-KS-S24a-O | 406.a/407.c | MPSB/MB/875 | Mb | 3 | 3 | 2026-01-31 | IPC - 27 | 1 | Palashbari | 931
P7-KS-S25a-O | P7-KS-S25a-O© | 406.a/407.c/408.c | MPSB/MB/931 | Mb | 1 | 3 | 2026-02-07 | IPC - 27 | 1 | Palashbari | 932
P7-KS-S25a-O | P7-KS-S25a-O© | 406.a/407.c/408.c | MPSB/Sur/2896 | Sur | 2 | 3 | 2026-02-09 | IPC - 27 | 1 | Palashbari | 932
P7-KS-S25a-O | P7-KS-S25a-O© | 406.a/407.c/408.c | MPSB/MB/942 | Mb | 3 | 3 | 2026-02-09 | IPC - 27 | 1 | Palashbari | 932
P7-KS-S26a-O | P7-KS-S26a-O | 406.a/407.c | MPSB/MB/980 | Mb | 1 | 3 | 2026-02-13 | IPC - 27 | 1 | Palashbari | 933
P7-KS-S26a-O | P7-KS-S26a-O | 406.a/407.c | MPSB/Sur/2941 | Sur | 2 | 3 | 2026-02-16 | IPC - 27 | 1 | Palashbari | 933
P7-KS-S26a-O | P7-KS-S26a-O | 406.a/407.c | MPSB/MB/999 | Mb | 3 | 3 | 2026-02-16 | IPC - 27 | 1 | Palashbari | 933
P7-KS-S27a-O | P7-KS-S27a-O© | 406.a/407.c/408.c | MPSB/MB/1000 | Mb | 1 | 3 | 2026-02-16 | IPC - 27 | 1 | Palashbari | 934
P7-KS-S27a-O | P7-KS-S27a-O© | 406.a/407.c/408.c | MPSB/Sur/2959 | Sur | 2 | 3 | 2026-02-19 | IPC - 27 | 1 | Palashbari | 934
P7-KS-S27a-O | P7-KS-S27a-O© | 406.a/407.c/408.c | MPSB/MB/1030 | Mb | 3 | 3 | 2026-02-19 | IPC - 27 | 1 | Palashbari | 934
P7-KS-S28a-O | P7-KS-S28a-O | 406.a/407.c | MPSB/MB/923 | Mb | 1 | 3 | 2026-02-06 | IPC - 27 | 1 | Palashbari | 935
P7-KS-S28a-O | P7-KS-S28a-O | 406.a/407.c | MPSB/Sur/2987 | Sur | 2 | 3 | 2026-02-24 | IPC - 27 | 1 | Palashbari | 935
P7-KS-S28a-O | P7-KS-S28a-O | 406.a/407.c | MPSB/MB/1073 | Mb | 3 | 3 | 2026-02-24 | IPC - 27 | 1 | Palashbari | 935
P7-KS-S29a-O | P7-KS-S29a-O© | 406.a/407.c/408.c | MPSB/MB/1082 | Mb | 1 | 3 | 2026-02-25 | IPC - 27 | 1 | Palashbari | 936
P7-KS-S29a-O | P7-KS-S29a-O© | 406.a/407.c/408.c | MPSB/Sur/3011 | Sur | 2 | 3 | 2026-02-26 | IPC - 27 | 1 | Palashbari | 936
P7-KS-S29a-O | P7-KS-S29a-O© | 406.a/407.c/408.c | MPSB/MB/1089 | Mb | 3 | 3 | 2026-02-26 | IPC - 27 | 1 | Palashbari | 936
P8-KS-S17-M | P8-KS-S17-M | 406.a/407.c | MPSB/MB/912 | Mb | 1 | 3 | 2026-02-05 | IPC - 27 | 1 | Palashbari | 937
P8-KS-S17-M | P8-KS-S17-M | 406.a/407.c | MPSB/Sur/2882 | Sur | 2 | 3 | 2026-02-07 | IPC - 27 | 1 | Palashbari | 937
P8-KS-S17-M | P8-KS-S17-M | 406.a/407.c | MPSB/MB/932 | Mb | 3 | 3 | 2026-02-07 | IPC - 27 | 1 | Palashbari | 937
P8-KS-S18-M | P8-KS-S18-M | 406.a/407.c | MPSB/MB/943 | Mb | 1 | 3 | 2026-02-09 | IPC - 27 | 1 | Palashbari | 938 | P9-KS-S01-O
P8-KS-S18-M | P8-KS-S18-M | 406.a/407.c | MPSB/Sur/2930 | Sur | 2 | 3 | 2026-02-14 | IPC - 27 | 1 | Palashbari | 938
P8-KS-S18-M | P8-KS-S18-M | 406.a/407.c | MPSB/MB/989 | Mb | 3 | 3 | 2026-02-14 | IPC - 27 | 1 | Palashbari | 938
P8-BP-S08-M | P8-BP-S08-M© | 406.a/407.c/408.c | MPSB/MB/1048 | Mb | 1 | 3 | 2026-02-23 | IPC - 27 | 1 | Palashbari | 939
P8-BP-S08-M | P8-BP-S08-M© | 406.a/407.c/408.c | MPSB/Sur/3005 | Sur | 2 | 3 | 2026-02-25 | IPC - 27 | 1 | Palashbari | 939
P8-BP-S08-M | P8-BP-S08-M© | 406.a/407.c/408.c | MPSB/MB/1081 | Mb | 3 | 3 | 2026-02-25 | IPC - 27 | 1 | Palashbari | 939
P8-BP-S09-M | P8-BP-S09-M | 406.a/407.c | MPSB/MB/1095 | Mb | 1 | 3 | 2026-02-26 | IPC - 27 | 1 | Palashbari | 940
P8-BP-S09-M | P8-BP-S09-M | 406.a/407.c | MPSB/Sur/3023 | Sur | 2 | 3 | 2026-02-27 | IPC - 27 | 1 | Palashbari | 940
P8-BP-S09-M | P8-BP-S09-M | 406.a/407.c | MPSB/MB/1101 | Mb | 3 | 3 | 2026-02-27 | IPC - 27 | 1 | Palashbari | 940
P9-KS-S01-O | P9-KS-S01-O | 406.a/407.c | MPSB/MB/943 | Mb | 1 | 3 | 2026-02-09 | IPC - 27 | 1 | Palashbari | 941 | P8-KS-S18-M
P9-KS-S01-O | P9-KS-S01-O | 406.a/407.c | MPSB/Sur/2859 | Sur | 2 | 3 | 2026-02-05 | IPC - 27 | 1 | Palashbari | 941
P9-KS-S01-O | P9-KS-S01-O | 406.a/407.c | MPSB/MB/911 | Mb | 3 | 3 | 2026-02-05 | IPC - 27 | 1 | Palashbari | 941
P9-KS-S02-O | P9-KS-S02-O | 406.a/407.c | MPSB/MB/944 | Mb | 1 | 3 | 2026-02-09 | IPC - 27 | 1 | Palashbari | 942
P9-KS-S02-O | P9-KS-S02-O | 406.a/407.c | MPSB/Sur/2917 | Sur | 2 | 3 | 2026-02-11 | IPC - 27 | 1 | Palashbari | 942
P9-KS-S02-O | P9-KS-S02-O | 406.a/407.c | MPSB/MB/964 | Mb | 3 | 3 | 2026-02-11 | IPC - 27 | 1 | Palashbari | 942
P9-KS-S03-O | P9-KS-S03-O | 406.a/407.c | MPSB/MB/1003 | Mb | 1 | 3 | 2026-02-17 | IPC - 27 | 1 | Palashbari | 943
P9-KS-S03-O | P9-KS-S03-O | 406.a/407.c | MPSB/Sur/2946 | Sur | 2 | 3 | 2026-02-17 | IPC - 27 | 1 | Palashbari | 943
P9-KS-S03-O | P9-KS-S03-O | 406.a/407.c | MPSB/MB/1009 | Mb | 3 | 3 | 2026-02-17 | IPC - 27 | 1 | Palashbari | 943
P9-KS-S04-O | P9-KS-S04-O | 406.a/407.c | MPSB/MB/1028 | Mb | 1 | 3 | 2026-02-19 | IPC - 27 | 1 | Palashbari | 944
P9-KS-S04-O | P9-KS-S04-O | 406.a/407.c | MPSB/Sur/2975 | Sur | 2 | 3 | 2026-02-21 | IPC - 27 | 1 | Palashbari | 944
P9-KS-S04-O | P9-KS-S04-O | 406.a/407.c | MPSB/MB/1042 | Mb | 3 | 3 | 2026-02-21 | IPC - 27 | 1 | Palashbari | 944
P9-KS-S05-O | P9-KS-S05-O | 406.a/407.c | MPSB/MB/1050 | Mb | 1 | 3 | 2026-02-23 | IPC - 27 | 1 | Palashbari | 945
P9-KS-S05-O | P9-KS-S05-O | 406.a/407.c | MPSB/Sur/3004 | Sur | 2 | 3 | 2026-02-25 | IPC - 27 | 1 | Palashbari | 945
P9-KS-S05-O | P9-KS-S05-O | 406.a/407.c | MPSB/MB/1080 | Mb | 3 | 3 | 2026-02-25 | IPC - 27 | 1 | Palashbari | 945
P9-KS-S06-O | P9-KS-S06-O | 406.a/407.c | MPSB/MB/1091 | Mb | 1 | 3 | 2026-02-26 | IPC - 27 | 1 | Palashbari | 946
P9-KS-S06-O | P9-KS-S06-O | 406.a/407.c | MPSB/Sur/3013 | Sur | 2 | 3 | 2026-02-26 | IPC - 27 | 1 | Palashbari | 946
P9-KS-S06-O | P9-KS-S06-O | 406.a/407.c | MPSB/MB/1096 | Mb | 3 | 3 | 2026-02-26 | IPC - 27 | 1 | Palashbari | 946
P9-KS-S07-O | P9-KS-S07-O | 406.a/407.c | MPSB/MB/1102 | Mb | 1 | 3 | 2026-02-27 | IPC - 27 | 1 | Palashbari | 947
P9-KS-S07-O | P9-KS-S07-O | 406.a/407.c | MPSB/Sur/3049 | Sur | 2 | 3 | 2026-02-28 | IPC - 27 | 1 | Palashbari | 947
P9-KS-S07-O | P9-KS-S07-O | 406.a/407.c | MPSB/MB/1126 | Mb | 3 | 3 | 2026-02-28 | IPC - 27 | 1 | Palashbari | 947
P9-BP-S09a-O | P9-BP-S09a-O© | 406.a/407.c/408.c | MPSB/MB/930 | Mb | 1 | 3 | 2026-02-07 | IPC - 27 | 1 | Palashbari | 948
P9-BP-S09a-O | P9-BP-S09a-O© | 406.a/407.c/408.c | MPSB/Sur/2895 | Sur | 2 | 3 | 2026-02-09 | IPC - 27 | 1 | Palashbari | 948
P9-BP-S09a-O | P9-BP-S09a-O© | 406.a/407.c/408.c | MPSB/MB/941 | Mb | 3 | 3 | 2026-02-09 | IPC - 27 | 1 | Palashbari | 948
P9-BP-S10a-O | P9-BP-S10a-O | 406.a/407.c | MPSB/MB/895 | Mb | 1 | 3 | 2026-02-03 | IPC - 27 | 1 | Palashbari | 949
P9-BP-S10a-O | P9-BP-S10a-O | 406.a/407.c | MPSB/Sur/2929 | Sur | 2 | 3 | 2026-02-14 | IPC - 27 | 1 | Palashbari | 949
P9-BP-S10a-O | P9-BP-S10a-O | 406.a/407.c | MPSB/MB/988 | Mb | 3 | 3 | 2026-02-14 | IPC - 27 | 1 | Palashbari | 949
P9-BP-S11a-O | P9-BP-S11a-O© | 406.a/407.c/408.c | MPSB/MB/1002 | Mb | 1 | 3 | 2026-02-17 | IPC - 27 | 1 | Palashbari | 950
P9-BP-S11a-O | P9-BP-S11a-O© | 406.a/407.c/408.c | MPSB/Sur/2945 | Sur | 2 | 3 | 2026-02-17 | IPC - 27 | 1 | Palashbari | 950
P9-BP-S11a-O | P9-BP-S11a-O© | 406.a/407.c/408.c | MPSB/MB/1008 | Mb | 3 | 3 | 2026-02-17 | IPC - 27 | 1 | Palashbari | 950
P9-BP-S12a-O | P9-BP-S12a-O | 406.a/407.c | MPSB/MB/1019 | Mb | 1 | 3 | 2026-02-18 | IPC - 27 | 1 | Palashbari | 951
P9-BP-S12a-O | P9-BP-S12a-O | 406.a/407.c | MPSB/Sur/2958 | Sur | 2 | 3 | 2026-02-19 | IPC - 27 | 1 | Palashbari | 951
P9-BP-S12a-O | P9-BP-S12a-O | 406.a/407.c | MPSB/MB/1029 | Mb | 3 | 3 | 2026-02-19 | IPC - 27 | 1 | Palashbari | 951
P9-BP-S13a-O | P9-BP-S13a-O© | 406.a/407.c/408.c | MPSB/MB/1049 | Mb | 1 | 3 | 2026-02-23 | IPC - 27 | 1 | Palashbari | 952
P9-BP-S13a-O | P9-BP-S13a-O© | 406.a/407.c/408.c | MPSB/Sur/2986 | Sur | 2 | 3 | 2026-02-24 | IPC - 27 | 1 | Palashbari | 952
P9-BP-S13a-O | P9-BP-S13a-O© | 406.a/407.c/408.c | MPSB/MB/1072 | Mb | 3 | 3 | 2026-02-24 | IPC - 27 | 1 | Palashbari | 952
P9-BP-S14a-O | P9-BP-S14a-O | 406.a/407.c | MPSB/MB/1083 | Mb | 1 | 3 | 2026-02-25 | IPC - 27 | 1 | Palashbari | 953
P9-BP-S14a-O | P9-BP-S14a-O | 406.a/407.c | MPSB/Sur/3012 | Sur | 2 | 3 | 2026-02-26 | IPC - 27 | 1 | Palashbari | 953
P9-BP-S14a-O | P9-BP-S14a-O | 406.a/407.c | MPSB/MB/1092 | Mb | 3 | 3 | 2026-02-26 | IPC - 27 | 1 | Palashbari | 953
P9-BP-S15a-O | P9-BP-S15a-O© | 406.a/407.c/408.c | MPSB/MB/1093 | Mb | 1 | 3 | 2026-02-26 | IPC - 27 | 1 | Palashbari | 954
P9-BP-S15a-O | P9-BP-S15a-O© | 406.a/407.c/408.c | MPSB/Sur/3047 | Sur | 2 | 3 | 2026-02-28 | IPC - 27 | 1 | Palashbari | 954
P9-BP-S15a-O | P9-BP-S15a-O© | 406.a/407.c/408.c | MPSB/MB/1124 | Mb | 3 | 3 | 2026-02-28 | IPC - 27 | 1 | Palashbari | 954
P10-KS-S01a-E | P10-KS-S01a-E | 406.a/407.c | MPSB/MB/1094 | Mb | 1 | 3 | 2026-02-26 | IPC - 27 | 1 | Palashbari | 955
P10-KS-S01a-E | P10-KS-S01a-E | 406.a/407.c | MPSB/Sur/3024 | Sur | 2 | 3 | 2026-02-27 | IPC - 27 | 1 | Palashbari | 955
P10-KS-S01a-E | P10-KS-S01a-E | 406.a/407.c | MPSB/MB/1125 | Mb | 3 | 3 | 2026-02-28 | IPC - 27 | 1 | Palashbari | 955
P23-KS-S24a-O | P23-KS-S24a-O | 406.a/407.c | MPSB/MB/928 | Mb | 1 | 3 | 2026-02-06 | IPC - 27 | 1 | Sualkuchi | 956
P23-KS-S24a-O | P23-KS-S24a-O | 406.a/407.c | MPSB/Sur/2885 | Sur | 2 | 3 | 2026-02-07 | IPC - 27 | 1 | Sualkuchi | 956
P23-KS-S24a-O | P23-KS-S24a-O | 406.a/407.c | MPSB/MB/936 | Mb | 3 | 3 | 2026-02-07 | IPC - 27 | 1 | Sualkuchi | 956
P23-KS-S25a-O | P23-KS-S25a-O© | 406.a/407.c/408.c | MPSB/MB/956 | Mb | 1 | 3 | 2026-02-10 | IPC - 27 | 1 | Sualkuchi | 957
P23-KS-S25a-O | P23-KS-S25a-O© | 406.a/407.c/408.c | MPSB/Sur/2916 | Sur | 2 | 3 | 2026-02-11 | IPC - 27 | 1 | Sualkuchi | 957
P23-KS-S25a-O | P23-KS-S25a-O© | 406.a/407.c/408.c | MPSB/MB/962 | Mb | 3 | 3 | 2026-02-11 | IPC - 27 | 1 | Sualkuchi | 957
P23-KS-S26a-O | P23-KS-S26a-O | 406.a/407.c | MPSB/MB/984 | Mb | 1 | 3 | 2026-02-13 | IPC - 27 | 1 | Sualkuchi | 958
P23-KS-S26a-O | P23-KS-S26a-O | 406.a/407.c | MPSB/Sur/2933 | Sur | 2 | 3 | 2026-02-14 | IPC - 27 | 1 | Sualkuchi | 958
P23-KS-S26a-O | P23-KS-S26a-O | 406.a/407.c | MPSB/MB/995 | Mb | 3 | 3 | 2026-02-14 | IPC - 27 | 1 | Sualkuchi | 958
P23-KS-S27a-O | P23-KS-S27a-O© | 406.a/407.c/408.c | MPSB/MB/1013 | Mb | 1 | 3 | 2026-02-17 | IPC - 27 | 1 | Sualkuchi | 959
P23-KS-S27a-O | P23-KS-S27a-O© | 406.a/407.c/408.c | MPSB/Sur/2950 | Sur | 2 | 3 | 2026-02-17 | IPC - 27 | 1 | Sualkuchi | 959
P23-KS-S27a-O | P23-KS-S27a-O© | 406.a/407.c/408.c | MPSB/MB/1012 | Mb | 3 | 3 | 2026-02-17 | IPC - 27 | 1 | Sualkuchi | 959
P23-KS-S28a-O | P23-KS-S28a-O | 406.a/407.c | MPSB/MB/1023 | Mb | 1 | 3 | 2026-02-18 | IPC - 27 | 1 | Sualkuchi | 960 | P23-KS-S29a-O
P23-KS-S28a-O | P23-KS-S28a-O | 406.a/407.c | MPSB/Sur/2968 | Sur | 2 | 3 | 2026-02-20 | IPC - 27 | 1 | Sualkuchi | 960
P23-KS-S28a-O | P23-KS-S28a-O | 406.a/407.c | MPSB/MB/1037 | Mb | 3 | 3 | 2026-02-20 | IPC - 27 | 1 | Sualkuchi | 960
P23-KS-S29a-O | P23-KS-S29a-O© | 406.a/407.c/408.c | MPSB/MB/1023 | Mb | 1 | 3 | 2026-02-18 | IPC - 27 | 1 | Sualkuchi | 961 | P23-KS-S28a-O
P23-KS-S29a-O | P23-KS-S29a-O© | 406.a/407.c/408.c | MPSB/Sur/2985 | Sur | 2 | 3 | 2026-02-24 | IPC - 27 | 1 | Sualkuchi | 961
P23-KS-S29a-O | P23-KS-S29a-O© | 406.a/407.c/408.c | MPSB/MB/1064 | Mb | 3 | 3 | 2026-02-24 | IPC - 27 | 1 | Sualkuchi | 961
P23-KS-S30a-O | P23-KS-S30a-O | 406.a/407.c | MPSB/MB/1066 | Mb | 1 | 3 | 2026-02-24 | IPC - 27 | 1 | Sualkuchi | 962
P23-KS-S30a-O | P23-KS-S30a-O | 406.a/407.c | MPSB/Sur/3026 | Sur | 2 | 3 | 2026-02-27 | IPC - 27 | 1 | Sualkuchi | 962
P23-KS-S30a-O | P23-KS-S30a-O | 406.a/407.c | MPSB/MB/1108 | Mb | 3 | 3 | 2026-02-27 | IPC - 27 | 1 | Sualkuchi | 962
P23-KS-S31a-O | P23-KS-S31a-O© | 406.a/407.c/408.c | MPSB/MB/1099 | Mb | 1 | 3 | 2026-02-26 | IPC - 27 | 1 | Sualkuchi | 963
P23-KS-S31a-O | P23-KS-S31a-O© | 406.a/407.c/408.c | MPSB/Sur/3030 | Sur | 2 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 963
P23-KS-S31a-O | P23-KS-S31a-O© | 406.a/407.c/408.c | MPSB/MB/1114 | Mb | 3 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 963
P23-BP-S21-O | P23-BP-S21-O© | 406.a/407.c/408.c | MPSB/MB/927 | Mb | 1 | 3 | 2026-02-06 | IPC - 27 | 1 | Sualkuchi | 964
P23-BP-S21-O | P23-BP-S21-O© | 406.a/407.c/408.c | MPSB/Sur/2897 | Sur | 2 | 3 | 2026-02-09 | IPC - 27 | 1 | Sualkuchi | 964
P23-BP-S21-O | P23-BP-S21-O© | 406.a/407.c/408.c | MPSB/MB/948 | Mb | 3 | 3 | 2026-02-09 | IPC - 27 | 1 | Sualkuchi | 964
P23-BP-S22-O | P23-BP-S22-O | 406.a/407.c | MPSB/MB/1061 | Mb | 1 | 3 | 2026-02-23 | IPC - 27 | 1 | Sualkuchi | 965
P23-BP-S22-O | P23-BP-S22-O | 406.a/407.c | MPSB/Sur/3002 | Sur | 2 | 3 | 2026-02-25 | IPC - 27 | 1 | Sualkuchi | 965
P23-BP-S22-O | P23-BP-S22-O | 406.a/407.c | MPSB/MB/1075 | Mb | 3 | 3 | 2026-02-25 | IPC - 27 | 1 | Sualkuchi | 965
P23-BP-S23-O | P23-BP-S23-O© | 406.a/407.c/408.c | MPSB/MB/1040 | Mb | 1 | 3 | 2026-02-20 | IPC - 27 | 1 | Sualkuchi | 966
P23-BP-S23-O | P23-BP-S23-O© | 406.a/407.c/408.c | MPSB/Sur/3025 | Sur | 2 | 3 | 2026-02-27 | IPC - 27 | 1 | Sualkuchi | 966
P23-BP-S23-O | P23-BP-S23-O© | 406.a/407.c/408.c | MPSB/MB/1107 | Mb | 3 | 3 | 2026-02-27 | IPC - 27 | 1 | Sualkuchi | 966
P23-BP-S24-O | P23-BP-S24-O | 406.a/407.c | MPSB/MB/1113 | Mb | 1 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 967
P23-BP-S24-O | P23-BP-S24-O | 406.a/407.c | MPSB/Sur/3029 | Sur | 2 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 967
P23-BP-S24-O | P23-BP-S24-O | 406.a/407.c | MPSB/MB/1112 | Mb | 3 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 967
P25-KS-S33-O | P25-KS-S33-O© | 406.a/407.c/408.c | MPSB/MB/940 | Mb | 1 | 3 | 2026-02-08 | IPC - 27 | 1 | Sualkuchi | 968
P25-KS-S33-O | P25-KS-S33-O© | 406.a/407.c/408.c | MPSB/Sur/2898 | Sur | 2 | 3 | 2026-02-09 | IPC - 27 | 1 | Sualkuchi | 968
P25-KS-S33-O | P25-KS-S33-O© | 406.a/407.c/408.c | MPSB/MB/949 | Mb | 3 | 3 | 2026-02-09 | IPC - 27 | 1 | Sualkuchi | 968
P25-KS-S34-O | P25-KS-S34-O | 406.a/407.c | MPSB/MB/970 | Mb | 1 | 3 | 2026-02-12 | IPC - 27 | 1 | Sualkuchi | 969
P25-KS-S34-O | P25-KS-S34-O | 406.a/407.c | MPSB/Sur/2925 | Sur | 2 | 3 | 2026-02-13 | IPC - 27 | 1 | Sualkuchi | 969
P25-KS-S34-O | P25-KS-S34-O | 406.a/407.c | MPSB/MB/987 | Mb | 3 | 3 | 2026-02-13 | IPC - 27 | 1 | Sualkuchi | 969
P25-KS-S02-O | P25-KS-S02-O | 406.a/407.c | MPSB/MB/888 | Mb | 1 | 3 | 2026-02-02 | IPC - 27 | 1 | Sualkuchi | 970
P25-KS-S02-O | P25-KS-S02-O | 406.a/407.c | MPSB/Sur/2849 | Sur | 2 | 3 | 2026-02-03 | IPC - 27 | 1 | Sualkuchi | 970
P25-KS-S02-O | P25-KS-S02-O | 406.a/407.c | MPSB/MB/891 | Mb | 3 | 3 | 2026-02-03 | IPC - 27 | 1 | Sualkuchi | 970
P25-KS-S03-O | P25-KS-S03-O | 406.a/407.c | MPSB/MB/939 | Mb | 1 | 3 | 2026-02-08 | IPC - 27 | 1 | Sualkuchi | 971
P25-KS-S03-O | P25-KS-S03-O | 406.a/407.c | MPSB/Sur/2903 | Sur | 2 | 3 | 2026-02-10 | IPC - 27 | 1 | Sualkuchi | 971
P25-KS-S03-O | P25-KS-S03-O | 406.a/407.c | MPSB/MB/958 | Mb | 3 | 3 | 2026-02-10 | IPC - 27 | 1 | Sualkuchi | 971
P25-KS-S04-O | P25-KS-S04-O | 406.a/407.c | MPSB/MB/983 | Mb | 1 | 3 | 2026-02-13 | IPC - 27 | 1 | Sualkuchi | 972
P25-KS-S04-O | P25-KS-S04-O | 406.a/407.c | MPSB/Sur/2932 | Sur | 2 | 3 | 2026-02-14 | IPC - 27 | 1 | Sualkuchi | 972
P25-KS-S04-O | P25-KS-S04-O | 406.a/407.c | MPSB/MB/994 | Mb | 3 | 3 | 2026-02-14 | IPC - 27 | 1 | Sualkuchi | 972
P25-KS-S05-O | P25-KS-S05-O | 406.a/407.c | MPSB/MB/1014 | Mb | 1 | 3 | 2026-02-17 | IPC - 27 | 1 | Sualkuchi | 973
P25-KS-S05-O | P25-KS-S05-O | 406.a/407.c | MPSB/Sur/2953 | Sur | 2 | 3 | 2026-02-18 | IPC - 27 | 1 | Sualkuchi | 973
P25-KS-S05-O | P25-KS-S05-O | 406.a/407.c | MPSB/MB/1021 | Mb | 3 | 3 | 2026-02-18 | IPC - 27 | 1 | Sualkuchi | 973
P25-KS-S06-O | P25-KS-S06-O | 406.a/407.c | MPSB/MB/1045 | Mb | 1 | 3 | 2026-02-21 | IPC - 27 | 1 | Sualkuchi | 974
P25-KS-S06-O | P25-KS-S06-O | 406.a/407.c | MPSB/Sur/2979 | Sur | 2 | 3 | 2026-02-23 | IPC - 27 | 1 | Sualkuchi | 974
P25-KS-S06-O | P25-KS-S06-O | 406.a/407.c | MPSB/MB/1058 | Mb | 3 | 3 | 2026-02-23 | IPC - 27 | 1 | Sualkuchi | 974
P25-KS-S07-O | P25-KS-S07-O | 406.a/407.c | MPSB/MB/1100 | Mb | 1 | 3 | 2026-02-26 | IPC - 27 | 1 | Sualkuchi | 975
P25-KS-S07-O | P25-KS-S07-O | 406.a/407.c | MPSB/Sur/3031 | Sur | 2 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 975
P25-KS-S07-O | P25-KS-S07-O | 406.a/407.c | MPSB/MB/1115 | Mb | 3 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 975
P25-BP-S25a-O | P25-BP-S25a-O© | 406.a/407.c/408.c | MPSB/MB/957 | Mb | 1 | 3 | 2026-02-10 | IPC - 27 | 1 | Sualkuchi | 976
P25-BP-S25a-O | P25-BP-S25a-O© | 406.a/407.c/408.c | MPSB/Sur/2915 | Sur | 2 | 3 | 2026-02-11 | IPC - 27 | 1 | Sualkuchi | 976
P25-BP-S25a-O | P25-BP-S25a-O© | 406.a/407.c/408.c | MPSB/MB/961 | Mb | 3 | 3 | 2026-02-11 | IPC - 27 | 1 | Sualkuchi | 976
P25-BP-S26a-O | P25-BP-S26a-O | 406.a/407.c | MPSB/MB/982 | Mb | 1 | 3 | 2026-02-13 | IPC - 27 | 1 | Sualkuchi | 977
P25-BP-S26a-O | P25-BP-S26a-O | 406.a/407.c | MPSB/Sur/2937 | Sur | 2 | 3 | 2026-02-15 | IPC - 27 | 1 | Sualkuchi | 977
P25-BP-S26a-O | P25-BP-S26a-O | 406.a/407.c | MPSB/MB/998 | Mb | 3 | 3 | 2026-02-15 | IPC - 27 | 1 | Sualkuchi | 977
P25-BP-S27a-O | P25-BP-S27a-O© | 406.a/407.c/408.c | MPSB/MB/1015 | Mb | 1 | 3 | 2026-02-17 | IPC - 27 | 1 | Sualkuchi | 978
P25-BP-S27a-O | P25-BP-S27a-O© | 406.a/407.c/408.c | MPSB/Sur/2954 | Sur | 2 | 3 | 2026-02-18 | IPC - 27 | 1 | Sualkuchi | 978
P25-BP-S27a-O | P25-BP-S27a-O© | 406.a/407.c/408.c | MPSB/MB/1022 | Mb | 3 | 3 | 2026-02-18 | IPC - 27 | 1 | Sualkuchi | 978
P25-BP-S28a-O | P25-BP-S28a-O | 406.a/407.c | MPSB/MB/1024 | Mb | 1 | 3 | 2026-02-18 | IPC - 27 | 1 | Sualkuchi | 979
P25-BP-S28a-O | P25-BP-S28a-O | 406.a/407.c | MPSB/Sur/2969 | Sur | 2 | 3 | 2026-02-20 | IPC - 27 | 1 | Sualkuchi | 979
P25-BP-S28a-O | P25-BP-S28a-O | 406.a/407.c | MPSB/MB/1038 | Mb | 3 | 3 | 2026-02-20 | IPC - 27 | 1 | Sualkuchi | 979
P25-BP-S29a-O | P25-BP-S29a-O© | 406.a/407.c/408.c | MPSB/MB/1039 | Mb | 1 | 3 | 2026-02-20 | IPC - 27 | 1 | Sualkuchi | 980
P25-BP-S29a-O | P25-BP-S29a-O© | 406.a/407.c/408.c | MPSB/Sur/2980 | Sur | 2 | 3 | 2026-02-23 | IPC - 27 | 1 | Sualkuchi | 980
P25-BP-S29a-O | P25-BP-S29a-O© | 406.a/407.c/408.c | MPSB/MB/1059 | Mb | 3 | 3 | 2026-02-23 | IPC - 27 | 1 | Sualkuchi | 980
P25-BP-S30a-O | P25-BP-S30a-O | 406.a/407.c | MPSB/MB/1065 | Mb | 1 | 3 | 2026-02-24 | IPC - 27 | 1 | Sualkuchi | 981
P25-BP-S30a-O | P25-BP-S30a-O | 406.a/407.c | MPSB/Sur/3014 | Sur | 2 | 3 | 2026-02-26 | IPC - 27 | 1 | Sualkuchi | 981
P25-BP-S30a-O | P25-BP-S30a-O | 406.a/407.c | MPSB/MB/1097 | Mb | 3 | 3 | 2026-02-26 | IPC - 27 | 1 | Sualkuchi | 981
P25-BP-S31a-O | P25-BP-S31a-O© | 406.a/407.c/408.c | MPSB/MB/1119 | Mb | 1 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 982
P25-BP-S31a-O | P25-BP-S31a-O© | 406.a/407.c/408.c | MPSB/Sur/3033 | Sur | 2 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 982
P25-BP-S31a-O | P25-BP-S31a-O© | 406.a/407.c/408.c | MPSB/MB/1120 | Mb | 3 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 982
P26-KS-S01a-E | P26-KS-S01a-E | 406.a/407.c | MPSB/MB/1060 | Mb | 1 | 3 | 2026-02-23 | IPC - 27 | 1 | Sualkuchi | 983
P26-KS-S01a-E | P26-KS-S01a-E | 406.a/407.c | MPSB/Sur/3003 | Sur | 2 | 3 | 2026-02-25 | IPC - 27 | 1 | Sualkuchi | 983
P26-KS-S01a-E | P26-KS-S01a-E | 406.a/407.c | MPSB/MB/1076 | Mb | 3 | 3 | 2026-02-25 | IPC - 27 | 1 | Sualkuchi | 983
P26-KS-S01-E | P26-KS-S01-E | 406.a/407.c | MPSB/MB/1109 | Mb | 1 | 3 | 2026-02-27 | IPC - 27 | 1 | Sualkuchi | 984
P26-KS-S01-E | P26-KS-S01-E | 406.a/407.c | MPSB/Sur/3032 | Sur | 2 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 984
P26-KS-S01-E | P26-KS-S01-E | 406.a/407.c | MPSB/MB/1116 | Mb | 3 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 984
P26-KS-S02-E | P26-KS-S02-E | 406.a/407.c | MPSB/MB/1121 | Mb | 1 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 985
P26-KS-S02-E | P26-KS-S02-E | 406.a/407.c | MPSB/Sur/3034 | Sur | 2 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 985
P26-KS-S02-E | P26-KS-S02-E | 406.a/407.c | MPSB/MB/1122 | Mb | 3 | 3 | 2026-02-28 | IPC - 27 | 1 | Sualkuchi | 985
P7-KS-S30a-O | P7-KS-S30a-O | 406.a/407.c | MPSB/MB/1090 | Mb | 1 | 3 | 2026-02-26 | IPC - 29 | 1 | Palashbari | 986
P7-KS-S30a-O | P7-KS-S30a-O | 406.a/407.c | MPSB/Sur/3065 | Sur | 2 | 3 | 2026-03-06 | IPC - 29 | 1 | Palashbari | 986
P7-KS-S30a-O | P7-KS-S30a-O | 406.a/407.c | MPSB/MB/1161 | Mb | 3 | 3 | 2026-03-06 | IPC - 29 | 1 | Palashbari | 986
P7-KS-S31a-O | P7-KS-S31a-O© | 406.a/407.c/408.c | MPSB/MB/1200 | Mb | 1 | 3 | 2026-03-09 | IPC - 29 | 1 | Palashbari | 987
P7-KS-S31a-O | P7-KS-S31a-O© | 406.a/407.c/408.c | MPSB/Sur/3085 | Sur | 2 | 3 | 2026-03-10 | IPC - 29 | 1 | Palashbari | 987
P7-KS-S31a-O | P7-KS-S31a-O© | 406.a/407.c/408.c | MPSB/MB/1206 | Mb | 3 | 3 | 2026-03-10 | IPC - 29 | 1 | Palashbari | 987
P7-KS-S32a-O | P7-KS-S32a-O | 406.a/407.c | MPSB/MB/1244 | Mb | 1 | 3 | 2026-03-12 | IPC - 29 | 1 | Palashbari | 988
P7-KS-S32a-O | P7-KS-S32a-O | 406.a/407.c | MPSB/Sur/3122 | Sur | 2 | 3 | 2026-03-14 | IPC - 29 | 1 | Palashbari | 988
P7-KS-S32a-O | P7-KS-S32a-O | 406.a/407.c | MPSB/Str/4118 | Str | 3 | 3 | 2026-03-14 | IPC - 29 | 1 | Palashbari | 988
P7-KS-S33a-O | P7-KS-S33a-O© | 406.a/407.c/408.c | MPSB/MB/1298 | Mb | 1 | 3 | 2026-03-18 | IPC - 29 | 1 | Palashbari | 989
P7-KS-S33a-O | P7-KS-S33a-O© | 406.a/407.c/408.c | MPSB/Sur/3144 | Sur | 2 | 3 | 2026-03-19 | IPC - 29 | 1 | Palashbari | 989
P7-KS-S33a-O | P7-KS-S33a-O© | 406.a/407.c/408.c | MPSB/MB/1303 | Mb | 3 | 3 | 2026-03-19 | IPC - 29 | 1 | Palashbari | 989
P7-KS-S34a-O | P7-KS-S34a-O | 406.a/407.c | MPSB/MB/1344 | Mb | 1 | 3 | 2026-03-24 | IPC - 29 | 1 | Palashbari | 990
P7-KS-S34a-O | P7-KS-S34a-O | 406.a/407.c | MPSB/Sur/3177 | Sur | 2 | 3 | 2026-03-26 | IPC - 29 | 1 | Palashbari | 990
P7-KS-S34a-O | P7-KS-S34a-O | 406.a/407.c | MPSB/MB/1362 | Mb | 3 | 3 | 2026-03-26 | IPC - 29 | 1 | Palashbari | 990
P8-BP-S10-M | P8-BP-S10-M© | 406.a/407.c/408.c | MPSB/MB/1160 | Mb | 1 | 3 | 2026-03-06 | IPC - 29 | 1 | Palashbari | 991
P8-BP-S10-M | P8-BP-S10-M© | 406.a/407.c/408.c | MPSB/Sur/3072 | Sur | 2 | 3 | 2026-03-07 | IPC - 29 | 1 | Palashbari | 991
P8-BP-S10-M | P8-BP-S10-M© | 406.a/407.c/408.c | MPSB/MB/1176 | Mb | 3 | 3 | 2026-03-07 | IPC - 29 | 1 | Palashbari | 991
P8-BP-S11-M | P8-BP-S11-M | 406.a/407.c | MPSB/MB/1231 | Mb | 1 | 3 | 2026-03-11 | IPC - 29 | 1 | Palashbari | 992
P8-BP-S11-M | P8-BP-S11-M | 406.a/407.c | MPSB/Sur/3107 | Sur | 2 | 3 | 2026-03-12 | IPC - 29 | 1 | Palashbari | 992
P8-BP-S11-M | P8-BP-S11-M | 406.a/407.c | MPSB/MB/1247 | Mb | 3 | 3 | 2026-03-12 | IPC - 29 | 1 | Palashbari | 992
P8-BP-S12-M | P8-BP-S12-M© | 406.a/407.c/408.c | MPSB/MB/1278 | Mb | 1 | 3 | 2026-03-16 | IPC - 29 | 1 | Palashbari | 993
P8-BP-S12-M | P8-BP-S12-M© | 406.a/407.c/408.c | MPSB/Sur/3139 | Sur | 2 | 3 | 2026-03-17 | IPC - 29 | 1 | Palashbari | 993
P8-BP-S12-M | P8-BP-S12-M© | 406.a/407.c/408.c | MPSB/MB/1288 | Mb | 3 | 3 | 2026-03-17 | IPC - 29 | 1 | Palashbari | 993
P8-BP-S13-M | P8-BP-S13-M | 406.a/407.c | MPSB/MB/1335 | Mb | 1 | 3 | 2026-03-23 | IPC - 29 | 1 | Palashbari | 994
P8-BP-S13-M | P8-BP-S13-M | 406.a/407.c | MPSB/Sur/3165 | Sur | 2 | 3 | 2026-03-24 | IPC - 29 | 1 | Palashbari | 994
P8-BP-S13-M | P8-BP-S13-M | 406.a/407.c | MPSB/MB/1341 | Mb | 3 | 3 | 2026-03-24 | IPC - 29 | 1 | Palashbari | 994
P8-BP-S14-M | P8-BP-S14-M© | 406.a/407.c/408.c | MPSB/MB/1370 | Mb | 1 | 3 | 2026-03-27 | IPC - 29 | 1 | Palashbari | 995
P8-BP-S14-M | P8-BP-S14-M© | 406.a/407.c/408.c | MPSB/Sur/3192 | Sur | 2 | 3 | 2026-03-29 | IPC - 29 | 1 | Palashbari | 995
P8-BP-S14-M | P8-BP-S14-M© | 406.a/407.c/408.c | MPSB/MB/1389 | Mb | 3 | 3 | 2026-03-29 | IPC - 29 | 1 | Palashbari | 995
P8-BP-S15-M | P8-BP-S15-M | 406.a/407.c | MPSB/MB/1399 | Mb | 1 | 3 | 2026-03-31 | IPC - 29 | 1 | Palashbari | 996
P8-BP-S15-M | P8-BP-S15-M | 406.a/407.c | MPSB/Sur/3229 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 1 | Palashbari | 996
P8-BP-S15-M | P8-BP-S15-M | 406.a/407.c | MPSB/MB/1419 | Mb | 3 | 3 | 2026-03-31 | IPC - 29 | 1 | Palashbari | 996
P8-KS-S01-M | P8-KS-S01-M | 406.a/407.c | MPSB/MB/1265 | Mb | 1 | 3 | 2026-03-14 | IPC - 29 | 1 | Palashbari | 997
P8-KS-S01-M | P8-KS-S01-M | 406.a/407.c | MPSB/Sur/3134 | Sur | 2 | 3 | 2026-03-17 | IPC - 29 | 1 | Palashbari | 997
P8-KS-S01-M | P8-KS-S01-M | 406.a/407.c | MPSB/MB/1275 | Mb | 3 | 3 | 2026-03-16 | IPC - 29 | 1 | Palashbari | 997
P8-KS-S02-M | P8-KS-S02-M | 406.a/407.c | MPSB/MB/1345 | Mb | 1 | 3 | 2026-03-24 | IPC - 29 | 1 | Palashbari | 998
P8-KS-S02-M | P8-KS-S02-M | 406.a/407.c | MPSB/Sur/3175 | Sur | 2 | 3 | 2026-03-26 | IPC - 29 | 1 | Palashbari | 998
P8-KS-S02-M | P8-KS-S02-M | 406.a/407.c | MPSB/MB/1358 | Mb | 3 | 3 | 2026-03-26 | IPC - 29 | 1 | Palashbari | 998
P8-KS-S03-M | P8-KS-S03-M | 406.a/407.c | MPSB/MB/1388 | Mb | 1 | 3 | 2026-03-29 | IPC - 29 | 1 | Palashbari | 999
P8-KS-S03-M | P8-KS-S03-M | 406.a/407.c | MPSB/Sur/3211 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 1 | Palashbari | 999
P8-KS-S03-M | P8-KS-S03-M | 406.a/407.c | MPSB/MB/1401 | Mb | 3 | 3 | 2026-03-31 | IPC - 29 | 1 | Palashbari | 999
P9-KS-S08-O | P9-KS-S08-O | 406.a/407.c | MPSB/MB/1158 | Mb | 1 | 3 | 2026-03-06 | IPC - 29 | 1 | Palashbari | 1000
P9-KS-S08-O | P9-KS-S08-O | 406.a/407.c | MPSB/Sur/3066 | Sur | 2 | 3 | 2026-03-06 | IPC - 29 | 1 | Palashbari | 1000
P9-KS-S08-O | P9-KS-S08-O | 406.a/407.c | MPSB/MB/1162 | Mb | 3 | 3 | 2026-03-07 | IPC - 29 | 1 | Palashbari | 1000
P9-BP-S16a-O | P9-BP-S16a-O | 406.a/407.c | MPSB/MB/1177 | Mb | 1 | 3 | 2026-03-07 | IPC - 29 | 1 | Palashbari | 1001
P9-BP-S16a-O | P9-BP-S16a-O | 406.a/407.c | MPSB/Sur/3077 | Sur | 2 | 3 | 2026-03-08 | IPC - 29 | 1 | Palashbari | 1001
P9-BP-S16a-O | P9-BP-S16a-O | 406.a/407.c | MPSB/MB/1191 | Mb | 3 | 3 | 2026-03-08 | IPC - 29 | 1 | Palashbari | 1001
P9-BP-S17a-O | P9-BP-S17a-O© | 406.a/407.c/408.c | MPSB/MB/1190 | Mb | 1 | 3 | 2026-03-09 | IPC - 29 | 1 | Palashbari | 1002
P9-BP-S17a-O | P9-BP-S17a-O© | 406.a/407.c/408.c | MPSB/Sur/3100 | Sur | 2 | 3 | 2026-03-11 | IPC - 29 | 1 | Palashbari | 1002
P9-BP-S17a-O | P9-BP-S17a-O© | 406.a/407.c/408.c | MPSB/MB/1232 | Mb | 3 | 3 | 2026-03-11 | IPC - 29 | 1 | Palashbari | 1002
P9-BP-S18a-O | P9-BP-S18a-O | 406.a/407.c | MPSB/MB/1257 | Mb | 1 | 3 | 2026-03-13 | IPC - 29 | 1 | Palashbari | 1003
P9-BP-S18a-O | P9-BP-S18a-O | 406.a/407.c | MPSB/Sur/3062 | Sur | 2 | 3 | 2026-03-14 | IPC - 29 | 1 | Palashbari | 1003 | P25-BP-S32a-O
P9-BP-S18a-O | P9-BP-S18a-O | 406.a/407.c | MPSB/str/4107 | Str | 3 | 3 | 2026-03-14 | IPC - 29 | 1 | Palashbari | 1003
P9-BP-S19a-O | P9-BP-S19a-O© | 406.a/407.c/408.c | MPSB/MB/1302 | Mb | 1 | 3 | 2026-03-19 | IPC - 29 | 1 | Palashbari | 1004
P9-BP-S19a-O | P9-BP-S19a-O© | 406.a/407.c/408.c | MPSB/Sur/3153 | Sur | 2 | 3 | 2026-03-20 | IPC - 29 | 1 | Palashbari | 1004
P9-BP-S19a-O | P9-BP-S19a-O© | 406.a/407.c/408.c | MPSB/MB/1311 | Mb | 3 | 3 | 2026-03-20 | IPC - 29 | 1 | Palashbari | 1004
P9-BP-S20a-O | P9-BP-S20a-O | 406.a/407.c | MPSB/MB/1343 | Mb | 1 | 3 | 2026-03-24 | IPC - 29 | 1 | Palashbari | 1005
P9-BP-S20a-O | P9-BP-S20a-O | 406.a/407.c | MPSB/Sur/3176 | Sur | 2 | 3 | 2026-03-26 | IPC - 29 | 1 | Palashbari | 1005
P9-BP-S20a-O | P9-BP-S20a-O | 406.a/407.c | MPSB/MB/1360 | Mb | 3 | 3 | 2026-03-26 | IPC - 29 | 1 | Palashbari | 1005
P9-BP-S21a-O | P9-BP-S21a-O© | 406.a/407.c/408.c | MPSB/MB/1387 | Mb | 1 | 3 | 2026-03-29 | IPC - 29 | 1 | Palashbari | 1006
P9-BP-S21a-O | P9-BP-S21a-O© | 406.a/407.c/408.c | MPSB/Sur/3210 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 1 | Palashbari | 1006
P9-BP-S21a-O | P9-BP-S21a-O© | 406.a/407.c/408.c | MPSB/MB/1398 | Mb | 3 | 3 | 2026-03-31 | IPC - 29 | 1 | Palashbari | 1006
P10-KS-S01-E | P10-KS-S01-E | 406.a/407.c | MPSB/MB/1159 | Mb | 1 | 3 | 2026-03-06 | IPC - 29 | 1 | Palashbari | 1007
P10-KS-S01-E | P10-KS-S01-E | 406.a/407.c | MPSB/Sur/3067 | Sur | 2 | 3 | 2026-03-06 | IPC - 29 | 1 | Palashbari | 1007
P10-KS-S01-E | P10-KS-S01-E | 406.a/407.c | MPSB/MB/1163 | Mb | 3 | 3 | 2026-03-06 | IPC - 29 | 1 | Palashbari | 1007
P10-KS-S02-E | P10-KS-S02-E | 406.a/407.c | MPSB/MB/1230 | Mb | 1 | 3 | 2026-03-11 | IPC - 29 | 1 | Palashbari | 1008
P10-KS-S02-E | P10-KS-S02-E | 406.a/407.c | MPSB/Sur/3106 | Sur | 2 | 3 | 2026-03-12 | IPC - 29 | 1 | Palashbari | 1008
P10-KS-S02-E | P10-KS-S02-E | 406.a/407.c | MPSB/MB/1246 | Mb | 3 | 3 | 2026-03-12 | IPC - 29 | 1 | Palashbari | 1008
P10-KS-S03-E | P10-KS-S03-E | 406.a/407.c | MPSB/MB/1277 | Mb | 1 | 3 | 2026-03-16 | IPC - 29 | 1 | Palashbari | 1009
P10-KS-S03-E | P10-KS-S03-E | 406.a/407.c | MPSB/Sur/3140 | Sur | 2 | 3 | 2026-03-17 | IPC - 29 | 1 | Palashbari | 1009
P10-KS-S03-E | P10-KS-S03-E | 406.a/407.c | MPSB/MB/1289 | Mb | 3 | 3 | 2026-03-17 | IPC - 29 | 1 | Palashbari | 1009
P10-KS-S04-E | P10-KS-S04-E | 406.a/407.c | MPSB/MB/1336 | Mb | 1 | 3 | 2026-03-23 | IPC - 29 | 1 | Palashbari | 1010
P10-KS-S04-E | P10-KS-S04-E | 406.a/407.c | MPSB/Sur/3166 | Sur | 2 | 3 | 2026-03-24 | IPC - 29 | 1 | Palashbari | 1010
P10-KS-S04-E | P10-KS-S04-E | 406.a/407.c | MPSB/MB/1342 | Mb | 3 | 3 | 2026-03-24 | IPC - 29 | 1 | Palashbari | 1010
P10-KS-S05-E | P10-KS-S05-E | 406.a/407.c | MPSB/MB/1361 | Mb | 1 | 3 | 2026-03-26 | IPC - 29 | 1 | Palashbari | 1011
P10-KS-S05-E | P10-KS-S05-E | 406.a/407.c | MPSB/Sur/3183 | Sur | 2 | 3 | 2026-03-28 | IPC - 29 | 1 | Palashbari | 1011
P10-KS-S05-E | P10-KS-S05-E | 406.a/407.c | MPSB/MB/1377 | Mb | 3 | 3 | 2026-03-28 | IPC - 29 | 1 | Palashbari | 1011
P10-KS-S06-E | P10-KS-S06-E | 406.a/407.c | MPSB/MB/1400 | Mb | 1 | 3 | 2026-03-31 | IPC - 29 | 1 | Palashbari | 1012
P10-KS-S06-E | P10-KS-S06-E | 406.a/407.c | MPSB/Sur/3227 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 1 | Palashbari | 1012
P10-KS-S06-E | P10-KS-S06-E | 406.a/407.c | MPSB/MB/1417 | Mb | 3 | 3 | 2026-03-31 | IPC - 29 | 1 | Palashbari | 1012
P21-KS-S09-O | P21-KS-S09-O© | 406.a/407.c/408.c | MPSB/MB/1352 | Mb | 1 | 3 | 2026-03-24 | IPC - 29 | 1 | Sualkuchi | 1013
P21-KS-S09-O | P21-KS-S09-O© | 406.a/407.c/408.c | MPSB/Sur/3179 | Sur | 2 | 3 | 2026-03-26 | IPC - 29 | 1 | Sualkuchi | 1013
P21-KS-S09-O | P21-KS-S09-O© | 406.a/407.c/408.c | MPSB/MB/1363 | Mb | 3 | 3 | 2026-03-26 | IPC - 29 | 1 | Sualkuchi | 1013
P21-KS-S10-O | P21-KS-S10-O | 406.a/407.c | MPSB/MB/1382 | Mb | 1 | 3 | 2026-03-28 | IPC - 29 | 1 | Sualkuchi | 1014
P21-KS-S10-O | P21-KS-S10-O | 406.a/407.c | MPSB/Sur/3217 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1014
P21-KS-S10-O | P21-KS-S10-O | 406.a/407.c | MPSB/MB/1407 | Mb | 3 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1014
P21-KS-S11-O | P21-KS-S11-O© | 406.a/407.c/408.c | MPSB/MB/1413 | Mb | 1 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1015
P21-KS-S11-O | P21-KS-S11-O© | 406.a/407.c/408.c | MPSB/Sur/3225 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1015
P21-KS-S11-O | P21-KS-S11-O© | 406.a/407.c/408.c | MPSB/MB/1414 | Mb | 3 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1015
P23-KS-S32a-O | P23-KS-S32a-O | 406.a/407.c | MPSB/MB/1145 | Mb | 1 | 3 | 2026-03-05 | IPC - 29 | 1 | Sualkuchi | 1016
P23-KS-S32a-O | P23-KS-S32a-O | 406.a/407.c | MPSB/Sur/3061 | Sur | 2 | 3 | 2026-03-05 | IPC - 29 | 1 | Sualkuchi | 1016
P23-KS-S32a-O | P23-KS-S32a-O | 406.a/407.c | MPSB/MB/1147 | Mb | 3 | 3 | 2026-03-05 | IPC - 29 | 1 | Sualkuchi | 1016
P23-KS-S33a-O | P23-KS-S33a-O© | 406.a/407.c/408.c | MPSB/MB/1210 | Mb | 1 | 3 | 2026-03-10 | IPC - 29 | 1 | Sualkuchi | 1017
P23-KS-S33a-O | P23-KS-S33a-O© | 406.a/407.c/408.c | MPSB/Sur/3104 | Sur | 2 | 3 | 2026-03-12 | IPC - 29 | 1 | Sualkuchi | 1017
P23-KS-S33a-O | P23-KS-S33a-O© | 406.a/407.c/408.c | MPSB/MB/1241 | Mb | 3 | 3 | 2026-03-12 | IPC - 29 | 1 | Sualkuchi | 1017
P23-KS-S34a-O | P23-KS-S34a-O | 406.a/407.c | MPSB/MB/1322 | Mb | 1 | 3 | 2026-03-16 | IPC - 29 | 1 | Sualkuchi | 1018
P23-KS-S34a-O | P23-KS-S34a-O | 406.a/407.c | MPSB/Sur/3127 | Sur | 2 | 3 | 2026-03-16 | IPC - 29 | 1 | Sualkuchi | 1018
P23-KS-S34a-O | P23-KS-S34a-O | 406.a/407.c | MPSB/MB/1269 | Mb | 3 | 3 | 2026-03-16 | IPC - 29 | 1 | Sualkuchi | 1018
P23-KS-S01a-O | P23-KS-S01a-O | 406.a/407.c | MPSB/MB/1233 | Mb | 1 | 3 | 2026-03-11 | IPC - 29 | 1 | Sualkuchi | 1019
P23-KS-S01a-O | P23-KS-S01a-O | 406.a/407.c | MPSB/Sur/3101 | Sur | 2 | 3 | 2026-03-11 | IPC - 29 | 1 | Sualkuchi | 1019
P23-KS-S01a-O | P23-KS-S01a-O | 406.a/407.c | MPSB/MB/1235 | Mb | 3 | 3 | 2026-03-11 | IPC - 29 | 1 | Sualkuchi | 1019
P23-KS-S02a-O | P23-KS-S02a-O | 406.a/407.c | MPSB/MB/1262 | Mb | 1 | 3 | 2026-03-13 | IPC - 29 | 1 | Sualkuchi | 1020
P23-KS-S02a-O | P23-KS-S02a-O | 406.a/407.c | MPSB/Sur/3128 | Sur | 2 | 3 | 2026-03-16 | IPC - 29 | 1 | Sualkuchi | 1020
P23-KS-S02a-O | P23-KS-S02a-O | 406.a/407.c | MPSB/MB/1270 | Mb | 3 | 3 | 2026-03-16 | IPC - 29 | 1 | Sualkuchi | 1020
P23-KS-S03a-O | P23-KS-S03a-O | 406.a/407.c | MPSB/MB/1299 | Mb | 1 | 3 | 2026-03-18 | IPC - 29 | 1 | Sualkuchi | 1021
P23-KS-S03a-O | P23-KS-S03a-O | 406.a/407.c | MPSB/Sur/3157 | Sur | 2 | 3 | 2026-03-21 | IPC - 29 | 1 | Sualkuchi | 1021
P23-KS-S03a-O | P23-KS-S03a-O | 406.a/407.c | MPSB/MB/1330 | Mb | 3 | 3 | 2026-03-21 | IPC - 29 | 1 | Sualkuchi | 1021
P23-KS-S04a-O | P23-KS-S04a-O | 406.a/407.c | MPSB/MB/1338 | Mb | 1 | 3 | 2026-03-23 | IPC - 29 | 1 | Sualkuchi | 1022
P23-KS-S04a-O | P23-KS-S04a-O | 406.a/407.c | MPSB/Sur/3167 | Sur | 2 | 3 | 2026-03-24 | IPC - 29 | 1 | Sualkuchi | 1022
P23-KS-S04a-O | P23-KS-S04a-O | 406.a/407.c | MPSB/MB/1350 | Mb | 3 | 3 | 2026-03-24 | IPC - 29 | 1 | Sualkuchi | 1022
P23-KS-S05a-O | P23-KS-S05a-O | 406.a/407.c | MPSB/MB/1372 | Mb | 1 | 3 | 2026-03-27 | IPC - 29 | 1 | Sualkuchi | 1023
P23-KS-S05a-O | P23-KS-S05a-O | 406.a/407.c | MPSB/Sur/3186 | Sur | 2 | 3 | 2026-03-28 | IPC - 29 | 1 | Sualkuchi | 1023
P23-KS-S05a-O | P23-KS-S05a-O | 406.a/407.c | MPSB/MB/1379 | Mb | 3 | 3 | 2026-03-28 | IPC - 29 | 1 | Sualkuchi | 1023
P23-KS-S06a-O | P23-KS-S06a-O | 406.a/407.c | MPSB/MB/1402 | Mb | 1 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1024
P23-KS-S06a-O | P23-KS-S06a-O | 406.a/407.c | MPSB/Sur/3222 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1024
P23-KS-S06a-O | P23-KS-S06a-O | 406.a/407.c | MPSB/MB/1410 | Mb | 3 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1024
P23-KS-S07a-O | P23-KS-S07a-O | 406.a/407.c | MPSB/MB/1409 | Mb | 1 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1025
P23-KS-S07a-O | P23-KS-S07a-O | 406.a/407.c | MPSB/Sur/3224 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1025
P23-KS-S07a-O | P23-KS-S07a-O | 406.a/407.c | MPSB/MB/1412 | Mb | 3 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1025
P23-BP-S25-O | P23-BP-S25-O© | 406.a/407.c/408.c | MPSB/MB/1171 | Mb | 1 | 3 | 2026-03-06 | IPC - 29 | 1 | Sualkuchi | 1026
P23-BP-S25-O | P23-BP-S25-O© | 406.a/407.c/408.c | MPSB/Sur/3073 | Sur | 2 | 3 | 2026-03-07 | IPC - 29 | 1 | Sualkuchi | 1026
P23-BP-S25-O | P23-BP-S25-O© | 406.a/407.c/408.c | MPSB/MB/1183 | Mb | 3 | 3 | 2026-03-07 | IPC - 29 | 1 | Sualkuchi | 1026
P23-BP-S26-O | P23-BP-S26-O | 406.a/407.c | MPSB/MB/1209 | Mb | 1 | 3 | 2026-03-10 | IPC - 29 | 1 | Sualkuchi | 1027
P23-BP-S26-O | P23-BP-S26-O | 406.a/407.c | MPSB/Sur/3088 | Sur | 2 | 3 | 2026-03-10 | IPC - 29 | 1 | Sualkuchi | 1027
P23-BP-S26-O | P23-BP-S26-O | 406.a/407.c | MPSB/MB/1211 | Mb | 3 | 3 | 2026-03-10 | IPC - 29 | 1 | Sualkuchi | 1027
P23-BP-S27-O | P23-BP-S27-O© | 406.a/407.c/408.c | MPSB/MB/1240 | Mb | 1 | 3 | 2026-03-12 | IPC - 29 | 1 | Sualkuchi | 1028
P23-BP-S27-O | P23-BP-S27-O© | 406.a/407.c/408.c | MPSB/Sur/3121 | Sur | 2 | 3 | 2026-03-14 | IPC - 29 | 1 | Sualkuchi | 1028
P23-BP-S27-O | P23-BP-S27-O© | 406.a/407.c/408.c | MPSB/MB/1267 | Mb | 3 | 3 | 2026-03-14 | IPC - 29 | 1 | Sualkuchi | 1028
P23-BP-S28-O | P23-BP-S28-O | 406.a/407.c | MPSB/MB/1268 | Mb | 1 | 3 | 2026-03-16 | IPC - 29 | 1 | Sualkuchi | 1029
P23-BP-S28-O | P23-BP-S28-O | 406.a/407.c | MPSB/Sur/3137 | Sur | 2 | 3 | 2026-03-17 | IPC - 29 | 1 | Sualkuchi | 1029
P23-BP-S28-O | P23-BP-S28-O | 406.a/407.c | MPSB/MB/1283 | Mb | 3 | 3 | 2026-03-17 | IPC - 29 | 1 | Sualkuchi | 1029
P23-BP-S29-O | P23-BP-S29-O© | 406.a/407.c/408.c | MPSB/MB/1329 | Mb | 1 | 3 | 2026-03-21 | IPC - 29 | 1 | Sualkuchi | 1030
P23-BP-S29-O | P23-BP-S29-O© | 406.a/407.c/408.c | MPSB/Sur/3161 | Sur | 2 | 3 | 2026-03-23 | IPC - 29 | 1 | Sualkuchi | 1030
P23-BP-S29-O | P23-BP-S29-O© | 406.a/407.c/408.c | MPSB/MB/1340 | Mb | 3 | 3 | 2026-03-23 | IPC - 29 | 1 | Sualkuchi | 1030
P23-BP-S30-O | P23-BP-S30-O | 406.a/407.c | MPSB/MB/1334 | Mb | 1 | 3 | 2026-03-21 | IPC - 29 | 1 | Sualkuchi | 1031
P23-BP-S30-O | P23-BP-S30-O | 406.a/407.c | MPSB/Sur/3174 | Sur | 2 | 3 | 2026-03-25 | IPC - 29 | 1 | Sualkuchi | 1031
P23-BP-S30-O | P23-BP-S30-O | 406.a/407.c | MPSB/MB/1357 | Mb | 3 | 3 | 2026-03-25 | IPC - 29 | 1 | Sualkuchi | 1031
P23-BP-S31-O | P23-BP-S31-O© | 406.a/407.c/408.c | MPSB/MB/1374 | Mb | 1 | 3 | 2026-03-27 | IPC - 29 | 1 | Sualkuchi | 1032
P23-BP-S31-O | P23-BP-S31-O© | 406.a/407.c/408.c | MPSB/Sur/3205 | Sur | 2 | 3 | 2026-03-30 | IPC - 29 | 1 | Sualkuchi | 1032
P23-BP-S31-O | P23-BP-S31-O© | 406.a/407.c/408.c | MPSB/MB/1394 | Mb | 3 | 3 | 2026-03-30 | IPC - 29 | 1 | Sualkuchi | 1032
P23-BP-S32-O | P23-BP-S32-O | 406.a/407.c | MPSB/MB/1404 | Mb | 1 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1033
P23-BP-S32-O | P23-BP-S32-O | 406.a/407.c | MPSB/Sur/3223 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1033
P23-BP-S32-O | P23-BP-S32-O | 406.a/407.c | MPSB/MB/1411 | Mb | 3 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1033
P24-BP-S08-M | P24-BP-S08-M© | 406.a/407.c/408.c | MPSB/MB/1381 | Mb | 1 | 3 | 2026-03-28 | IPC - 29 | 1 | Sualkuchi | 1034
P24-BP-S08-M | P24-BP-S08-M© | 406.a/407.c/408.c | MPSB/Sur/3218 | Sur | 2 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1034
P24-BP-S08-M | P24-BP-S08-M© | 406.a/407.c/408.c | MPSB/MB/1408 | Mb | 3 | 3 | 2026-03-31 | IPC - 29 | 1 | Sualkuchi | 1034
P25-BP-S32a-O | P25-BP-S32a-O | 406.a/407.c | MPSB/MB/1146 | Mb | 1 | 3 | 2026-03-05 | IPC - 29 | 1 | Sualkuchi | 1035
P25-BP-S32a-O | P25-BP-S32a-O | 406.a/407.c | MPSB/Sur/3062 | Sur | 2 | 3 | 2026-03-05 | IPC - 29 | 1 | Sualkuchi | 1035 | P9-BP-S18a-O
P25-BP-S32a-O | P25-BP-S32a-O | 406.a/407.c | MPSB/MB/1148 | Mb | 3 | 3 | 2026-03-05 | IPC - 29 | 1 | Sualkuchi | 1035
P25-BP-S33a-O | P25-BP-S33a-O© | 406.a/407.c/408.c | MPSB/MB/1182 | Mb | 1 | 3 | 2026-03-07 | IPC - 29 | 1 | Sualkuchi | 1036
P25-BP-S33a-O | P25-BP-S33a-O© | 406.a/407.c/408.c | MPSB/Sur/3078 | Sur | 2 | 3 | 2026-03-08 | IPC - 29 | 1 | Sualkuchi | 1036
P25-BP-S33a-O | P25-BP-S33a-O© | 406.a/407.c/408.c | MPSB/MB/1195 | Mb | 3 | 3 | 2026-03-08 | IPC - 29 | 1 | Sualkuchi | 1036
P25-BP-S34a-O | P25-BP-S34a-O | 406.a/407.c | MPSB/MB/1234 | Mb | 1 | 3 | 2026-03-11 | IPC - 29 | 1 | Sualkuchi | 1037
P25-BP-S34a-O | P25-BP-S34a-O | 406.a/407.c | MPSB/Sur/3103 | Sur | 2 | 3 | 2026-03-12 | IPC - 29 | 1 | Sualkuchi | 1037
P25-BP-S34a-O | P25-BP-S34a-O | 406.a/407.c | MPSB/MB/1239 | Mb | 3 | 3 | 2026-03-12 | IPC - 29 | 1 | Sualkuchi | 1037
P26-KS-S03-E | P26-KS-S03-E | 406.a/407.c | MPSB/MB/1181 | Mb | 1 | 3 | 2026-03-07 | IPC - 29 | 1 | Sualkuchi | 1038
P26-KS-S03-E | P26-KS-S03-E | 406.a/407.c | MPSB/Sur/3079 | Sur | 2 | 3 | 2026-03-08 | IPC - 29 | 1 | Sualkuchi | 1038
P26-KS-S03-E | P26-KS-S03-E | 406.a/407.c | MPSB/MB/1196 | Mb | 3 | 3 | 2026-03-08 | IPC - 29 | 1 | Sualkuchi | 1038
P26-KS-S04-E | P26-KS-S04-E | 406.a/407.c | MPSB/MB/1258 | Mb | 1 | 3 | 2026-03-13 | IPC - 29 | 1 | Sualkuchi | 1039
P26-KS-S04-E | P26-KS-S04-E | 406.a/407.c | MPSB/Sur/3113 | Sur | 2 | 3 | 2026-03-13 | IPC - 29 | 1 | Sualkuchi | 1039
P26-KS-S04-E | P26-KS-S04-E | 406.a/407.c | MPSB/MB/1259 | Mb | 3 | 3 | 2026-03-13 | IPC - 29 | 1 | Sualkuchi | 1039
P26-KS-S05-E | P26-KS-S05-E | 406.a/407.c | MPSB/Sur/3138 | Sur | 1 | 2 | 2026-03-17 | IPC - 29 | 1 | Sualkuchi | 1040
P26-KS-S05-E | P26-KS-S05-E | 406.a/407.c | MPSB/MB/1284 | Mb | 2 | 2 | 2026-03-17 | IPC - 29 | 1 | Sualkuchi | 1040
P26-KS-S06-E | P26-KS-S06-E | 406.a/407.c | MPSB/MB/1300 | Mb | 1 | 3 | 2026-03-18 | IPC - 29 | 1 | Sualkuchi | 1041
P26-KS-S06-E | P26-KS-S06-E | 406.a/407.c | MPSB/Sur/3158 | Sur | 2 | 3 | 2026-03-21 | IPC - 29 | 1 | Sualkuchi | 1041
P26-KS-S06-E | P26-KS-S06-E | 406.a/407.c | MPSB/MB/1331 | Mb | 3 | 3 | 2026-03-21 | IPC - 29 | 1 | Sualkuchi | 1041
P8-BP-S16-M | P8-BP-S16-M© | 406.a/407.c/408.c | MPSB/MB/1422 | Mb | 1 | 3 | 2026-03-31 | IPC - 30 | 1 | Palashbari | 1042
P8-BP-S16-M | P8-BP-S16-M© | 406.a/407.c/408.c | MPSB/Sur/3253 | Sur | 2 | 3 | 2026-04-06 | IPC - 30 | 1 | Palashbari | 1042
P8-BP-S16-M | P8-BP-S16-M© | 406.a/407.c/408.c | MPSB/MB/1449 | Mb | 3 | 3 | 2026-04-06 | IPC - 30 | 1 | Palashbari | 1042
P8-BP-S17-M | P8-BP-S17-M | 406.a/407.c | MPSB/MB/1452 | Mb | 1 | 3 | 2026-04-07 | IPC - 30 | 1 | Palashbari | 1043
P8-BP-S17-M | P8-BP-S17-M | 406.a/407.c | MPSB/Sur/3290 | Sur | 2 | 3 | 2026-04-13 | IPC - 30 | 1 | Palashbari | 1043
P8-BP-S17-M | P8-BP-S17-M | 406.a/407.c | MPSB/MB/1517 | Mb | 3 | 3 | 2026-04-13 | IPC - 30 | 1 | Palashbari | 1043
P8-BP-S18-M | P8-BP-S18-M | 406.a/407.c | MPSB/MB/1532 | Mb | 1 | 3 | 2026-04-14 | IPC - 30 | 1 | Palashbari | 1044
P8-BP-S18-M | P8-BP-S18-M | 406.a/407.c | MPSB/Sur/3312 | Sur | 2 | 3 | 2026-04-17 | IPC - 30 | 1 | Palashbari | 1044
P8-BP-S18-M | P8-BP-S18-M | 406.a/407.c | MPSB/MB/1556 | Mb | 3 | 3 | 2026-04-17 | IPC - 30 | 1 | Palashbari | 1044
P8-BP-S01-M | P8-BP-S01-M | 406.a/407.c | MPSB/MB/1622 | Mb | 1 | 3 | 2026-04-24 | IPC - 30 | 1 | Palashbari | 1045
P8-BP-S01-M | P8-BP-S01-M | 406.a/407.c | MPSB/Sur/3349 | Sur | 2 | 3 | 2026-04-25 | IPC - 30 | 1 | Palashbari | 1045
P8-BP-S01-M | P8-BP-S01-M | 406.a/407.c | MPSB/MB/1639 | Mb | 3 | 3 | 2026-04-25 | IPC - 30 | 1 | Palashbari | 1045
P8-BP-S02-M | P8-BP-S02-M | 406.a/407.c | MPSB/MB/1651 | Mb | 1 | 3 | 2026-04-27 | IPC - 30 | 1 | Palashbari | 1046
P8-BP-S02-M | P8-BP-S02-M | 406.a/407.c | MPSB/Sur/3385 | Sur | 2 | 3 | 2026-04-29 | IPC - 30 | 1 | Palashbari | 1046
P8-BP-S02-M | P8-BP-S02-M | 406.a/407.c | MPSB/MB/1665 | Mb | 3 | 3 | 2026-04-29 | IPC - 30 | 1 | Palashbari | 1046
P8-KS-S04-M | P8-KS-S04-M | 406.a/407.c | MPSB/MB/1421 | Mb | 1 | 3 | 2026-03-31 | IPC - 30 | 1 | Palashbari | 1047
P8-KS-S04-M | P8-KS-S04-M | 406.a/407.c | MPSB/Sur/3254 | Sur | 2 | 3 | 2026-04-06 | IPC - 30 | 1 | Palashbari | 1047
P8-KS-S04-M | P8-KS-S04-M | 406.a/407.c | MPSB/MB/1450 | Mb | 3 | 3 | 2026-04-06 | IPC - 30 | 1 | Palashbari | 1047
P8-KS-S05-M | P8-KS-S05-M | 406.a/407.c | MPSB/MB/1473 | Mb | 1 | 3 | 2026-04-10 | IPC - 30 | 1 | Palashbari | 1048
P8-KS-S05-M | P8-KS-S05-M | 406.a/407.c | MPSB/Sur/3280 | Sur | 2 | 3 | 2026-04-12 | IPC - 30 | 1 | Palashbari | 1048
P8-KS-S05-M | P8-KS-S05-M | 406.a/407.c | MPSB/MB/1510 | Mb | 3 | 3 | 2026-04-12 | IPC - 30 | 1 | Palashbari | 1048
P8-KS-S06-M | P8-KS-S06-M | 406.a/407.c | MPSB/MB/1525 | Mb | 1 | 3 | 2026-04-14 | IPC - 30 | 1 | Palashbari | 1049
P8-KS-S06-M | P8-KS-S06-M | 406.a/407.c | MPSB/Sur/3298 | Sur | 2 | 3 | 2026-04-14 | IPC - 30 | 1 | Palashbari | 1049
P8-KS-S06-M | P8-KS-S06-M | 406.a/407.c | MPSB/MB/1544 | Mb | 3 | 3 | 2026-04-16 | IPC - 30 | 1 | Palashbari | 1049
P8-KS-S07-M | P8-KS-S07-M | 406.a/407.c | MPSB/MB/1569 | Mb | 1 | 3 | 2026-04-18 | IPC - 30 | 1 | Palashbari | 1050
P8-KS-S07-M | P8-KS-S07-M | 406.a/407.c | MPSB/Sur/3325 | Sur | 2 | 3 | 2026-04-18 | IPC - 30 | 1 | Palashbari | 1050
P8-KS-S07-M | P8-KS-S07-M | 406.a/407.c | MPSB/MB/1570 | Mb | 3 | 3 | 2026-04-18 | IPC - 30 | 1 | Palashbari | 1050
P9-KS-S09-O | P9-KS-S09-O© | 406.a/407.c/408.c | MPSB/MB/1474 | Mb | 1 | 3 | 2026-04-10 | IPC - 30 | 1 | Palashbari | 1051
P9-KS-S09-O | P9-KS-S09-O© | 406.a/407.c/408.c | MPSB/Sur/3272 | Sur | 2 | 3 | 2026-04-10 | IPC - 30 | 1 | Palashbari | 1051
P9-KS-S09-O | P9-KS-S09-O© | 406.a/407.c/408.c | MPSB/MB/1490 | Mb | 3 | 3 | 2026-04-10 | IPC - 30 | 1 | Palashbari | 1051
P9-KS-S10-O | P9-KS-S10-O | 406.a/407.c | MPSB/MB/1531 | Mb | 1 | 3 | 2026-04-14 | IPC - 30 | 1 | Palashbari | 1052
P9-KS-S10-O | P9-KS-S10-O | 406.a/407.c | MPSB/Sur/3306 | Sur | 2 | 3 | 2026-04-15 | IPC - 30 | 1 | Palashbari | 1052
P9-KS-S10-O | P9-KS-S10-O | 406.a/407.c | MPSB/MB/1534 | Mb | 3 | 3 | 2026-04-15 | IPC - 30 | 1 | Palashbari | 1052
P9-KS-S11-O | P9-KS-S11-O© | 406.a/407.c/408.c | MPSB/MB/1558 | Mb | 1 | 3 | 2026-04-17 | IPC - 30 | 1 | Palashbari | 1053
P9-KS-S11-O | P9-KS-S11-O© | 406.a/407.c/408.c | MPSB/Sur/3326 | Sur | 2 | 3 | 2026-04-18 | IPC - 30 | 1 | Palashbari | 1053
P9-KS-S11-O | P9-KS-S11-O© | 406.a/407.c/408.c | MPSB/MB/1573 | Mb | 3 | 3 | 2026-04-18 | IPC - 30 | 1 | Palashbari | 1053
P9-KS-S12-O | P9-KS-S12-O | 406.a/407.c | MPSB/MB/1605 | Mb | 1 | 3 | 2026-04-21 | IPC - 30 | 1 | Palashbari | 1054
P9-KS-S12-O | P9-KS-S12-O | 406.a/407.c | MPSB/Sur/3335 | Sur | 2 | 3 | 2026-04-21 | IPC - 30 | 1 | Palashbari | 1054
P9-KS-S12-O | P9-KS-S12-O | 406.a/407.c | MPSB/MB/1606 | Mb | 3 | 3 | 2026-04-21 | IPC - 30 | 1 | Palashbari | 1054
P9-KS-S13-O | P9-KS-S13-O© | 406.a/407.c/408.c | MPSB/MB/1619 | Mb | 1 | 3 | 2026-04-23 | IPC - 30 | 1 | Palashbari | 1055
P9-KS-S13-O | P9-KS-S13-O© | 406.a/407.c/408.c | MPSB/Sur/3345 | Sur | 2 | 3 | 2026-04-24 | IPC - 30 | 1 | Palashbari | 1055
P9-KS-S13-O | P9-KS-S13-O© | 406.a/407.c/408.c | MPSB/MB/1621 | Mb | 3 | 3 | 2026-04-24 | IPC - 30 | 1 | Palashbari | 1055
P9-KS-S14-O | P9-KS-S14-O | 406.a/407.c | MPSB/MB/1636 | Mb | 1 | 3 | 2026-04-25 | IPC - 30 | 1 | Palashbari | 1056
P9-KS-S14-O | P9-KS-S14-O | 406.a/407.c | MPSB/Sur/3365 | Sur | 2 | 3 | 2026-04-27 | IPC - 30 | 1 | Palashbari | 1056
P9-KS-S14-O | P9-KS-S14-O | 406.a/407.c | MPSB/MB/1652 | Mb | 3 | 3 | 2026-04-27 | IPC - 30 | 1 | Palashbari | 1056
P9-KS-S15-O | P9-KS-S15-O© | 406.a/407.c/408.c | MPSB/MB/1668 | Mb | 1 | 3 | 2026-04-29 | IPC - 30 | 1 | Palashbari | 1057
P9-KS-S15-O | P9-KS-S15-O© | 406.a/407.c/408.c | MPSB/Sur/3401 | Sur | 2 | 3 | 2026-04-30 | IPC - 30 | 1 | Palashbari | 1057
P9-KS-S15-O | P9-KS-S15-O© | 406.a/407.c/408.c | MPSB/MB/1680 | Mb | 3 | 3 | 2026-04-30 | IPC - 30 | 1 | Palashbari | 1057
P9-KS-S22-O | P9-KS-S22-O | 406.a/407.c | MPSB/MB/1637 | Mb | 1 | 3 | 2026-04-25 | IPC - 30 | 1 | Palashbari | 1058
P9-KS-S22-O | P9-KS-S22-O | 406.a/407.c | MPSB/Sur/3386 | Sur | 2 | 3 | 2026-04-29 | IPC - 30 | 1 | Palashbari | 1058
P9-KS-S22-O | P9-KS-S22-O | 406.a/407.c | MPSB/MB/1667 | Mb | 3 | 3 | 2026-04-29 | IPC - 30 | 1 | Palashbari | 1058
P9-BP-S22a-O | P9-BP-S22a-O | 406.a/407.c | MPSB/MB/1451 | Mb | 1 | 3 | 2026-04-07 | IPC - 30 | 1 | Palashbari | 1059
P9-BP-S22a-O | P9-BP-S22a-O | 406.a/407.c | MPSB/Sur/3256 | Sur | 2 | 3 | 2026-04-07 | IPC - 30 | 1 | Palashbari | 1059
P9-BP-S22a-O | P9-BP-S22a-O | 406.a/407.c | MPSB/MB/1453 | Mb | 3 | 3 | 2026-04-07 | IPC - 30 | 1 | Palashbari | 1059
P9-BP-S23a-O | P9-BP-S23a-O© | 406.a/407.c/408.c | MPSB/MB/1471 | Mb | 1 | 3 | 2026-04-08 | IPC - 30 | 1 | Palashbari | 1060
P9-BP-S23a-O | P9-BP-S23a-O© | 406.a/407.c/408.c | MPSB/Sur/3275 | Sur | 2 | 3 | 2026-04-11 | IPC - 30 | 1 | Palashbari | 1060
P9-BP-S23a-O | P9-BP-S23a-O© | 406.a/407.c/408.c | MPSB/MB/1493 | Mb | 3 | 3 | 2026-04-11 | IPC - 30 | 1 | Palashbari | 1060
P9-BP-S24a-O | P9-BP-S24a-O | 406.a/407.c | MPSB/MB/1516 | Mb | 1 | 3 | 2026-04-13 | IPC - 30 | 1 | Palashbari | 1061
P9-BP-S24a-O | P9-BP-S24a-O | 406.a/407.c | MPSB/Sur/3297 | Sur | 2 | 3 | 2026-04-14 | IPC - 30 | 1 | Palashbari | 1061
P9-BP-S24a-O | P9-BP-S24a-O | 406.a/407.c | MPSB/MB/1524 | Mb | 3 | 3 | 2026-04-14 | IPC - 30 | 1 | Palashbari | 1061
P9-BP-S25a-O | P9-BP-S25a-O© | 406.a/407.c/408.c | MPSB/MB/1545 | Mb | 1 | 3 | 2026-04-16 | IPC - 30 | 1 | Palashbari | 1062
P9-BP-S25a-O | P9-BP-S25a-O© | 406.a/407.c/408.c | MPSB/Sur/3313 | Sur | 2 | 3 | 2026-04-17 | IPC - 30 | 1 | Palashbari | 1062
P9-BP-S25a-O | P9-BP-S25a-O© | 406.a/407.c/408.c | MPSB/MB/1557 | Mb | 3 | 3 | 2026-04-17 | IPC - 30 | 1 | Palashbari | 1062
P9-BP-S26a-O | P9-BP-S26a-O | 406.a/407.c | MPSB/MB/1578 | Mb | 1 | 3 | 2026-04-19 | IPC - 30 | 1 | Palashbari | 1063
P9-BP-S26a-O | P9-BP-S26a-O | 406.a/407.c | MPSB/Sur/3330 | Sur | 2 | 3 | 2026-04-20 | IPC - 30 | 1 | Palashbari | 1063
P9-BP-S26a-O | P9-BP-S26a-O | 406.a/407.c | MPSB/MB/1585 | Mb | 3 | 3 | 2026-04-20 | IPC - 30 | 1 | Palashbari | 1063
P9-BP-S27a-O | P9-BP-S27a-O© | 406.a/407.c/408.c | MPSB/MB/1607 | Mb | 1 | 3 | 2026-04-21 | IPC - 30 | 1 | Palashbari | 1064
P9-BP-S27a-O | P9-BP-S27a-O© | 406.a/407.c/408.c | MPSB/Sur/3343 | Sur | 2 | 3 | 2026-04-23 | IPC - 30 | 1 | Palashbari | 1064
P9-BP-S27a-O | P9-BP-S27a-O© | 406.a/407.c/408.c | MPSB/MB/1618 | Mb | 3 | 3 | 2026-04-23 | IPC - 30 | 1 | Palashbari | 1064
P9-BP-S28a-O | P9-BP-S28a-O | 406.a/407.c | MPSB/MB/1638 | Mb | 1 | 3 | 2026-04-25 | IPC - 30 | 1 | Palashbari | 1065
P9-BP-S28a-O | P9-BP-S28a-O | 406.a/407.c | MPSB/Sur/3366 | Sur | 2 | 3 | 2026-04-27 | IPC - 30 | 1 | Palashbari | 1065
P9-BP-S28a-O | P9-BP-S28a-O | 406.a/407.c | MPSB/MB/1653 | Mb | 3 | 3 | 2026-04-27 | IPC - 30 | 1 | Palashbari | 1065
P21-BP-S09a-O | P21-BP-S09a-O© | 406.a/407.c/408.c | MPSB/MB/1641 | Mb | 1 | 3 | 2026-04-25 | IPC - 30 | 1 | Sualkuchi | 1066
P21-BP-S09a-O | P21-BP-S09a-O© | 406.a/407.c/408.c | MPSB/Sur/3377 | Sur | 2 | 3 | 2026-04-28 | IPC - 30 | 1 | Sualkuchi | 1066
P21-BP-S09a-O | P21-BP-S09a-O© | 406.a/407.c/408.c | MPSB/MB/1646 | Mb | 3 | 3 | 2026-04-27 | IPC - 30 | 1 | Sualkuchi | 1066
P21-BP-S10a-O | P21-BP-S10a-O | 406.a/407.c | MPSB/MB/1673 | Mb | 1 | 3 | 2026-04-30 | IPC - 30 | 1 | Sualkuchi | 1067
P21-BP-S10a-O | P21-BP-S10a-O | 406.a/407.c | MPSB/Sur/3392 | Sur | 2 | 3 | 2026-04-30 | IPC - 30 | 1 | Sualkuchi | 1067
P21-BP-S10a-O | P21-BP-S10a-O | 406.a/407.c | MPSB/MB/1676 | Mb | 3 | 3 | 2026-04-30 | IPC - 30 | 1 | Sualkuchi | 1067
P21-KS-S12-O | P21-KS-S12-O | 406.a/407.c | MPSB/MB/1444 | Mb | 1 | 3 | 2026-04-06 | IPC - 30 | 1 | Sualkuchi | 1068
P21-KS-S12-O | P21-KS-S12-O | 406.a/407.c | MPSB/Sur/3248 | Sur | 2 | 3 | 2026-04-06 | IPC - 30 | 1 | Sualkuchi | 1068
P21-KS-S12-O | P21-KS-S12-O | 406.a/407.c | MPSB/MB/1445 | Mb | 3 | 3 | 2026-04-06 | IPC - 30 | 1 | Sualkuchi | 1068
P21-KS-S13-O | P21-KS-S13-O© | 406.a/407.c/408.c | MPSB/MB/1465 | Mb | 1 | 3 | 2026-04-07 | IPC - 30 | 1 | Sualkuchi | 1069
P21-KS-S13-O | P21-KS-S13-O© | 406.a/407.c/408.c | MPSB/Sur/3268 | Sur | 2 | 3 | 2026-04-10 | IPC - 30 | 1 | Sualkuchi | 1069
P21-KS-S13-O | P21-KS-S13-O© | 406.a/407.c/408.c | MPSB/MB/1487 | Mb | 3 | 3 | 2026-04-10 | IPC - 30 | 1 | Sualkuchi | 1069
P21-KS-S14-O | P21-KS-S14-O | 406.a/407.c | MPSB/MB/1491 | Mb | 1 | 3 | 2026-04-10 | IPC - 30 | 1 | Sualkuchi | 1070
P21-KS-S14-O | P21-KS-S14-O | 406.a/407.c | MPSB/Sur/3288 | Sur | 2 | 3 | 2026-04-13 | IPC - 30 | 1 | Sualkuchi | 1070
P21-KS-S14-O | P21-KS-S14-O | 406.a/407.c | MPSB/MB/1511 | Mb | 3 | 3 | 2026-04-13 | IPC - 30 | 1 | Sualkuchi | 1070
P23-KS-S08a-O | P23-KS-S08a-O | 406.a/407.c | MPSB/MB/1443 | Mb | 1 | 3 | 2026-04-06 | IPC - 30 | 1 | Sualkuchi | 1071
P23-KS-S08a-O | P23-KS-S08a-O | 406.a/407.c | MPSB/Sur/3257 | Sur | 2 | 3 | 2026-04-07 | IPC - 30 | 1 | Sualkuchi | 1071
P23-KS-S08a-O | P23-KS-S08a-O | 406.a/407.c | MPSB/MB/1467 | Mb | 3 | 3 | 2026-04-07 | IPC - 30 | 1 | Sualkuchi | 1071
P23-BP-S34-O | P23-BP-S34-O | 406.a/407.c | MPSB/MB/1488 | Mb | 1 | 3 | 2026-04-10 | IPC - 30 | 1 | Sualkuchi | 1072
P23-BP-S34-O | P23-BP-S34-O | 406.a/407.c | MPSB/Sur/3277 | Sur | 2 | 3 | 2026-04-11 | IPC - 30 | 1 | Sualkuchi | 1072
P23-BP-S34-O | P23-BP-S34-O | 406.a/407.c | MPSB/MB/1500 | Mb | 3 | 3 | 2026-04-11 | IPC - 30 | 1 | Sualkuchi | 1072
P23-BP-S33-O | P23-BP-S33-O© | 406.a/407.c/408.c | MPSB/Sur/3258 | Sur | 1 | 2 | 2026-04-08 | IPC - 30 | 1 | Sualkuchi | 1073
P23-BP-S33-O | P23-BP-S33-O© | 406.a/407.c/408.c | MPSB/MB/1472 | Mb | 2 | 2 | 2026-04-08 | IPC - 30 | 1 | Sualkuchi | 1073
P24-BP-S17-M | P24-BP-S17-M | 406.a/407.c | MPSB/MB/1672 | Mb | 1 | 3 | 2026-04-30 | IPC - 30 | 1 | Sualkuchi | 1074
P24-BP-S17-M | P24-BP-S17-M | 406.a/407.c | MPSB/Sur/3391 | Sur | 2 | 3 | 2026-04-30 | IPC - 30 | 1 | Sualkuchi | 1074
P24-BP-S17-M | P24-BP-S17-M | 406.a/407.c | MPSB/MB/1675 | Mb | 3 | 3 | 2026-04-30 | IPC - 30 | 1 | Sualkuchi | 1074
P24-BP-S16-M | P24-BP-S16-M© | 406.a/407.c/408.c | MPSB/MB/1664 | Mb | 1 | 3 | 2026-04-29 | IPC - 30 | 1 | Sualkuchi | 1075
P24-BP-S16-M | P24-BP-S16-M© | 406.a/407.c/408.c | MPSB/Sur/3390 | Sur | 2 | 3 | 2026-04-30 | IPC - 30 | 1 | Sualkuchi | 1075
P24-BP-S16-M | P24-BP-S16-M© | 406.a/407.c/408.c | MPSB/MB/1674 | Mb | 3 | 3 | 2026-04-30 | IPC - 30 | 1 | Sualkuchi | 1075
P24-BP-S15-M | P24-BP-S15-M | 406.a/407.c | MPSB/MB/1631 | Mb | 1 | 3 | 2026-04-24 | IPC - 30 | 1 | Sualkuchi | 1076
P24-BP-S15-M | P24-BP-S15-M | 406.a/407.c | MPSB/Sur/3364 | Sur | 2 | 3 | 2026-04-27 | IPC - 30 | 1 | Sualkuchi | 1076
P24-BP-S15-M | P24-BP-S15-M | 406.a/407.c | MPSB/MB/1645 | Mb | 3 | 3 | 2026-04-27 | IPC - 30 | 1 | Sualkuchi | 1076
P24-BP-S14-M | P24-BP-S14-M© | 406.a/407.c/408.c | MPSB/MB/1593 | Mb | 1 | 3 | 2026-04-20 | IPC - 30 | 1 | Sualkuchi | 1077
P24-BP-S14-M | P24-BP-S14-M© | 406.a/407.c/408.c | MPSB/Sur/3346 | Sur | 2 | 3 | 2026-04-24 | IPC - 30 | 1 | Sualkuchi | 1077
P24-BP-S14-M | P24-BP-S14-M© | 406.a/407.c/408.c | MPSB/MB/1630 | Mb | 3 | 3 | 2026-04-24 | IPC - 30 | 1 | Sualkuchi | 1077
P24-BP-S13-M | P24-BP-S13-M | 406.a/407.c | MPSB/MB/1560 | Mb | 1 | 3 | 2026-04-17 | IPC - 30 | 1 | Sualkuchi | 1078
P24-BP-S13-M | P24-BP-S13-M | 406.a/407.c | MPSB/Sur/3332 | Sur | 2 | 3 | 2026-04-20 | IPC - 30 | 1 | Sualkuchi | 1078
P24-BP-S13-M | P24-BP-S13-M | 406.a/407.c | MPSB/MB/1594 | Mb | 3 | 3 | 2026-04-20 | IPC - 30 | 1 | Sualkuchi | 1078
P24-BP-S12-M | P24-BP-S12-M© | 406.a/407.c/408.c | MPSB/MB/1536 | Mb | 1 | 3 | 2026-04-15 | IPC - 30 | 1 | Sualkuchi | 1079
P24-BP-S12-M | P24-BP-S12-M© | 406.a/407.c/408.c | MPSB/Sur/3314 | Sur | 2 | 3 | 2026-04-17 | IPC - 30 | 1 | Sualkuchi | 1079
P24-BP-S12-M | P24-BP-S12-M© | 406.a/407.c/408.c | MPSB/MB/1561 | Mb | 3 | 3 | 2026-04-17 | IPC - 30 | 1 | Sualkuchi | 1079
P24-BP-S11-M | P24-BP-S11-M | 406.a/407.c | MPSB/MB/1498 | Mb | 1 | 3 | 2026-04-11 | IPC - 30 | 1 | Sualkuchi | 1080
P24-BP-S11-M | P24-BP-S11-M | 406.a/407.c | MPSB/Sur/3289 | Sur | 2 | 3 | 2026-04-13 | IPC - 30 | 1 | Sualkuchi | 1080
P24-BP-S11-M | P24-BP-S11-M | 406.a/407.c | MPSB/MB/1513 | Mb | 3 | 3 | 2026-04-13 | IPC - 30 | 1 | Sualkuchi | 1080
P24-BP-S10-M | P24-BP-S10-M© | 406.a/407.c/408.c | MPSB/MB/1485 | Mb | 1 | 3 | 2026-04-10 | IPC - 30 | 1 | Sualkuchi | 1081
P24-BP-S10-M | P24-BP-S10-M© | 406.a/407.c/408.c | MPSB/Sur/3267 | Sur | 2 | 3 | 2026-04-10 | IPC - 30 | 1 | Sualkuchi | 1081
P24-BP-S10-M | P24-BP-S10-M© | 406.a/407.c/408.c | MPSB/MB/1486 | Mb | 3 | 3 | 2026-04-10 | IPC - 30 | 1 | Sualkuchi | 1081
P24-BP-S09-M | P24-BP-S09-M | 406.a/407.c | MPSB/MB/1416 | Mb | 1 | 3 | 2026-03-31 | IPC - 30 | 1 | Sualkuchi | 1082
P24-BP-S09-M | P24-BP-S09-M | 406.a/407.c | MPSB/Sur/3249 | Sur | 2 | 3 | 2026-04-06 | IPC - 30 | 1 | Sualkuchi | 1082
P24-BP-S09-M | P24-BP-S09-M | 406.a/407.c | MPSB/MB/1446 | Mb | 3 | 3 | 2026-04-06 | IPC - 30 | 1 | Sualkuchi | 1082
P25-BP-S01a-O | P25-BP-S01a-O | 406.a/407.c | MPSB/MB/1497 | Mb | 1 | 3 | 2026-04-11 | IPC - 30 | 1 | Sualkuchi | 1083
P25-BP-S01a-O | P25-BP-S01a-O | 406.a/407.c | MPSB/Sur/3315 | Sur | 2 | 3 | 2026-04-17 | IPC - 30 | 1 | Sualkuchi | 1083
P25-BP-S01a-O | P25-BP-S01a-O | 406.a/407.c | MPSB/MB/1566 | Mb | 3 | 3 | 2026-04-17 | IPC - 30 | 1 | Sualkuchi | 1083
P25-BP-S02a-O | P25-BP-S02a-O | 406.a/407.c | MPSB/MB/1596 | Mb | 1 | 3 | 2026-04-20 | IPC - 30 | 1 | Sualkuchi | 1084
P25-BP-S02a-O | P25-BP-S02a-O | 406.a/407.c | MPSB/Sur/3384 | Sur | 2 | 3 | 2026-04-29 | IPC - 30 | 1 | Sualkuchi | 1084
P25-BP-S02a-O | P25-BP-S02a-O | 406.a/407.c | MPSB/MB/1663 | Mb | 3 | 3 | 2026-04-29 | IPC - 30 | 1 | Sualkuchi | 1084
P25-BP-S03a-O | P25-BP-S03a-O | 406.a/407.c | MPSB/MB/1666 | Mb | 1 | 3 | 2026-04-29 | IPC - 30 | 1 | Sualkuchi | 1085
P25-BP-S03a-O | P25-BP-S03a-O | 406.a/407.c | MPSB/Sur/3389 | Sur | 2 | 3 | 2026-04-30 | IPC - 30 | 1 | Sualkuchi | 1085
P25-BP-S03a-O | P25-BP-S03a-O | 406.a/407.c | MPSB/MB/1671 | Mb | 3 | 3 | 2026-04-30 | IPC - 30 | 1 | Sualkuchi | 1085
P9-KS-S16-O | P9-KS-S16-O | 406.a/407.c | MPSB/MB/1686 | Mb | 1 | 3 | 2026-05-02 | IPC - 31 | 1 | Palashbari | 1086
P9-KS-S16-O | P9-KS-S16-O | 406.a/407.c | MPSB/Sur/3417 | Sur | 2 | 3 | 2026-05-05 | IPC - 31 | 1 | Palashbari | 1086
P9-KS-S16-O | P9-KS-S16-O | 406.a/407.c | MPSB/MB/1701 | Mb | 3 | 3 | 2026-05-05 | IPC - 31 | 1 | Palashbari | 1086
P9-KS-S17-O | P9-KS-S17-O© | 406.a/407.c/408.c | MPSB/MB/1721 | Mb | 1 | 3 | 2026-05-08 | IPC - 31 | 1 | Palashbari | 1087
P9-KS-S17-O | P9-KS-S17-O© | 406.a/407.c/408.c | MPSB/Sur/3459 | Sur | 2 | 3 | 2026-05-11 | IPC - 31 | 1 | Palashbari | 1087
P9-KS-S17-O | P9-KS-S17-O© | 406.a/407.c/408.c | MPSB/MB/1743 | Mb | 3 | 3 | 2026-05-11 | IPC - 31 | 1 | Palashbari | 1087
P9-KS-S18-O | P9-KS-S18-O | 406.a/407.c | MPSB/MB/1758 | Mb | 1 | 3 | 2026-05-14 | IPC - 31 | 1 | Palashbari | 1088
P9-KS-S18-O | P9-KS-S18-O | 406.a/407.c | MPSB/Sur/3487 | Sur | 2 | 3 | 2026-05-16 | IPC - 31 | 1 | Palashbari | 1088
P9-KS-S18-O | P9-KS-S18-O | 406.a/407.c | MPSB/MB/1776 | Mb | 3 | 3 | 2026-05-16 | IPC - 31 | 1 | Palashbari | 1088
P9-KS-S19-O | P9-KS-S19-O© | 406.a/407.c/408.c | MPSB/MB/1807 | Mb | 1 | 3 | 2026-05-20 | IPC - 31 | 1 | Palashbari | 1089
P9-KS-S19-O | P9-KS-S19-O© | 406.a/407.c/408.c | MPSB/Sur/3525 | Sur | 2 | 3 | 2026-05-21 | IPC - 31 | 1 | Palashbari | 1089
P9-KS-S19-O | P9-KS-S19-O© | 406.a/407.c/408.c | MPSB/MB/1817 | Mb | 3 | 3 | 2026-05-21 | IPC - 31 | 1 | Palashbari | 1089
P9-KS-S23-O | P9-KS-S23-O© | 406.a/407.c/408.c | MPSB/MB/1698 | Mb | 1 | 3 | 2026-05-05 | IPC - 31 | 1 | Palashbari | 1090
P9-KS-S23-O | P9-KS-S23-O© | 406.a/407.c/408.c | MPSB/Sur/3425 | Sur | 2 | 3 | 2026-05-07 | IPC - 31 | 1 | Palashbari | 1090
P9-KS-S23-O | P9-KS-S23-O© | 406.a/407.c/408.c | MPSB/MB/1712 | Mb | 3 | 3 | 2026-05-07 | IPC - 31 | 1 | Palashbari | 1090
P9-KS-S24-O | P9-KS-S24-O | 406.a/407.c | MPSB/MB/1741 | Mb | 1 | 3 | 2026-05-11 | IPC - 31 | 1 | Palashbari | 1091
P9-KS-S24-O | P9-KS-S24-O | 406.a/407.c | MPSB/Sur/3467 | Sur | 2 | 3 | 2026-05-12 | IPC - 31 | 1 | Palashbari | 1091
P9-KS-S24-O | P9-KS-S24-O | 406.a/407.c | MPSB/MB/1748 | Mb | 3 | 3 | 2026-05-12 | IPC - 31 | 1 | Palashbari | 1091
P9-KS-S25-O | P9-KS-S25-O© | 406.a/407.c/408.c | MPSB/MB/1784 | Mb | 1 | 3 | 2026-05-17 | IPC - 31 | 1 | Palashbari | 1092
P9-KS-S25-O | P9-KS-S25-O© | 406.a/407.c/408.c | MPSB/Sur/3505 | Sur | 2 | 3 | 2026-05-18 | IPC - 31 | 1 | Palashbari | 1092
P9-KS-S25-O | P9-KS-S25-O© | 406.a/407.c/408.c | MPSB/MB/1795 | Mb | 3 | 3 | 2026-05-18 | IPC - 31 | 1 | Palashbari | 1092
P9-KS-S26-O | P9-KS-S26-O | 406.a/407.c | MPSB/MB/1836 | Mb | 1 | 3 | 2026-05-23 | IPC - 31 | 1 | Palashbari | 1093
P9-KS-S26-O | P9-KS-S26-O | 406.a/407.c | MPSB/Sur/3553 | Sur | 2 | 3 | 2026-05-26 | IPC - 31 | 1 | Palashbari | 1093
P9-KS-S26-O | P9-KS-S26-O | 406.a/407.c | MPSB/MB/1852 | Mb | 3 | 3 | 2026-05-26 | IPC - 31 | 1 | Palashbari | 1093
P9-BP-S29a-O | P9-BP-S29a-O© | 406.a/407.c/408.c | MPSB/MB/1681 | Mb | 1 | 3 | 2026-04-30 | IPC - 31 | 1 | Palashbari | 1094
P9-BP-S29a-O | P9-BP-S29a-O© | 406.a/407.c/408.c | MPSB/Sur/3412 | Sur | 2 | 3 | 2026-05-04 | IPC - 31 | 1 | Palashbari | 1094
P9-BP-S29a-O | P9-BP-S29a-O© | 406.a/407.c/408.c | MPSB/MB/1691 | Mb | 3 | 3 | 2026-05-04 | IPC - 31 | 1 | Palashbari | 1094
P9-BP-S30a-O | P9-BP-S30a-O | 406.a/407.c | MPSB/MB/1720 | Mb | 1 | 3 | 2026-05-08 | IPC - 31 | 1 | Palashbari | 1095
P9-BP-S30a-O | P9-BP-S30a-O | 406.a/407.c | MPSB/Sur/3442 | Sur | 2 | 3 | 2026-05-09 | IPC - 31 | 1 | Palashbari | 1095
P9-BP-S30a-O | P9-BP-S30a-O | 406.a/407.c | MPSB/MB/1729 | Mb | 3 | 3 | 2026-05-09 | IPC - 31 | 1 | Palashbari | 1095
P9-BP-S31a-O | P9-BP-S31a-O© | 406.a/407.c/408.c | MPSB/MB/1753 | Mb | 1 | 3 | 2026-05-13 | IPC - 31 | 1 | Palashbari | 1096
P9-BP-S31a-O | P9-BP-S31a-O© | 406.a/407.c/408.c | MPSB/Sur/3493 | Sur | 2 | 3 | 2026-05-16 | IPC - 31 | 1 | Palashbari | 1096
P9-BP-S31a-O | P9-BP-S31a-O© | 406.a/407.c/408.c | MPSB/MB/1783 | Mb | 3 | 3 | 2026-05-16 | IPC - 31 | 1 | Palashbari | 1096
P9-BP-S32a-O | P9-BP-S32a-O | 406.a/407.c | MPSB/MB/1808 | Mb | 1 | 3 | 2026-05-20 | IPC - 31 | 1 | Palashbari | 1097
P9-BP-S32a-O | P9-BP-S32a-O | 406.a/407.c | MPSB/Sur/3531 | Sur | 2 | 3 | 2026-05-22 | IPC - 31 | 1 | Palashbari | 1097
P9-BP-S32a-O | P9-BP-S32a-O | 406.a/407.c | MPSB/MB/1824 | Mb | 3 | 3 | 2026-05-22 | IPC - 31 | 1 | Palashbari | 1097
P9-BP-S33a-O | P9-BP-S33a-O© | 406.a/407.c/408.c | MPSB/MB/1843 | Mb | 1 | 3 | 2026-05-25 | IPC - 31 | 1 | Palashbari | 1098
P9-BP-S33a-O | P9-BP-S33a-O© | 406.a/407.c/408.c | MPSB/Sur/3592 | Sur | 2 | 3 | 2026-05-31 | IPC - 31 | 1 | Palashbari | 1098
P9-BP-S33a-O | P9-BP-S33a-O© | 406.a/407.c/408.c | MPSB/MB/1888 | Mb | 3 | 3 | 2026-05-31 | IPC - 31 | 1 | Palashbari | 1098
P8-BP-S03-M | P8-BP-S03-M | 406.a/407.c | MPSB/MB/1687 | Mb | 1 | 3 | 2026-05-02 | IPC - 31 | 1 | Palashbari | 1099
P8-BP-S03-M | P8-BP-S03-M | 406.a/407.c | MPSB/Sur/3414 | Sur | 2 | 3 | 2026-05-04 | IPC - 31 | 1 | Palashbari | 1099
P8-BP-S03-M | P8-BP-S03-M | 406.a/407.c | MPSB/MB/1696 | Mb | 3 | 3 | 2026-05-04 | IPC - 31 | 1 | Palashbari | 1099
P8-BP-S04-M | P8-BP-S04-M | 406.a/407.c | MPSB/MB/1700 | Mb | 1 | 3 | 2026-05-05 | IPC - 31 | 1 | Palashbari | 1100
P8-BP-S04-M | P8-BP-S04-M | 406.a/407.c | MPSB/Sur/3426 | Sur | 2 | 3 | 2026-05-07 | IPC - 31 | 1 | Palashbari | 1100
P8-BP-S04-M | P8-BP-S04-M | 406.a/407.c | MPSB/MB/1713 | Mb | 3 | 3 | 2026-05-07 | IPC - 31 | 1 | Palashbari | 1100
P8-BP-S05-M | P8-BP-S05-M | 406.a/407.c | MPSB/MB/1742 | Mb | 1 | 3 | 2026-05-11 | IPC - 31 | 1 | Palashbari | 1101
P8-BP-S05-M | P8-BP-S05-M | 406.a/407.c | MPSB/Sur/3473 | Sur | 2 | 3 | 2026-05-13 | IPC - 31 | 1 | Palashbari | 1101
P8-BP-S05-M | P8-BP-S05-M | 406.a/407.c | MPSB/MB/1752 | Mb | 3 | 3 | 2026-05-13 | IPC - 31 | 1 | Palashbari | 1101
P8-BP-S06-M | P8-BP-S06-M | 406.a/407.c | MPSB/MB/1785 | Mb | 1 | 3 | 2026-05-17 | IPC - 31 | 1 | Palashbari | 1102
P8-BP-S06-M | P8-BP-S06-M | 406.a/407.c | MPSB/Sur/3518 | Sur | 2 | 3 | 2026-05-20 | IPC - 31 | 1 | Palashbari | 1102
P8-BP-S06-M | P8-BP-S06-M | 406.a/407.c | MPSB/MB/1806 | Mb | 3 | 3 | 2026-05-20 | IPC - 31 | 1 | Palashbari | 1102
P8-BP-S07-M | P8-BP-S07-M | 406.a/407.c | MPSB/MB/1825 | Mb | 1 | 3 | 2026-05-22 | IPC - 31 | 1 | Palashbari | 1103
P8-BP-S07-M | P8-BP-S07-M | 406.a/407.c | MPSB/Sur/3539 | Sur | 2 | 3 | 2026-05-23 | IPC - 31 | 1 | Palashbari | 1103
P8-BP-S07-M | P8-BP-S07-M | 406.a/407.c | MPSB/MB/1837 | Mb | 3 | 3 | 2026-05-23 | IPC - 31 | 1 | Palashbari | 1103
P16-BP-S08-M | P16-BP-S08-M© | 406.a/407.c/408.c | MPSB/MB/1685 | Mb | 1 | 2 | 2026-05-02 | IPC - 31 | 1 | Palashbari | 1104
P16-BP-S08-M | P16-BP-S08-M© | 406.a/407.c/408.c | MPSB/MB/1690 | Mb | 2 | 2 | 2026-05-04 | IPC - 31 | 1 | Palashbari | 1104
P16-BP-S09-M | P16-BP-S09-M | 406.a/407.c | MPSB/MB/1709 | Mb | 1 | 3 | 2026-05-06 | IPC - 31 | 1 | Palashbari | 1105
P16-BP-S09-M | P16-BP-S09-M | 406.a/407.c | MPSB/Sur/3424 | Sur | 2 | 3 | 2026-05-07 | IPC - 31 | 1 | Palashbari | 1105
P16-BP-S09-M | P16-BP-S09-M | 406.a/407.c | MPSB/MB/1711 | Mb | 3 | 3 | 2026-05-07 | IPC - 31 | 1 | Palashbari | 1105
P16-BP-S10-M | P16-BP-S10-M© | 406.a/407.c/408.c | MPSB/MB/1744 | Mb | 1 | 3 | 2026-05-11 | IPC - 31 | 1 | Palashbari | 1106
P16-BP-S10-M | P16-BP-S10-M© | 406.a/407.c/408.c | MPSB/Sur/3472 | Sur | 2 | 3 | 2026-05-13 | IPC - 31 | 1 | Palashbari | 1106
P16-BP-S10-M | P16-BP-S10-M© | 406.a/407.c/408.c | MPSB/MB/1751 | Mb | 3 | 3 | 2026-05-13 | IPC - 31 | 1 | Palashbari | 1106
P16-BP-S11-M | P16-BP-S11-M | 406.a/407.c | MPSB/MB/1768 | Mb | 1 | 3 | 2026-05-15 | IPC - 31 | 1 | Palashbari | 1107
P16-BP-S11-M | P16-BP-S11-M | 406.a/407.c | MPSB/Sur/3517 | Sur | 2 | 3 | 2026-05-20 | IPC - 31 | 1 | Palashbari | 1107
P16-BP-S11-M | P16-BP-S11-M | 406.a/407.c | MPSB/MB/1805 | Mb | 3 | 3 | 2026-05-20 | IPC - 31 | 1 | Palashbari | 1107
P16-BP-S12-M | P16-BP-S12-M© | 406.a/407.c/408.c | MPSB/MB/1835 | Mb | 1 | 3 | 2026-05-23 | IPC - 31 | 1 | Palashbari | 1108
P16-BP-S12-M | P16-BP-S12-M© | 406.a/407.c/408.c | MPSB/Sur/3548 | Sur | 2 | 3 | 2026-05-25 | IPC - 31 | 1 | Palashbari | 1108
P16-BP-S12-M | P16-BP-S12-M© | 406.a/407.c/408.c | MPSB/MB/1844 | Mb | 3 | 3 | 2026-05-25 | IPC - 31 | 1 | Palashbari | 1108
P21-KS-S15-O | P21-KS-S15-O© | 406.a/407.c/408.c | MPSB/MB/1706 | Mb | 1 | 3 | 2026-05-05 | IPC - 31 | 1 | Sualkuchi | 1109
P21-KS-S15-O | P21-KS-S15-O© | 406.a/407.c/408.c | MPSB/Sur/3427 | Sur | 2 | 3 | 2026-05-07 | IPC - 31 | 1 | Sualkuchi | 1109 | P21-KS-S16-O
P21-KS-S15-O | P21-KS-S15-O© | 406.a/407.c/408.c | MPSB/MB/1716 | Mb | 3 | 3 | 2026-05-07 | IPC - 31 | 1 | Sualkuchi | 1109
P21-KS-S16-O | P21-KS-S16-O | 406.a/407.c | MPSB/MB/1735 | Mb | 1 | 3 | 2026-05-09 | IPC - 31 | 1 | Sualkuchi | 1110
P21-KS-S16-O | P21-KS-S16-O | 406.a/407.c | MPSB/Sur/3427 | Sur | 2 | 3 | 2026-05-12 | IPC - 31 | 1 | Sualkuchi | 1110 | P21-KS-S15-O
P21-KS-S16-O | P21-KS-S16-O | 406.a/407.c | MPSB/MB/1747 | Mb | 3 | 3 | 2026-05-12 | IPC - 31 | 1 | Sualkuchi | 1110
P21-KS-S17-O | P21-KS-S17-O© | 406.a/407.c/408.c | MPSB/MB/1761 | Mb | 1 | 3 | 2026-05-14 | IPC - 31 | 1 | Sualkuchi | 1111
P21-KS-S17-O | P21-KS-S17-O© | 406.a/407.c/408.c | MPSB/Sur/3488 | Sur | 2 | 3 | 2026-05-16 | IPC - 31 | 1 | Sualkuchi | 1111
P21-KS-S17-O | P21-KS-S17-O© | 406.a/407.c/408.c | MPSB/MB/1777 | Mb | 3 | 3 | 2026-05-16 | IPC - 31 | 1 | Sualkuchi | 1111
P21-KS-S18-O | P21-KS-S18-O | 406.a/407.c | MPSB/MB/1787 | Mb | 1 | 3 | 2026-05-18 | IPC - 31 | 1 | Sualkuchi | 1112
P21-KS-S18-O | P21-KS-S18-O | 406.a/407.c | MPSB/Sur/3509 | Sur | 2 | 3 | 2026-05-19 | IPC - 31 | 1 | Sualkuchi | 1112
P21-KS-S18-O | P21-KS-S18-O | 406.a/407.c | MPSB/MB/1802 | Mb | 3 | 3 | 2026-05-19 | IPC - 31 | 1 | Sualkuchi | 1112
P21-KS-S19-O | P21-KS-S19-O© | 406.a/407.c/408.c | MPSB/MB/1827 | Mb | 1 | 3 | 2026-05-22 | IPC - 31 | 1 | Sualkuchi | 1113
P21-KS-S19-O | P21-KS-S19-O© | 406.a/407.c/408.c | MPSB/Sur/3562 | Sur | 2 | 3 | 2026-05-27 | IPC - 31 | 1 | Sualkuchi | 1113
P21-KS-S19-O | P21-KS-S19-O© | 406.a/407.c/408.c | MPSB/MB/1863 | Mb | 3 | 3 | 2026-05-27 | IPC - 31 | 1 | Sualkuchi | 1113
P21-KS-S20-O | P21-KS-S20-O | 406.a/407.c | MPSB/MB/1874 | Mb | 1 | 3 | 2026-05-29 | IPC - 31 | 1 | Sualkuchi | 1114
P21-KS-S20-O | P21-KS-S20-O | 406.a/407.c | MPSB/Sur/3579 | Sur | 2 | 3 | 2026-05-30 | IPC - 31 | 1 | Sualkuchi | 1114
P21-KS-S20-O | P21-KS-S20-O | 406.a/407.c | MPSB/MB/1880 | Mb | 3 | 3 | 2026-05-30 | IPC - 31 | 1 | Sualkuchi | 1114 | P21-KS-S22-O
P21-KS-S22-O | P21-KS-S22-O | 406.a/407.c | MPSB/MB/1880 | Mb | 1 | 3 | 2026-05-19 | IPC - 31 | 1 | Sualkuchi | 1115 | P21-KS-S20-O
P21-KS-S22-O | P21-KS-S22-O | 406.a/407.c | MPSB/Sur/3534 | Sur | 2 | 3 | 2026-05-22 | IPC - 31 | 1 | Sualkuchi | 1115
P21-KS-S22-O | P21-KS-S22-O | 406.a/407.c | MPSB/MB/1832 | Mb | 3 | 3 | 2026-05-22 | IPC - 31 | 1 | Sualkuchi | 1115
P21-KS-S23-O | P21-KS-S23-O© | 406.a/407.c/408.c | MPSB/MB/1856 | Mb | 1 | 3 | 2026-05-26 | IPC - 31 | 1 | Sualkuchi | 1116
P21-KS-S23-O | P21-KS-S23-O© | 406.a/407.c/408.c | MPSB/Sur/3554 | Sur | 2 | 3 | 2026-05-26 | IPC - 31 | 1 | Sualkuchi | 1116
P21-KS-S23-O | P21-KS-S23-O© | 406.a/407.c/408.c | MPSB/MB/1857 | Mb | 3 | 3 | 2026-05-26 | IPC - 31 | 1 | Sualkuchi | 1116
P21-KS-S24-O | P21-KS-S24-O | 406.a/407.c | MPSB/MB/1862 | Mb | 1 | 3 | 2026-05-27 | IPC - 31 | 1 | Sualkuchi | 1117
P21-KS-S24-O | P21-KS-S24-O | 406.a/407.c | MPSB/Sur/3569 | Sur | 2 | 3 | 2026-05-29 | IPC - 31 | 1 | Sualkuchi | 1117
P21-KS-S24-O | P21-KS-S24-O | 406.a/407.c | MPSB/MB/1868 | Mb | 3 | 3 | 2026-05-29 | IPC - 31 | 1 | Sualkuchi | 1117
P21-KS-S25-O | P21-KS-S25-O© | 406.a/407.c/408.c | MPSB/MB/1881 | Mb | 1 | 3 | 2026-05-30 | IPC - 31 | 1 | Sualkuchi | 1118
P21-KS-S25-O | P21-KS-S25-O© | 406.a/407.c/408.c | MPSB/Sur/3581 | Sur | 2 | 3 | 2026-05-30 | IPC - 31 | 1 | Sualkuchi | 1118
P21-KS-S25-O | P21-KS-S25-O© | 406.a/407.c/408.c | MPSB/MB/1883 | Mb | 3 | 3 | 2026-05-30 | IPC - 31 | 1 | Sualkuchi | 1118
P21-BP-S11a-O | P21-BP-S11a-O© | 406.a/407.c/408.c | MPSB/MB/1718 | Mb | 1 | 3 | 2026-05-07 | IPC - 31 | 1 | Sualkuchi | 1119
P21-BP-S11a-O | P21-BP-S11a-O© | 406.a/407.c/408.c | MPSB/Sur/3457 | Sur | 2 | 3 | 2026-05-11 | IPC - 31 | 1 | Sualkuchi | 1119
P21-BP-S11a-O | P21-BP-S11a-O© | 406.a/407.c/408.c | MPSB/MB/1737 | Mb | 3 | 3 | 2026-05-11 | IPC - 31 | 1 | Sualkuchi | 1119
P21-BP-S12a-O | P21-BP-S12a-O | 406.a/407.c | MPSB/MB/1738 | Mb | 1 | 2 | 2026-05-11 | IPC - 31 | 1 | Sualkuchi | 1120
P21-BP-S12a-O | P21-BP-S12a-O | 406.a/407.c | MPSB/MB/1762 | Mb | 2 | 2 | 2026-05-14 | IPC - 31 | 1 | Sualkuchi | 1120
P21-BP-S13a-O | P21-BP-S13a-O© | 406.a/407.c/408.c | MPSB/MB/1763 | Mb | 1 | 3 | 2026-05-14 | IPC - 31 | 1 | Sualkuchi | 1121
P21-BP-S13a-O | P21-BP-S13a-O© | 406.a/407.c/408.c | MPSB/Sur/3489 | Sur | 2 | 3 | 2026-05-16 | IPC - 31 | 1 | Sualkuchi | 1121
P21-BP-S13a-O | P21-BP-S13a-O© | 406.a/407.c/408.c | MPSB/MB/1778 | Mb | 3 | 3 | 2026-05-16 | IPC - 31 | 1 | Sualkuchi | 1121
P21-BP-S14a-O | P21-BP-S14a-O | 406.a/407.c | MPSB/MB/1813 | Mb | 1 | 3 | 2026-05-20 | IPC - 31 | 1 | Sualkuchi | 1122
P21-BP-S14a-O | P21-BP-S14a-O | 406.a/407.c | MPSB/Sur/3522 | Sur | 2 | 3 | 2026-05-20 | IPC - 31 | 1 | Sualkuchi | 1122
P21-BP-S14a-O | P21-BP-S14a-O | 406.a/407.c | MPSB/MB/1814 | Mb | 3 | 3 | 2026-05-20 | IPC - 31 | 1 | Sualkuchi | 1122
P21-BP-S15a-O | P21-BP-S15a-O© | 406.a/407.c/408.c | MPSB/MB/1821 | Mb | 1 | 3 | 2026-05-21 | IPC - 31 | 1 | Sualkuchi | 1123
P21-BP-S15a-O | P21-BP-S15a-O© | 406.a/407.c/408.c | MPSB/Sur/3535 | Sur | 2 | 3 | 2026-05-22 | IPC - 31 | 1 | Sualkuchi | 1123
P21-BP-S15a-O | P21-BP-S15a-O© | 406.a/407.c/408.c | MPSB/MB/1833 | Mb | 3 | 3 | 2026-05-22 | IPC - 31 | 1 | Sualkuchi | 1123
P21-BP-S16a-O | P21-BP-S16a-O | 406.a/407.c | MPSB/MB/1845 | Mb | 1 | 3 | 2026-05-25 | IPC - 31 | 1 | Sualkuchi | 1124
P21-BP-S16a-O | P21-BP-S16a-O | 406.a/407.c | MPSB/Sur/3555 | Sur | 2 | 3 | 2026-05-26 | IPC - 31 | 1 | Sualkuchi | 1124
P21-BP-S16a-O | P21-BP-S16a-O | 406.a/407.c | MPSB/MB/1860 | Mb | 3 | 3 | 2026-05-26 | IPC - 31 | 1 | Sualkuchi | 1124
P21-BP-S17a-O | P21-BP-S17a-O© | 406.a/407.c/408.c | MPSB/MB/1872 | Mb | 1 | 3 | 2026-05-29 | IPC - 31 | 1 | Sualkuchi | 1125
P21-BP-S17a-O | P21-BP-S17a-O© | 406.a/407.c/408.c | MPSB/Sur/3571 | Sur | 2 | 3 | 2026-05-29 | IPC - 31 | 1 | Sualkuchi | 1125
P21-BP-S17a-O | P21-BP-S17a-O© | 406.a/407.c/408.c | MPSB/MB/1873 | Mb | 3 | 3 | 2026-05-29 | IPC - 31 | 1 | Sualkuchi | 1125
P23-BP-S01-O | P23-BP-S01-O | 406.a/407.c | MPSB/MB/1865 | Mb | 1 | 3 | 2026-05-28 | IPC - 31 | 1 | Sualkuchi | 1126
P23-BP-S01-O | P23-BP-S01-O | 406.a/407.c | MPSB/Sur/3570 | Sur | 2 | 3 | 2026-05-29 | IPC - 31 | 1 | Sualkuchi | 1126
P23-BP-S01-O | P23-BP-S01-O | 406.a/407.c | MPSB/MB/1871 | Mb | 3 | 3 | 2026-05-29 | IPC - 31 | 1 | Sualkuchi | 1126
P23-BP-S02-O | P23-BP-S02-O | 406.a/407.c | MPSB/MB/1875 | Mb | 1 | 3 | 2026-05-29 | IPC - 31 | 1 | Sualkuchi | 1127
P23-BP-S02-O | P23-BP-S02-O | 406.a/407.c | MPSB/Sur/3577 | Sur | 2 | 3 | 2026-05-30 | IPC - 31 | 1 | Sualkuchi | 1127
P23-BP-S02-O | P23-BP-S02-O | 406.a/407.c | MPSB/MB/1877 | Mb | 3 | 3 | 2026-05-30 | IPC - 31 | 1 | Sualkuchi | 1127
P24-BP-S18-M | P24-BP-S18-M | 406.a/407.c | MPSB/MB/1727 | Mb | 1 | 3 | 2026-05-08 | IPC - 31 | 1 | Sualkuchi | 1128
P24-BP-S18-M | P24-BP-S18-M | 406.a/407.c | MPSB/Sur/3446 | Sur | 2 | 3 | 2026-05-09 | IPC - 31 | 1 | Sualkuchi | 1128
P24-BP-S18-M | P24-BP-S18-M | 406.a/407.c | MPSB/MB/1734 | Mb | 3 | 3 | 2026-05-09 | IPC - 31 | 1 | Sualkuchi | 1128
P25-BP-S05a-O | P25-BP-S05a-O | 406.a/407.c | MPSB/MB/1728 | Mb | 1 | 3 | 2026-05-08 | IPC - 31 | 1 | Sualkuchi | 1129
P25-BP-S05a-O | P25-BP-S05a-O | 406.a/407.c | MPSB/Sur/3458 | Sur | 2 | 3 | 2026-05-11 | IPC - 31 | 1 | Sualkuchi | 1129
P25-BP-S05a-O | P25-BP-S05a-O | 406.a/407.c | MPSB/MB/1740 | Mb | 3 | 3 | 2026-05-11 | IPC - 31 | 1 | Sualkuchi | 1129
P25-BP-S06a-O | P25-BP-S06a-O | 406.a/407.c | MPSB/MB/1756 | Mb | 1 | 3 | 2026-05-13 | IPC - 31 | 1 | Sualkuchi | 1130
P25-BP-S06a-O | P25-BP-S06a-O | 406.a/407.c | MPSB/Sur/3482 | Sur | 2 | 3 | 2026-05-15 | IPC - 31 | 1 | Sualkuchi | 1130
P25-BP-S06a-O | P25-BP-S06a-O | 406.a/407.c | MPSB/MB/1773 | Mb | 3 | 3 | 2026-05-15 | IPC - 31 | 1 | Sualkuchi | 1130
P25-BP-S07a-O | P25-BP-S07a-O | 406.a/407.c | MPSB/MB/1782 | Mb | 1 | 3 | 2026-05-16 | IPC - 31 | 1 | Sualkuchi | 1131
P25-BP-S07a-O | P25-BP-S07a-O | 406.a/407.c | MPSB/Sur/3508 | Sur | 2 | 3 | 2026-05-19 | IPC - 31 | 1 | Sualkuchi | 1131
P25-BP-S07a-O | P25-BP-S07a-O | 406.a/407.c | MPSB/MB/1801 | Mb | 3 | 3 | 2026-05-19 | IPC - 31 | 1 | Sualkuchi | 1131
P25-BP-S08a-O | P25-BP-S08a-O | 406.a/407.c | MPSB/MB/1822 | Mb | 1 | 3 | 2026-05-21 | IPC - 31 | 1 | Sualkuchi | 1132
P25-BP-S08a-O | P25-BP-S08a-O | 406.a/407.c | MPSB/Sur/3533 | Sur | 2 | 3 | 2026-05-22 | IPC - 31 | 1 | Sualkuchi | 1132
P25-BP-S08a-O | P25-BP-S08a-O | 406.a/407.c | MPSB/MB/1831 | Mb | 3 | 3 | 2026-05-22 | IPC - 31 | 1 | Sualkuchi | 1132
P9-BP-S01a-O | P9-BP-S01a-O | 406.a/407.c | MPSB/MB/2002 | Mb | 1 | 3 | 2026-06-22 | IPC - 33 | 1 | Palashbari | 1133
P9-BP-S01a-O | P9-BP-S01a-O | 406.a/407.c | MPSB/Sur/3686 | Sur | 2 | 3 | 2026-06-24 | IPC - 33 | 1 | Palashbari | 1133
P9-BP-S01a-O | P9-BP-S01a-O | 406.a/407.c | MPSB/MB/2022 | Mb | 3 | 3 | 2026-06-24 | IPC - 33 | 1 | Palashbari | 1133
P9-BP-S02a-O | P9-BP-S02a-O | 406.a/407.c | MPSB/MB/2035 | Mb | 1 | 3 | 2026-06-26 | IPC - 33 | 1 | Palashbari | 1134
P9-BP-S02a-O | P9-BP-S02a-O | 406.a/407.c | MPSB/Sur/3698 | Sur | 2 | 3 | 2026-06-28 | IPC - 33 | 1 | Palashbari | 1134
P9-BP-S02a-O | P9-BP-S02a-O | 406.a/407.c | MPSB/MB/2046 | Mb | 3 | 3 | 2026-06-28 | IPC - 33 | 1 | Palashbari | 1134
P9-BP-S03a-O | P9-BP-S03a-O | 406.a/407.c | MPSB/MB/2044 | Mb | 1 | 3 | 2026-06-27 | IPC - 33 | 1 | Palashbari | 1135
P9-BP-S03a-O | P9-BP-S03a-O | 406.a/407.c | MPSB/Sur/3707 | Sur | 2 | 3 | 2026-06-30 | IPC - 33 | 1 | Palashbari | 1135
P9-BP-S03a-O | P9-BP-S03a-O | 406.a/407.c | MPSB/MB/2056 | Mb | 3 | 3 | 2026-06-30 | IPC - 33 | 1 | Palashbari | 1135
P9-BP-S34a-O | P9-BP-S34a-O | 406.a/407.c | MPSB/MB/1920 | Mb | 1 | 3 | 2026-06-06 | IPC - 33 | 1 | Palashbari | 1136
P9-BP-S34a-O | P9-BP-S34a-O | 406.a/407.c | MPSB/Sur/3626 | Sur | 2 | 3 | 2026-06-10 | IPC - 33 | 1 | Palashbari | 1136
P9-BP-S34a-O | P9-BP-S34a-O | 406.a/407.c | MPSB/MB/1942 | Mb | 3 | 3 | 2026-06-10 | IPC - 33 | 1 | Palashbari | 1136
P9-KS-S20-O | P9-KS-S20-O | 406.a/407.c | MPSB/Sur/1842 | Sur | 1 | 3 | 2026-05-25 | IPC - 33 | 1 | Palashbari | 1137
P9-KS-S20-O | P9-KS-S20-O | 406.a/407.c | MPSB/Sur/3619 | Sur | 2 | 3 | 2026-06-08 | IPC - 33 | 1 | Palashbari | 1137
P9-KS-S20-O | P9-KS-S20-O | 406.a/407.c | MPSB/MB/1935 | Mb | 3 | 3 | 2026-06-08 | IPC - 33 | 1 | Palashbari | 1137
P9-KS-S21-O | P9-KS-S21-O© | 406.a/407.c/408.c | MPSB/MB/1854 | Mb | 1 | 3 | 2026-05-26 | IPC - 33 | 1 | Palashbari | 1138
P9-KS-S21-O | P9-KS-S21-O© | 406.a/407.c/408.c | MPSB/Sur/3638 | Sur | 2 | 3 | 2026-06-11 | IPC - 33 | 1 | Palashbari | 1138
P9-KS-S21-O | P9-KS-S21-O© | 406.a/407.c/408.c | MPSB/MB/1957 | Mb | 3 | 3 | 2026-06-11 | IPC - 33 | 1 | Palashbari | 1138
P9-KS-S27-O | P9-KS-S27-O© | 406.a/407.c/408.c | MPSB/MB/1908 | Mb | 1 | 3 | 2026-06-04 | IPC - 33 | 1 | Palashbari | 1139
P9-KS-S27-O | P9-KS-S27-O© | 406.a/407.c/408.c | MPSB/Sur/3610 | Sur | 2 | 3 | 2026-06-05 | IPC - 33 | 1 | Palashbari | 1139
P9-KS-S27-O | P9-KS-S27-O© | 406.a/407.c/408.c | MPSB/MB/1910 | Mb | 3 | 3 | 2026-06-05 | IPC - 33 | 1 | Palashbari | 1139
P9-KS-S28-O | P9-KS-S28-O | 406.a/407.c | MPSB/MB/1943 | Mb | 1 | 3 | 2026-06-10 | IPC - 33 | 1 | Palashbari | 1140
P9-KS-S28-O | P9-KS-S28-O | 406.a/407.c | MPSB/Sur/3645 | Sur | 2 | 3 | 2026-06-12 | IPC - 33 | 1 | Palashbari | 1140
P9-KS-S28-O | P9-KS-S28-O | 406.a/407.c | MPSB/MB/1961 | Mb | 3 | 3 | 2026-06-12 | IPC - 33 | 1 | Palashbari | 1140
P9-KS-S29-O | P9-KS-S29-O© | 406.a/407.c/408.c | MPSB/MB/1969 | Mb | 1 | 3 | 2026-06-15 | IPC - 33 | 1 | Palashbari | 1141
P9-KS-S29-O | P9-KS-S29-O© | 406.a/407.c/408.c | MPSB/Sur/3661 | Sur | 2 | 3 | 2026-06-17 | IPC - 33 | 1 | Palashbari | 1141
P9-KS-S29-O | P9-KS-S29-O© | 406.a/407.c/408.c | MPSB/MB/1984 | Mb | 3 | 3 | 2026-06-17 | IPC - 33 | 1 | Palashbari | 1141
P9-KS-S30-O | P9-KS-S30-O | 406.a/407.c | MPSB/MB/1989 | Mb | 1 | 3 | 2026-06-18 | IPC - 33 | 1 | Palashbari | 1142
P9-KS-S30-O | P9-KS-S30-O | 406.a/407.c | MPSB/Sur/3678 | Sur | 2 | 3 | 2026-06-22 | IPC - 33 | 1 | Palashbari | 1142
P9-KS-S30-O | P9-KS-S30-O | 406.a/407.c | MPSB/MB/2004 | Mb | 3 | 3 | 2026-06-22 | IPC - 33 | 1 | Palashbari | 1142
P9-KS-S31-O | P9-KS-S31-O© | 406.a/407.c/408.c | MPSB/MB/2019 | Mb | 1 | 3 | 2026-06-24 | IPC - 33 | 1 | Palashbari | 1143
P9-KS-S31-O | P9-KS-S31-O© | 406.a/407.c/408.c | MPSB/Sur/3702 | Sur | 2 | 3 | 2026-06-29 | IPC - 33 | 1 | Palashbari | 1143
P9-KS-S31-O | P9-KS-S31-O© | 406.a/407.c/408.c | MPSB/MB/2053 | Mb | 3 | 3 | 2026-06-29 | IPC - 33 | 1 | Palashbari | 1143
P16-BP-S13-M | P16-BP-S13-M | 406.a/407.c | MPSB/MB/1967 | Mb | 1 | 3 | 2026-06-14 | IPC - 33 | 1 | Palashbari | 1144
P16-BP-S13-M | P16-BP-S13-M | 406.a/407.c | MPSB/Sur/3657 | Sur | 2 | 3 | 2026-06-16 | IPC - 33 | 1 | Palashbari | 1144
P16-BP-S13-M | P16-BP-S13-M | 406.a/407.c | MPSB/MB/1978 | Mb | 3 | 3 | 2026-06-16 | IPC - 33 | 1 | Palashbari | 1144
P16-BP-S14-M | P16-BP-S14-M© | 406.a/407.c/408.c | MPSB/MB/1998 | Mb | 1 | 3 | 2026-06-19 | IPC - 33 | 1 | Palashbari | 1145
P16-BP-S14-M | P16-BP-S14-M© | 406.a/407.c/408.c | MPSB/Sur/3677 | Sur | 2 | 3 | 2026-06-22 | IPC - 33 | 1 | Palashbari | 1145
P16-BP-S14-M | P16-BP-S14-M© | 406.a/407.c/408.c | MPSB/MB/2003 | Mb | 3 | 3 | 2026-06-22 | IPC - 33 | 1 | Palashbari | 1145
P16-BP-S15-M | P16-BP-S15-M | 406.a/407.c | MPSB/MB/2024 | Mb | 1 | 3 | 2026-06-24 | IPC - 33 | 1 | Palashbari | 1146
P16-BP-S15-M | P16-BP-S15-M | 406.a/407.c | MPSB/Sur/3695 | Sur | 2 | 3 | 2026-06-26 | IPC - 33 | 1 | Palashbari | 1146
P16-BP-S15-M | P16-BP-S15-M | 406.a/407.c | MPSB/MB/2033 | Mb | 3 | 3 | 2026-06-26 | IPC - 33 | 1 | Palashbari | 1146
P16-BP-S16-M | P16-BP-S16-M© | 406.a/407.c/408.c | MPSB/MB/2047 | Mb | 1 | 3 | 2026-06-28 | IPC - 33 | 1 | Palashbari | 1147
P16-BP-S16-M | P16-BP-S16-M© | 406.a/407.c/408.c | MPSB/Sur/3705 | Sur | 2 | 3 | 2026-06-30 | IPC - 33 | 1 | Palashbari | 1147
P16-BP-S16-M | P16-BP-S16-M© | 406.a/407.c/408.c | MPSB/MB/2054 | Mb | 3 | 3 | 2026-06-30 | IPC - 33 | 1 | Palashbari | 1147
P16-KS-S08-M | P16-KS-S08-M© | 406.a/407.c/408.c | MPSB/MB/2034 | Mb | 1 | 3 | 2026-06-26 | IPC - 33 | 1 | Palashbari | 1148
P16-KS-S08-M | P16-KS-S08-M© | 406.a/407.c/408.c | MPSB/Sur/3701 | Sur | 2 | 3 | 2026-06-29 | IPC - 33 | 1 | Palashbari | 1148
P16-KS-S08-M | P16-KS-S08-M© | 406.a/407.c/408.c | MPSB/MB/2052 | Mb | 3 | 3 | 2026-06-29 | IPC - 33 | 1 | Palashbari | 1148
P21-BP-S18a-O | P21-BP-S18a-O | 406.a/407.c | MPSB/MB/1878 | Mb | 1 | 3 | 2026-05-30 | IPC - 33 | 1 | Sualkuchi | 1149
P21-BP-S18a-O | P21-BP-S18a-O | 406.a/407.c | MPSB/Sur/3578 | Sur | 2 | 3 | 2026-05-30 | IPC - 33 | 1 | Sualkuchi | 1149
P21-BP-S18a-O | P21-BP-S18a-O | 406.a/407.c | MPSB/MB/1941 | Mb | 3 | 3 | 2026-06-09 | IPC - 33 | 1 | Sualkuchi | 1149
P21-BP-S19a-O | P21-BP-S19a-O© | 406.a/407.c/408.c | MPSB/MB/1982 | Mb | 1 | 3 | 2026-06-17 | IPC - 33 | 1 | Sualkuchi | 1150
P21-BP-S19a-O | P21-BP-S19a-O© | 406.a/407.c/408.c | MPSB/Sur/3665 | Sur | 2 | 3 | 2026-06-18 | IPC - 33 | 1 | Sualkuchi | 1150
P21-BP-S19a-O | P21-BP-S19a-O© | 406.a/407.c/408.c | MPSB/MB/1986 | Mb | 3 | 3 | 2026-06-18 | IPC - 33 | 1 | Sualkuchi | 1150
P21-BP-S20a-O | P21-BP-S20a-O | 406.a/407.c | MPSB/MB/2051 | Mb | 1 | 3 | 2026-06-29 | IPC - 33 | 1 | Sualkuchi | 1151
P21-BP-S20a-O | P21-BP-S20a-O | 406.a/407.c | MPSB/Sur/3715 | Sur | 2 | 3 | 2026-06-30 | IPC - 33 | 1 | Sualkuchi | 1151
P21-BP-S20a-O | P21-BP-S20a-O | 406.a/407.c | MPSB/MB/2060 | Mb | 3 | 3 | 2026-06-30 | IPC - 33 | 1 | Sualkuchi | 1151
P21-BP-S22a-O | P21-BP-S22a-O | 406.a/407.c | MPSB/MB/1876 | Mb | 1 | 3 | 2026-05-29 | IPC - 33 | 1 | Sualkuchi | 1152
P21-BP-S22a-O | P21-BP-S22a-O | 406.a/407.c | MPSB/Sur/3615 | Sur | 2 | 3 | 2026-06-06 | IPC - 33 | 1 | Sualkuchi | 1152
P21-BP-S22a-O | P21-BP-S22a-O | 406.a/407.c | MPSB/MB/1925 | Mb | 3 | 3 | 2026-06-06 | IPC - 33 | 1 | Sualkuchi | 1152
P21-BP-S23a-O | P21-BP-S23a-O© | 406.a/407.c/408.c | MPSB/MB/1952 | Mb | 1 | 3 | 2026-06-11 | IPC - 33 | 1 | Sualkuchi | 1153
P21-BP-S23a-O | P21-BP-S23a-O© | 406.a/407.c/408.c | MPSB/Sur/3650 | Sur | 2 | 3 | 2026-06-13 | IPC - 33 | 1 | Sualkuchi | 1153
P21-BP-S23a-O | P21-BP-S23a-O© | 406.a/407.c/408.c | MPSB/MB/1964 | Mb | 3 | 3 | 2026-06-13 | IPC - 33 | 1 | Sualkuchi | 1153
P21-BP-S24a-O | P21-BP-S24a-O | 406.a/407.c | MPSB/MB/2001 | Mb | 1 | 3 | 2026-06-21 | IPC - 33 | 1 | Sualkuchi | 1154
P21-BP-S24a-O | P21-BP-S24a-O | 406.a/407.c | MPSB/Sur/3679 | Sur | 2 | 3 | 2026-06-22 | IPC - 33 | 1 | Sualkuchi | 1154
P21-BP-S24a-O | P21-BP-S24a-O | 406.a/407.c | MPSB/MB/2007 | Mb | 3 | 3 | 2026-06-22 | IPC - 33 | 1 | Sualkuchi | 1154
P21-KS-S21-O | P21-KS-S21-O© | 406.a/407.c/408.c | MPSB/MB/1916 | Mb | 1 | 3 | 2026-06-05 | IPC - 33 | 1 | Sualkuchi | 1155
P21-KS-S21-O | P21-KS-S21-O© | 406.a/407.c/408.c | MPSB/Sur/3611 | Sur | 2 | 3 | 2026-06-05 | IPC - 33 | 1 | Sualkuchi | 1155
P21-KS-S21-O | P21-KS-S21-O© | 406.a/407.c/408.c | MPSB/MB/1917 | Mb | 3 | 3 | 2026-06-05 | IPC - 33 | 1 | Sualkuchi | 1155
P21-KS-S26-O | P21-KS-S26-O | 406.a/407.c | MPSB/MB/1919 | Mb | 1 | 3 | 2026-06-05 | IPC - 33 | 1 | Sualkuchi | 1156
P21-KS-S26-O | P21-KS-S26-O | 406.a/407.c | MPSB/Sur/3616 | Sur | 2 | 3 | 2026-06-06 | IPC - 33 | 1 | Sualkuchi | 1156
P21-KS-S26-O | P21-KS-S26-O | 406.a/407.c | MPSB/MB/1926 | Mb | 3 | 3 | 2026-06-06 | IPC - 33 | 1 | Sualkuchi | 1156
P21-KS-S27-O | P21-KS-S27-O© | 406.a/407.c/408.c | MPSB/MB/1933 | Mb | 1 | 3 | 2026-06-08 | IPC - 33 | 1 | Sualkuchi | 1157
P21-KS-S27-O | P21-KS-S27-O© | 406.a/407.c/408.c | MPSB/Sur/3627 | Sur | 2 | 3 | 2026-06-10 | IPC - 33 | 1 | Sualkuchi | 1157
P21-KS-S27-O | P21-KS-S27-O© | 406.a/407.c/408.c | MPSB/MB/1947 | Mb | 3 | 3 | 2026-06-10 | IPC - 33 | 1 | Sualkuchi | 1157
P21-KS-S28-O | P21-KS-S28-O | 406.a/407.c | MPSB/MB/1948 | Mb | 1 | 3 | 2026-06-10 | IPC - 33 | 1 | Sualkuchi | 1158
P21-KS-S28-O | P21-KS-S28-O | 406.a/407.c | MPSB/Sur/3656 | Sur | 2 | 3 | 2026-06-15 | IPC - 33 | 1 | Sualkuchi | 1158
P21-KS-S28-O | P21-KS-S28-O | 406.a/407.c | MPSB/MB/1972 | Mb | 3 | 3 | 2026-06-15 | IPC - 33 | 1 | Sualkuchi | 1158
P21-KS-S29-O | P21-KS-S29-O© | 406.a/407.c/408.c | MPSB/MB/1966 | Mb | 1 | 3 | 2026-06-13 | IPC - 33 | 1 | Sualkuchi | 1159
P21-KS-S29-O | P21-KS-S29-O© | 406.a/407.c/408.c | MPSB/Sur/3659 | Sur | 2 | 3 | 2026-06-17 | IPC - 33 | 1 | Sualkuchi | 1159
P21-KS-S29-O | P21-KS-S29-O© | 406.a/407.c/408.c | MPSB/MB/1983 | Mb | 3 | 3 | 2026-06-17 | IPC - 33 | 1 | Sualkuchi | 1159
P21-KS-S30-O | P21-KS-S30-O | 406.a/407.c | MPSB/MB/1988 | Mb | 1 | 3 | 2026-06-18 | IPC - 33 | 1 | Sualkuchi | 1160
P21-KS-S30-O | P21-KS-S30-O | 406.a/407.c | MPSB/Sur/3688 | Sur | 2 | 3 | 2026-06-24 | IPC - 33 | 1 | Sualkuchi | 1160
P21-KS-S30-O | P21-KS-S30-O | 406.a/407.c | MPSB/MB/2025 | Mb | 3 | 3 | 2026-06-24 | IPC - 33 | 1 | Sualkuchi | 1160
P21-KS-S31-O | P21-KS-S31-O© | 406.a/407.c/408.c | MPSB/MB/2010 | Mb | 1 | 3 | 2026-06-22 | IPC - 33 | 1 | Sualkuchi | 1161
P21-KS-S31-O | P21-KS-S31-O© | 406.a/407.c/408.c | MPSB/MB/2048 | Mb | 2 | 3 | 2026-06-29 | IPC - 33 | 1 | Sualkuchi | 1161
P21-KS-S31-O | P21-KS-S31-O© | 406.a/407.c/408.c | MPSB/MB/2049 | Mb | 3 | 3 | 2026-06-29 | IPC - 33 | 1 | Sualkuchi | 1161
P21-KS-S32-O | P21-KS-S32-O | 406.a/407.c | MPSB/MB/2063 | Mb | 1 | 3 | 2026-06-30 | IPC - 33 | 1 | Sualkuchi | 1162
P21-KS-S32-O | P21-KS-S32-O | 406.a/407.c | MPSB/Sur/3718 | Sur | 2 | 3 | 2026-06-30 | IPC - 33 | 1 | Sualkuchi | 1162
P21-KS-S32-O | P21-KS-S32-O | 406.a/407.c | MPSB/MB/2065 | Mb | 3 | 3 | 2026-06-30 | IPC - 33 | 1 | Sualkuchi | 1162
P22-BP-S01a-E | P22-BP-S01a-E | 406.a/407.c | MPSB/MB/1993 | Mb | 1 | 3 | 2026-06-19 | IPC - 33 | 1 | Sualkuchi | 1163
P22-BP-S01a-E | P22-BP-S01a-E | 406.a/407.c | MPSB/Sur/3669 | Sur | 2 | 3 | 2026-06-19 | IPC - 33 | 1 | Sualkuchi | 1163
P22-BP-S01a-E | P22-BP-S01a-E | 406.a/407.c | MPSB/MB/1994 | Mb | 3 | 3 | 2026-06-19 | IPC - 33 | 1 | Sualkuchi | 1163
P22-BP-S01-E | P22-BP-S01-E | 406.a/407.c | MPSB/MB/2012 | Mb | 1 | 3 | 2026-06-23 | IPC - 33 | 1 | Sualkuchi | 1164
P22-BP-S01-E | P22-BP-S01-E | 406.a/407.c | MPSB/Sur/3683 | Sur | 2 | 3 | 2026-06-23 | IPC - 33 | 1 | Sualkuchi | 1164
P22-BP-S01-E | P22-BP-S01-E | 406.a/407.c | MPSB/MB/2013 | Mb | 3 | 3 | 2026-06-23 | IPC - 33 | 1 | Sualkuchi | 1164
P22-BP-S02-E | P22-BP-S02-E | 406.a/407.c | MPSB/MB/2026 | Mb | 1 | 3 | 2026-06-24 | IPC - 33 | 1 | Sualkuchi | 1165
P22-BP-S02-E | P22-BP-S02-E | 406.a/407.c | MPSB/Sur/3696 | Sur | 2 | 3 | 2026-06-26 | IPC - 33 | 1 | Sualkuchi | 1165
P22-BP-S02-E | P22-BP-S02-E | 406.a/407.c | MPSB/MB/2036 | Mb | 3 | 3 | 2026-06-26 | IPC - 33 | 1 | Sualkuchi | 1165
P22-BP-S03-E | P22-BP-S03-E | 406.a/407.c | MPSB/MB/2041 | Mb | 1 | 3 | 2026-06-27 | IPC - 33 | 1 | Sualkuchi | 1166
P22-BP-S03-E | P22-BP-S03-E | 406.a/407.c | MPSB/Sur/3716 | Sur | 2 | 3 | 2026-06-30 | IPC - 33 | 1 | Sualkuchi | 1166
P22-BP-S03-E | P22-BP-S03-E | 406.a/407.c | MPSB/MB/2061 | Mb | 3 | 3 | 2026-06-30 | IPC - 33 | 1 | Sualkuchi | 1166
P23-BP-S03-O | P23-BP-S03-O | 406.a/407.c | MPSB/Sur/3617 | Sur | 1 | 2 | 2026-06-08 | IPC - 33 | 1 | Sualkuchi | 1167
P23-BP-S03-O | P23-BP-S03-O | 406.a/407.c | MPSB/MB/1930 | Mb | 2 | 2 | 2026-06-08 | IPC - 33 | 1 | Sualkuchi | 1167
P23-BP-S04-O | P23-BP-S04-O | 406.a/407.c | MPSB/MB/1940 | Mb | 1 | 3 | 2026-06-09 | IPC - 33 | 1 | Sualkuchi | 1168
P23-BP-S04-O | P23-BP-S04-O | 406.a/407.c | MPSB/Sur/3636 | Sur | 2 | 3 | 2026-06-11 | IPC - 33 | 1 | Sualkuchi | 1168
P23-BP-S04-O | P23-BP-S04-O | 406.a/407.c | MPSB/MB/1951 | Mb | 3 | 3 | 2026-06-11 | IPC - 33 | 1 | Sualkuchi | 1168
P23-BP-S05-O | P23-BP-S05-O | 406.a/407.c | MPSB/MB/1963 | Mb | 1 | 3 | 2026-06-13 | IPC - 33 | 1 | Sualkuchi | 1169
P23-BP-S05-O | P23-BP-S05-O | 406.a/407.c | MPSB/Sur/3655 | Sur | 2 | 3 | 2026-06-15 | IPC - 33 | 1 | Sualkuchi | 1169
P23-BP-S05-O | P23-BP-S05-O | 406.a/407.c | MPSB/MB/1971 | Mb | 3 | 3 | 2026-06-15 | IPC - 33 | 1 | Sualkuchi | 1169
P23-BP-S06-O | P23-BP-S06-O | 406.a/407.c | MPSB/MB/1981 | Mb | 1 | 3 | 2026-06-17 | IPC - 33 | 1 | Sualkuchi | 1170
P23-BP-S06-O | P23-BP-S06-O | 406.a/407.c | MPSB/Sur/3670 | Sur | 2 | 3 | 2026-06-19 | IPC - 33 | 1 | Sualkuchi | 1170
P23-BP-S06-O | P23-BP-S06-O | 406.a/407.c | MPSB/MB/1996 | Mb | 3 | 3 | 2026-06-19 | IPC - 33 | 1 | Sualkuchi | 1170
P23-BP-S07-O | P23-BP-S07-O | 406.a/407.c | MPSB/MB/2005 | Mb | 1 | 3 | 2026-06-20 | IPC - 33 | 1 | Sualkuchi | 1171
P23-BP-S07-O | P23-BP-S07-O | 406.a/407.c | MPSB/Sur/3684 | Sur | 2 | 3 | 2026-06-23 | IPC - 33 | 1 | Sualkuchi | 1171
P23-BP-S07-O | P23-BP-S07-O | 406.a/407.c | MPSB/MB/2015 | Mb | 3 | 3 | 2026-06-23 | IPC - 33 | 1 | Sualkuchi | 1171
P23-BP-S08-O | P23-BP-S08-O | 406.a/407.c | MPSB/MB/2016 | Mb | 1 | 2 | 2026-06-23 | IPC - 33 | 1 | Sualkuchi | 1172
P23-BP-S08-O | P23-BP-S08-O | 406.a/407.c | MPSB/MB/2037 | Mb | 2 | 2 | 2026-06-26 | IPC - 33 | 1 | Sualkuchi | 1172
P17-BP-S32a-O | P17-BP-S32a-O | 406.a/407.c | MPSB/MB/237 | Mb | 1 | 3 | 2025-10-08 | IPC - 34 | 1 | Palashbari | 1173
P17-BP-S32a-O | P17-BP-S32a-O | 406.a/407.c | MPSB/Sur/1963 | Sur | 2 | 3 | 2025-10-10 | IPC - 34 | 1 | Palashbari | 1173
P17-BP-S32a-O | P17-BP-S32a-O | 406.a/407.c | MPSB/MB/244 | Mb | 3 | 3 | 2025-10-10 | IPC - 34 | 1 | Palashbari | 1173
P9-BP-S04a-O | P9-BP-S04a-O | 406.a/407.c | MPSB/MB/2084 | Mb | 1 | 3 | 2026-07-07 | IPC - 34 | 1 | Palashbari | 1174
P9-BP-S04a-O | P9-BP-S04a-O | 406.a/407.c | MPSB/Sur/3736 | Sur | 2 | 3 | 2026-07-09 | IPC - 34 | 1 | Palashbari | 1174
P9-BP-S04a-O | P9-BP-S04a-O | 406.a/407.c | MPSB/MB/2090 | Mb | 3 | 3 | 2026-07-09 | IPC - 34 | 1 | Palashbari | 1174
P9-BP-S05a-O | P9-BP-S05a-O | 406.a/407.c | MPSB/MB/2099 | Mb | 1 | 3 | 2026-07-10 | IPC - 34 | 1 | Palashbari | 1175
P9-BP-S05a-O | P9-BP-S05a-O | 406.a/407.c | MPSB/Sur/3762 | Sur | 2 | 3 | 2026-07-14 | IPC - 34 | 1 | Palashbari | 1175
P9-BP-S05a-O | P9-BP-S05a-O | 406.a/407.c | MPSB/MB/2133 | Mb | 3 | 3 | 2026-07-14 | IPC - 34 | 1 | Palashbari | 1175
P9-BP-S06a-O | P9-BP-S06a-O | 406.a/407.c | MPSB/MB/2150 | Mb | 1 | 3 | 2026-07-17 | IPC - 34 | 1 | Palashbari | 1176
P9-BP-S06a-O | P9-BP-S06a-O | 406.a/407.c | MPSB/Sur/3779 | Sur | 2 | 3 | 2026-07-20 | IPC - 34 | 1 | Palashbari | 1176
P9-BP-S06a-O | P9-BP-S06a-O | 406.a/407.c | MPSB/MB/2166 | Mb | 3 | 3 | 2026-07-20 | IPC - 34 | 1 | Palashbari | 1176
P9-BP-S07a-O | P9-BP-S07a-O | 406.a/407.c | MPSB/MB/2169 | Mb | 1 | 3 | 2026-07-21 | IPC - 34 | 1 | Palashbari | 1177
P9-BP-S07a-O | P9-BP-S07a-O | 406.a/407.c | MPSB/Sur/3787 | Sur | 2 | 3 | 2026-07-23 | IPC - 34 | 1 | Palashbari | 1177
P9-BP-S07a-O | P9-BP-S07a-O | 406.a/407.c | MPSB/MB/2183 | Mb | 3 | 3 | 2026-07-23 | IPC - 34 | 1 | Palashbari | 1177
P9-BP-S08a-O | P9-BP-S08a-O | 406.a/407.c | MPSB/MB/2201 | Mb | 1 | 3 | 2026-07-25 | IPC - 34 | 1 | Palashbari | 1178
P9-BP-S08a-O | P9-BP-S08a-O | 406.a/407.c | MPSB/Sur/3800 | Sur | 2 | 3 | 2026-07-28 | IPC - 34 | 1 | Palashbari | 1178
P9-BP-S08a-O | P9-BP-S08a-O | 406.a/407.c | MPSB/MB/2218 | Mb | 3 | 3 | 2026-07-28 | IPC - 34 | 1 | Palashbari | 1178
P9-KS-S32-O | P9-KS-S32-O | 406.a/407.c | MPSB/MB/2097 | Mb | 1 | 3 | 2026-07-10 | IPC - 34 | 1 | Palashbari | 1179
P9-KS-S32-O | P9-KS-S32-O | 406.a/407.c | MPSB/Sur/3741 | Sur | 2 | 3 | 2026-07-10 | IPC - 34 | 1 | Palashbari | 1179
P9-KS-S32-O | P9-KS-S32-O | 406.a/407.c | MPSB/MB/2101 | Mb | 3 | 3 | 2026-07-10 | IPC - 34 | 1 | Palashbari | 1179
P9-KS-S33-O | P9-KS-S33-O© | 406.a/407.c/408.c | MPSB/MB/2131 | Mb | 1 | 3 | 2026-07-14 | IPC - 34 | 1 | Palashbari | 1180
P9-KS-S33-O | P9-KS-S33-O© | 406.a/407.c/408.c | MPSB/Sur/3766 | Sur | 2 | 3 | 2026-07-15 | IPC - 34 | 1 | Palashbari | 1180
P9-KS-S33-O | P9-KS-S33-O© | 406.a/407.c/408.c | MPSB/MB/2140 | Mb | 3 | 3 | 2026-07-15 | IPC - 34 | 1 | Palashbari | 1180
P9-KS-S34-O | P9-KS-S34-O | 406.a/407.c | MPSB/MB/2161 | Mb | 1 | 3 | 2026-07-19 | IPC - 34 | 1 | Palashbari | 1181
P9-KS-S34-O | P9-KS-S34-O | 406.a/407.c | MPSB/Sur/3783 | Sur | 2 | 3 | 2026-07-21 | IPC - 34 | 1 | Palashbari | 1181
P9-KS-S34-O | P9-KS-S34-O | 406.a/407.c | MPSB/MB/2171 | Mb | 3 | 3 | 2026-07-21 | IPC - 34 | 1 | Palashbari | 1181
P15-BP-S10-O | P15-BP-S10-O | 406.a/407.c | MPSB/MB/2086 | Mb | 1 | 3 | 2026-07-07 | IPC - 34 | 1 | Palashbari | 1182
P15-BP-S10-O | P15-BP-S10-O | 406.a/407.c | MPSB/Sur/3731 | Sur | 2 | 3 | 2026-07-08 | IPC - 34 | 1 | Palashbari | 1182
P15-BP-S10-O | P15-BP-S10-O | 406.a/407.c | MPSB/MB/2087 | Mb | 3 | 3 | 2026-07-08 | IPC - 34 | 1 | Palashbari | 1182
P15-BP-S11-O | P15-BP-S11-O© | 406.a/407.c/408.c | MPSB/MB/2098 | Mb | 1 | 3 | 2026-07-10 | IPC - 34 | 1 | Palashbari | 1183
P15-BP-S11-O | P15-BP-S11-O© | 406.a/407.c/408.c | MPSB/Sur/3758 | Sur | 2 | 3 | 2026-07-13 | IPC - 34 | 1 | Palashbari | 1183
P15-BP-S11-O | P15-BP-S11-O© | 406.a/407.c/408.c | MPSB/MB/2116 | Mb | 3 | 3 | 2026-07-13 | IPC - 34 | 1 | Palashbari | 1183
P15-BP-S12-O | P15-BP-S12-O | 406.a/407.c | MPSB/MB/2148 | Mb | 1 | 2 | 2026-07-17 | IPC - 34 | 1 | Palashbari | 1184
P15-BP-S12-O | P15-BP-S12-O | 406.a/407.c | MPSB/MB/2156 | Mb | 2 | 2 | 2026-07-18 | IPC - 34 | 1 | Palashbari | 1184
P15-BP-S13-O | P15-BP-S13-O© | 406.a/407.c/408.c | MPSB/MB/2170 | Mb | 1 | 3 | 2026-07-21 | IPC - 34 | 1 | Palashbari | 1185
P15-BP-S13-O | P15-BP-S13-O© | 406.a/407.c/408.c | MPSB/Sur/3789 | Sur | 2 | 3 | 2026-07-23 | IPC - 34 | 1 | Palashbari | 1185
P15-BP-S13-O | P15-BP-S13-O© | 406.a/407.c/408.c | MPSB/MB/2192 | Mb | 3 | 3 | 2026-07-23 | IPC - 34 | 1 | Palashbari | 1185
P15-BP-S14-O | P15-BP-S14-O | 406.a/407.c | MPSB/MB/2181 | Mb | 1 | 3 | 2026-07-23 | IPC - 34 | 1 | Palashbari | 1186
P15-BP-S14-O | P15-BP-S14-O | 406.a/407.c | MPSB/Sur/3797 | Sur | 2 | 3 | 2026-07-27 | IPC - 34 | 1 | Palashbari | 1186
P15-BP-S14-O | P15-BP-S14-O | 406.a/407.c | MPSB/MB/2211 | Mb | 3 | 3 | 2026-07-27 | IPC - 34 | 1 | Palashbari | 1186
P15-BP-S15-O | P15-BP-S15-O© | 406.a/407.c/408.c | MPSB/MB/2224 | Mb | 1 | 3 | 2026-07-29 | IPC - 34 | 1 | Palashbari | 1187
P15-BP-S15-O | P15-BP-S15-O© | 406.a/407.c/408.c | MPSB/Sur/3808 | Sur | 2 | 3 | 2026-07-30 | IPC - 34 | 1 | Palashbari | 1187
P15-BP-S15-O | P15-BP-S15-O© | 406.a/407.c/408.c | MPSB/MB/2232 | Mb | 3 | 3 | 2026-07-30 | IPC - 34 | 1 | Palashbari | 1187
P15-BP-S22-O | P15-BP-S22-O | 406.a/407.c | MPSB/MB/2227 | Mb | 1 | 3 | 2026-07-30 | IPC - 34 | 1 | Palashbari | 1188
P15-BP-S22-O | P15-BP-S22-O | 406.a/407.c | MPSB/Sur/3816 | Sur | 2 | 3 | 2026-07-31 | IPC - 34 | 1 | Palashbari | 1188
P15-BP-S22-O | P15-BP-S22-O | 406.a/407.c | MPSB/MB/2243 | Mb | 3 | 3 | 2026-07-31 | IPC - 34 | 1 | Palashbari | 1188
P15-KS-S09a-O | P15-KS-S09a-O© | 406.a/407.c/408.c | MPSB/MB/2223 | Mb | 1 | 3 | 2026-07-29 | IPC - 34 | 1 | Palashbari | 1189
P15-KS-S09a-O | P15-KS-S09a-O© | 406.a/407.c/408.c | MPSB/Sur/3807 | Sur | 2 | 3 | 2026-07-30 | IPC - 34 | 1 | Palashbari | 1189
P15-KS-S09a-O | P15-KS-S09a-O© | 406.a/407.c/408.c | MPSB/MB/2231 | Mb | 3 | 3 | 2026-07-30 | IPC - 34 | 1 | Palashbari | 1189
P15-KS-S10a-O | P15-KS-S10a-O | 406.a/407.c | MPSB/MB/2230 | Mb | 1 | 3 | 2026-07-30 | IPC - 34 | 1 | Palashbari | 1190
P15-KS-S10a-O | P15-KS-S10a-O | 406.a/407.c | MPSB/Sur/3819 | Sur | 2 | 3 | 2026-07-31 | IPC - 34 | 1 | Palashbari | 1190
P15-KS-S10a-O | P15-KS-S10a-O | 406.a/407.c | MPSB/MB/2246 | Mb | 3 | 3 | 2026-07-31 | IPC - 34 | 1 | Palashbari | 1190
P16-BP-S17-M | P16-BP-S17-M | 406.a/407.c | MPSB/MB/2100 | Mb | 1 | 3 | 2026-07-10 | IPC - 34 | 1 | Palashbari | 1191
P16-BP-S17-M | P16-BP-S17-M | 406.a/407.c | MPSB/Sur/3748 | Sur | 2 | 3 | 2026-07-11 | IPC - 34 | 1 | Palashbari | 1191
P16-BP-S17-M | P16-BP-S17-M | 406.a/407.c | MPSB/MB/2109 | Mb | 3 | 3 | 2026-07-11 | IPC - 34 | 1 | Palashbari | 1191
P16-BP-S18-M | P16-BP-S18-M | 406.a/407.c | MPSB/MB/2147 | Mb | 1 | 3 | 2026-07-17 | IPC - 34 | 1 | Palashbari | 1192
P16-BP-S18-M | P16-BP-S18-M | 406.a/407.c | MPSB/Sur/3773 | Sur | 2 | 3 | 2026-07-17 | IPC - 34 | 1 | Palashbari | 1192
P16-BP-S18-M | P16-BP-S18-M | 406.a/407.c | MPSB/MB/2149 | Mb | 3 | 3 | 2026-07-17 | IPC - 34 | 1 | Palashbari | 1192
P16-KS-S09-M | P16-KS-S09-M | 406.a/407.c | MPSB/MB/2085 | Mb | 1 | 3 | 2026-07-07 | IPC - 34 | 1 | Palashbari | 1193
P16-KS-S09-M | P16-KS-S09-M | 406.a/407.c | MPSB/Sur/3735 | Sur | 2 | 3 | 2026-07-09 | IPC - 34 | 1 | Palashbari | 1193
P16-KS-S09-M | P16-KS-S09-M | 406.a/407.c | MPSB/MB/2089 | Mb | 3 | 3 | 2026-07-09 | IPC - 34 | 1 | Palashbari | 1193
P16-KS-S10-M | P16-KS-S10-M© | 406.a/407.c/408.c | MPSB/MB/2132 | Mb | 1 | 3 | 2026-07-14 | IPC - 34 | 1 | Palashbari | 1194
P16-KS-S10-M | P16-KS-S10-M© | 406.a/407.c/408.c | MPSB/Sur/3765 | Sur | 2 | 3 | 2026-07-15 | IPC - 34 | 1 | Palashbari | 1194
P16-KS-S10-M | P16-KS-S10-M© | 406.a/407.c/408.c | MPSB/MB/2139 | Mb | 3 | 3 | 2026-07-15 | IPC - 34 | 1 | Palashbari | 1194
P16-KS-S11-M | P16-KS-S11-M | 406.a/407.c | MPSB/MB/2163 | Mb | 1 | 3 | 2026-07-19 | IPC - 34 | 1 | Palashbari | 1195
P16-KS-S11-M | P16-KS-S11-M | 406.a/407.c | MPSB/Sur/3780 | Sur | 2 | 3 | 2026-07-20 | IPC - 34 | 1 | Palashbari | 1195
P16-KS-S11-M | P16-KS-S11-M | 406.a/407.c | MPSB/MB/2167 | Mb | 3 | 3 | 2026-07-20 | IPC - 34 | 1 | Palashbari | 1195
P16-KS-S12-M | P16-KS-S12-M© | 406.a/407.c/408.c | MPSB/MB/2168 | Mb | 1 | 3 | 2026-07-21 | IPC - 34 | 1 | Palashbari | 1196
P16-KS-S12-M | P16-KS-S12-M© | 406.a/407.c/408.c | MPSB/Sur/3786 | Sur | 2 | 3 | 2026-07-23 | IPC - 34 | 1 | Palashbari | 1196
P16-KS-S12-M | P16-KS-S12-M© | 406.a/407.c/408.c | MPSB/MB/2182 | Mb | 3 | 3 | 2026-07-23 | IPC - 34 | 1 | Palashbari | 1196
P16-KS-S13-M | P16-KS-S13-M | 406.a/407.c | MPSB/MB/2180 | Mb | 1 | 3 | 2026-07-23 | IPC - 34 | 1 | Palashbari | 1197
P16-KS-S13-M | P16-KS-S13-M | 406.a/407.c | MPSB/Sur/3796 | Sur | 2 | 3 | 2026-07-27 | IPC - 34 | 1 | Palashbari | 1197
P16-KS-S13-M | P16-KS-S13-M | 406.a/407.c | MPSB/MB/2210 | Mb | 3 | 3 | 2026-07-27 | IPC - 34 | 1 | Palashbari | 1197
P16-KS-S14-M | P16-KS-S14-M© | 406.a/407.c/408.c | MPSB/MB/2228 | Mb | 1 | 3 | 2026-07-30 | IPC - 34 | 1 | Palashbari | 1198
P16-KS-S14-M | P16-KS-S14-M© | 406.a/407.c/408.c | MPSB/Sur/3817 | Sur | 2 | 3 | 2026-07-31 | IPC - 34 | 1 | Palashbari | 1198
P16-KS-S14-M | P16-KS-S14-M© | 406.a/407.c/408.c | MPSB/MB/2244 | Mb | 3 | 3 | 2026-07-31 | IPC - 34 | 1 | Palashbari | 1198
P19-KS-S09a-O | P19-KS-S09a-O© | 406.a/407.c/408.c | MPSB/MB/2234 | Mb | 1 | 3 | 2026-07-30 | IPC - 34 | 1 | Sualkuchi | 1199
P19-KS-S09a-O | P19-KS-S09a-O© | 406.a/407.c/408.c | MPSB/Sur/3812 | Sur | 2 | 3 | 2026-07-31 | IPC - 34 | 1 | Sualkuchi | 1199
P19-KS-S09a-O | P19-KS-S09a-O© | 406.a/407.c/408.c | MPSB/MB/2238 | Mb | 3 | 3 | 2026-07-31 | IPC - 34 | 1 | Sualkuchi | 1199
P21-BP-S21a-O | P21-BP-S21a-O© | 406.a/407.c/408.c | MPSB/MB/2114 | Mb | 1 | 3 | 2026-07-11 | IPC - 34 | 1 | Sualkuchi | 1200
P21-BP-S21a-O | P21-BP-S21a-O© | 406.a/407.c/408.c | MPSB/Sur/3763 | Sur | 2 | 3 | 2026-07-15 | IPC - 34 | 1 | Sualkuchi | 1200
P21-BP-S21a-O | P21-BP-S21a-O© | 406.a/407.c/408.c | MPSB/MB/2137 | Mb | 3 | 3 | 2026-07-15 | IPC - 34 | 1 | Sualkuchi | 1200
P21-BP-S25a-O | P21-BP-S25a-O© | 406.a/407.c/408.c | MPSB/Sur/3749 | Sur | 1 | 2 | 2026-07-11 | IPC - 34 | 1 | Sualkuchi | 1201
P21-BP-S25a-O | P21-BP-S25a-O© | 406.a/407.c/408.c | MPSB/MB/2113 | Mb | 2 | 2 | 2026-07-11 | IPC - 34 | 1 | Sualkuchi | 1201
P21-BP-S26a-O | P21-BP-S26a-O | 406.a/407.c | MPSB/MB/2135 | Mb | 1 | 3 | 2026-07-15 | IPC - 34 | 1 | Sualkuchi | 1202
P21-BP-S26a-O | P21-BP-S26a-O | 406.a/407.c | MPSB/Sur/3777 | Sur | 2 | 3 | 2026-07-18 | IPC - 34 | 1 | Sualkuchi | 1202
P21-BP-S26a-O | P21-BP-S26a-O | 406.a/407.c | MPSB/MB/2159 | Mb | 3 | 3 | 2026-07-18 | IPC - 34 | 1 | Sualkuchi | 1202
P21-BP-S27a-O | P21-BP-S27a-O© | 406.a/407.c/408.c | MPSB/MB/2165 | Mb | 1 | 3 | 2026-07-19 | IPC - 34 | 1 | Sualkuchi | 1203
P21-BP-S27a-O | P21-BP-S27a-O© | 406.a/407.c/408.c | MPSB/Sur/3785 | Sur | 2 | 3 | 2026-07-22 | IPC - 34 | 1 | Sualkuchi | 1203
P21-BP-S27a-O | P21-BP-S27a-O© | 406.a/407.c/408.c | MPSB/MB/2179 | Mb | 3 | 3 | 2026-07-22 | IPC - 34 | 1 | Sualkuchi | 1203
P21-BP-S28a-O | P21-BP-S28a-O | 406.a/407.c | MPSB/MB/2189 | Mb | 1 | 3 | 2026-07-23 | IPC - 34 | 1 | Sualkuchi | 1204
P21-BP-S28a-O | P21-BP-S28a-O | 406.a/407.c | MPSB/Sur/3791 | Sur | 2 | 3 | 2026-07-25 | IPC - 34 | 1 | Sualkuchi | 1204
P21-BP-S28a-O | P21-BP-S28a-O | 406.a/407.c | MPSB/MB/2196 | Mb | 3 | 3 | 2026-07-25 | IPC - 34 | 1 | Sualkuchi | 1204
P21-BP-S29a-O | P21-BP-S29a-O© | 406.a/407.c/408.c | MPSB/MB/2199 | Mb | 1 | 3 | 2026-07-25 | IPC - 34 | 1 | Sualkuchi | 1205
P21-BP-S29a-O | P21-BP-S29a-O© | 406.a/407.c/408.c | MPSB/Sur/3799 | Sur | 2 | 3 | 2026-07-28 | IPC - 34 | 1 | Sualkuchi | 1205
P21-BP-S29a-O | P21-BP-S29a-O© | 406.a/407.c/408.c | MPSB/MB/2214 | Mb | 3 | 3 | 2026-07-28 | IPC - 34 | 1 | Sualkuchi | 1205
P21-BP-S30a-O | P21-BP-S30a-O | 406.a/407.c | MPSB/MB/2217 | Mb | 1 | 3 | 2026-07-28 | IPC - 34 | 1 | Sualkuchi | 1206
P21-BP-S30a-O | P21-BP-S30a-O | 406.a/407.c | MPSB/Sur/3809 | Sur | 2 | 3 | 2026-07-30 | IPC - 34 | 1 | Sualkuchi | 1206
P21-BP-S30a-O | P21-BP-S30a-O | 406.a/407.c | MPSB/MB/2235 | Mb | 3 | 3 | 2026-07-30 | IPC - 34 | 1 | Sualkuchi | 1206
P21-BP-S31a-O | P21-BP-S31a-O© | 406.a/407.c/408.c | MPSB/MB/2236 | Mb | 1 | 3 | 2026-07-30 | IPC - 34 | 1 | Sualkuchi | 1207
P21-BP-S31a-O | P21-BP-S31a-O© | 406.a/407.c/408.c | MPSB/Sur/3813 | Sur | 2 | 3 | 2026-07-31 | IPC - 34 | 1 | Sualkuchi | 1207
P21-BP-S31a-O | P21-BP-S31a-O© | 406.a/407.c/408.c | MPSB/MB/2239 | Mb | 3 | 3 | 2026-07-31 | IPC - 34 | 1 | Sualkuchi | 1207
P21-KS-S33-O | P21-KS-S33-O© | 406.a/407.c/408.c | MPSB/MB/2095 | Mb | 1 | 3 | 2026-07-09 | IPC - 34 | 1 | Sualkuchi | 1208
P21-KS-S33-O | P21-KS-S33-O© | 406.a/407.c/408.c | MPSB/Sur/3745 | Sur | 2 | 3 | 2026-07-10 | IPC - 34 | 1 | Sualkuchi | 1208
P21-KS-S33-O | P21-KS-S33-O© | 406.a/407.c/408.c | MPSB/MB/2107 | Mb | 3 | 3 | 2026-07-10 | IPC - 34 | 1 | Sualkuchi | 1208
P21-KS-S34-O | P21-KS-S34-O | 406.a/407.c | MPSB/MB/2120 | Mb | 1 | 3 | 2026-07-13 | IPC - 34 | 1 | Sualkuchi | 1209
P21-KS-S34-O | P21-KS-S34-O | 406.a/407.c | MPSB/Sur/3764 | Sur | 2 | 3 | 2026-07-15 | IPC - 34 | 1 | Sualkuchi | 1209
P21-KS-S34-O | P21-KS-S34-O | 406.a/407.c | MPSB/MB/2138 | Mb | 3 | 3 | 2026-07-15 | IPC - 34 | 1 | Sualkuchi | 1209
P22-BP-S04-E | P22-BP-S04-E | 406.a/407.c | MPSB/MB/2081 | Mb | 1 | 3 | 2026-07-07 | IPC - 34 | 1 | Sualkuchi | 1210
P22-BP-S04-E | P22-BP-S04-E | 406.a/407.c | MPSB/Sur/3759 | Sur | 2 | 3 | 2026-07-13 | IPC - 34 | 1 | Sualkuchi | 1210
P22-BP-S04-E | P22-BP-S04-E | 406.a/407.c | MPSB/MB/2118 | Mb | 3 | 3 | 2026-07-13 | IPC - 34 | 1 | Sualkuchi | 1210
P22-BP-S05-E | P22-BP-S05-E | 406.a/407.c | MPSB/MB/2136 | Mb | 1 | 3 | 2026-07-15 | IPC - 34 | 1 | Sualkuchi | 1211
P22-BP-S05-E | P22-BP-S05-E | 406.a/407.c | MPSB/Sur/3775 | Sur | 2 | 3 | 2026-07-17 | IPC - 34 | 1 | Sualkuchi | 1211
P22-BP-S05-E | P22-BP-S05-E | 406.a/407.c | MPSB/MB/2154 | Mb | 3 | 3 | 2026-07-17 | IPC - 34 | 1 | Sualkuchi | 1211
P22-BP-S06-E | P22-BP-S06-E | 406.a/407.c | MPSB/MB/2153 | Mb | 1 | 3 | 2026-07-17 | IPC - 34 | 1 | Sualkuchi | 1212
P22-BP-S06-E | P22-BP-S06-E | 406.a/407.c | MPSB/Sur/3784 | Sur | 2 | 3 | 2026-07-22 | IPC - 34 | 1 | Sualkuchi | 1212
P22-BP-S06-E | P22-BP-S06-E | 406.a/407.c | MPSB/MB/2178 | Mb | 3 | 3 | 2026-07-22 | IPC - 34 | 1 | Sualkuchi | 1212
P24-KS-S01-M | P24-KS-S01-M | 406.a/407.c | MPSB/MB/2127 | Mb | 1 | 3 | 2026-07-14 | IPC - 34 | 1 | Sualkuchi | 1213
P24-KS-S01-M | P24-KS-S01-M | 406.a/407.c | MPSB/Sur/3771 | Sur | 2 | 3 | 2026-07-16 | IPC - 34 | 1 | Sualkuchi | 1213
P24-KS-S01-M | P24-KS-S01-M | 406.a/407.c | MPSB/MB/2144 | Mb | 3 | 3 | 2026-07-16 | IPC - 34 | 1 | Sualkuchi | 1213
P24-KS-S02-M | P24-KS-S02-M | 406.a/407.c | MPSB/MB/2164 | Mb | 1 | 3 | 2026-07-19 | IPC - 34 | 1 | Sualkuchi | 1214
P24-KS-S02-M | P24-KS-S02-M | 406.a/407.c | MPSB/Sur/3790 | Sur | 2 | 3 | 2026-07-24 | IPC - 34 | 1 | Sualkuchi | 1214
P24-KS-S02-M | P24-KS-S02-M | 406.a/407.c | MPSB/MB/2195 | Mb | 3 | 3 | 2026-07-24 | IPC - 34 | 1 | Sualkuchi | 1214
P24-KS-S03-M | P24-KS-S03-M | 406.a/407.c | MPSB/MB/2216 | Mb | 1 | 3 | 2026-07-28 | IPC - 34 | 1 | Sualkuchi | 1215
P24-KS-S03-M | P24-KS-S03-M | 406.a/407.c | MPSB/Sur/3802 | Sur | 2 | 3 | 2026-07-29 | IPC - 34 | 1 | Sualkuchi | 1215
P24-KS-S03-M | P24-KS-S03-M | 406.a/407.c | MPSB/MB/2225 | Mb | 3 | 3 | 2026-07-29 | IPC - 34 | 1 | Sualkuchi | 1215
P24-KS-S04-M | P24-KS-S04-M | 406.a/407.c | MPSB/MB/2237 | Mb | 1 | 3 | 2026-07-30 | IPC - 34 | 1 | Sualkuchi | 1216
P24-KS-S04-M | P24-KS-S04-M | 406.a/407.c | MPSB/Sur/3815 | Sur | 2 | 3 | 2026-07-31 | IPC - 34 | 1 | Sualkuchi | 1216
P24-KS-S04-M | P24-KS-S04-M | 406.a/407.c | MPSB/MB/2241 | Mb | 3 | 3 | 2026-07-31 | IPC - 34 | 1 | Sualkuchi | 1216
|  | 408.a | As per Annexures | Letter/Other | 1 | 1 |  | IPC - 29 | 450.478 |  | 1233
|  | 408.a | As per Annexures | Letter/Other | 1 | 1 |  | IPC - 31 | 354.343 |  | 1234
|  | 408.b | MPSB/L&T/TIIC/2026/1543 | Letter/Other | 1 | 1 | 2026-03-31 | IPC - 30 | 450.478 |  | 1240
|  | 408.b | As per Annexures | Letter/Other | 1 | 1 |  | IPC - 34 | 354.343 |  | 1241

## Status_Legend
Status | Viewer colour (hex) | Comes from | Swatch
Not started | #D9DDE3 | In scope, no RFI yet — show as ghost / transparent
Cutting edge fabricated | #F4E3B5 | 401.a
Cutting edge placed | #F2D48A | 401.b
Shutter & scaffold done | #EFC45E | 401.c — ready to cast curb
Cast & sunk | #2E9E6B | 402.a — lift cast AND sunk (billing needs both)
Plugged | #1F7A52 | 402.b
Cast | #2E9E6B | 402.c / 403.a / 404.a / 405.a
Cast in yard | #E8A33D | 406.a (+407.c, +408.c if ©) — exists, but in the CASTING YARD, not on the bridge
Erected | #3B7DD8 | 406.b — placed on the cantilever
Stressed | #2F5FB3 | 407.d
Grouted | #254A8C | 407.e
Stay stressed | #7B5CC4 | 408.d (© segments only)
Deck complete | #2E9E6B | 409.a
Stay final | #5B3FA6 | 409.b (© segments only)
Continuity PT done | #1F7A52 | 409.c
Reversed (toppled) | #C9463D | Billed then reversed (P12 / P14 toppled wells) — hide or show red
BOQ items for a segment, in order: 406.a cast (75% of 406) → 406.b erected (25%) → 407.d stressed → 407.e grouted → 409.a deck complete → 409.c continuity PT; © segments also 408.c at casting, 408.d / 409.b for the stay.